## 0018
Site list BoQ DRM INFRASTRUKTUR B2S JABOTABEK 16 site
No. | Batch | KKST No. | Regional | KOM Date | DRM Date | Plan Site (KOM based) | [5 empty] | Final Site (DRM based) |  |  |  |  | TP Site DRM |  |  |  | Address | Band EQP | SoW EQP | Reason | Type Site | Type Tower | Tinggi Tower | Antenna RF Direction | Antenna RF Height | Ant RF Type | Quantity RF | Dimensi RF | RRU Height | RRU type | Quantity RRU | Dimensi RRU | Antenna MW Height | Ant MW Type | Antenna MW Diameter | Quantity MW | MW Azimuth | FAR END |  |  | Power Supply | RFI Date Target | TSSR | Change SAR | Remarks | Cand# | Hasil DRM (Continue/ Cancel)
[6 empty] | Site ID | Site Name | SoW | Long | Lat | Coordinate review | Site ID | Site Name | SoW | Long | Lat | Site ID | Site Name | Long | Lat | [21 empty] | Site ID | Site Name | MW Azimuth
1 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR035 | TANGKOLOCIRACAP | B2S | 106.5178 | -7.3455 |  | PLR035 | TANGKOLOCIRACAP | B2S | 106.519 | -7.344 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 40/220/310 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | Cand Q, OK | Continue
2 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR016 | TANJUNGSARI | B2S | 106.9693 | -7.2194 |  | PLR016 | TANJUNGSARI | B2S | 106.9694 | -7.2189 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 5/120/240 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
3 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR049 | PARUNGCIAMBAR | B2S | 106.7545 | -6.863 |  | PLR049 | PARUNGCIAMBAR | B2S | 106.7546 | -6.863 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 105/245/325 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
4 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR026 | GIRIJAYADAMARRAJA | B2S | 106.7234 | -6.9535 |  | PLR026 | GIRIJAYADAMARRAJA | B2S | 106.7231 | -6.9532 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 60/190/305 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
5 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR023 | GUNUNGWALATHEGARMANAH | B2S | 106.8017 | -6.9346 |  | PLR023 | GUNUNGWALATHEGARMANAH | B2S | 106.8019 | -6.9345 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 40/170/260 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 41 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
6 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR036 | CIRACAPUJUNGGENTENG | B2S | 106.4339 | -7.3309 |  | PLR036 | CIRACAPUJUNGGENTENG | B2S | 106.4334 | -7.3311 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 110/210/300 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
7 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR015 | BUNIWANGIGEGERBITUNG | B2S | 107.0147 | -6.9567 |  | PLR015 | BUNIWANGIGEGERBITUNG | B2S | 107.0148 | -6.9566 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 75/150/295 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
8 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR038 | PUNCAKBULUH | B2S | 106.6446 | -7.2254 |  | PLR038 | PUNCAKBULUH | B2S | 106.6444 | -7.2254 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 20/120/190 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
9 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR029 | LENGKONG | B2S | 106.686 | -7.1168 |  | PLR029 | LENGKONG | B2S | 106.6855 | -7.1169 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 140/200/355 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND Q, OK | Continue
10 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | TGR571 | RANCAKALAPAPANONGAN | B2S | 106.5144 | -6.29 |  | TGR571 | RANCAKALAPAPANONGAN | B2S | 106.5138 | -6.2888 | [5 empty] | GL1800 | NEW LTE | Wide Coverage | MACRO | SST | 52 | 90/150/330 | 51 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 51 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
11 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | TGR579 | TANAHMERAHSEPATANTIMUR | B2S | 106.5942 | -6.1116 |  | TGR579 | TANAHMERAHSEPATANTIMUR | B2S | 106.5942 | -6.1118 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 42 | 120/200/350 | 41 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 41 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
12 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | TGR574 | SINDANGSONO | B2S | 106.4878 | -6.1773 |  | TGR574 | SINDANGSONO | B2S | 106.4874 | -6.1775 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 52 | 50/170/280 | 51 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 51 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
13 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR025 | GIRIJAYA | B2S | 106.7318 | -6.9325 |  | PLR025 | GIRIJAYA | B2S | 106.7325 | -6.9341 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 130/200/280 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
14 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR028 | SMAN1LENGKONGSUKABUMI | B2S | 106.7087 | -7.1351 |  | PLR028 | SMAN1LENGKONGSUKABUMI | B2S | 106.7075 | -7.1334 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 40/110/260 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND U, OK | Continue
15 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | CBN656 | JALANRAYAJONGGOLCARIU | B2S | 107.0724 | -6.4785 |  | CBN656 | JALANRAYAJONGGOLCARIU | B2S | 107.0724 | -6.4791 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 52 | 80/140/350 | 51 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 51 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
16 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | CBN647 | CILAMEPABAMBONG | B2S | 106.5875 | -6.6299 |  | CBN647 | CILAMEPABAMBONG | B2S | 106.5872 | -6.6299 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 | 40/140/300 | 61 | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
|  | Telkomsel |  |  |  |  | Tower Bersama Group
|  | Rudi Susanto |  |  |  |  | Atan M Balfas |  |  | Ihsan Pandu Wijaya
|  | Mgr. RANE Outer Jabotabek |  |  |  |  | Lead AM |  |  | PM Sacme Jabo
Formulas:
RFI Date Target = [KOM Date]+120