## 0018
Site list BoQ DRM INFRASTRUKTUR B2S JABOTABEK 16 site
No. | Batch | KKST No. | Regional | KOM Date | DRM Date | Plan Site (KOM based) | [5 empty] | Final Site (DRM based) |  |  |  |  | TP Site DRM |  |  |  | Address | Band EQP | SoW EQP | Reason | Type Site | Type Tower | Tinggi Tower | Antenna RF Direction | Antenna RF Height | Ant RF Type | Quantity RF | Dimensi RF | RRU Height | RRU type | Quantity RRU | Dimensi RRU | Antenna MW Height | Ant MW Type | Antenna MW Diameter | Quantity MW | MW Azimuth | FAR END |  |  | Power Supply | RFI Date Target | TSSR | Change SAR | Remarks | Cand# | Hasil DRM (Continue/ Cancel)
[6 empty] | Site ID | Site Name | SoW | Long | Lat | Coordinate review | Site ID | Site Name | SoW | Long | Lat | Site ID | Site Name | Long | Lat | [21 empty] | Site ID | Site Name | MW Azimuth
1 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-20 | RKB086 | JATIMULYARANGKASBITUNG | B2S | 106.2689 | -6.3541 |  | RKB086 | JATIMULYARANGKASBITUNG | B2S | 106.2691 | -6.3557 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 42 |  |  | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 41 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | Cand Q, OK | Continue
2 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-13 | RKB092 | CIAKARGUNUNGKENCANA | B2S | 106.0856 | -6.6057 |  | RKB092 | CIAKARGUNUNGKENCANA | B2S | 106.0851 | -6.6062 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 |  |  | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
3 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-28 | SKB914 | JMBATANMERAHSKB | B2S | 106.9343 | -6.9574 |  | SKB914 | JMBATANMERAHSKB | B2S | 106.9339 | -6.95621, | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 42 |  |  | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 41 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND T, OK | Continue
4 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-20 | CKR388 | VILLA SETU WANGI | B2S | 107.0464 | -6.3445 |  | CKR388 | VILLA SETU WANGI | B2S | 107.047 | -6.3444 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 42 |  |  | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 41 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
5 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-20 | CBN646 | SMAN1TENJOBOGOR | B2S | 106.4638 | -6.348 |  | CBN646 | SMAN1TENJOBOGOR | B2S | 106.4651 | -6.35 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 |  |  | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND R, OK | Continue
6 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | PLR047 | PERMANENBUKITALGORITMA | B2S | 106.7035 | -6.9076 |  | PLR047 | PERMANENBUKITALGORITMA | B2S | 106.7044 | -6.9082 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 |  |  | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND Q, OK | Continue
7 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | CBN658 | PERMANENCIARUTENILIRCIBUNGBULANG | B2S | 106.6696 | -6.5374 |  | CBN658 | PERMANENCIARUTENILIRCIBUNGBULANG | B2S | 106.6728 | -6.537 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 |  |  | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND Q, OK | Continue
8 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-20 | CKR383 | HARVESTCITYCLUSTERBARAT | B2S | 107.0208 | -6.3801 |  | CKR383 | HARVESTCITYCLUSTERBARAT | B2S | 107.0207 | -6.3799 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 42 |  |  | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 41 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND P, OK | Continue
9 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | RKB084 | SUKAMANAHRANGKASBITUNG | B2S | 106.2781 | -6.3232 |  | RKB084 | SUKAMANAHRANGKASBITUNG | B2S | 106.279 | -6.3251 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 62 |  |  | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND Q, OK | Continue
9 | Batch 2 | 0001/KOM/TBG/OPEX RAN New Infra Batch2 2022/X/2022 | JABOTABEK | 2022-10-04 | 2022-10-07 | SKB913 | PERMANENSINDANGSARILEMBURSITU | B2S | 106.9142 | -6.9615 |  | SKB913 | PERMANENSINDANGSARILEMBURSITU | B2S | 106.9141 | -6.9616 | [5 empty] | GL1800 | NEW LTE | Winning Java | MACRO | SST | 42 |  |  | ASI4518R42v06 | 3 | 2099 x 449 x 196 | 61 | RRU5513 | 3 | 400 x 300 x 100 | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | FO TELKOM | 10.6 KVA | 2023-02-01 |  |  |  | CAND S, OK | Continue
|  | Telkomsel |  |  |  |  | Tower Bersama Group
Validasi 1.0 (10/7/2022)
|  | Rudi Susanto |  |  |  |  | Atan M Balfas |  |  | Ihsan Pandu Wijaya |  |  | Validasi 2.0 20/10/2022
|  | Mgr. RANE Outer Jabotabek |  |  |  |  | Lead AM |  |  | PM Sacme Jabo |  |  | Validasi 3.0(21/10/2022)
Formulas:
RFI Date Target = [KOM Date]+120