## Sheet1
AREA | REGION | SITE_ID | SITE_NAME | LONG | LAT | INFRA_TYPE | ANTENA HEIGHT | Tower Height Adjustment | Residence | Regulasi | Lahan | Private / Corporate | Power | History Commcase | Twr terdekat TBIG ( jika ada berapa mtr ? ) | Rekomendasi ( OK / Ok With Note / NOK with Note ) | Remarks | Final Assesment | Quota | Propose Mitra | Final Remark | TSSR Status
AREA 2 | R03 Jabotabek | PLR035 | TANGKOLOCIRACAP | 106.5178 | -7.3455 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Available |  | NO | YES | Lahan Berkontur | Rank 1 | In Quota | Tritama | TBG | Done
AREA 2 | R03 Jabotabek | PLR016 | TANJUNGSARI | 106.9693 | -7.2194 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Available |  | NO | YES | Lahan Berkontur, check klasifikasi lahan (Lahan darat atau lahan sawah) | Rank 1 | In Quota | BNP | TBG | Done
AREA 2 | R03 Jabotabek | PLR028 | SMAN1LENGKONGSUKABUMI | 106.7087 | -7.1351 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Available |  | NO | YES | Lahan Berkontur | Rank 1 | In Quota | Orlie | TBG | Done
AREA 2 | R03 Jabotabek | PLR049 | PARUNGCIAMBAR | 106.7545 | -6.863 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Available |  | NO | YES | Lahan Berkontur | Rank 1 | In Quota | Orlie | TBG | Done
AREA 2 | R03 Jabotabek | PLR026 | GIRIJAYADAMARRAJA | 106.7234 | -6.9535 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Available |  | NO | YES | Lahan Berkontur, bersebelahan dengan batas lahan milik PTPN (Perkebunan) | Rank 1 | In Quota | Datatel | TBG | Done
AREA 2 | R03 Jabotabek | CKR383 | HARVESTCITYCLUSTERBARAT | 107.0208 | -6.3801 | B2S | 41 | 42 | BEKASI | CELLPLAN Kab Bekas (OUTCELL) | GF | Private | Available |  | NO | YES WITH NOTE | Propose MCP 20m karena aturan regulasi cellplan Kab Bekasi. Titik NOM pernah masuk ke STIP 8 PKP bulan Mei 2022. Namun tidak ada kelanjutan dari PKP. Sudah pernah di survey oleh inhouse TBG namun belum di follow up kembali dengan LL | Rank 2 | NO | Aulia | TBG | OG Survey
AREA 2 | R03 Jabotabek | CKR388 | VILLA SETU WANGI | 107.0464 | -6.3445 | B2S | 41 | 42 | BEKASI | CELLPLAN Kab Bekas (OUTCELL) | GF | Private | Available |  | NO | YES WITH NOTE | Propose MCP 20m karena aturan regulasi cellplan Kab Bekasi. Titik NOM Wilayah Kampung warga namun dikelilingi cluster perumahan | Rank 2 | NO | Aulia | TBG | OG Survey
AREA 2 | R03 Jabotabek | CBN658 | PERMANENCIARUTENILIRCIBUNGBULANG | 106.6696 | -6.5374 | B2S | 61 | 62 | BOGOR | Check Zonasi dan RTRW Kab Bogor | GF | Private | Available |  | NO | YES | Tanah berkontur. Banyak lahan kosong dan sawah. Dekat dengan Sungai | Rank 1 | In Quota | BNP | TBG | Done
AREA 2 | R03 Jabotabek | CBN656 | JALANRAYAJONGGOLCARIU | 107.0724 | -6.4785 | B2S | 51 | 52 | BOGOR | Check Zonasi dan RTRW Kab Bogor | GF | Private | Available |  | NO | YES | Tanah berkontur. Banyak lahan kosong dan sawah. Dekat dengan Sungai | Rank 1 | In Quota | BNP | TBG
AREA 2 | R03 Jabotabek | CBN647 | CILAMEPABAMBONG | 106.5875 | -6.6299 | B2S | 61 | 62 | BOGOR | Check Zonasi dan RTRW Kab Bogor | GF | Private | Available |  | NO | YES | Tanah berkontur. Banyak lahan kosong dan sawah. Dekat dengan Sungai | Rank 1 | In Quota | BNP | TBG
AREA 2 | R03 Jabotabek | CBN646 | SMAN1TENJOBOGOR | 106.4638 | -6.348 | B2S | 61 | 62 | BOGOR | Check Zonasi dan RTRW Kab Bogor | GF | Corporate | Available |  | NO | YES | Titik NOM berada di sekolahan. Radius 200m didominasi oleh sawah | Rank 1 | In Quota | BNP | TBG | Done
AREA 2 | R03 Jabotabek | SKB914 | JMBATANMERAHSKB | 106.9343 | -6.9574 | B2S | 41 | 42 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Available |  | Tower terdekat 350m dari titik NOM (1269842004 - IBS BAROS - JAYARAKSA) | COLO |  | Rank 2 | NO | COLO | TBG
AREA 2 | R03 Jabotabek | SKB913 | PERMANENSINDANGSARILEMBURSITU | 106.9142 | -6.9615 | B2S | 41 | 42 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Available |  | NO | YES | Titik NOM berada di wilayah pemukiman warga | Rank 1 | In Quota | BNP | TBG | Done
AREA 2 | R03 Jabotabek | RKB092 | CIAKARGUNUNGKENCANA | 106.0856 | -6.6057 | B2S | 61 | 62 | LEBAK | Check RTRW dan LANUD | GF | Private | Available |  | NO | YES | No Issue | Rank 1 | In Quota | BKM | TBG | OG Survey
AREA 2 | R03 Jabotabek | RKB084 | SUKAMANAHRANGKASBITUNG | 106.2781 | -6.3232 | B2S | 61 | 62 | LEBAK | Check RTRW dan LANUD | GF | Private | Available |  | Tower terdekat 700m dari titik NOM | YES | No Issue | Rank 1 | In Quota | KLS | TBG | On Progress
AREA 2 | R03 Jabotabek | RKB086 | JATIMULYARANGKASBITUNG | 106.2689 | -6.3541 | B2S | 41 | 42 | LEBAK | Check RTRW dan LANUD | GF | Private | Available |  | NO | YES | Berada di wilayah pemakaman warga, dan berbatasan dengan cluster perumahan | Rank 1 | In Quota | BKM | TBG | OG Survey
AREA 2 | R03 Jabotabek | PLR023 | GUNUNGWALATHEGARMANAH | 106.8017 | -6.9346 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Issue |  | NO | YES | Titik NOM berada di wilayah pemukiman warga | Rank 1 | In Quota | Datatel | TBG | Done
AREA 2 | R03 Jabotabek | PLR047 | PERMANENBUKITALGORITMA | 106.7035 | -6.9076 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Corporate | Issue |  | NO | YES WITH NOTE | Lahan milik corporate (Bukit Algoritma) | Rank 2 | NO | In House | TBG | On Progress
AREA 2 | R03 Jabotabek | PLR036 | CIRACAPUJUNGGENTENG | 106.4339 | -7.3309 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Issue |  | NO | YES | Titik NOM berada di wilayah pemukiman warga | Rank 1 | In Quota | Datatel | TBG | Done
AREA 2 | R03 Jabotabek | PLR015 | BUNIWANGIGEGERBITUNG | 107.0147 | -6.9567 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Issue |  | NO | YES | Titik NOM berada di wilayah pemukiman warga | Rank 1 | In Quota | BNP | TBG | Done
AREA 2 | R03 Jabotabek | PLR038 | PUNCAKBULUH | 106.6446 | -7.2254 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Issue |  | NO | YES | Titik NOM berada di wilayah pemukiman warga | Rank 1 | In Quota | Tritama | TBG | Done
AREA 2 | R03 Jabotabek | PLR029 | LENGKONG | 106.686 | -7.1168 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Issue |  | NO | YES | Titik NOM berada di wilayah pemukiman warga | Rank 1 | In Quota | Tritama | TBG | Done
AREA 2 | R03 Jabotabek | PLR025 | GIRIJAYA | 106.7318 | -6.9325 | B2S | 61 | 62 | SUKABUMI | Need IMB Before CME. Check lahan hijau dan gistaru | GF | Private | Issue |  | NO | YES | Titik NOM berada di wilayah pemukiman warga, lahan berkontur | Rank 1 | In Quota | Tritama | TBG | Done
AREA 2 | R03 Jabotabek | TGR571 | RANCAKALAPAPANONGAN | 106.5144 | -6.29 | B2S | 51 | 52 | TANGERANG | Check RTRW dan LANUD | GF | Private | Available |  | NO | YES | No Issue | Rank 1 | In Quota | MAJAA | TBG | On Progress
AREA 2 | R03 Jabotabek | TGR579 | TANAHMERAHSEPATANTIMUR | 106.5942 | -6.1116 | B2S | 41 | 42 | TANGERANG | Check RTRW dan LANUD | GF | Private | Available |  | NO | YES | No Issue | Rank 1 | In Quota | MAJAA | TBG | On Progress
AREA 2 | R03 Jabotabek | TGR574 | SINDANGSONO | 106.4878 | -6.1773 | B2S | 51 | 52 | TANGERANG | Check RTRW dan LANUD | GF | Private | Available |  | NO | YES | No Issue | Rank 1 | In Quota | MAJAA | TBG | On Progress