## Pvt
TAHAPAN PROJECT | (Multiple Items)
[12 empty] | Site ID | Site Name | Regional | Residence | Current Progress Status | PROBLEM ISSUE | Action Plan
Count of SONum | Column Labels | [10 empty] | TNX323 | PASIRJAYAJATIUWUNG | JABO OUTER | TANGERANG KOTA | SITAC - BAN/BAK | LAHAN CORPORATE | Masih menunggu review permohonan kita dengan PT Gajah Tunggal
Row Labels | Grand Total | [10 empty] | CBN623 | PERMANENCOMBATTIRTAWARNARUMPIN | JABO OUTER | BOGOR | SITAC - REHUNTING | KKOP, PENOLAKAN WARGA | menunggu Konfirmasi ketinggian yang diperbolehkan dari pihak KKOP untuk kandidat R untuk dikirim ke RTPE,
Grand Total | [11 empty] | BKX430 | PERMANENCOMBATPERUMPTMBEKASI | JABO OUTER | KOTA BEKASI | SITAC - REHUNTING | KAWASAN PERUMAHAN | Approval Titik Kandidat Q MCP 25 NOK dari RTPE. Rehunting untuk arahan baru pihak RTPE
[12 empty] | BOX049 | PERMANENCOMBATRAYASEMPLAK | JABO OUTER | KOTA BOGOR | SITAC - REHUNTING | KKOP, PENOLAKAN WARGA | Kand Q NOK. Arahan Hunting dari RTPE mendapat penolakan dari Kawasan Gudang (PT. Rafael), Area Curam, dan Lahan kebanyakan tidak mau disewa. Alternatif kandidat masih menunggu konfirmasi dari pemilik lahan
[12 empty] | BKX431 | PERMANENCOMBATJAKAPERMAI | JABO OUTER | KOTA BEKASI | SITAC - APPROVAL KANDIDAT | KAWASAN PERUMAHAN | Approval Titik Kandidat R (MCP 25). Lokasi disamping titik COMBAT
[12 empty] | CBN614 | PERMANENLEBAKWANGI2 | JABO OUTER | BOGOR | SITAC - REHUNTING | SENGKETA LAHAN, PENOLAKAN WARGA | IW Failed kand P dan Kand S. Kandidat Q dan R NOK dari RTPE. Arahan RTPE mengalami penolakan warga dan area lahan sengketa. Pengajuan titik kandidat Q ke RTPE. Justifikasi Report sudah di lampirkan.
[12 empty] | SKB896 | GUNUNGJAYACISAAT | JABO OUTER | SUKABUMI | SITAC - BAN/BAK | PENOLAKAN WARGA | Plan pertemuan dengan yayasan Lajnah Khairiyah Musytarakah Jakarta (Yayasan Pondok Pesantren Al-Matuq) minggu depan untuk membahas masalah sewa menyewa lahan untuk tower. Kandidat Alternatif masih dalam proses review RTPE
TAHAPAN PROJECT | (Multiple Items)
Company ID | TB
Row Labels | Count of SONum
(blank) | 27
ONTIME | 3
Grand Total | 30
Operator | Bulan Forecast |  |  |  | SLA |  |  |  | LT
| Agustus | September | Oktober | Grand Total | IN SLA | OUT SLA |  |  | 2020 | Jan-Jul | Ags-Des
TSEL | 3 | 1 | 0 | 4 | 4 | 0 |  |  |  | 174 | 59
SF | 1 | 3 | 0 | 4 | 4 | 0
H3I | 0 | 1 | 0 | 1 | 0 | 1
Grand Total | 4 | 5 | 0 | 9 | 8 | 1
TAHAPAN PROJECT | (Multiple Items)
[6 empty] | RFC Date | (All)
Row Labels | Count of Site ID
(blank) | 3 |  |  |  |  | Row Labels | Count of Site ID
JAKARTA SELATAN | 1 |  |  |  |  | DELAY | 24 | 47 | 24
JAKARTA TIMUR | 1 |  |  |  |  | ONTIME | 50 | 59 | 9
SUKABUMI | 1 |  |  |  |  | Grand Total | 74 | 106 | 68.49% | 80% | 85.62%
Rahadian | 19
BEKASI | 6
BOGOR | 8 |  |  |  |  | 67.57% | 55.66% |  | 24.34%
JAKARTA TIMUR | 1
KOTA BEKASI | 2 | [7 empty] | 69.58%
KOTA BOGOR | 2
Rinaldi | 14
JAKARTA BARAT | 3
JAKARTA UTARA | 3
KOTA TANGERANG | 4
TANGERANG | 4
Grand Total | 36

## Progress
2022-09-30
SONum | Site ID | Site ID Operator | Site Name TBG | Site Name Operator | Site Type | STIP Category | Operator ID | Company ID | SOW Year | STIP Number | STIP Date | Latitude NOM | Longitude NOM | Address | Regional | Residence | Province | Tower Height | Mitra | SITAC Officer | Cand | Latitude Candidate | Longitude Candidat | Propose Tower Height | RF Height | Approval RNP Date | MW Height/Diameter | Approval TNP Date | Tower Type | Field Type | RFC Projection | RFC Month Projection | RFI Projection | RFC Date | Aging RFC | RFC Remark | SLA | Aging SLA | TAHAPAN PROJECT | PROGRESS STATUS | DETAIL PROGRESS | Issue | Action Plan
23054786231 | 125932123 | JAK0742 | DEPOK CIMANGGIS | DEPOK CIMANGGIS | NEW BUILD | STIP 1 | SMART8 | TB | 2019-09-02 | 013913/TBG-TB/SMART8/MKT/09/2019 | 2019-09-02 | -6.363496 | -6.363496 |  | JABODETABEK (INNER) | KOTA DEPOK | JAWA BARAT | 32 | [5 empty] | 32 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1124 |  |  |  | PRE CANCEL
23054864231 | 131699123 | JAK1028 | KELAPA DUA TANGERANG | KELAPA DUA TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | 2019-09-02 | 013991/TBG-TB/SMART8/MKT/09/2019 | 2019-09-02 | -6.239031 | -6.239031 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 32 | [5 empty] | 32 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1124 |  |  |  | PRE CANCEL
0230553940231 | 1127001023 | ZJKT2_5296 | KEBON JERUK 362 | KEBON JERUK 362 | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2019-11-20 | 015105/TBG-TB/SMART8/MKT/11/2019 | 2019-11-20 | -6.202117 | -6.202117 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 30 | [5 empty] | 30 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1045 |  |  |  | PRE CANCEL
0230553950231 | 1127011023 | ZJKT2_5301 | DURI KOSAMBI 371 | DURI KOSAMBI 371 | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2019-11-20 | 015106/TBG-TB/SMART8/MKT/11/2019 | 2019-11-20 | -6.177989 | -6.177989 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 20 | [5 empty] | 20 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1045 |  |  |  | PRE CANCEL
0230553960231 | 1127021023 | ZJKT2_5337 | HALIM PERDANA KUSUMAH 497 | HALIM PERDANA KUSUMAH 497 | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2019-11-20 | 015107/TBG-TB/SMART8/MKT/11/2019 | 2019-11-20 | -6.266275 | -6.266275 |  | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA | 40 | [5 empty] | 40 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1045 |  |  |  | PRE CANCEL
0230560240231 | 1317261023 | ZJKT_5552 | SEPATAN TANGERANG | SEPATAN TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 016837/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.14699 | 106.58906 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | PT. MANDIRA INFRA TRIPAKARTI | [9 empty] | SST | GF | DONE | DONE | #VALUE! | 2020-11-20 | 326 | DONE |  |  | RFI | RFC
0030571840031 | 1127661003 | JAW-JK-KYB-0105 | JALAN KUBUR ISLAM | Jalan Kubur Islam | NEW MCP NON FO | STIP 1 | XL | TB |  | 018369/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.231306 | 106.782136 |  | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 20 | PT. KARYA LINTAS SEJAHTERA | Aditya R |  | -6.2325 | 106.781 | 20 | 20 | 2020-11-17 |  |  | POLE | GF | DONE | DONE | #VALUE! | 2020-12-02 | 323 | DONE |  |  | RFI | RFC
00230560280231 | 1260541023 | ZBGR_4269 | SUKARAJA BOGOR | SUKARAJA BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | 2019 | 016841/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.5545 | 106.831 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 35 | [5 empty] | 35 |  |  |  |  | SST | GF | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL | Realisasi IW
0230560250231 | 1317271023 | ZJKT2_4070 | CIPUTAT TIMUR | CIPUTAT TIMUR | NEW BUILD | STIP 1 | SMART8 | TB | 2019-12-30 | 016838/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.31615 | -6.31615 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 25 | [5 empty] | 25 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL
0230560260231 | 1260521023 | ZJKT2_4174 | BEKASI UTARA 1 | BEKASI UTARA 1 | NEW BUILD | STIP 1 | SMART8 | TB | 2019-12-30 | 016839/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.20892 | -6.20892 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 27 | [5 empty] | 27 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL
0230560270231 | 1260531023 | ZBGR_4046 | CIBINONG BOGOR | CIBINONG BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | 2019-12-30 | 016840/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.519681 | -6.519681 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 30 | [5 empty] | 30 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL
0230560300231 | 1317291023 | ZJKT2_4388 | PAMULANG TANGERANG SELATAN | PAMULANG TANGERANG SELATAN | NEW BUILD | STIP 1 | SMART8 | TB | 2019-12-30 | 016843/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.334573 | -6.334573 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 30 | [5 empty] | 30 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL | Realisasi IW | [9.12.20] Submit eskalasi SITAC |  | Propose Fortuna
0230560320231 | 1260551023 | ZJKT2_4306 | BEJIDEPOK | BEJIDEPOK | NEW BUILD | STIP 1 | SMART8 | TB | 2019-12-30 | 016845/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.372441 | -6.372441 |  | JABODETABEK (INNER) | KOTA DEPOK | JAWA BARAT | 25 | [5 empty] | 25 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL
0230560330231 | 1317311023 | ZJKT2_4350 | KARANG TENGAH KOTA TANGERANG | KARANG TENGAH KOTA TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | 2019-12-30 | 016846/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.226212 | -6.226212 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 25 | [5 empty] | 25 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL
0230560340231 | 1260561023 | ZJKT2_4514 | BEKASI UTARA 2 | BEKASI UTARA 2 | NEW BUILD | STIP 1 | SMART8 | TB | 2019-12-30 | 016847/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.177563 | -6.177563 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 30 | [5 empty] | 30 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL
0230560350231 | 1260571023 | ZBGR_4355 | GUNUNG PUTRI BOGOR | GUNUNG PUTRI BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | 2019-12-30 | 016848/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.461526 | -6.461526 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 30 | [5 empty] | 30 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL
0230560360231 | 1317321023 | ZJKT2_4999 | CIPUTAT 2 | CIPUTAT 2 | NEW BUILD | STIP 1 | SMART8 | TB | 2019-12-30 | 016849/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.299844 | -6.299844 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 28 | [5 empty] | 28 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL
0230560380231 | 1317331023 | ZJKT2_5122 | CIPUTAT 3 | CIPUTAT 3 | NEW BUILD | STIP 1 | SMART8 | TB | 2019-12-30 | 016851/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.299819 | -6.299819 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 25 | [5 empty] | 25 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL
0230560390231 | 1317341023 | ZJKT2_5175 | PINANG | PINANG | NEW BUILD | STIP 1 | SMART8 | TB | 2019-12-30 | 016852/TBG-TB/SMART8/MKT/12/2019 | 2019-12-30 | -6.195118 | -6.195118 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 25 | [5 empty] | 25 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1005 |  |  |  | PRE CANCEL
0230560780231 | 1127541023 | ZJKT2_4248 | KEMAYORAN | KEMAYORAN | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2019-12-31 | 016907/TBG-TB/SMART8/MKT/12/2019 | 2019-12-31 | -6.157403 | -6.157403 |  | JABODETABEK (INNER) | JAKARTA PUSAT | DKI JAKARTA | 20 | [5 empty] | 20 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 1004 |  |  |  | PRE CANCEL
0030572100031 | 1260911003 | JAW-JB-CBI-0070 | KANDANG RODA SENTUL | Kandang Roda Sentul | NEW BUILD | STIP 1 | XL | TB | 2020 | 018395/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.52122 | 106.84114 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 50 | SS | SS Devi |  |  |  | 52 |  |  |  |  | SST | GF | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 990 |  |  |  | PRE CANCEL | Re-Hunting | [9.12.20] Re-Hunting Kandidat
0030572380031 | 1127881003 | JAW-JK-TJP-0625 | JALAN PANTAI INDAH SELATAN 2 | Jalan Pantai Indah Selatan 2 | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 018423/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.128104 | 106.760621 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | PT. KARYA LINTAS SEJAHTERA | Handri P |  |  |  | 20 |  |  |  |  | POLE | GF | DONE | DONE | #VALUE! | 2020-11-20 | 311 | DONE |  |  | RFI | RFC | RFC
0030571930031 | 1127731003 | JAW-JK-TJP-0616 | KOMPLEK GREEN GARDEN | Komplek Green Garden | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 018378/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.152426 | 106.949209 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | [10 empty] | MONOPOLE | GF | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 990 |  |  |  | PRE CANCEL
0030572370031 | 1127871003 | JAW-JK-CKG-0669 | JALAN R. A. FADILLAH | Jalan R. A. Fadillah | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 018422/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.317092 | 106.85829 |  | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA | 20 | PT. KARYA LINTAS SEJAHTERA | Aditya R |  |  |  | 20 |  |  |  |  | POLE | GF | DONE | DONE | #VALUE! | 2021-01-15 | 367 | DONE | DELAY |  | RFI | RFC | RFC [5.1.21] Submit PKS ke Legal, deviasi OG [9.12.20] Waiting Review PKS | Update TSSR di TBG Sys | PKS Done Review, Finishing PKS
0030572180031 | 1317501003 | JAW-BT-CPT-0476 | PONDOK CABE RAYA | Pondok Cabe Raya | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 018403/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.331283 | 106.766244 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 20 | PT. BANJARPASIR NUSA PRATAMA | Aditya R | B | -6.3308 | 106.7695 | 20 | 20 | 2020-10-08 | 19 | 2020-11-24 | POLE | GF | DONE | DONE | #VALUE! | 2020-11-20 | 311 | DONE |  |  | RFI | RFC | RFC
0030572080031 | 1317441003 | JAW-BT-TNG-1458 | TAMAN GOLF BOULEVARD | Taman Golf Boulevard | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 018393/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.193476 | 106.649175 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 35 | PT. BANJARPASIR NUSA PRATAMA | Aditya R | C | -6.1928 | 106.6496 | 20 | 20 | 2020-11-11 | 20 | 2020-11-24 | POLE | GF | DONE | DONE | #VALUE! | 2021-01-29 | 381 | DONE | DELAY |  | RFI | RFC | RFC [10.12.20] PKS TTD pihak TBG [9.12.20] Rekom Camat NY |  | IMB Expired, Rekom Camat NY, menunggu SKRD
0030572590031 | 1317781003 | JAW-BT-TNG-1467 | JL INDUSTRI JATAKE | JL INDUSTRI JATAKE | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 018444/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.198783 | 106.567911 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 35 | PT. ROTUA | Handri P |  |  |  | 20 |  |  |  |  | POLE | GF | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 990 |  |  |  | PRE CANCEL | Re-Hunting
0030572600031 | 1317791003 | JAW-BT-TNG-1468 | KARANGSARI NEGLASARI | KARANGSARI NEGLASARI | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 018445/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.158613 | 106.636761 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 35 | [10 empty] | POLE | GF | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 990 |  |  |  | PRE CANCEL | Re-Hunting
0030572620031 | 1317811003 | JAW-BT-TGR-0061 | JL TELESONIC PASIRJAYA | JL TELESONIC PASIRJAYA | NEW BUILD | STIP 1 | XL | TB | 2020 | 018447/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.20141 | 106.558209 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 35 | SS | SS Devi | [8 empty] | SST | GF | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 990 |  |  |  | PRE CANCEL | Re-Hunting
0030572010031 | 1317401003 | JAW-BT-TGR-0022 | TAMAN KOTA TANGERANG | Taman Kota Tangerang | NEW BUILD | STIP 1 | XL | TB | 2020 | 018386/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.269968 | 106.485605 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 35 | [10 empty] | SST | GF | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 990 |  |  |  | PRE CANCEL | Re-Hunting | [4.12.20] Submit permohonan perijinan PEMDA TANGKOT
0030572500031 | 1317691003 | JAW-BT-CPT-0472 | WIJAYAKUSUMA CEGER | Wijaya Kusuma Ceger | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 018435/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.26192 | 106.72722 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 25 | PT. TURANGGA EMPAT TIGA |  | D | -6.2612 | 106.737 | 20 |  |  |  |  | MCP | GF | DONE | DONE | 26 Maret 2021 | 2021-03-16 | 427 | DONE | DELAY |  | RFI | RFC | [12.3.21] Rekom LC done, paralel submit system [4.3.21] Eskalasi done approve, go realisasi. Rekom LC 8/9 Maret [2.3.21] Approval eskalasi SITAC [23.2.21] Cancel PO SITAC Turangga [21.2.21] IW OG, waiting eskalasi Submit by mitra [15.1.21] IW OG [4.12.20] mendapatkan harga sewa lahan
0010587980011 | 1128331001 | JUX570 | PERMANENCOMBATRUSUNMARUNDA | PERMANENCOMBATRUSUNMARUNDA | NEW MCP NON FO | STIP 1 | TSEL | TB | 2020-03-20 | 021471/TBG-TB/TSEL/MKT/03/2020 | 2020-03-20 | -6.0955 | 106.9645 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | [5 empty] | 20 | [6 empty] | #N/A | #N/A | #N/A |  | 924 |  |  |  | RFI | BAN/BAK
0030594960031 | 1318231003 | JAW-BT-CPT-0447 | JALAN MENTAWAI TOL | Jalan Mentawai Tol | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 023435/TBG-TB/XL/MKT/06/2020 | 2020-06-24 | -6.300262 | 106.695322 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 20 | PT. BANJARPASIR NUSA PRATAMA | Handri P | B | -6.2998 | 106.6961 | 20 |  |  |  |  | POLE | GF | DONE | DONE | #VALUE! | 2020-11-20 | 149 | DONE |  |  | RFI | RFC | RFC
0030572030031 | 1317421003 | JAW-BT-TNG-1457 | KEDAUNG WETAN NEGLASARI | Kedaung Wetan Neglasari | NEW MCP NON FO | STIP 1 | XL | TB | 2020-01-14 | 018388/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.125174 | -6.125174 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 35 | [5 empty] | 35 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 990 |  |  |  | PRE CANCEL
0030572060031 | 1127781003 | JAW-JK-TJP-0627 | PADEMANGAN TANJUNG PRIOK | Pademangan Tanjung Priok | NEW MCP NON FO | STIP 1 | XL | TB | 2020-01-14 | 018391/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.121079 | -6.121079 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | [5 empty] | 20 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 990 |  |  |  | PRE CANCEL
0030572450031 | 1317641003 | JAW-BT-CPT-0464 | MENTENG BINTARO | MENTENG BINTARO | NEW MCP NON FO | STIP 1 | XL | TB | 2020-01-14 | 018430/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.27837 | -6.27837 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 35 | [5 empty] | 35 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 990 |  |  |  | PRE CANCEL
0230575230231 | 1261051023 | ZBGR_4328 | BOJONGGEDE_BOGOR | BOJONGGEDE_BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | 2020-01-28 | 019275/TBG-TB/SMART8/MKT/01/2020 | 2020-01-28 | -6.487618 | -6.487618 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 35 | [5 empty] | 35 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 976 |  |  |  | PRE CANCEL
0230575270231 | 1261071023 | ZJKT2_4181 | CIMANGGIS DEPOK 162 | CIMANGGIS DEPOK 162 | NEW BUILD | STIP 1 | SMART8 | TB | 2020-01-28 | 019279/TBG-TB/SMART8/MKT/01/2020 | 2020-01-28 | -6.372332 | -6.372332 |  | JABODETABEK (INNER) | KOTA DEPOK | JAWA BARAT | 35 | [5 empty] | 35 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 976 |  |  |  | PRE CANCEL
0230575300231 | 1261091023 | ZJKT2_4968 | BEKASI UTARA | BEKASI UTARA | NEW BUILD | STIP 1 | SMART8 | TB | 2020-01-28 | 019282/TBG-TB/SMART8/MKT/01/2020 | 2020-01-28 | -6.228204 | -6.228204 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 35 | [5 empty] | 35 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 976 |  |  |  | PRE CANCEL
0230575320231 | 1317881023 | ZJKT2_5056 | PASARKEMIS TANGERANG | PASARKEMIS TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | 2020-01-28 | 019284/TBG-TB/SMART8/MKT/01/2020 | 2020-01-28 | -6.163653 | -6.163653 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 30 | [5 empty] | 30 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 976 |  |  |  | PRE CANCEL
0230575330231 | 1261101023 | ZJKT2_5192 | CIMANGGIS DEPOK 025 | CIMANGGIS DEPOK 025 | NEW BUILD | STIP 1 | SMART8 | TB | 2020-01-28 | 019285/TBG-TB/SMART8/MKT/01/2020 | 2020-01-28 | -6.356348 | -6.356348 |  | JABODETABEK (INNER) | KOTA DEPOK | JAWA BARAT | 32 | [5 empty] | 32 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 976 |  |  |  | PRE CANCEL
0230579860231 | 1128021023 | ZJKT2_6011 | LUBANG BUAYA CIPAYUNG | Lubang Buaya Cipayung | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2020 | 019763/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.294797 | 106.896936 |  | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA | 20 | TBG IN HOUSE | [9 empty] | MONOPOLE | GF | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579370231 | 1317901023 | ZJKT2_6083 | KUTA JAYA PASARKEMIS | Kuta Jaya Pasarkemis | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019714/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.163851 | -6.163851 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579380231 | 1261131023 | ZJKT2_6073 | SUKAASIH SUKATANI | Sukaasih Sukatani | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019715/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.221338 | -6.221338 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579410231 | 1261141023 | ZJKT2_6061 | CIBATU CIKARANG SELATAN | Cibatu Cikarang Selatan | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019718/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.338886 | -6.338886 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579440231 | 1261151023 | ZJKT2_6058 | PASIRSARI CIKARANG SELATAN | Pasirsari Cikarang Selatan | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019721/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.307019 | -6.307019 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579450231 | 1261161023 | ZJKT2_6053 | CIKEDOKAN CIKARANG BARAT | Cikedokan Cikarang Barat | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019722/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.328378 | -6.328378 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579480231 | 1261171023 | ZJKT2_6052 | GANDAMEKAR CIKARANG BARAT | Gandamekar Cikarang Barat | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019725/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.294671 | -6.294671 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579500231 | 1261191023 | ZBGR_4676 | KEBONKELAPA BOGOR TENGAH | Kebonkelapa Bogor Tengah | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019727/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.591009 | -6.591009 |  | JABODETABEK (OUTER) | KOTA BOGOR | JAWA BARAT | 32 | [5 empty] | 32 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579530231 | 1261201023 | ZBGR_4675 | SITU ILIR CIBUNGBULANG | Situ Ilir Cibungbulang | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019730/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.604124 | -6.604124 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579590231 | 1261221023 | ZJKT2_5964 | MANGUNJAYA TAMBUN SELATAN | Mangunjaya Tambun Selatan | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019736/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.24255 | -6.24255 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579610231 | 1261231023 | ZJKT2_5956 | BAHAGIA BABELAN | Bahagia Babelan | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019738/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.17631 | -6.17631 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579620231 | 1261241023 | ZJKT2_5953 | PAHLAWAN SETIA TARUMAJAYA | Pahlawan Setia Tarumajaya | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019739/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.13007 | -6.13007 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579640231 | 1317941023 | ZJKT2_5936 | MEKAR BAKTI PANONGAN | Mekar Bakti Panongan | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019741/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.252882 | -6.252882 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579660231 | 1261251023 | ZBGR_4660 | SUSUKAN BOJONG GEDE | Susukan Bojong Gede | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019743/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.478516 | -6.478516 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579790231 | 1261261023 | ZJKT2_6036 | MEDAN SATRIA MEDAN SATRIA | Medan Satria Medan Satria | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019756/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.206452 | -6.206452 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 25 | [5 empty] | 25 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579800231 | 1261271023 | ZJKT2_6016 | KOTA BARU BEKASI BARAT | Kota Baru Bekasi Barat | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019757/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.21632 | -6.21632 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 25 | [5 empty] | 25 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579810231 | 1261281023 | ZJKT2_5986 | JATIRAHAYU PONDOKMELATI | Jatirahayu Pondokmelati | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019758/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.295498 | -6.295498 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 25 | [5 empty] | 25 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230579820231 | 1261291023 | ZJKT2_5911 | CIMUNING MUSTIKAJAYA | Cimuning Mustikajaya | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-10 | 019759/TBG-TB/SMART8/MKT/02/2020 | 2020-02-10 | -6.316367 | -6.316367 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 25 | [5 empty] | 25 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 963 |  |  |  | PRE CANCEL
0230580710231 | 1317981023 | ZJKT2_6087 | WANA KERTA SINDANG JAYA | Wana Kerta Sindang Jaya | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 019848/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.196603 | 106.5079 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | PT. MANDIRA INFRA TRIPAKARTI | [9 empty] | SST | GF | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL | BAN/BAK
0230579910231 | 1261301023 | ZBGR_4657 | CIAPUS CIOMAS | Ciapus Ciomas | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019768/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.601142 | -6.601142 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230579920231 | 1261311023 | ZJKT2_5922 | TANAH BARU BEJI | Tanah Baru Beji | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019769/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.38254 | -6.38254 |  | JABODETABEK (INNER) | KOTA DEPOK | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230579960231 | 1261321023 | ZBGR_4653 | PARIGI MEKAR CISEENG | Parigi Mekar Ciseeng | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019773/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.450596 | -6.450596 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230579970231 | 1261331023 | ZJKT2_5921 | CIANTRA CIKARANG SELATAN | Ciantra Cikarang Selatan | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019774/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.340953 | -6.340953 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230579980231 | 1261341023 | ZJKT2_5920 | RAWAKALONG GUNUNG SINDUR | Rawakalong Gunung Sindur | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019775/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.362964 | -6.362964 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230579990231 | 1261351023 | ZJKT2_5918 | RAGAJAYA BOJONG GEDE | Ragajaya Bojong Gede | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019776/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.44698 | -6.44698 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580000231 | 1261361023 | ZJKT2_5917 | KEDUNGJAYA BABELAN | Kedungjaya Babelan | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019777/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.157705 | -6.157705 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580010231 | 1261371023 | ZJKT2_5913 | KEBALEN BABELAN | Kebalen Babelan | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019778/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.19394 | -6.19394 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580020231 | 1261381023 | ZBGR_4652 | PABUARAN CIBINONG | Pabuaran Cibinong | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019779/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.46181 | -6.46181 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580030231 | 1261391023 | ZJKT2_5904 | BABELAN BEKASI | Babelan Bekasi | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019780/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.176712 | -6.176712 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580060231 | 1261401023 | ZJKT2_5902 | KEBALEN BEKASI | Kebalen Bekasi | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019783/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.196864 | -6.196864 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580070231 | 1261411023 | ZJKT2_5898 | TUGU CIMANGGIS | Tugu Cimanggis | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019784/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.347367 | -6.347367 |  | JABODETABEK (INNER) | KOTA DEPOK | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580080231 | 1317951023 | ZJKT2_5897 | BOJONG NANGKA BANTEN | Bojong Nangka Banten | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019785/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.256287 | -6.256287 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580380231 | 1261431023 | ZJKT2_4000 | SUKAHURIP SUKATANI | Sukahurip Sukatani | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019815/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.213369 | -6.213369 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580640231 | 1261541023 | ZJKT2_6107 | PINAYUNGAN TELUKJAMBE TIMUR | Pinayungan Telukjambe Timur | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019841/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.360136 | -6.360136 |  | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580650231 | 1261551023 | ZJKT2_6105 | BENGLE MAJALAYA | Bengle Majalaya | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019842/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.323467 | -6.323467 |  | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580720231 | 1317991023 | ZJKT2_6074 | KARANGKEPUH BOJONEGARA | Karangkepuh Bojonegara | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019849/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -5.978916 | -5.978916 |  | JABODETABEK (OUTER) | SERANG | BANTEN | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580770231 | 1318001023 | ZJKT2_5925 | SUKADALEM WARINGINKURUNG | Sukadalem Waringinkurung | NEW BUILD | STIP 1 | SMART8 | TB | 2020-02-11 | 019854/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.050434 | -6.050434 |  | JABODETABEK (OUTER) | SERANG | BANTEN | 42 | [5 empty] | 42 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230580870231 | 1261581023 | ZJKT_6886 | PEJUANG MEDAN SATRIA | Pejuang Medan Satria | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2020-02-11 | 019864/TBG-TB/SMART8/MKT/02/2020 | 2020-02-11 | -6.180512 | -6.180512 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 20 | [5 empty] | 20 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 962 |  |  |  | PRE CANCEL
0230581860231 | 1318011023 | ZJKT2_4247 | NEGLASARI TANGERANG | NEGLASARI TANGERANG | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2020-02-17 | 020065/TBG-TB/SMART8/MKT/02/2020 | 2020-02-17 | -6.1563 | -6.1563 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 20 | [5 empty] | 20 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 956 |  |  |  | PRE CANCEL
0230581870231 | 1128061023 | ZJKT2_4362 | TANJUNG PRIOK UTARA | TANJUNG PRIOK UTARA | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2020-02-17 | 020066/TBG-TB/SMART8/MKT/02/2020 | 2020-02-17 | -6.11648 | -6.11648 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | [5 empty] | 20 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 956 |  |  |  | PRE CANCEL
0230581880231 | 1318021023 | ZJKT2_4539 | PONDOK AREN SELATAN | PONDOK AREN SELATAN | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2020-02-17 | 020067/TBG-TB/SMART8/MKT/02/2020 | 2020-02-17 | -6.26639 | -6.26639 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 20 | [5 empty] | 20 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 956 |  |  |  | PRE CANCEL
0230581890231 | 1318031023 | ZJKT2_5117 | PONDOK AREN 5117 | PONDOK AREN 5117 | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2020-02-17 | 020068/TBG-TB/SMART8/MKT/02/2020 | 2020-02-17 | -6.25382 | -6.25382 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 20 | [5 empty] | 20 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 956 |  |  |  | PRE CANCEL
0230581900231 | 1318041023 | ZJKT2_5209 | CIPUTAT SELATAN | CIPUTAT SELATAN | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2020-02-17 | 020069/TBG-TB/SMART8/MKT/02/2020 | 2020-02-17 | -6.29892 | -6.29892 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 20 | [5 empty] | 20 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 956 |  |  |  | PRE CANCEL
0030587400031 | 1261811003 | JAW-JB-CBI-0065 | PURA GUNUNG SALAK PERMANEN | PURA GUNUNG SALAK Permanen | NEW BUILD | STIP 1 | XL | TB | 2020 | 020978/TBG-TB/XL/MKT/03/2020 | 2020-03-14 | -6.668111 | 106.7359 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | SS | SS Devi |  |  |  | 42 |  |  |  |  | SST | GF | 2020-12-15 | 2020-12-15 | 2021-01-14 |  | 930 |  |  |  | PRE CANCEL | Realisasi IW | [9.12.20] Submit eskalasi SITAC [4.12.20] Kandidat Approve
0230587600231 | 1318111023 | ZJKT2_6091 | GANDASARI TANGERANG | Gandasari Tangerang | NEW BUILD | STIP 1 | SMART8 | TB | 2020-03-18 | 021239/TBG-TB/SMART8/MKT/03/2020 | 2020-03-18 | -6.203108 | -6.203108 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 28 | [5 empty] | 28 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 926 |  |  |  | PRE CANCEL
0230587630231 | 1128261023 | ZJKT2_5899 | JAKTIM CAKUNG BARAT | Jaktim Cakung Barat | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2020-03-18 | 021242/TBG-TB/SMART8/MKT/03/2020 | 2020-03-18 | -6.168942 | -6.168942 |  | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA | 25 | [5 empty] | 25 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 926 |  |  |  | PRE CANCEL
0230587650231 | 1318121023 | ZJKT2_5945 | KUNCIRAN | Kunciran | NEW BUILD | STIP 1 | SMART8 | TB | 2020-03-18 | 021244/TBG-TB/SMART8/MKT/03/2020 | 2020-03-18 | -6.230812 | -6.230812 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 27 | [5 empty] | 27 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 926 |  |  |  | PRE CANCEL
0230587660231 | 1128281023 | ZJKT2_5961 | DURI KOSAMBI JAKARTA | Duri Kosambi Jakarta | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2020-03-18 | 021245/TBG-TB/SMART8/MKT/03/2020 | 2020-03-18 | -6.182605 | -6.182605 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 26 | [5 empty] | 26 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 926 |  |  |  | PRE CANCEL
0230587670231 | 1128291023 | ZJKT2_6017 | CAKUNG BARAT JAKTIM | Cakung Barat Jaktim | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2020-03-18 | 021246/TBG-TB/SMART8/MKT/03/2020 | 2020-03-18 | -6.167689 | -6.167689 |  | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA | 30 | [5 empty] | 30 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 926 |  |  |  | PRE CANCEL
0230587680231 | 1128301023 | ZJKT2_6081 | KALIDERES JAKBAR | Kalideres Jakbar | NEW MCP NON FO | STIP 1 | SMART8 | TB | 2020-03-18 | 021247/TBG-TB/SMART8/MKT/03/2020 | 2020-03-18 | -6.153465 | -6.153465 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 24 | [5 empty] | 24 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 926 |  |  |  | PRE CANCEL
0230587690231 | 1318131023 | ZJKT2_6082 | PERIUK | Periuk | NEW BUILD | STIP 1 | SMART8 | TB | 2020-03-18 | 021248/TBG-TB/SMART8/MKT/03/2020 | 2020-03-18 | -6.15483 | -6.15483 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 30 | [5 empty] | 30 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 926 |  |  |  | PRE CANCEL
0230587700231 | 1318141023 | ZJKT2_6089 | KENANGA | Kenanga | NEW BUILD | STIP 1 | SMART8 | TB | 2020-03-18 | 021249/TBG-TB/SMART8/MKT/03/2020 | 2020-03-18 | -6.198763 | -6.198763 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 24 | [5 empty] | 24 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 926 |  |  |  | PRE CANCEL
0230587710231 | 1318151023 | ZJKT2_6095 | GAGA | Gaga | NEW BUILD | STIP 1 | SMART8 | TB | 2020-03-18 | 021250/TBG-TB/SMART8/MKT/03/2020 | 2020-03-18 | -6.24051 | -6.24051 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 24 | [5 empty] | 24 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 926 |  |  |  | PRE CANCEL
0030594980031 | 1128751003 | JAW-JK-TJP-0679 | LONTAR DALAM KOJA | LONTAR DALAM KOJA | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 023437/TBG-TB/XL/MKT/06/2020 | 2020-06-24 | -6.118810 | 106.913530 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | TBG IN HOUSE | Aditya R | B | -6.1188 | 106.9135 | 20 | 20 | 2020-09-16 | 20 | 2020-11-24 | POLE | GF | DONE | DONE | #VALUE! | 2020-11-20 | 149 | DONE |  |  | RFI | RFC | RFC
0030594970031 | 1128741003 | JAW-JK-TJP-0677 | SWASEMBADA TANJUNG PRIOK | SWASEMBADA TANJUNG PRIOK | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 023436/TBG-TB/XL/MKT/06/2020 | 2020-06-24 | -6.1218 | 106.888 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | PT. KARYA LINTAS SEJAHTERA | Handri P | E | -6.1221 | 106.8878 | 20 | 20 | 2020-09-16 | 20 | 2020-11-24 | POLE | GF | DONE | DONE | #VALUE! | 2020-12-02 | 161 | DONE |  |  | RFI | RFC | RFC
0030595820031 | 1262221003 | JAW-JB-BKS-0708 | BINTARA KENCANA TIMUR | BINTARA KENCANA TIMUR | NEW BUILD | STIP 1 | XL | TB | 2020 | 023606/TBG-TB/XL/MKT/07/2020 | 2020-07-06 | -6.224850 | 106.957570 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 32 | PT. FERGACO TEKNIKA | Handri P | D | -6.2249 | 106.9576 | 27 | 25 |  |  |  | SST | GF | DONE | DONE | #VALUE! | 2021-01-18 | 196 | DONE | DELAY |  | RFI | RFC | RFC [4.1.21] APD Done by konsultan [9.12.20] APD NY Done, review by consultant Rekom Camat NY
0030600930031 | 1129171003 | JAW-JK-TJP-0628 | WARAKAS TANJUNG PRIOK | WARAKAS TANJUNG PRIOK | NEW BUILD | STIP 1 | XL | PKP | 2020-09-15 | 025157/TBG-PKP/XL/MKT/09/2020 | 2020-09-15 | -6.11765 | -6.11765 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 16.5 | PKP | PKP |  |  |  | 16.5 | [6 empty] | 2021-01-10 | 2021-01-10 | 2021-02-09 | 2020-11-10 | 56 | DONE |  |  | RFI | RFC
0030594990031 | 1128761003 | JAW-JK-TJP-0680 | KAMPUNG BETING KOJA | KAMPUNG BETING KOJA | NEW MCP NON FO | STIP 1 | XL | TB | 2020-06-24 | 023438/TBG-TB/XL/MKT/06/2020 | 2020-06-24 | -6.119154 | -6.119154 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | [5 empty] | 20 | [6 empty] | 2021-01-06 | 2021-01-06 | 2021-02-05 |  | 828 |  |  |  | PRE CANCEL
0030595440031 | 1262201003 | JAW-JB-BGR-0227 | CILEUKSA SUKAJAYA | Cileuksa Sukajaya | NEW BUILD | STIP 1 | XL | TB | 2020 | 023524/TBG-TB/XL/MKT/06/2020 | 2020-06-25 | -6.59522 | 106.44636 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 40 | SS | Rahadian | [8 empty] | SST | GF | #N/A | #N/A | #N/A |  | 827 |  |  | #N/A | DROP | DROP | Re-Hunting Kandidat
0010601920011 | 1262801001 | SKB146 | AWILEGA | AWILEGA | NEW BUILD | STIP 1 | TSEL | TB | 2020 | 025397/TBG-TB/TSEL/MKT/09/2020 | 2020-09-23 | -6.98871 | 106.83992 |  | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 72 | PT. BANJARPASIR NUSA PRATAMA | Aditya R |  |  |  | 72 |  |  |  |  | SST | GF | DONE | DONE | #VALUE! | 2020-11-20 | 58 | DONE |  |  | RFI | RFC | RFC
0030600240031 | 1129131003 | JAW-JK-TJP-0640 | KALIBARU CILINCING | Kalibaru Cilincing | NEW BUILD | STIP 1 | XL | PKP | 2020-09-08 | 025012/TBG-PKP/XL/MKT/09/2020 | 2020-09-08 | -6.100122 | -6.100122 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 23 |  | Rahadian |  |  |  | 23 | [6 empty] | #N/A | #N/A | #N/A |  | 752 |  |  |  | DROP | DROP
0010601840011 | 1129181001 | JUX064 | JLBUDIMULYAUTARA | JLBUDIMULYAUTARA | NEW MCP NON FO | STIP 1 | TSEL | TB | 2020 | 025389/TBG-TB/TSEL/MKT/09/2020 | 2020-09-23 | -6.13228 | 106.83543 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | PT. KARYA LINTAS SEJAHTERA | Handri P |  |  |  | 20 |  |  |  |  | MCP | GF | DONE | DONE | #VALUE! | 2021-02-09 | 139 | DONE | DELAY |  | RFI | RFC | RFC [9.2.21] RFC [27.1.21] Legalitas lahan dan nadzir sedang diurus, rekom LC dikejar [25.1.21] IW done, BAK Done, Nego start CME [5.1.21] Validasi Titik to RANE TSEL [9.12.20] Submit Kandidat Z IW On Going
0230605900231 | 1129321023 | ZJKT2_4563 | ALFAMART TIPAR CAKUNG 2 | ALFAMART TIPAR CAKUNG 2 | NEW MCP NON FO | STIP 1 | SMART8 | PKP | 2020-10-15 | 025829/TBG-PKP/SMART8/MKT/10/2020 | 2020-10-15 | -6.1555 | 106.92906 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 21 | PT. LINTAS BANYU LESTARI | Aditya R |  |  |  | 20 |  |  |  |  | POLE | GF | 2020-12-15 | 2020-12-15 | 2021-01-14 | 2021-01-18 | 95 | DONE |  |  | RFI | RFC | RFC [18.12.20] Start CME [15.12.20] Join Survey SAT, LBL, TBG [14.12.20] Rekom LC sudah clear, Proses SIK dari PKP plan release tanggal 14
0230613770231 | 1263671023 | ZJKT2_5926 | BEKASI UTARA KOTA BEKASI | BEKASI UTARA KOTA BEKASI | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027761/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.222518 | 107.009133 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 42 |  | Rahadian | [8 empty] | SST | GF | #N/A | #N/A | #N/A |  | 676 |  |  | #N/A | SITAC | IW On Going | [7.3.21] Need New kandidat, rehunting by SS [3.3.21] Dapat 2 kandidat follow up BAN/BAK [1.3.21] Pak Jimmy hunting [15.2.21] Negosiasi BAN dengan yayasan, angka BAN 37jt/thn [10.2.21] Jovis with yayasan brata bhakti [8.2.21] Comcase warga radius, geser kandidat. kandidat ke yayasan brata bhakti [4.2.21] IW onGOing [2.2.21] Validation done OG IW [26.1.21] Re-submit kandidat C dan D setelah meeting "clinic" hari jumat, hasil nego BAN ke mitra submit hari ini [30.12.20] Rejected via siteforge, waiting internal review SF [22.12.20] Submit Kandidat C, D, E. [20.12.20] Kandidat reject A dan B outsar, re-hunting [16.12.20] Mitra submit kandidat, validation bia siteforge, TSSR NY [15.12.20] Propose Datatel [14.12.20] Pihak UBHARA menolak disewa, rehunting kandidat Berkirim surat propose lahan UBHARA | Paralel IW untuk lahan kandidat baru, Kandidat NY submit siteforge | System Precancel
0230613630231 | 1263651023 | ZBGR_4588 | CIBUNGBULANG BOGOR | CIBUNGBULANG BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027747/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.61969 | 106.65947 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. TURANGGA EMPAT TIGA | Rahadian | B | -6.6182 | 106.6585 | 52 | 49 | 2020-12-08 | 35/0.3 | 2020-12-08 | SST | GF | #N/A | #N/A | #N/A |  | 676 |  |  | #N/A | DROP | DROP | [11.3.21] Validasi kandidat by siteforge [19.2.21] Need Take Over Mitra [11.2.21] Jovis with SF [2.2.21] Return by BNP, Pak Handri hunting titik kandidat [26.1.21] Follow up mitra kandidat baru, maksimal jumat baru mitra di takeover [7.1.21] Kandidat Approve, Eskalasi Submit 13.1.21 [5.1.21] Resubmit kandidat C, Plan IW clear 8.1.21 [22.12.20] Kandidat B, kepastian harga dari LL 23.12.20, check IW, Paralel Rehunting kandidat C [20.12.20] BNP Submit kandidat, Check IW dan BAN 22.12.20 [17.12.20] Paralel Re-Hunting IW NY Clear [14.12.20] Plan IW clear 16.12.20 IW OG, Koordinasi dengan lingkungan RF validation Done, Candidat Approve Submit Validasi 7.12.20 | Validasi Kandidat terakhir dengan ketinggian 72m di siteforge
0070607420071 | 1263081007 | 604034 | RAWA LUMBU 4 | RAWA LUMBU 4 | NEW BUILD | STIP 1 | HCPT | PKP | 2020-11-11 | 027046/TBG-PKP/HCPT/MKT/11/2020 | 2020-11-11 | -6.27475 | -6.27475 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 21 | PT. BANJARPASIR NUSA PRATAMA |  |  |  |  | 21 | [6 empty] | 2021-01-15 | 2021-01-15 | 2021-02-14 |  | 688 |  |  |  | PRE CANCEL
0230613620231 | 1263641023 | IN20_JB_0812 | CITEUREUP BOGOR 2 | CITEUREUP BOGOR 2 | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027746/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.526776 | 106.907988 | Kp. Legokrati RT. 002 RW. 003 Desa Tajur Kec. Citeureup Kab. Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. BANJARPASIR NUSA PRATAMA | Handri P | A | -6.5271 | 106.9073 | 52 | 43 | 2020-12-02 | 47/0.3 | 2020-12-07 | SST | GF | DONE | DONE | #VALUE! | 2021-01-24 | 62 | DONE | ONTIME |  | RFI | RFC | [24.1.21] RFC [11.1.21] Rekom LC OG, kades masih diluar kota [5.1.21] Resubmit eskalasi SITAC [28.12.20] Eskalasi Rejected by ARO, waiting eskalasi submit 30.12.20 [22.12.20] Waiting validasi Kand. B siteforge, submit eskalasi ke ARO, Kandidat B IW Clear [18.12.20] Resubmit kandidat via siteforge [15.12.20] Approval kandidat reject [14.12.20] IW OG done 15 KK, 11 KK 17.12.20 Plan Sabtu SOSWAR | Waiting hasil eskalasi ARO
0230613560231 | 1319301023 | IN20_JB_1199 | GUNUNG KALER TANGERANG | GUNUNG KALER TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027740/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.100917 | 106.371353 | Kp. Serdang RT 010 RW 004, Desa Cipayeh , Kec. Gunung Kaler, Kab Tangerang | JABODETABEK (OUTER) | TANGERANG | BANTEN | 52 | PT. PANEN | Aditya R | H | -6.0982 | 106.3706 | 52 | 48 | 2021-12-01 | 35/1.2 | 2021-12-01 | SST | GF | DONE | DONE | #VALUE! | 2021-03-02 | 99 | DONE | DELAY |  | RFI | RFC | [18.2.21] Rekom Camat Done, waiting APD dan Soil Test Result [8.2.21] Rekom Camat [5.2.21] Approval eskalasi to ARO, Approve ARO Rekom LC OG [1.2.21] Approve by Operator Kand H, Follow Up Panen IW Clear [23.1.21] Validasi by WA kand G [9.1.21] Arahan Huntin baru, assign mitra rehunting kand E [30.12.20] Reject kandidat by Siteforge. Waiting Internal Review [28.12.20] Submit kandidat D dengan JR [22.12.20] Plan Submit Mitra BNP 23.12.20 [17.12.20] Approval kandidat via siteforge [16.12.20] Submit New Kandidat [14.12.20] Kandidat A fail IW soswar tanggal 11.12.20. proses Rehunting plan submit TSSR 16.12.20 IW On Going
0230614440231 | 1263691023 | HUNew_BGR4085-2 | GUNUNG SINDUR BOGOR | GUNUNG SINDUR BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027829/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.37713 | 106.659012 | Kp.Gunung Sindur RT 003 RW 011 Desa Gunung Sindur Kec.Gunung Sindur Kab.Bogor Provinsi Jawa Barat | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | PT. ORLIE INDONESIA | Aditya R | E | -6.3792 | 106.6559 | 52 | 45 | 2021-02-01 | 35/0.3 |  | SST | GF | DONE | DONE | #VALUE! | 2021-03-18 | 115 | DONE | DELAY |  | RFI | RFC | [15.3.21] SOIL Test, rekom Done [9.3.21] eskalasi approve by ARO, Kejar Rekom LC W2 Maret [2.3.21] Eskalasi submit. high price, nego eskalasi [26.2.21] Waiting Mitra submit eskalasi hari ini 26.2.21 [23.1.21] Re-hunting akibat penolakan warga. BA terlampir. [17.2.21] IW minus 1 orang, Plan IW clear 22.2.21 [14.2.21] IW minus 2 orang lagi [6.2.21] IW minus 4 KK, LL lahan kosong berada di luar daerah [1.2.21] Approval kandidat by operator, Follow Up IW [26.1.21] Follow BA tertulis dari pergudangan Sigma Kartika Gunung Sindur hari ini [28.12.20] Reject via siteforge, waiting internal review [28.12.20] Resubmit kandidat B dengan JR [22.12.20] Surat penolakan dari pergudangan, BAN Kandidat A dan B, Follow Up Approval SF [14.12.20] proses Validasi SF Validation to Candidat B 11.12.20 Candidate NY Approve 8.12.20 Submit Validasi 7.12.20 | Rekom LC
0230613640231 | 1263661023 | ZBGR_4610 | GUNUNG SINDUR JAWA BARAT | GUNUNG SINDUR JAWA BARAT | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027748/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.3913 | 106.690697 | Kp. Kemang RT 001/RW 007 Desa Cibinong, Kecamatan Gunung Sindur, Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | PT. ORLIE INDONESIA | Handri P | E | -6.39 | 106.6939 | 52 | 45 | 2020-12-08 | 35/0.3 | 2020-12-08 | SST | GF | DONE | DONE | #VALUE! | 2021-04-05 | 133 | DONE | DELAY |  | RFI | RFC | [30.3.21] Rekom Done [24.3.21] Rekom Camat OG [22.3.21] Realisasi Done, OG rekom LC plan finish 25.3.21 SOIL TEST done request [18.3.21] Approval OK, Follow Up IW dan Rekom LC [3.3.21] input siteforge waiting internal review batch 3 [23.2.21] Hard space, maksimal 25.2.21 submit new kandidat, take over mitra [22.2.21] Submit New Kandidat, Kandidat E NOK Planning. [19.2.21] Soswar kandidat B [16.2.21] Comcase Warga, geser titik kandidat yang sudah pernah diapprove, waiting Soswar Plan 19.2.21 [8.2.21] Rekom Camat [5.2.1] Approve ARO Rekom LC OG [2.2.21] Nego eskalasi SITAC [1.2.21] Approval operator kandidat C [22.1.21] Update status approval ke Planning SF, masih menunggu atasan planning approve [4.1.21] Submit New Kandidat C via siteforge [30.12.20] Kandidat B reject via siteforge. waiting internal review [28.12.20] Validasi via siteforge kandidat B [22.12.20] Takeover, Need New Mitra [14.12.20] Rehunting Kandidat, 16.12.20 submit kandidat IW OG, Renego BAN RF validation Done, Candidat Approve Submit Validasi 7.12.20 | Waiting Update VP, Progres Lapangan Bowplank
0230613710231 | 1319321023 | ZJKT2_5467 | KOSAMBI BANTEN | KOSAMBI BANTEN | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027755/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.076241 | 106.688004 | Kp. Rawa Lindung RT 07/RW 05, Desa Cengklong, Kecamatan Kosambi, Kabupaten Tangerang, Propinsi Banten | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | PT. DATATEL | Aditya R | D | -6.0774 | 106.684 | [5 empty] | SST | GF | 2021-06-18 | 2021-06-18 | 2021-07-18 | 2021-06-21 | 210 | DONE | DELAY |  | RFI | RFC | [4.6.21] Pengajuan email eskalasi ke ARO [28.5.21] IW Clear kandidat D, waiting submit eskalasi SITAC [24.5.21] approval operator kandidat D [5.3.21] Validasi KKOP lewat pak alfian [23.2.21] Submit Kandidat C tower height 42m [11.2.21] Reject via siteforge, waiting internal review [5.2.21] kandidat C Submitted, OG validasi by siteforge [26.1.21] SITAC panti asuhan, surat tanah panti asuhan diminta [22.12.20] BAN 19/tahun, SOSWAR OG [21.12.20] BAN dengan Landlord [14.12.20] Negosiasi by Phone oleh PM Negosiasi harga dengan LL untuk Sewa | Waiting Internal Review | Approval Planning SF, SAR 3 need pak nimesh dan pak kelpa
0230613930231 | 1319351023 | ZJKT2_6111 | KOSAMBI TANGERANG | KOSAMBI TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027777/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.111795 | 106.649533 | Kp Pintu Kapuk Rt.028 Rw.011 Desa Bojong Renged Kecamatan Teluk Naga Kab. Tangerang | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | PT. DWI SAMUDERA RAYA | Aditya R | A | -6.1078 | 106.6466 | 32 |  |  |  |  | SST | GF | DONE | DONE | #VALUE! | 2021-04-12 | 140 | DONE | DELAY |  | RFI | RFC | [30.3.21] Rekom Done [25.3.21] Rekom Lurah OG [22.3.21] Realisasi OG, Plan Rekom LC 26.3.21 [16.3.21] Waiting Catra Update eskalasi SITAC [10.3.21] Nego Eskalasi SITAC [8.3.21] Eskalasi submit by mitra [13.2.21] Harga lurah terlalu tinggi, nego harga lurah [9.2.21] Koordinasi lingkungan dan lurah [4.2.21] IW OG, warga radius clear [1.2.21] Approval kandidat by operator, Follow Up IW [26.1.21] Follow Up Pak Dicky terkait miscomm hasil approval titik dan ketinggian. 32m hanya bisa di titik A [4.1.21] Waiting internal review SF Planning [22.12.20] Tanya Pak alfian soal KKOP dan Follup Approval SF (Pak Dicky) [17.12.20] Submit approval kandidat via siteforge [14.12.20] Proses konfirmasi lahan milik PT. AP Candidate NY Approve Submit Validasi 7.12.20 | Waiting Update VP, Progres Lapangan Bowplank
0230614370231 | 1263681023 | ZJKT2_4127 | LIMO KOTA DEPOK | LIMO KOTA DEPOK | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027822/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.37966 | 106.77532 | Jl. Mushola Darussalam RT. 001 / RW. 011, Kel Meruyung, Kec Limo, Kota Depok, Prov. Jawa barat | JABODETABEK (INNER) | KOTA DEPOK | JAWA BARAT | 42 | PT. DATATEL | Aditya R | E | -6.3784 | 106.7754 | 32 | 30.5 | 2020-12-08 |  |  | SST | GF | 2021-05-17 | 2021-05-17 | 2021-06-16 | 2021-05-31 | 189 | DONE | DELAY |  | RFI | RFC | [27.2.21] Kandidat failed high price [23.2.21] Submit kandidat validasi to RANE [19.2.21] Take over Mitra, submit kandidat 21.2.21 [7.2.21] IW failed [1.2.21] Approval kandidat by operator, Follow Up IW [26.1.21] Follow up titik dengan ketinggian di 42m [22.12.20] Follow Up Approval ke Smarfren [17.12.20] Resubmit kandidat via siteforge [14.12.20] Proses Validasi SF Submit kandidat A 11.12.20 | Re-hunting lahan
0230613590231 | 1263621023 | ZBDG_5616 | PARUNG KUDA SUKABUMI | PARUNG KUDA SUKABUMI | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027743/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.868283 | 106.770666 | Jl. Raya Siliwangi RT 30 RW 12, Desa Sundawenang, Kec. Parung Kuda, Kabupaten Sukabumi | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 52 | PT. DWI SAMUDERA RAYA | Handri P | E | -6.8683 | 106.7685 | 52 |  |  |  |  | SST | GF | #N/A | #N/A | #N/A | 2021-04-19 | 147 | DONE | DELAY |  | RFI | RFC | [24.3.21] Rekom Camat Done [17.3.21] Waiting Rekom LC dan SOIL TEST [8.3.21] Eskalasi approve, IW done [4.3.21] Eskalasi reject, need nego [2.3.21] Approval eskalasi to ARO [22.2.21] IW Clear, Kades dan Camat Clear waiting eskalasi submit [18.2.21] Nego Kades, RT, RW. permintaan tinggi [3.2.21] IW OG [26.1.21] Submit siteforge kandidat, Mitra IW di proses [5.1.21] Resubmit kandidat B [29.12.21] Rehunting kandidat SAR, Kandidat OutSAR Rejected via siteforge [22.12.20] Kandidat A Not Accepted by TBG, Re-Hunting, Ada lahan refrensi dari KADES. Follow Up harga PT DAEHAN [18.12.20] Validasi kandidat via siteforge [17.12.20] Mitra submit kandidat, need check RTRW [15.12.20] Re-hunting lahan [14.12.20] Proses konfirmasi lahan desa, Submit TSSR/Kandidat to PM 15.12.20 [10.12.20] take over BNP ke DSR NY Kandidat | Waiting Update VP, Progres Lapangan Bowplank
0230613830231 | 1319341023 | ZJKT2_6085 | PERIUK KOTA TANGERANG | PERIUK KOTA TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027767/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.16775 | 106.59571 | Perumahan Mutiara Pluit Blok C6 No.38 RT02 RW11 Kelurahan Periuk Kecamatan Periuk Kota Tangerang Provinsi Banten | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 42 | PT. DWI PILAR PRATAMA | Rinaldi | D | -6.1679 | 106.5962 | 42 |  |  |  |  | SST | GF | #N/A | #N/A | #N/A | 2021-12-29 | 401 | DONE |  | #N/A | RFI | RFC | [26.1.21] Hunting di jalan villa mutiara pluit, BA hasil nego dengan developer soal titik kandidat, mencari info lahan sebelah barat NOM [4.1.21] Validasi kandidat A dan B melalui siteforge [30.12.20] Submit JR & TSSR [22.12.20] Takeover, Need New Mitra [14.12.20] Update hasil re-hunting kandidat, 16.12.20 dapat kandidat Candidate NY Approve Submit Validasi 7.12.20 | IW site permanent dan COMBAT. Site permanent rooftop dengan 10m+25m. Paralel nego ke planning
0230613750231 | 1319331023 | ZJKT2_5468 | TIGARAKSA TANGERANG 2 | TIGARAKSA TANGERANG 2 | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027759/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.243617 | 106.478106 | Kp Matagara RT 02 RW 02, Desa Matagara, Kecamatan Tigaraksa, Kabupaten Tangerang | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | PT. ORLIE INDONESIA | Aditya R | D | -6.2441 | 106.4806 | 52 | 40 | 2020-12-08 | 35/0.3 | 2020-12-08 | SST | GF | 2021-07-15 | 2021-07-15 | 2021-08-14 | 2021-07-12 | 231 | DONE | DELAY |  | RFI | RFC | [21.6.21] Approval Siteforge [4.6.21] Submit titik kandidat D ke siteforge [23.5.21] Switch Mitra ke Orlie [4.2.21] Reject via siteforge, waiting internal review [3.2.21] Submitted kandidat to siteforge [2.2.21] New Kandidat submit, need discuss with Planning [26.1.21] Take over mitra [22.12.20] Submit Re-Hunting mitra, Target 24.12.20, paralel Mitra Pengkondisian Kandidat A [19.12.20] Bertemu ketua lingkungan , pembahasan planning soswar [14.12.20] Proses validasi SF, Paralel IW follow up SOSWAR 17.12.20 Submit Validasi 7.12.20 | Waiting Internal Review | Approval Planning SF, SAR 3 need pak nimesh dan pak kelpa
0230613570231 | 1319311023 | IN20_JB_1136 | WALANTAKA KOTA SERANG | WALANTAKA KOTA SERANG | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 027741/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.179163 | 106.226535 | Kp. Kadu Buntung, RT 003/RW 004, Desa Silebu, Kec. Kragilan, Kab Serang | JABODETABEK (OUTER) | KOTA SERANG | BANTEN | 52 | PT. BANJARPASIR NUSA PRATAMA | Aditya R | C | -6.1811 | 106.2268 | 52 | 44 | 2020-12-22 | 35/0.3 | 2020-12-22 | SST | GF | DONE | DONE | #VALUE! | 2021-01-14 | 52 | DONE | ONTIME |  | RFI | RFC | [14.1.21] RFC [5.1.21] Rekom Camat Done. [4.1.21] Rekom LC OG, Plan Rekom Done 8.1.21 [28.12.20] Approval ARO done, Follow Up BNP IW Done [22.12.20] Kandidat approve, plan submit eskalasi 22.12.20 [18.12.20] Approval kandidat via siteforge [17.12.20] Mitra submit new kandidat [14.12.20] Kandidat B, IW failed, plan IW paralel nego kandidat A 16.12.20 IW On Going | Follow Up update VP BNP, Follow Up APD ke Pak Virma
0230560290231 | 1317281023 | ZJKT2_4285 | CIPONDOH KOTA TANGERANG | CIPONDOH KOTA TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 016842/TBG-TB/SMART8/MKT/12/2019 | 2020-11-30 | -6.18155 | 106.6724 | Jl. Tugu Karya 2, Kp. Sambi Doyong, RT 02/01, Kel. Cipondoh Makmur, Kec. Cipondoh, Kota Tangerang, Prov. Banten | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 25 | PT. DWI SAMUDERA RAYA | Handri P |  | -6.1822 | 106.6723 | 32 |  |  |  |  | SST | GF | DONE | DONE | #VALUE! | 2021-03-26 | 116 | DONE | DELAY |  | RFI | RFC | [12.3.21] Antenna Height Approve, Rekom LC OG [10.3.21] Waiting approval to siteforge, By WA done [15.2.21] Need Follow Up Planning validasi antenna [5.2.21] Rekom LC OG, approval eskalasi done [26.1.21] Eskalasi IW [4.1.21] Reject Eskalasi, waiting submit eskalasi mitra 7.1.21 [23.12.20] Eskalasi Mitra NY, Follow Up [20.12.20] Bertemu RT/RW, plan Submit eskalasi 22.12.20 [16.12.20] Propose DSR, Sabtu plan ketemu RT [14.12.20] Follow Negosiasi harga max 200jt 11 Tahun. [8.12.20] Plan hari senin IW ulang, Renego BAN | Aktual Done CME, OG update system
0230615270231 | 1263821023 | ZBGR_4261 | BOGOR UTARA KOTA BOGOR | BOGOR UTARA KOTA BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 028045/TBG-TB/SMART8/MKT/12/2020 | 2020-12-08 | -6.5403 | 106.8149 |  | JABODETABEK (OUTER) | KOTA BOGOR | JAWA BARAT | 42 |  | Rahadian | [10 empty] | #N/A | #N/A | #N/A |  | 661 |  |  | #N/A | DROP | DROP | [21.5.21] Clinic with SF [12.5.21] Submit New Kandidat [11.2.21] Jovis with SF [4.2.21] Kandidat B dan C submitted by mitra, need check material minaret [26.1.21] Datangi developer untuk pengajuan kerja sama menara telekomunikasi [5.1.21] Resubmit siteforge [22.12.20] Mitra submit kandidat baru maksimal 24.12.20 [14.12.20] Plan Submit Kandidat 14.12.20 NY Kandidat | Follow Up by Pak Kamto
0230615380231 | 1263831023 | ZBGR_4605 | CIBUNGBULANG BOGOR 2 | CIBUNGBULANG BOGOR 2 | NEW BUILD | STIP 1 | SMART8 | TB | 2020 | 028056/TBG-TB/SMART8/MKT/12/2020 | 2020-12-08 | -6.585862 | 106.66486 | Jl. Kapten Dasuki Bakri RT 001 RW 01 Cibatok II, Kecamatan Cibungbulang, Kabupaten Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. ORLIE INDONESIA | Handri P | B | -6.586 | 106.6628 | 62 | 55 | 2021-02-03 | 30/0.9 | 2021-02-03 | SST | GF | DONE | DONE | #VALUE! | 2021-03-15 | 97 | DONE | DELAY |  | RFI | RFC | [12.3.21] RFC [7.3.21] waiting soil test and APD [4.3.21] Go Realisasi IW dan Rekom [26.2.21] Issue by LL, solving w1 Maret [21.2.21] Eskalasi approve ARO, realisasi + Rekom LC 14 hari [18.2.21] Submit eskalasi to ARO [15.2.21] Renego eskalasi [8.2.21] Renego eskalasi SITAC [26.1.21] Submit siteforge tinggi 52, GO SITAC di 62m [29.12.20] Validasi via Siteforge 22.12.20, BA IW dijalankan [16.12.20] Mitra submit kandidat [14.12.20] Plan Submit Kandidat 14.12.20 NY Kandidat
0030615460031 | 1129561003 | JAW-JK-TJP-0653 | POLE_KAWASAN_INDUSTRI_RELOCATION | POLE_KAWASAN_INDUSTRI_RELOCATION | NEW MCP NON FO | STIP 1 | XL | TB | 2020 | 028066/TBG-TB/XL/MKT/12/2020 | 2020-12-08 | -6.100736 | 106.715155 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | PT. KARYA LINTAS SEJAHTERA | Aditya R | D | -6.1017 | 106.7157 | 20 | [6 empty] | DONE | DONE | #VALUE! | 2021-01-08 | 31 | DONE | ONTIME |  | RFI | RFC | [4.1.21] IW, Done, rekom LC plan 10.1.21 [24.12.20] Approval kandidat D dan E, KLS Follow Up Need Approval Operator | Follow Up SUPER RFC untuk naik RFC
0230618470231 | 1264091023 | INJB21_0218 | LEUWILIANG BOGOR | LEUWILIANG BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | 2020 |  | 2020-12-30 | -6.582 | 106.6295 | Kp. Banyusuci RT. 004 RW. 004 Desa leuwimekar kec. Leuwiliang kab. Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. ORLIE INDONESIA | Handri P | E | -6.5833 | 106.6354 | 62m | [6 empty] | 2021-08-05 | Agustus | 2021-08-30 | 2021-08-05 | 218 | DONE | DELAY | 218 | RFI | RFC | [15.7.21] IW Done, Rekom waiting 1 week [25.3.21] Rekom Lurah On Going [16.3.21] Approval eskalasi Done, Request Soil done [3.3.21] Nego harga sitac lapangan [23.2.21] Waiting eskalasi submit by mitra, pengajuan geser sedikit 15m to RANE [18.2.21] Submit Kandidat C to Siteforge [11.2.21] Jovis with SF [4.2.21] Kandidat C submitted by mitra OG validation siteforge [26.1.21] Take over mitra [30.12.20] STIP Input, Mitra assignment |  | Re-Hunting kandidat
0230618500231 | 1264121023 | IN20_JB_1421 | PARUNG PANJANG GOROWONG | PARUNG PANJANG GOROWONG | NEW BUILD | STIP 1 | SMART8 | TB | 2020 |  | 2020-12-30 | -6.379 | 106.5548 | Jl. Kp. Lebak Ciung, Rt.14 Rw.01, Desa Gorowong, Kec. Parung Panjang, Kab. Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 62 | PT. ROTUA | Handri P | C | -6.3791 | 106.5547 | 62 | [6 empty] | 2021-05-14 | 2021-05-14 | 2021-06-13 | 2021-05-05 | 126 | DONE | DELAY |  | RFI | RFC | [29.3.21] Rekom Done, Start Gali [17.3.21] Waiting Rekom LC dan SOIL TEST [15.3.21] Approve eskalasi. IW done [12.3.21] Approval SF done [8.3.21] Submit kandidat by siteforge [26.2.21] Kandidat sebelumnya Surat tanah palsu. Submit kandidat baru 26.2.21 ke siteforge [3.2.21] Renego eskalasi SITAC [26.1.21] BAN 20 jt/tahun plan submit eskalasi 26 Jan 21 [19.1.21] Validasi Done Kand A [30.12.20] STIP Input, Mitra assignment | Waiting Update VP, Progres Lapangan Galian OG
0230618480231 | 1264101023 | INJB21_0538 | TENJOLAYA BOGOR | TENJOLAYA BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | 2020 |  | 2020-12-30 | -6.6588 | 106.7141 | Kp. Pasir Gaok RT. 01 RW. 04 Desa. Gunung Malang Kec. Tenjolaya Kab. Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. DATATEL | Handri P | A | -6.6587 | 106.7141 | 52 | 50 | 2021-01-18 | 35/0.3 | 2021-01-19 |  |  | DONE | DONE | #VALUE! | 2021-02-26 | 58 | DONE | ONTIME |  | RFI | RFC | [26.2.21] RFC [23.2.21] Rekom Camat Done, waiting update VP and system [19.2.21] Rekom Lurah Done, Soil Test Done [10.2.21] Eskalasi Approve, Rekom LC OG [3.2.21] Renego eskalasi SITAC [26.1.21] IW OG 18KK dari 22KK, BAN 17jt tahun. Plan submit eskalasi 28 Jan 21 [19.1.21] Validasi Done Kand A [30.12.20] STIP Input, Mitra assignment | [19.1.21] Validasi Done, Kandidat A Approve.
0230618490231 | 1264111023 | HUNew_BDG4716-2 | WARUNG KIARA SUKABUMI | WARUNG KIARA SUKABUMI | NEW BUILD | STIP 1 | SMART8 | TB | 2020 |  | 2020-12-30 | -6.9987 | 106.7177 | Kp. Cilandak RT. 02/04 Desa. Sirnajaya Kec. Warung Kiara Kab. Sukabumi | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | PT. DATATEL | Handri P | B | -7.0008 | 106.718 | 62 | 60.5 | [5 empty] | DONE | DONE | #VALUE! | 2021-03-09 | 69 | DONE | ONTIME |  | RFI | RFC | [3.3.21] Rekom Lurah Camat Done, waiting APD Design. [24.2.21] Realisasi by mitra [21.2.21] Eskalasi approve ARO, realisasi + Rekom LC 14 hari [18.2.21] Submit eskalasi to ARO [10.2.21] Reject eskalasi, Renego BAN [6.2.21] Reject ekalasi [3.2.21] Renego eskalasi SITAC [25.1.21] Validasi Done Kand B, BAN 15 juta/tahun [30.12.20] STIP Input, Mitra assignment
0010622740011 | 1319661001 | TGR238 | BENCONGANKELAPADUA | BENCONGANKELAPADUA | NEW BUILD | STIP 1 | TSEL | TB |  | 030796/TBG-TB/TSEL/MKT/03/2021 | 2021-03-04 | -6.2402 | 106.6012 | Kp Cibogo Kulon RT 001 RW 002, Desa Kelapa Dua, Kecamatan Kelapa Dua, Kab. Tangerang | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 |  | Rinaldi | S | -6.2425 | 106.607 | 20 | [6 empty] | #N/A | #N/A | #N/A | 2021-11-30 | 271 | DONE | DELAY | #N/A | RFI | RFI | [14.6.21] Go SITAC kandidat luar SAR BNP. SST 52m [1.3.21] Pengajuan ke PWU selaku penanggung jawab telekomunikasi Lippo Village [24.2.21] Penawaran ke Lippo Village [23.2.21] Penawaran ke water treatment plant NOK. Waiting marketing LippoKarawaci [22.2.21] Kandidat NOK | Done RFI site COLO
0010622720011 | 1319651001 | RKB069 | CURUGBADAKMAJA | CURUGBADAKMAJA | NEW BUILD | STIP 1 | TSEL | TB |  | 030794/TBG-TB/TSEL/MKT/03/2021 | 2021-03-04 | -6.3446 | 106.3804 | Kp. Ciganjur RT 001 RW 005 Kelurahan Curugbadak Kecamatan Maja Kabupaten Lebak | JABODETABEK (OUTER) | LEBAK | BANTEN | 52 | PT. KARYA LINTAS SEJAHTERA | Aditya R | Q | -6.3455 | 106.3798 | 52m | [6 empty] | DONE | DONE | #VALUE! | 2021-04-15 | 42 | DONE | ONTIME |  | RFI | RFC | [30.3.21] Eskalasi Approve by ARO [22.3.21] Validation OK, IW Clear, pengajuan eskalasi by mitra [18.3.21] Validasi to RANE TSEL Kand Q [9.3.21] Menunggu pihak developer untuk mejawab IW [8.3.21] Menemui pihak developer untuk meminta jawaban atas ijin warga dan juga ijin developer [3.3.21] IW Kurang 15 KK (Warga Cluster Baru) [22.2.21] Kandidat OK by TSEL IW OG
0010622750011 | 1264691001 | CBN436 | CURUGBITUNGNANGGUNG | CURUGBITUNGNANGGUNG | NEW BUILD | STIP 1 | TSEL | TB |  | 030797/TBG-TB/TSEL/MKT/03/2021 | 2021-03-04 | -6.6298 | 106.5421 | Kp. Situhiang RT 001 RW 005 Desa Curugbitung Kecamatan Nanggung Kabupaten Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. BANJARPASIR NUSA PRATAMA | Handri P | V | -6.6285 | 106.5426 | 52m | [6 empty] | DONE | DONE | #VALUE! | 2021-04-14 | 41 | DONE | ONTIME |  | RFI | RFC | [6.4.21] Eskalasi SITAC submit [5.4.21] Kandidat V OK from RANE [26.3.21] Approval kandidat V to RANE [22.3.21] Candidate U OK from planning, IW On Going [19.3.21] Candidate T dan U submit [9.3.21] Re-hunting kandidat. Kandidat Q failed IW [3.3.21] IW kurang 15 KK akibat pergeseran kandidat LP2B. [22.2.21] Kandidat OK by TSEL IW OG
0010622730011 | 1264681001 | SKB204 | PASAR CISAATSKB | PASAR CISAATSKB | NEW BUILD | STIP 1 | TSEL | TB |  | 030795/TBG-TB/TSEL/MKT/03/2021 | 2021-03-04 | -6.9002 | 106.8933 |  | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 52 | PT. BANJARPASIR NUSA PRATAMA | Aditya R | R | -6.9002 | 106.8933 | 52 | [6 empty] | DONE | DONE | #VALUE! | 2021-03-12 | 8 | DONE | ONTIME |  | RFI | RFC | [9.3.21] RFC done, update system [1.3.21] IW Clear, OG Rekom LC [15.2.21] Waiting mitra submit eskalasi
0010622710011 | 1319641001 | SRG269 | PERMANENTCOMBATCIKANDEPERMAI | PERMANENTCOMBATCIKANDEPERMAI | NEW BUILD | STIP 1 | TSEL | TB |  | 030793/TBG-TB/TSEL/MKT/03/2021 | 2021-03-04 | -6.2236 | 106.3451 | Kp. Kalutuk RT 007 RW 003 Desa Cikande Permai Kecamatan Cikande Kabupaten Serang | JABODETABEK (OUTER) | SERANG | BANTEN | 42 | PT. BANJARPASIR NUSA PRATAMA | Aditya R | P | -6.2236 | 106.3451 | 42 | [6 empty] | DONE | DONE | #VALUE! | 2021-03-23 | 19 | DONE | ONTIME |  | RFI | RFC | [15.3.21] SOIL TEST OG, Rekom Done [8.3.21] IW clear, eskalasi approve, go rekom LC [3.3.21] IW kurang warga perumahan [22.2.21] Kandidat OK by TSEL IW OG
0010623880011 | 1265101001 | TGR236 | PERMANENTCMBTLIONAIR | PERMANENTCMBTLIONAIR | NEW BUILD | STIP 1 | TSEL | TB |  | 031056/TBG-TB/TSEL/MKT/03/2021 | 2021-03-18 | -6.1936 | 106.4988 | Ruko Telaga Bestari RT 008 RW 05 Desa Wanakerta, Kecamatan Sindang Jaya, Kabupaten Tangerang | JABODETABEK (OUTER) | TANGERANG | BANTEN |  | PT. ORLIE INDONESIA | Rinaldi | V | -6.1938 | 106.4971 | RT 8 + MT 25 | [6 empty] | 2022-01-28 | #N/A | #N/A |  | 561 |  |  | 316 | SITAC | BAN/BAK | [3.6.21] Submit kandidat V ke pak arsyad OK. Make sure IW dan BAN [28.5.21] IW Failed, 3 KK penolakan, rehunting kandidat [27.3.21] Geser Kandidat, Rehuntinh [22.3.21] IW minus 7 KK [10.3.21] Go SITAC need height 30m. Kandidat P P1 | Rekom Lurah terdelay karena ada provokator. Lahan altirnatif IW OG minus 1 RT, paralel di validasikan
0010623860011 | 1130171001 | JBX306 | STAKALIDERES | STAKALIDERES | NEW BUILD | STIP 1 | TSEL | TB |  | 031054/TBG-TB/TSEL/MKT/03/2021 | 2021-03-18 | -6.1632 | 106.6999 | Kp. Pangkalan RT 005 RW 010, Kel. Semanan, Kec. Kalideres, Jakarta Barat | JABODETABEK (INNER) | KOTA JAKARTA BARAT | DKI JAKARTA | 25 | PT. KARYA LINTAS SEJAHTERA | Aditya R | P | -6.1633 | 106.6998 | 25 | [6 empty] | DONE | DONE | #VALUE! | 2021-03-30 | 12 | DONE | ONTIME |  | RFI | RFC | [10.3.21] Go SITAC need height 25m
0010623840011 | 1265091001 | SKB215 | SUKAJAYASALABINTANA | SUKAJAYASALABINTANA | NEW BUILD | STIP 1 | TSEL | TB |  | 031052/TBG-TB/TSEL/MKT/03/2021 | 2021-03-18 | -6.8957 | 106.9497 | Kp. Nangewer RT 012 RW 005 Desa Sukajaya Kecamatan Sukabumi Kabupaten Sukabumi | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 52 | PT. BANJARPASIR NUSA PRATAMA | Aditya R | S | -6.896 | 106.9481 | 52 | 51 | [5 empty] | 2021-05-15 | 2021-05-15 | 2021-06-14 | 2021-05-03 | 46 | DONE | ONTIME |  | RFI | RFC | [10.3.21] Go SITAC need height 50m. Kandidat P P1
0010624640011 | 1130261001 | JBX304 | MANYARKALIDERES | MANYARKALIDERES | NEW MCP NON FO | STIP 1 | TSEL | TB |  | 031294/TBG-TB/TSEL/MKT/03/2021 | 2021-03-26 | -6.1204 | 106.7145 |  | JABODETABEK (INNER) | KOTA JAKARTA BARAT | DKI JAKARTA |  | PT. KARYA LINTAS SEJAHTERA | Handri P | S | -6.1216 | 106.7127 | 25 | [6 empty] | 2021-06-09 | 2021-06-09 | 2021-07-09 | 2021-06-22 | 88 | DONE | DELAY |  | RFI | RFC | [7.6.21] IW OG, minus 1 KK. Paralel renego harga sewa lahan [2.6.21] Validasi kandidat S [10.3.21] Done DRM, Propose to COLO need strengthening. Check ke ASSET
0010624650011 | 1130271001 | JTX483 | PONDOKRANGGONCIPAYUNG | PONDOKRANGGONCIPAYUNG | NEW MCP NON FO | STIP 1 | TSEL | TB |  | 031295/TBG-TB/TSEL/MKT/03/2021 | 2021-03-26 | -6.3513 | 106.9068 | Jl. Kupu Kupu RT 010 RW 005 Kel. Pondok Ranggon Kec. Cipayung Kota Jakarta Utara | JABODETABEK (INNER) | KOTA JAKARTA TIMUR | DKI JAKARTA |  | PT. KARYA LINTAS SEJAHTERA | Handri P | Q | -6.3516 | 106.9071 | 25 | [6 empty] | 2021-04-08 | 2021-04-08 | 2021-05-08 | 2021-04-22 | 27 | DONE | ONTIME |  | RFI | RFC | [30.3.21] IW OG minus 5 KK [10.3.21] Done DRM, Propose to COLO need strengthening. Check ke ASSET
10626540011 | 1319701001 | TNX324 | NEGLASARINEGLASARI | NEGLASARINEGLASARI | NEW MCP NON FO | STIP 1 | TSEL | TB |  | 031520/TBG-TB/TSEL/MKT/03/2021 | 2021-03-31 | -6.151 | 106.6325 | Jl. Marsekal Surya Darma No.26b, RT.004/RW.002, Neglasari, Kec. Neglasari, Kota Tangerang, Banten 15129 | JABODETABEK (OUTER) | KOTA TANGERANG | BANTEN |  | PT. LINTAS BANYU LESTARI | Aditya R | S | -6.1525 | 106.6324 | 25 | [6 empty] | DONE | DONE | #VALUE! | 2021-04-16 | 16 | DONE | ONTIME |  | RFI | RFC | [9.3.21] IW OG untuk kandidat Q dan R dengan plan IW 42m [1.3.21] Bersurat ke PEMKOT tangerang terkait ketinggian antenna | ISSUE CELLPLAN
0010626550011 | 1319711001 | CPT249 | PARADISESERPONG2 | PARADISESERPONG2 | NEW BUILD | STIP 1 | TSEL | TB |  | 031521/TBG-TB/TSEL/MKT/03/2021 | 2021-03-31 | -6.3539 | 106.7021 | Jl. AMD Bakti Jayapocis RT 08 RW 02 Kel. Bakti Jaya, Kec. Setu, Kota Tangerang Selatan, Provinsi Banten | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN |  | PT. AULIA DANARDANA |  | Q | -6.3541 | 106.7024 | 25 | [6 empty] | 2021-04-15 | 2021-04-15 | 2021-05-15 | 2021-04-29 | 29 | DONE | ONTIME |  | RFI | RFC | [10.3.21] Rehunting, need height 40m, Issue Ketinggian.
0010680100011 | 1321801001 | TNX322 | PASARBARUKARAWACI | PASARBARUKARAWACI | NEW BUILD | STIP 1 | TSEL | TB |  | 036988/TBG-TB/TSEL/MKT/04/2021 | 2021-04-14 | -6.16344 | 106.62673 | Jl. KS Tubun No 30, RT.005 RW. 03 Kelurahan Koang Jaya, Kec. Krawaci, Kota Tangerang, Provinsi Banten | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 42 | PT CATRA MEDIA INDONESIA | Rinaldi | Q | -6.1634 | 106.6267 | 42 | [6 empty] | 2022-01-28 | #N/A | #N/A |  | 534 |  |  | 289 | SITAC | BAN/BAK | [7.6.21] Proses Landclearing, plan SOIL TEST 8.7.21. Rekom Camat NY waiting rekom PUPR | Waiting Disposisi PDAM
0010680090011 | 1271391001 | CKR338 | PERUMAHAN KSB | PERUMAHAN KSB | NEW BUILD | STIP 1 | TSEL | TB |  | 036987/TBG-TB/TSEL/MKT/04/2021 | 2021-04-14 | -6.40208 | 107.11406 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 32 | PT. AULIA DANARDANA | Rahadian | Q | -6.4019 | 107.1144 | [7 empty] | #N/A | #N/A | #N/A |  | 534 |  |  | #N/A | SITAC | SITAC Done | [7.7.21] menunggu BAN dari BPD dan Kades, legal lahan fix lahan desa [6.7.21] Kandidat Q Approve RANE | Waiting Rekom Camat Senin 04.10
0030572280031 | 1127821003 | JAW-JK-TJP-0621 | DUFAN MARINA | Dufan Marina | NEW BUILD | STIP 1 | XL | TB | 2020 | 018413/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.125313 | 106.830387 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | PT. KARYA LINTAS SEJAHTERA | Rinaldi |  |  |  | 20 |  |  |  |  | SST | GF | #N/A | #N/A | #N/A |  | 990 |  |  | #N/A | DROP | DROP | [24.2.21] Follow Up orang PT Ancol untuk diskusi lahan di ancol dibantu Camat Pademangan [15.2.21] Kandidat Rooftop menolak, Re-Hunting [9.2.21] Follow Up titik IW clear pak Magfuri sebelumnya [8.2.21] Pengajuan Surat ke PT Surya Citra Multimedia untuk pengajuan kerjasama [4.2.21] re-hunting sekitar, pengajuan kandidat C (rooftop). Validasi kandidat to pak Budi [3.2.21] Mendatangi hotel discovery
0010680110011 | 1271401001 | CKR330 | PERUMAHANCIBARUSAHJAYA | PERUMAHANCIBARUSAHJAYA | NEW BUILD | STIP 1 | TSEL | TB |  | 036989/TBG-TB/TSEL/MKT/04/2021 | 2021-04-14 | -6.42799 | 107.07734 | Kp Malaka RT 001 RW 006, Desa Cibarusah Kota, Kec. Cibarusah, Kab. Bekasi, Jawa Barat | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | PT. KARYA LINTAS SEJAHTERA | Rahadian | Q | -6.4319 | 107.0789 | [7 empty] | #N/A | #N/A | #N/A | 2021-11-25 | 225 | DONE | DELAY | #N/A | RFI | RFC | [8.7.21] SOIL TEST Done, Rekom LC OG [6.7.21] Eskalasi Done Approve [3.7.21] RANE OK kandidat Q, Submit eskalasi [16.6.21] NOK from Sales, rehunting KLS [27.5.21] Submit kandidat ke pak arsyad, OUTSAR tapi INCELL. Plan submit ke bu nikken untuk dibahas terkait jaraknya [20.4.21] Rehunting kearah incell | Done RFI COMBAT, NY RFC, Rekom Camat W2 Oktober
0230680590231 | 1271491023 | ZBGR_4663 | PAMIJAHAN BOGOR 2 | PAMIJAHAN BOGOR 2 | NEW BUILD | STIP 1 | SMART8 | TB |  | 037047/TBG-TB/SMART8/MKT/04/2021 | 2021-04-19 | -6.646675 | 106.647478 | Kp Tonjong RT 03 RW 03, Kelurahan Cibitung Wetan, Kecamatan Pamijahan, Kabupaten Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. ORLIE INDONESIA | Aditya R | D | -6.6468 | 106.6456 | 52 | [6 empty] | 2021-07-29 | 2021-07-29 | 2021-08-09 | 2021-07-12 | 84 | DONE | ONTIME |  | RFI | RFC
0070681390071 | 1133721007 | 094686R | EX MAHONI SELATAN | EX MAHONI SELATAN | NEW MCP NON FO | STIP 1 | HCPT | PKP |  | 037230/TBG-PKP/HCPT/MKT/04/2021 | 2021-04-28 | -6.1161 | 106.91436 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | PT. KARYA LINTAS SEJAHTERA | Rinaldi | [10 empty] | #N/A | #N/A | #N/A |  | 520 |  |  | #N/A | PRE-SITAC | Rehunting |  | Hard Space, issue di warga dan perangkat lingkungan
0010685800011 | 1321901001 | TNX323 | PASIRJAYAJATIUWUNG | PASIRJAYAJATIUWUNG | NEW BUILD | STIP 1 | TSEL | TB |  | 038350/TBG-TB/TSEL/MKT/06/2021 | 2021-06-22 | -6.1895 | 106.5701 |  | JABODETABEK (OUTER) | KOTA TANGERANG | BANTEN |  |  | Rinaldi | R | -6.1929 | 106.5716 | [7 empty] | 2022-01-28 | #N/A | #N/A |  | 465 |  |  | 220 | PRE-SITAC | Rehunting | [14.6.21] Kandidat luar SAR OK, kandidat jalan BNP [26.5.21] Submit kandidat OUTSAR tapi INCELL. Blm ada kejelasan dari bu Nikken terkait OK atau tidak [8.3.21] Waiting Response PT Gajah Tunggal, Propose Rooftop [1.3.21] Bersurat ke PEMKOT tangerang terkait ketinggian antenna
0010685930011 | 1134141001 | - | ALFAMART PANTJORAN PIK | ALFAMART PANTJORAN PIK | NEW BUILD | STIP 1 | TSEL | PKP |  | 039081/TBG-PKP/TSEL/MKT/06/2021 | 2021-06-25 | -6.08979 | 106.74383 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 6 | PT. NAYAKA | [11 empty] | #N/A | #N/A | #N/A |  | 462 |  |  | #N/A | RFC | CME |  | No Need RFC (No SITAC)
0230686620231 | 1321931023 | ZJKT2_6180 | TANGERANG KOSAMBI | TANGERANG KOSAMBI | NEW BUILD | STIP 1 | SMART8 | TB | 2021 | 039423/TBG-TB/SMART8/MKT/07/2021 | 2021-07-01 10:27 | -6.1022 | 106.664 | Kp Kresek RT 04 RW 07, Desa Rawaburung, Kec. Kosambi, Kab. Tangerang, Banten | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | PT. BANJARPASIR NUSA PRATAMA |  | B | -6.1015 | 106.6643 | 32 | [6 empty] | 2021-08-13 | Agustus | 2021-08-29 | 2021-08-13 | 42.5644 | DONE | ONTIME | 43 | RFI | RFC | [8.7.21] Need Confirmation IW dan BAN kandidat A. JR selesai, siteforge blm ready. Validasi NY
0230686800231 | 1134171023 | ZJKT2_5300 | PKP JAKARTA BARAT CENGKARENG | PKP JAKARTA BARAT CENGKARENG | NEW BUILD | STIP 1 | SMART8 | PKP | 2021 | 039661/TBG-PKP/SMART8/MKT/07/2021 | 2021-07-02 08:43 | -6.1411 | 106.7685 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 32 | PT. KARYA LINTAS SEJAHTERA | Rinaldi |  | -6.1407 | 106.7689 | [7 empty] | #N/A | #N/A | #N/A | 2021-11-30 | 150.6371 | DONE |  | #N/A | RFC | RFC | [8.7.21] Geser titik kandidat, Kandidat rooftop A menolak | Rehunting kandidat alternati untuk rooftop
0230687020231 | 1134221023 | INJB21_0283 | PKP KALI DERES JAKARTA BARAT | PKP KALI DERES JAKARTA BARAT | NEW BUILD | STIP 1 | SMART8 | PKP | 2021 | 039715/TBG-PKP/SMART8/MKT/07/2021 | 2021-07-02 16:16 | -6.11 | 106.7109 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 32 | PT. KARYA LINTAS SEJAHTERA | [11 empty] | 2021-09-08 | September | 2021-09-28 | 2021-08-30 | 58.3221 | DONE |  | 68 | RFI | RFC | [8.7.21] Propose Colo to TBG, paralel hunting 2 kandidat. Siteforge NY Ready
0230686810231 | 1134181023 | INJB21_0272 | PKP JAKARTA BARAT TAMBORA | PKP JAKARTA BARAT TAMBORA | NEW BUILD | STIP 1 | SMART8 | PKP | 2021 | 039662/TBG-PKP/SMART8/MKT/07/2021 | 2021-07-02 08:44 | -6.151 | 106.7958 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 32 | PT. KARYA LINTAS SEJAHTERA | Rinaldi |  | -6.1522 | 106.7956 | [7 empty] | #N/A | #N/A | #N/A | 2021-12-03 | 153.6358 | DONE |  | #N/A | RFC | RFC | [8.7.21] BAN 20jt. Kandidat A IW Potensi tinggi | Rekom Camat Release, Delay CME Comcase penolakan warga. Plan rehunting kandidat
0230687030231 | 1134231023 | HUNew_JKT24157 | PKP PENJARINGAN JAKARTA UTARA | PKP PENJARINGAN JAKARTA UTARA | NEW BUILD | STIP 1 | SMART8 | PKP | 2021 | 039716/TBG-PKP/SMART8/MKT/07/2021 | 2021-07-02 16:16 | -6.1301 | 106.7977 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 32 | PT. KARYA LINTAS SEJAHTERA | Rinaldi |  | -6.13 | 106.7978 | [7 empty] | #N/A | #N/A | #N/A | 2021-12-01 | 151.3221 | DONE |  | #N/A | RFC | RFC | [8.7.21] Makesure BAN. Titik Kandidat A. Siteforge NY Ready
0230687710231 | 1134321023 | ZJKT2_6031 | JAKARTA BARAT CENGKARENG-1 | JAKARTA BARAT CENGKARENG-1 | NEW BUILD | STIP 1 | SMART8 | TB | 2021 | 039819/TBG-TB/SMART8/MKT/07/2021 | 2021-07-06 06:44 | -6.1371 | 106.7488 | Kapuk RT 010 RW 012, Kelurahan Kapuk, Kecamatan Cengkareng, Kota Jakarta Barat | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 32 | PT. KARYA LINTAS SEJAHTERA | Rinaldi | C | -6.1372 | 106.7482 | 25 | [6 empty] | 2021-10-29 | 2021-10-29 | 2021-11-28 | 2021-10-31 | 116.7198 | DONE | DELAY | 115 | RFI | RFC | [8.7.21] Makesure BAN. Titik Kandidat A. Siteforge NY Ready | [14.10] IW Clear, Approval Kandidat masih di bu Reni. Follow Up Approval titik kandidat hari ini sampai clear RF Planning IW OG masih 1 KK yang pendekatan dengan RT RW, paralel hunting kandidat
0230687720231 | 1134331023 | ZJKT2_6428 | JAKARTA BARAT CENGKARENG-2 | JAKARTA BARAT CENGKARENG-2 | NEW BUILD | STIP 1 | SMART8 | TB | 2021 | 039820/TBG-TB/SMART8/MKT/07/2021 | 2021-07-06 06:44 | -6.1344 | 106.7456 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 32 | PT. KARYA LINTAS SEJAHTERA | Rinaldi |  | -6.1341 | 106.7464 | [7 empty] | 2022-01-24 | #N/A | #N/A |  | 450.7198 |  |  | 202 | PRE-SITAC | Approval Operator | [8.7.21] Rehunting, titik kandidat sementara OUTSAR. Siteforge NY Ready | Approval ketinggian antenna
0230687850231 | 1322021023 | ZJKT2_6089 | TANGERANG CIPONDOH | TANGERANG CIPONDOH | NEW BUILD | STIP 1 | SMART8 | TB | 2021 | 039833/TBG-TB/SMART8/MKT/07/2021 | 2021-07-06 06:44 | -6.1988 | 106.6888 | Jalan Kenanga RT 003/RW 001, Kelurahan Kenanga, Kecamatan CIpondoh,Kabupaten Tangerang | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 32 | PT. PAMENGKANG JAGAT ABADI | Rinaldi | P | -6.1974 | 106.686 | 42 | [6 empty] | 2022-01-16 | #N/A | #N/A |  | 450.7197 |  |  | 194 | SITAC | Rekom Lurah Camat | [8.7.21] Rehunting, sebelumnya titik order ke TBG 2020, Hard SITAC | Hard Space, lahan kebanyakan didominasi pabrik
0230687860231 | 1134341023 | ZJKT2_4619 | JAKARTA UTARA PADEMANGAN | JAKARTA UTARA PADEMANGAN | NEW BUILD | STIP 1 | SMART8 | TB | 2021 | 039834/TBG-TB/SMART8/MKT/07/2021 | 2021-07-06 06:44 | -6.1336 | 106.8419 | Pademangan IV GG 28/30, Kelurahan Pademangan Timur, Kecamatan Pademangan, Kota Jakarta Utara | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 32 | PT. KARYA LINTAS SEJAHTERA | Rinaldi | D | -6.1341 | 106.8421 | 25 | [6 empty] | 2021-10-31 | 2021-10-31 | 2021-11-30 | 2021-10-29 | 114.7197 | DONE | DELAY | 117 | RFI | RFC | [8.7.21] Makesure BAN dan Detail bangunan. Titik Kandidat A Rooftop. Siteforge NY Ready | [14.10] Galian done, Rekom Camat NY Release IW OG, SOSWAR 03.10
0230687940231 | 1272131023 | HUNew_BDG5992-2 | SUKABUMI CIKIDANG | SUKABUMI CIKIDANG | NEW BUILD | STIP 1 | SMART8 | TB | 2021 | 039842/TBG-TB/SMART8/MKT/07/2021 | 2021-07-06 06:44 | -6.8768 | 106.6726 | Kp. Simpang RT 002 RW 005, Desa Pangkalan, Kec. Cikidang, Kab Sukabumi | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 72 | PT. BANJARPASIR NUSA PRATAMA |  | B | -6.8822 | 106.6699 | 72 | [6 empty] | 2021-08-31 | Agustus | 2021-09-30 | 2021-09-01 | 56.7197 | DONE | ONTIME | 56 | CME | RFC | [8.7.21] Need Siteforge validation dan Nego BAN. Update IW potensi clear
0230687880231 | 1272121023 | ZBGR_4687 | BOGOR BOJONG GEDE | BOGOR BOJONG GEDE | NEW BUILD | STIP 1 | SMART8 | TB | 2021 | 039836/TBG-TB/SMART8/MKT/07/2021 | 2021-07-06 06:44 | -6.4712 | 106.7957 | Kp Parakan Jati RT 004 RW 004, Desa Susukan, Kecamatan Bojon Geda, Kabupaten Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | PT. LINTAS BANYU LESTARI | Rahadian | B | -6.4704 | 106.7963 | [7 empty] | 2021-08-10 | Agustus | 2021-09-09 | 2021-08-24 | 48.7197 | Done | ONTIME | 35 | RFI | RFC | [8.7.21] Submit kandidat A, BAN 20 jt need nego. Siteforge NY ready
0230688640231 | 1272241023 | ZBGR_4655 | BOGOR SUKARAJA | BOGOR SUKARAJA | NEW BUILD | STIP 1 | SMART8 | TB |  | 040778/TBG-TB/SMART8/MKT/07/2021 | 2021-07-14 06:44 | -6.542636 | 106.82084 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 |  | Rahadian | [10 empty] | #N/A | #N/A | #N/A |  | 442.7197 |  |  | #N/A | PRE-SITAC | Rehunting
0230688650231 | 1272251023 | INJB21_0322 | KARAWANG MAJALAYA | KARAWANG MAJALAYA | NEW BUILD | STIP 1 | SMART8 | TB |  | 040779/TBG-TB/SMART8/MKT/07/2021 | 2021-07-14 06:44 | -6.313947 | 107.35046 | Kp. Wagir II RT 067 RW 06, Desa Bengle, Kec. Majalaya, Kab. Karawang, Jawa Barat | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 42 | PT. ORLIE INDONESIA |  | A | -6.315 | 107.3503 | 42 | [6 empty] | 2021-08-15 | Agustus | 2021-09-14 | 2021-09-01 | 48.7197 | DONE | ONTIME | 32 | RFI | RFC
0010688680011 | 1134381001 | JSX943 | CILANDAKBAWAH | CILANDAKBAWAH | NEW MCP NON FO | STIP 1 | TSEL | TB |  | 040792/TBG-TB/TSEL/MKT/07/2021 | 2021-07-14 06:44 | -6.28701 | 106.80065 | JL. CILANDAK BAWAH RT 010.RW 013 CILANDAK BARAT, CILANDAK, JAKARTA SELATAN | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 25 | PT. KARYA LINTAS SEJAHTERA |  | W | -6.2869 | 106.8007 | 25 | [8 empty] | 1900-01-29 | 2021-07-29 | 14.7197 | DONE | ONTIME |  | RFI | RFC
0010688670011 | 1134371001 | JUX067 | ELANGLAUT | ELANGLAUT | NEW MCP NON FO | STIP 1 | TSEL | TB |  | 040791/TBG-TB/TSEL/MKT/07/2021 | 2021-07-14 06:44 | -6.12779 | 106.74943 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 25 | PT. KARYA LINTAS SEJAHTERA | Rinaldi | [10 empty] | 2021-10-07 | 2021-10-07 | 2021-11-06 | 2021-10-19 | 96.7197 | DONE | DELAY | 85 | RFI | RFC |  | RFC system error
0010690930011 | 1134481001 | JBX309 | GAGASEMANAN | GAGASEMANAN | NEW BUILD | STIP 1 | TSEL | PKP |  | 041580/TBG-PKP/TSEL/MKT/07/2021 | 2021-07-28 | -6.166582 | 106.702146 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 32 | PT. KARYA LINTAS SEJAHTERA | [11 empty] | 2021-08-17 | Agustus | 2021-09-06 | 2021-08-12 | 15 | DONE |  | 20 | RFI | RFC
0010690940011 | 1134491001 | JTX537 | RAYAPONCOL | RAYAPONCOL | NEW BUILD | STIP 1 | TSEL | PKP |  | 041581/TBG-PKP/TSEL/MKT/07/2021 | 2021-07-28 | -6.320899 | 106.870287 |  | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA | 32 | PT. LINTAS BANYU LESTARI | Rahadian | [10 empty] | 2021-10-25 | 2021-10-25 | 2021-11-14 | 2021-10-11 | 75 | DONE |  | 89 | CME | RFC
0010690920011 | 1134471001 | JUX075 | SWASEMBADABARATJAKUT | SWASEMBADABARATJAKUT | NEW BUILD | STIP 1 | TSEL | PKP |  | 041579/TBG-PKP/TSEL/MKT/07/2021 | 2021-07-28 | -6.122359 | 106.888589 | Jl. Swasembada Barat RT 011 RW 013, Kelurahan Kebon Bawang, Kecamatan Tanjung Priok, Kota Jakarta Utara | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 32 | PT. LINTAS BANYU LESTARI | Rinaldi | A | -6.1221 | 106.8887 | 25 | [6 empty] | #N/A | #N/A | #N/A |  | 429 |  |  | #N/A | SITAC | Rekom Lurah Camat |  | Need Rehunting masalah SPL
0230691590231 | 1322071023 | ZJKT_6991 | KOTA TANGERANG CIPONDOH | KOTA TANGERANG CIPONDOH | NEW BUILD | STIP 1 | SMART8 | TB |  | 041752/TBG-TB/SMART8/MKT/08/2021 | 2021-08-05 | -6.17658 | 106.6926 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 32 | PT. CATRA MEDIA INDONESIA | Rinaldi | [10 empty] | #N/A | #N/A | #N/A |  | 421 |  |  |  | DROP | DROP |  | Hold by SF
0230691670231 | 1272421023 | ZBGR_4212 | PKP KAREHKEL BOGOR | PKP KAREHKEL BOGOR | NEW BUILD | STIP 1 | SMART8 | PKP |  | 041786/TBG-PKP/SMART8/MKT/08/2021 | 2021-08-05 | -6.553646 | 106.639913 | Kp. Parung Panjang Lebak RT. 002 RW. 007 Desa Leuwiliang Kecamatan Leuwiliang Kabupaten Bogor Prov. Jawa Barat | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 62 | PT. ORLIE INDONESIA | Rahadian | D | -6.5633 | 106.6333 | 62 | [6 empty] | 2021-10-25 | 2021-10-25 |  | 2021-10-05 | 61 | DONE |  |  | CME | RFC
0030696360031 | 1134551003 | JAW-JK-KSU-1132 | PULAU BIDADARI | PULAU BIDADARI | NEW BUILD | STIP 1 | XL | TB |  | 042492/TBG-TB/XL/MKT/08/2021 | 2021-08-18 | -6.0356 | 106.7468 | [5 empty] | PT. KARYA LINTAS SEJAHTERA | Rinaldi | [10 empty] | #N/A | #N/A | #N/A |  | 408 |  |  |  | DROP | DROP |  | Change Plan from XL
0230700240231 | 1273391023 | HUNew_BGR4379-1 | BOGOR BOJONG GEDE-2 | BOGOR BOJONG GEDE-2 | NEW BUILD | STIP 1 | SMART8 | TB |  | 043103/TBG-TB/SMART8/MKT/08/2021 | 2021-08-26 | -6.46242 | 106.80435 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | PT. TRITAMA AJI LAKSANA | Rahadian | [10 empty] | #N/A | #N/A | #N/A |  | 400 |  |  |  | SITAC | IW On Going |  |  | System Precancel
0230700270231 | 1322371023 | INJB21_0174 | TANGERANG JAYANTI | TANGERANG JAYANTI | NEW BUILD | STIP 1 | SMART8 | TB |  | 043106/TBG-TB/SMART8/MKT/08/2021 | 2021-08-26 | -6.21707 | 106.41086 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | PT. SURYASANTIKA INFRASTURKTUR | Rinaldi | D | -6.2168 | 106.4123 | 42 | [6 empty] | #N/A | #N/A | #N/A | 2021-12-29 | 125 | DONE |  |  | RFI | RFC
0230700230231 | 1322361023 | INJB21_0107 | TANGERANG TELUKNAGA | TANGERANG TELUKNAGA | NEW BUILD | STIP 1 | SMART8 | TB |  | 043102/TBG-TB/SMART8/MKT/08/2021 | 2021-08-26 | -6.06795 | 106.6453 | Kp. Sukadamai RT 06 RW 08, Desa Pangkalan, Kecamatan Teluknaga, Kabupaten Tangerang | JABODETABEK (OUTER) | TANGERANG | BANTEN | 52 | PT. SURYASANTIKA INFRASTURKTUR | Rinaldi | C | -6.0672 | 106.6436 | 52 | [6 empty] | #N/A | #N/A | #N/A | 2021-12-23 | 119 | DONE |  |  | RFI | RFC |  | IW OG, door to door. BAN ke pemilik lahan (corporate
0260703940261 | 1134811026 | JKB-TBG21-0001 | DURI TAMBORA | DURI TAMBORA | NEW BUILD | STIP 1 | TBG | TB |  | 043924/TBG-TB/TBG/MKT/09/2021 | 2021-09-02 | -6.154541 | 106.803271 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 9 | PT. KARYA LINTAS SEJAHTERA | Rinaldi | [10 empty] | #N/A | #N/A | #N/A | 2021-09-30 | 28 | DONE | ONTIME |  | RFI | RFC
0010704590011 | 1322471001 | CLG115 | BENDUNGANCILEGON | BENDUNGANCILEGON | NEW BUILD | STIP 1 | TSEL | TB |  | 044442/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.03402 | 106.05061 | Jl. K. H. Musatmil, Kelurahan Karang Asem, Kecamatan Cibeber, Kota Cilegon | JABODETABEK (OUTER) | KOTA CILEGON | BANTEN | 42 | PT. PAMENGKANG JAGAT ABADI | Rinaldi | S | -6.0365 | 106.0513 | 42 | [6 empty] | #N/A | #N/A | #N/A | 2021-12-01 | 89 | DONE | DELAY |  | RFI | SITAC Done
0010704620011 | 1273681001 | CBN483 | CARINGINBOCIMI | CARINGINBOCIMI | NEW BUILD | STIP 1 | TSEL | TB |  | 044445/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.68864 | 106.82696 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. BANJARPASIR NUSA PRATAMA | Rahadian | [10 empty] | #N/A | #N/A | #N/A |  | 392 |  |  |  | DROP | DROP |  | Propose Drop
0010704500011 | 1273601001 | KRW263 | CIKARANG CILAMAYA WETAN | Cikarang Cilamaya Wetan | NEW BUILD | STIP 1 | TSEL | TB |  | 044433/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.27009 | 107.54675 | Kp. Cimahi RT 010 RW 006 Desa Cikarang, Kecamatan Cilamaya Wetan, Kab. Karawang | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 52 | PT. ORLIE INDONESIA | Rahadian | P | -6.2701 | 107.5468 | 52 | [6 empty] | 2021-10-18 | 2021-10-18 | 2021-11-17 | 2021-10-14 | 41 | DONE | ONTIME |  | RFI | RFC |  | RFC system error
0010704480011 | 1273591001 | KRW262 | CILAMAYA KULONPASIRJAYA | CILAMAYA KULONPASIRJAYA | NEW BUILD | STIP 1 | TSEL | TB |  | 044431/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.19333 | 107.52742 |  | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 52 | PT. ORLIE INDONESIA | Rahadian | P | -6.1928 | 107.5256 | 52 | [6 empty] | #N/A | #N/A | #N/A | 2021-09-30 | 27 | DONE | ONTIME |  | RFI | RFC
0010704490011 | 1322441001 | PDG123 | DESAPANGGUKINGAN | DESAPANGGUKINGAN | NEW BUILD | STIP 1 | TSEL | TB |  | 044432/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.278 | 106.16816 |  | JABODETABEK (OUTER) | PANDEGLANG | BANTEN | 52 | PT. KARYA LINTAS SEJAHTERA | Rinaldi | P | -6.278 | 106.1682 | 52 | [8 empty] | 1900-01-29 | 2021-09-22 | 19 | DONE | ONTIME |  | RFI | RFC
0010704560011 | 1322461001 | RKB078 | JALUPANGMULYA | JALUPANGMULYA | NEW BUILD | STIP 1 | TSEL | TB |  | 044439/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.52753 | 106.22568 |  | JABODETABEK (OUTER) | LEBAK | BANTEN | 62 | PT. KARYA LINTAS SEJAHTERA | Rinaldi | P | -6.5275 | 106.2257 | 62 | [8 empty] | 1900-01-29 | 2021-09-22 | 19 | DONE | ONTIME |  | RFI | RFC
0010704540011 | 1273631001 | KRW252 | KARAWANG BARATMEKARJATI | KARAWANG BARATMEKARJATI | NEW BUILD | STIP 1 | TSEL | TB |  | 044437/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.24426 | 107.29665 | Kp. Secang RT 01 RW 08, Kel.,Mekarjati, Kec. Karawang Barat, Kab. Tangerang | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 52 | PT. ORLIE INDONESIA | Rahadian | S | -6.2446 | 107.2984 | 52 | [6 empty] | 2021-10-15 | 2021-10-15 | 2021-11-14 | 2021-10-10 | 37 | DONE | ONTIME |  | RFI | RFC
0010704610011 | 1322481001 | SRG284 | KAREOJAWILAN | KAREOJAWILAN | NEW BUILD | STIP 1 | TSEL | TB |  | 044444/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.24999 | 106.34715 | Kp. Paya Umbul RT.13/RW 05 Desa Junti, Kec. Jawilan, Kab. Serang | JABODETABEK (OUTER) | SERANG | BANTEN | 52 | PT. TRITAMA AJI LAKSANA | Rinaldi | P | -6.25 | 106.3471 | 52 | [6 empty] | #N/A | #N/A | #N/A | 2021-09-30 | 27 | DONE | ONTIME |  | RFI | RFC
0010704600011 | 1273671001 | BOX048 | MEKARWANGITANAHSEREAL | MEKARWANGITANAHSEREAL | NEW BUILD | STIP 1 | TSEL | TB |  | 044443/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.54738 | 106.7873 | Kp. Situ pete RT. 01/10 Kel. Sukadamai Kec. Tanah Sereal Kota Bogor | JABODETABEK (OUTER) | KOTA BOGOR | JAWA BARAT | 42 | PT. AKSES FEMTO INDONESIA | Rahadian | P | -6.5474 | 106.7873 | 42 | [6 empty] | 2021-10-05 | 2021-10-05 | 2021-11-04 | 2021-10-08 | 35 | DONE | ONTIME |  | CME | RFC
0010704550011 | 1273641001 | CBN471 | PARUNG PANJANGJAGABITA | PARUNG PANJANGJAGABITA | NEW BUILD | STIP 1 | TSEL | TB |  | 044438/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.32951 | 106.51726 | Kp Jawiah RT 02 RW 01 Kelurahan Jagabita, Kecamatan Parung Panjang, Kab Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 62 | PT. BANJARPASIR NUSA PRATAMA | Rahadian | P | -6.3295 | 106.5173 | 62 | [6 empty] | #N/A | #N/A | #N/A | 2021-09-24 | 21 | DONE | ONTIME |  | RFI | RFC
0010704520011 | 1322451001 | TGR433 | RAJEG_TANJAKAN MEKAR | RAJEG_TANJAKAN MEKAR | NEW BUILD | STIP 1 | TSEL | TB |  | 044435/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.10103 | 106.5318 | Kp. Jungkel RT 10 RW 04, Kel. Tanjakan Mekar, Kecamatan Rajeg, Kab. Tangerang | JABODETABEK (OUTER) | TANGERANG | BANTEN | 52 | PT. RAKA MITRA BERSAMA | Rinaldi | P | -6.101 | 106.5318 | 52 | [6 empty] | #N/A | #N/A | #N/A | 2021-10-19 | 46 | DONE | ONTIME |  | CME | RFC |  | Done SITAC, update VP OG, system error
0010704670011 | 1322511001 | TGR542 | RANCAGEDEGUNUNGKALER | RANCAGEDEGUNUNGKALER | NEW BUILD | STIP 1 | TSEL | TB |  | 044450/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.08935 | 106.38714 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | PT. PAMENGKANG JAGAT ABADI | Rinaldi | R | -6.0893 | 106.3871 | 52 | [6 empty] | #N/A | #N/A | #N/A | 2021-09-30 | 27 | DONE | ONTIME |  | RFI | RFC
0010704660011 | 1322501001 | TGR543 | RAYAKRONJOMEKARBARU | RAYAKRONJOMEKARBARU | NEW BUILD | STIP 1 | TSEL | TB |  | 044449/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.04723 | 106.40115 | JL Raya Kronjo – Jenggot RT 005/RW 002 Desa Muncung, Kecamatan Kronjo, Kabupaten Tangerang | JABODETABEK (OUTER) | TANGERANG | BANTEN | 62 | PT. PAMENGKANG JAGAT ABADI | Rinaldi | Q | -6.0472 | 106.4022 | 62 | [6 empty] | #N/A | #N/A | #N/A | 2021-11-08 | 66 | DONE | ONTIME |  | CME | RFC |  | Need Update TBGSys
0010704650011 | 1273701001 | CBN521 | RUMPINTAMANSARI | RUMPINTAMANSARI | NEW BUILD | STIP 1 | TSEL | TB |  | 044448/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.40421 | 106.61632 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | PT. BANJARPASIR NUSA PRATAMA | Rahadian | P | -6.4042 | 106.6163 | 42 | [8 empty] | 1900-01-29 | 2021-09-13 | 10 | DONE | ONTIME |  | RFI | RFC
0010704530011 | 1273621001 | PWK085 | SMKN1DARANGDANPURWAKARTA | SMKN1DARANGDANPURWAKARTA | NEW BUILD | STIP 1 | TSEL | TB |  | 044436/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.73225 | 107.4976 |  | JABAR | PURWAKARTA | JAWA BARAT | 52 | PT. TURANGGA EMPAT TIGA | JABAR | [10 empty] | #N/A | #N/A | #N/A | 2021-10-05 | 32 | DONE |  |  | RFI | RFC |  | JABAR
0010704570011 | 1273651001 | PWK083 | SMKN3SUKATANIPWK | SMKN3SUKATANIPWK | NEW BUILD | STIP 1 | TSEL | TB |  | 044440/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.60919 | 107.39166 |  | JABAR | PURWAKARTA | JAWA BARAT | 52 | PT. TURANGGA EMPAT TIGA | JABAR | P | -6.6092 | 107.3917 | [7 empty] | #N/A | #N/A | #N/A | 2021-10-05 | 32 | DONE |  |  | RFI | RFC |  | JABAR
0010704640011 | 1322491001 | TGR546 | SOLEARTANGERANG | SOLEARTANGERANG | NEW BUILD | STIP 1 | TSEL | TB |  | 044447/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.28988 | 106.4025 | Kp. Sukamanah RT 04 RW 03, Desa Solear, Kecamatan Solear, Kabupaten Tangerang | JABODETABEK (OUTER) | TANGERANG | BANTEN | 52 | PT. RAKA MITRA BERSAMA | Rinaldi | P | -6.2897 | 106.4025 | 52 | [6 empty] | 2021-10-11 | 2021-10-11 | 2021-11-10 | 2021-10-19 | 46 | DONE | ONTIME |  | CME | RFC |  | Dokumen Rekom Camat NY, issue permintaan harga camat
0010704630011 | 1273691001 | PLR012 | SUDAJAYAGIRANGSKB | SUDAJAYAGIRANGSKB | NEW BUILD | STIP 1 | TSEL | TB |  | 044446/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.88618 | 106.94962 | Blok Palasari RT 23 RW 07, Kelurahan Sudajayagirang, kecamatan Sukabumi, Kab. Sukabumi | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 52 | PT. BANJARPASIR NUSA PRATAMA | Rahadian | P | -6.8862 | 106.9496 | 52 | [6 empty] | 2021-10-20 | 2021-10-20 | 2021-11-19 | 2021-10-08 | 35 | DONE | ONTIME |  | RFC | RFC |  | Done SITAC, update VP OG
0010704580011 | 1273661001 | SKB155 | TANJUNGJAMPANGKULON | TANJUNGJAMPANGKULON | NEW BUILD | STIP 1 | TSEL | TB |  | 044441/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -7.24782 | 106.62646 | Kp. Neglababakan RT 06 RW 05, Desa Tanjung, Kecamatan Jampang Kulon, Kabupaten Sukabumi | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 52 | PT. BANJARPASIR NUSA PRATAMA | Rahadian | S | -7.2471 | 106.6245 | 52 | [6 empty] | 2021-10-27 | 2021-10-27 | 2021-11-26 | 2021-10-29 | 56 | DONE | ONTIME |  | RFI | RFC |  | Eskalasi Approve done, OG Rekom
0010704510011 | 1273611001 | KRW256 | TBG KLARI | TBG KLARI | NEW BUILD | STIP 1 | TSEL | TB |  | 044434/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.34738 | 107.35659 | Dusun Kopo RT 008 RW 002 Desa Klari, Kecamatan Klari, Kab Karawang | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 42 | PT. ORLIE INDONESIA | Rahadian | R | -6.3484 | 107.3575 | 42 | [6 empty] | 2021-10-13 | 2021-10-13 | 2021-11-12 | 2021-10-17 | 44 | DONE | ONTIME |  | RFC | RFC
0230707220231 | 1274311023 | IN20_JB_0117 | BOGOR RUMPIN | BOGOR RUMPIN | NEW BUILD | STIP 1 | SMART8 | TB |  | 045936/TBG-TB/SMART8/MKT/09/2021 | 2021-09-14 | -6.383769 | 106.630629 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | PT. TRITAMA AJI LAKSANA | Rahadian | [10 empty] | #N/A | #N/A | #N/A |  | 381 |  |  |  | PRE-SITAC | Hunting |  | KKOP bandara ATANGSANJAYA, need up Clinic | System Precancel
0230708380231 | 1274421023 | ZBGR_4578 | PABUARAN BOJONG GEDE | Pabuaran Bojong Gede | NEW BUILD | STIP 1 | SMART8 | TB |  | 046205/TBG-TB/SMART8/MKT/09/2021 | 2021-09-20 | -6.4554 | 106.79749 | Kp. Pintu Air RT 001 RW 009, Kelurahan Pabuaran, Kecamatan Bojong Gede, Kab. Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | PT. BANJARPASIR NUSA PRATAMA | Rahadian | A | -6.455 | 106.7974 | 42 | [6 empty] | #N/A | #N/A | #N/A | 2021-11-18 | 59 | DONE | ONTIME |  | CME | RFC
0010708690011 | 1274441001 | CBN480 | BANTARSARIRANCABUNGUR | BANTARSARIRANCABUNGUR | NEW BUILD | STIP 1 | TSEL | TB |  | 046309/TBG-TB/TSEL/MKT/09/2021 | 2021-09-21 | -6.5293 | 106.7435 | Jl. Bantarsari RT 01 RW 06, Desa Bantarsari, Kecamatan Rancabungur, Kabupaten Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. BANJARPASIR NUSA PRATAMA | Rahadian | S | 106.7433 | -6.5291 | 42 | [6 empty] | #N/A | #N/A | #N/A | 2021-11-30 | 70 | DONE | ONTIME |  | CME | RFC
0010708710011 | 1274461001 | BOX045 | BUKITCIMANGGUCITY | BUKITCIMANGGUCITY | NEW BUILD | STIP 1 | TSEL | TB |  | 046311/TBG-TB/TSEL/MKT/09/2021 | 2021-09-21 | -6.53534 | 106.78978 | Jalan Raya Kencana RT 05 RW 02, Kelurahan Kencana, Kecamatan Tanah Sereal, Kota Bogor | JABODETABEK (OUTER) | KOTA BOGOR | JAWA BARAT | 42 | PT. TURANGGA EMPAT TIGA | Rahadian | S | -6.5344 | 106.7871 | 42 | [6 empty] | #N/A | #N/A | #N/A | 2021-12-27 | 97 | DONE |  |  | SITAC | SITAC Done |  | Need justifikasi untuk approval kand T
0010708730011 | 1274481001 | CBN500 | CIPEUCANG | CIPEUCANG | NEW BUILD | STIP 1 | TSEL | TB |  | 046313/TBG-TB/TSEL/MKT/09/2021 | 2021-09-21 | -6.41207 | 107.05146 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. BANJARPASIR NUSA PRATAMA | Rahadian | [10 empty] | 2021-10-20 | 2021-10-20 | 2021-11-19 | 2021-10-17 | 26 | DONE | ONTIME |  | RFC | RFC |  | Update RFC on System
0010708700011 | 1274451001 | CKR349 | KARANGANYARBAHAGIA | KARANGANYARBAHAGIA | NEW BUILD | STIP 1 | TSEL | TB |  | 046310/TBG-TB/TSEL/MKT/09/2021 | 2021-09-21 | -6.20118 | 107.18568 | Kp. Kedaung RT 001 RW 005, Desa Karang Anyar, Kecamatan Karang Bahagia, Kab. Bekasi | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 52 | PT. ORLIE INDONESIA | Rahadian | R | -6.2019 | 107.1842 | 52 | [6 empty] | #N/A | #N/A | #N/A | 2021-11-30 | 70 | DONE | ONTIME |  | CME | Rekom Lurah Camat |  |  | NY Validate
0010714710011 | 1275311001 | CKR346 | KARANGSETIAKARANGBAHAGIA | KARANGSETIAKARANGBAHAGIA | NEW BUILD | STIP 1 | TSEL | TB |  | 047730/TBG-TB/TSEL/MKT/10/2021 | 2021-10-25 | -6.21825 | 107.1747 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 52 | PT. AULIA DANARDANA | Rahadian | [10 empty] | 2022-01-25 | #N/A | #N/A |  | 340 |  |  |  | SITAC | IW On Going |  |  | NY Validate
|  | JSX942 | M. KAHFI 3 | MKAHFISRENGSENG | NEW MCP NON FO | STIP 1 | TSEL | PKP |  |  |  | -6.3432 | 106.8173 |  | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 20 | PT. KARYA LINTAS SEJAHTERA | Aditya R |  |  |  | 20 | [6 empty] | 2021-01-20 | 2021-01-20 | 2021-02-19 |  | 0 | DONE |  |  | RFI
0010708680011 | 1134881001 | JTX539 | PERMANENASRAMAHAJI | PERMANENASRAMAHAJI | NEW MCP NON FO | STIP 1 | TSEL | TB |  | 046308/TBG-TB/TSEL/MKT/09/2021 | 2021-09-21 | -6.28582 | 106.88461 |  | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA | 25 | PT. KARYA LINTAS SEJAHTERA | Rahadian | R | -6.2845 | 106.8849 | 25 | [6 empty] | 2022-01-18 | #N/A | #N/A |  | 374 |  |  |  | PRE-SITAC | Rehunting |  | Lahan corporate milik UPT Asrama haji
0010722820011 | 1275731001 | BKX431 | PERMANENCOMBATJAKAPERMAI | PERMANENCOMBATJAKAPERMAI | NEW MCP NON FO | STIP 1 | TSEL | TB |  | 050597/TBG-TB/TSEL/MKT/12/2021 | 2021-12-24 | -6.24522 | 106.97348 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 25 | PT. CATRA MEDIA INDONESIA | Rahadian |  | 106.8849 | [8 empty] | 2022-01-28 | #N/A | #N/A |  | 280 |  |  |  | PRE-SITAC | Rehunting
0010722830011 | 1275741001 | BKX430 | PERMANENCOMBATPERUMPTMBEKASI | PERMANENCOMBATPERUMPTMBEKASI |  | STIP 1 | TSEL | TB |  | 050598/TBG-TB/TSEL/MKT/12/2021 | 2021-12-24 | -6.25363 | 106.97314 | Pondok Jingga, RT.003/RW.013, Kel. Jaka Setia, Kec. Bekasi Selatan, Kota Bekasi, Jawa Barat | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 25 | PT. CATRA MEDIA INDONESIA | Rahadian | R | -6.2535 | 106.9731 | 25 | [6 empty] | 2022-01-17 | #N/A | #N/A |  | 280 |  |  |  | PRE-SITAC | Rehunting
0010714570011 | 1135111001 | JTX541 | PERMANENCOMBATPTPUTIK | PERMANENCOMBATPTPUTIK | NEW MCP NON FO | STIP 1 | TSEL | TB |  | 047716/TBG-TB/TSEL/MKT/10/2021 | 2021-10-25 | -6.18925 | 106.92519 |  | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA | 25 | PT. KARYA LINTAS SEJAHTERA | Rahadian | R | -6.1893 | 106.9252 | 25 | [6 empty] | #N/A | #N/A | #N/A | 2021-11-08 | 14 | DONE | ONTIME |  | CME | RFC |  |  | NY Validate
0010709080011 | 1274531001 | BOX049 | PERMANENCOMBATRAYASEMPLAK | PERMANENCOMBATRAYASEMPLAK | NEW BUILD | STIP 1 | TSEL | TB |  | 046400/TBG-TB/TSEL/MKT/09/2021 | 2021-09-22 | -6.55816 | 106.76346 |  | JABODETABEK (OUTER) | KOTA BOGOR | JAWA BARAT | 42 | PT. TURANGGA EMPAT TIGA | Rahadian | [10 empty] | 2022-02-02 | #N/A | #N/A |  | 373 |  |  |  | PRE-SITAC | Approval Operator
0010709120011 | 1274551001 | CBN623 | PERMANENCOMBATTIRTAWARNARUMPIN | PERMANENCOMBATTIRTAWARNARUMPIN | NEW BUILD | STIP 1 | TSEL | TB |  | 046404/TBG-TB/TSEL/MKT/09/2021 | 2021-09-22 | -6.37718 | 106.63531 | Kp Legok Nyerang RT 002 RW 007 Desa Sukamulya Kecamatan Rumpin, Kab. Rumpin | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | PT. TRITAMA AJI LAKSANA | Rahadian | P | -6.3779 | 106.6368 | 42 | [6 empty] | 2022-01-08 | #N/A | #N/A |  | 373 |  |  |  | PRE-SITAC | Approval Operator
0010709110011 | 1322591001 | TGR555 | PERMANENDANGDANGCISAUK2 | PERMANENDANGDANGCISAUK2 | NEW BUILD | STIP 1 | TSEL | TB |  | 046403/TBG-TB/TSEL/MKT/09/2021 | 2021-09-22 | -6.3567 | 106.62048 | Kp. Dukuh RT 011 RW.004 Desa Dangdang Kecamatan Cisauk Kabupaten Tangerang | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | PT. CATRA MEDIA INDONESIA | Rinaldi | P | -6.3567 | 106.6205 | 42 | [6 empty] | 2021-10-12 | 2021-10-12 | 2021-11-11 | 2021-10-29 | 37 | DONE | ONTIME |  | RFI | RFC
0010709100011 | 1322581001 | TGR553 | PERMANENDRIYACATANIA | PERMANENDRIYACATANIA | NEW BUILD | STIP 1 | TSEL | TB |  | 046402/TBG-TB/TSEL/MKT/09/2021 | 2021-09-22 | -6.27635 | 106.53189 | Kp Panongan RT.01 RW.04, Desa Panongan, Kec. Panongan, Kab. Tangerang | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | PT. CATRA MEDIA INDONESIA | Rinaldi | P | -6.2763 | 106.5319 | 42 | [6 empty] | #N/A | #N/A | #N/A | 2021-11-19 | 58 | DONE | ONTIME |  | CME | RFC
0010714690011 | 1275291001 | CKR364 | PERMANENKAREDOKCIBARUSAH | PERMANENKAREDOKCIBARUSAH | NEW BUILD | STIP 1 | TSEL | TB |  | 047728/TBG-TB/TSEL/MKT/10/2021 | 2021-10-25 | -6.40507 | 107.08378 | Kp. Sampora RT 015 RW 007 Desa Jayamulya, Kec. Serang Baru, Kabupaten Bekasi, Jawa Barat | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | PT. AULIA DANARDANA | Rahadian | P | -6.4051 | 107.0838 | 42 | [6 empty] | #N/A | #N/A | #N/A | 2021-12-27 | 63 | DONE |  |  | SITAC | SITAC Done
0010714680011 | 1275281001 | CBN618 | PERMANENKERTAJAYARUMPIN | PERMANENKERTAJAYARUMPIN | NEW BUILD | STIP 1 | TSEL | TB |  | 047727/TBG-TB/TSEL/MKT/10/2021 | 2021-10-25 | -6.38655 | 106.61019 | Kp. Kemang RT 002/RW 004, Desa Mekarsari, Kecamatan Rumpin, Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | PT. TRITAMA AJI LAKSANA | Rahadian | R | -6.3859 | 106.612 | 42 | [6 empty] | #N/A | #N/A | #N/A | 2021-12-06 | 42 | DONE | ONTIME |  | SITAC | Rekom Lurah Camat |  |  | NY Validate
0010709070011 | 1274521001 | CBN614 | PERMANENLEBAKWANGI2 | PERMANENLEBAKWANGI2 | NEW BUILD | STIP 1 | TSEL | TB |  | 046398/TBG-TB/TSEL/MKT/09/2021 | 2021-09-22 | -6.43032 | 106.54474 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | PT. TRITAMA AJI LAKSANA | Rahadian | [10 empty] | 2022-02-02 | #N/A | #N/A |  | 373 |  |  |  | PRE-SITAC | Approval Operator |  |  | NY Validate
0010722760011 | 1275671001 | CKR366 | PERMANENPERUMPERMATAINDAH | PERMANENPERUMPERMATAINDAH | NEW BUILD | STIP 1 | TSEL | TB |  | 050586/TBG-TB/TSEL/MKT/12/2021 | 2021-11-23 | -6.2515 | 107.2427 | Kampung Baleker RT 004/RW 004 Desa Waringin Jaya Kec. Kedung Waringin Kab. Bekasi | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | PT. ROTUA | Rahadian | S | -6.2515 | 107.2427 | 42 | [6 empty] | 2022-01-15 | #N/A | #N/A |  | 311 |  |  |  | SITAC | IW Clear |  |  | NY Validate
0010709090011 | 1274541001 | CKR368 | PERMANENPERUMSERANGSELALU | PERMANENPERUMSERANGSELALU | NEW BUILD | STIP 1 | TSEL | TB |  | 046401/TBG-TB/TSEL/MKT/09/2021 | 2021-09-22 | -6.39291 | 107.15075 | Kp Karang Sambung RT 008 RW 004 Desa Nagasari, Kec. Serang Baru, Kabupaten Bekasi | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | PT. AULIA DANARDANA | Rahadian | P | -6.3926 | 107.1504 | 42 | [6 empty] | 2021-10-12 | 2021-10-12 | 2021-11-11 | 2021-10-29 | 37 | DONE | ONTIME |  | RFI | RFC
0010719630011 | 1275471001 | CKR367 | PERMANENPTIDEMITSU | PERMANENPTIDEMITSU | NEW BUILD | STIP 1 | TSEL | TB |  | 049332/TBG-TB/TSEL/MKT/11/2021 | 2021-11-23 | -6.3997 | 107.2125 | Kp. Rawadomba RT 013 RW 006 Desa Sukabunga Kec. Bojongmangu, Kabupaten Bekasi, Jawa Barat | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | PT. AULIA DANARDANA | Rahadian | P | -6.3998 | 107.2125 | 42 | [6 empty] | #N/A | #N/A | #N/A | 2021-12-24 | 31 | DONE |  |  | SITAC | SITAC Done |  |  | NY Validate
0010709060011 | 1274511001 | CKR363 | PERMANENRAYAPEBANYURANN | PERMANENRAYAPEBANYURANN | NEW BUILD | STIP 1 | TSEL | TB |  | 046396/TBG-TB/TSEL/MKT/09/2021 | 2021-09-22 | -6.23078 | 107.26785 | Jln Kampung Wate RT 03 RW 04, Desa Karang Mekar. Kecamatan Kedungwaringin, Kab. Bekasi, Jawa Barat | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | PT. TURANGGA EMPAT TIGA | Rahadian | R | -6.2305 | 107.2652 | 42 | [6 empty] | #N/A | #N/A | #N/A | 2021-12-06 | 75 | DONE | ONTIME |  | SITAC | Rekom Lurah Camat |  |  | NY Validate
0030705690031 | 1274061003 | JAW-JB-CKR-0068 | Pondok Ungu Permai Relocation | Pondok Ungu Permai Relocation | NEW BUILD | STIP 1 | XL | TB |  | 045223/TBG-TB/XL/MKT/09/2021 | 2021-09-08 | -6.179669 | 107.012981 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 32 | PT. CATRA MEDIA INDONESIA | Rahadian | [10 empty] | 2022-02-07 | #N/A | #N/A |  | 387 |  |  |  | SITAC | IW On Going
0010708720011 | 1274471001 | CKR360 | TELAGAMURNICIKARANGBARAT | TELAGAMURNICIKARANGBARAT | NEW BUILD | STIP 1 | TSEL | TB |  | 046312/TBG-TB/TSEL/MKT/09/2021 | 2021-09-21 | -6.24663 | 107.1228 | Jln Kampung Sri Bodas RT 03 RW 09 Desa Telaga Murni, Kecamatan Cikarang Barat, Kab. Bekasi | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 52 | PT. ABBASY | Rahadian | R | -6.2487 | 107.1262 | 52 | [6 empty] | 2022-01-16 | #N/A | #N/A |  | 374 |  |  |  | SITAC | Rekom Lurah Camat |  |  | NY Validate
0010714700011 | 1275301001 | CKR361 | WALUYACIKARANGUTARA | WALUYACIKARANGUTARA | NEW BUILD | STIP 1 | TSEL | TB |  | 047729/TBG-TB/TSEL/MKT/10/2021 | 2021-10-25 | -6.25926 | 107.1906 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | PT. ABBASY | Rahadian | [10 empty] | 2022-02-08 | #N/A | #N/A |  | 340 |  |  |  | SITAC | IW On Going |  | Lahan corporate milik PT Bumi Cipta Lestari | NY Validate
0230707930231 | 1274391023 | INBGR4334-3 | PAMIJAHAN BOGOR 3 | Pamijahan Bogor 3 | NEW BUILD | STIP 1 | SMART8 | TB |  | 046160/TBG-TB/SMART8/MKT/09/2021 | 2021-09-20 | -6.60809 | 106.6679 | Kp. Cimayang Asem RT 06 RW 02, Desa Cimayang, Kecamatan Pamijahan, Kabupaten Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. DATATEL | Rahadian | C | -6.6088 | 106.6656 | 52 | [6 empty] | #N/A | #N/A | #N/A | 2021-12-09 | 80 | DONE | ONTIME |  | SITAC | IW Clear |  | Submit eskalasi SITAC 14.10
0230707770231 | 1322571023 | INJB21_0244 | TANGERANG LEGOK | TANGERANG LEGOK | NEW BUILD | STIP 1 | SMART8 | TB |  | 046144/TBG-TB/SMART8/MKT/09/2021 | 2021-09-20 | -6.30039 | 106.585 | Kp. Bojong Indah RT.03/02 Desa kemuning kec. Legok, Kab Tangerang, Banten | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | PT. BANJARPASIR NUSA PRATAMA | Rinaldi | E | -6.3053 | 106.5811 | 32 | [6 empty] | 2022-01-14 | #N/A | #N/A |  | 375 |  |  |  | SITAC | IW Clear |  | KKOP bandara | Justifikasi Report,
0230707780231 | 1274361023 | ZBGR_4576 | BOGOR SUKARAJA 2 | BOGOR SUKARAJA 2 | NEW BUILD | STIP 1 | SMART8 | TB |  | 046145/TBG-TB/SMART8/MKT/09/2021 | 2021-09-20 | -6.518757 | 106.843372 | Kp. Babakan Rawahaur RT 03 RW 05, Desa Sentul, Kec. Babakan, Kab. Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | PT. DWI PILAR PRATAMA | Rahadian | A | -6.5183 | 106.8459 | 42 | [6 empty] | #N/A | #N/A | #N/A | 2021-12-27 | 98 | DONE |  |  | SITAC | SITAC Done |  | Validasi OG
0260713990261 | 1135101026 | JKS-TBG21-0001 | RAGUNANRAYA | RAGUNANRAYA | NEW BUILD | STIP 1 | TBG | TB | 047620/TBG-TB/TBG/MKT/10/2021 | 047620/TBG-TB/TBG/MKT/10/2021 | 2021-10-19 | -6.282181 | 106.83391 |  | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 32 | [12 empty] | #N/A | #N/A | #N/A | 2021-12-23 | 65 | DONE |  |  | RFC | RFC
0030712640031 | 1135001003 | JAW-JK-CKG-0743 | JAW-JK-CKG-0743 | RAYA BOGOR RELOCATION | NEW BUILD | STIP 1 | XL | PKP |  | 047275/TBG-PKP/XL/MKT/10/2021 | 2021-10-08 | -6.34322 | 106.869 |  | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA | 25 | [12 empty] | #N/A | #N/A | #N/A | 2021-11-19 | 42 | DONE |  |  | RFC | RFC
0010714820011 | 1135191001 | JBX313 | RELOCKOSAMBIBARU | RELOCKOSAMBIBARU | NEW MCP NON FO | STIP 1 | TSEL | PKP |  | 047746/TBG-PKP/TSEL/MKT/10/2021 | 2021-10-26 | -6.17858 | 106.7166 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 25 | PT. KARYA LINTAS SEJAHTERA |  | B | -6.1786 | 106.7166 | 25 | [6 empty] | #N/A | #N/A | #N/A | 2021-11-03 | 8 | DONE |  |  | RFI | RFC
0040714980041 | 1275381004 | 03SUK682 | UBRUG_WARUNGKIARA_SUK | UBRUG_WARUNGKIARA_SUK | NEW BUILD | STIP 1 | ISAT | TB |  | 048048/TBG-TB/ISAT/MKT/10/2021 | 2021-10-29 | -6.953746 | 106.748922 | Kp. Cicatih RT. 05 RW 05 Desa. Cimanggu Kec. Cikembar Kab. Sukabumi | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 42 | PT. DATATEL | Rahadian | D | -6.9574 | 106.7579 | 62 | [6 empty] | #N/A | #N/A | #N/A | 2021-12-31 | 63 | DONE |  |  | SITAC | IW On Going
0040714960041 | 1275361004 | 03CKR841 | CILANGKARA_SERANGBARU_CKR | CILANGKARA_SERANGBARU_CKR | NEW BUILD | STIP 1 | ISAT | TB |  | 048046/TBG-TB/ISAT/MKT/10/2021 | 2021-10-29 | -6.395015 | 107.148203 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 52 | [16 empty] | 336 |  |  |  | DROP | Drop
0040714990041 | 1275391004 | 03SUK700 | KARANGMEKAR_CIMANGGU_SUK | KARANGMEKAR_CIMANGGU_SUK | NEW BUILD | STIP 1 | ISAT | TB |  | 048049/TBG-TB/ISAT/MKT/10/2021 | 2021-10-29 | -7.244779 | 106.650542 | Kp Batununggul RT 03/RW 02, Desa Karangmekar, Kecamatan Cimanggu, Kab. Sukabumi, Jawa Barat | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | PT. DATATEL | Rahadian | B | -7.2455 | 106.6518 | 62 | [9 empty] | 2021-11-30 | 32 | DONE | ONTIME |  | CME
0040714970041 | 1275371004 | 03SUK692 | TEGALBULEUD_TEGALBULEUD_SUK | TEGALBULEUD_TEGALBULEUD_SUK | NEW BUILD | STIP 1 | ISAT | TB |  | 048047/TBG-TB/ISAT/MKT/10/2021 | 2021-10-29 | -7.41698 | 106.783271 |  | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 52 | PT. ORLIE INDONESIA | Rahadian | A | -7.417 | 106.7817 | 52 | [9 empty] | 2021-11-30 | 32 | DONE | ONTIME |  | CME
0230720970231 | 1275521023 | INBDG4152-3 | SUKABUMI CARINGIN | SUKABUMI CARINGIN | NEW BUILD | STIP 1 | SMART8 | TB |  | 050288/TBG-TB/SMART8/MKT/12/2021 | 2021-12-16 | -6.851537 | 106.884227 | KP. CIHEULAGIRANG RT 007 RW 003, DESA SUKAMULYA, KEC. CARINGIN, KAB. SUKABUMI | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | PT. ORLIE INDONESIA | Rahadian | A | -6.8507 | 106.8847 | 62 | [6 empty] | 2022-01-13 |  |  |  | 288 |  |  |  | PRE-SITAC | Approval Operator
0230721390231 | 1322631023 | INJB21_0327 | SERANG CARENANG | SERANG CARENANG | NEW BUILD | STIP 1 | SMART8 | TB |  | 050330/TBG-TB/SMART8/MKT/12/2021 | 2021-12-16 | -6.09652 | 106.305026 | Kp Tegalsere RT 26/RW 04, Desa Walikukun, Kecamatan Carenang, Kab. Serang | JABODETABEK (OUTER) | SERANG | BANTEN | 52 | PT. KARYA LINTAS SEJAHTERA | Rinaldi | A | -6.0974 | 106.3047 | 52 | [6 empty] | 2022-01-13 |  |  |  | 288 |  |  |  | PRE-SITAC | Approval Operator
0230721630231 | 1275581023 | HUNew_BDG4854-1 | SUKABUMI KADUDAMPIT | SUKABUMI KADUDAMPIT | NEW BUILD | STIP 1 | SMART8 | TB |  | 050354/TBG-TB/SMART8/MKT/12/2021 | 2021-12-16 | -6.855159 | 106.924334 |  | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 52 | PT. ORLIE INDONESIA | Rahadian | [14 empty] | 288 |  |  |  | PRE-SITAC | Hunting
0230721360231 | 1275561023 | INBGR4075-2 | BOGOR CIBUNGBULANG | BOGOR CIBUNGBULANG | NEW BUILD | STIP 1 | SMART8 | TB |  | 050327/TBG-TB/SMART8/MKT/12/2021 | 2021-12-16 | -6.580568 | 106.668079 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PT. BANJARPASIR NUSA PRATAMA | Rahadian | [14 empty] | 288 |  |  |  | PRE-SITAC | Approval Operator
0070723080071 | 1322661007 | 104671 | PKP TANGERANG 104671 | PKP TANGERANG 104671 | NEW BUILD | STIP 1 | HCPT | PKP |  | 050625/TBG-PKP/HCPT/MKT/12/2021 | 2021-12-28 | -6.226200 | 106.606000 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | [17 empty] | 276
0070723110071 | 1135891007 | 91488 | PKP JAKARTA UTARA 91488 | PKP JAKARTA UTARA 91488 | NEW BUILD | STIP 1 | HCPT | PKP |  | 050633/TBG-PKP/HCPT/MKT/12/2021 | 2021-12-28 | -6.134200 | 106.833800 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | [17 empty] | 276
0010722750011 | 1135821001 | JTX643 | AGUNGSEDAYUJAKUT | AGUNGSEDAYUJAKUT | NEW BUILD | STIP 1 | TSEL | TB |  | 050585/TBG-TB/TSEL/MKT/12/2021 | 2021-12-23 | -6.16529 | 106.925 |  | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA | 35 | [16 empty] | 281
0040719590041 | 1135421004 | 01JKU809 | GABUS_TELUKGONG_JKU | GABUS_TELUKGONG_JKU | NEW MCP NON FO | STIP 1 | ISAT | PKP |  | 049327/TBG-PKP/ISAT/MKT/11/2021 | 2021-11-22 | -6.13295 | 106.78006 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | [16 empty] | 312
0010722500011 | 1322641001 | CPT250 | PERMANENCOMBATLIVINGWORLD | PERMANENCOMBATLIVINGWORLD | NEW BUILD | STIP 1 | TSEL | TB |  | 050560/TBG-TB/TSEL/MKT/12/2021 | 2021-12-23 | -6.24345 | 106.655 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 42 | [16 empty] | 281
0010722490011 | 1135811001 | JBX310 | KINTAMANITIMUR | KINTAMANITIMUR | NEW BUILD | STIP 1 | TSEL | TB |  | 050559/TBG-TB/TSEL/MKT/12/2021 | 2021-12-23 | -6.14877 | 106.71375 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 32 | [16 empty] | 281
Formulas:
SOW Year = [STIP Date]
Aging SLA = DAYS(Table13[[#This Row],[RFC Projection]],Table13[[#This Row],[STIP Date]])

## Validasi TSEL
Site ID Operator | Site Name TBG | Regional | Residence | Province | Longitude NOM | Latitude NOM | Cand | Longitude Candidat | Latitude Candidate | Propose Tower Height | Remarks
| KOSAMBI KRESEK | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | -6.1786 | 106.7169 | B | 106.7167 | -6.1786 | 20
[7 empty] | C | 106.7173 | -6.1787 | 20
[7 empty] | D | 106.7162 | -6.1779 | 20
[7 empty] | E | 106.7157 | -6.1782 | 20
[7 empty] | F | 106.7156 | -6.1779 | 20
SKB204 | PASAR CISAATSKB | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | -6.9031 | 106.8935 | P | 106.8932 | -6.9027 | 52
[7 empty] | Q | 106.8937 | -6.9019 | 52
[7 empty] | R | 106.8933 | -6.9002 | 52
RKB069 | CURUGBADAKMAJA | JABODETABEK (OUTER) | LEBAK | BANTEN | -6.344 | 106.3808 | P | 106.3804 | -6.3446 | 52 | IW Failed
[7 empty] | Q | 106.3798 | -6.3455 | 52 | OK
CBN436 | CURUGBITUNGNANGGUNG | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.344 | 106.3808 | P | 106.5421 | -6.6298 | 52 | Lahan LP2B, tidak bisa digunakan untuk pembangunan
[7 empty] | Q | 106.5419 | -6.6289 | 52 | IW Failed
[7 empty] | R | 106.5416 | -6.6311 | 52 | DRM NOK
[7 empty] | S | 106.5429 | -6.6282 | 52 | IW Failed
[7 empty] | T | 106.5434 | -6.6276 | 52 | NOK (19.03.21), Kontur tanah rendah
[7 empty] | U | 106.5405 | -6.6289 | 52 | IW Failed, Penolakan warga Luar Radius
[7 empty] | V | 106.5426 | -6.6285 | 52 | Need Approval
SRG269 | PERMANENTCOMBATCIKANDEPERMAI | JABODETABEK (OUTER) | SERANG | BANTEN | -6.2237 | 106.3456 | P | 106.3451 | -6.2236 | 42
[7 empty] | Q | 106.347 | -6.2223 | 42
TNX324 | NEGLASARINEGLASARI | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | -6.151 | 106.6325 | P | 106.6356 | -6.152 | RT 12m + MT20m | NOK DRM
[7 empty] | Q | 106.6322 | -6.1509 | 32m | Issue Legalitas Lahan
[7 empty] | R | 106.6321 | -6.1527 | RT 8m + MT 20m | Issue Legalitas Lahan, IW Failed
[7 empty] | S | 106.6324 | -6.1525 | Monopole 25m | Need Approval
TNX323 | PASIRJAYAJATIUWUNG | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | -6.1895 | 106.5701 | P | 106.5698 | -6.1894 | 20
[7 empty] | Q | 106.5698 | -6.1894 | 20
TGR238 | BENCONGANKELAPADUA | JABODETABEK (OUTER) | TANGERANG | BANTEN | -6.2392 | 106.6021 | P | 106.6039 | -6.2403 | 25 | Lahan internal PWU
[7 empty] | Q | 106.6012 | -6.2402 | 32
[7 empty] | R | 106.6079 | -6.2419 | 42
[7 empty] | S | 106.607 | -6.2425 | 42
JBX304 | MANYARKALIDERES | JABODETABEK (INNER) | KOTA JAKARTA TIMUR | DKI JAKARTA | -6.1204 | 106.7145 | P | 106.7154 | -6.1203 | MCP 20 | Existing TBG
[7 empty] | Q | 106.7144 | -6.1204 | MCP 25 | Kandidat hasil Join Survey, Penolakan dari RT dan RW
[7 empty] | R | 106.7155 | -6.1196 | MCP 25 | Tidak sesuai skema TBG, penolakan warga
[7 empty] | S | 106.7127 | -6.1216 | MCP 25 | OK | Lahan di dalam gang sempit, CME erection manual
JBX306 | STAKALIDERES | JABODETABEK (INNER) | KOTA JAKARTA TIMUR | DKI JAKARTA | -6.1632 | 106.6999 | P | 106.6998 | -6.1633 | MCP 20m | OK DRM, MCP 25m
JTX483 | PONDOKRANGGONCIPAYUNG | JABODETABEK (INNER) | KOTA JAKARTA BARAT | DKI JAKARTA | -6.3513 | 106.9068 | P | 106.9073 | -6.35 | MCP 20m | Existing TBG
[5 empty] | -6.3513 | 106.9068 | Q | 106.9071 | -6.3516
TGR236 | PERMANENTCMBTLIONAIR | JABODETABEK (OUTER) | TANGERANG | BANTEN | -6.1936 | 106.4988 | P | 106.4987 | -6.1936 | RT 8 + MT 25m | IW failed penolakan warga
[7 empty] | Q | 106.4984 | -6.194 | Monopole 32m | IW failed, Penolakan warga Luar Radius (Cluster)
[7 empty] | R | 106.498 | -6.1937 | RT 8 + MT 25m | Ada penolakan dari pihak pengontrak ruko
[7 empty] | S | 106.4992 | -6.1958 | SST 42m | NOK
[7 empty] | T | 106.4954 | -6.1941 | SST 42m | NOK
[7 empty] | U | 106.4992 | -6.1938 | RT 7m + MT 25m | OK, IW Failed : penolakan 3 KK
[7 empty] | V | 106.4971 | -6.1938 | RT 7m + MT 25m | Need Approval
CPT249 | PARADISESERPONG2 | JABODETABEK (OUTER) | KOTA TANGERANG SELATAN | BANTEN | -6.3539 | 106.7021 | P | 106.7024 | -6.3541 | Propose Colo MCP 20 | NOK DRM
[7 empty] | Q | 106.7024 | -6.3541 | Monopole 25m | Need Approval
SKB215 | SUKAJAYASALABINTANA | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | -6.8957 | 106.9497 | P | 106.9504 | -6.8957 | SST 52m
[7 empty] | Q | 106.9498 | -6.8965 | SST 52m
[7 empty] | R | 106.9494 | -6.8981 | SST 62m
[7 empty] | S | 106.9481 | -6.896 | SST 52m | OK
SKB896 | GUNUNGJAYACISAAT | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | -6.8797 | 106.9049 | P | 106.906 | -6.8792 | SST 52m | Lahan LP2B
[7 empty] | Q | 106.9055 | -6.8766 | SST 52m | Legalitas lahan
[7 empty] | R | 106.903 | -6.8761 | SST 52m | NOK
[7 empty] | S | 106.9052 | -6.8768 | SST 52m
[7 empty] | T | 106.906 | -6.8792 | SST 52m
[7 empty] | U | 106.9079 | -6.8787
[7 empty] | V | 106.9038 | -6.8808
[7 empty] | W | 106.9028 | -6.8747
[7 empty] | X | 107.9033 | -6.8751
CKR338 | PERUMAHAN KSB | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 107.1141 | -6.4007 | P | 107.1141 | -6.4021 | SST 32 | OK, IW Failed
[7 empty] | R | 107.1145 | -6.4044 | SST 32 | Kandidat Terlalu Jauh
[7 empty] | S | 107.1144 | -6.4031 | SST 32 | Kandidat Terlalu Jauh
TNX322 | PASARBARUKARAWACI | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 106.6229 | -6.1656 | P | 106.6279 | -6.1633 | SST 42 | NOK
[7 empty] | Q | 106.6267 | -6.1634 | SST 42 | Failed
[7 empty] | S | 106.6231 | -6.1683 | SST 42 | OK
CKR330 | PERUMAHANCIBARUSAHJAYA | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 107.077 | -6.429 | P | 107.0773 | -6.428 | MCP 20 | NOK
[7 empty] | Q | 107.0788 | -6.4317 | SST 42 | OK RANE 30.6.21
[7 empty] | R | 107.0803 | -6.432 | SST 42 | Terlalu Jauh, Kurang Grid
[7 empty] | S | 107.0838 | -6.43 | SST 42 | NOK
[7 empty] | T | 107.0831 | -6.4299 | SST 42 | NOK
[7 empty] | U | 107.0835 | -6.4292 | SST 42 | NOK
JUX067 | ELANGLAUT | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 106.7496 | -6.1282 | P | 106.7984 | -6.2867 | MCP 25 | OK DRM, IW Failed. Penolakan dari pabrik
[7 empty] | Q | 106.7492 | -6.1303 | MCP 25 | NOK, kurang Grid
[7 empty] | R | 106.7494 | -6.1278 | MCP 25 | OK RANE
JSX943 | CILANDAKBAWAH | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 106.7992 | -6.2866 | P | 106.7508 | -6.1294 | MCP 25 | NOK
[7 empty] | Q | 106.8029 | -6.2865 | MCP 25 | NOK, Terlalu Jauh dari NOM
[7 empty] | R | 106.7996 | -6.2849 | MCP 25 | NOK, Near Existing
[7 empty] | S | 106.8014 | -6.2872 | MCP 25 | Kandidat OK (Jovis) IW Failed
[7 empty] | T | 106.8022 | -6.2871 | MCP 25 | NOK
[7 empty] | U | 106.8019 | -6.2879 | MCP 25 | NOK
[7 empty] | V | 106.8005 | -6.2853 | MCP 25 | OK 30.06, Failed IW
[7 empty] | W | 106.8007 | -6.287 | MCP 25 | OK, IW Failed
JUX075 | SWASEMBADABARATJAKUT | JABODETABEK (INNER) |  |  | 106.8886 | -6.1224 | P | 106.8887 | -6.122 | MCP 25
[7 empty] | Q | 106.8891 | -6.1217 | RT 15 + Pole 15
JBX309 | GAGASEMANAN | JABODETABEK (INNER) |  |  | 106.7021 | -6.1666 | P | 106.701 | -6.1672 | MCP 25
[7 empty] | Q | 106.701 | -6.1668 | MCP 25
JTX537 | RAYAPONCOL | JABODETABEK (INNER) |  |  | 106.8703 | -6.3209 | P | 106.8705 | -6.3204 | MCP 25
[7 empty] | Q | 106.8708 | -6.3197 | SST 32
[7 empty] | R | 106.8711 | -6.3227 | SST 32
[7 empty] | S | 106.8703 | -6.32 | SST 32
| DURIUTARA2 | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 106.8033 | -6.1545 | P | 106.8043 | -6.1546 | MCP 25
[7 empty] | Q | 106.8037 | -6.1541 | RT 12m + POLE 6m
[7 empty] | R | 106.8041 | -6.1546 | MCP 25
[7 empty] | S | 106.8044 | -6.1544 | RT 18m + POLE 6m
BOX048 | MEKARWANGITANAHSEREAL | JABODETABEK (OUTER) | KOTA BOGOR | JAWA BARAT | 106.7876 | -6.5448 | P | 106.7873 | -6.5474
CBN471 | PARUNG PANJANGJAGABITA | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 106.5181 | -6.3295 | P | 106.5173 | -6.3295 | SST 62m | Cand P, Priority 1
[7 empty] | Q | 106.5174 | -6.3284 | SST 62m | Cand Q, Priority 2
[7 empty] | R | 106.5204 | -6.3301 | SST 62m | Cand R, NOK
TGR543 | RAYAKRONJOMEKARBARU | JABODETABEK (OUTER) | TANGERANG | BANTEN | 106.4009 | -6.0472 | P | 106.4012 | -6.0472 |  | Cand P, Priority 1
[7 empty] | Q | 106.4022 | -6.0472 |  | Cand Q, Priority 2
[7 empty] | R | 106.4034 | -6.0479 |  | Cand R, NOK
SRG284 | KAREOJAWILAN | JABODETABEK (OUTER) | SERANG | BANTEN | 106.3469 | -6.2508 | P | 106.3471 | -6.25 |  | Cand P, Priority 1
[7 empty] | Q | 106.3472 | -6.249 |  | Cand Q, Priority 2
[7 empty] | R | 106.3474 | -6.2483 |  | Cand R, Priority 3
PDG123 | DESAPANGGUKINGAN | JABODETABEK (OUTER) | PANDEGLANG | BANTEN | 106.1688 | -6.277 | P | 106.1682 | -6.278 | SST 52m | OK, GO SITAC
RKB078 | JALUPANGMULYA | JABODETABEK (OUTER) | LEBAK | BANTEN | 106.2256 | -6.5278 | P | 106.2257 | -6.5275 | SST 52m | OK, GO SITAC
JTX539 | PERMANENASRAMAHAJI | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA |  |  | P | 106.8846 | -6.2858 | MCP 25m
[7 empty] | Q | 106.8849 | -6.2845 | MCP 25m
TGR542 | RANCAGEDEGUNUNGKALER | JABODETABEK (OUTER) | TANGERANG | BANTEN | 106.3876 | -6.0904 | P | 106.3884 | -6.0896 |  | Cand P, Priority 2
[7 empty] | Q | 106.3885 | -6.0907 |  | Cand Q, NOK
[7 empty] | R | 106.3871 | -6.0893 |  | Cand R, Priority 1
KRW252 | KARAWANG BARATMEKARJATI | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 107.2965 | -6.2447 | P | 107.2955 | -6.2471 | SST 52m | Cand P, NOK
[7 empty] | Q | 107.2952 | -6.2462 | SST 52m | Cand Q, NOK
[7 empty] | R | 107.2966 | -6.2443 | SST 52m | Cand R, Priority 1
[7 empty] | S | 107.2984 | -6.2446 | SST 52m | OK, DRM 15.09
[7 empty] | T | 107.2984 | -6.2446 | SST 52m
KRW256 | KLARI | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 107.3558 | -6.3477 | P | 107.3566 | -6.3474 | SST 42m | Cand P, Priority 1
[7 empty] | Q | 107.3574 | -6.3472 | SST 42m | Cand Q, Priority 2
[7 empty] | R | 107.3575 | -6.3484 | SST 42m
[7 empty] | S | 107.3574 | -6.3486 | SST 42m | Cand R, Priority 3
KRW262 | CILAMAYA KULONPASIRJAYA | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 107.5264 | -6.1922 | P | 107.5256 | -6.1928 | SST 52m | Cand P, Priority 2
[7 empty] | Q | 107.5274 | -6.1933 | SST 52m | Cand Q, Priority 1
KRW263 | Cikarang Cilamaya Wetan | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 107.5464 | -6.2701 | P | 107.5468 | -6.2701 | SST 52m | Cand P, Priority 1
[7 empty] | Q | 107.5478 | -6.2708 | SST 52m | Cand Q, Priority 2
CBN521 | RUMPINTAMANSARI | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 106.6172 | -6.4037 | P | 106.6163 | -6.4042 | SST 42m | Cand P, Priority 1
[7 empty] | Q | 106.6164 | -6.4035 | SST 42m | Cand Q, Priority 2
PWK083 | SMKN3SUKATANIPWK | JABAR | PURWAKARTA | JAWA BARAT | 107.3922 | -6.6093 | P | 107.3917 | -6.6092 | SST 52m | Cand P, Priority 1
[7 empty] | Q | 107.3896 | -6.6098 | SST 52m | Cand Q, Priority 2
[7 empty] | R | 107.3925 | -6.6076 | SST 52m | Cand R, NOK
PWK085 | SMKN1DARANGDANPURWAKARTA | JABAR | PURWAKARTA | JAWA BARAT | 107.4985 | -6.7294 | P | 107.5017 | -6.734 | SST 52m | Cand P, NOK
[7 empty] | Q | 107.4976 | -6.7322 | SST 52m | Cand Q, Priority 1
[7 empty] | R | 107.4973 | -6.7312 | SST 52m | Cand R, Priority 2
[7 empty] | S | 107.4966 | -6.7308 | SST 52m | Cand S, Priority 3
[7 empty] | T | 107.4964 | -6.7309 | SST 52m | OK
SKB155 | TANJUNGJAMPANGKULON | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 106.625 | -7.2472 | P | 106.6265 | -7.2478 | SST 52m | Cand P, Priority 1
[7 empty] | Q | 106.6242 | -7.2455 | SST 52m | Cand Q, NOK
[7 empty] | R | 106.6221 | -7.247 | SST 52m | Cand R, NOK
[7 empty] | S | 106.6245 | -7.2471 | SST 52m | Cand S, OK
CLG115 | BENDUNGANCILEGON | JABODETABEK (OUTER) | KOTA CILEGON | BANTEN | 106.0506 | -6.0346 | P | 106.0506 | -6.034 | SST 42m | Cand P, Priority 1
[7 empty] | Q | 106.0494 | -6.0346 | SST 42m | Cand Q, NOK
[7 empty] | R | 106.05 | -6.036 | SST 42m | Kand R OK RTPE, Penolakan 6KK warga rebahan
[7 empty] | S | 106.0513 | -6.0365 | SST 42m | Need Review
TGR433 | RAJEG_TANJAKAN MEKAR | JABODETABEK (OUTER) | TANGERANG | BANTEN | 106.5317 | -6.1009 | P | 106.5318 | -6.101 | SST 52m | Cand P, Priority 1
[7 empty] | Q | 106.5322 | -6.1019 | SST 52m | Cand Q, NOK
TGR546 | SOLEARTANGERANG | JABODETABEK (OUTER) | TANGERANG | BANTEN | 106.4028 | -6.2901 | P | 106.4025 | -6.2899 | SST 52m | Cand P, Priority 1
[7 empty] | Q | 106.4035 | -6.2896 | SST 52m | Cand Q, Priority 2
PLR012 | SUDAJAYAGIRANGSKB | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 106.9498 | -6.8856 | P | 106.9496 | -6.8862 | SST 52m | Cand P, OK
CBN483 | CARINGINBOCIMI | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 106.8283 | -6.6881 | P | 106.827 | -6.6886 | SST 52m | Cand P, Priority 1
[7 empty] | Q | 106.8288 | -6.6888 | SST 52m | Cand Q, Priority 2
[7 empty] | R | 106.9496 | -6.8862 | SST 52m | Cand R, NOK
BOX045 | BUKITCIMANGGUCITY | JABODETABEK (OUTER) | KOTA BOGOR | JAWA BARAT | 106.7892 | -6.5359 | A | 106.7897 | -6.535 | SST 42m | OK, IW Failed
[7 empty] | B | 106.7882 | -6.535 | SST 42m | OK, IW Failed, Penolakan dari RT dan RW
[7 empty] | C | 106.7884 | -6.5336 | SST 42m | NOK RANE, Too FAR
[7 empty] | D | 106.7908 | -6.5358 | SST 42m | Need Re-Review
[7 empty] | P | 106.7898 | -6.5353 | SST 42m | OK, IW Failed
[7 empty] | Q | 106.7854 | -6.541 | SST 42m | NOK RANE, Too FAR
[7 empty] | R | 106.7876 | -6.5347 | SST 42m | IW Failed di ketinggian 42 (6KK)
[7 empty] | S | 106.7871 | -6.5344 | SST 42m | NOK RANE, Too FAR
[7 empty] | T | 106.7905 | -6.5343 | SST 42m | Need Review
[7 empty] | U | 106. 79103 | -6.536 | SST 42m | Need Review
CBN500 | CIPEUCANG | JABODETABEK (OUTER) | BOGOR | JAWA BARAT |  |  | P | 107.0515 | -6.4121 |  | OK, Priority 1
[7 empty] | Q | 107.0511 | -6.4109 |  | OK, Priority 2
[7 empty] | R | 107.0494 | -6.4131 |  | NOK
CKR346 | KARANGSETIAKARANGBAHAGIA | JABODETABEK (OUTER) | BEKASI | JAWA BARAT |  |  | P | 107.1697 | -6.2149 | SST 52m | NOK, need rehunting Near NOM propose COMBAT 42m
[7 empty] | Q | 107.1747 | -6.2183 | SST 52m | OK RTPE, Failed IW, akses ke site blocking developer
[7 empty] | R | 107.1821 | -6.2187 | SST 52m | Need Review
[7 empty] | S | 107.1793 | -6.2241 | SST 52m | Need Review
CKR349 | KARANGANYARBAHAGIA | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 107.1857 | -6.2012 | P | 107.1857 | -6.2012 | SST 52m | OK
[7 empty] | Q | 107.1886 | -6.2016 | SST 52m | NOK RANE, DRM 15.09
[7 empty] | S | 107.187 | -6.202 | SST 52m | Failed. IW issue di warga cluster
[7 empty] | R | 107.1842 | -6.2019 | SST 52m | Need Review RTPE
CKR360 | TELAGAMURNICIKARANGBARAT | JABODETABEK (OUTER) | BEKASI | JAWA BARAT |  |  | P | 107.1228 | -6.2466 |  | OK, Solusi COMBAT 42m
[7 empty] | Q | 107.1263 | -6.249 |  | Need Review RTPE
[7 empty] | R | 107.1262 | -6.2487 |  | Need Review RTPE
CKR361 | WALUYACIKARANGUTARA | JABODETABEK (OUTER) | BEKASI | JAWA BARAT |  |  | P | 107.1902 | -6.2623 |  | NOK, Propose lahan masjid INCELL
[7 empty] | Q | 107.1904 | -6.2619 |  | NOK, Propose lahan masjid INCELL
[7 empty] | R | 107.1881 | -6.2619 |  | NOK, Propose lahan masjid INCELL
[7 empty] | S | 107.1906 | -6.2593 | SST 52m | Need Review, Jarak ke NOM 230m titik INCELL
CBN480 | BANTARSARIRANCABUNGUR | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 106.7434 | -6.5294 | P | 106.7435 | -6.5293 | SST 52m | OK, P1
[7 empty] | Q | 106.7433 | -6.5291 | SST 52m | NOK
[7 empty] | R | 106.7451 | 6.5292 | SST 52m | NOK
[7 empty] | S | 106.7433 | -6.5291 | SST 52m | Need Review
TGR555 | PERMANENDANGDANGCISAUK2 | JABODETABEK (OUTER) | TANGERANG | BANTEN | 106.6203 | -6.3564 | P | 106.6205 | -6.3567
CKR363 | PERMANENRAYAPEBANYURANN | JABODETABEK (OUTER) | BEKASI | JAWA BARAT |  |  |  | 107.2678 | -6.2308 |  | IW Failed
[8 empty] | 107.2668 | -6.2348 |  | Too Far From NOM
[8 empty] | 107.2652 | -6.2305 |  | Need Review RTPE
CBN623 | PERMANENCOMBATTIRTAWARNARUMPIN | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 106.6353 | -6.3772 | P | 106.6353 | -6.3772 |  | Penolakan warga terkait akses lahan
[7 empty] | Q | 106.6368 | -6.3779 |  | Need Review
JTX541 | PERMANENCOMBATPTPUTIK | JABODETABEK (INNER) | JAKARTA TIMUR | DKI JAKARTA |  |  |  | 106.9279 | -6.1883 |  | NOK RTPE DRM 16.09
[8 empty] | 106.9236 | -6.1894 |  | NOK RTPE DRM 18.09
[8 empty] | 106.9252 | -6.1893 |  | Need Review
TGR553 | PERMANENDRIYACATANIA
CKR367 | PERMANENPTIDEMITSU | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 107.2125 | -6.3997 | P | 107.2125 | -6.3998 |  | Need Review RTPE
[7 empty] | Q | 107.2047 | -6.4012 | SST 42m | NOK RTPE
BOX049 | PERMANENCOMBATRAYASEMPLAK | JABODETABEK (OUTER) | KOTA BOGOR | JAWA BARAT | 106.7628 | -6.5591 | P | 106.7635 | -6.5582 | SST 42m | OK RTPE DRM 19.09. IW Failed penolakan warga cluster
[7 empty] | Q | 106.7646 | -6.561 | SST 42m
[7 empty] | R | 106.7625 | -6.5553 | SST 42m | Need Review
[7 empty] | S | 106.7648 | -6.5598 | SST 42m | Need Review RTPE
CKR364 | PERMANENKAREDOKCIBARUSAH | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 107.0838 | -6.4051 | P | -6.4051 | 107.0838 | SST 42m | Titik OK, Plan RF 41m
CKR368 | PERMANENPERUMSERANGSELALU
CBN618 | PERMANENKERTAJAYARUMPIN | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 106.6114 | -6.38541 | P | 106.6121 | -6.3875 | SST 42m | NOK RTPE DRM 16.09
[7 empty] | Q | 106.6102 | -6.3865 | SST 42m | OK RTPE, Failed IW
[7 empty] | R | 106.612 | -6.3859 | SST 42m | Need Review RTPE
CBN614 | PERMANENLEBAKWANGI2 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 106.5447 | -6.4303 | P | 106.5447 | -6.4303 | SST 42m | IW Failed
[7 empty] | Q | 106.5457 | -6.4326 | SST 42m | NOK, titik kurang optimal untuk antenna
[7 empty] | R | 106.5455 | -6.4288 | SST 42m | NOK
[7 empty] | S | 106.5432 | -6.4318 | SST 42m | Need Review RTPE
CBN620 | PERMANENBOJONGKONENGKM0 | JABODETABEK (INNER) | BOGOR | JAWA BARAT
CBN480 | BANTARSARIRANCABUNGUR | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 106.7434 | -6.5294 | P | 106.7435 | -6.5293 | SST 52m | OK, P1. IW Failed, Penolakan Warga
[7 empty] | Q | 106.7433 | -6.5291 | SST 52m | NOK
[7 empty] | R | 106.7451 | 6.5292 | SST 52m | NOK
[7 empty] | S | 106.7433 | -6.5291 | SST 52m | OK, Lanjut sitac
CKR366 | PERMANENPERUMPERMATAINDAH | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 107.2427 | -6.2515 | P | 107.2359 | -6.2506 | SST 42m | NOK
[7 empty] | Q | 107.2354 | -6.2504 | SST 42m | NOK
[7 empty] | R | 107.2356 | -6.2526 | SST 42m | NOK
[7 empty] | S | 107.2427 | -6.2515 | SST 42m | Need Review RTPE
BKX430 | PERMANENCOMBATPERUMPTMBEKASI | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 106.971 | -6.2552 | P | 106.9717 | -6.2547 | MCP 25m | IW Failed, Penolakan warga arah selatan
[7 empty] | Q | 106. 97254 | -6.2515 | MCP 25m | Need Review RTPE
[8 empty] | 106.9731 | -6.2536 | MCP 25m
BKX431 | PERMANENCOMBATJAKAPERMAI | JABODETABEK (INNER) | KOTA BEKASI | JAWA BARAT | 106.9732 | -6.2446 | P | 106.9736 | -6.245 | SST 42m | NOK
[7 empty] | Q | 106.9748 | -6.2419 | MCP 25m | NOK
[7 empty] | R | 106.9735 | -6.2452 | MCP 25m | Need Review RTPE

## Kandidat Tracker
SONum | Site ID | Site ID Operator | Site Name TBG | Site Name Operator | Operator ID | Regional | Residence | Province | Latitude NOM | Longitude NOM | Tower Height (PI) | RF LOI | MW LOI | SAR | Cand | Longitude Candidat | Latitude Candidate | Propose Tower Height | RF Plan | Submit RNP Date | MW Plan | Submit TNP Date | Distance to NOM | Tower Type | Field Type | Status SITAC | Remark SITAC | Evidence | Aging | RF Validate | RF Remarks | RF Date | TX Validate | Diameter | TX Remarks | TX Date
0230613560231 | 1319301023 | IN20_JB_1199 | GUNUNG KALER TANGERANG | GUNUNG KALER TANGERANG | SMART8 | JABODETABEK (OUTER) | TANGERANG | BANTEN | -6.100917 | 106.371353 | 52 | 43 | 30 | 150 | A | 106.3711 | -6.099 | 42m | [5 empty] | SST | GF | IW Not Clear |  | Yes
[15 empty] | B | 106.3727 | -6.1011 | 52m | 43 |  | 30 |  | 115 | SST | GF | IW Not Clear |  | Yes |  | OK |  | 2020-12-02 | OK | 0.3 |  | 2020-12-08
[15 empty] | C | 106.3732 | -6.1014 | 42m | 40 | 2020-12-17 | 30 | 2020-12-17 | 213 | SST | GF | IW Clear | Propose 42 untuk menghindari penolakan warga, BA Penolakan terlampir | Yes
[15 empty] | D | 106.3719 | -6.1039 | 52m | 43 | 2020-12-28 | 30 | 2020-12-28 | 335.8 | SST | GF | IW Clear | JR Terlampir |  |  |  | Reject Kandidat
[15 empty] | E | 106.367 | -6.0964 | 52m | 43
[15 empty] | F | 106.3684 | -6.0963 | 52m | 43 | [11 empty] | Waitig Internal Review, Siteforge Reject
[15 empty] | G | 106.367 | -6.0964 | 52m | 43
[15 empty] | H | 106.3706 | -6.0982 | 52m | 43 | 2021-01-26 | 30 | 2021-01-26 | 310.08 | SST | GF |  |  |  |  | OK | Antenna 48m |  | OK | 0.3
0230613570231 | 1319311023 | IN20_JB_1136 | WALANTAKA KOTA SERANG | WALANTAKA KOTA SERANG | SMART8 | JABODETABEK (OUTER) | KOTA SERANG | BANTEN | -6.179163 | 106.226535 | 52 | 44 | 30 | 250 | A | 106.2268 | -6.1811 | 52m | 43 | 2020-12-02 | 30 | 2020-12-02 | 214 | SST | GF | Penolakan LL |  |  |  | Feasible | Backup for P1 | 2020-12-02
[15 empty] | B | 106.2278 | -6.18 | 52m | 43 | 2020-12-02 | 30 | 2020-12-02 | 166 | SST | GF | IW Not Clear |  |  |  | Feasible | P1 | 2020-12-02
[15 empty] | C | 106.2268 | -6.1811 | 52m | 43 | 2020-12-17 | 30 | 2020-12-17 | 221.6 | SST | GF | IW Clear | Geser Kandidat untuk menghindari Warga Sepadan tower yang menolak. BA Terlampir | Yes |  | Feasible |  | 2020-12-22 | 34m | 0.3 |  | 2020-12-22
|  | ZBDG_5616 | PARUNG KUDA SUKABUMI | PARUNG KUDA SUKABUMI | SMART8 | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | -6.868283 | 106.770666 | 52 | 50 | 32 | 250 | B | 106.7679 | -6.8647 | 52m | 50
0230613590231 | 1263621023 | [13 empty] | C | 106.7698 | -6.8675 | 52m | 50 | 2021-01-26 |  |  | 133.95 | SST | GF
[15 empty] | D | 106.7693 | -6.8674 | 52m | 50 | 2021-02-02 | 30 | 2021-02-02 | 180.55 | SST | GF
[15 empty] | E | 106.7685 | -6.8683 |  |  | 2021-03-01 |  |  | 234.71
0230613620231 | 1263641023 | IN20_JB_0812 | CITEUREUP BOGOR 2 | CITEUREUP BOGOR 2 | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.526776 | 106.907988 | 52 | 43 | 40 | 150 | A | 106.9073 | -6.5271 | 52m | 43 | 2020-12-02 | 40 | 2020-12-02 | 91 | SST | GF | IW Clear | Eskalasi done submit |  |  | Feasible | Backup candidate | 2020-12-02 | 47m | 0.3
[15 empty] | B | 106.908 | -6.5268 | 52m | 43 | 2020-12-02 | 40 | 2020-12-02 | 14 | SST | GF | IW Not Clear |  |  |  | Feasible | P1 | 2020-12-02
0230613630231 | 1263651023 | ZBGR_4588 | CIBUNGBULANG BOGOR | CIBUNGBULANG BOGOR | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.61969 | 106.65947 | 52 | 49 | 30 | 150 | A | 106.6586 | -6.6185 | 52m | 49 | 2020-12-07 | 30 | 2020-12-07 | 160 | SST | GF |  |  |  |  | Feasible | Backup candidate B | 2020-12-07 | 35m | 0.3
[15 empty] | B | 106.6585 | -6.6182 | 52m | 49 | 2020-12-07 | 30 | 2020-12-07 | 193 | SST | GF |  |  |  |  | Feasible |  | 2020-12-07 | 35m | 0.3
[15 empty] | C | 106.6591 | -6.6189 | 52m | 49 | 2021-01-05 | 30 | 2021-01-05 | 99m | SST | GF
[15 empty] | D | 106.6586 | -6.6203 | 52m | 49 | 2021-03-17 | 30 | 2021-03-17 | 111.84 | SST | GF
[15 empty] | E | 106.6593 | -6.6189 | 52m | 49 | 2021-06-16 |  | 2021-06-16 | 90.7
[15 empty] | F | 106.6601 | -6.6231 | 62m | 59 | 2021-08-18 |  | 2021-06-16 | 381.34 | SST
[15 empty] | G | 106.6605 | -6.6228 | 72m | 59 | 2021-08-18 |  | 2021-06-16 | 360.34 | SST
0230613640231 | 1263661023 | ZBGR_4610 | GUNUNG SINDUR JAWA BARAT | GUNUNG SINDUR JAWA BARAT | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.3913 | 106.690697 | 42 | 35 | 26 | 150 | A | [11 empty] | Near Existing |  |  | Feasible
[15 empty] | B | [11 empty] | BAN too High |  |  | Feasible
[15 empty] | C | [11 empty] | IW Failed
[15 empty] | D | 106.6934 | -6.3916 | 52m | 45 | 2020-12-31 |  |  | 304.6 | SST | GF
[15 empty] | E | 106.6939 | -6.39 | 52m | 45 | 2021-03-01 |  |  | 387.6 | SST | GF
0230613710231 | 1319321023 | ZJKT2_5467 | KOSAMBI BANTEN | KOSAMBI BANTEN | SMART8 | JABODETABEK (OUTER) | TANGERANG | BANTEN | -6.076241 | 106.688004 | 42 | 35 | 30 | 150 | A | 106.6856 | -6.0759 | 42m | 35 | 2020-12-17 | 30 | 2020-12-17 | 273m | SST | GF |  |  |  |  | NOK | Too FAR
[15 empty] | B | 106.6853 | -6.0757 | 42m | 35 | [10 empty] | NOK | Need Antenna Height 45
[15 empty] | C | 106.6851 | -6.0776 | 42m | 40.5 | 2021-02-10 |  | 2021-02-10 | 358m | SST | GF |  |  |  |  | OK | OK
[15 empty] | D | 106.684 | -6.0774 | 42m | 40.5 | 2021-05-10 |  | 2021-05-10 | 459m | SST | GF
0230613750231 | 1319331023 | ZJKT2_5468 | TIGARAKSA TANGERANG 2 | TIGARAKSA TANGERANG 2 | SMART8 | JABODETABEK (OUTER) | TANGERANG | BANTEN | -6.243617 | 106.478106 | 42 | 39 | 30 | 150 | A | 106.475 | -6.2459 | 42m | 39 | 2020-12-07 | 30 | 2020-12-07 | 430 | SST | GF | IW OG |  |  |  | Feasible | Considering JR, Height needed 40m | 2020-12-07 | 35m | 0.3
[15 empty] | B | 106.474 | -6.24 | 42 | 39 | 2021-02-02 |  |  | 699.99 | SST | GF
[15 empty] | C | 106.4744 | -6.2487 | 52 | 49 | 2021-02-02 |  |  | 602.47 | SST | GF
[15 empty] | D | 106.4806 | -6.2441 | 52 | 44 | 2021-06-14 |  |  | 276.78 | SST
0230613770231 | 1263671023 | ZJKT2_5926 | BEKASI UTARA KOTA BEKASI | BEKASI UTARA KOTA BEKASI | SMART8 | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | -6.222518 | 107.009133 | 42 | 35 | 30 | 150 | A | 107.0088 | -6.2246 | 42m | 35 | 2020-12-29 |  | 2020-12-29 | 232m | SST | GF
[15 empty] | C | 107.0075 | -6.2249 | 52m | 45 | 2021-05-21 |  |  | 324m
0230613830231 | 1319341023 | ZJKT2_6085 | PERIUK KOTA TANGERANG | PERIUK KOTA TANGERANG | SMART8 | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | -6.16775 | 106.59571 | 42 | 35 | 30 | 150 | A | 106.596 | -6.1682 | 42m | 35 | 2021-01-04 |  | 2021-01-04 | 56m
[15 empty] | Alt 1 (B) | 106.5959 | -6.171 | 42m | 35 | 2021-01-04 |  | 2021-01-04 | 363.10m
0230613930231 | 1319351023 | ZJKT2_6111 | KOSAMBI TANGERANG | KOSAMBI TANGERANG | SMART8 | JABODETABEK (OUTER) | TANGERANG | BANTEN | -6.111795 | 106.649533 | 42 | 35 | 30 | 150 | A | 106.6466 | -6.1078 | 32 | 35 | 2020-12-17 |  |  | 547 | SST | GF
[15 empty] | B | 106.646 | -6.1097 | 25 | 30 | 2020-12-17 |  |  | 375 | SST | GF
0230614370231 | 1263681023 | ZJKT2_4127 | LIMO KOTA DEPOK | LIMO KOTA DEPOK | SMART8 | JABODETABEK (INNER) | KOTA DEPOK | JAWA BARAT | -6.3797 | 106.77532 | 42 | 35 | 30 | 150 | A | 106.7776 | -6.3802 | 32 | 30 | 2020-12-17 |  | 2020-12-17 |  | Camouflage | GF
[15 empty] | B | 106.7758 | -6.3796
[15 empty] | C | 106.7741 | -6.3788 | 32 | 30 | 2021-03-24 |  | 2021-03-24 | 167.48 | Camouflage | GF
[15 empty] | D | 106.7754 | -6.3784 | 32 | 30 | 2021-03-24 |  | 2021-03-24 | 134.71 | Camouflage | GF
[15 empty] | E | 106.7755 | -6.3784 | 32 | 30 | 2021-04-23 |  | 2021-04-23 | 146.48 | Camouflage | GF
[15 empty] | F | 106.7754 | -6.3784
0230614440231 | 1263691023 | HUNew_BGR4085-2 | GUNUNG SINDUR BOGOR | GUNUNG SINDUR BOGOR | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.37713 | 106.659012 | 42 |  |  |  | B | 106.6556 | -6.3792 | 52 | 45 | 2020-12-28 |  | 2020-12-28 | 448 | SST | GF
[15 empty] | E | 106.6559 | -6.3792 | 52 | 45 | 2021-02-25 |  |  | 417.5 | SST | GF
0030615460031 | 1129561003 | JAW-JK-TJP-0653 | POLE_KAWASAN_INDUSTRI_RELOCATION | POLE_KAWASAN_INDUSTRI_RELOCATION | XL | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | -6.100736 | 106.715155 | 20 | 20 |  | 150 | A | 106.7159 | -6.1021 | 20 | 20 | 2020-12-15 |  |  | 173.39m | MCP | GF
[15 empty] | B | 106.7162 | -6.1029 | 20 | 20 | 2020-12-15 |  |  | 262.38m | MCP | GF
[15 empty] | C | 106.716 | -6.1071 | 20 | 20 | 2020-12-15 |  |  | 713.1m | MCP | GF
[15 empty] | D | 106.7157 | -6.1017 | 20 | 20 |  |  |  | 121.3m | MCP | GF |  |  |  |  | P1 |  | 2020-12-24 | OK | 0.3 |  | 2020-12-29
[15 empty] | E | 106.7156 | -6.1015 | 20 | 20 |  |  |  | 96.4m | MCP | GF |  |  |  |  | P2 |  | 2020-12-24 | OK | 0.3 |  | 2020-12-29
0230615270231 | 1263821023 | ZBGR_4261 | BOGOR UTARA KOTA BOGOR | BOGOR UTARA KOTA BOGOR | SMART8 | JABODETABEK (OUTER) | KOTA BOGOR | JAWA BARAT | -6.5403 | 106.8149 | 42 | 35 |  | 150 | A | 106.8139 | -6.5377 | 42 | 35 | 2021-01-05 |  |  | 318m | SST | GF
[15 empty] | B | 106.8165 | -6.5399 | 32 | 30.5
[15 empty] | C | 106.8143 | -6.5388 | 42 | 35 | 2021-05-24 |  |  | 181 | SST | GF
[15 empty] | D | 106.8163 | -6.5444 | 52 | 45 | 2021-08-19 |  |  | 477 | SST
0230615380231 | 1263831023 | ZBGR_4605 | CIBUNGBULANG BOGOR 2 | CIBUNGBULANG BOGOR 2 | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.585862 | 106.66486 | 52 | 50 |  | 150 | A | 106.6628 | -6.586 | 52 | 50 | 2020-12-29 |  | 2020-12-29 | 233.73m | SST | GF
[15 empty] | B | 106.6628 | -6.586 | 62 | 50 | 2021-02-02 |  | 2021-02-02 | 223.45m | SST | GF
|  | ZJKT2_4285 | CIPONDOH KOTA TANGERANG | CIPONDOH KOTA TANGERANG | SMART8 | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | -6.1815 | 106.6724 | 32 |  |  |  | A | 106.6723 | -6.1822 | 29 | 25
[15 empty] | B | 106.6723 | -6.1822 | 29 | 28 | 2021-02-25 |  |  | 55.27
|  | INJB21_0218 | LEUWILIANG BOGOR | LEUWILIANG BOGOR | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.582 | 106.6295 | 52 | 52 |  | 250 | A | 106.628 | -6.5815 | 52 | 50.5 | 2021-01-14 |  |  | 171.21m | SST | GF
[15 empty] | B | 106.6313 | -6.5811 | 52 | 50.5 | 2021-01-14 |  |  | 222.03m | SST | GF
[15 empty] | C | 106.6274 | -6.5829 | 52 | 50.5 | 2021-02-19 |  |  | 254m | SST | GF |  | Geser
[15 empty] | D | 106.6276 | -6.5824 | 52 | 50.5 |  |  |  | 212.67
[15 empty] | E | 106.6281 | -6.5831 | 52 | 50.5
[15 empty] | F | 106.6354 | -6.5833 | 62 | 60,5 | 2021-06-25 |  |  | 674.85 | SST | GF
[15 empty] | G | 106.6344 | -6.584
|  | INJB21_0538 | TENJOLAYA BOGOR | TENJOLAYA BOGOR | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.6588 | 106.7141 | 52 | 50 |  | 150 | A | 106.7141 | -6.6587 | 52 | 50 | 2021-01-14 |  |  | 14.97m | SST | GF |  |  |  |  | Feasible | Antenna di ketinggian 50 | 2021-01-18 | 35m | 0.3 |  | 2021-01-19
|  | HUNew_BDG4716-2 | WARUNG KIARA SUKABUMI | WARUNG KIARA SUKABUMI | SMART8 | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | -6.9987 | 106.7177 | 62 | 62 |  | 250 | A | 106.7176 | -6.9974 | 62 | 60.5 | 2021-01-14 |  |  | 149.69m | SST | GF |  |  |  |  | Feasible | P1, antena 60.5 | 2021-01-25 | OK | 0.3 |  | 2021-01-25
[15 empty] | B | 106.7179 | -7.001 | 62 | 60.5 | 2021-01-14 |  |  | 253.96m | SST | GF |  |  |  |  | Feasible | P2, antena 60.5 | 2021-01-25 | OK | 0.3 |  | 2021-01-25
[15 empty] | C | 106.718 | -7.0008 |  |  | 2021-02-25 |  |  | 229.07
|  | IN20_JB_1421 | PARUNG PANJANG GOROWONG | PARUNG PANJANG GOROWONG | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.379 | 106.5548 | 62 | 60 |  | 250 | A | 106.5554 | -6.3771 | 62 | 60 | 2021-01-14 |  |  | 217.82m | SST | GF
[15 empty] | B | 106.5545 | -6.3783 | 62 | 60 | 2021-01-14 |  |  | 87.9m | SST | GF
[15 empty] | C | 106.5547 | -6.3791 | 62 | 60 | 2021-03-09 |  |  | 14.97m | SST | GF
|  | SKB204 | PASAR CISAATSKB | PASAR CISAATSKB | TSEL | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | -6.9031 | 106.8935 | 52 |  |  |  | P | 106.8932 | -6.9027 | 52 | [5 empty] | SST
[15 empty] | Q | 106.8937 | -6.9019 | 52 | [5 empty] | SST
[15 empty] | R | 106.8933 | -6.9002 | 52 |  | 2021-02-16 |  | 2021-02-16 | 312.19m | SST | GF
|  | ZBGR_4663 | PAMIJAHAN BOGOR 2 |  | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.6467 | 106.6475 | 52 | 45 |  |  | A | 106.6474 | -6.6478 | 52 | 45 | 2021-05-10 |  | 2021-05-10 | 121.93m | SST | GF
[15 empty] | B | 106.6483 | -6.6458 | 52 | 45 | 2021-05-24 |  |  | 127m | SST | GF
[15 empty] | C | 106.6495 | -6.6491 | 52 | 55 | 2021-06-07
[15 empty] | D | 106.6456 | -6.6468 | 52 | 50 | 2021-06-15 |  |  | 210.25m
|  | ZJKT2_6180 | TANGERANG KOSAMBI |  | SMART8 | JABODETABEK (OUTER) | TANGERANG | BANTEN | -6.1022 | 106.664 | 42 | 35 |  |  | A | 106.6642 | -6.1021 | 32 | 30.5 | 2021-07-09 |  |  | 28m | SST
[15 empty] | B | 106.6643 | -6.1015 | 32 | 30.5 | 2021-07-26 |  |  | 86,4m | SST
|  | ZJKT2_6089 | TANGERANG CIPONDOH |  | SMART8 | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | -6.1988 | 106.6888 | 32 | 30 |  |  | A | 106.6894 | -6.1972 | [13 empty] | OUTCELL
[15 empty] | B | 106.687 | -6.1998
[15 empty] | C | 106.687 | -6.1987 | 42 | 35 | 2021-07-10 |  |  | 195 | SST
[15 empty] | D | 106.6868 | -6.1975 | 52 | 45 | 2021-08-03 |  |  | 253.15 | SST
[15 empty] | E | 106.686 | -6.1974 | 52 | 45 | 27/0/2021 |  |  | 339.15 | SST
|  | ZJKT2_4619 | JAKARTA UTARA PADEMANGAN |  | SMART8 | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | -6.1336 | 106.8419 | 32 | 30 |  |  | A | 106.8418 | -6.1342 | 35 | 30 | 2021-07-09 |  |  | 68.98 | RT + MT
[15 empty] | B | 106.8421 | -6.1341 | 25 | 23.5
|  | INJB21_0272 | PKP JAKARTA BARAT TAMBORA |  | SMART8 | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | -6.151 | 106.7958 | 25 | 25 |  |  | A | 106.7959 | -6.1511 | 25 | 24 | 2021-07-09 |  |  | 10.75 | MCP
|  | ZJKT2_5300 | PKP JAKARTA BARAT CENGKARENG |  | SMART8 | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | -6.1411 | 106.7685 | 32 | 30 |  |  | A | 106.7679 | -6.1416 | 25
|  | HUNew_BDG5992-2 | SUKABUMI CIKIDANG |  | SMART8 | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | -6.8768 | 106.6726 | 72 | 66 |  |  | A | 106.6739 | -6.8768 | 72 | 66 | 2021-07-09 |  |  | 145.39 | SST
[15 empty] | B | 106.6699 | -6.8822 | 72 | 70.5 | 2021-08-03 |  |  | 668.59 | SST
[15 empty] | C | 106.6727 | -6.8824 | 72 | 70.5 | 2021-08-03 |  |  | 626.1 | SST
|  | ZBGR_4687 | BOGOR BOJONG GEDE |  | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.4712 | 106.7957 | 42 | 35 |  |  | A | 106.7959 | -6.4717 | 42 | 35 | 2021-07-09 |  |  | 58.5 | SST | [5 empty] | P2 | OK GO SITAC |  | P1
[15 empty] | B | 106.7963 | -6.4704 | 42 | 35 | 2021-07-09 |  |  | 107.64 | SST | [5 empty] | P1 | OK GO SITAC |  | P2
|  | ZJKT2_6031 | JAKARTA BARAT CENGKARENG-1 |  | SMART8 | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | -6.1371 | 106.7488 | 32 | 30 |  |  | A | 106.7488 | -6.1368 | 25 | 24 | 2021-07-09 |  |  | 34.61 | MCP
[15 empty] | B | 106.7485 | -6.1366 | 25 | 24 | 2021-07-09 |  |  | 64.18 | MCP
[15 empty] | C | 106.7482 | -6.1372 | 25 | 24 | 2021-07-09 |  |  | 66.21 | MCP
|  | INJB21_0283 | PKP KALI DERES JAKARTA BARAT |  | SMART8 | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | -6.11 | 106.7109 | 25 | 25 |  |  | A | 106.7112 | -6.1103 | 25 | 24 | 2021-07-09 |  |  | 42.04 | MCP
[15 empty] | B | 106.7113 | -6.1098 | 25 | 24 | 2021-07-09 |  |  | 48.1 | MCP
[15 empty] | C | 106.7105 | -6.1103 | 25 | 24 | 2021-07-29 |  |  | 51.52 | MCP
|  | HUNew_JKT24157 | PKP PENJARINGAN JAKARTA UTARA |  | SMART8 | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | -6.1301 | 106.7977 | 25 | 25 |  |  | A | 106.7978 | -6.13 | 32 | 25 | 2021-07-13 |  |  | 17.02 | RT + MT
[15 empty] | B | 106.7982 | -6.1299 | 25 | 24 | 2021-07-29 |  |  | 56 | MCP
|  | INJB21_0322 | KARAWANG MAJALAYA |  | SMART8 | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | -6.313947 | 107.35046 | 42 | 35 |  |  | A | 107.3503 | -6.315 | 42 | 35 | 2021-07-16 |  |  | 114.85 | SST
|  | ZBGR_4655 | BOGOR SUKARAJA |  | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.542636 | 106.82084 | 42 | 35 |  |  | A | 106.8217 | -6.5428 | 42 | 35 | 2021-07-16 |  |  | 101.16 | SST | [5 empty] | P2
[15 empty] | B | 106.8197 | -6.5427 | 42 | 35 | 2021-07-16 |  |  | 122.65 | SST | [5 empty] | P1
[15 empty] | C | 106.8225 | -6.5433 | 42 | 40 | 2021-08-03 |  |  | 201 | SST
[15 empty] | D | 106.822 | -6.542 | 42 | 40 | 2021-10-03 |  |  | 149 | SST
|  | ZJKT2_6428 | JAKARTA BARAT CENGKARENG-2 |  | SMART8 | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | -6.1344 | 106.7456 | 25 | 25 |  |  | A | 106.7449 | -6.134
[15 empty] | B | 106.7461 | -6.1338
|  | ZJKT2_5300 | PKP JAKARTA BARAT CENGKARENG |  | SMART8 | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | -6.1411 | 106.7685 | 25 | 25 |  |  | A | 106.7689 | -6.1407 | 25 | 24 | 2021-07-23 |  |  | 57.28 | MCP | [5 empty] | NOK | To far
[15 empty] | B | 106.7685 | -6.1403
|  |  | KOTA TANGERANG CIPONDOH |  | SMART8 | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | -6.1766 | 106.6926 | 32 | 30 |  |  | A | 106.6926 | -6.1768 | 32 | 30 | 2021-09-01 |  |  | 19.19 | SST
|  | JAW-JB-CKR-0068 | Pondok Ungu Permai Relocation |  | XL | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | -6.179669 | 107.012981 | 32 |  |  |  | A | 107.0124 | -6.1796 | 32
[15 empty] | B | 107.014 | -6.1802 | 32
|  | JAW-JB-CKR-0068 | Pondok Ungu Permai Relocation |  | XL | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | -6.179669 | 107.012981 | 32 | 30 |  |  | C | 107.014 | -6.1791 | 32 |  |  |  |  | 129m
|  | IN20_JB_0117 | BOGOR RUMPIN |  | SMART8 | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | -6.3838 | 106.6306 | 42 |  |  |  | A | 106.6353 | -6.3772 | 42 | 40.5
|  | INBDG4152-3 | SUKABUMI CARINGIN |  | SMART8 | WEST JAVA | SUKABUMI | JAWA BARAT | -6.851537 | 106.884227 |  | 47 |  |  | A | 106.8847 | -6.8507 | 52 | 47
|  | INJB21_0327 | SERANG CARENANG |  | SMART8 | JABODETABEK | SERANG | BANTEN | -6.09652 | 106.305026 |  | 54 |  |  | A | 106.3047 | -6.0974 | 62 | 54
|  | INBGR4075-2 | BOGOR CIBUNGBULANG |  | SMART8 | JABODETABEK | BOGOR | JAWA BARAT | -6.580568 | 106.668079 |  | 43 |  |  | A | 106.6716 | -6.5809 | 52 | 50

## Validasi XL
Site ID | Site Name | Region XL | Propinsi | Residence | Proposed RF Height | Propose Tower Height | NOM Longitude | NOM Latitude | Kandidat | Kandidat Longitude DMS | Kandidat Latitude DMS | Kandidat Longitude Decimal | Kandidat Latitude Decimal | Distance NOM to Candidate (m) | Bearing NOM to Candidate | Status IW
JAW-JK-TJP-0653 | POLE_KAWASAN_INDUSTRI_RELOCATION | JABO | DKI JAKARTA | JAKARTA UTARA | 20 | 20 | 106.7152 | -6.1007 | A | 106°42'57.4" E | 06°06'07.6" S | 106.7159 | -6.1021 | 173.39m | 150.34
JAW-JK-TJP-0653 | POLE_KAWASAN_INDUSTRI_RELOCATION | JABO | DKI JAKARTA | JAKARTA UTARA | 20 | 20 | 106.7152 | -6.1007 | B | 106°42'58.3" E | 06°06'10.3" S | 106.7162 | -6.1029 | 262.38m | 153.98
JAW-JK-TJP-0653 | POLE_KAWASAN_INDUSTRI_RELOCATION | JABO | DKI JAKARTA | JAKARTA UTARA | 20 | 20 | 106.7152 | -6.1007 | C | 106°42'57.7" E | 06°06'25.6" S | 106.716 | -6.1071 | 713.1m | 172.3
JAW-JK-TJP-0653 | POLE_KAWASAN_INDUSTRI_RELOCATION | JABO | DKI JAKARTA | JAKARTA UTARA | 20 | 20 | 106.7152 | -6.1007 | D | 106°42'56.6" E | 06°06'06.11" S | 106.7157 | -6.1017 | 122.15m | 150.13 | On Going NY Clear
JAW-JK-TJP-0653 | POLE_KAWASAN_INDUSTRI_RELOCATION | JABO | DKI JAKARTA | JAKARTA UTARA | 20 | 20 | 106.7152 | -6.1007 | E | 106°42'56.14" E | 06°06'05.4" S | 106.7156 | -6.1015 | 97.21m | 149.37
JAW-BT-CPT-0472 | WIJAYAKUSUMA CEGER |  | BANTEN | KOTA TANGERANG SELATAN |  | 20 | [5 empty] | 106.7302 | -6.261 |  |  | On Going NY Clear
JAW-BT-CPT-0472 | WIJAYAKUSUMA CEGER |  | BANTEN | KOTA TANGERANG SELATAN |  | 20 | [5 empty] | 106.7307 | -6.2612 |  |  | On Going NY Clear
JAW-JK-TJP-0621 | DUFAN MARINA | JABO | DKI JAKARTA | JAKARTA UTARA | 20 | 20 | 106.8304 | -6.1253 |  | 106°49'44.1" E | 06°07'30.9" S | 106.8289 | -6.1253 | 158.06m | 274.24
JAW-JK-CKG-0743 | RAYA BOGOR RELOCATION | JABO | DKI JAKARTA | JAKARTA TIMUR | 20 | 20 | 106.869 | -6.3432 | A | 106°52'10.56" E | 06°20'35.16" S | 106.8696 | -6.3431 |  |  | NY Secure
[9 empty] | B | 106°52'07.32" E | 06°20'38.76" S | 106.8687 | -6.3441 |  |  | NY Secure
[9 empty] | C | 106°52'09.84" E | 06°20'31.56" S | 106.8694 | -6.3421 |  |  | NY Secure

## Validasi SF
| Submit Date | Nominal | Category | Category Sales | Region | Province | Kabupaten | Kecamatan | Nom_Long | Nom_Lat | RF Plan (m) - LOI | TX Plan (m) - LOI | Search Ring (m) - LOI | Candidate # | Long (Dec) | Lat (Dec) | Site Type | Proposed Tower Type | Proposed Height (m) | In/ Out Polygon | Distance to Nom (m) | RF Validate | RF Remarks | RF Date | TX Validate | FE | Diameter | TX Remarks | TX Date | TX Date
| 2020-11-23 | HUNew_BGR4085-2 |  | JABO 1 | Jabodetabek | Jawa Barat | Bogor | Gunung Sindur | 106.659 | -6.3771 | 40m | 30m | 250m | A | 106.6609 | -6.3796 | SST |  | 52m | Out SAR | 347 m
| 2020-11-23 | HUNew_BGR4085-2 |  | JABO 1 | Jabodetabek | [8 empty] | B | 106.6556 | -6.3792 | SST |  | 52m | Out SAR | 326 m
| 2020-11-23 | ZBGR_4610 |  | JABO 1 | Jabodetabek | Jawa Barat | Bogor | Gunung Sindur | 106.6907 | -6.3913 | 35m | 26m | 150m | A | 106.6932 | -6.3894 | SST |  | 42m | Out SAR | 344 m
| 2020-11-23 | ZBGR_4610 |  | JABO 1 | Jabodetabek | [8 empty] | B | 106.6936 | -6.391 | SST |  | 42m | Out SAR | 326 m
| 2020-11-26 | ZJKT2_6111 |  | JABO 2 | Jabodetabek | Banten | Tangerang | Kosambi | 106.6495 | -6.1118 | 35m | 30m | 150m | A | 107.0336 | -6.2459 | SST |  | 42m | Out SAR | 547 m
| 2020-11-26 | ZJKT2_6111 |  | JABO 2 | Jabodetabek | [8 empty] | B | 106.6454 | -6.1083 | SST |  | 42m | Out SAR | 601 m
| 2020-11-26 | IN20_JB_1199 |  | JABO 2 | Jabodetabek | Banten | Tangerang | Gunung Kaler | 106.3714 | -6.1009 | 43 | 30 | 250m | A | 106.3727 | -6.1011 | SST |  | 52m | In SAR | 115m
| 2020-11-26 | IN20_JB_0812 |  | JABO 3 | Jabodetabek | Jawa Barat | Bogor | Citeureup | 106.6907 | -6.5268 | 43m | 40m | 150m | A | 106.9073 | -6.5271 | SST |  | 52m | In SAR | 91 m
| 2020-11-26 | IN20_JB_0812 |  | JABO 3 | Jabodetabek | [8 empty] | B | 106.908 | -6.5268 | SST |  | 52m | In SAR | 14 m
| 2020-11-26 | IN20_JB_1136 |  | JABO 2 | Jabodetabek | Banten | Kota Serang | Walantaka | 106.2265 | -6.1792 | 44m | 30m | 150m | A | 106.2268 | -6.1811 | SST |  | 52m | Out SAR | 214m
| 2020-11-26 | IN20_JB_1136 |  | JABO 2 | Jabodetabek | [8 empty] | B | 106.2278 | -6.18 | SST |  | 52m | Out SAR | 166m
No. | Submit Date | SF NOMINAL | Category | Category Sales | Region | Province | Kabupaten | Kecamatan | Nom_Long | Nom_Lat | RF Plan (m) - LOI | TX Plan (m) - LOI | Search Ring (m) - LOI | Candidate # | Long (Dec) | Lat (Dec) | Site Type | Proposed Tower Type | Proposed Height (m) | In/ Out Polygon | Distance to Nom (m) | RF Validate | RF Remarks | RF Date | TX Validate | FE | Diameter | TX Remarks | TX Date
1 | 2020-12-07 | HUNew_BGR4085-2 | GUNUNG SINDUR BOGOR |  | Jabodetabek | Jawa Barat | BOGOR | Gunung SIndur | 106.659 | -6.3771 | 40 | 30 | 250 | C | 106.6579 | -6.37 | GREEN FIELD | SST | SST 52 | OUT SAR | 789m
2 | 2020-12-07 | HUNew_BGR4085-2 | GUNUNG SINDUR BOGOR |  | Jabodetabek | Jawa Barat | BOGOR | Gunung SIndur | 106.659 | -6.3771 | 40 | 30 | 250 | D | 106.6629 | -6.3704 | GREEN FIELD | SST | SST 52 | OUT SAR | 867m
3 | 2020-12-07 | ZBGR_4610 | GUNUNG SINDUR JAWA BARAT |  | Jabodetabek | Jawa Barat | BOGOR | Gunung SIndur | 106.6907 | -6.3913 | 35 | 26 | 150 | A | 106.6932 | -6.3894 | GREEN FIELD | SST | SST 52 | OUT SAR | 345m
4 | 2020-12-07 | ZBGR_4588 | CIBUNGBULANG BOGOR |  | Jabodetabek | Jawa Barat | BOGOR | Cibungbulang | 106.65947 | -6.61969 | 49 | 30 | 150 | A | 106.6586 | -6.6185 | GREEN FIELD | SST | SST 52 | OUT SAR | 160m
5 | 2020-12-07 | ZBGR_4588 | CIBUNGBULANG BOGOR |  | Jabodetabek | Jawa Barat | BOGOR | Cibungbulang | 106.65947 | -6.61969 | 49 | 30 | 150 | B | 106.6585 | -6.6182 | GREEN FIELD | SST | SST 52 | OUT SAR | 193m
6 | 2020-12-07 | ZJKT2_6085 | PERIUK KOTA TANGERANG |  | Jabodetabek | Banten | KOTA TANGERANG | Periuk | 106.59571 | -6.16775 | 35 | 30 | 150 | A | 106.5957 | -6.1677 | GREEN FIELD | Monopole | MCP 20 | IN SAR | 3m
7 | 2020-12-07 | ZJKT2_5468 | TIGARAKSA TANGERANG 2 |  | Jabodetabek | Banten | TANGERANG | Tigaraksa | 106.478106 | -6.243617 | 39 | 30 | 150 | A | 106.475 | -6.2459 | GREEN FIELD | SST | SST 42 | OUT SAR | 430m
8 | 2020-12-01 | ZJKT2_6111 | KOSAMBI TANGERANG |  | Jabodetabek | BANTEN | Tangerang | Kosambi | 106.6495 | -6.1118 | 35 | 30 | 150 | A | 106.6466 | -6.1078 | GREEN FIELD | SST | SST 42 | Out SAR | 547m
| Submit Date | SF NOMINAL | Category | Category Sales | Region | Province | Kabupaten | Kecamatan | Nom_Long | Nom_Lat | RF Plan (m) - LOI | TX Plan (m) - LOI | Search Ring (m) - LOI | Candidate # | Long (Dec) | Lat (Dec) | Proposed Tower Type | Proposed Height (m) | In/ Out Polygon | Remark | Distance to Nom (m) | RF Validate | RF Remarks | RF Validation Date | TX Validate | FE | Diameter | TX Remarks | TX Date
| 2020-12-02 | IN20_JB_1136 | WALANTAKA KOTA SERANG | JABO 2 | Jabodetabek | BANTEN | Kota Serang |  | 10622654 | -61792 | 44 | 30 | 250 | A | 106.2268 | -6.1811 | SST | 52m | Out SAR |  | 214 | Feasible | Backup for P1 | 2020-12-02
| 2020-12-02 | IN20_JB_1136 | WALANTAKA KOTA SERANG | JABO 2 | Jabodetabek | BANTEN | Kota Serang |  | 10622654 | -61792 | 44 | 30 | 250 | B | 106.2278 | -6.18 | SST | 52m | Out SAR |  | 166 | Feasible | P1 | 2020-12-02
| 2020-12-01 | ZJKT2_6111 | KOSAMBI TANGERANG | JABO 2 | Jabodetabek | BANTEN | Tangerang |  | 106.6495 | -6.1118 | 35 | 30 | 150 | A | 106.6466 | -6.1078 | SST | 42m | Out SAR |  | 547 | Confirmation Needed | Please check candidate coordinate | 2020-12-02
| 2020-12-01 | ZJKT2_6111 | KOSAMBI TANGERANG | JABO 2 | Jabodetabek | BANTEN | Tangerang |  | 106.6495 | -6.1118 | 35 | 30 | 150 | B | 106.6454 | -6.1083 | SST | 42m | Out SAR |  | 601 | Not Feasible | Too near to OA sites, try to acquire around -6.1107234/106.6454356 | 2020-12-02
| 2020-12-01 | IN20_JB_1199 | GUNUNG KALER TANGERANG | JABO 2 | Jabodetabek | BANTEN | Tangerang |  | 106.3714 | -6.1009 | 43 | 30 | 150 | A | 106.3727 | -6.1011 | SST | 52m | In SAR |  | 115 | Feasible |  | 2020-12-02
| 2020-12-01 | IN20_JB_0812 | CITEUREUP BOGOR 2 | JABO 3 | Jabodetabek | JAWA BARAT | Bogor |  | 106.6907 | -6.5268 | 43 | 40 | 150 | A | 106.9073 | -6.5271 | SST | 52m | In SAR |  | 91 | Feasible | Backup candidate | 2020-12-02
| 2020-12-01 | IN20_JB_0812 | CITEUREUP BOGOR 2 | JABO 3 | Jabodetabek | JAWA BARAT | Bogor |  | 106.6907 | -6.5268 | 43 | 40 | 150 | B | 106.908 | -6.5268 | SST | 52m | In SAR |  | 14 | Feasible | P1 | 2020-12-02
150
| Submit Date | SF NOMINAL | SiteName | Category Sales | Region | Province | Kabupaten | Kecamatan | Nom_Long | Nom_Lat | RF Plan (m) - LOI | TX Plan (m) - LOI | Candidate # | Long (Dec) | Lat (Dec) | Proposed Tower Type | Proposed Height (m) | In/ Out Polygon | Remark | Distance to Nom (m) | RF Validate | RF Remarks | RF Validation Date | TX Validate | FE | Diameter | TX Remarks | TX Date
| 2020-12-07 | HUNew_BGR4085-2 | GUNUNG SINDUR BOGOR |  | Jabodetabek | Jawa Barat | BOGOR | Gunung SIndur | 106.659 | -6.3771 | 40 | 30 | C | 106.6579 | -6.37 | GREEN FIELD | SST | SST 52 | OUT SAR | 789 | Not Feasible | Candidate location is too far from target area. Consider JR, Use candidate B -6.37925/106.65556 . Height Needed 45m, Please confirm | 2020-12-07 | TX not validated, RF not feasible
| 2020-12-07 | HUNew_BGR4085-2 | GUNUNG SINDUR BOGOR |  | Jabodetabek | Jawa Barat | BOGOR | Gunung SIndur | 106.659 | -6.3771 | 40 | 30 | D | 106.6629 | -6.3704 | GREEN FIELD | SST | SST 52 | OUT SAR | 867 | Not Feasible | Candidate location is too far from target area. Consider JR, Use candidate B -6.37925/106.65556 . Height Needed 45m, Please confirm | 2020-12-07 | TX not validated, RF not feasible
| 2020-12-07 | ZBGR_4610 | GUNUNG SINDUR JAWA BARAT | Jabo_Outer_add_028 | Jabodetabek | Jawa Barat | BOGOR | Gunung SIndur | 106.6907 | -6.3913 | 35 | 26 | A | 106.6932 | -6.3894 | GREEN FIELD | SST | SST 52 | OUT SAR | 345.15 | Feasible | Height Needed 45m | 2020-12-07 | 35m | ZBGR_4006 | 0.3
| 2020-12-07 | ZBGR_4588 | CIBUNGBULANG BOGOR | BOG0152 | Jabodetabek | Jawa Barat | BOGOR | Cibungbulang | 106.6595 | -6.6197 | 49 | 30 | A | 106.6586 | -6.6185 | GREEN FIELD | SST | SST 52 | OUT SAR | 160 | Feasible | Backup candidate B | 2020-12-07 | 35m | ZBGR_4175 | 0.3
| 2020-12-07 | ZBGR_4588 | CIBUNGBULANG BOGOR | BOG0152 | Jabodetabek | Jawa Barat | BOGOR | Cibungbulang | 106.6595 | -6.6197 | 49 | 30 | B | 106.6585 | -6.6182 | GREEN FIELD | SST | SST 52 | OUT SAR | 193 | Feasible |  | 2020-12-07 | 35m | ZBGR_4175 | 0.3
| 2020-12-07 | ZJKT2_6085 | PERIUK KOTA TANGERANG |  | Jabodetabek | Banten | KOTA TANGERANG | Periuk | 106.5957 | -6.1677 | 35 | 30 | A | 106.5957 | -6.1677 | GREEN FIELD | Monopole | MCP 20 | IN SAR | 3 | Not Feasible | Height needed 35m | 2020-12-07 | TX not validated, RF not feasible
| 2020-12-07 | ZJKT2_5468 | TIGARAKSA TANGERANG 2 | JAK1027 | Jabodetabek | Banten | TANGERANG | Tigaraksa | 106.4781 | -6.2436 | 39 | 30 | A | 106.475 | -6.2459 | GREEN FIELD | SST | SST 42 | OUT SAR | 430 | Feasible | Considering JR, Height needed 40m | 2020-12-07 | 35m | ZJKT_4455 | 0.3
| 2020-12-07 | ZJKT2_6111 | KOSAMBI TANGERANG | IN20_JB_1525 | Jabodetabek | BANTEN | Tangerang | Kosambi | 106.6495 | -6.1118 | 35 | 30 | A | 106.6466 | -6.1078 | GREEN FIELD | SST 42 | Out SAR |  | 547 | Confirmation Needed | Please check and justification needed if not possible, for location around -6.1107234/106.6454356 | 2020-12-07 | 35m | ZJKT_6330 | 0.3
|  |  | Parung Kuda | lahan desa
|  | NOM ID | RESIDENCE | PROVINCE | SAR | RF Antenna | Propose Tower | NOM Long | NOM Lat | Arahan Kand | Long Kand. | Lat Kand.
|  | ZBGR_4663 | BOGOR | JAWA BARAT | 150 | 45 | SST 52 | 106.6475 | -6.6467 | A | 106.6483 | -6.6459
[10 empty] | B | 106.6483 | -6.6471
[10 empty] | C | 106.6475 | -6.6479

## Eskalasi Ready
| Site Name |  | VILLAGADINGHARAPAN
No | Description | qty | Price | CAPEX PLAN 2018 | Remarks | AVRG COST 2016/2017
1 | BAN | 11 th | 17000000 | 187000000 |  | 385000000 | 35000000
2 | SIS | 1 | 3000000 | 3000000
3 | SITAC
| Biaya Rekom | Ls | 25700000 | 25700000 | LS Price as per SITAC TBG Shop Price 2016 ( exclude PPH )
| Biaya Legalitas | Ls | 5500000 | 5500000 | PKS, Koordinasi & dokumentasi (exclude PPH)
| Biaya Ijin Warga per KK | 30 KK | 0 | 25000000
| Fasos Fasum Ormas | Ls | 10000000 | 10000000
| Total SITAC |  |  | 66200000 |  | 170000000
4 | IMB | 1 | 33800000 | 33800000 | IMB Reference
5 | CME + TOWER | GM 42 | MCP 20 | MCP 20 | GM 42
6 | CME + TOWER | SST 42 | 0 | 0 | SST 42
7 | CAPEX CME with Structure GM |  |  | #VALUE!
8 | CAPEX CME with GM dan Pemanen |  |  | #VALUE! | Excl cost of relocation material
-103800000
No | Description | qty | Price | CAPEX PLAN 2022 | AVRG COST 2020/Year
1 | BAN | 11 Tahun | 30000000 | 330000000 | 0 | #N/A
2 | SIS | 1 | 3000000 | 3000000
3 | SITAC
| Ijin Warga | 5 KK @ 1.000.000, 23 KK @500.000 | 16500000 | 16500000 |  |  |  | 8750000
| Biaya Jasa Operasional Site | Ls | 25000000 | 25000000 |  |  |  | 15000000
| Additional Operasional Site | Ls | 53500000 | 53500000 |  |  |  | 62250000
| Biaya Sitac (Tanpa IW) | Ls | 78500000 | 78500000 |  |  |  | 77250000
| Total SITAC |  |  | 95000000 |  |  |  | 86000000
4 | Biaya Operasional Sitac | Ls | 15000000 | 15000000 |  | SPK Pre Sitac Release
5 | CME + TOWER Temporary |  | 0 | 0
6 | CME + TOWER | SST 42m | 353505181 | 353505181
7 | CAPEX CME with Structure GM |  |  | 443000000 |  |  | 86000000
7 | CAPEX |  |  | 796505181
60000000
4500000
64500000
| UBRUG | [6 empty] | Permata Indah
No | Description | qty | Price | CAPEX PLAN 2021 | AVRG COST 2020/Year |  | No | Description | qty | Price | CAPEX PLAN 2021 | AVRG COST 2020/Year
1 | BAN | 20 Tahun | 17500000 | 350000000 | 22500000 |  | 1 | BAN | 10 Tahun | 25000000 | 250000000 | 25000000
2 | SIS | 1 | 3000000 | 3000000 |  |  | 2 | SIS | 1 | 3000000 | 3000000
3 | SITAC | [5 empty] | 3 | SITAC
| Ijin Warga | 25 KK | 28000000 | 28000000 |  |  |  | Ijin Warga | 24 KK | 12000000 | 12000000
| Biaya Jasa Operasional Site | Ls | 25000000 | 25000000 |  |  |  | Biaya Jasa Operasional Site | Ls | 25000000 | 25000000
| Additional Operasional Site | Ls | 46000000 | 46000000 |  |  |  | Additional Operasional Site | Ls | 62000000 | 62000000
| Biaya Sitac (Tanpa IW) | Ls | 71000000 | 71000000 |  |  |  | Biaya Sitac (Tanpa IW) | Ls | 87000000 | 87000000
| Total SITAC |  |  | 99000000 |  |  |  | Total SITAC |  |  | 99000000
4 | Biaya Operasional Sitac | Ls | 15000000 | 15000000 |  |  | 4 | Biaya Operasional Sitac | Ls | 15000000 | 15000000
5 | CME + TOWER Temporary |  | 0 | 0 |  |  | 5 | CME + TOWER Temporary |  | 0 | 0
6 | CME + TOWER | SST 62m | 527299431 | 527299431 |  |  | 6 | CME + TOWER | SST 42m | 353505181 | 353505181
7 | CAPEX CME with Structure GM |  |  | 467000000 |  |  | 7 | CAPEX CME with Structure GM |  |  | 367000000
7 | CAPEX |  |  | 994299431 |  |  | 7 | CAPEX |  |  | 720505181
IDEMITSU
No | Description | qty | Price | CAPEX PLAN 2021 | AVRG COST 2020/Year
1 | BAN | 20 Tahun | 30000000 | 330000000 | 0
2 | SIS | 1 | 3000000 | 3000000
3 | SITAC
| Ijin Warga | 5 KK @ 1.000.000, 23 KK @500.000 | 16500000 | 16500000
| Biaya Jasa Operasional Site | Ls | 25000000 | 25000000
| Additional Operasional Site | Ls | 53500000 | 53500000
| Biaya Sitac (Tanpa IW) | Ls | 78500000 | 78500000
| Total SITAC |  |  | 95000000
4 | Biaya Operasional Sitac | Ls | 15000000 | 15000000
5 | CME + TOWER Temporary |  | 0 | 0
6 | CME + TOWER | SST 42m | 353505181 | 353505181
7 | CAPEX CME with Structure GM |  |  | 443000000
7 | CAPEX |  |  | 796505181
No | Description | qty | Price | CAPEX PLAN 2021 | AVRG COST 2020/Year
1 | BAN | 20 Tahun | 19000000 | 380000000 | 19000000
2 | SIS | 1 | 3000000 | 3000000
3 | SITAC
| Ijin Warga | 42 KK | 31200000 | 31200000
| Biaya Jasa Operasional Site | Ls | 25000000 | 25000000
| Additional Operasional Site | Ls | 40800000 | 40800000
| Biaya Sitac (Tanpa IW) | Ls | 65800000 | 65800000
| Total SITAC |  |  | 97000000
4 | Biaya Operasional Sitac | Ls | 15000000 | 15000000
5 | CME + TOWER Temporary |  | 0 | 0
6 | CME + TOWER | SST 52m | 423293218 | 423293218
7 | CAPEX CME with Structure GM |  |  | 495000000
7 | CAPEX |  |  | 918293218
No | Description | qty | Price | CAPEX PLAN 2021 | AVRG COST 2020
1 | BAN | 20 Tahun | 16000000 | 320000000 | 392000000
2 | SIS | 1 | 3000000 | 3000000
3 | SITAC
| Ijin Warga | 19 KK | 9500000 | 9500000
| Biaya Jasa Operasional Site | Ls | 25000000 | 25000000
| Additional Operasional Site | Ls | 46000000 | 46000000
| Biaya Sitac (Tanpa IW) | Ls | 71000000 | 71000000
| Total SITAC |  |  | 80500000
4 | Biaya Operasional Sitac | Ls | 15000000 | 15000000
5 | CME + TOWER Temporary |  | 0 | 0
6 | CME + TOWER | SST 52m | 423293218 | 423293218
7 | CAPEX CME with Structure GM |  |  | 418500000
8 | CAPEX |  |  | 841793218

## Input
[17 empty] | Report Internal | Report Opr | BAN |  |  |  | LUMSUM PRICE |  |  | IW &FASUM
Tinggal Copy atasnya
Abaikan Saja
Isi sesuai SPH
Input harga Total SPH nya dulu
YEAR RFI | Site Name | KABUPATEN | Longitude NOM | Latitude NOM | Longitude Actual | Latitude Actual | Alamat | Nama LL | No HP LL | Infra Type | Tower Height | Power Supply | PIC Sitac2 | Mitra Sitac | Mitra CME | Milestone | Progress Detail | Progress Detail | BAN 1 th (Reference : Average 2020) | BAN 11 th (Reference : Average 2020) | BAN Actual ( 1 th ) | BAN ACTUAL 11th | SIS | Operasional Site | PKS dan Notaris | Jml KK | Biaya Ijin Warga (Reference : Average 2017) | Jumlah Cost IW (Reference : Average 2017) | FASUM/Ormas (Reference : Average 2017) | Jml KK (Actual ) | IW (ACTUAL) | Total IW (Actual) | Additional Operational Cost Site | Biaya sitac tanpa IW | Sitac Service 2 | Harga Asli | CME Type | Cost CME with GM | Cost CME Permanen | Total Sitac (Reference) | CAPEX with GM | CAPEX GM + Permanen | Total Sitac Tanpa IW | Total Sitac Reference + IMB | STATUS | KETERANGAN
| TIGARAKSA TANGERANG | KAB. TANGERANG | [7 empty] | B2S | 32 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 |  | 25 |  |  |  | 25 KK | 300000 | 7500000 | 47500000 | 72500000 | 15000000 |  | SST 32 | 256500000 | 377220384 |  | 479500000 | 856720384 |  |  | APPROVED
| TELUKNAGA | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 38 KK | 500000 | 19000000 | 52000000 | 77000000 | 15000000 |  | GM 42m/SST 42m | 256500000 | 353505181 |  | 495500000 | 849005181 |  |  | APPROVED
| Jalan Raya Kukun Daun | KAB. TANGERANG | [7 empty] | B2S | 52 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 15 KK | 500000 | 7500000 | 49500000 | 74500000 | 15000000 |  | SST 52m | 0 | 423293218 |  | 225000000 | 648293218 |  |  | APPROVED
| SERANG CIKANDE | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 28 KK | 500000 | 14000000 | 50000000 | 75000000 | 15000000 |  | SST 42m | 0 | 353505181 |  | 232000000 | 585505181 |  |  | APPROVED
| CIRUMPAK TANGERANG | KAB. TANGERANG | [7 empty] | B2S | 52 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 26 KK | 500000 | 13000000 | 50000000 | 75000000 | 15000000 |  | SST 52m | 0 | 423293218 |  | 231000000 | 654293218 |  |  | APPROVED
| PATRASANA KRESEK | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 16 KK | 500000 | 8000000 | 46000000 | 71000000 | 15000000 |  | SST 42m | 0 | 353505181 |  | 222000000 |  |  |  | APPROVED
| STASIUN CIKOYA | KAB. TANGERANG | [7 empty] | B2S | 32 | [7 empty] | 21049242 | 231541662 | 15000000 | 75000000 | 3000000 | 25000000 | [5 empty] | 2 KK | 1000000 | 2000000 | 43400000 | 68400000 | 15000000 |  | SST 32m | 0 | 377220384 | [5 empty] | APPROVED
| STASIUN CIKOYA_Rev | KAB. TANGERANG | [7 empty] | B2S | 32 | [7 empty] | 21049242 | 231541662 | 15000000 | 75000000 | 3000000 | 25000000 | [5 empty] | 22 KK | - | 8000000 | 43400000 | 68400000 | 15000000 |  | SST 32m | 0 | 377220384
| MEKAR WANGI TANGERANG | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 15 KK | 500000 | 7500000 | 45500000 | 70500000 | 15000000 |  | SST 42m | 0 | 353505181 | [5 empty] | APPROVED
| MEKAR WANGI TANGERANG_Rev | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 15000000 | 75000000 | 3000000 | 25000000 | [5 empty] | 15 KK | 500000 | 7500000 | 45500000 | 70500000 | 15000000 |  | SST 42m | 0 | 353505181
| CIBUGEL CISOKA | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 15000000 | 75000000 | 3000000 | 25000000 | [5 empty] | 23 KK | 500000 | 11500000 | 51980000 | 76980000 | 15000000 |  | SST 42m | 0 | 353505181 | [5 empty] | APPROVED
| PANONGAN TANGERANG | KAB. TANGERANG | [7 empty] | B2S | 32 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 34 KK | 500000 | 17000000 | 38500000 | 63500000 | 15000000 |  | SST 32m | - | 377220384 | [5 empty] | APPROVED
| Raya Cisauk BSD | KAB. TANGERANG | [7 empty] | B2S | 32 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 8 KK | 500000 | 4000000 | 58500000 | 83500000 | 15000000 |  | SST 32m |  | 377220384
| Jatake Rangkasbitung | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 18000000 | 90000000 | 3000000 | 25000000 | [5 empty] | 21 KK | 500000 | 10500000 | 59500000 | 84500000 | 15000000 |  | SST 42m |  | 377220384
| GEMPOLSARISEPATANTIMURBANTEN | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 18000000 | 90000000 | 3000000 | 25000000 | [5 empty] | 16 KK | 500000 | 8000000 | 51000000 | 76000000 | 15000000 |  | SST 42m |  | 377220384
| BOJONG NANGKA KELAPA DUA | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 21 KK | 500000 | 10500000 | 56500000 | 81500000 | 15000000 |  | SST 42m |  | 377220384
| KADUSIRUNG | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 26 KK | 500000 | 13000000 | 51500000 | 76500000 | 15000000 |  | SST 42m |  | 377220384
| Dukuh Cukanggalih | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 26 KK | 500000 | 13000000 | 50500000 | 75500000 | 15000000 |  | SST 42m |  | 377220384
| SALEMBARAN JAYA KOSAMBI | KAB. TANGERANG | [7 empty] | B2S | 52 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 60 KK | 500000 | 30000000 | 44000000 | 69000000 | 15000000 |  | SST 52m |  | 377220384
| KAMPUNG BESAR TELUK NAGA | KAB. TANGERANG | [7 empty] | B2S | 52 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 58 KK | 500000 | 29000000 | 43500000 | 68500000 | 15000000 |  | SST 52m |  | 377220384
| PANTAI DADAP | KAB. TANGERANG | [7 empty] | B2S | 52 | [7 empty] | 21049242 | 231541662 | 22500000 | 112500000 | 3000000 | 25000000 | [5 empty] | 49 KK | 1000000 | 49000000 | 23000000 | 48000000 | 15000000 |  | SST 52m |  | 377220384
| Jalan Raya Korelet | KAB. TANGERANG | [7 empty] | B2S | 36 | [7 empty] | 21049242 | 231541662 | 19000000 | 95000000 | 3000000 | 25000000 | [5 empty] | 18 KK | 2000000 | 36000000 | 32000000 | 57000000 | 15000000 |  | SST 36m |  | 433505181.0503
| PASANGGRAHAN SOLEAR | TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 19000000 | 95000000 | 3000000 | 25000000 | [5 empty] | 11 KK | 1000000 | 11000000 | 45500000 | 70500000 | 15000000 |  | SST 42m |  | 377220384 | [5 empty] | APPROVED
| Kayu Agung Sepatan | TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 30 KK | 500000 | 15000000 | 49500000 | 74500000 | 15000000 |  | SST 42m |  | 377220384 | [5 empty] | APPROVED
| PEMATANG TIGARAKSA | TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 13 KK | 500000 | 6500000 | 54500000 | 79500000 | 15000000 |  | SST 42m |  | 377220384 | [5 empty] | NY
| SOLEAR BANTEN | TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 19000000 | 95000000 | 3000000 | 25000000 | [5 empty] | 5 KK | 1000000 | 5000000 | 49500000 | 74500000 | 15000000 |  | SST 42m |  | 377220384 | [5 empty] | NY
| GRIYA SUKATANI MEKARSARI | TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 31 KK | 500000 | 15500000 | 51500000 | 76500000 | 15000000 |  | SST 42m |  | 377220384 | [5 empty] | APPROVED
| GRIYA SUKATANI MEKARSARI_Rev | TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 41 KK | - | 23500000 | 50500000 | 75500000 | 15000000 |  | SST 42m |  | 377220384
| SEPATAN TANGERANG | TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 22KK | 500000 | 11000000 | 52500000 | 77500000 | 15000000 |  | SST 42m |  | 377220384
| KARET SEPATAN TANGERANG | TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 34 KK | 500000 | 17000000 | 46000000 | 71000000 | 15000000 |  | SST 42m |  | 377220384 | [5 empty] | NY
| SUMUR BANDUNG JAYANTI | TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 15 KK | 500000 | 7500000 | 57500000 | 82500000 | 15000000 |  | SST 42m |  | 377220384
| WANA KERTA SINDANG JAYA | TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 30 KK | 500000 | 15000000 | 56500000 | 81500000 | 15000000 |  | SST 42m |  | 377220384
| BABAKAN ASEM TELUK NAGA | TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 48 KK | 500000 | 24000000 | 49500000 | 74500000 | 15000000 |  | SST 42m |  | 377220384
| BELIMBING KOSAMBI | TANGERANG | [7 empty] | B2S | 52 | [7 empty] | 21049242 | 231541662 | 20000000 | 100000000 | 3000000 | 25000000 | [5 empty] | 70 KK | 500000 | 35000000 | 39000000 | 64000000 | 15000000 |  | SST 52m |  | 423293218
| CITEUREUP BOGOR | KAB. BOGOR | [7 empty] | B2S | 36 | [7 empty] | 18750000 | 206250000 | 16000000 | 320000000 | 3000000 | 25000000 | [5 empty] | 22 KK | 1000000 | 22000000 | 45000000 | 70000000 | 15000000 |  | Kamuflase Pohon 42m |  | 433505181.0503 | 90466667 | 455000000 | 888505181.0503 |  |  | APPROVED
| BAKTI ABRI | KOTA DEPOK | [7 empty] | B2S | 42 | [7 empty] | 27272727 | 299999997 | 15000000 | 300000000 | 3000000 | 25000000 | [5 empty] | 18 KK | 500000 | 9000000 | 28000000 | 53000000 | 15000000 |  | Kamuflase Pohon 42m |  | 433505181.0503 | 90466667 | 405000000 | 838505181.0503 |  |  | APPROVED
| BEJI KOTA DEPOK | KOTA DEPOK | [7 empty] | B2S | 32 | [7 empty] | 27272727 | 299999997 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 24 KK |  | 16700000 | 41500000 | 66500000 | 15000000 |  | Kamuflase Pohon 32m |  | 433505181.0503 | 90466667 | 486200000 | 919705181.0503 |  |  | APPROVED
| TAJUR HALANG BOGOR | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 29 KK | 500000 | 24500000 | 47000000 | 72000000 | 15000000 |  | GM 42m / SST 36 | 256500000 | 433505181.0503 | 90466667 | 776000000 | 1209505181.0503 |  |  | APPROVED
| PAMIJAHAN BOGOR | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 5 KK | 500000 | 2500000 | 38500000 | 63500000 | 15000000 |  | GM 42m / Kamufalse Pohon 42m | 256500000 | 433505181.0503 | 90466667 | 765500000 | 1199005181.0503 |  |  | APPROVED
| PANDANSARI CIAWI | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 13 KK |  | 8500000 | 38000000 | 63000000 | 15000000 |  | GM/SST 42 | 256500000 | 353505181 | 90466667 | 771000000 | 1124505181 |  |  | APPROVED
| ABDUL FATAH | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 15000000 | 300000000 | 3000000 | 25000000 | [5 empty] | 70 KK |  | 19000000 | 51000000 | 76000000 | 15000000 |  | GM 42m / SST 42 | 256500000 | 353505181 | 90466667 | 694500000 | 1048005181 |  |  | APPROVED
| SUKARAJA CILEBUT | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 23 KK | 1000000 | 23000000 | 48500000 | 73500000 | 15000000 |  | GM 42m / SST 42 | 256500000 | 353505181 | 90466667 | 796000000 | 1149505181 |  |  | APPROVED
| BOJONG GEDE BOGOR | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 25000000 | 500000000 | 3000000 | 25000000 | [5 empty] | 32 KK | 650000 | 20800000 | 48000000 | 73000000 | 15000000 |  | SST 42 | 256500000 | 353505181 | [5 empty] | APPROVED
| CIOMAS BOGOR | KAB. BOGOR | [7 empty] | B2S | 32 | [7 empty] | 18750000 | 206250000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 20 KK | 500000 | 10000000 | 62000000 | 87000000 | 15000000 |  | GM 42m / SST 42 | 256500000 | 353505181 | 90466667 | 756500000 | 1110005181 |  |  | APPROVED
| CIMANGGU 2 CIBUNGBULANG | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 17000000 | 340000000 | 3000000 | 25000000 | [5 empty] | 12 KK | 500000 | 6000000 | 39000000 | 64000000 | 15000000 |  | SST 42 | 256500000 | 353505181 | [5 empty] | APPROVED
| CIMANGGU 2 CIBUNGBULANG_Kand B | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 12 KK | 500000 | 6000000 | 43000000 | 68000000 | 15000000 |  | SST 42 | 256500000 | 353505181
| SUKARESMI TAMANSARI | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 15000000 | 300000000 | 3000000 | 25000000 | [5 empty] | 17 KK | 500000 | 8500000 | 42500000 | 67500000 | 15000000 |  | SST 42 | 256500000 | 353505181 | [5 empty] | APPROVED
| Pabuaran Kemang | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 55 KK | - | 16000000 | 52500000 | 77500000 | 15000000 |  | SST 42 | 256500000 | 353505181 | [5 empty] | hold
| Pengasinan Gunung Sindur | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 27 KK |  | 18000000 | 53500000 | 78500000 | 15000000 |  | SST 42 | 256500000 | 353505181 | [5 empty] | APPROVED
| Pengasinan Gunung Sindur_Rev | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 27 KK | - | 18000000 | 56500000 | 81500000 | 15000000 |  | SST 42 |  | 353505181
| Pengasinan Gunung Sindur_Rev2 | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 27 KK |  | 18000000 | 54500000 | 79500000 | 15000000 |  | SST 42 |  | 353505181
| CIBINONG NANGGEWER | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 12 KK | - | 50000000 | 35000000 | 60000000 | 15000000 |  | GM 42m / SST 42 | 256500000 | 353505181 | 90466667 | 789500000 | 1143005181 |  |  | APPROVED
| JALAN RAYA PUSPITEK | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 55 KK | - | 22700000 | 42000000 | 67000000 | 15000000 |  | SST 42 |  | 353505181
| PASIRMUKTI CITEUREUP | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 28 KK | - | 28600000 | 45000000 | 70000000 | 15000000 |  | SST 42 | 256500000 | 353505181 | [5 empty] | NY
| KLAPANUNGGAL CILEUNGSI | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 29 KK | - | 31500000 | 40500000 | 65500000 | 15000000 |  | SST 42 | 256500000 | 353505181 | [5 empty] | hold
| KP PABUARAN | KOTA BOGOR | [7 empty] | B2S | 36 | [7 empty] | 43750000 | 481250000 | 24000000 | 480000000 | 3000000 | 25000000 | [5 empty] | 14 KK | 1000000 | 14000000 | 51000000 | 76000000 | 15000000 |  | SST 36m |  | 433505181.0503 | 90466667 | 613000000 | 1046505181.0503 |  |  | APPROVED
| BOGOR BARAT | KOTA BOGOR | [7 empty] | B2S | 36 | [7 empty] | 43750000 | 481250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 30 KK | 750000 | 22500000 | 46500000 | 71500000 | 15000000 |  | SST 36m |  | 433505181.0503 | 90466667 | 537000000 | 970505181.0503 |  |  | APPROVED
| TAMBUN SELATAN BEKASI | KAB. BEKASI | [7 empty] | MCP | 20 | [7 empty] | 25000000 | 275000000 | 15000000 | 300000000 | 3000000 | 25000000 | [5 empty] | 17 KK | 500000 | 8500000 | 45000000 | 70000000 | 15000000 |  | MCP 20m |  | 140000000 | 90466667 | 421500000 | 561500000 |  |  | APPROVED
| PONDOKMELATI | KOTA BEKASI | [7 empty] | B2S | 36 | [7 empty] | 25000000 | 275000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 10 KK | 500000 | 5000000 | 49500000 | 74500000 | 15000000 |  | GM / SST 36 | 256500000 | 433505181.0503 | 90466667 | 779000000 | 1212505181.0503 |  |  | APPROVED
| JLJAWASATU | KOTA BEKASI | [7 empty] | B2S | 42 | [7 empty] | 25000000 | 275000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 88 KK | - | 44200000 | 60800000 | 85800000 | 15000000 |  | SST 42 | 256500000 | 433505181.0503 | [5 empty] | APPROVED
| MUSTIKAJAYA BEKASI | KOTA BEKASI | [7 empty] | B2S | 32 | [7 empty] | 25000000 | 275000000 | 20000000 | 200000000 | 3000000 | 25000000 | [5 empty] | 38 KK | 700000 | 26600000 | 44000000 | 69000000 | 15000000 |  | SST 32
2021 | BINTARA KENCANA TIMUR | KOTA BEKASI | [7 empty] | B2S | 27 | [7 empty] | 25000000 | 275000000 | 45000000 | 495000000 | 3000000 | 25000000 | [5 empty] | 23 KK | 1000000 | 23000000 | 47000000 | 72000000 | 15000000 | 95000000 | Minaret 27m |  | 259307105
| CIKARANG BARAT BEKASI | KAB. BEKASI | [7 empty] | MCP | 20 | [7 empty] | 25000000 | 275000000 | 15000000 | 300000000 | 3000000 | 25000000 | [5 empty] | 19 KK | 500000 | 9500000 | 45000000 | 70000000 | 15000000 |  | MCP 20m |  | 140000000 | 90466667 | 422500000 | 562500000 |  |  | APPROVED
| KUTA MEGAMENDUNG | KAB. BOGOR | [7 empty] | B2S | 52 | [7 empty] | 18750000 | 206250000 | 17500000 | 192500000 | 3000000 | 25700000 | [5 empty] | 26 KK | 500000 | 13000000 | 45300000 | 71000000 | 15000000 |  | SST 52m |  | 423293218 | 90466667 | 320200000 | 743493218 |  |  | APPROVED
| BANJAR WANGI CIAWI | KAB. BOGOR | [7 empty] | B2S | 52 | [7 empty] | 18750000 | 206250000 | 18181818.1818 | 200000000 | 3000000 | 25700000 | [5 empty] | 21 KK | 500000 | 10500000 | 40300000 | 66000000 | 15000000 |  | SST 52m |  | 423293218 | 90466667 | 320200000 | 743493218 |  |  | APPROVED
| KANTOR PUSPITEK RELOCATION | KAB. BOGOR | [7 empty] | B2S | 52 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25700000 | [5 empty] | 20 KK |  | 9600000 | 28800000 | 54500000 | 15000000 |  | SST 52m |  | 423293218 | 90466667 | 507800000 | 931093218 |  |  | APPROVED
| PANGRADIN | KAB. BOGOR | [7 empty] | B2S | 52 | [7 empty] | 18750000 | 206250000 | 15000000 | 300000000 | 3000000 | 25700000 | [5 empty] | 17 KK | 300000 | 5100000 | 40800000 | 66500000 | 15000000 |  | SST 52m |  | 423293218 | 90466667 | 415300000 | 838593218 |  |  | APPROVED
| JALAN RAGAJAYA | KAB. BOGOR | [7 empty] | B2S | 52 | [7 empty] | 18750000 | 206250000 | 25000000 | 500000000 | 3000000 | 25700000 | [5 empty] | 42 KK | 500000 | 21500000 | 47800000 | 73500000 | 15000000 |  | SST 52m |  | 423293218 | 90466667 | 638700000 | 1061993218 |  |  | APPROVED
| BOJONGGEDE_BOGOR | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 24000000 | 480000000 | 3000000 | 25000000 | [5 empty] | 36 KK | 650000 | 23400000 | 49000000 | 74000000 | 15000000 |  | SST 42m |  | 423293218
| Sabililah Citeureup | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 17000000 | 340000000 | 3000000 | 25000000 | [5 empty] | 45 KK | - | 25500000 | 47500000 | 72500000 | 15000000 |  | SST 42m |  | 353505181
| Cilliwung Pondok Rajeg | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 22500000 | 450000000 | 3000000 | 25000000 | [5 empty] | 12 KK | - | 22000000 | 40000000 | 65000000 | 15000000 |  | SST 42m |  | 353505181
| CIBEBER BARENGKOK | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 22 KK | 800000 | 17600000 | 47400000 | 72400000 | 15000000 |  | SST 42m |  | 353505181
| MEKARWANGI BOGOR | KAB. BOGOR | [7 empty] | B2S | 52 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 36 KK | - | 15600000 | 50000000 | 75000000 | 15000000 |  | SST 52m |  | 423293218
| PARUNG PANJANG BOGOR | KAB. BOGOR | [7 empty] | B2S | 52 | [7 empty] | 18750000 | 206250000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 12 KK | - | 7500000 | 51500000 | 76500000 | 15000000 |  | SST 52m |  | 423293218
| BERINGIN BATULAYANG | KAB. BOGOR | [7 empty] | B2S | 52 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 50 KK | - |  |  | 25000000
| JALAN RAYA CARIU JONGGOL | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 43 KK | 300000 | 12900000 | 52000000 | 77000000 | 15000000 |  | SST 42m |  | 353505181
| PERMANENCOMBATPUSDIKRESKRIM | KAB. BOGOR | [7 empty] | B2S | 52 | [7 empty] | 18750000 | 206250000 | 40000000 | 400000000 | 3000000 | 25000000 | [5 empty] | - | - | 0 | 70000000 | 95000000 | 0 |  | SST 52 |  | 423293218
| CIPINANG RUMPIN BOGOR | KAB. BOGOR | [7 empty] | B2S | 52 | [7 empty] | 18750000 | 206250000 | 19000000 | 190000000 | 3000000 | 25000000 | [5 empty] | 58 KK | - | 26500000 | 45000000 | 70000000 | 15000000 |  | SST 52 |  | 423293218
| BABAKAN MADANG BOGOR | KAB. BOGOR | [7 empty] | B2S | 52 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 50 KK | - | 20500000 | 49500000 | 74500000 | 15000000 |  | SST 52 |  | 423293218
| DAYEUHLUHURWARUDOYONG | KOTA SUKABUMI | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 23000000 | 460000000 | 3000000 | 25000000 | [5 empty] | 40 KK | - | 13400000 | 48000000 | 73000000 | 15000000 |  | SST 42m |  | 423293218
| PANENMAS | SUKABUMI | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 60 KK | - | 18000000 | 52000000 | 77000000 | 15000000 |  | SST 42m |  | 423293218
| AWILEGA | SUKABUMI | [7 empty] | B2S | 72 | [7 empty] | 18750000 | 206250000 | 25000000 | 500000000 | 3000000 | 25000000 | [5 empty] | 29 KK | - | 11500000 | 56500000 | 81500000 | 15000000 |  | SST 72m |  | 577.778.043
| PASIRMULYA | KOTA BOGOR | [7 empty] | B2S | 32 | [7 empty] | 43750000 | 481250000 | 30000000 | 330000000 | 3000000 | 25700000 | [5 empty] | 1 KK |  | 6000000 | 44300000 | 70000000 | 15000000 |  | RT 3m + stacking 4m + MT 25m |  | 303505181 | 90466667 | 449700000 | 753205181 |  |  | APPROVED
| DUREN MEKAR BOJONGSARI | KOTA DEPOK | [7 empty] | B2S | 32 | [7 empty] | 27272727 | 299999997 | 20000000 | 220000000 | 3000000 | 25700000 | [5 empty] | 15 KK | 500000 | 7500000 | 31300000 | 57000000 | 15000000 |  | Kamuflase Pohon 32m |  | 504809896 | 74000000 | 328200000 | 833009896 |  |  | APPROVED
| SERUA BOJONGSARI | KOTA DEPOK | [7 empty] | B2S | 32 | [7 empty] | 27272727 | 299999997 | 20000000 | 400000000 | 3000000 | 25700000 | [5 empty] | 8 KK | 500000 | 4000000 | 36300000 | 62000000 | 15000000 |  | Kamuflase Pohon 42m |  | 433505181.0503 | 74000000 | 509700000 | 943205181.0503 |  |  | APPROVED
| BERINDUNGAN | KOTA DEPOK | [7 empty] | B2S | 32 | [7 empty] | 27272727 | 299999997 | 23000000 | 460000000 | 3000000 | 25000000 | [5 empty] | 24 KK | 1000000 | 24000000 | 23300000 | 48300000 | 15000000 |  | Kamuflase Pohon 32m |  | 433505181.0503 | 74000000 | 575300000 | 1008805181.0503 |  |  | APPROVED
| TAPOS DEPOK | KOTA DEPOK | [7 empty] | B2S | 32 | [7 empty] | 27272727 | 299999997 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 15 KK | 1000000 | 15000000 | 30000000 | 55000000 | 15000000 |  | Kamuflase Pohon 32m |  | 433505181.0503
| CILANGKAP TAPOS | KOTA DEPOK | [7 empty] | B2S | 32 | [7 empty] | 27272727 | 299999997 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 29 KK | 500000 | 14500000 | 55000000 | 80000000 | 15000000 |  | Kamuflase Pohon 32m |  | 433505181.0503
| KEDUNG GUNUNG KALER | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 20000000 | 220000000 | 3000000 | 25000000 | [5 empty] | 25 KK | 500000 | 12500000 | 29000000 | 54000000 | 15000000 |  | SST 42 |  | 353505181 | 70733333 | 329500000 | 683005181 |  |  | APPROVED
| SUKAMANAH TABAN | KAB. TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 21049242 | 231541662 | 23000000 | 253000000 | 3000000 | 25000000 | [5 empty] | 18 KK | 500000 | 9000000 | 35000000 | 60000000 | 15000000 |  | SST 42 |  | 353505181 | 70733333 | 365000000 | 718505181 |  |  | APPROVED
| JL RAYA CIKANDE RANGKASBITUNG | KAB. SERANG | [7 empty] | B2S | 32 | [7 empty] | 11792929 | 129722219 | 22000000 | 242000000 | 3000000 | 25000000 | [5 empty] | 34 KK | 1000000 | 34000000 | 30000000 | 55000000 | 15000000 |  | SST 32 |  | 377220384 | 64220000 | 374000000 | 751220384 |  |  | APPROVED
| CIJERUK KIBIN | KAB. SERANG | [7 empty] | B2S | 52 | [7 empty] | 11792929 | 129722219 | 23000000 | 253000000 | 3000000 | 25000000 | [5 empty] | 32 KK | 1500000 | 48000000 | 27000000 | 52000000 | 15000000 |  | SST 52m |  | 423293218 | 64220000 | 396000000 | 819293218 |  |  | APPROVED
| TOL SERTIM CIUJUNG | KAB. SERANG | [7 empty] | B2S | 42 | [7 empty] | 11792929 | 129722219 | 45000000 | 495000000 | 3000000 | 25000000 | [5 empty] | 1 KK |  | 45000000 | 30000000 | 55000000 | 15000000 |  | SST 42 |  | 353505181 | 64220000 | 638000000 | 991505181 |  |  | APPROVED
| CISAIT KRAGILAN | KAB. SERANG | [7 empty] | B2S | 42 | [7 empty] | 11792929 | 129722219 | 16000000 | 176000000 | 3000000 | 25000000 | [5 empty] | 18 KK | 500000 | 9000000 | 46000000 | 71000000 | 15000000 |  | SST 42 |  | 353505181 | [5 empty] | APPROVED
| SITUTERATECIKANDE | KAB. SERANG | [7 empty] | B2S | 42 | [7 empty] | 11792929 | 129722219 | 18000000 | 198000000 | 3000000 | 25000000 | [5 empty] | 27 KK | 500000 | 13500000 | 50000000 | 75000000 | 15000000 |  | SST 42 |  | 353505181
| TAMAN PUSPA CIKUPA | KAB. TANGERANG | [7 empty] | B2S | 32 | [7 empty] | 21049242 | 231541662 | 26000000 | 520000000 | 3000000 | 25000000 | [9 empty] | 25000000 | [5 empty] | 64220000 | 573000000 | 573000000 |  |  | APPROVED
| PAMULANG PERMAI BARAT | KOTA TANGERANG SELATAN | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 15000000 | 165000000 | 3000000 | 15000000 | [7 empty] | 66000000 |  | 15000000 | 15000000 |  | MCP Non FO 20 |  | 170000000 | 64220000 | 279000000 | 449000000 |  |  | APPROVED
| KOMPLEKS SASMITA LOKA PAMULANG BARAT | KOTA TANGERANG SELATAN | [7 empty] | MCP | 25 | [7 empty] | 35000000 | 385000000 | 17000000 | 187000000 | 3000000 | 15000000 | [5 empty] | 20KK | 750000 | 15000000 | 38000000 | 53000000 | 15000000 |  | MCP Non FO 25 |  | 170000000
| Ciater Serpong | KOTA TANGERANG SELATAN | [7 empty] | MCP | 25 | [7 empty] | 35000000 | 385000000 | 16000000 | 176000000 | 3000000 | 15000000 | [5 empty] | 24 KK | 750000 | 18000000 | 35000000 | 50000000 | 15000000 |  | MCP Non FO 25 |  | 170000000
| VILLA MELATI MAS RAYA | KOTA TANGERANG SELATAN | [7 empty] | MCP | 25 | [7 empty] | 35000000 | 385000000 | 19000000 | 209000000 | 3000000 | 15000000 | [5 empty] | 15 KK | - | 12000000 | 38000000 | 53000000 | 15000000 |  | MCP Non FO 25 |  | 170000000
| VILLA MELATI MAS RAYA_Rev | KOTA TANGERANG SELATAN | [7 empty] | MCP | 25 | [7 empty] | 35000000 | 385000000 | 19000000 | 209000000 | 3000000 | 15000000 | [5 empty] | 15 KK | - | 12000000 | 48000000 | 63000000 | 15000000 |  | MCP Non FO 25 |  | 170000000
2021 | WIJAYAKUSUMA CEGER | KOTA TANGERANG SELATAN | [7 empty] | MCP | 25 | [7 empty] | 21179826 | 232978086 | 18000000 | 180000000 | 3000000 | 15000000 | [5 empty] | 19 KK | 500000 | 9000000 | 68500000 | 83500000 | 15000000 | 92500000 | MCP Non FO 20 |  | 140000000
| Djuna Raya Pakujaya | KOTA TANGERANG SELATAN | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 18000000 | 198000000 | 3000000 | 15000000 | [5 empty] | 20 KK | 1000000 | 20000000 | 53000000 | 68000000 | 15000000 |  | MCP Non FO 20 |  | 170000000
| UNIVERSITAS TERBUKA PAMULANG | KOTA TANGERANG SELATAN | [7 empty] | MCP | 25 | [7 empty] | 35000000 | 385000000 | 19000000 | 209000000 | 3000000 | 15000000 | [5 empty] | 10 KK | 1000000 | 10000000 | 66000000 | 81000000 | 15000000 |  | MCP Non FO 25 |  | 170000000
| BERANDA SERPONG | KOTA TANGERANG SELATAN | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 20000000 | 220000000 | 3000000 | 15000000 | [5 empty] | 12 KK | - | 12500000 | 58000000 | 73000000 | 15000000 |  | MCP Non FO 20 |  | 170000000
| DISCOVERY CONSERVA | KOTA TANGERANG SELATAN | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 17000000 | 187000000 | 3000000 | 15000000 | [5 empty] | 20 KK | 750000 | 15000000 | 55000000 | 70000000 | 15000000 |  | MCP Non FO 20 |  | 170000000
| SITU GINTUNG CIREUNDEU | KOTA TANGERANG SELATAN | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 20000000 | 220000000 | 3000000 | 15000000 | [5 empty] | 7 KK | 1250000 | 8750000 | 65000000 | 80000000 | 15000000 |  | MCP Non FO 20 |  | 170000000
| GN RAYA CIREUNDEU | KOTA TANGERANG SELATAN | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 20000000 | 220000000 | 3000000 | 15000000 | [5 empty] | 17 KK | 1000000 | 17000000 | 59500000 | 74500000 | 15000000 |  | MCP Non FO 20 |  | 170000000
| JALAN MENTAWAI TOL | KOTA TANGERANG SELATAN | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 15000000 | 150000000 | 3000000 | 15000000 | [5 empty] | 20 KK | 500000 | 10000000 | 74000000 | 89000000 | 15000000 |  | MCP Non FO 20 |  | 170000000
| KENANGA WALUYA | KAB. BEKASI | [7 empty] | B2S | 52 | [7 empty] | 25000000 | 275000000 | 24000000 | 480000000 | 3000000 | 25700000 | [5 empty] | 24 KK | 500000 | 12000000 | 39300000 | 65000000 | 15000000 |  | SST 52m |  | 423293218 | 60000000 | 600700000 | 1023993218 |  |  | APPROVED
| TELUKJAMBE TIMUR | KARAWANG | [7 empty] | B2S | 32 | [7 empty] | 25000000 | 275000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 25 KK |  | 16000000 | 52500000 | 77500000 | 15000000 |  | SST 32m |  | 423293218 | [5 empty] | APPROVED
| TELUKJAMBE TIMUR_KAND D | KARAWANG | [7 empty] | B2S | 36 | [7 empty] | 25000000 | 275000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 13 KK | 500000 | 6500000 | 58500000 | 83500000 | 15000000 |  | SST 42m |  | 423293218
| BELENDUNGKLARI | KARAWANG | [7 empty] | B2S | 42 | [7 empty] | 25000000 | 275000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 40 KK | 500000 | 20000000 | 49000000 | 74000000 | 15000000 |  | SST 42 |  | 423293218
| JLRAYACIKUNGKUNG | KARAWANG | [7 empty] | B2S | 42 | [7 empty] | 25000000 | 275000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 44 KK | - | 39250000 | 34000000 | 59000000 | 15000000 |  | SST 42 |  | 423293218
| PERUMAHANRESINDA | KARAWANG | [7 empty] | B2S | 42 | [7 empty] | 25000000 | 275000000 | 17000000 | 340000000 | 3000000 | 25000000 | [5 empty] | 29 KK | - | 18500000 | 50500000 | 75500000 | 15000000 |  | SST 42 |  | 423293218
| RSU TANGERANG | KOTA TANGERANG | [7 empty] | B2S | 32 | [7 empty] | 35000000 | 385000000 | 26000000 | 520000000 | 3000000 | 25700000 | [5 empty] | 14 KK | 1000000 | 14000000 | 20000000 | 45700000 | 15000000 |  | Kamuflase Pohon 32m |  | 504809896 | 60000000 | 623400000 | 1128209896 |  |  | APPROVED
| KARAWACI 850 | KOTA TANGERANG | [7 empty] | B2S | MT 20 | [7 empty] | 35000000 | 385000000 | 25000000 | 500000000 | 3000000 | [6 empty] | 12 KK | 1500000 | 18000000 | 55000000 | 55000000 | 15000000 |  | MT 25 |  | 504809896
| Kedaung Wetan Neglasari | KOTA TANGERANG | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 15000000 | 300000000 | 3000000 | 15000000 | [5 empty] | 11 KK | 1500000 | 16500000 | 35500000 | 50500000 | 15000000 |  | MCP 20 m |  | 170000000
| Mawi Kunciran Indah | KOTA TANGERANG | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 20000000 | 400000000 | 3000000 | 15000000 | [5 empty] | 19 KK | 500000 | 9500000 | 65500000 | 80500000 | 15000000 |  | MCP 20 m |  | 170000000
| Karang Timur Tangerang | KOTA TANGERANG | [7 empty] | B2S | 32 | [7 empty] | 35000000 | 385000000 | 24000000 | 480000000 | 3000000 | 25000000 | [5 empty] | 40 KK | 750000 | 30000000 | 44000000 | 69000000 | 15000000 |  | Kamuflase Pohon 32m |  | 504809896
| Elang Sawah | KOTA TANGERANG | [7 empty] | MCP | 25 | [7 empty] | 35000000 | 385000000 | 17000000 | 340000000 | 3000000 | 15000000 | [5 empty] | 12 KK | 1500000 | 18000000 | 36000000 | 51000000 | 15000000 |  | MCP 25m
| PASIR JAYA JATIUWUNG | KOTA TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 35000000 | 385000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 30 KK | 700000 | 21000000 | 53000000 | 78000000 | 15000000 |  | SST 42 |  | 353505181
| ALAM JAYA JATIUWUNG | KOTA TANGERANG | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 19000000 | 380000000 | 3000000 | 15000000 | [5 empty] | 7 KK | 500000 | 3500000 | 76500000 | 91500000 | 15000000 |  | MCP 20 m |  | 140000000
| Pandawa Cibodas | KOTA TANGERANG | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 18000000 | 360000000 | 3000000 | 15000000 | [5 empty] | 17 KK | 500000 | 8500000 | 65500000 | 80500000 | 15000000 |  | MCP 20 m |  | 140000000
| SMPN 14 Tangerang | KOTA TANGERANG | [7 empty] | MCP | 20 | [7 empty] | 35000000 | 385000000 | 17000000 | 340000000 | 3000000 | 15000000 | [5 empty] | 13 KK | 500000 | 6500000 | 63500000 | 78500000 | 15000000 |  | MCP 20 m |  | 140000000
| JL KAYU PUTIH RAYA | JAKARTA TIMUR | [7 empty] | B2S | 26 | [9 empty] | 40000000 | 200000000 | 3000000 | 25700000 | [5 empty] | 1 KK |  |  | 54300000 | 80000000 | 160000000 |  | Kamuflase Pohon 26m |  | 477646529 | [5 empty] | APPROVED
| LUBANG BUAYA CIPAYUNG | JAKARTA TIMUR | [7 empty] | MCP | 20 | [9 empty] | 17000000 | 85000000 | [11 empty] | 0 |  |  | MCP Non FO 20 |  | 140000000
| Nyiur Pondok Kelapa | JAKARTA TIMUR | [7 empty] | MCP | 20 | [9 empty] | 19000000 | 209000000 | [11 empty] | 0 |  |  | MCP Non FO 20 |  | 140000000
| Krama Yudha Cakung | JAKARTA TIMUR | [7 empty] | MCP | 20 | [9 empty] | 18181818.1818 | 200000000 | [14 empty] | MCP Non FO 20 |  | 140000000
| Menteng Lenteng Agung | JAKARTA SELATAN | [7 empty] | MCP | 20 | [9 empty] | 20000000 | 100000000 | [11 empty] | 0 | 15000000 |  | MCP Non FO 20 |  | 140000000
| Jalan Asem Cipedak | JAKARTA SELATAN | [7 empty] | MCP | 21 | [9 empty] | 19000000 | 190000000 | [11 empty] | 0 |  |  | MCP Non FO 21
| Jalan Pemuda Cipedak | JAKARTA SELATAN | [7 empty] | MCP | 20 | [9 empty] | 18000000 | 90000000 | [11 empty] | 0 |  |  | MCP Non FO 20 |  | 140000000
| Jalan Garuda Mas | JAKARTA SELATAN | [7 empty] | MCP | 25 | [9 empty] | 17000000 | 85000000 | [11 empty] | 0 |  |  | MCP Non FO 25 |  | 140000000
| Kemuning Matraman_Kand E | JAKARTA SELATAN | [7 empty] | MCP | 25 | [9 empty] | 17000000 | 85000000 | [11 empty] | 0 |  |  | MCP Non FO 25 |  | 140000000
| JLKOSTRAD | JAKARTA SELATAN | [7 empty] | MCP | 20 | [9 empty] | 17500000 | 175000000 | [14 empty] | MCP Non FO 20 |  | 140000000
| Benda Ciganjur | JAKARTA SELATAN | [7 empty] | MCP | 20 | [9 empty] | 18000000 | 90000000 | [11 empty] | 0 |  |  | MCP Non FO 20 |  | 140000000
| KEBONBARUTEBET | JAKARTA SELATAN | [7 empty] | MCP | 20 | [9 empty] | 17000000 | 170000000 | [14 empty] | MCP Non FO 20 |  | 140000000
| Pegadungan Tegal Alur | JAKARTA BARAT | [7 empty] | MCP | 25 | [9 empty] | 17000000 | 85000000 | [11 empty] | 0 |  |  | MCP Non FO 25
| Sabar Raya Kemajuan | JAKARTA SELATAN | [7 empty] | MCP | 20 | [9 empty] | 18000000 | 90000000 | [7 empty] | 8 KK |  |  |  | 0 |  |  | MCP Non FO 20 |  | 140000000
| PERMANENCOMBATTERMPENUMPANG | JAKARTA UTARA | [7 empty] | MCP | 20 | [9 empty] | 35280000 | 215387928 | [11 empty] | 0 |  |  | MCP Non FO 20 |  | 140000000
| PERMANENCOMBATKEPANDUANPELINDO | JAKARTA UTARA | [7 empty] | MCP | 20 | [9 empty] | 35280000 | 215387928 | [11 empty] | 0 |  |  | MCP Non FO 20 |  | 140000000
| Tol Pelabuhan Ancol | JAKARTA UTARA | [7 empty] | MCP | 20 | [9 empty] | 18500000 | 185000000 | [14 empty] | MCP Non FO 20 |  | 140000000
| DUFAN MARINA | JAKARTA UTARA | [7 empty] | POLE | 6m | [9 empty] | 45454545.4545 | 500000000 | [14 empty] | Pole 6m |  | 259132869
| LONTAR DALAM KOJA | JAKARTA UTARA | [7 empty] | MCP | 20 | [9 empty] | 19000000 | 190000000 | [14 empty] | MCP Non FO 20 |  | 140000000
| SITU COGARONGSONG PENGASINAN | KAB. BOGOR | [7 empty] | B2S | 42 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 27 KK | - | 21500000 | 50000000 | 75000000 | 15000000 |  | SST 42 |  | 353505181
| PONDOK CABE RAYA | TANGERANG SELATAN | [7 empty] | MCP | 20 | [7 empty] | 18750000 | 206250000 | 18000000 | 180000000 | 3000000 | 25000000 | [5 empty] | 22 KK | 500000 | 11000000 | 55000000 | 80000000 | 15000000 |  | MCP 20m |  | 140000000 | 90466667 | 314000000 | 454000000 |  |  | APPROVED
2021 | TAMAN GOLF BOULEVARD | KOTA TANGERANG | [7 empty] | MCP | 20 | [7 empty] | 18750000 | 206250000 |  |  | 3000000 | 15000000 | [5 empty] | 6 KK | 1000000 | 6000000 | 72000000 | 71000000 | 15000000 | 77000000 | MCP 20m |  | 140000000
2021 | JLBUDIMULYAUTARA | KOTA JAKARTA UTARA | [7 empty] | MCP | 20 | [7 empty] | 18750000 | 206250000 | 20000000 | 220000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  |  | MCP NON FO 20 |  | PO LUMPSUM
2021 | SWASEMBADA TANJUNG PRIOK | KOTA JAKARTA UTARA | [7 empty] | MCP | 20 | [7 empty] | 18750000 | 206250000 | 18000000 | 180000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  |  | MCP NON FO 20 |  | 140000000
| ALFAMART TIPAR CAKUNG 2 | KOTA JAKARTA UTARA | [7 empty] | MCP | 20 | [7 empty] | 18750000 | 206250000 | 15000000 | 150000000 |  | 15000000 | [5 empty] | 7 KK | 500000 | 3500000 | 54500000 | 69500000 |  |  | MCP 20m |  | 140000000
2021 | CITEUREUP BOGOR 2 | BOGOR | [7 empty] | SST | 52 | [7 empty] | 18750000 | 206250000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 23 KK | 500000 | 16000000 | 52000000 | 77000000 | 15000000 | 93000000 | SST 52M |  | 423293218
2021 | WALANTAKA KOTA SERANG | SERANG | [7 empty] | SST | 52 | [7 empty] | 18750000 | 206250000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 88 KK | 300000 | 21500000 | 45500000 | 70500000 | 15000000 | 92000000 | SST 52m |  | 423293218
| JALAN KUBUR ISLAM | JAKARTA SELATAN | [7 empty] | MCP | 20 | [7 empty] | 18750000 | 206250000 | 20000000 | 200000000 | 3000000 | 15000000 | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  | MCP 20m |  | 140000000
| Newsite2195 | SERANG | [7 empty] | SST | 42 | [7 empty] | 18750000 | 206250000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 33 KK + 2 Tokoh Masyarakat | 300000 + 2000000 | 13900000 | 45000000 | 70000000 | 15000000 |  | SST 42m |  | 353505181
2021 | JALAN R. A. FADILLAH | JAKARTA TIMUR | [7 empty] | MCP | 20 | [7 empty] | 18750000 | 206250000 | 20000000 | 100000000 | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  | MCP 20m |  | 140000000
| M. KAHFI 3 | JAKARTA SELATAN | [7 empty] | MCP | 20 | [7 empty] | 18280000 | 182800000 | 17000000 | 170000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  | MCP 20m |  | PO LUMPSUM
2021 | PARUNG PANJANG GOROWONG | BOGOR | [7 empty] | SST | 62 | [7 empty] | 20300000 | 406000000 | 17000000 | 340000000 | 3000000 | 25000000 | [5 empty] | 19 KK | 500000 | 9500000 | 57000000 | 82000000 | 15000000 | 91500000 | SST 62m |  | 527299431
2021 | TENJOLAYA BOGOR | BOGOR | [7 empty] | SST | 52 | [7 empty] | 20300000 | 406000000 | 17000000 | 340000000 | 3000000 | 25000000 | [5 empty] | 24 KK | 1000000 + 1500000 | 25500000 | 43500000 | 68500000 | 15000000 | 94000000 | SST 52m |  | 423293218
2021 | GUNUNG SINDUR JAWA BARAT | BOGOR | [7 empty] | SST | 52 | [7 empty] | 20300000 | 406000000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 32 KK | 500000 | 18500000 | 55500000 | 80500000 | 15000000 | 99000000 | SST 52m |  | 423293218
2021 | CIPONDOH KOTA TANGERANG | KOTA TANGERANG | [7 empty] | SST | 32 | [7 empty] | 23500000 | 470000000 | 20000000 | 220000000 | 3000000 | 25000000 | [5 empty] | 25 KK | 500000 | 12500000 | 61500000 | 86500000 | 15000000 | 99000000 | SST 32m |  | 377220384
2021 | GUNUNG KALER TANGERANG | TANGERANG | [7 empty] | SST | 52 | [7 empty] | 19600000 | 392000000 | 15000000 | 300000000 | 3000000 | 25000000 | [5 empty] | 19 KK | 500000 | 9500000 | 46000000 | 71000000 | 15000000 | 80500000 | SST 52m |  | 423293218
2021 | WARUNG KIARA SUKABUMI | SUKABUMI | [7 empty] | SST | 62 | [7 empty] | 22500000 | 450000000 | 17000000 | 340000000 | 3000000 | 25000000 | [5 empty] | 38 KK | 500000 | 19000000 | 47000000 | 72000000 | 15000000 | 91000000 | SST 62m |  | 527299431
2021 | CIBUNGBULANG BOGOR 2 | BOGOR | [7 empty] | SST | 62 | [7 empty] | 20300000 | 406000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 23 KK | 700000 | 16100000 | 57500000 | 82500000 | 15000000 | 98600000 | SST 62m |  | 527299431
2021 | TIGARAKSA TANGERANG 2 | TANGERANG | [7 empty] | SST | 52 | [7 empty] | 19603448 | 392068960 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 43 KK | 300000 | 25500000 | 44500000 | 69500000 | 15000000 | 95000000 | SST 52m |  | 423293218
2021 | PASAR CISAATSKB | SUKABUMI | [7 empty] | SST | 52 | [7 empty] | 22500000 | 450000000 | 23000000 | 253000000 | 3000000 | 25000000 | [5 empty] | 11 KK + 4 KK | 1000000 & 2500000 | 21000000 | 53500000 | 78500000 | 15000000 | 99500000 | SST 52m |  | 423293218
2021 | PARUNG KUDA SUKABUMI | SUKABUMI | [7 empty] | SST | 52 | [7 empty] | 22500000 | 450000000 | 30000000 | 330000000 | 3000000 | 25000000 | [5 empty] | 1 Perusahaan + 4 KK | 1000000 | 5000000 | 61500000 | 86500000 | 15000000 | 91500000 | SST 52m | 423293218 | 423293218
2021 | PERMANENTCOMBATCIKANDEPERMAI | SERANG | [7 empty] | SST | 42 | [7 empty] | 17000000 | 340000000 | 20000000 | 220000000 | 3000000 | 25000000 | 1 Perusahaan + 4 KK | 1000000 | 5000000 | 61500000 | 86500000 | 31 KK | 400000 | 12400000 | 56600000 | 81600000 | 15000000 | 94000000 | SST 42m |  | 353505181
2021 | GUNUNG SINDUR BOGOR | BOGOR | [7 empty] | SST | 52 | [7 empty] | 20300000 | 406000000 | 17000000 | 340000000 | 3000000 | 25000000 | [5 empty] | 53 KK | 1500000 + 500000 + 250000 | 29750000 | 45000000 | 70000000 | 15000000 | 99750000 | SST 52m |  | 423293218
2021 | LEUWILIANG BOGOR | BOGOR | [7 empty] | SST | 62 | [7 empty] | 20300000 | 406000000 | 20000000 | 200000000 | 3000000 | 25000000 | [5 empty] | 77 KK | 1000000 | 32800000 | 40200000 | 65200000 | 15000000 | 98000000 | SST 52m |  | 423293218
2021 | KOSAMBI TANGERANG | TANGERANG | [7 empty] | SST | 32 | [7 empty] | 19600000 | 392000000 | 18181818 | 200000000 | 3000000 | 25000000 | [5 empty] | 40 KK | 300000 | 12000000 | 60000000 | 85000000 | 15000000 | 97000000 | SST 32m |  | 336315892
2021 | STAKALIDERES | JAKARTA BARAT | [7 empty] | MCP | 25 | [7 empty] | 17000000 | 340000000 | 18500000 | 370000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | 25 KK | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  | MCP 25m |  | 262625556
2021 | CURUGBADAKMAJA | LEBAK | [7 empty] | SST | 52 | [7 empty] | 21179826 | 423596520 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 18 KK | 500000 | 9000000 | 61000000 | 86000000 | 15000000 | 95000000 | SST 52m |  | 423293218
2021 | NEGLASARINEGLASARI | KOTA TANGERANG | [7 empty] | MCP | 25 | [7 empty] | 23500000 | 470000000 | 17000000 | 170000000 | 3000000 | 15000000 | [5 empty] | 10 KK | 500000 + 700000 | 5200000 | 68000000 | 83000000 | 15000000 | 88200000 | MCP 25m |  | 262625556
2021 | PONDOKRANGGONCIPAYUNG | JAKARTA TIMUR | [7 empty] | MCP | 25 | [7 empty] | 18750000 | 206250000 | 17000000 | 340000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  | MCP 25m |  | 262625556
2021 | CURUGBITUNGNANGGUNG | BOGOR | [7 empty] | SST | 52 | [7 empty] | 20300000 | 406000000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 35 KK |  | 14600000 | 53500000 | 78500000 | 15000000 | 93100000 | SST 52m |  | 423293218
2021 | PARADISESERPONG2 | KOTA TANGERANG SELATAN | [7 empty] | MCP | 25 | [7 empty] | 35000000 | 385000000 | 16000000 | 320000000 | 3000000 | 15000000 | [5 empty] | 16 KK | 500000 | 8000000 | 50000000 | 65000000 | 15000000 | 73000000 | MCP 25m |  | 262625556
2021 | LIMO KOTA DEPOK | KOTA DEPOK | [7 empty] | B2S | 32 | [7 empty] | 27272727 | 299999997 | 25000000 | 500000000 | 3000000 | 25000000 | [5 empty] | 25 KK | 1000000 | 25000000 | 48100000 | 73100000 | 15000000 | 98100000 | Kamuflase Pohon 32m |  | 433505181.0503
2021 | SUKAJAYASALABINTANA | SUKABUMI | B2S | 32 | 27272727 | 299999997 | 25000000 | 500000000 | 3000000 | B2S | 52 | 1000000 | 25000000 | 48100000 | 73100000 | 15000000 | Kamuflase Pohon 32m | 433505181.0503 | 22500000 | 450000000 | 22000000 | 440000000 | 3000000 | 25000000 | [5 empty] | 32 KK |  | 19000000 | 48000000 | 73000000 | 15000000 | 92000000 | SST 52m | 423293218 | 423293218
| PASARBARUKARAWACI | KOTA TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 23500000 | 470000000 | 20000000 | 200000000 | 3000000 | 25000000 | [5 empty] | 20 KK | 1000000 | 20000000 | 50000000 | 75000000 | 15000000 |  | SST 42m |  | 353505181
2021 | MANYARKALIDERES | JAKARTA BARAT | [7 empty] | MCP | 25 | [7 empty] | 17000000 | 340000000 | 20000000 | 400000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  | MCP 25m |  | 262625556
2021 | KOSAMBI BANTEN | TANGERANG | [7 empty] | SST | 42 | [7 empty] | 19600000 | 392000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 37 KK | 33 KK @ Rp 1000000 + 4 KK @Rp 1500000 | 39000000 | 30000000 | 55000000 | 15000000 | 94000000 | SST 42m |  | 353505181
2021 | PAMIJAHAN BOGOR 2 | BOGOR | [7 empty] | SST | 52 | [7 empty] | 20300000 | 406000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 68 KK |  | 24800000 | 45200000 | 70200000 | 15000000 | 95000000 | SST 52m |  | 423293218
2021 | PERUMAHANCIBARUSAHJAYA | BEKASI | [7 empty] | SST | 42 | [7 empty] | 25000000 | 275000000 | 17500000 | 350000000 | 3000000 | 25000000 | [5 empty] | 22 KK | 1000000 | 22000000 | 48000000 | 73000000 | 15000000 | 95000000 | SST 42 |  | 433505181.0503
| PASIRJAYAJATIUWUNG | KOTA TANGERANG | [7 empty] | SST | 42 | [9 empty] | 30000000 | 300000000 | 3000000 | 25000000 | [5 empty] | 24 KK |  | 14500000 | -39500000 | -14500000 | 15000000 |  | SST 42m |  | 353505181
2021 | CILANDAKBAWAH | JAKARTA SELATAN | [7 empty] | MCP | 25 | [7 empty] | 17000000 | 340000000 | 18000000 | 360000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  | MCP 25m |  | 262625556
2021 | BOGOR BOJONG GEDE | BOGOR | [7 empty] | SST | 42 | [7 empty] | 20300000 | 406000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 40 KK | 500000 | 20000000 | 44500000 | 69500000 | 15000000 | 89500000 | SST 42m |  | 353505181
2021 | TANGERANG KOSAMBI | TANGERANG | [7 empty] | SST | 32 | [7 empty] | 19600000 | 392000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 45 KK | 300000 | 13500000 | 51500000 | 76500000 | 15000000 | 90000000 | SST 32m |  | 336315892
2021 | KARAWANG MAJALAYA | KARAWANG | [7 empty] | SST | 42 | [7 empty] | 19000000 | 380000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 25 KK | 500000 + 1500000 | 17500000 | 50500000 | 75500000 | 15000000 | 93000000 | SST 42m |  | 353505181
| BENCONGANKELAPADUA | TANGERANG | [7 empty] | SST | 52 | [7 empty] | 19600000 | 392000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 69 KK | 500000 + 1000000 | 41000000 | 50000000 | 75000000 | 15000000 | 116000000 | SST 52m |  | 423293218
2021 | PERUMAHAN KSB | BEKASI | [7 empty] | SST | 32 | [7 empty] | 15000000 | 300000000 | 25000000 | 250000000 | 3000000 | 25000000 | [5 empty] | 15 KK | 500000 | 7500000 | 51000000 | 76000000 | 15000000 | 83500000 | SST 32m |  | 336315892
2021 | DURI TAMBORA | JAKARTA UTARA | [7 empty] | POLE | 9 | [7 empty] | 27000000 | 540000000 | 35000000 | 350000000 | 3000000 | 25000000 | [5 empty] | 1 KK | 1000000 | 1000000 | 72000000 | 97000000 | 15000000 | 98000000 | Pole 9m |  | 141516308
2021 | SUKABUMI CIKIDANG | SUKABUMI | [7 empty] | B2S | 72 | [7 empty] | 22500000 | 450000000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 27 KK | 500000 + 1000000 | 14500000 | 51500000 | 76500000 | 15000000 | 91000000 | SST 72m |  | 577778043
2021 | SWASEMBADABARATJAKUT | JAKARTA UTARA | [7 empty] | MCP | 25 | [7 empty] | 18750000 | 206250000 |  |  | 3000000 | 15000000 | [5 empty] | 6 KK | 2500000 | 15000000 | 55000000 | 70000000 | 15000000 | 85000000 | MCP 25m |  | 262625556
2021 | PERMANENTCMBTLIONAIR | TANGERANG | [7 empty] | MT | 25 | [7 empty] | 19600000 | 392000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 7 KK | 500000 | 3500000 | 81500000 | 106500000 | 15000000 | 110000000 | MT 25m |  | 259307105
2021 | JALUPANGMULYA | LEBAK | [7 empty] | SST | 62 | [7 empty] | 21179826 | 423596520 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 5 KK | 1000000 | 5000000 | 60500000 | 85500000 | 15000000 | 90500000 | SST 62m |  | 527299431
2021 | DESAPANGGUKINGAN | PANDEGLANG | [7 empty] | SST | 52 | [7 empty] | 21179826 | 423596520 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 6 KK | 1000000 | 6000000 | 63000000 | 88000000 | 15000000 | 94000000 | SST 52m |  | 423293218
2021 | RUMPINTAMANSARI | BOGOR | [7 empty] | SST | 42 | [7 empty] | 20300000 | 406000000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 33 KK | 500000 | 16500000 | 48000000 | 73000000 | 15000000 | 89500000 | SST 42m |  | 353505181
2021 | CILAMAYA KULONPASIRJAYA | KARAWANG | [7 empty] | SST | 52 | [7 empty] | 19000000 | 380000000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 20 KK | 500000 + 1500000 | 15000000 | 54000000 | 79000000 | 15000000 | 94000000 | SST 52m |  | 423293218
2021 | RANCAGEDEGUNUNGKALER | TANGERANG | [7 empty] | SST | 42 | [7 empty] | 19600000 | 392000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 24 KK | 500000 + 1000000 | 14000000 | 41000000 | 66000000 | 15000000 | 80000000 | SST 42m |  | 353505181
2021 | MEKARWANGITANAHSEREAL | KOTA BOGOR | [7 empty] | SST | 42 | [7 empty] | 22000000 | 440000000 | 25000000 | 500000000 | 3000000 | 25000000 | [5 empty] | 60 KK | 500000 + 1000000 | 45000000 | 29500000 | 54500000 | 15000000 | 99500000 | SST 42m |  | 353505181
2021 | PARUNG PANJANGJAGABITA | BOGOR | [7 empty] | SST | 62 | [7 empty] | 20300000 | 406000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 31 KK | 500000 | 15500000 | 49500000 | 74500000 | 15000000 | 90000000 | SST 62m |  | 527299431
2021 | KAREOJAWILAN | SERANG | [7 empty] | SST | 52 | [7 empty] | 17000000 | 340000000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 9 KK | 500000 | 4500000 | 58000000 | 83000000 | 15000000 | 87500000 | SST 52m |  | 423293218
2021 | SOLEARTANGERANG | TANGERANG | [7 empty] | SST | 52 | [7 empty] | 19600000 | 392000000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 30 KK | 1000000 | 30000000 | 40000000 | 65000000 | 15000000 | 95000000 | SST 52m |  | 423293218
2021 | RAJEG_TANJAKANMEKAR | TANGERANG | [7 empty] | SST | 52 | [7 empty] | 19600000 | 392000000 | 25000000 | 500000000 | 3000000 | 25000000 | [5 empty] | 57 KK | 1000000 + 500000 | 43500000 | 26500000 | 51500000 | 15000000 | 95000000 | SST 52m |  | 423293218
2021 | H. BAPING | JAKARTA TIMUR | [7 empty] | SST | 32 | [7 empty] | 18750000 | 206250000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 17 KK | 2500000 + 1000000 | 20000000 | 48500000 | 73500000 | 15000000 | 93500000 | MT 25m |  | 259307105
2021 | SUDAJAYAGIRANGSKB | SUKABUMI | [7 empty] | SST | 52 | [7 empty] | 22500000 | 450000000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 40 KK | 2000000 + 500000 | 26000000 | 44500000 | 69500000 | 15000000 | 95500000 | SST 52m |  | 423293218
2021 | CIPEUCANG | BOGOR | [7 empty] | SST | 52 | [7 empty] | 20300000 | 406000000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 43 KK | 500000 + 300000 | 16900000 | 50500000 | 75500000 | 15000000 | 92400000 | SST 52m |  | 423293218
2021 | RAYAKRONJOMEKARBARU | TANGERANG | [7 empty] | SST | 62 | [7 empty] | 19600000 | 392000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 55 KK | 1000000 + 500000 | 28500000 | 44000000 | 69000000 | 15000000 | 97500000 | SST 62m |  | 527299431
2021 | PKP KAHREKEL BOGOR | BOGOR | [7 empty] | SST | 62 | [7 empty] | 20300000 | 406000000 | 17000000 | 170000000 | 3000000 | 25000000 | [5 empty] | 27 KK | 500000 | 13500000 | 59500000 | 84500000 | 15000000 | 98000000 | SST 62m |  | 527299431
2021 | PERMANENDANGDANGCISAUK2 | TANGERANG | [7 empty] | SST | 42 | [7 empty] | 19600000 | 392000000 | 20000000 | 200000000 | 3000000 | 25000000 | [5 empty] | 10 KK | 500000 | 5000000 | 62000000 | 87000000 | 15000000 | 92000000 | SST 42m |  | 353505181
2021 | TBG KLARI | KARAWANG | [7 empty] | SST | 42 | [7 empty] | 19000000 | 380000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 21 KK | 1500000 | 31500000 | 38500000 | 63500000 | 15000000 | 95000000 | SST 42m |  | 353505181
2021 | CIKARANG CILAMAYA WETAN | KARAWANG | [7 empty] | SST | 52 | [7 empty] | 19000000 | 380000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 42 KK | 1000000 + 750000 + 300000 | 31200000 | 40800000 | 65800000 | 15000000 | 97000000 | SST 52m |  | 423293218
2021 | KARAWANG BARATMEKARJATI | KARAWANG | [7 empty] | SST | 52 | [7 empty] | 19000000 | 380000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 48 KK | 1000000 + 500000 | 26500000 | 36500000 | 61500000 | 15000000 | 88000000 | SST 52m |  | 423293218
2021 | PERMANENCOMBATTIRTAWARNARUMPIN | BOGOR | [7 empty] | SST | 42 | [7 empty] | 20300000 | 406000000 | 25000000 | 500000000 | 3000000 | 25000000 | [5 empty] | 53 KK |  | 17000000 | 57400000 | 82400000 | 15000000 | 99400000 | SST 42m |  | 353505181
2021 | PERMANENPERUMSERANGSELALU | BEKASI | [7 empty] | SST | 42 | [7 empty] | 25000000 | 275000000 | 22500000 | 450000000 | 3000000 | 25000000 | [5 empty] | 74 KK | 300000 | 22200000 | 49000000 | 74000000 | 15000000 | 96200000 | SST 42m |  | 353505181
2021 | JAKARTA UTARA PADEMANGAN | JAKARTA UTARA | [7 empty] | MCP | 25 | [7 empty] | 18750000 | 206250000 | 18000000 | 360000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  |  | MCP 25m |  | 262625556
2021 | RAGUNANRAYA | JAKARTA SELATAN | [7 empty] | MT | 25 | [7 empty] | 17000000 | 340000000 | 45000000 | 450000000 | 3000000 | 25000000 | [5 empty] | 35 KK |  | 15000000 | 31000000 | 56000000 | 15000000 | 71000000 | MT 25m |  | 259307105
2021 | TANJUNGJAMPANGKULON | SUKABUMI | [7 empty] | SST | 52 | [7 empty] | 22500000 | 450000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 45 KK | 1000000 + 500000 | 25500000 | 45500000 | 70500000 | 15000000 | 96000000 | SST 52m |  | 423293218
2021 | JAKARTA BARAT CENGKARENG - 1 | JAKARTA BARAT | [7 empty] | MCP | 25 | [7 empty] | 17000000 | 340000000 | 18000000 | 360000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  |  | MCP 25m |  | 262625556
2021 | PERMANENCOMBATPTPUTIK | JAKARTA TIMUR | [7 empty] | MCP | 25 | [7 empty] | 18750000 | 206250000 | 17000000 | 340000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  |  | MCP 25m |  | 262625556
2021 | PERMANENDRIYACATANIA | TANGERANG | [7 empty] | SST | 42 | [7 empty] | 19600000 | 392000000 | 22000000 | 220000000 | 3000000 | 25000000 | [5 empty] | 35 KK | 300000 | 10500000 | 57500000 | 82500000 | 15000000 | 93000000 | SST 42m |  | 353505181
2021 | RELOCKOSAMBIBARU | JAKARTA BARAT | [7 empty] | MCP | 25 | [7 empty] | 17000000 | 340000000 | 18000000 | 180000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  |  | MCP 25m |  | PO LUMPSUM
2021 | PERMANENRAYAPEBANYURANN | BEKASI | [7 empty] | SST | 42 | [7 empty] | 25000000 | 275000000 | 22000000 | 440000000 | 3000000 | 25000000 | [5 empty] | 34 KK | 850000 | 28900000 | 45100000 | 70100000 | 15000000 | 99000000 | SST 42m |  | 353505181
2021 | BOGOR SUKARAJA 2 | BOGOR | [7 empty] | SST | 42 | [7 empty] | 20300000 | 406000000 | 30000000 | 600000000 | 3000000 | 25000000 | [5 empty] | 60 KK | 750000 | 45000000 | 50000000 | 75000000 | 15000000 | 120000000 | SST 42m |  | 353505181
2021 | TELAGAMURNICIKARANGBARAT | BEKASI | [7 empty] | SST | 42 | [7 empty] | 25000000 | 275000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 45 kk | 1000000 | 45000000 | 26000000 | 51000000 | 15000000 | 96000000 | SST 52m |  | 423293218
2021 | PABUARAN BOJONG GEDE | BOGOR | [7 empty] | SST | 42 | [7 empty] | 20300000 | 406000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 46 KK | 1000000 + 300000 | 21000000 | 52000000 | 77000000 | 15000000 | 98000000 | SST 42m |  | 353505181
2021 | PERMANENKERTAJAYARUMPIN | BOGOR | [7 empty] | SST | 42 | [7 empty] | 20300000 | 406000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 16 KK | 500000 | 9000000 | 63000000 | 88000000 | 15000000 | 97000000 | SST 42m |  | 353505181
2021 | TANGERANG JAYANTI | TANGERANG | [7 empty] | SST | 42 | [7 empty] | 19600000 | 392000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 44 KK |  | 18150000 | 41000000 | 66000000 | 15000000 | 84150000 | SST 42m |  | 353505181
2021 | TEGALBULEUD_TEGALBULEUD_SUK | SUKABUMI | [7 empty] | SST | 52 | [7 empty] | 22500000 | 450000000 | 19000000 | 380000000 | 3000000 | 25000000 | [5 empty] | 38 KK | 400000 | 15200000 | 59300000 | 84300000 | 15000000 | 99500000 | SST 52m |  | 423293218
2021 | BUKITCIMANGGUCITY | KOTA BOGOR | [7 empty] | SST | 42 | [7 empty] | 22000000 | 440000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 40 KK | 500000 | 20000000 | 54000000 | 79000000 | 15000000 | 99000000 | SST 42m |  | 353505181
2021 | BENDUNGANCILEGON | KOTA CILEGON | [7 empty] | SST | 42 | [7 empty] | 21179826 | 423596520 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 31 KK |  | 17500000 | 44500000 | 69500000 | 15000000 | 87000000 | SST 42m |  | 353505181
2021 | KARANGMEKAR_CIMANGGU_SUK | SUKABUMI | [7 empty] | SST | 62 | [7 empty] | 22500000 | 450000000 | 17500000 | 350000000 | 3000000 | 25000000 | [5 empty] | 12 KK |  | 13500000 | 53500000 | 78500000 | 15000000 | 92000000 | SST 62m |  | 527299431
2021 | PERMANENPTIDEMITSU | BEKASI | [7 empty] | SST | 42 | [7 empty] | 25000000 | 275000000 | 25000000 | 500000000 | 3000000 | 25000000 | [5 empty] | 18 KK |  | 18000000 | 36000000 | 61000000 | 15000000 | 79000000 | SST 42m |  | 353505181
| BANTARSARIRANCABUNGUR | BOGOR | [7 empty] | SST | 42 | [7 empty] | 20300000 | 406000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 33 KK | 2000000 + 500000 | 19500000 | 51500000 | 76500000 | 15000000 | 96000000 | SST 42m |  | 353505181
| KARANGANYARBAHAGIA | BEKASI | [7 empty] | SST | 52 | [7 empty] | 25000000 | 275000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 53 KK |  | 28000000 | 57000000 | 82000000 | 15000000 | 110000000 | SST 52m |  | 423293218
| PERMANENKAREDOKCIBARUSAH | BEKASI | [7 empty] | SST | 42 | [7 empty] | 25000000 | 275000000 | 25000000 | 250000000 | 3000000 | 25000000 | [5 empty] | 23 KK | 500000 | 11500000 | 41000000 | 66000000 | 15000000 | 77500000 | SST 42m |  | 353505181
| TANGERANG CIPONDOH | TANGERANG | [7 empty] | SST | 42 | [7 empty] | 19600000 | 392000000 | 25000000 | 500000000 | 3000000 | 25000000 | [5 empty] | 20 KK |  | 8750000 | 44500000 | 69500000 | 15000000 | 78250000 | SST 42m |  | 353505181
| PERIUK KOTA TANGERANG | KOTA TANGERANG | [7 empty] | B2S | 42 | [7 empty] | 23500000 | 470000000 | 25000000 | 500000000 | 3000000 | 25000000 | [5 empty] | 25 KK | 1000000 | 25000000 | 49500000 | 74500000 | 15000000 | 99500000 | SST 42m |  | 353505181
| PAMIJAHAN BOGOR 3 | BOGOR | [7 empty] | SST | 52 | [7 empty] | 20300000 | 406000000 | 20000000 | 400000000 | 3000000 | 25000000 | [5 empty] | 20 KK | 1500000 + 1000000 | 21000000 | 52000000 | 77000000 | 15000000 | 98000000 | SST 52m |  | 423293218
| TANGERANG TELUKNAGA | TANGERANG | [7 empty] | SST | 52 | [7 empty] | 20300000 | 406000000 | 15000000 | 300000000 | 3000000 | 25000000 | [5 empty] | 65 KK | 750000 + 500000 | 36250000 | 37750000 | 62750000 | 15000000 | 99000000 | SST 52m |  | 423293218
| TANGERANG LEGOK | TANGERANG | [7 empty] | SST | 32 | [7 empty] | 19600000 | 392000000 | 25000000 | 500000000 | 3000000 | 25000000 | [5 empty] | 25 KK | 500000 | 12500000 | 62000000 | 87000000 | 15000000 | 99500000 | SST 32m |  | 336315892
| PERMANENASRAMAHAJI | JAKARTA TIMUR | [7 empty] | MCP | 25 | [7 empty] | 18750000 | 206250000 | 20000000 | 60000000 | PO LUMPSUM | PO LUMPSUM | [5 empty] | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM | PO LUMPSUM |  |  | MCP 25m |  | PO LUMPSUM
| PERMANENPERUMPERMATAINDAH | BEKASI | [7 empty] | SST | 42 | [7 empty] | 25000000 | 275000000 | 25000000 | 250000000 | 3000000 | 25000000 | [5 empty] | 24 KK | 500000 | 12000000 | 62000000 | 87000000 | 15000000 | 99000000 | SST 42m |  | 353505181
| UBRUG_WARUNGKIARA_SUK | SUKABUMI | [7 empty] | SST | 62 | [7 empty] | 22500000 | 450000000 | 17500000 | 350000000 | 3000000 | 25000000 | [5 empty] | 25 KK | 2000000 + 1000000 | 28000000 | 46000000 | 71000000 | 15000000 | 99000000 | SST 62m |  | 527299431
| SUKABUMI CARINGIN | SUKABUMI | [7 empty] | SST | 62 | [7 empty] | 22500000 | 450000000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 32 KK | 500000 | 16000000 | 55000000 | 80000000 | 15000000 | 96000000 | SST 62m |  | 527299431
| SERANG CARENANG | SERANG | [7 empty] | SST | 52 | [7 empty] | 17000000 | 340000000 | 18000000 | 360000000 | 3000000 | 25000000 | [5 empty] | 15 KK | 500000 | 8500000 | 64500000 | 89500000 | 15000000 | 98000000 | SST 52m |  | 423293218
| VILLAGADINGHARAPAN | BEKASI | [7 empty] | SST | 42 | [9 empty] | 30000000 | 330000000 | 3000000 | 25000000 | [5 empty] | 5 KK @ 1.000.000, 23 KK @500.000 | 1000000+500000 | 16500000 | 53500000 | 78500000 | 15000000 | 95000000 | SST 42m |  | 353505181
Note on Z7: Jane Claudia Oktavia: MCP : 15JT B2S : 25JT
Note on AI7: Jane Claudia Oktavia: ESKALASI - IW - 25JT
Note on AK7: Jane Claudia Oktavia: BIAYA OPSIC : 15JT
Note on AI56: Jane Claudia Oktavia: tambahan add opsic 5jt
Note on AI57: Jane Claudia Oktavia: tambahan add opsic 5jt
Note on X68: Jane Claudia Oktavia: SEWA 10THN 5-5
Note on AI152: Jane Claudia Oktavia: TAMBAHAN OPSIC 5JT

## CAPEX
Site Type | Supplier Sitac | Total Site | Avg of BAN | Avg of IW Cost | Avg of Operasional Cost | Avg of Total Sitac |  |  |  | Land Lease By System |  |  | 21179826 | 116 sites
NEW BUILD | PT. ARENAS ADI PERKASA | 3 | 22333333.3333 | 19666666.6667 | 72000000 | 91666666.6667 |  |  |  | Biaya SITAC |  |  | 94483550
| PT. Banjarpasir Nusa Pratama | 25 | 19740000 | 13666666.6667 | 74620833.3333 | 88287500
| PT. DATATEL INDONESIA | 3 | 18000000 | 9166666.6667 | 75793333.3333 | 84960000
| PT. DWI SAMUDERA RAYA | 6 | 20000000 | 25666666.6667 | 75716666.6667 | 101383333.3333 | [6 empty] | 105899130
| PT. KARYA LINTAS SEJAHTERA | 1 | 40000000 |  | 95000000 | 95000000 | Tidak ada IW - Pusdikreskrim | [5 empty] | 1058991.3
| PT. Lintas Banyu Lestari | 6 | 19666666.6667 | 14116666.6667 | 73750000 | 87866666.6667
| PT. MANDIRA INFRA TRIPAKARTI | 12 | 19666666.6667 | 12958333.3333 | 74416666.6667 | 87375000 | [6 empty] | 85000000 | 4250000
| PT. MULTI KREASI INVESTAMA | 2 | 20000000 | 27000000 | 71750000 | 98750000 | [6 empty] | 89250000 | 4462500
| PT. PANEN KARYA BERSAMA | 1 | 19000000 | 24500000 | 72000000 | 96500000 | [6 empty] | 93712500 | 4685625
| PT. ROTUA ABADI JAYA | 3 | 22166666.6667 | 34333333.3333 | 61666666.6667 | 96000000 | [6 empty] | 98398125
| PT. TURANGGA EMPAT TIGA | 1 | 20000000 | 22500000 | 71500000 | 94000000 | [6 empty] | 366360625 | 18318031.25
| PT. ORLIE INDONESIA | 12 | 19666666.6667 | 24137500 | 71958333.3333 | 96095833.3333
NEW BUILD Total |  | 75 | 20133333.3333 | 17840410.9589 | 73710540.5405 | 91550951.4994 | [7 empty] | 20300000 | 1015000
NEW MCP NON FO | PT. AULIA DANARDANA | 1 | 19000000 | 12000000 | 63000000 | 75000000
| PT. Banjarpasir Nusa Pratama | 5 | 17400000 | 7900000 | 83900000 | 91800000
| PT. KARYA LINTAS SEJAHTERA | 41 | 21655990.9091 |  |  | 0 | Site KLS, Lumpsum
| PT. PANEN KARYA BERSAMA | 2 | 15000000 | 9000000 | 70000000 | 79000000
| PT. RAKA MITRA BERSAMA | 1 | 20000000 | 9500000 | 80500000 | 90000000
| PT. ROTUA ABADI JAYA | 1 | 17000000 | 18000000 | 54000000 | 72000000
| PT. TURANGGA EMPAT TIGA | 8 | 18375000 | 14531250 | 67781250 | 82312500
NEW MCP NON FO Total |  | 59 | 19818942.5837 | 11847222.2222 | 72180555.5556 | 84027777.7778
Grand Total |  | 134 | 20027609.0105 | 16654945.0549 | 73411195.6522 | 90066140.7071
Row Labels | Count of site_id | Average of BAN |  | Row Labels | Site | Average of Additional Operational Cost Site |  | Row Labels | Site | Average of BIAYA IW
BEKASI | 2 | 15000000 |  | BEKASI | 2 | 70000000 |  | BEKASI | 2 | 9000000 | 79000000 | 2 | 9000000 | 18000000 |  | 2 | 70000000 | 140000000
BOGOR | 25 | 20300000 |  | BOGOR | 25 | 72766666.6667 |  | BOGOR | 25 | 20117391.3043 | 92884057.971 | 25 | 20117391.3043 | 502934782.6087 |  | 25 | 72766666.6667 | 1819166666.6667
JAKARTA BARAT | 8 | 17000000 |  | JAKARTA BARAT | 8 |  |  | JAKARTA BARAT | 8 |  |  | 4 | 23437500 | 93750000 |  | 4 | 70625000 | 282500000
JAKARTA SELATAN | 14 | 18277777.7778 |  | JAKARTA SELATAN | 14 |  |  | JAKARTA SELATAN | 14 |  |  | 3 | 25266666.6667 | 75800000 |  | 3 | 76433333.3333 | 229300000
JAKARTA TIMUR | 8 | 25311963.6364 |  | JAKARTA TIMUR | 8 |  |  | JAKARTA TIMUR | 8 |  |  | 2 | 18250000 | 36500000 |  | 2 | 73750000 | 147500000
JAKARTA UTARA | 11 | 27015000 |  | JAKARTA UTARA | 11 |  |  | JAKARTA UTARA | 11 |  |  | 3 | 12900000 | 38700000 |  | 3 | 74666666.6667 | 224000000
KARAWANG | 4 | 19000000 |  | KARAWANG | 4 | 70625000 |  | KARAWANG | 4 | 23437500 | 94062500 | 1 | 13400000 | 13400000 |  | 1 | 73000000 | 73000000
KOTA BEKASI | 3 | 20000000 |  | KOTA BEKASI | 3 | 76433333.3333 |  | KOTA BEKASI | 3 | 25266666.6667 | 101700000 | 8 | 12875000 | 103000000 |  | 8 | 81375000 | 651000000
KOTA BOGOR | 2 | 22000000 |  | KOTA BOGOR | 2 | 73750000 |  | KOTA BOGOR | 2 | 18250000 | 92000000 | 2 | 11250000 | 22500000 |  | 2 | 73000000 | 146000000
KOTA DEPOK | 3 | 19333333.3333 |  | KOTA DEPOK | 3 | 74666666.6667 |  | KOTA DEPOK | 3 | 12900000 | 87566666.6667 | 2 | 14750000 | 29500000 |  | 2 | 79250000 | 158500000
KOTA SUKABUMI | 1 | 23000000 |  | KOTA SUKABUMI | 1 | 73000000 |  | KOTA SUKABUMI | 1 | 13400000 | 86400000 | 29 | 15672413.7931 | 454500000 |  | 29 | 73357931.0345 | 2127380000
KOTA TANGERANG | 8 | 21000000 |  | KOTA TANGERANG | 8 | 81375000 |  | KOTA TANGERANG | 8 | 12875000 | 94250000 | 12 | 13937500 | 167250000 |  | 12 | 69020833.3333 | 828250000
SERANG | 2 | 17000000 |  | SERANG | 2 | 73000000 |  | SERANG | 2 | 11250000 | 84250000 | 93 |  | 1555834782.6087 |  | 93 |  | 6826596666.6667
SUKABUMI | 2 | 22500000 |  | SUKABUMI | 2 | 79250000 |  | SUKABUMI | 2 | 14750000 | 94000000 |  | Average IW | 16729406.2646 |  |  | Average Eskalasi | 73404265.233
TANGERANG | 29 | 19603448.2759 |  | TANGERANG | 29 | 73357931.0345 |  | TANGERANG | 29 | 15672413.7931 | 89030344.8276
TANGERANG SELATAN | 12 | 18000000 |  | TANGERANG SELATAN | 12 | 69020833.3333 |  | TANGERANG SELATAN | 12 | 13937500 | 82958333.3333
Grand Total | 134 | 20027609.0105 |  | Grand Total | 134 | 73411195.6522 |  | Grand Total | 134 | 16654945.0549 | 90066140.7071

## Pengajuan Approval to ARO
MCP |  |  | 70JT | Roof top MT |  | 30JT
B2S |  |  | 100JT
Site Name TBG | Last Update | Validasi OK | Mitra | SUBMIT | OPERATOR | Site Type | BAN | IW | HARGA ESKALASI SITAC | TOTAL Pengajuan tanpa IW | KONFIRMASI HARGA ESKALASI | NEED FU | SUPER SOIL | update ESKALASI
CIMANGGU 2 CIBUNGBULANG | IW clear ( 12 KK ) hrg Ban 17jt/thn, skema pembayaran 5,5,5,5 | Candidat A | BNP | ESKALASI APPROVED |  | B2S | 17000000 | ESKALASI APPROVED | ESKALASI APPROVED | ESKALASI APPROVED | ESKALASI APPROVED | 16.03.2020 Eskalasi approved, done share mitra Submit 13.03.2020 | DONE
SUKARESMI TAMANSARI | IW Clear hrg ban 15jt/thn skema pembayaran 5,5,5,5, | Candidat A | BNP | ESKALASI APPROVED |  | B2S | 15000000 | ESKALASI APPROVED | ESKALASI APPROVED | ESKALASI APPROVED | ESKALASI APPROVED | 16.03.2020 Eskalasi approved, done share mitra Submit 13.03.2020 | DONE
KARET SEPATAN |  |  | BNP | ESKALASI APPROVED |  | B2S | 20000000 | 17.000.000(34KK@500.000) | 88000000 |  | OK, PRICE | 16.03.2020 Eskalasi approved, done share mitra 16.03.2020 done email to ARO | DONE
Dayeuhluhurwarudoyong |  |  | BNP | ESKALASI APPROVED |  | B2S | 23000000 | 13.400.000 (18KK @500.000 & 22KK @Rp.200.000) | 86400000 |  | OK, PRICE | 26.03.2020 Eskalasi approved aro, done send to mitra and req soil test 24. 03. 2020 submit eskalasi to aro Need Nego BAN, need surat pernyataan soil test | DONE
Gempolsarisepatantimurbanten |  |  | BNP | ESKALASI APPROVED |  | B2S | 18000000 | 8.000.000 ( 16KK, @Rp.500.000) | 84000000 |  | OK, PRICE | Eskalasi approved aro, done send to mitra and req soil test 24. 03. 2020 submit eskalasi to aro Need konfirmasi IW dan Surat pernyataan ready to soil | DONE
JALAN RAYA PUSPITEK |  |  | DSR | ESKALASI APPROVED |  | B2S | 20000000 | Warga Radius 1 (6) @ 1.000.000,- Warga Radius 2 (10) @ 500.000,- Warga Radius 3 (39) @ 300.000,- | 89700000 |  | OK, PRICE | 18.03.2020 Eskalasi approved, done share mitra 18.03.2020 Eskalasi submit to ARO | DONE
TAPOS DEPOK |  |  | GNJ | ESKALASI APPROVED |  | B2S | 20000000 | 15.000.000(15KK@1.000.000) | 70000000 |  | OK, PRICE | 23.03.2020 Eskalasi approved 23.03.2020 Eskalasi submit to aro | DONE
BABAKAN ASEM TELUK NAGA |  |  | MKI | ESKALASI APPROVED | XL | B2S | 20000000 | 24.000.000(48KK @500.000) | 98500000 | 76500000 | OK, PRICE | 12.4.2020 Eskalasi submit to AR0 31.03.2020 lokasi site berpindah mundur ttp masih di lahan LL yg sama need Revalidasi 31.03.2020 Eskalasi turun dari 100500000 menjadi 98500000 17.03.2020 Eskalasi turun 2jt need revisi eskalasi sitac Need bukti BAN dan IW High price need Nego, Need bukti BAN dan IW | ny
PEMATANG TIGARAKSA |  |  | MIT | ESKALASI APPROVED |  | B2S | 20000000 | 6.500.000(13@500.000) | 86.000.000 |  | OK, PRICE | 16.03.2020 Eskalasi approved, done share mitra 16.03.2020 done email to ARO 13.03.2020 Need Konfirmasi IW 2 KK, BAN 20JT | DONE
SOLEAR BANTEN |  |  | MIT | ESKALASI APPROVED |  | B2S | 19000000 | 5.000.000(5kk@1.000.000) | 79500000 |  | OK, PRICE | 16.03.2020 Eskalasi approved, done share mitra 16.03.2020 done email to ARO 13.03.2020 Neew konfirmasi fasum fasos 9jt atau 5jt, BAN 19JT, IW OK | DONE
Raya Cisauk BSD |  |  | MIT | ESKALASI APPROVED |  | B2S | 20000000 | 4.000.000( 8KK@ 500.000) | 87500000 |  | OK, PRICE | 23.03.2020 eskalasi approved, done send mitra 20.03.2020 Done submit eskalasi to ARO 20.03.2020 Mitra submit eskalasi | DONE
Jatake Rangkasbitung |  |  | MIT | ESKALASI APPROVED |  | B2S | 18000000 | 10.500.000 (21 KK@500.000) | 95000000 |  | OK, PRICE | 23.03.2020 eskalasi approved, done send mitra 20.03.2020 Done submit eskalasi to ARO 20.03.2020 Mitra submit eskalasi | DONE
SALEMBARAN JAYA KOSAMBI |  |  | MKI | SITE AKAN DI REHUNTING |  | B2S | 20000000 | 28.500.000 (57KK@500.000) | 114000000 | 85500000 | NOK HIGH PRICE | High price need Nego, Need bukti BAN dan IW | ny
TEGAL ALUR KALI DERES |  |  | KLS | Eskalasi approved | SMARTFREN | MCP | 17000000 | - | PO LUMPSUM |  | OK, PRICE | 8.5.2020 Perubahan skema BAN 11thn 4.14.2020 Eskalasi submit to ARO
PABUARAN KEMANG | BA 25JT, Eskalasi sitac 105.500.000 |  | ORLIE | ESKALASI APPROVED |  | B2S | 20000000 | 16.000.000 | 93500000 |  | OK, PRICE | 16.03.2020 Eskalasi approved, done share mitra 16.03.2020 Ban update 20jt, eskalasi done submit to aro Ban 25 jt need nego ban | DONE
Pasir Mukti Citereup |  |  | ORLIE | ESKALASI APPROVED |  | B2S | 20000000 | 30000000 | 98600000 |  | OK, PRICE | 16.03.2020 Eskalasi approved, done share mitra 16.03.2020 Done submit eskalasi to ARO, Ban update 20jt BAN Mahal (21jt) Need Nego, | DONE
Klapanunggal Cileungsi | BAN 19jt, IW clear | Candidat C | Orlie | ESKALASI APPROVED |  | B2S | 20000000 | 31500000 | 97000000 |  | OK, PRICE | 31.3.2020 Eskalasi approved 30.3.2020 Submit eskalasi to ARO 26.03.2020 Need Konfirmasi IW, eskalasi akan di revisi sejumlah 29KK 26.03.2020 TX OK, 19.03.2020, hasil validasi RX OK, Need hasil validasi TX Need Hasil validasi done submit 12.03.2020 | DONE
BOJONG GEDE_BOGOR |  |  | ORLIE | ESKALASI APPROVED |  | B2S | 24000000 | 36KK @ 650,000 | 97400000 |  | OK, PRICE | 23.03.2020 Eskalasi approved 19.03.2020 Done submit eskalasi to ARO | DONE
JLRAYACIKUNGKUNG |  |  | ORLIE | ESKALASI APPROVED |  | B2S | 19000000 | 39.250.000 ( 25KK @ 1.000.000, 19KK @ 750.000) | 98250000 |  | OK, PRICE | 31.3.2020 Eskalasi approved 30.3.2020 Submit eskalasi to ARO 30.3.2020 harga awal 110750000 turun menjadi 98250000 20.03.2020 Mitra submit Eskalasi, NOK high price need nego harga eskalasi <100.000.000 | DONE
Blendungklari TBG |  |  | ORLIE | ESKALASI APPROVED |  | B2S | 20000000 | 20.000.000 (40KK @ 500.000) | 94000000 |  | OK, PRICE | 26.03.2020 eskalasi done approved, done send ke mitra 26.03.2020 Eskalasi submit to ARO Need konfirmasi IW dan Surat pernyataan ready to soil | DONE
Menteng Lenteng Agung |  |  | KLS | ESKALASI APPROVED | XL | MCP | 20000000 | - | PO LUMPSUM |  | - | 4.14.2020 Eskalasi submit to ARO |  | 75000000
CIPUTAT 3 |  |  | Turangga | SITE AKAN DI REHUNTING |  | MCP | 30000000 | 19.500.000 (26KK @ 750.000) | 96500000 |  | NOK HIGH PRICE(MCP) | Need bukti IW dan BAN (30Jt) need nego 15jt , nego eskalasi ban 60jt | ny
PANENMAS |  |  | BNP | ESKALASI APPROVED | TSEL | B2S | 20000000 | 18000000 | 95000000 |  | OK, PRICE | 16.04.2020 Eskalasi submit to ARO
Sumur Bandung Jayati |  |  | MIT | ESKALASI APPROVED |  | B2S | 20000000 | 7.500.000 (15 @500.000) | 90000000 |  | OK, PRICE | 31.3.2020 Eskalasi approved 30.3.2020 Submit eskalasi to ARO IW kurang jelas terdapat warga yg belum ttd di IW dan super soil | DONE
KADUSIRUNG |  |  | BNP | ESKALASI APPROVED | TSEL | B2S | 20000000 | 13.000.000 | 89500000 |  | OK, PRICE | 9.4.2020 Eskalasi approved 7.4.2020 ESKALASI SUBMIT TO ARO
WANA KERTA SINDANG JAYA |  |  | MIT | ESKALASI SUBMIT TO ARO (After W2 May) | SMARTFREN | B2S | 23000000 | 15.000.000 (30 @500.000) | 96500000 |  | OK, PRICE | Site termasuk out WK 2 mei 2.4.2020 Eskalasi submit to ARO 30.3.2020 jumlah KK di IW dan di eskalasi berbeda di Form IW 35 KK, di esklasi 30KK Need IW dan Surat pernyataan ready to soil | DONE
Mustikajaya Bekasi |  |  | DSR | Eskalasi approved | SMARTFREN | B2S | 20000000 | 26.600.000 (38 @700.000) | 95600000 |  | OK, PRICE | 8.4.2020 Eskalasi submit to ARO 7.4.2020 NEED BAN 20JT (10 THN, 5 -5)
Pengasinan Gunung Sindur |  |  | DSR | ESKALASI APPROVED | XL | B2S | 20000000 | 18.000.000 | 97500000 |  | OK, PRICE | 30.4.2020 Eskalasi submit to aro, nilai eskalasi sudah turun 2jt dari 99.500.000
Situ Cogarongsong Pengasinan |  |  | DSR | ESKALASI APPROVED | XL | B2S | 20000000 | 21.500.000 | 96500000 |  | OK, PRICE | 9.4.2020 Eskalasi approved 8.4.2020 Eskalasi submit to aro | done
Revisi_Approval Eskalasi Mekar Wangi Tangerang (Perubahan BAN) |  |  | ARENAS | ESKALASI APPROVED | XL | B2S | 15000000 | 7.500.000 | 78000000 |  | OK, PRICE | 4.14.2020 Eskalasi approved BAN sebelumnya 20jt menjadi 15jt
CILANGKAP TAPOS |  |  | LBL | ESKALASI APPROVED | SMARTFREN | B2S | 20000000 | 14500000 | 94500000 |  | OK, PRICE | 16.04.2020 Eskalasi submit to ARO
Jalan Asem Cipedak |  |  | KLS | NEED FOLLOW UP | XL | MCP | 17000000 | - | PO LUMPSUM |  | OK, PRICE | 14.4.2020 Need revalidasi ketinggian 25m
STASIUN CIKOYA_Rev |  |  | DATATEL | ESKALASI APPROVED | XL | B2S | 15000000 | 8.000.000 | 76400000 |  | OK, PRICE | 4.15.2020 Eskalasi approved 4.14.2020 Eskalasi submit to ARO,revisi penambahan IW senilai 6 jt
Jalan Pemuda Cipedak |  |  | KLS | NEED FOLLOW UP | XL | MCP | 20000000 | - | PO LUMPSUM |  | - | 14.4.2020 Need FU koordinat Kand B tidak sesuai yg di validasi,need revisi BAN luas lahan 5x5m
CIMANGGIS 025 |  |  | GNJ | NEED FOLLOW UP (After W2 May) | SMARTFREN | B2S | 20000000 | 17.000.000 (17KK @1.000.000) | 80000000 |  | OK, PRICE | Need IW dan Surat pernyataan ready to soil | DONE
PAMULANG TANGERANG SELATAN | BAN 17jt, IW clear | Candidat A | Turangga | NEED FOLLOW UP (After W2 May) | SMARTFREN | MCP | 17000000 | 18.750.000 (25KK@750.000) | 70000000 |  | OK, PRICE | 30.03.2020 Eskalasi turun menjadi 70jt, tetapi validasi SF meminta ketinggian 30m, need drone 27.03.2020 eskalasi turun jadi 75.000.000 need nego menjadi 70jt Need bukti BAN (17jt) need nego 15jt dan IW, nego eskalasi ban 60jt | ny
BOJONG NANGKA KELAPA DUA |  |  | MIT | NEED FOLLOW UP (After W2 May) | SMARTFREN | B2S | 23000000 | 10500000 (21KK @500.000) | 92000000 |  | OK, PRICE | 7.4.2020 Need hasil validasi kand B
Sabar Raya Kemajuan |  |  | KLS | ESKALASI APPROVED | XL | MCP | 18000000 | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 30.4.2020 Eskalasi submit to ARO
TELUKJAMBE TIMUR |  |  | LBL | Eskalasi approved | SF | B2S | 20000000 | 16.000.000 | 93.500.000 |  | OK, PRICE | 8.5.2020 Revisi eskalasi masa sewa 10thn
CIMANGGU 2 CIBUNGBULANG_Kand B |  |  | BNP | Eskalasi approved | SF | B2S | 18000000 | 6.000.000 | 74000000 |  | OK, PRICE | 8.5.2020 Kand Geser ke B, eskalasi ulang
Dukuh Cukanggalih |  |  | BNP | Eskalasi approved | XL | B2S | 20000000 | 13.000.000 | 88500000 |  | OK, PRICE | 8.5.2020 Esklasi submit to ARO
SALEMBARAN JAYA KOSAMBI |  |  | MKI | ESKALASI APPROVED | XL | B2S | 20000000 | 30.000.000 | 99.000.000 |  | OK, PRICE | 11.5.2020 Eskalasi submit to ARO
PERMANENCOMBATTERMPENUMPANG |  |  | KLS | ESKALASI APPROVED | TSEL | MCP | 35.280.000/5thn kenaikan 10% | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 15.5.2020 Eskalasi submit to aro
PERMANENCOMBATKEPANDUANPELINDO |  |  | KLS | ESKALASI APPROVED | TSEL | MCP | 35.280.000/5thn kenaikan 10% | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 15.5.2020 Eskalasi submit to aro
PERUMAHANRESINDA |  |  | ORLIE | Eskalasi approved | TSEL | B2S | 17.000.000 | 18.500.000 | 94000000 |  | OK, PRICE | 19.5.2020 Eskalasi submit to ARO
Ciater Serpong |  |  | Turangga | ESKALASI APPROVED | XL | MCP | 16000000 | 18.000.000 | 68000000 |  | OK, PRICE | 28.5.2020 Eskalasi submit to ARO
Jalan Asem Cipedak |  |  | KLS | Eskalasi approved | XL | MCP | 19.000.000 (Luas Lahan 5x5) | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 6.2.2020 Eskalasi submit to ARO
Pegadungan Tegal Alur |  |  | KLS | Eskalasi approved | XL | MCP | 17.000.000 (Luas Lahan 2x2) | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 6.2.2020 Eskalasi submit to ARO
Kemuning Matraman |  |  | KLS | Eskalasi approved | XL | MCP | 17.000.000 | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 11.2.2020 Eskalasi submit to ARO
KAMPUNG BESAR TELUK NAGA |  |  | MIT | Eskalasi approved | XL | B2S | 20.000.000 | 29.000.000 | 97.500.000 |  | OK, PRICE | 11.2.2020 Eskalasi submit to ARO
VILLA MELATI MAS RAYA |  |  | AULIA | ESKALASI APPROVED | XL | MCP | 19.000.000 | 12.000.000 | 65000000 |  | OK, PRICE | 12.2.2020 Eskalasi submit to ARO
WANA KERTA SINDANG JAYA_Revisi |  |  | MIT | ESKALASI APPROVED | SF | B2S | 20.000.000 | 15.000.000 | 96500000 |  | OK, PRICE | 12.2.2020 Eskalasi submit to ARO
Griya Sukatani Mekarsari_Revisi |  |  | BNP | ESKALASI APPROVED | XL | B2S | 20.000.000 | 23.500.000 | 99000000 |  | OK, PRICE | 13.2.2020 Eskalasi submit to ARO
Jalan Garuda Mas |  |  | KLS | ESKALASI APPROVED | XL | MCP | 17.000.000 | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 16.6 .2020 Eskalasi submit to ARO
KARAWACI 850 |  |  | ROTUA | ESKALASI APPROVED | SF | B2S | 25.000.000 ( Rooftop MT 25m) | 18.000.000 | 98.000.000 |  | OK, PRICE | 17.6.2020 Eskalasi submit to ARO
BOJONG NANGKA KELAPA DUA |  |  | MIT | ESKALASI APPROVED | SF | B2S | 20.000.000 | 10.500.000 | 92.000.000 |  | OK, PRICE | 18.6.2020 Eskalasi submit to ARO
SEPATAN TANGERANG |  |  | MIT | ESKALASI APPROVED | SF | B2S | 20.000.000 | 11.000.000 | 88.500.000 |  | OK, PRICE | 19.6.2020 Eskalasi submit to ARO
TAPOS DEPOK_LBL |  |  | LBL | ESKALASI APPROVED | SF | B2S | 20000000 | 7.500.000 | 85000000 |  | OK, PRICE | Beda GPS dengan Approval
JL RAYA KORELET |  |  | ROTUA | ESKALASI APPROVED | XL | B2S | 19000000 | 36000000 | 89000000 |  | OK, PRICE | Beda GPS dengan Approval | 2020-06-24
TELUKJAMBE TIMUR_KAND D |  |  | LBL | ESKALASI APPROVED | SF | B2S | 20000000 | 6.500.000 | 90000000 |  | OK, PRICE | 6.25.2020 Eskalasi submit to ARO
LUBANG BUAYA CIPAYUNG |  |  | KLS | ESKALASI APPROVED | SF | MCP | 17.000.000 | PO LUMPSUM | PO LUMPSUM |  | OK, PRICE | 6.25.2020 Eskalasi submit to ARO
Elang Sawang |  |  | ROTUA | ESKALASI APPROVED | XL | MCP | 17000000 | 24000000 | 73000000 |  | NOT OK PRICE | Nego Eskalasi di 65JT , need BAN , IW dan GPS
PANTAI DADAP |  |  | ROTUA | ESKALASI APPROVED | XL | B2S | 22500000 | 49000000 | 97000000 |  | OK, PRICE | 1.7.2020 Eskalasi submit to ARO | blm ada hasil validasi
PASIR JAMBU SUKARAJA |  |  | LBL | ESKALASI APPROVED | SF | B2S | 20000000 | 16000000 | 99500000 |  | NOT OK PRICE | Nego Eskalasi di 85JT , beda gps dengan approval
Nyiur Pondok Kelapa |  |  | KLS | ESKALASI APPROVED | XL | MCP | 18000000 | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 1.7.2020 Eskalasi submit to ARO Masa Sewa 10 thn Langsung
Jalan Pemuda Cipedak |  |  | KLS | ESKALASI APPROVED | XL | MCP | 18000000 | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 1.7.2020 Eskalasi submit to ARO Masa Sewa 10 thn Skema 5,5
Kemuning Matraman_Kand E |  |  | KLS | ESKALASI APPROVED | XL | MCP | 17000000 | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 1.7.2020 Eskalasi submit to ARO
WIJAYAKUSUMA CEGER |  |  | TURANGGA EMPAT TIGA | ESKALASI APPROVED | XL | MCP | 18.000.000/THN, MASA SEWA 10 TAHUN LANGSUNG | 13500000 | 89000000 |  | Waiting Approval | 2.3.21 Re-Submit eskalasi ARO
Sabililah Citeureup |  |  | BNP | ESKALASI APPROVED | XL | B2S | 17000000 | 25500000 | 98000000 |  | OK, PRICE | 7.7.2020 Eskalasi submit to ARO
CIBEBER BARENGKOK |  |  | BNP | ESKALASI APPROVED | XL | B2S | 18000000 | 17600000 | 90000000 |  | OK, PRICE | 14.7.2020 Eskalasi submit to ARO
BELIMBING KOSAMBI |  |  | MIT | ESKALASI APPROVED | XL | B2S | 20000000 | 35000000 | 99000000 |  | OK, PRICE | 16.7.2020 Eskalasi submit to ARO
JL RAYA KORELET |  |  | ROTUA | ESKALASI APPROVED | XL | B2S | 19000000 | 36000000 | 89000000 |  | OK, PRICE | 16.7.2020 Revisi Masa sewa 10thn, 5-5
BERANDA SERPONG |  |  | TURANGGA | ESKALASI APPROVED | XL | MCP | 20000000 | 12500000 | 85500000 |  | OK, PRICE | 20.7.2020 Eskalasi submit to ARO
MEKARWANGI BOGOR |  |  | ORLIE | Eskalasi Reject | XL | B2S | 20000000 | 15600000 | 90600000 |  | OK, PRICE | 22.7.2020 Eskalasi submit to ARO
PARUNG PANJANG BOGOR |  |  | BNP | ESKALASI APPROVED | XL | B2S | 19000000 | 7500000 | 84000000 |  | OK, PRICE | 22.7.2020 Eskalasi submit to ARO
JALAN RAYA CARIU JONGGOL |  |  | ORLIE | ESKALASI APPROVED | XL | B2S | 19000000 | 12900000 | 89900000 |  | OK, PRICE | 16.8.2020 Eskalasi submit to ARO
DISCOVERY CONSERVA |  |  | TURANGGA | ESKALASI APPROVED | XL | MCP | 17000000 | 15000000 | 85000000 |  | OK, PRICE | 27.7.2020 Eskalasi submit to ARO
Karang Timur Tangerang |  |  | ARENAS | ESKALASI APPROVED | XL | B2S | 24000000 | 30000000 | 99000000 |  | OK, PRICE | 28.7.2020 Eskalasi submit to ARO
PERMANENCOMBATPUSDIKRESKRIM |  |  | KLS | ESKALASI APPROVED | XL | B2S | 40000000 | - | 95000000 |  | OK, PRICE | 30.7.2020 Eskalasi submit to ARO
Tol Pelabuhan Ancol |  |  | KLS | ESKALASI APPROVED | XL | MCP | 18500000 | - | PO LUMPSUM |  | PO LUMPSUM | 10.8.2020 Eskalasi submit to ARO
CIPINANG RUMPIN BOGOR |  |  | ORLIE | ESKALASI APPROVED | XL | B2S | 19000000 | 26500000 | 96500000 |  | OK, PRICE | 13.8.2020 Eskalasi submit to ARO
Elang Sawang |  |  | ROTUA | ESKALASI APPROVED | XL | MCP | 17000000 | 18000000 | 69000000 |  | OK, PRICE | 19.8.2020 Revisi nilai eskalasi tambah 4jt
Krama Yudha Cakung |  |  | KLS | ESKALASI APPROVED | XL | MCP | 200.000.000 UNTUK 11 TAHUN | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 21.8.2020 Eskalasi submit to ARO
Beringin Batulayang |  |  | BNP | ESKALASI APPROVED | XL | B2S | 20000000 | 15400000 | 90400000 |  | OK, PRICE | 24.8.2020 Eskalasi submit to ARO
Pandawa Cibodas |  |  | BNP | ESKALASI APPROVED | XL | MCP | 18000000 | 8500000 | 89000000 |  | OK, PRICE | 9.4.2020 Eskalasi submit to ARO
ALAM JAYA JATIUWUNG |  |  | BNP | ESKALASI APPROVED | XL | MCP | 19000000 | 3500000 | 96000000 |  | OK, PRICE | 9.3.2020 Eskalasi submit to ARO
PASIR JAYA JATIUWUNG |  |  | DSR | ESKALASI APPROVED | XL | B2S | 20000000 | 21000000 | 99000000 |  | OK, PRICE | 9.11.2020 Eskalasi submit to ARO
SITUTERATECIKANDE |  |  | BNP | ESKALASI APPROVED | TSEL | B2S | 18000000 | 13500000 | 88500000 |  | OK, PRICE | 9.14.2020 Eskalasi submit to ARO
SMPN 14 TANGERANG |  |  | BNP | ESKALASI APPROVED | XL | MCP | 17000000 | 6500000 | 85000000 |  | OK, PRICE | 9.16.2020 Eskalasi Submit to ARO
LONTAR DALAM KOJA |  |  | KLS | ESKALASI APPROVED | XL | MCP | 19JT/11THN | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 09.22.2020 Eskalasi submit to ARO
Nyiur Pondok Kelapa |  |  | KLS | ESKALASI APPROVED | XL | MCP | 19JT/11THN | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 9.24.2020 Eskalasi submit to ARO
JLKOSTRAD |  |  | KLS | ESKALASI APPROVED | TSEL | MCP | 17.500.000/10THN | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 9.30.2020 Eskalasi submit to ARO
Tol Pelabuhan Ancol_Rev Masa Sewa | KLS | ESKALASI APPROVED | KLS | ESKALASI APPROVED | XL | MCP | 18500000 | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 10.1.2020 Eskalasi submit to ARO, rev masa sewa 10 tahun
BINTARA KENCANA TIMUR |  |  | FERGACO | HOLD NEED harga dan validasi 24m | XL | B2S | 45.000.000/THN, MASA SEWA 11 THN | 23.000.000 | 95.000.000 |  | OK, PRICE | 30.11.2020 Eskalasi resubmit to ARO
BABAKAN MADANG BOGOR |  |  | BNP | ESKALASI APPROVED | XL | B2S | 20000000 | 20500000 | 95000000 |  | OK, PRICE | 10.5.2020 Eskalasi submit to ARO
KEBONBARUTEBET |  |  | KLS | ESKALASI APPROVED | TSEL | MCP | 17.000.000/THN, MASA SEWA 10 THN LANGSUNG | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 10.12.2020 Eskalasi submit to ARO
JALAN MENTAWAI TOL |  |  | BNP | DONE APPROVE | XL | MCP | 15.000.000/THN, MASA SEWA 10 THN LANGSUNG | 10000000 | 99000000 |  | OK, PRICE | 10.26.2020 Eskalasi submit to ARO
PONDOK CABE RAYA |  |  | BNP | DONE APPROVE | XL | MCP | 18.000.000/THN, MASA SEWA 10 TAHUN LANGSUNG | 11000000 | 93000000 |  |  | 4.11.2020 Eskalasi submit to ARO 9.11.2020 Done Approve
TAMAN GOLF BOULEVARD |  |  | BNP | DONE APPROVE | XL | MCP | TANPA BAN, LAHAN FASUM | 6000000 | 71000000 |  |  | 13.11.2020 Eskalasi Submit
JLBUDIMULYAUTARA |  |  | KLS | WAITING APPROVAL | TSEL | MCP | 20.000.000/THN, MASA SEWA 11 TAHUN LANGSUNG | PO LUMPSUM | PO LUMPSUM |  | Waiting Approval | 1.2.2021 Resubmit revisi eskalasi to ARO
SWASEMBADA TANJUNG PRIOK |  |  | KLS | WAITING APPROVAL | XL | MCP | 18.000.000/THN, MASA SEWA 10 TAHUN LANGSUNG | PO LUMPSUM | PO LUMPSUM |  | PO LUMPSUM | 17.11.2020 ESKALASI SUBMIT ARO
CITEUREUP BOGOR 2 |  |  | BNP |  | SMARTFREN | B2S | 19.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 16.000.000 | 77.000.000 |  | Waiting Approval | 05.01.2021 Resubmit Eskalasi
WALANTAKA KOTA SERANG |  |  | BNP |  | SMARTFREN | B2S | 18.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 21.500.000 | 75.500.000 |  | Waiting Approval | 8.1.2020 Resubmit revisi eskalasi
JALAN KUBUR ISLAM |  |  | KLS |  | XL | MCP | 20.000.000/THN, MASA SEWA 10 TAHUN LANGSUNG | PO LUMPSUM | PO LUMPSUM |  | OK, PRICE | 28.12.2020 Approve ARO
TENJOLAYA BOGOR |  |  | DATATEL |  | SMARTFREN | B2S | 17.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 24.500.000 | 68.500.000 |  | Approve | 9.2.2021 Re-Submit eskalasi
GUNUNG SINDUR JAWA BARAT |  |  | ORLIE |  | SMARTFREN | B2S | 18.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 18.500.000 | 80.500.000 |  | Approve | 2.2.2021 Submit eskalasi
CIPONDOH KOTA TANGERANG |  |  | DSR |  | SMARTFREN | B2S | 20.000.000/THN, MASA SEWA 11 TAHUN LANGSUNG | 12500000 | 86500000 |  | Approve | 5.2.2021 Submit eskalasi
PARUNG PANJANG GOROWONG |  |  | ROTUA |  | SMARTFREN | B2S | 17.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 9500000 | 82000000 |  | Approve | 12.3.2021 Submit eskalasi
GUNUNG KALER TANGERANG |  |  | PANEN |  | SMARTFREN | B2S | 15.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 9500000 | 71000000 |  | Approve | 5.2.2021 Submit eskalasi
WARUNG KIARA SUKABUMI |  |  | DATATEL |  | SMARTFREN | B2S | 17.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 19000000 | 72000000 |  | Approve | 18.2.2021 Re-Submit eskalasi
CIBUNGBULANG BOGOR 2 |  |  | ORLIE |  | SMARTFREN | B2S | 19.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 16100000 | 82500000 |  | Approve | 2.3.21 Re-Submit eskalasi ARO
PASARCISAATSKB |  |  | BNP |  | TSEL | B2S | 23.000.000/THN, MASA SEWA 10 TAHUN LANGSUNG | 21000000 | 78500000 |  | Approve | 25.2.2021 Submit Eskalasi to ARO
PARUNG KUDA SUKABUMI |  |  | DSR |  | SMARTFREN | B2S | 30.000.000/THN, MASA SEWA 10 TAHUN LANGSUNG | 5000000 | 86500000 |  | Approve | 2.3.21 Submit eskalasi ARO
PERMANENCOMBATCIKANDEPERMAI |  |  | BNP |  | TSEL | B2S | 20.000.000/THN, MASA SEWA 11 TAHUN LANGSUNG | 12400000 | 81600000 |  | Approve | 5.3.21 Submit eskalasi ARO
GUNUNG SINDUR BOGOR |  |  | ORLIE |  | SMARTFREN | B2S | 17.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 27500000 | 70000000 |  | Approve | 9.3.21 Submit eskalasi to ARO
LEUWILIANG BOGOR |  |  | ROTUA |  | SMARTFREN | B2S | 18.000.000/THN, MASA SEWA 20 TAHUN (10+5+5) | 6000000 | 84500000 |  | Approve | 16.3.21 Submit eskalasi to ARO
STAKALIDERES |  |  | KLS |  | TELKOMSEL | MCP | 18.500.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | PO LUMPSUM | PO LUMPSUM |  | Waiting Approval | 24.3.21 Submit eskalasi to ARO
CURUGBADAKMAJA |  |  | KLS |  | TELKOMSEL | B2S | 20.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 9000000 | 76000000 |  | Waiting Approval | 24.3.21 Submit eskalasi to ARO
PONDOKRANGGONCIPAYUNG |  |  | KLS |  | TELKOMSEL | MCP | 17.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | PO LUMPSUM | PO LUMPSUM |  | Waiting Approval | 5.4.21 Submit eskalasi to ARO
CURUGBITUNGNANGGUNG |  |  | BNP |  | TELKOMSEL | B2S | 18.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 14600000 | 78500000 |  | Waiting Approval | 6.4.21 Submit eskalasi to ARO
PARADISESERPONG2 |  |  | AULIA |  | TELKOMSEL | MCP | 16.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 8000000 | 65000000 |  | Waiting Approval | 8.4.21 Submit eskalasi to ARO
SUKAJAYASALABINTANA |  |  | BNP |  | TELKOMSEL | SST | 22.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 19000000 | 73000000 | Waiting Approval | Waiting Approval | 20.4.21 Submit eskalasi to ARO
PASARBARUKARAWACI |  |  | CMI |  | TELKOMSEL | SST | 20.000.000/THN, MASA SEWA 10 TAHUN (5+5) | 20000000 | 75000000 | Waiting Approval | Waiting Approval | 4.5.21 Submit eskalasi to ARO
CILANDAKBAWAH |  |  | KLS |  | TELKOMSEL | MCP 25 | 18.000.000/THN, MASA SEWA 20 TAHUN (10+10) | PO LUMPSUM | PO LUMPSUM |  | Waiting Approval | 25.7.21 Submit eskalasi to ARO
BOGOR BOJONG GEDE |  |  | LBL |  | SMARTFREN | SST 42 | 20.000.000/THN, MASA SEWA 20 TAHUN (5+5+5+5) | 20000000 | 69500000 |  | Waiting Approval | 26.7.21 Submit eskalasi to ARO

## Request Soil Test
SITE ID OPERATOR 2 | So Numb | Site ID TBG | Site ID Operator | Site Name | Site Type | STIP Category | Operator | Company | Kandidat | Latitude | Longitude | Regional | Address | Residence | Province | Tower height | PIC Mitra | PIC TBG | NAMA MITRA
0 | 23054806231 |  |  | TIGARAKSA TANGERANG | NEW BUILD | STIP 1 | SMARTFREN | TB | A | 106.47349 | -6.22917 | JABODETABEK OUTER | Jalan Jayasantika Desa pasir Nangka Kec. Tigaraksa | KAB TANGERANG | BANTEN | 32 m
JAK1040 | 23055072231 | 131701123 | JAK1040 | TELUKNAGA | NEW BUILD | STIP 1 | SMARTFREN | TB | D | 106.636430° | -6.081660° | JABODETABEK OUTER | Kp Kalor Kohod RT 01 RW 05 Desa Gaga Kec. Pakishaji Kab. Tangerang | KAB TANGERANG | BANTEN | 42 m
0 | 23054784231 |  |  | CITEUREUP BOGOR | NEW BUILD | STIP 1 | SMARTFREN | TB | B | 106.89954 | -6.4982 | JABODETABEK OUTER | Jp Tonggoh RT 03 RW 01 Kel Gunungsari Kec. Citeureup Kab. Bogor | KAB BOGOR | JAWA BARAT | 42 m | Imam : 081383932662 | Adit : 0895392876255
0 | 4054727041 |  |  | BAKTIABRI | NEW BUILD | STIP 1 | INDOSAT | TB | D | 106.878880° | -6.414510° | JABODETABEK INNER | Jl Bakti Abri Kel Sukamaju Kec Tapos Kota Depok | KOTA DEPOK | JAWA BARAT | 42 m | Ridwan : 081317600620 | Adit : 0895392876255
JAK0743 | 23054785231 |  | JAK0743 | BEJI KOTA DEPOK | NEW BUILD | STIP 1 | SMARTFREN | TB | G | 106,81202 | -6.37447 | JABODETABEK INNER | Jl Sawo I RT 005 RW 05 Kel Beji Kec Beji Kota Depok | KOTA DEPOK | JAWA BARAT | 32 m | Ridwan : 081317600620 | Adit : 0895392876255
Jabo_Outer_add_024 | 23054805231 | 125943123 | Jabo_Outer_add_024 | TAJUR HALANG BOGOR | NEW BUILD | STIP 1 | SMARTFREN | TB | C | 106.74626 | -6.45157 | JABODETABEK OUTER | Komp Inkopad Blok D 16/13 RT 09 RW 05 Kel Sasakpanjang Kec Tajurhalang Kab Bogor | KAB BOGOR | JAWA BARAT | 36 m
Jabo_Outer_add_023 | 23054782231 | 125928123 | Jabo_Outer_add_023 | PAMIJAHAN BOGOR | NEW BUILD | STIP 1 | SMARTFREN | TB | E | 106.67167 | -6.63600 | JABODETABEK OUTER | Kp Pasir Datar RT 01 RW 06 Desa Cibening Kec. Pamijahan Kab. Bogor | KAB BOGOR | JAWA BARAT | 36 m
BOG0119 | 23055088231 | 125967123 | BOG0119 | ABDUL FATAH | NEW BUILD | STIP 1 | SMARTFREN | TB | A | 106.695640° | -6.647070° | JABODETABEK OUTER | Kp Tapos Udik RT 01 RW 02 Desa Tapos I Kec. Tenjolaya | KAB BOGOR | JAWA BARAT | 42 m | Donny : 08119018899 | Adit : 0895392876255
02RKB025 | 4054932041 |  | 02RKB025 | KP_PABUARAN | NEW BUILD | STIP 1 | INDOSAT | TB | C | 106.78091 | -6.53303 | JABODETABEK OUTER | Kp. Rawataman RT.001 RW.003 Kelurahan Mekarwangi Kecamatan Tanah Sareal Kota Bogor | KOTA BOGOR | JAWA BARAT | 36 m | Erdi : +62 896-6161-7384 | Adit : 0895392876255
BOG0175 | 23055075231 | 125964123 | BOG0175 | PANDANSARI CIAWI | NEW BUILD | STIP 1 | SMARTFREN | TB | C | 106.84496 | -6.63563 | JABODETABEK OUTER | Kp. Sinabeul RT 01 RW 02 Desa Cibanon Kec. Sukaraja Kab. Bogor | KAB. BOGOR | JAWA BARAT | 42 m | Didik : 0817141234 | Adit : 0895392876255
BOG0064 | 23055087231 | 125966123 | BOG0064 | SUKARAJA CILEBUT | NEW BUILD | STIP 1 | SMARTFREN | TB | E | 106.79885 | -6.52195 | JABODETABEK OUTER | Kp. Bojong Simpu RT 3 RW 6 Kel. Cilebut Barat Kec. Sukaraja Kab. Bogor | KAB. BOGOR | JAWA BARAT | 42 m | Ronal : 0823-2222-8333 | Adit : 0895392876255
BOG0142 | 23054746231 | 125922123 | BOG0142 | CIOMAS BOGOR | NEW BUILD | STIP 1 | SMARTFREN | TB | G | 106.76167 | -6.60399 | JABODETABEK OUTER | Kp Sukamanah RT 03 RW 03 Desa Pagelaran Kec Ciomas | KAB. BOGOR | JAWA BARAT | 42 m | Heri : +62 813-8022-5151 | Adit : 0895392876255
BOG0055 | 23055089231 | 125968123 | BOG0055 | CIBINONG NANGGEWER | NEW BUILD | STIP 1 | SMARTFREN | TB | B | 106.82498 | -6.51957 | JABODETABEK OUTER | Jalan Pramuka RT 01 RW 08 Kelurahan Nanggewer Kecamatan Cibinong | KAB. BOGOR | JAWA BARAT | 42 m | Heri : +62 813-8022-5151 | Adit : 0895392876255
BOG0136 | 23054747231 |  | BOG0136 | BOGOR BARAT | NEW BUILD | STIP 1 | SMARTFREN | TB | A | 106.74019 | -6.56033 | JABODETABEK OUTER | Jalan Babakan Lio RT 05 RW 11 Kel. Belimbing jaya Kec. Bogor Barat Kota Bogor | KOTA BOGOR | JAWA BARAT | 36 m | Dani : 081320217971 | Adit : 0895392876255
JAK0266 | 23054745231 |  | JAK0266 | CIKARANG BARAT BEKASI | NEW MCP NON FO | STIP 1 | SMARTFREN | TB | A | 107.07726 | -6.23244 | JABODETABEK OUTER | Jalan Mekar Jaya Kel. Sumberjaya Kec. Tambun Selatan Kab Bekasi | KAB. BEKASI | JAWA BARAT | 20 m | Imam : 081383932662 | Adit : 0895392876255
JAK0292 | 23054744231 |  | JAK0292 | TAMBUN SELATAN BEKASI | NEW MCP NON FO | STIP 1 | SMARTFREN | TB | A | 107.11301 | -6.28242 | JABODETABEK OUTER | Jalan Cikarang Kel. Sukadanau Kec. Cikarang Barat, Kab Bekasi | KAB. BEKASI | JAWA BARAT | 20 m | Imam : 081383932662 | Adit : 0895392876255
JAW-BT-TGR-0030 | 30572040031 | 1317431003 | JAW-BT-TGR-0030 | Jalan Raya Kukun Daun | NEW BUILD | STIP 1 | XL | TB | B | 106°26'45.1"E | 6°08'45.2"S | JABODETABEK OUTER | Jalan Raya Kukun Daun Kp Benda RT 01 RW 02 Desa Benda Kec. Sukamulya Kab. Tangerang | KAB. TANGERANG | BANTEN | 52 m | Ronal : 0823-2222-8333 | Adit : 0895392876255 | soil test done
JAK0633 | 23055068231 | 125962123 | JAK0633 | PONDOKMELATI | NEW BUILD | STIP 1 | SMARTFREN | TB | G | 106.924430° | -6.317000° | JABODETABEK OUTER | Jalan Raya Hankam GangH. Kunyil RT 04 RW 05 Kel. Jati Melati Kec. Pondok Melati Kota Bekasi | KOTA BEKASI | JAWA BARAT | 36 m | Ridwan : 081317600620 | Adit : 0895392876255 | soil test done
JAW-BT-TGR-0032 | 30572170031 | 1317491003 | JAW-BT-TGR-0032 | Serang Cikande | NEW BUILD | STIP 1 | XL | TB | A | 106°22'58.6"E | 6°11'11.8"S | JABODETABEK OUTER | Kp Babakan RT 12 RW 02 Desa Pasir Gintung Kec. Jayanti Kab. Tangerang | KAB. TANGERANG | BANTEN | 42 m | Ronal : 0823-2222-8333 | Adit : 0895392876255 | soil test done
JAW-BT-TGR-0026 | 30572250031 | 1317551003 | JAW-BT-TGR-0026 | Cirumpak Tangerang | NEW BUILD | STIP 1 | XL | TB | B | 106°26'15.85"E | 6°06'15.41"S | JABODETABEK OUTER | Kp Pasir RT 06 RW 03 Desa Pasir Kec. Kronjo Kab. Tangerang | KAB. TANGERANG | BANTEN | 52 m | Ronal : 0823-2222-8333 | Adit : 0895392876255 | soil test done
JAW-BT-TGR-0025 | 30572240031 | 1317541003 | JAW-BT-TGR-0025 | Patrasana Kresek | NEW BUILD | STIP 1 | XL | TB | A | 106°24'12.1"E | 6°09'18.3"S | JABODETABEK OUTER | Jalan Raya Kresek RT 01 RW 01 Desa Patrasana Kec. Kresek Kab, Tangerang | KAB. TANGERANG | BANTEN | 42 m | Ronal : 0823-2222-8333 | Adit : 0895392876255 | soil test done
JAW-BT-TGR-0051 | 30572200031 | 1317521003 | JAW-BT-TGR-0051 | Stasiun Cikoya | NEW BUILD | STIP 1 | XL | TB | A | 106°24'45.01" E | -6°20'5.57"S | JABODETABEK OUTER | Jalan Raya Maja, Kp Solear RT 02 RW 01 Desa Cikasungka Kec. Solear Kab. Tangerang | KAB. TANGERANG | BANTEN | 32 m | Erdi : +62 896-6161-7384 | Adit : 0895392876255 | soil test done
JAW-BT-TGR-0021 | 30572000031 | 1317391003 | JAW-BT-TGR-0021 | Mekar Wangi Tangerang | NEW BUILD | STIP 1 | XL | TB | A | 106°35'27.4"E | 6°20'47.1"S | JABODETABEK OUTER | Kp Panyirapan RT 08 RW 04 Desa Mekarwangi Kec. Cisauk kab. Tangerang | KAB. TANGERANG | BANTEN | 42 m | Sugianto : 0812-9590-3552 | Adit : 0895392876255 | soil test done
JAW-BT-TGR-0040 | 30572300031 | 1317561003 | JAW-BT-TGR-0040 | Cibugel Cisoka | NEW BUILD | STIP 1 | XL | TB | A | 106°25'21.25" E | -6°14'59.82"S | JABODETABEK OUTER | Kp Cibugel RT 09 RW 04 Desa Cibugel Kec. Cisoka Kab. Tangerang | KAB. TANGERANG | BANTEN | 42 m | Erdi : +62 896-6161-7384 | Adit : 0895392876255 | soil test done
ZJKT2_5027 | 0230575310231 | 1317871023 | ZJKT2_5027 | PANONGAN TANGERANG | NEW BUILD | STIP 1 | SMARTFREN | TB | B | 106.5444 | -6.267013 | JABODETABEK (OUTER) | Kp. Ciakar RT. 04 RW. 01 Desa Ciakar Kec. Panongan | KAB. TANGERANG | BANTEN | 32m | Imam : 081383932662 | Adit : 0895392876255 | soil test done
JAK0589 | 0230560370231 | 1260581023 | JAK0589 | TELUKJAMBE TIMUR | NEW BUILD | STIP 1 | SMARTFREN | TB | C | 107.29108 | -6.33465 | JABODETABEK (OUTER) | Kp. Kalipandan RT. 02 RW. 01 Desa Sukaluyu Kec.Teluk Jambe Timur, Kab. Karawang | KARAWANG | JAWA BARAT | 32m | Ridwan : 081317600620 | Handri : 081297986667 | soil test done
03BKS499 | 4054934041 | 125959104 | 03BKS499 | JLJAWASATU | NEW BUILD | STIP 1 | INDOSAT | TB | B | 107.0336 | -6.2459 | JABODETABEK OUTER | Kp Rawa Aren RT 07 RW 12 Kel. Rawa Aren Kec. Bekasi Timur Kota Bekasi | KOTA BEKASI | JAWA BARAT | 42 m | Angga : 0812-9033-7872 | Fadhil : 0816-1479-766 | soil test done
JAW-JB-CBI-0082 | 30572360031 | 1260951003 | JAW-JB-CBI-0082 | Pengasinan Gunung Sindur | NEW BUILD | STIP 1 | XL | TB | B | 106.692267° | -6.376572° | JABODETABEK (OUTER) | Kp Kebon Kopi RT. 05 RW. 06 Kel. Pengasinan Kec. Gunung Sindur, Kab. Bogor | BOGOR | JAWA BARAT | 42 m | Sam : 087774724777 | Adit : 0895392876255
BOG0140 | 23054781231 | 125927123 | BOG0140 | BOJONG GEDE BOGOR | 28.11.19 : rehunting, take over mitra 12.11.19 : gagal IW kandidat F, rehunting kand G 11.11.19 : IW OG kandidat F 06.11.19 : kandidat F OK 04.11.19 : submit kandidat F 24.10.19 : failed IW, rehunting kandidat F 18.10.19 : still IW on going kandidat E, warga susah untuk dikumpulkan 01.10.19 : kandidat E OK, BAN OG 26.09.19 : kandidat D NOK, submit kandidat E 24.09.19 : submit kandidat D 18.09.19 : Kandidat A gagal IW, submit kandidat B dan C, kandidat B OK 10.09.19 : terdapat 5 ahli waris, 3 ahli waris sudah menyetujui harga sewa 15jt/thn dengan skema 2+3+5+5+5. menunggu keputusan 2 ahli waris 09.09.19 : waiitng keputusan keluarga untuk harga sewa lahan 05.09.19 : approve TNP oleh Pak Olly 04.09.19 : approve RNP oleh Pak Parlin | Visit kandidat Pak yadi, propose penurunan ketinggian menjadi 25m | SMARTFREN | TB | JABODETABEK (OUTER) | H | BOGOR | -6.49870 | 106.79063 | Heri : +62 813-8022-5151 | Handri : 081297986667 | 106.79063 | Heri : +62 813-8022-5151 | Handri : 081297986667
ZJKT2_4241 | 230579340231 | 1317891023 | ZJKT2_4241 | PASANGGRAHAN SOLEAR | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | A | TANGERANG | -6.2902 | 106.4224 | Imam : 081383932662 | Adit : 0895392876255 | 106.4224 | Imam : 081383932662 | Adit : 0895392876255
JAW-BT-TGR-0031 | 30572160031 | 1317481003 | JAW-BT-TGR-0031 | Kayu Agung Sepatan | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | TANGERANG | -6.096156° | 106.592519° | Ronal : 0823-2222-8333 | Adit : 0895392876255 | 106.592519° | Ronal : 0823-2222-8333 | Adit : 0895392876255
JAW-BT-TGR-0049 | 30572190031 | 1317511003 | JAW-BT-TGR-0049 | Griya Sukatani Mekarsari | 0 | 0 | XL | TB | JABODETABEK (OUTER) | A | TANGERANG | -6.128375° | 106.532867° | Ronal : 0823-2222-8333 | Adit : 0895392876255 | 106.532867° | Ronal : 0823-2222-8333 | Adit : 0895392876255
ZJKT2_6065 | 230579400231 | 1317911023 | ZJKT2_6065 | CISAIT KRAGILAN | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | B | SERANG | -6.1527 | 106.2625 | Ronal : 0823-2222-8333 | Adit : 0895392876255 | 106.2625 | Ronal : 0823-2222-8333 | Adit : 0895392876255
ZBGR_4670 | 230580760231 | 1261571023 | ZBGR_4670 | CIMANGGU 2 CIBUNGBULANG | NEW BUILD | STIP 1 | SMARTFREN | -6.5663 | JABODETABEK (OUTER) | Kp. Cibungbulang, Blok 4, RT.5/3, Desa Cimanggu II, Kec. Cibungbulang, Kab.Bogor | BOGOR | JAWA BARAT | 42 m | Ronal : 0823-2222-8333 | Adit : 0895392876255 | 42 m | Ronal : 0823-2222-8333 | Adit : 0895392876255 | Hold
ZBGR_4671 | 230580750231 | 1261561023 | ZBGR_4671 | SUKARESMI TAMANSARI | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | C | BOGOR | -6.62475 | 106.7604 | Ronal : 0823-2222-8333 | Adit : 0895392876255 | 106.7604 | Ronal : 0823-2222-8333 | Adit : 0895392876255 | Hold
ZJKT2_5971 | 230579570231 | 1317921023 | ZJKT2_5971 | PEMATANG TIGARAKSA | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | A | TANGERANG | -6.24075 | 106.45417 | Imam : 081383932662 | Handri : 081297986667 | 106.45417 | Imam : 081383932662 | Handri : 081297986667 | ready
ZJKT2_6101 | 230580660231 | 1317961023 | ZJKT2_6101 | SOLEAR BANTEN | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | A | TANGERANG | -6.285556 | 106.43283 | Imam : 081383932662 | Handri : 081297986667 | 106.43283 | Imam : 081383932662 | Handri : 081297986667 | ready
JAW-BT-TGR-0029 | 30572020031 | 1317411003 | JAW-BT-TGR-0029 | Karet Sepatan Tangerang | 0 | 0 | XL | TB | JABODETABEK (OUTER) | D | TANGERANG | -6.145972° | 106.581139° | Ronal : 0823-2222-8333 | Adit : 0895392876255 | 106.581139° | Ronal : 0823-2222-8333 | Adit : 0895392876255 | ready
JAW-JB-CBI-0066 | 30572070031 | 1260891003 | JAW-JB-CBI-0066 | Pasirmukti Citeureup | 0 | 0 | XL | TB | JABODETABEK (OUTER) | B | BOGOR | -6.505611° | 106.899817° | Heri : +62 813-8022-5151 | Handri : 081297986667 | 106.899817° | Heri : +62 813-8022-5151 | Handri : 081297986667 | ready
JAW-JB-CBI-0071 | 30572150031 | 1260931003 | JAW-JB-CBI-0071 | Pabuaran Kemang | 0 | 0 | XL | TB | JABODETABEK (OUTER) | A | BOGOR | -6.5042 | 106.7494 | Heri : +62 813-8022-5151 | Handri : 081297986667 | 106.7494 | Heri : +62 813-8022-5151 | Handri : 081297986667 | ready
JAW-JB-CBI-0063 | 30572230031 | 1260941003 | JAW-JB-CBI-0063 | Jalan Raya Puspitek | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | BOGOR | -6.367789 | 106.683114 | Sam : 087774724777 | Adit : 0895392876255 | 106.683114 | Sam : 087774724777 | Adit : 0895392876255 | done send
ZBGR_4328 | 230575230231 | 1261051023 | ZBGR_4328 | BOJONGGEDE_BOGOR | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | A | BOGOR | -6.48802 | 106.79822 | Heri : +62 813-8022-5151 | Handri : 081297986667 | 106.79822 | Heri : +62 813-8022-5151 | Handri : 081297986667 | done send
JAW-BT-TGR-0024 | 30572220031 | 1317531003 | JAW-BT-TGR-0024 | Raya Cisauk BSD | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | TANGERANG | -6.308500° | 32 m | Teguh :0852 7321 1366 | Handri : 081297986667 | 32 m | Teguh :0852 7321 1366 | Handri : 081297986667 | done send
JAW-BT-TGR-0027 | 30572310031 | 1317571003 | JAW-BT-TGR-0027 | Jatake Rangkasbitung | 0 | 0 | XL | TB | JABODETABEK (OUTER) | B | TANGERANG | -6.338472° | 106.600861° | Teguh :0852 7321 1366 | Handri : 081297986667 | 106.600861° | Teguh :0852 7321 1366 | Handri : 081297986667 | done send
ZJKT2_4258 | 230575280231 | 1261081023 | ZJKT2_4258 | TAPOS DEPOK | 0 | 0 | SMARTFREN | TB | JABODETABEK (INNER) | A | KOTA DEPOK | -6.4111 | 106.88383 | Figur :08561065681 / 0811879600 | Adit : 0895392876255 | 106.88383 | Figur :08561065681 / 0811879600 | Adit : 0895392876255 | PT. GNJ
SKB904 | 0010587860011 | 1261951001 | SKB904 | DAYEUHLUHURWARUDOYONG | 0 | 0 | TSEL | -6.94016 | JABODETABEK OUTER | Kp. Sukasari RT. 01 RW. 08 Desa Dayeuhluhur Kec. Warudoyong Kota Sukabumi | KOTA SUKABUMI | JAWA BARAT | 42 m | Ronal : 0823-2222-8333 | Adit : 0895392876255 | 42 m | Ronal : 0823-2222-8333 | Adit : 0895392876255 | PT. BNP
TGR529 | 10587940011 | 1318181001 | TGR529 | GEMPOLSARISEPATANTIMURBANTEN | 0 | 0 | TSEL | TB | JABODETABEK OUTER | Q | TANGERANG | -6.10873 | 106.61962 | Ronal : 0823-2222-8333 | Adit : 0895392876255 | 106.61962 | Ronal : 0823-2222-8333 | Adit : 0895392876255 | PT. BNP
KRW198 | 0010587920011 | 1261991001 | KRW198 | BELENDUNGKLARI | 0 | 0 | TSEL | TB | JABODETABEK OUTER | P | KARAWANG | -6.3519 | 107.388 | Teguh :0813-8824-1444 | Handri : 081297986667 | 107.388 | Teguh :0813-8824-1444 | Handri : 081297986667
JAW-JB-CBI-0068 | 30573430031 | 1260971003 | JAW-JB-CBI-0068 | Klapanunggal Cileungsi | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | BOGOR | -6.44443 | 106.95828 | Heri : +62 813-8022-5151 | Handri : 081297986667 | 106.95828 | Heri : +62 813-8022-5151 | Handri : 081297986667
KRW224 | 0010587900011 | 1261971001 | KRW224 | JLRAYACIKUNGKUNG | 0 | 0 | TSEL | TB | JABODETABEK OUTER | P | KARAWANG | -6.12789 | 107.28315 | Teguh :0813-8824-1444 | Handri : 081297986667 | 107.28315 | Teguh :0813-8824-1444 | Handri : 081297986667
ZJKT2_6092 | 230580690231 | 1317971023 | ZJKT2_6092 | SUMUR BANDUNG JAYANTI | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | B | TANGERANG | -6.20863 | 106.40324 | Imam : 081383932662 | Handri : 081297986667 | 106.40324 | Imam : 081383932662 | Handri : 081297986667
TGR523 | 0010587880011 | 1318171001 | TGR523 | KADUSIRUNG | 0 | 0 | TSEL | TB | JABODETABEK OUTER | P | TANGERANG | -6.3135 | 106.6109 | Beni : 087777366007 | Adit : 0895392876255 | 106.6109 | Beni : 087777366007 | Adit : 0895392876255 | PT. BNP
JAW-JB-CBI-0086 | 30572110031 | 1260921003 | JAW-JB-CBI-0086 | Situ Cogarongsong Pengasinan | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | BOGOR | -6.36180 | 106.69205 | Sam : 087774724777 | Adit : 0895392876255 | 106.69205 | Sam : 087774724777 | Adit : 0895392876255 | PT. DSR
ZJKT2_4373 | 230581800231 | 1261611023 | ZJKT2_4373 | MUSTIKAJAYA BEKASI | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | A | KOTA BEKASI | -6.30420 | 107.02915 | Sam : 087774724777 | Handri : 081297986667 | 107.02915 | Sam : 087774724777 | Handri : 081297986667
JAW-BT-TGR-0042 | 30572520031 | 1317711003 | JAW-BT-TGR-0042 | BABAKAN ASEM TELUK NAGA | 0 | 0 | XL | TB | JABODETABEK (OUTER) | A | TANGERANG | -6.08597 | 106.66314 | John : +62 813-8984-7599 | Adit : 0895392876255 | 106.66314 | John : +62 813-8984-7599 | Adit : 0895392876255
JAW-JK-KYB-0102 | 30571790031 | 1127641003 | JAW-JK-KYB-0102 | Menteng Lenteng Agung | 0 | 0 | XL | TB | JABODETABEK (INNER) | B | JAKARTA SELATAN | -6.32869 | 106.83049 |  |  | 106.83049
ZJKT_5207 | 230579850231 | 1128011023 | ZJKT_5207 | TEGAL ALUR KALI DERES | 0 | 0 | SMARTFREN | TB | JABODETABEK (INNER) | A | JAKARTA BARAT | -6.11359 | 106.71122 |  |  | 106.71122
ZJKT2_6038 | 230579490231 | 1261181023 | ZJKT2_6038 | CILANGKAP TAPOS | 0 | 0 | SMARTFREN | TB | JABODETABEK (INNER) | A | KOTA DEPOK | -6.45459 | 106.8635 | Ridwan : 081317600620 | Handri : 081297986667 | 106.8635 | Ridwan : 081317600620 | Handri : 081297986667 | PT. Lintas Banyu Lestari
SKB144 | 0010587930011 | 1262001001 | SKB144 | PANENMAS | 0 | 0 | TSEL | TB | JABODETABEK OUTER | P | SUKABUMI | -6.7752 | 106.8139 | Beni : 087777366007 | Adit : 0895392876255 | 106.8139 | Beni : 087777366007 | Adit : 0895392876255
JAW-JB-CBI-0082 | 30572360031 | 1260951003 | JAW-JB-CBI-0082 | Pengasinan Gunung Sindur | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | BOGOR | -6.3766 | 106.6925 | Sam : 087774724777 | Adit : 0895392876255 | 106.6925 | Sam : 087774724777 | Adit : 0895392876255 | PT. DSR
JAW-BT-CPT-0461 | 30572420031 | 1317611003 | JAW-BT-CPT-0461 | KOMPLEKS SASMITA LOKA PAMULANG BARAT | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | TANGERANG SELATAN | -6.3519 | 106.7325 |  |  | 106.7325
JAW-JK-KYB-0027 | 30571980031 | 1127761003 | JAW-JK-KYB-0027 | Sabar Raya Kemajuan | 0 | 0 | XL | TB | JABODETABEK (INNER) | C | JAKARTA SELATAN | -6.24077 | 106.75289 |  |  | 106.75289
ZBGR_4670 | 230580760231 | 1261571023 | ZBGR_4670 | CIMANGGU 2 CIBUNGBULANG | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | B | BOGOR | -6.56514 | 106.66093 | Beni : 087777366007 | Adit : 0895392876255 | 106.66093 | Beni : 087777366007 | Adit : 0895392876255 | PT. BNP
JAW-BT-TGR-0023 | 30571910031 | 1317371003 | JAW-BT-TGR-0023 | Dukuh Cukanggalih | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | TANGERANG | -6.243058 | 106.543347 | Beni : 087777366007 | Adit : 0895392876255 | 106.543347 | Beni : 087777366007 | Adit : 0895392876255 | PT. BNP
JAW-BT-TGR-0043 | 30572530031 | 1317721003 | JAW-BT-TGR-0043 | SALEMBARAN JAYA KOSAMBI | 0 | 0 | XL | TB | JABODETABEK (OUTER) | B | TANGERANG | -6.078712 | 106.666176 | John : +62 813-8984-7599 | Adit : 0895392876255 | 106.666176 | John : +62 813-8984-7599 | Adit : 0895392876255 | PT. MKI
JUX569 | JUX569 | JUX569 | JUX569 | PERMANENCOMBATTERMPENUMPANG | 0 | 0 | TSEL | TB | JABODETABEK INNER | A | JAKARTA UTARA | -6.1032 | 106.8806 |  |  | 106.8806
JUX583 | JUX583 | JUX583 | JUX583 | PERMANENCOMBATKEPANDUANPELINDO | 0 | 0 | TSEL | TB | JABODETABEK INNER | A | JAKARTA UTARA | -6.09690 | 106.8863 | Fahmi : 08119146116 | Adit : 0895392876255 | 106.8863 | Fahmi : 08119146116 | Adit : 0895392876255
KRW238 | 0010587910011 | 1261981001 | KRW238 | PERUMAHANRESINDA | 0 | 0 | TSEL | TB | JABODETABEK OUTER | Q | KARAWANG | -6.29228 | 107.27731 | Teguh :0852 7321 1366 | Handri : 081297986667 | 107.27731 | Teguh :0852 7321 1366 | Handri : 081297986667
JAW-BT-CPT-0451 | 30573420031 | 1317831003 | JAW-BT-CPT-0451 | Ciater Serpong | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | TANGERANG SELATAN | -6,32153 | 106,69678 |  |  | 106,69678
JAW-JK-KYB-0097 | 30571760031 | 1127611003 | JAW-JK-KYB-0097 | Jalan Asem Cipedak | 0 | 0 | XL | TB | JABODETABEK (INNER) | B | JAKARTA SELATAN | -6.3526 | 106.8044 |  |  | 106.8044
JAW-JK-GGP-0529 | 30571970031 | 1127751003 | JAW-JK-GGP-0529 | Pegadungan Tegal Alur | 0 | 0 | XL | TB | JABODETABEK (INNER) | C | JAKARTA BARAT | -6.1163 | 106.7049 |  |  | 106.7049
CBN552 | 10587890011 | 1261961001 | CBN552 | PERMANENCOMBATPUSDIKRESKRIM | 0 | 0 | TSEL | TB | JABODETABEK OUTER | D | BOGOR | -6.64350 | 106.9258 |  | Handri : 081297986667 | 106.9258 |  | Handri : 081297986667
JAW-JK-CKG-0666 | 30572260031 | 1127801003 | JAW-JK-CKG-0666 | Kemuning Matraman | MCP | STIP 1 | XL | -6.19742 | JABODETABEK (INNER) | Jl. Kemuning II RT. 04 RW. 04 Kel. Utan Kayu Utara Kec. Matraman, Jakarta Timur | JAKARTA TIMUR | DKI Jakarta | 20 m |  |  | 20 m
JAW-BT-TGR-0045 | 30572550031 | 1317741003 | JAW-BT-TGR-0045 | KAMPUNG BESAR TELUK NAGA | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | TANGERANG | -6.0624 | 106.6546 | Imam : 081232101679 | Adit : 0895392876255 | 106.6546 | Imam : 081232101679 | Adit : 0895392876255
JAW-BT-CPT-0460 | 30572410031 | 1317601003 | JAW-BT-CPT-0460 | VILLA MELATI MAS RAYA | 0 | 0 | XL | TB | JABODETABEK (OUTER) | B | TANGERANG SELATAN | -6.257367 | 106.6655 |  |  | 106.6655
ZJKT2_6087 | 230580710231 | 1317981023 | ZJKT2_6087 | WANA KERTA SINDANG JAYA | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | B | TANGERANG | -6.19599 | 106.50744 | Imam : 081232101679 | Adit : 0895392876255 | 106.50744 | Imam : 081232101679 | Adit : 0895392876255
JAW-BT-TNG-1457 | 30572030031 | 1317421003 | JAW-BT-TNG-1457 | Kedaung Wetan Neglasari | 0 | 0 | XL | TB | JABODETABEK (INNER) | C | KOTA TANGERANG | -6.125 | 106.6261 |  |  | 106.6261
JAW-JK-KYB-0096 | 30571750031 | 1127601003 | JAW-JK-KYB-0096 | Jalan Garuda Mas | 0 | 0 | XL | TB | JABODETABEK (INNER) | F | JAKARTA SELATAN | -6.30917 | 106.84661 |  |  | 106.84661
ZJKT2_4537 | 230575290231 | 1317861023 | ZJKT2_4537 | KARAWACI 850 | 0 | 0 | SMARTFREN | TB | JABODETABEK (INNER) | A | KOTA TANGERANG | -6.17607 | 106.62659 | Dibang : 081314245585 | Handri : 081297986667 | 106.62659 | Dibang : 081314245585 | Handri : 081297986667
ZJKT2_5966 | 230579580231 | 1317931023 | ZJKT2_5966 | BOJONG NANGKA KELAPA DUA | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | B | TANGERANG | -6.2672 | 106.597 | Imam : 081383932662 | Handri : 081297986667 | 106.597 | Imam : 081383932662 | Handri : 081297986667
ZJKT_5552 | 230560240231 | 1317261023 | ZJKT_5552 | SEPATAN TANGERANG | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | E | TANGERANG | -6.14674 | 106.58908 | Imam : 081383932662 | Handri : 081297986667 | 106.58908 | Imam : 081383932662 | Handri : 081297986667
ZJKT2_5014 | 230560370231 | 1260581023 | ZJKT2_5014 | TELUKJAMBE TIMUR | 0 | 0 | SMARTFREN | TB | JABODETABEK (OUTER) | D | KARAWANG | -6.3369 | 107.291 |  |  | 107.291
ZJKT2_6011 | 230579860231 | 1128021023 | ZJKT2_6011 | LUBANG BUAYA CIPAYUNG | 0 | 0 | SMARTFREN | TB | JABODETABEK (INNER) | C | JAKARTA TIMUR | -6.29475 | 106.8975 |  |  | 106.8975
JAW-BT-TGR-0044 | 30572540031 | 1317731003 | JAW-BT-TGR-0044 | PANTAI DADAP | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | TANGERANG | -6.0888 | 106.7203 | Dibang : 081314245585 | Handri : 081297986667 | 106.7203 | Dibang : 081314245585 | Handri : 081297986667
JAW-JK-CKG-0662 | 30573640031 | 1127961003 | JAW-JK-CKG-0662 | Nyiur Pondok Kelapa | 0 | 0 | XL | TB | JABODETABEK (INNER) | I | JAKARTA TIMUR | -6.24186 | 106.92663 |  |  | 106.92663
JAW-JK-KYB-0098 | 30571770031 | 1127621003 | JAW-JK-KYB-0098 | Jalan Pemuda Cipedak | 0 | 0 | XL | TB | JABODETABEK (INNER) | E | JAKARTA SELATAN | -6.3587 | 106.8122 |  |  | 106.8122
JAW-JK-CKG-0666 | 30572260031 | 1127801003 | JAW-JK-CKG-0666 | Kemuning Matraman | 0 | 0 | XL | TB | JABODETABEK (INNER) | E | JAKARTA TIMUR | -6.1976 | 106.8626 |  |  | 106.8626
JAW-BT-CPT-0472 | 30572500031 | 1317691003 | JAW-BT-CPT-0472 | WIJAYAKUSUMA CEGER | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | TANGERANG SELATAN | -6.2618 | 106.7274 |  |  | 106.7274
JAW-BT-CPT-0473 | 30572130031 | 1317461003 | JAW-BT-CPT-0473 | Djuna Raya Pakujaya | 0 | 0 | XL | TB | JABODETABEK (OUTER) | B | TANGERANG SELATAN | -6.2306 | 106.6906 |  |  | 106.6906
JAW-JB-CBI-0084 | 30572400031 | 1260961003 | JAW-JB-CBI-0084 | Sabililah Citeureup | 0 | 0 | XL | TB | JABODETABEK (OUTER) | D | BOGOR | -6.48569 | 106.89312 | Beni : 087777366007 | Adit : 0895392876255 | 106.89312 | Beni : 087777366007 | Adit : 0895392876255
JAW-JB-CBI-0085 | 30572090031 | 1260901003 | JAW-JB-CBI-0085 | Cilliwung Pondok Rajeg | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | BOGOR | -6.46290 | 106.81956 | Beni : 087777366007 | Adit : 0895392876255 | 106.81956 | Beni : 087777366007 | Adit : 0895392876255
JAW-JB-BGR-0213 | 30595370031 | 1262131003 | JAW-JB-BGR-0213 | CIBEBER BARENGKOK | 0 | 0 | XL | TB | JABODETABEK OUTER | A | BOGOR | -6.60523 | 106.64031 | Beni : 087777366007 | Adit : 0895392876255 | 106.64031 | Beni : 087777366007 | Adit : 0895392876255 | PT. BANJARPASIR NUSA PRATAMA
JAW-BT-CPT-0463 | 30572440031 | 1317631003 | JAW-BT-CPT-0463 | UNIVERSITAS TERBUKA PAMULANG | 0 | 0 | XL | TB | JABODETABEK (OUTER) | D | TANGERANG SELATAN | -6.339528 | 106.759917 |  |  | 106.759917
JAW-BT-TGR-0041 | 30573470031 | 1317851003 | JAW-BT-TGR-0041 | BELIMBING KOSAMBI | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | TANGERANG | -6.0829 | 106.6767 | Imam : 081383932662 | Handri : 081297986667 | 106.6767 | Imam : 081383932662 | Handri : 081297986667 | PT. mandirainfratripakarti
JAW-BT-CPT-0465 | 30572460031 | 1317651003 | JAW-BT-CPT-0465 | BERANDA SERPONG | 0 | 0 | XL | TB | JABODETABEK (OUTER) | C | TANGERANG SELATAN | -6.31657 | 106.70642 |  |  | 106.70642
JAW-BT-TGR-0028 | 30572320031 | 1317581003 | JAW-BT-TGR-0028 | Jalan Raya Korelet | 0 | 0 | XL | TB | JABODETABEK (OUTER) | D | TANGERANG | -6.2892 | 106.5386 |  |  | 106.5386
JAW-BT-TNG-1470 | 30572120031 | 1317451003 | JAW-BT-TNG-1470 | Mawi Kunciran Indah | 0 | 0 | XL | TB | JABODETABEK (INNER) | B | KOTA TANGERANG | -6.2284 | 106.6817 |  |  | 106.6817
JAW-JK-KYB-0103 | 30573400031 | 1127901003 | JAW-JK-KYB-0103 | Benda Ciganjur | 0 | 0 | XL | TB | JABODETABEK (INNER) | D | JAKARTA SELATAN | -6.3257 | 106.8061 |  |  | 106.8061
JAW-BT-TNG-1450 | 30571990031 | 1317381003 | JAW-BT-TNG-1450 | Kedaung Baru Tangerang | 0 | 0 | XL | TB | JABODETABEK (INNER) | D | KOTA TANGERANG | -6.12976 | 106.61312 | Fahrudin : 081318328292 | Adit : 0895392876255 | 106.61312 | Fahrudin : 081318328292 | Adit : 0895392876255
JAW-JB-BGR-0214 | 30595380031 | 1262141003 | JAW-JB-BGR-0214 | MEKARWANGI BOGOR | 0 | 0 | XL | TB | JABODETABEK OUTER | A | BOGOR | -6.521 | 107.1186 | Heri : +62 813-8022-5151 | Adit : 0895392876255 | 107.1186 | Heri : +62 813-8022-5151 | Adit : 0895392876255
JAW-JB-BGR-0220 | 30595400031 | 1262161003 | JAW-JB-BGR-0220 | PARUNG PANJANG BOGOR | 0 | 0 | XL | TB | JABODETABEK OUTER | C | BOGOR | -6.4141 | 106.58765 |  |  | 106.58765
JAW-BT-CPT-0469 | 30572490031 | 1317681003 | JAW-BT-CPT-0469 | DISCOVERY CONSERVA | 0 | 0 | XL | TB | JABODETABEK (OUTER) | D | TANGERANG SELATAN | -6.2611 | 106.6971 |  |  | 106.6971
JAW-JB-BGR-0223 | 30595420031 | 1262181003 | JAW-JB-BGR-0223 | JALAN RAYA CARIU JONGGOL | 0 | 0 | XL | TB | JABODETABEK OUTER | A | BOGOR | -6.4861 | 107.1097 | Heri : +62 813-8022-5151 | Adit : 0895392876255 | 107.1097 | Heri : +62 813-8022-5151 | Adit : 0895392876255
JAW-BT-TNG-1492 | 30571820031 | 1317351003 | JAW-BT-TNG-1492 | Karang Timur Tangerang | 0 | 0 | XL | TB | JABODETABEK (INNER) | E | KOTA TANGERANG | -6.2211 | 106.7156 |  |  | 106.7156
JAW-BT-CPT-0468 | 30572480031 | 1317671003 | JAW-BT-CPT-0468 | GN RAYA CIREUNDEU | 0 | 0 | XL | MCP | JABODETABEK (OUTER) | A | TANGERANG SELATAN | -6.304911 | 106.7648 |  |  | 106.7648
JAW-BT-CPT-0467 | 30572470031 | 1317661003 | JAW-BT-CPT-0467 | SITU GINTUNG CIREUNDEU | 0 | 0 | XL | TB | JABODETABEK (OUTER) | E | TANGERANG SELATAN | -6.30095 | 106.76260 |  |  | 106.76260
JAW-JK-TJP-0622 | 30572290031 | 1127831003 | JAW-JK-TJP-0622 | Tol Pelabuhan Ancol | 0 | 0 | XL | TB | JABODETABEK (INNER) | E | JAKARTA UTARA | -6.13057 | 106.83448 |  |  | 106.83448
JAW-JB-BGR-0224 | 0030595430031 | 1262191003 | JAW-JB-BGR-0224 | CIPINANG RUMPIN BOGOR | 0 | 0 | XL | TB | JABODETABEK OUTER | C | BOGOR | -6.44 | 106.6177 | Heri : +62 813-8022-5151 | Adit : 0895392876255 | 106.6177 | Heri : +62 813-8022-5151 | Adit : 0895392876255
JAW-JK-CKG-0665 | 30571850031 | 1127671003 | JAW-JK-CKG-0665 | Krama Yudha Cakung | 0 | 0 | XL | TB | JABODETABEK (INNER) | C | JAKARTA TIMUR | -6.17911 | 106.92233 |  |  | 106.92233
JAW-BT-TNG-1464 | 30572570031 | 1317761003 | JAW-BT-TNG-1464 | ALAM JAYA JATIUWUNG | 0 | 0 | XL | TB | JABODETABEK (INNER) | C | KOTA TANGERANG | -6.19367 | 106.57746 |  |  | 106.57746
JAW-BT-TNG-1452 | 30571830031 | 1317361003 | JAW-BT-TNG-1452 | Pandawa Cibodas | 0 | 0 | XL | TB | JABODETABEK (INNER) | D | KOTA TANGERANG | -6.199049° | 106.605185° |  |  | 106.605185°
| 30595360031 | 1262121003 | JAW-JB-BGR-0210 | Beringin Batulayang | NEW BUILD | STIP 1 | XL | -6.6734 | JABODETABEK OUTER | Kp. Batu kasur RT. 02 RW. 03 Kel. Batulayang Kec. Cisarua Kab. Bogor | BOGOR | JAWA BARAT | 52m | Beni : 087777366007 | Adit : 0895392876255 | 52m | Beni : 087777366007 | Adit : 0895392876255
JAW-BT-TNG-1465 | 30572580031 | 1317771003 | JAW-BT-TNG-1465 | PASIR JAYA JATIUWUNG | 0 | 0 | XL | TB | JABODETABEK (INNER) | E | KOTA TANGERANG | -6.19267 | 106.56358 | Ali : 085281006542 | Handri : 081297986667 | 106.56358 | Ali : 085281006542 | Handri : 081297986667
SRG261 | 0 | 0 | SRG261 | SITUTERATECIKANDE | 0 | 0 | TSEL | TB | JABODETABEK OUTER | Q | KAB. SERANG | -6.2082 | 106.3423 | Beni : 087777366007 | Adit : 0895392876255 | 106.3423 | Beni : 087777366007 | Adit : 0895392876255
JAW-BT-TNG-1456 | 30572510031 | 1317701003 | JAW-BT-TNG-1456 | SMPN 14 Tangerang | 0 | 0 | XL | TB | JABODETABEK (INNER) | D | KOTA TANGERANG | -6.21767 | 106.64248 |  |  | 106.64248
JAW-JK-TJP-0679 | 0030594980031 | 1128751003 | JAW-JK-TJP-0679 | LONTAR DALAM KOJA | 30.10.20 - Meminta Surat Kuasa Lurah kepada SEKCAM | 0 | XL | TB | JABODETABEK (INNER) | B | JAKARTA UTARA | -6.11881 | 106.91353 |  |  | 106.91353
JAW-JK-CKG-0662 | 30573640031 | 1127961003 | JAW-JK-CKG-0662 | Nyiur Pondok Kelapa | 0 | 0 | XL | TB | JABODETABEK (INNER) | I | JAKARTA TIMUR | -6.24186 | 106.92663 |  |  | 106.92663
JSX825 | 0 | 0 | JSX825 | JLKOSTRAD | 0 | 0 | TSEL | TB | JABODETABEK (INNER) | U | JAKARTA SELATAN | -6.23304 | 106.7606 |  |  | 106.7606
JAW-JB-BKS-0708 | 0030595820031 | 1262221003 | JAW-JB-BKS-0708 | BINTARA KENCANA TIMUR | 0 | 0 | XL | TB | JABODETABEK (OUTER) | D | KOTA BEKASI | -6.22488 | 106.95764 |  |  | 106.95764
JAW-JB-BGR-0222 | 0030595410031 | 1262171003 | JAW-JB-BGR-0222 | BABAKAN MADANG BOGOR | 0 | 0 | XL | TB | JABODETABEK (OUTER) | E | BOGOR | -6.62145 | 106.90257 | Beni : 087777366007 | Adit : 0895392876255 | 106.90257 | Beni : 087777366007 | Adit : 0895392876255
JSX900 | 0010601850011 | 1129191001 | JSX900 | KEBONBARUTEBET | 0 | 0 | TSEL | TB | JABODETABEK (INNER) | T | JAKARTA SELATAN | -6.2349 | 106.8637 |  |  | 106.8637
JAW-BT-CPT-0447 | 0030594960031 | 1318231003 | JAW-BT-CPT-0447 | JALAN MENTAWAI TOL | 0 | 0 | XL | TB | JABODETABEK (OUTER) | B | TANGERANG SELATAN | -6.29977 | 106.69607 |  |  | 106.69607
JAW-BT-CPT-0476 | 30572180031 | 1317501003 | JAW-BT-CPT-0476 | Pondok Cabe Raya | 0 | 0 | XL | TB | JABODETABEK (OUTER) | B | TANGERANG SELATAN | -6.3308 | 106.7695 |  |  | 106.7695
IN20_JB_1136 | 0230613570231 | 1319311023 | IN20_JB_1136 | WALANTAKA KOTA SERANG | NEW BUILD | STIP 1 | SMART8 | TB | C | -6.1811 | 106.2268 | JABODETABEK (OUTER) | Kp. Kadu Buntung, RT 003/RW 004, Desa Silebu, Kec. Kragilan, Kab Serang | KOTA SERANG | BANTEN | 52 | Beni : 087777366007 | Aditya R | PT BNP
| 0230613620231 | 1263641023 | IN20_JB_0812 | CITEUREUP BOGOR 2 | NEW BUILD | STIP 1 | SMART8 | TB | A | -6.5271 | 106.9073 | JABODETABEK (OUTER) | Kp. Legokrati RT. 002 RW. 003 Desa Tajur Kec. Citeureup Kab. Bogor | BOGOR | JAWA BARAT | 52 | Beni : 087777366007 | Aditya R | PT BNP
| 0230618500231 | 1264121023 | IN20_JB_1421 | PARUNG PANJANG GOROWONG | NEW BUILD | STIP 1 | SMART8 | TB | C | -6.3791 | 106.5547 | JABODETABEK (OUTER) | Jl. Kp. Lebak Ciung, Rt.14 Rw.01, Desa Gorowong, Kec. Parung Panjang, Kab. Bogor | BOGOR | JAWA BARAT | 62 | Dedi : 081387254343 | Handri P | PT ROTUA
| 0230560290231 | 1317281023 | ZJKT2_4285 | CIPONDOH KOTA TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | D | -6.1822 | 106.6723 | JABODETABEK (INNER) |  | KOTA TANGERANG | BANTEN | 32 | Ali : 085281006542 | Handri P | PT DSR
| 0230613560231 | 1319301023 | IN20_JB_1199 | GUNUNG KALER TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | H | -6.0982 | 106.3706 | JABODETABEK (OUTER) | Kp. Serdang RT 010 RW 004, Desa Cipayeh , Kec. Gunung Kaler, Kab Tangerang | TANGERANG | BANTEN | SST 52 | Wahyudi : 081318329358 | Aditya R | PT. PANEN
| 0230613640231 | 1263661023 | ZBGR_4610 | GUNUNG SINDUR JAWA BARAT | NEW BUILD | STIP 1 | SMART8 | TB | D | -6.3916 | 106.6934 | JABODETABEK (OUTER) | Kp. Kemang RT 001/RW 007 Desa Cibinong, Kecamatan Gunung Sindur, Bogor | BOGOR | JAWA BARAT | SST 52 | Teguh : 081388241444 | Aditya R | PT. ORLIE
| 0230618480231 | 1264101023 | INJB21_0538 | TENJOLAYA BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | A | -6.6587 | 106.7141 | JABODETABEK (OUTER) | Kp. Pasir Gaok RT. 01 RW. 04 Desa. Gunung Malang Kec. Tenjolaya Kab. Bogor | BOGOR | JAWA BARAT | SST 52 |  | Handri P | PT Datatel
| 0230615380231 | 1263831023 | ZBGR_4605 | CIBUNGBULANG BOGOR 2 | NEW BUILD | STIP 1 | SMART8 | TB | B | -6.586 | 106.6628 | JABODETABEK (OUTER) | Jl. Kapten Dasuki Bakri RT 001 RW 01 Cibatok II, Kecamatan Cibungbulang, Kabupaten Bogor | BOGOR | JAWA BARAT | SST 62 | Teguh : 081388241444 | Handri P | PT. ORLIE
| 0230618490231 | 1264111023 | HUNew_BDG4716-2 | WARUNG KIARA SUKABUMI | NEW BUILD | STIP 1 | SMART8 | TB | B | -7.001 | 106.7179 | JABODETABEK (OUTER) | Kp. Cilandak RT. 02/04 Desa. Sirnajaya Kec. Warung Kiara Kab. Sukabumi | SUKABUMI | JAWA BARAT | SST 62 | July : 087885357910 | Handri P | PT Datatel
| 0010619490011 | 1264281001 | SKB204 | PASARCISAATSKB | NEW BUILD | STIP 1 | TSEL | TB | R | -6.9002 | 106.8933 | JABODETABEK (OUTER) | Jl. Kadu Dampit RT 17/RW 03 Desa Nagrak, Kecamatan Cisaat, Sukabumi | SUKABUMI | JAWA BARAT | SST 52 | Beni : 087777366007 | Aditya R | PT. BNP
| 0010622710011 | 1319641001 | SRG269 | PERMANENTCOMBATCIKANDEPERMAI | NEW BUILD | STIP 1 | TSEL | TB | P | -6.2236 | 106.3451 | JABODETABEK (OUTER) | Kp. Kalutuk RT 007 RW 003 Desa Cikande Permai Kecamatan Cikande Kabupaten Serang | SERANG | BANTEN | SST 42 | Beni : 087777366007 | Aditya R | PT. BNP
| 0230613590231 | 1263621023 | ZBDG_5616 | PARUNG KUDA SUKABUMI | NEW BUILD | STIP 1 | SMART8 | TB | E | -6.8683 | 106.7685 | JABODETABEK (OUTER) | Jl. Raya Siliwangi RT 30 RW 12, Desa Sundawenang, Kec. Parung Kuda, Kabupaten Sukabumi | SUKABUMI | JAWA BARAT | SST 52 | Ali : 085281006542 | Handri P | PT DSR
| 0230614440231 | 1263691023 | HUNew_BGR4085-2 | GUNUNG SINDUR BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | E | -6.3792 | 106.6559 | JABODETABEK (OUTER) | Kp.Gunung Sindur RT 003 RW 011 Desa Gunung Sindur Kec.Gunung Sindur Kab.Bogor Provinsi Jawa Barat | BOGOR | JAWA BARAT | SST 52 | Teguh : 081388241444 | Handri P | PT. ORLIE
| 0230618470231 | 1264091023 | INJB21_0218 | LEUWILIANG BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | E | -6.5833 | 106.6354 | JABODETABEK (OUTER) | Kp. Banyusuci RT. 004 RW. 004 Desa leuwimekar kec. Leuwiliang kab. Bogor | BOGOR | JAWA BARAT | SST 62 | Heri : +62 81380225151 |  | PT ORLIE
| 0230613930231 | 1319351023 | ZJKT2_6111 | KOSAMBI TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | A | -6.1078 | 106.6466 | JABODETABEK (OUTER) | Kp Pintu Kapuk Rt.028 Rw.011 Desa Bojong Renged Kecamatan Teluk Naga Kab. Tangerang | TANGERANG | BANTEN | SST 32 | Ali : 085281006542 | Handri P | PT CMI
| 0010622720011 | 1319651001 | RKB069 | CURUGBADAKMAJA | NEW BUILD | STIP 1 | TSEL | TB | Q | -6.3455 | 106.3798 | JABODETABEK (OUTER) | Kp. Ciganjur RT 001 RW 005 Kelurahan Curugbadak Kecamatan Maja Kabupaten Lebak | LEBAK | BANTEN | SST 52 | Fahmi : 08119146116 | Aditya R | PT. KLS
| 0010622750011 | 1264691001 | CBN436 | CURUGBITUNGNANGGUNG | NEW BUILD | STIP 1 | TSEL | TB | V | -6.6285 | 106.5426 | JABODETABEK (OUTER) | Kp. Situhiang RT 001 RW 005 Desa Curugbitung Kecamatan Nanggung Kabupaten Bogor | BOGOR | JAWA BARAT | SST 52 | Beni : 087777366007 | Handri P | PT. BNP
| 0010623840011 | 1265091001 | SKB215 | SUKAJAYASALABINTANA | NEW BUILD | STIP 1 | TSEL | TB | S | -6.896 | 106.9481 | JABODETABEK (OUTER) | Kp. Nangewer RT 012 RW 005 Desa Sukajaya Kecamatan Sukabumi Kabupaten Sukabumi | SUKABUMI | JAWA BARAT | SST 52 | Beni : 087777366007 | Handri P | PT. BNP
| 0230614370231 | 1263681023 | ZJKT2_4127 | LIMO KOTA DEPOK | NEW BUILD | STIP 1 | SMART8 | TB | E | -6.3784 | 106.7755 | JABODETABEK (INNER) | Jl. Mushola Darussalam RT. 001 / RW. 011, Kel Meruyung, Kec Limo, Kota Depok, Prov. Jawa barat | KOTA DEPOK | JAWA BARAT | CMF 32 | July : 087885357910 | Aditya R | PT. Datatel
| 0010680100011 | 1321801001 | TNX322 | PASARBARUKARAWACI | NEW BUILD | STIP 1 | TSEL | TB | Q | -6.1634 | 106.6267 | JABODETABEK (INNER) | Jl. KS Tubun No 30, RT.005 RW. 03 Kelurahan Koang Jaya, Kec. Krawaci, Kota Tangerang, Provinsi Banten | KOTA TANGERANG | BANTEN | SST 42 | Fauzal : 081282637926 | Aditya R | PT. CMI
| 03047667031 | 131579110 | JAW-BT-TNG-1653 | PANUNGGANGAN BARAT KARAWACI RELOCATION | NEW BUILD | STIP 1 | XL | TB |  | -6.2156 | 106.6213 | JABODETABEK (INNER) | Kp. Kebon Kelapa Rt 001/006 Kel Panunggangan Barat Kec Cibodas Kota Tangerang Kec. Cibodas Kota Tangerang | KOTA TANGERANG | BANTEN | SST 32 | Dani : 081320217971 |  | PT. Turangga
| 0230613710231 | 1319321023 | ZJKT2_5467 | KOSAMBI BANTEN | NEW BUILD | STIP 1 | SMART8 | TB | D | -6.0774 | 106.684 | JABODETABEK (OUTER) | Kp. Rawa Lindung RT 07/RW 05, Desa Cengklong, Kecamatan Kosambi, Kabupaten Tangerang, Propinsi Banten |  | BANTEN | SST 42 | July : 087885357910 | Aditya R | PT. Datatel
| 0010684910011 | 1134051001 | TF71 | Alfamart Pantjoran PIK |  | STIP 8 | TSEL | PKP |  | -6.0898 | 106.7438 | JABODETABEK (INNER) | Rukan The Golf D Nomor 050-052 Type Hoek Plus, Kel. Kamal Muara, Kec. Penjaringan, Jakarta Utara, DKI Jakarta | Jakarta Utara | DKI JAKARTA | RT 17.5 + Pole 6
| 0230613750231 | 1319331023 | ZJKT2_5468 | TIGARAKSA TANGERANG 2 | NEW BUILD | STIP 1 | SMART8 | TB | D | -6.2441 | 106.4806 | JABODETABEK (OUTER) | Kp Matagara RT 02 RW 02, Desa Matagara, Kecamatan Tigaraksa, Kabupaten Tangerang | TANGERANG | BANTEN | SST 52 | Teguh : 081388241444 | Aditya R | PT. ORLIE
| 0230680590231 | 1271491023 | ZBGR_4663 | PAMIJAHAN BOGOR 2 | NEW BUILD | STIP 1 | SMART8 | TB | D | -6.6468 | 106.6456 | JABODETABEK (OUTER) | Kp Tonjong RT 03 RW 03, Kelurahan Cibitung Wetan, Kecamatan Pamijahan, Kabupaten Bogor | BOGOR | JAWA BARAT | SST 52 | Heri : 081380225151 | Aditya R | PT. ORLIE
| 0010680110011 | 1271401001 | CKR330 | PERUMAHANCIBARUSAHJAYA | NEW BUILD | STIP 1 | TSEL | TB | Q | -6.4319 | 107.0789 | JABODETABEK (OUTER) | Kp Malaka RT 001 RW 006, Desa Cibarusah Kota, Kec. Cibarusah, Kab. Bekasi, Jawa Barat | BEKASI | JAWA BARAT | SST 42 | Fahmi : 08119146116 |  | PT. KLS
| 0010688680011 | 1134381001 | JSX943 | CILANDAKBAWAH | NEW BUILD | STIP 1 | TSEL | TB | W | -6.2869 | 106.8007 | JABODETABEK (INNER) | JL. CILANDAK BAWAH RT 010.RW 013 CILANDAK BARAT, CILANDAK, JAKARTA SELATAN | JAKARTA SELATAN | DKI JAKARTA | MCP 25 | Reboin : 081298832281 |  | PT KLS
| 0230687880231 | 1272121023 | ZBGR_4687 | BOGOR BOJONG GEDE | NEW BUILD | STIP 1 | SMART8 | TB | B | -6.4704 | 106.7963 | JABODETABEK (OUTER) | Kp Parakan Jati RT 004 RW 004, Desa Susukan, Kecamatan Bojon Geda, Kabupaten Bogor | BOGOR | JAWA BARAT | SST 42 | Iron : 081617668742 |  | PT. LBL
| 0230686620231 | 1321931023 | ZJKT2_6180 | TANGERANG KOSAMBI | NEW BUILD | STIP 1 | SMART8 | TB | B | -6.1015 | 106.6643 | JABODETABEK (OUTER) | Kp Kresek RT 04 RW 07, Desa Rawaburung, Kec. Kosambi, Kab. Tangerang, Banten | TANGERANG | BANTEN | SST 32 | Beni : 087777366007 |  | PT. BNP
| 0230688650231 | 1272251023 | INJB21_0322 | KARAWANG MAJALAYA | NEW BUILD | STIP 1 | SMART8 | TB | A | -6.315 | 107.3503 | JABODETABEK (OUTER) | Kp. Wagir II RT 067 RW 06, Desa Bengle, Kec. Majalaya, Kab. Karawang, Jawa Barat | KARAWANG | JAWA BARAT | SST 42 | Teguh : 081388241444 |  | PT. ORLIE
| 0010623880011 | 1265101001 | TGR236 | PERMANENTCMBTLIONAIR | NEW BUILD | STIP 1 | TSEL | TB | V | -6.1938 | 106.4971 | JABODETABEK (OUTER) | Ruko Telaga Bestari RT 008 RW 05 Desa Wanakerta, Kecamatan Sindang Jaya, Kabupaten Tangerang | TANGERANG | BANTEN | RT 8 + MT 25 | Teguh : 081388241444 |  | PT. ORLIE
| 0230687940231 | 1272131023 | HUNew_BDG5992-2 | SUKABUMI CIKIDANG | NEW BUILD | STIP 1 | SMART8 | TB | B | -6.8822 | 106.6699 | JABODETABEK (OUTER) | Kp. Simpang RT 002 RW 005, Desa Pangkalan, Kec. Cikidang, Kab Sukabumi | SUKABUMI | JAWA BARAT | SST 72 | Beni : 087777366007 |  | PT. BNP
|  |  | CBN521 | RUMPINTAMASARI | NEW BUILD | STIP 1 | TSEL | TB | P | -6.4042 | 106.6163 | JABODETABEK (OUTER) | Kp. Cibuluheun RT 003 RW 009, Desa Tamansari, Kecamatan Rumpin, Kabupaten Bogor | BOGOR | JAWA BARAT | SST 42 | Beni : 087777366007 |  | PT. BNP
|  |  | RKB078 | JALUPANGMULYA | NEW BUILD | STIP 1 | TSEL | TB | P | -6.5275 | 106.2257 | JABODETABEK (OUTER) | Kp. Sukatani RT 04 RW 02, Desa Jalupang Mulya, Kecamatan Leuwidamar, Kabupaten Lebak | LEBAK | BANTEN | SST 62 | Fahmi : 08119146116 |  | PT. KLS
|  |  | PDG123 | DESAPANGGUKINGAN | NEW BUILD | STIP 1 | TSEL | TB | P | -6.278 | 106.1682 | JABODETABEK (OUTER) | Kp. Cirembang RT 001 RW 003 Desa Koroncong, Kec. Koroncong, Kab. Pandeglang | PANDEGLANG | BANTEN | SST 52 | Fahmi : 08119146116 |  | PT. KLS
|  |  | TGR542 | RANCAGEDEGUNUNGKALER | NEW BUILD | STIP 1 | TSEL | TB | R | -6.0893 | 106.3871 | JABODETABEK (OUTER) | Kp. Bolang Pabrik, Desa Ranca Gede, Kecamatan Gunung Kaler, Kabupaten Tangerang | TANGERANG | BANTEN | SST 42 | Yudin : 081298521940 |  | PT. PJA
|  |  | KRW262 | CILAMAYA KULONPASIRJAYA | NEW BUILD | STIP 1 | TSEL | TB | P | -6.1928 | 107.5256 | JABODETABEK (OUTER) | Kp. Asan RT 002 RW 001, Desa Pasirjaya, Kecamatan Cilamaya Kulon, Kabupaten Karawang | KARAWANG | JAWA BARAT | SST 52 | Angga : 089691459292 |  | PT. ORLIE
| 0010704600011 | 1273671001 | BOX048 | MEKARWANGITANAHSEREAL | NEW BUILD | STIP 1 | TSEL | TB | P | -6.5474 | 106.7873 | JABODETABEK (OUTER) | Kp. Situ pete RT. 01/10 Kel. Sukadamai Kec. Tanah Sereal Kota Bogor | KOTA BOGOR | JAWA BARAT | SST 42 | Dave : 087773922777 |  | PT. AFI
| 0010704550011 | 1273641001 | CBN471 | PARUNG PANJANGJAGABITA | NEW BUILD | STIP 1 | TSEL | TB | P | -6.3295 | 106.5173 | JABODETABEK (OUTER) | Kp Jawiah RT 02 RW 01 Kelurahan Jagabita, Kecamatan Parung Panjang, Kab Bogor | BOGOR | JAWA BARAT | SST 62 | Beni : 087777366007 |  | PT. BNP
| 0010704640011 | 1322491001 | TGR546 | SOLEARTANGERANG | NEW BUILD | STIP 1 | TSEL | TB | P | -6.2897 | 106.4025 | JABODETABEK (OUTER) | Kp. Sukamanah RT 04 RW 03, Desa Solear, Kecamatan Solear, Kabupaten Tangerang | TANGERANG | BANTEN | SST 52 | Nurdiansyah : 081385545728 |  | PT. RMB
| 0010704520011 | 1322451001 | TGR433 | RAJEG_TANJAKAN MEKAR | NEW BUILD | STIP 1 | TSEL | TB | P | -6.101 | 106.5318 | JABODETABEK (OUTER) | Kp. Jungkel RT 10 RW 04, Kel. Tanjakan Mekar, Kecamatan Rajeg, Kab. Tangerang | TANGERANG | BANTEN | SST 52 | Nurdiansyah : 081385545728 |  | PT. RMB
| 0010704610011 | 1322481001 | SRG284 | KAREOJAWILAN | NEW BUILD | STIP 1 | TSEL | TB | P | -6.25 | 106.3471 | JABODETABEK (OUTER) | Kp. Paya Umbul RT.13/RW 05 Desa Junti, Kec. Jawilan, Kab. Serang | SERANG | BANTEN | SST 52 | Fahmi : 082311769797 |  | PT. Tritama
| 0010690940011 | 1134491001 | JTX537 | RAYAPONCOL | NEW BUILD | STIP 1 | TSEL | PKP | S | -6.32 | 106.873 | JABODETABEK (INNER) | Jl Masjid RT 11 RW 07 Kelurahan Susukan Kecamatan Ciracas Kota Jakarta Timur | JAKARTA TIMUR | DKI JAKARTA | Stacking 6m + MT 25m | Iron : 081617668742 |  | PT. LBL
|  |  | CBN500 | CIPEUCANG | NEW BUILD | STIP 1 | TSEL | TB | P | -6.8862 | 106.9496 | JABODETABEK (OUTER) | Blok Palasari RT 23 RW 07, Kelurahan Sudajayagirang, kecamatan Sukabumi, Kab. Sukabumi | SUKABUMI | JAWA BARAT | SST 52 | Beni : 087777366007 |  | PT. BNP
| 0010704630011 | 1273691001 | PLR012 | SUDAJAYAGIRANGSKB | NEW BUILD | STIP 1 | TSEL | TB | P | -6.4121 | 107.0515 | JABODETABEK (OUTER) | Kp. Kubang RT 11 RW 05, Kelurahan Jatisari, Kecamatan Cileungsi, Kab. Bogor | BOGOR | JAWA BARAT | SST 52 | Beni : 087777366007 |  | PT. BNP
| 0010704500011 | 1273601001 | KRW263 | CIKARANG CILAMAYA WETAN | NEW BUILD | STIP 1 | TSEL | TB | P | -6.2701 | 107.5468 | JABODETABEK (OUTER) | Kp. Cimahi RT 010 RW 006 Desa Cikarang, Kecamatan Cilamaya Wetan, Kab. Karawang | KARAWANG | JAWA BARAT | SST 52 | Angga : 089691459292 |  | PT. ORLIE
| 0010704540011 | 1273631001 | KRW252 | KARAWANG BARATMEKARJATI | NEW BUILD | STIP 1 | TSEL | TB | S | -6.2446 | 107.2984 | JABODETABEK (OUTER) | Kp. Secang RT 01 RW 08, Kel.,Mekarjati, Kec. Karawang Barat, Kab. Tangerang | KARAWANG | JAWA BARAT | SST 52 | Angga : 089691459292 |  | PT. ORLIE
| 0010704660011 | 1322501001 | TGR543 | RAYAKRONJOMEKARBARU | NEW BUILD | STIP 1 | TSEL | TB | Q | -6.0472 | 106.4022 | JABODETABEK (OUTER) | JL Raya Kronjo – Jenggot RT 005/RW 002 Desa Muncung, Kecamatan Kronjo, Kabupaten Tangerang | TANGERANG | BANTEN | SST 62 | Yudin : 081298521940 |  | PT. PJA
| 0010704510011 | 1273611001 | KRW256 | TBG KLARI | NEW BUILD | STIP 1 | TSEL | TB | R | -6.3484 | 107.3575 | JABODETABEK (OUTER) | Dusun Kopo RT 008 RW 002 Desa Klari, Kecamatan Klari, Kab Karawang | KARAWANG | JAWA BARAT | SST 42 | Angga : 089691459292 |  | PT. ORLIE
| 0230691670231 | 1272421023 | ZBGR_4212 | PKP KAREHKEL BOGOR | NEW BUILD | STIP 1 | SMART8 | PKP | D | -6.5633 | 106.6333 | JABODETABEK (OUTER) | Kp. Parung Panjang Lebak RT. 002 RW. 007 Desa Leuwiliang Kecamatan Leuwiliang Kabupaten Bogor Prov. Jawa Barat | BOGOR | JAWA BARAT | SST 62 | Angga : 089691459292 |  | PT ORLIE
| 0010709110011 | 1322591001 | TGR555 | PERMANENDANGDANGCISAUK2 | NEW BUILD | STIP 1 | TSEL | TB | P | -6.3567 | 106.6205 | JABODETABEK (OUTER) | Kp. Dukuh RT 011 RW.004 Desa Dangdang Kecamatan Cisauk Kabupaten Tangerang | TANGERANG | BANTEN | SST 42 | Ali : 085281006542 |  | PT CMI
| 0010709120011 | 1274551001 | CBN623 | PERMANENCOMBATTIRTAWARNARUMPIN | NEW BUILD | STIP 1 | TSEL | TB | P | -6.3779 | 106.6368 | JABODETABEK (OUTER) | Kp Legok Nyerang RT 001 RW 007 Desa Sukamulya Kecamatan Rumpin, Kab. Rumpin | BOGOR | JAWA BARAT | SST 42 | Fahmi : 082311769797 |  | PT Tritama
| 0010709090011 | 1274541001 | CKR368 | PERMANENPERUMSERANGSELALU | NEW BUILD | STIP 1 | TSEL | TB | P | 107.1504 | -6.3926 | JABODETABEK (OUTER) | Kp Karang Sambung RT 008 RW 004 Desa Nagasari, Kec. Serang Baru, Kabupaten Bekasi | BEKASI | JAWA BARAT | SST 42 | Anggia : 087870951715 |  | PT Aulia
| 0010704580011 | 1273661001 | SKB155 | TANJUNGJAMPANGKULON | NEW BUILD | STIP 1 | TSEL | TB | S | -7.2471 | 106.6245 | JABODETABEK (OUTER) | Kp. Neglababakan RT 06 RW 05, Desa Tanjung, Kecamatan Jampang Kulon, Kabupaten Sukabumi | SUKABUMI | JAWA BARAT | SST 52 | Beni : 087777366007 |  | PT BNP
| 0010709100011 | 1322581001 | TGR553 | PERMANENDRIYACATANIA | NEW BUILD | STIP 1 | TSEL | TB | P | -6.2763 | 106.5319 | JABODETABEK (OUTER) | Kp Panongan RT.01 RW.04, Desa Panongan, Kec. Panongan, Kab. Tangerang | TANGERANG | BANTEN | SST 42 | Ali : 085281006542 |  | PT. CMI
| 0230708380231 | 1274421023 | ZBGR_4578 | PABUARAN BOJONG GEDE | NEW BUILD | STIP 1 | SMART8 | TB | A | -6.455 | 106.7974 | JABODETABEK (OUTER) | Kp. Pintu Air RT 001 RW 009, Kelurahan Pabuaran, Kecamatan Bojong Gede, Kab. Bogor | BOGOR | JAWA BARAT | SST 42 | Beni : 087777366007 |  | PT. BNP
| 0010709060011 | 1274511001 | CKR363 | PERMANENRAYAPEBANYURANN | NEW BUILD | STIP 1 | TSEL | TB | R | -6.2305 | 107.2652 | JABODETABEK (OUTER) | Jln Kampung Wate RT 03 RW 04, Desa Karang Mekar. Kecamatan Kedungwaringin, Kab. Bekasi, Jawa Barat | BEKASI | JAWA BARAT | SST 42 | Dani : 081320217971 |  | PT. Turangga
| 0010708720011 | 1274471001 | CKR360 | TELAGAMURNICIKARANGBARAT | NEW BUILD | STIP 1 | TSEL | TB | R | -6.2487 | 107.1262 | JABODETABEK (OUTER) | Jln Kampung Sri Bodas RT 03 RW 09 Desa Telaga Murni, Kecamatan Cikarang Barat, Kab. Bekasi | BEKASI | JAWA BARAT | SST 52 | Dickson : 08118883611 |  | PT. Abbasy
| 0010708710011 | 1274461001 | BOX045 | BUKITCIMANGGUCITY | NEW BUILD | STIP 1 | TSEL | TB | S | -6.5344 | 106.7871 | JABODETABEK (OUTER) | Jalan Raya Kencana RT 05 RW 02, Kelurahan Kencana, Kecamatan Tanah Sereal, Kota Bogor | KOTA BOGOR | JAWA BARAT | SST 42 | Fahmi : 082311769797 |  | PT. Tritama
| 0230700270231 | 1322371023 | INJB21_0174 | TANGERANG JAYANTI | NEW BUILD | STIP 1 | SMART8 | TB | D | -6.2168 | 106.4123 | JABODETABEK (OUTER) | Kp. Kramat RT 012/RW 003, Desa Sumurbandung, Kec. Jayanti, Kab. Tangerang | TANGERANG | BANTEN | SST 42 | Danang : 081280349804 |  | PT. Sinfra
| 0010704590011 | 1322471001 | CLG115 | BENDUNGANCILEGON | NEW BUILD | STIP 1 | TSEL | TB | S | -6.0365 | 106.0513 | JABODETABEK (OUTER) | Jl. K. H. Musatmil, Kelurahan Karang Asem, Kecamatan Cibeber, Kota Cilegon | TANGERANG | BANTEN | SST 42 | Yudin : 081298521940 |  | PT. PJA
| 0040714990041 | 1275391004 | 03SUK700 | KARANGMEKAR_CIMANGGU_SUK | NEW BUILD | STIP 1 | ISAT | TB | B | -7.2455 | 106.6518 | JABODETABEK (OUTER) | Kp Batununggul RT 03/RW 02, Desa Karangmekar, Kecamatan Cimanggu, Kab. Sukabumi, Jawa Barat | SUKABUMI | JAWA BARAT | SST 62 | July : 087885357910 |  | PT. Datatel
| 0040714970041 | 1275371004 | 03SUK692 | TEGALBULEUD_TEGALBULEUD_SUK | NEW BUILD | STIP 1 | ISAT | TB | A | -7.417 | 106.7817 | JABODETABEK (OUTER) | Kp Karang Anyar RT 001 RW 005 Desa Tegal Bulued, Kecamatan Tegal Bulued Kab Bekasi | SUKABUMI | JAWA BARAT | SST 52 | Angga : 089691459292 |  | PT. ORLIE
| 0010714680011 | 1275281001 | CBN618 | PERMANENKERTAJAYARUMPIN | NEW BUILD | STIP 1 | TSEL | TB | R | -6.3859 | 106.612 | JABODETABEK (OUTER) | Kp. Kemang RT 002/RW 004, Desa Mekarsari, Kecamatan Rumpin, Bogor | BOGOR | JAWA BARAT | SST 42 | Fahmi : 082311769797 |  | PT. Tritama
| 0230707780231 | 1274361023 | ZBGR_4576 | BOGOR SUKARAJA 2 | NEW BUILD | STIP 1 | SMART8 | TB | A | -6.5183 | 106.8459 | JABODETABEK (OUTER) | Kp. Babakan Rawahaur RT 03 RW 05, Desa Sentul, Kec. Babakan, Kab. Bogor | BOGOR | JAWA BARAT | SST 42 | Robi : 082218823364 |  | PT. DPP
| 0010708700011 | 1274451001 | CKR349 | KARANGANYARBAHAGIA | NEW BUILD | STIP 1 | TSEL | TB | R | -6.2019 | 107.1842 | JABODETABEK (OUTER) | Kp. Kedaung RT 001 RW 005, Desa Karang Anyar, Kecamatan Karang Bahagia, Kab. Bekasi | BEKASI | JAWA BARAT | SST 52 | Angga : 089691459292 |  | PT. ORLIE
| 0010708690011 | 1274441001 | CBN480 | BANTARSARIRANCABUNGUR | NEW BUILD | STIP 1 | TSEL | TB | S | 106.7433 | -6.5291 | JABODETABEK (OUTER) | Jl. Bantarsari RT 01 RW 06, Desa Bantarsari, Kecamatan Rancabungur, Kabupaten Bogor | BOGOR | JAWA BARAT | SST 42 | Beni : 087777366007 |  | PT. BNP
| 0010714690011 | 1275291001 | CKR364 | PERMANENKAREDOKCIBARUSAH | NEW BUILD | STIP 1 | TSEL | TB | P | -6.4051 | 107.0838 | JABODETABEK (OUTER) | Kp. Sampora RT 015 RW 007 Desa Jayamulya, Kec. Serang Baru, Kabupaten Bekasi, Jawa Barat | BEKASI | JAWA BARAT | SST 42 | Anggia : 087870951715 |  | PT. Aulia
|  |  | CKR367 | PERMANENPTIDEMITSU | NEW BUILD | STIP 1 | TSEL | TB | P | -6.3998 | 107.2125 | JABODETABEK (OUTER) | Kp. Rawadomba RT 013 RW 006 Desa Sukabunga Kec. Bojongmangu, Kabupaten Bekasi, Jawa Barat | BEKASI | JAWA BARAT | SST 42 | Anggia : 087870951715 |  | PT. Aulia
| 0230613830231 | 1319341023 | ZJKT2_6085 | PERIUK KOTA TANGERANG | NEW BUILD | STIP 1 | SMART8 | TB | D | -6.1679 | 106.5962 | JABODETABEK (INNER) | Perumahan Mutiara Pluit Blok C6 No.38 RT02 RW11 Kelurahan Periuk Kecamatan Periuk Kota Tangerang Provinsi Banten | KOTA TANGERANG | BANTEN | SST 42 (3 Legs) | Robi : 082218823364 |  | PT. DPP
| 0230687850231 | 1322021023 | ZJKT2_6089 | TANGERANG CIPONDOH | NEW BUILD | STIP 1 | SMART8 | TB | P | -6.1974 | 106.686 | JABODETABEK (INNER) | Jalan Kenanga RT 003/RW 001, Kelurahan Kenanga, Kecamatan CIpondoh,Kabupaten Tangerang | TANGERANG | BANTEN | SST 42 (4 Legs) | Yudin : 081298521940 |  | PT. PJA
| 0230707930231 | 1274391023 | INBGR4334-3 | PAMIJAHAN BOGOR 3 | NEW BUILD | STIP 1 | SMART8 | TB | C | -6.6088 | 106.6656 | JABODETABEK (OUTER) | Kp. Cimayang Asem RT 06 RW 02, Desa Cimayang, Kecamatan Pamijahan, Kabupaten Bogor | BOGOR | JAWA BARAT | SST 52 | July : 087885357910 |  | PT. Datatel
| 0230700230231 | 1322361023 | INJB21_0107 | TANGERANG TELUKNAGA | NEW BUILD | STIP 1 | SMART8 | TB | C | -6.0672 | 106.6436 | JABODETABEK (OUTER) | Kp. Sukadamai RT 06 RW 08, Desa Pangkalan, Kecamatan Teluknaga, Kabupaten Tangerang | TANGERANG | BANTEN | SST 52 | Ardha : 08122122082 |  | PT. RMB
| 0010722830011 | 1275741001 | BKX430 | PERMANENCOMBATPERUMPTMBEKASI | NEW BUILD | STIP 1 | TSEL | TB | R | -6.2515 | 107.2427 | JABODETABEK (OUTER) | Pondok Jingga, RT.003/RW.013, Kel. Jaka Setia, Kec. Bekasi Selatan, Kota Bekasi, Jawa Barat | KOTA BEKASI | JAWA BARAT | MCP 25 | Fauzal : 081282637926 |  | PT. CMI
| 0010722760011 | 1275671001 | CKR366 | PERMANENPERUMPERMATAINDAH | NEW BUILD | STIP 1 | TSEL | TB | S | -6.2515 | 107.2427 | JABODETABEK (OUTER) | Kampung Baleker RT 004/RW 004 Desa Waringin Jaya Kec. Kedung Waringin Kab. Bekasi | BEKASI | JAWA BARAT | SST 42 | Yusuf : 085314917853 |  | PT. Rotua
| 0040714980041 | 1275381004 | 03SUK682 | UBRUG_WARUNGKIARA_SUK | NEW BUILD | STIP 1 | ISAT | TB | D | -6.9574 | 106.7579 | JABODETABEK (OUTER) | Kp. Cicatih RT. 05 RW 05 Desa. Cimanggu Kec. Cikembar Kab. Sukabumi | SUKABUMI | JAWA BARAT | SST 62 | July : 087885357910 |  | PT. Datatel
| 0230720970231 | 1275521023 | INBDG4152-3 | SUKABUMI CARINGIN | NEW BUILD | STIP 1 | SMART8 | TB | A | -6.8507 | 106.8847 | JABODETABEK (OUTER) | KP. CIHEULAGIRANG RT 007 RW 003, DESA SUKAMULYA, KEC. CARINGIN, KAB. SUKABUMI | SUKABUMI | JAWA BARAT | SST 62 | Angga : 089691459292 |  | PT. ORLIE
| 0230707770231 | 1322571023 | INJB21_0244 | TANGERANG LEGOK | NEW BUILD | STIP 1 | SMART8 | TB | E | -6.3053 | 106.5811 | JABODETABEK (OUTER) | Kp. Bojong Indah RT.03/02 Desa kemuning kec. Legok, Kab Tangerang, Banten | TANGERANG | BANTEN | SST 32 | Beni : 087777366007 |  | PT. BNP
| 0230721390231 | 1322631023 | INJB21_0327 | SERANG CARENANG | NEW BUILD | STIP 1 | SMART8 | TB | A | -6.0974 | 106.3047 | JABODETABEK (OUTER) | Kp Tegalsere RT 26/RW 04, Desa Walikukun, Kecamatan Carenang, Kab. Serang | SERANG | BANTEN | SST 52 | Reboin : 081298832281 |  | PT. KLS

## Cancle
sonumb | site_id | site_id_opr | SiteName | sitename_opr | Site_Type | STIPCategory | operator_id | company_id | No_FPKI_STIP | Tgl_FPKI_STIP | latitude | longitude | Address | regional_name | kabupaten_name | province_name | Height | Tahapan_Project
0030572280031 | 1127821003 | JAW-JK-TJP-0621 | DUFAN MARINA | Dufan Marina | NEW BUILD | STIP 1 | XL | TB | 018413/TBG-TB/XL/MKT/01/2020 | 2020-01-14 | -6.125313 | 106.830387 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 20 | CIP
0030696360031 | 1134551003 | JAW-JK-KSU-1132 | PULAU BIDADARI | PULAU BIDADARI | NEW BUILD | STIP 1 | XL | TB | 042492/TBG-TB/XL/MKT/08/2021 | 2021-08-18 | -6.035588 | 106.746780 |  | JABODETABEK (INNER) | ADMINISTRASI KEPULAUAN SERIBU | DKI JAKARTA | 42 | PRECANCEL
0010704620011 | 1273681001 | CBN483 | CARINGINBOCIMI | CARINGINBOCIMI | NEW BUILD | STIP 1 | TSEL | TB | 044445/TBG-TB/TSEL/MKT/09/2021 | 2021-09-03 | -6.68864 | 106.82696 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | PRECANCEL
0030595440031 | 1262201003 | JAW-JB-BGR-0227 | CILEUKSA SUKAJAYA | Cileuksa Sukajaya | NEW BUILD | STIP 1 | XL | TB | 023524/TBG-TB/XL/MKT/06/2020 | 2020-06-25 | -6.59522 | 106.44636 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 40 | CIP
0030600240031 | 1129131003 | JAW-JK-TJP-0640 | KALIBARU CILINCING | Kalibaru Cilincing | NEW BUILD | STIP 1 | XL | PKP | 025012/TBG-PKP/XL/MKT/09/2020 | 2020-09-08 | -6.100122 | 106.92812 |  | JABODETABEK (INNER) | JAKARTA UTARA | DKI JAKARTA | 23 | CIP
0040714960041 | 1275361004 | 03CKR841 | CILANGKARA | CILANGKARA_SERANGBARU_CKR | NEW BUILD | STIP 1 | ISAT | TB | 048046/TBG-TB/ISAT/MKT/10/2021 | 2021-10-29 | -6.395015 | 107.148203 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 52 | PRECANCEL
0230615270231 | 1263821023 | ZBGR_4261 | BOGOR UTARA KOTA BOGOR | BOGOR UTARA KOTA BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | 028045/TBG-TB/SMART8/MKT/12/2020 | 2020-12-08 | -6.540304 | 106.814931 |  | JABODETABEK (OUTER) | KOTA BOGOR | JAWA BARAT | 42 | CIP
0230613630231 | 1263651023 | ZBGR_4588 | CIBUNGBULANG BOGOR | CIBUNGBULANG BOGOR | NEW BUILD | STIP 1 | SMART8 | TB | 027747/TBG-TB/SMART8/MKT/11/2020 | 2020-11-23 | -6.61969 | 106.65947 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | CIP
0230691590231 | 1322071023 | ZJKT_6991 | KOTA TANGERANG CIPONDOH | KOTA TANGERANG CIPONDOH | NEW BUILD | STIP 1 | SMART8 | TB | 041752/TBG-TB/SMART8/MKT/08/2021 | 2021-08-05 | -6.17658 | 106.6926 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 32 | CIP