## Sitelist
95
Site ID | Site Name | Batch# Year | Batch | SOW KKST | SOW ACTUAL | Regional | Residence | DRM Status | Current Progress Status | 14.10.2022 | PROBLEM ISSUE | Action Plan | Remarks Progress | RFC Date | RFI Date | KOM Date | DRM Date | Aging | Status RFI | Target RFC | Target RFI | Target RFI Month | Longitude Aktual | Latitude Aktual | Site ID TBG | Site Name TBG | LL Informasi | Jarak Combat (m) | Target Validasi | Target IW Clear | Target RFC | Target CME Start | Target Pouring | Target Erection | Target RFI
JTX629 | PULO ASEM MC-T-GF | 2020 | Batch #1 2020 - Colo | COLO | COLO | JABODETABEK | JAKARTA TIMUR | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-02-20 | 2020-03-13 | 2020-02-20 | 2020-02-20 |  | RFI DONE | EXISTING | DONE
TGR524 | JALAN HAJI UPNICICAYUR | 2020 | Batch #1 2020 - Colo | COLO | COLO | JABODETABEK | TANGERANG | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-02-20 | 2020-03-08 | 2020-02-20 | 2020-02-20 |  | RFI DONE | EXISTING | DONE
JUX584 | PERMANENRUKOPLUITDLM | 2020 | Batch #1 2020 - MCP | MCP | MCP | JABODETABEK | DKI JAKARTA | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-04-05 | 2020-04-29 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
JBX440 | PERMANENCMBTALMUBAROKJOGLO | 2020 | Batch #1 2020 - MCP | MCP | MCP | JABODETABEK | DKI JAKARTA | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-03-30 | 2020-05-12 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
KRW198 | BELENDUNGKLARI | 2020 | Batch #1 2020 - B2S | B2S | B2S | JABODETABEK | KARAWANG | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-04-15 | 2020-05-19 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
KRW224 | JLRAYACIKUNGKUNG | 2020 | Batch #1 2020 - B2S | B2S | B2S | JABODETABEK | KARAWANG | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-04-20 | 2020-05-21 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
SKB904 | DAYEUHLUHURWARUDOYONG | 2020 | Batch #1 2020 - B2S | B2S | B2S | JABODETABEK | KOTA SUKABUMI | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-04-27 | 2020-05-28 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
TGR523 | KADUSIRUNG | 2020 | Batch #1 2020 - B2S | B2S | B2S | JABODETABEK | KAB. TANGERANG | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-04-30 | 2020-05-31 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
TGR529 | GEMPOLSARISEPATANTIMURBANTEN | 2020 | Batch #1 2020 - B2S | B2S | B2S | JABODETABEK | KAB. TANGERANG | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-05-05 | 2020-05-31 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
SKB144 | PANENMAS | 2020 | Batch #1 2020 - B2S | B2S | B2S | JABODETABEK | KAB. SUKABUMI | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-04-27 | 2020-06-15 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
KRW238 | PERUMAHANRESINDA | 2020 | Batch #1 2020 - B2S | B2S | B2S | JABODETABEK | KARAWANG | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-06-12 | 2020-07-05 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
TNX314 | PAJAJARANTANGERANG | 2020 | Batch #1 2020 - B2S | B2S | B2S | JABODETABEK | KOTA TANGERANG | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-08-11 | 2020-08-15 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
CBN552 | PERMANENCOMBATPUSDIKRESKRIM | 2020 | Batch #1 2020 - B2S | B2S | B2S | JABODETABEK | KAB. BOGOR | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-07-29 | 2020-08-31 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
JUX570 | PERMANENCOMBATRUSUNMARUNDA | 2020 | Batch #1 2020 - MCP | MCP | MCP | JABODETABEK | DKI JAKARTA | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-08-25 | 2020-09-03 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
JUX569 | PERMANENCOMBATTERMPENUMPANG | 2020 | Batch #1 2020 - MCP | MCP | MCP | JABODETABEK | DKI JAKARTA | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-09-02 | 2020-09-24 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
JUX583 | PERMANENCOMBATKEPANDUANPELINDO | 2020 | Batch #1 2020 - MCP | MCP | MCP | JABODETABEK | DKI JAKARTA | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-09-02 | 2020-09-28 | 2020-03-02 | 2020-03-05 |  | RFI DONE | DONE | DONE
BKX395 | PEDURENANBEKASITIMUR | 2020 | Batch #1 2020 - Colo | COLO | COLO | JABODETABEK | KOTA BEKASI | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-08-07 | 2020-09-03 | 2020-08-07 | 2020-08-12 |  | RFI DONE | EXISTING | DONE
JKT100 | RELOCPTBDRENSAWIT | 2020 | Batch #2 2020 - Colo | COLO | COLO | JABODETABEK | DKI JAKARTA | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-10-20 | 2020-10-27 | 2020-10-20 | 2020-10-21 |  | RFI DONE | 2020-10-20 | DONE
SRG261 | SITUTERATECIKANDE | 2020 | Batch #2 2020 - B2S | B2S | B2S | JABODETABEK | SERANG | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-10-04 | 2020-10-23 | 2020-09-04 | 2020-10-14 |  | RFI DONE | DONE | DONE
JSX825 | JLKOSTRAD | 2020 | Batch #2 2020 - MCP | MCP | MCP | JABODETABEK | DKI JAKARTA | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-10-10 | 2020-10-27 | 2020-09-04 | 2020-09-28 |  | RFI DONE | DONE | DONE
JSX900 | KEBONBARUTEBET | 2020 | Batch #2 2020 - MCP | MCP | MCP | JABODETABEK | DKI JAKARTA | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-10-28 | 2020-10-30 | 2020-09-04 | 2020-10-14 |  | RFI DONE | DONE | DONE
JUX065 | WADUKPLUIT | 2020 | Batch #2 2020 - MCP | MCP | MCP | JABODETABEK | DKI JAKARTA | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-10-28 | 2020-11-02 | 2020-09-04 | 2020-10-14 |  | RFI DONE | DONE | DONE
SKB146 | AWILEGA | 2020 | Batch #2 2020 - B2S | B2S | B2S | JABODETABEK | SUKABUMI | GO CME | RFI DONE |  | NO ISSUE |  |  | 2020-11-20 |  | 2020-09-10 | 2020-09-21 |  | RFI DONE | DONE | DONE
KRW206 | GEMPOLBANYUSARI | 2021 | Batch #1 2021 - COLO | COLO | COLO | JABO OUTER | KARAWANG | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-01-02 | 2021-04-16 | 2021-04-14 | 2021-04-16 | DONE | RFI DONE | DONE | DONE | DONE
TGR241 | PAGEDANGANPAGEDANGAN | 2021 | Batch #1 2021 - COLO | COLO | COLO | JABO OUTER | TANGERANG | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-01-02 | 2021-04-16 | 2021-04-14 | 2021-04-16 | DONE | RFI DONE | DONE | DONE | DONE
JSX942 | MKAHFISRENGSENG | 2021 | Batch #1 2021 - COLO | COLO | COLO | JABO INNER | JAKARTA SELATAN | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-01-20 | 2021-04-16 | 2021-04-14 | 2021-04-16 | DONE | RFI DONE | DONE | DONE | DONE
BKX468 | RELOCGRAPARIBK | 2021 | Batch #1 2021 - COLO | COLO | COLO | JABO OUTER | BEKASI | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-02-10 | 2021-02-22 | 2021-02-04 |  | DONE | RFI DONE | DONE | DONE | DONE
JUX064 | JLBUDIMULYAUTARA | 2020 | Batch #2 2020 - MCP | MCP | MCP | JABODETABEK | DKI JAKARTA | GO CME | RFI DONE |  | NO ISSUE |  |  |  |  | 2020-09-04 | 2020-10-14 |  | RFI DONE | DONE | DONE
SKB204 | PASARCISAATSKB | 2021 | Batch #1 2021 - B2S (Part 01) | B2S | B2S | JABO OUTER | SUKABUMI | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-03-08 | 2021-04-11 | 2021-02-15 | 2021-03-01 | DONE | RFI DONE | DONE | DONE | DONE | 106.893 | -6.9002
SRG269 | PERMANENTCOMBATCIKANDEPERMAI | 2021 | Batch #1 2021 - B2S (Part 01) | B2S | B2S | JABO OUTER | SERANG | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-03-20 | 2021-04-12 | 2021-02-15 | 2021-03-01 | DONE | RFI DONE | DONE | DONE | DONE | 106.3452 | -6.2237
TNX324 | NEGLASARINEGLASARI | 2021 | Batch #1 2021 - B2S (Part 01) | B2S | B2S | JABO OUTER | TANGERANG KOTA | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-04-09 | 2021-04-29 | 2021-02-15 | 2021-03-01 | DONE | RFI DONE | DONE | DONE | DONE | 106.6322 | -6.1527
RKB069 | CURUGBADAKMAJA | 2021 | Batch #1 2021 - B2S (Part 01) | B2S | B2S | JABO OUTER | LEBAK | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-04-06 | 2021-05-11 | 2021-02-15 | 2021-03-01 | DONE | RFI DONE | DONE | DONE | DONE | 106.3798 | -6.3456
CBN436 | CURUGBITUNGNANGGUNG | 2021 | Batch #1 2021 - B2S (Part 01) | B2S | B2S | JABO OUTER | BOGOR | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-04-14 | 2021-05-11 | 2021-02-15 | 2021-03-01 | DONE | RFI DONE | DONE | DONE | DONE | 106.5426 | -6.6285
JBX306 | STAKALIDERES | 2021 | Batch #1 2021 - B2S (Part 03) | B2S | MINI MACRO | JABO INNER | KOTA JAKARTA BARAT | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-03-28 | 2021-04-10 | 2021-03-02 | 2021-03-10 | DONE | RFI DONE | DONE | DONE | DONE | 106.6997 | -6.1633
TGR236 | PERMANENTCMBTLIONAIR | CO 2021 | Batch #1 2021 - B2S (Part 02) | B2S | B2S | JABO OUTER | TANGERANG | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE | Penolakan warga cand P, Q, R (IW clear), S, T dan U. Kandidat V IW On Going, pengurusan akses developer done, Minus Ijin Warga ke Training Center Lion Air & konfirmasi jalur Helipad, delay karena PPKM sehingga susah koordinasi dengan pihak Kantor Lion Air | 2022-03-02 | 2022-03-31 | 2021-03-02 | 2021-03-10 | DONE | RFI DONE | DONE | DONE | DONE | 106.4951 | -6.1941 |  |  |  |  | DONE | 2021-11-19 | 2021-11-24 | 2021-11-26 | 0 | 0 | 0
TGR238 | BENCONGANKELAPADUA | 2021 | Batch #1 2021 - B2S (Part 01) | B2S | B2S | JABO OUTER | TANGERANG | RFI | RFI DONE | RFI DONE | LAHAN CORPORATE | RFI Done | NOM Berada di Kawasan Lippo Karawaci, terdapat pole existing PWU (Ex INUX). Permohonan kerjasama ke pihak PWU sudah dijukan | 2021-10-01 | 2021-09-11 | 2021-02-15 | 2021-03-01 | DONE | RFI DONE | 2021-08-10 | DONE | DONE
TNX323 | PASIRJAYAJATIUWUNG | CO 2021 | Batch #1 2021 - B2S (Part 01) | B2S | B2S | JABO OUTER | TANGERANG KOTA | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE | Pihak lahan lurah dan kecamatan, tidak mau mengeluarkan rekomendasi tanpa persetujuan 2 gudang kosong, IW OG (23kk, minus 2 gudang kosong), masih terkendala Pemilik Gudang yang masih dicarikan tempat tinggalnya dan PPKM dikarenakan pembatasan pergerakan warga. | 2022-02-18 | 2022-02-24 | 2021-02-15 | 2021-03-01 | DONE | RFI DONE | DONE | DONE | DONE | 106.5723 | -6.1941 |  |  |  |  | 2021-11-19 | 2021-11-22 | 2021-11-26 | 2021-12-01 | 0 | 0 | 0
JBX304 | MANYARKALIDERES | 2021 | Batch #1 2021 - B2S (Part 02) | B2S | B2S | JABO INNER | KOTA JAKARTA BARAT | RFI | RFI DONE | RFI DONE | NO ISSUE |  |  | 2021-06-11 | 2021-06-23 | 2021-03-02 | 2021-03-10 | DONE | RFI DONE | DONE | DONE | DONE | 106.7125 | -6.1216
JTX483 | PONDOKRANGGONCIPAYUNG | 2021 | Batch #1 2021 - B2S (Part 02) | B2S | B2S | JABO INNER | KOTA JAKARTA TIMUR | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-04-14 | 2021-04-26 | 2021-03-02 | 2021-03-10 | DONE | RFI DONE | DONE | DONE | DONE | 106.9071 | -6.3517
CPT249 | PARADISESERPONG2 | 2021 | Batch #1 2021 - B2S (Part 02) | B2S | B2S | JABO OUTER | KOTA TANGERANG SELATAN | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-04-29 | 2021-05-11 | 2021-03-02 | 2021-03-10 | DONE | RFI DONE | DONE | DONE | DONE | 106.7024 | -6.3541
SKB215 | SUKAJAYASALABINTANA | 2021 | Batch #1 2021 - B2S (Part 02) | B2S | B2S | JABO OUTER | SUKABUMI | RFI | RFI DONE | RFI DONE | NO ISSUE |  | RFI DONE | 2021-04-30 | 2021-06-22 | 2021-03-02 | 2021-03-10 | DONE | RFI DONE | Done | DONE | DONE | 106.9481 | -6.8958
TNX322 | BMTOPPO Ex PASARBARUKARAWACI | CO 2021 | Batch #1 2021 - B2S (Part 03) | B2S | B2S | JABO OUTER | TANGERANG KOTA | GO SITAC | CME - FOUNDATION | RFI | LAHAN CORPORATE | plan zoom dengan OPPO dan RTPE tertunda. Review peletakkan Pole 9m hasil survey dan simulasi dengan pihak OPPO 22/06 | CME stop by LL, issue pembahasan pasal PKS, Soil test done, Asplan drawing done. Adanya permintaan revisi poin2 dalam PKS | OG | OG | 2021-03-30 | 2021-04-09 | 555 | NOT YET RFI | 2022-02-28 | 2022-07-05 | Jul 22 | [6 empty] | DONE | 2021-11-17 | 2021-11-22 | 2021-11-26 | 2021-12-04 | 2021-12-08 | 2021-12-10
CKR338 | PERUMAHAN KSB | 2021 | Batch #1 2021 - B2S (Part 03) | B2S | B2S | JABO OUTER | BEKASI | RFI | RFI DONE | RFI DONE | CELL PLAN | Plan Erection done 14/10, Plan RFI 18/10 | Kepala desa sudah setuju untuk pemanfaatan lahan desa. Proses musyarawah antara BPD dan Kepala Desa terkait harga sewa lahan desa. | 2021-10-05 | 2021-10-17 | 2021-03-30 | 2021-04-09 | DONE | RFI DONE | DONE | DONE | DONE | 107.1143 | -6.4022
CKR330 | PERUMAHANCIBARUSAHJAYA | 2021 | Batch #1 2021 - B2S (Part 03) | B2S | B2S | JABO OUTER | BEKASI | RFI | RFI DONE | RFI DONE | REKOM ZONASI TOWER | RFI COMBAT DONE | Camat meminta REKOM Zonasi Tower released, sebelum start CME | 2021-07-30 | 2021-08-13 | 2021-03-30 | 2021-04-09 | DONE | RFI DONE | DONE | DONE | DONE | 107.0791 | -6.4315
JSX943 | CILANDAKBAWAH | 2021 | Batch #2 2021 - B2S | B2S | MINI MACRO | JABO INNER | JAKARTA SELATAN | RFI | RFI DONE | RFI DONE | NO ISSUE |  |  | 2021-07-05 | 2021-08-03 | 2021-05-06 | 2021-07-01 | DONE | RFI DONE | DONE | DONE | DONE | 106.8005 | -6.2869
JUX067 | ELANGLAUT | 2021 | Batch #2 2021 - B2S | B2S | MINI MACRO | JABO INNER | JAKARTA UTARA | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-10-22 | 2021-10-30 | 2021-05-06 | 2021-07-01 | DONE | RFI DONE | DONE | DONE | DONE | 106.7494 | -6.1278
PWK081 | CIRAMAHILIRMANIIS | 2021 | Batch #3 2021 - COLO | COLO | COLO | JABO OUTER | PURWAKARTA | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-05-27 | 2021-06-07 | 2021-05-20 | 44343 | DONE | RFI DONE | DONE | DONE | DONE
KRW250 | PANGKALAN_TAMANMEKAR | 2021 | Batch #3 2021 - COLO | COLO | COLO | JABO OUTER | KARAWANG | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-05-27 | 2021-06-06 | 2021-05-20 | 44343 | DONE | RFI DONE | DONE | DONE | DONE
KRW249 | CIPEUNDEUYKIARASARI2 | 2021 | Batch #3 2021 - COLO | COLO | COLO | JABO OUTER | KARAWANG | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-05-27 | 2021-06-10 | 2021-05-20 | 44343 | Done | RFI DONE | DONE | DONE | DONE
SKB158 | WARUNG KIARA_BOJONGKERTA | 2021 | Batch #3 2021 - COLO | COLO | COLO | JABO OUTER | SUKABUMI | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-05-27 | 2021-06-07 | 2021-05-20 | 44343 | DONE | RFI DONE | DONE | DONE | DONE
PLR004 | JAMPANGKULONBOJONGSARI | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | SUKABUMI | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-31 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | T002290 | BOJONGSARI
TGR549 | SUKAMULYABENDA | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | KAB. TANGERANG | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-31 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 1317431003 | JALAN RAYA KUKUN DAUN
SRG278 | BAROSCURUGAGUNG | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | SERANG | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-30 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 120836104 | CURUG AGUNG
CKR345 | HLOJICIBARUSAH | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | BEKASI | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-31 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 120308104 | CIJATI / TONGGOL
PLR010 | SALABINTANA2 | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | SUKABUMI | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-08-27 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 120657104 | SALABINTANA2
CBN503 | HAURKUNINGJONGGOL | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | KAB. BOGOR | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-29 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 1268202004 | IBS HAURKUNINGJGL
TGR548 | SUKAMANAHJAMBE | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | KAB. TANGERANG | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-31 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 131681103 | SUKAMANAH TABAN
CBN492 | CIBENING | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | KAB. BOGOR | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-31 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 125928123 | PAMIJAHAN BOGOR
TGR551 | TALOKKRESEK | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | KAB. TANGERANG | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-08-28 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 1321632001 | IBS TALOK KRESEK
PWK078 | MEKARGALIHJATILUHUR | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | PURWAKARTA | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-31 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 121217104 | BDGCKMPTOL1
CBN491 | CIBADUNGGUNUNGSINDUR | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | KAB. BOGOR | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-29 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 1268182003 | IBS BOG0109
CBN519 | RAYASINGASARIJONGGOL | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | KAB. BOGOR | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-31 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 125620110 | SINGASARI AZKA FARM
CBN526 | SUKAWANGISUKAMAKMUR | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | KAB. BOGOR | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-29 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 1265772003 | IBS REP. JONGGOL
PLR003 | GEGERBITUNGKARANGJAYA | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | SUKABUMI | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-07-29 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 120769104 | CIJUREY
PLR007 | NAGRAKCIHANYAWAR | 2021 | Batch #4 2021 - COLO | COLO | COLO | JABO OUTER | SUKABUMI | GO CME | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | RFI DONE | 2021-07-19 | 2021-08-27 | 2021-07-17 | 2021-07-19 | DONE | RFI DONE | DONE | DONE | DONE |  |  | 121410104 | CIHANJAWAR
BOX048 | MEKARWANGITANAHSEREAL | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | KOTA BOGOR | GO CME | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2021-10-01 | 2021-11-22 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 106.7873 | -6.5474
CBN471 | PARUNG PANJANGJAGABITA | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | BOGOR | RFI | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2021-09-13 | 2021-10-12 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 106.5173 | -6.3295
CBN521 | RUMPINTAMANSARI | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | BOGOR | RFI | RFI DONE | RFI DONE | FINISH | RFI DONE | RFC done 10/09 | 2021-09-10 | 2021-09-19 | 2021-08-23 | 2021-09-09 | 27 | RFI DONE | DONE | DONE | DONE | 106.6163 | -6.4042 | 1273701001 | RUMPINTAMANSARI
KRW252 | KARAWANG BARATMEKARJATI | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | KARAWANG | GO CME | RFI DONE | RFI DONE | NO ISSUE | Plan Erection done 26/10, PLN done connect |  | 2021-10-05 | 2021-10-27 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 107.2984 | -6.2446 |  | KARAWANG BARATMEKARJATI
KRW256 | KLARI | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | KARAWANG | RFI | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2021-09-30 | 2021-10-04 | 2021-08-23 | 2021-09-09 | 42 | RFI DONE | DONE | DONE | DONE | 107.3575 | -6.3484 | 1273301001 | KLARI_
KRW262 | CILAMAYA KULONPASIRJAYA | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | KARAWANG | GO CME | RFI DONE | RFI DONE | PLN OVERBLAST | Plan PLN Connect 26/10 | 05.10.2021 Erection OG, Plan finish 09/10, ME done 12/10, PLN connect 15/10 | 2021-09-23 | 2021-10-26 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 107.5274 | -6.1933 |  | CILAMAYA KULONPASIRJAYA
KRW263 | Cikarang Cilamaya Wetan | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | KARAWANG | GO CME | RFI DONE | RFI DONE | NO ISSUE | Plan Erection done 26/10, PLN done connect 26/10 |  | 2021-10-05 | 2021-10-26 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 107.5468 | -6.2701 |  | Cikarang Cilamaya Wetan
PDG123 | DESAPANGGUKINGAN | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | PANDEGLANG | RFI | RFI DONE | RFI DONE | FINISH | RFI DONE | RFC Done 06/09 | 2021-09-06 | 2021-09-26 | 2021-08-23 | 2021-09-09 | 34 | RFI DONE | DONE | DONE | DONE | 106.1682 | -6.278 | 1322441001 | DESAPANGGUKINGAN
RKB078 | JALUPANGMULYA | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | LEBAK | RFI | RFI DONE | RFI DONE | FINISH | RFI DONE | RFC Done 06/09 | 2021-09-06 | 2021-09-30 | 2021-08-23 | 2021-09-09 | 38 | RFI DONE | DONE | DONE | DONE | 106.2257 | -6.5275 | 1322341001 | JALUPANGMULYA
SRG284 | KAREOJAWILAN | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | SERANG | RFI | RFI DONE | RFI DONE | FINISH | RFI DONE | Plan erection done 21/10, RFI 23/10 | 2021-09-24 | 2021-10-25 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 106.3471 | -6.25
TGR542 | RANCAGEDEGUNUNGKALER | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | TANGERANG | RFI | RFI DONE | RFI DONE | FINISH | RFI DONE | Plan RFI released 19/10 | 2021-09-07 | 2021-10-19 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 106.3871 | -6.0893
TGR543 | RAYAKRONJOMEKARBARU | CO 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | TANGERANG | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE | 03.11.2021 OG pengecoran Borepile | 2021-11-10 | 2022-01-19 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 106.4012 | -6.0472
PWK083 | SMKN3SUKATANIPWK | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | PURWAKARTA | RFI | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2021-09-08 | 2021-09-30 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 107.3917 | -6.6092
PWK085 | SMKN1DARANGDANPURWAKARTA | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | PURWAKARTA | RFI | RFI DONE | RFI DONE | FINISH | RFI DONE | Plan erection done 23/10, RFI done 25/10 | 2021-09-27 | 2021-10-25 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 107.4973 | -6.7312
CLG115 | BENDUNGANCILEGON | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | KOTA CILEGON | GO SITAC | RFI DONE | RFI | NO ISSUE | Plan erection Finish 28/12, Plan Pondasi Done 29/12, PLN 29/12 |  | 2021-12-02 | 2021-12-31 | 2021-08-23 |  | 409 | RFI DONE | DONE | DONE | DONE | 106.0513 | -6.0365 |  |  |  |  | DONE | DONE | 2021-11-19 | 2021-11-23 | 0 | 0 | 0
SKB155 | TANJUNGJAMPANGKULON | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | SUKABUMI | GO CME | RFI DONE | RFI DONE | FINISH | RFI DONE | 03.11.2021 Plan start CME 06/11 | 2021-11-04 | 2021-11-29 | 2021-08-23 |  | 409 | RFI DONE | DONE | DONE | DONE | 106.6245 | -7.2471
TGR433 | RAJEG_TANJAKAN MEKAR | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | TANGERANG | GO CME | RFI DONE | RFI DONE | NO ISSUE | Plan erection done, 29/10, ME done 30/10, RFI 31/10 |  | 2021-09-01 | 2021-10-31 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 106.5318 | -6.101 |  | RAJEG_TANJAKAN MEKAR
TGR546 | SOLEARTANGERANG | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | TANGERANG | GO CME | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2021-09-05 | 2021-11-15 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 106.4025 | -6.2899
CBN472 | KOPIDAONG | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | BOGOR | DRM CHANGE SITE | DROP | DROP | CHANGE CLUSTER | Proposed Change Site dengan DMT |  | DROP | DROP | 2021-08-23 | DROP | DROP | DROP | DROP | DROP | DONE
CBN483 | CARINGINBOCIMI | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | BOGOR | GO SITAC | DROP | DROP | CHANGE CLUSTER | Proposed Change Site dengan DMT |  | DROP | DROP | 2021-08-23 | DROP | DROP | DROP | DROP | DROP | DONE | 106.827 | -6.6886
JTX539 | PERMANENASRAMAHAJI | CO 2021 | Batch #3 2021 - B2S | B2S | MINI MACRO | JABO INNER | JAKARTA TIMUR | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2021-12-15 | 2022-01-13 | 2021-09-14 | 2021-09-16 | DONE | RFI DONE | DONE | DONE | DONE | 106.8849 | -6.2845 |  |  |  |  | DONE | 2021-11-19 | 2021-11-26 | 2021-11-29 | 2021-11-25 | 2021-11-29 | 2021-11-10
CBN500 | CIPEUCANG | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | BOGOR | GO CME | RFI DONE | RFI DONE | NO ISSUE | Plan Erection done 27/10, PLN done connect |  | 2021-09-05 | 2021-10-28 | 2021-08-23 | 2021-09-07 | DONE | RFI DONE | DONE | DONE | DONE | 107.0515 | -6.4121 |  | CIPEUCANG
CBN620 | PERMANENBOJONGKONENGKM0 | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | BOGOR | DRM PROSES | RFI DONE | RFI | FINISH |  | Titik NOM tanah sengketa, lahan combat tidak boleh dipermanenkan karena permintaan pemilik lahan |  | 2021-12-21 | 2021-09-14 | 2021-09-16 | 387 | RFI DONE | 2021-12-10 | DONE | DONE
CKR346 | KARANGSETIAKARANGBAHAGIA | CO 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | BEKASI | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-02-02 | 2022-03-14 | 2021-08-23 | 2021-09-16 | DONE | RFI DONE | DONE | DONE | DONE | 107.1821 | -6.2176 |  |  |  |  | 2021-11-17 | 2021-11-19 | 2021-11-24 | 2021-11-26 | 0 | 0 | 2021-12-15
CKR349 | KARANGANYARKARANGBAHAGIA | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | BEKASI | GO SITAC | RFI DONE | RFI | FINISH |  | Need Konfirmasi akses melalui kompleks perumahan |  | 2021-12-27 | 2021-08-23 |  | 409 | RFI DONE | 2021-12-10 | DONE | DONE | 107.1842 | -6.2019 |  |  |  |  | DONE | 2021-11-16 | 2021-11-22 | 2021-11-26 | 0 | 0 | 2021-12-21
CKR360 | TELAGAMURNICIKARANGBARAT | CO 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | BEKASI | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2021-11-28 | 2022-03-30 | 2021-08-23 | 2021-09-16 | DONE | RFI DONE | DONE | DONE | DONE | 107.1259 | -6.2482 |  |  |  |  | DONE | DONE | 2021-11-17 | 2021-11-19 | 0 | 0 | 2021-12-08
CKR376 ex CKR361 | GREENPERMATA2 Ex WALUYACIKARANGUTARA | CO 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | BEKASI | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-04-04 | 2022-04-14 | 2021-08-23 |  | DONE | RFI DONE | DONE | DONE | DONE | 107.0878 | -6.2166 |  |  |  |  | DONE | 2021-11-19 | 2021-11-26 | 2021-11-29 | 0 | 0 | 2021-12-15
PLR012 | SUDAJAYAGIRANGSKB | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | SUKABUMI | GO CME | RFI DONE | RFI DONE | FINISH | RFI DONE | 10.11.2021 Lantai Kerja 05.11.2021 Start Galian pondasi | 2021-09-05 | 2021-11-29 | 2021-08-23 | 2021-09-07 | 43 | RFI DONE | DONE | DONE | DONE | 106.9496 | -6.8862
BOX045 | BUKITCIMANGGUCITY | CO 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | KOTA BOGOR | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2021-12-02 | 2022-01-01 | 2021-08-23 |  | DONE | RFI DONE | DONE | DONE | DONE | 106.7898 | -6.5353 |  |  |  |  | DONE | DONE | 2021-11-17 | 2021-11-19 | 2021-11-27 | 2021-12-01 | 2021-12-10
CKR363 | PERMANENRAYAPEBANYURANN | 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | BEKASI | GO SITAC | RFI DONE | RFI | ZONASI CELLPLAN | Plan erection Finish 28/12, Plan Pondasi Done 29/12, PLN 29/12 |  | 2021-12-02 | 2021-12-31 | 2021-09-14 | 2021-09-16 | 387 | RFI DONE | 2021-11-10 | DONE | DONE | 107.2652 | -6.2305 |  |  | Tidak sama dengan COMBAT | 62m | DONE | DONE | 2021-11-19 | 2021-11-22 | 2021-12-04 | 2021-12-08 | 2021-12-10
CBN623 | PERMANENCOMBATTIRTAWARNARUMPIN | CO 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | BOGOR | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE | 03.11.2021 Re soil test | 2022-12-30 | 2022-01-25 | 2021-09-14 | 2021-09-16 | DONE | RFI DONE | DONE | DONE | DONE | 106.6368 | -6.3779 |  |  |  |  | 2021-11-17 | 2021-11-19 | 2021-11-24 | 2021-11-26 | 2021-12-04 | 2021-12-08 | 2021-12-10
JTX541 | PERMANENCOMBATPTPUTIK | 2021 | Batch #4 2021 - B2S | B2S | MINI MACRO | JABO INNER | JAKARTA TIMUR | GO CME | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2021-10-25 | 2021-11-22 | 2021-09-14 | 2021-09-16 | DONE | RFI DONE | DONE | DONE | DONE | 106.9252 | 6.1893
TGR553 | PERMANENDRIYACATANIA | 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | TANGERANG | GO CME | RFI DONE | RFI DONE | FINISH | RFI DONE | 03.11.2021 RFC done | 2021-11-02 | 2021-11-30 | 2021-09-14 | 2021-09-16 | 387 | RFI DONE | DONE | DONE | DONE | 106.5319 | -6.2763
CKR366 | PERMANENPERUMPERMATAINDAH | CO 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | BEKASI | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2021-12-27 | 2022-01-19 | 2021-09-14 | 2021-09-16 | DONE | RFI DONE | DONE | DONE | DONE | 107.2427 | -6.2515
CKR367 | PERMANENPTIDEMITSU | 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | BEKASI | GO SITAC | RFI DONE | RFI | FINISH |  |  |  | 2021-12-27 | 2021-09-14 | 2021-09-16 | 387 | RFI DONE | 2021-11-20 | DONE | DONE | 107.2125 | -6.3998 |  |  | Sama dengan COMBAT | 10m | 2021-11-17: DONE; 2021-11-19: DONE; 2021-11-24: 2021-11-21; 2021-11-26: 2021-11-23
BKX430 | VILLAGADINGHARAPAN Ex PERMANENCOMBATPERUMPTMBEKASI | CO 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | KOTA BEKASI | GO SITAC | RFI DONE | RFI | KAWASAN PERUMAHAN | Proses Land Preparation untuk Guyed Mast. |  | OG | OG | 2021-09-14 | 2021-09-16 | 387 | NOT YET RFI | 2022-02-11 | 2022-07-05 | Jul 22 | 107.2427 | -6.2515 |  | Need combat
BOX049 | PERMANENCOMBATRAYASEMPLAK | CO 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | KOTA BOGOR | GO SITAC | RFI DONE | RFI | KKOP | issue penolakan warga, Plan penyelesaian 21/06 sekaligus realisasi warga setelah geser. |  | OG | OG | 2021-09-14 | 2021-09-16 | 387 | NOT YET RFI | 2022-02-21 | 2022-07-08 | Jul 22 | 106.7643 | -6.5598 |  |  |  |  | 2021-11-17 | 2021-11-19 | 2021-11-24 | 2021-11-26 | 0 | 0 | 0
CKR364 | PERMANENKAREDOKCIBARUSAH | 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | BEKASI | GO SITAC | RFI DONE | RFI | ZONASI CELLPLAN | Erection finish 28/12, PLN done connect |  | 2021-11-28 | 2021-12-30 | 2021-09-14 | 2021-09-16 | 387 | RFI DONE | 2021-11-20 | DONE | DONE | 107.0838 | -6.4051 |  |  | Sama dengan COMBAT | 11m | DONE | 2021-11-16 | 2021-11-23 | 2021-11-25 | 0 | 0 | 2021-12-15
CKR368 | PERMANENPERUMSERANGSELALU | 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | BEKASI | GO CME | RFI DONE | RFI DONE | FINISH | RFI DONE | 10.11. Lean concrete 03.11.2021 Re deisgn pondasi done, Galian pondasi OG 26.10.2021 Plan Galian done 01/11, Pondasi cor 05/11, Erection start 10/11 finish 17/11, ME done 18/11, PLN 19/11, RFI 20/11 | 2021-10-22 | 2021-11-30 | 2021-09-14 | 2021-09-16 | 387 | RFI DONE | DONE | DONE | DONE | 107.1504 | -6.3926
BKX431 | PERMANENCOMBATJAKAPERMAI | CO 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | KOTA BEKASI | GO SITAC | RFI DONE | RFI DONE | KAWASAN PERUMAHAN | RFI DONE |  | OG | OG | 2021-09-14 | 2021-09-16 | 387 | NOT YET RFI | 2022-02-11 | DONE | DONE
TGR555 | PERMANENDANGDANGCISAUK2 | 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | TANGERANG | GO CME | RFI DONE | RFI DONE | FINISH | RFI DONE | 03.11.2021 erection OG | 2021-10-15 | 2021-11-17 | 2021-09-14 | 2021-09-16 | DONE | RFI DONE | DONE | DONE | DONE | 106.6205 | -6.3567
CBN618 | PERMANENKERTAJAYARUMPIN | CO 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | BOGOR | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2021-11-20 | 2022-04-11 | 2021-09-14 | 2021-09-16 | DONE | RFI DONE | DONE | DONE | DONE | 106.612 | -6.3859 |  |  | Berbeda dengan COMBAT | 88m | DONE | DONE | 2021-11-17 | 2021-11-22 | 0 | 0 | 2021-12-10
CBN614 | PERMANENLEBAKWANGI2 | CO 2021 | Batch #4 2021 - B2S | B2S | B2S | JABO OUTER | BOGOR | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-01-24 | 2022-02-21 | 2021-09-14 | 2021-09-16 | DONE | RFI DONE | DONE | DONE | DONE | 106.5455 | -6.4288 |  |  |  |  | 2021-11-17 | 2021-11-19 | 2021-11-26 | 2021-11-29 | 0 | 0 | 2021-12-15
CBN480 | BANTARSARIRANCABUNGUR | 2021 | Batch #3 2021 - B2S | B2S | B2S | JABO OUTER | BOGOR | GO SITAC | RFI DONE | RFI | FINISH |  |  |  | 2021-12-23 | 2021-08-23 |  | 409 | RFI DONE | 2021-11-10 | DONE | DONE | 106.7433 | -6.5291 |  |  |  |  | DONE | DONE | 2021-11-24 | 2021-11-26 | 2021-12-04 | 2021-12-08 | 2021-12-10
CBN523 | SMAN 1CIBUNGBULANG BOGOR | 2021 | Batch #3 2021 - B2S | B2S | COLO | JABO OUTER | BOGOR | GO CME | RFI DONE | RFI DONE | NO ISSUE | Plan PLN connect 26/10 |  | 2021-10-11 | 2021-10-27 | 2021-10-08 | 2021-10-11 | DONE | RFI DONE | DONE | DONE | DONE | 106.6629 | -6.5861 |  | CIBUNGBULANG BOGOR 2
JTX643 | AGUNGSEDAYUJAKUT | CO 2021 | Bacth #5 2021 - B2S | B2S | B2S | JABO INNER | JAKARTA UTARA | GO SITAC | DROP | DROP | LAHAN CORPORATE | DROP |  | OG | OG |  |  | 2022-10-06 | NOT YET RFI | 2022-02-11 | RISK | RISK
CPT250 | PERMANENCOMBATLIVINGWORLD | CO 2021 | Bacth #5 2021 - B2S | B2S | B2S | JABO OUTER | KOTA TANGERANG SELATAN | GO SITAC | SITAC - BAN/BAK | CME - FOUNDATION | ISSUE CELLPLAN, KAWASAN DEVELOPER | Proses pengurusan SIK dengan Estate |  | OG | OG |  |  | 2022-10-06 | NOT YET RFI | 2022-02-21 | 2022-07-24 | Jul 22 | 106.6525 | -6.2421
JBX453 ex JBX310 | ADHIKARYAKEDOYA ex KINTAMANITIMUR | CO 2021 | Bacth #5 2021 - B2S | B2S | B2S | JABO INNER | JAKARTA BARAT | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-03-20 | 2022-04-13 |  |  | DONE | RFI DONE | DONE | DONE | DONE | 106.7584 | -6.1779
SRG996 | CIKANDECIKANDE2 | 2022_Percepatan | Batch 1 2022 - B2S (Percepatan) | B2S | B2S | JABO OUTER | SERANG | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-02-20 | 2022-03-25 |  |  | DONE | RFI DONE | DONE | DONE | DONE | 106.3586 | -6.2204
SRG997 | PENGAMPELANWALANTAKA | 2022_Percepatan | Batch 1 2022 - B2S (Percepatan) | B2S | B2S | JABO OUTER | KOTA SERANG | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-02-28 | 2022-03-21 |  |  | DONE | RFI DONE | DONE | DONE | DONE | 106.2332 | -6.1495
SRG998 | CISARNOLDIT | 2022_Percepatan | Batch 1 2022 - B2S (Percepatan) | B2S | B2S | JABO OUTER | SERANG | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-02-20 | 2022-03-21 |  |  | DONE | RFI DONE | DONE | DONE | DONE | 106.2562 | -6.1562
TGR561 | CURUG KULONCURUG | 2022_Percepatan | Batch 1 2022 - B2S (Percepatan) | B2S | B2S | JABO OUTER | TANGERANG | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-03-04 | 2022-03-21 |  |  | DONE | RFI DONE | DONE | DONE | DONE | 106.5528 | -6.2581
CBN632 | GUNUNGMULYATENJOBOGOR | 2022_Percepatan | Batch 1 2022 - B2S (Percepatan) | B2S | B2S | JABO OUTER | BOGOR | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-02-20 | 2022-03-15 |  |  | DONE | RFI DONE | DONE | DONE | DONE | 106.7065 | -6.6322
CBN633 | CIMANGGU1CIBUNGBULANG | 2022_Percepatan | Batch 1 2022 - B2S (Percepatan) | B2S | B2S | JABO OUTER | BOGOR | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-02-27 | 2022-03-15 |  |  | DONE | RFI DONE | DONE | DONE | DONE | 106.6666 | -6.5625
KRW923 | PALAWAD | 2022_Percepatan | Batch 1 2022 - B2S (Percepatan) | B2S | B2S | JABO OUTER | KARAWANG | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-02-15 | 2022-03-01 |  |  | DONE | RFI DONE | DONE | DONE | DONE | 107.3482 | -6.2813
JUX594 | KAMALMUARAPENJARINGAN Ex ALAMINKRAMATJATI | 2022 | Batch 1 2022 - Mini Macro | MCP |  | JABO INNER | JAKARTA TIMUR | GO SITAC | RFI DONE | RFI | COMMCASE | Galian Pondasi OG. Plan Cor pondasi 24/06, Plan erection 27/06 Finish 28/06, RFI 29/06 |  | 2022-03-11 |  |  |  | 2022-10-06 | NOT YET RFI | 2022-03-28 | 2022-07-01 | Jul 22 | 106.8715 | -6.2719
JTX647 | RAYAJENGKI | 2022 | Batch 1 2022 - Mini Macro | Mini Macro | MCP | JABO INNER | JAKARTA TIMUR | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-03-08 | 2022-03-31 |  |  | 2022-10-06 | RFI DONE | 2022-03-29 | DONE | DONE | 106.8783 | -6.2612
JPX281 | CEMPAKAWANGI | 2022 | Batch 1 2022 - Mini Macro | Mini Macro |  | JABO INNER | JAKARTA PUSAT | GO SITAC | RFI DONE | RFI |  | Plan Galian Done 24/06, Cor Pondasi 26/06, Erection start 29/06, RFI 30/06 | [5 empty] | 2022-10-06 | NOT YET RFI | 2022-03-30 | 2022-07-01 | Jul 22 | 106.8552 | -6.167
JSX717 | PEPAYAJAGAKARSA Ex PETOGOGANGANDARIA | 2022 | Batch 1 2022 - Mini Macro | Mini Macro |  | JABO INNER | JAKARTA SELATAN | GO SITAC | RFI DONE | RFI | Limit Akses, Penolakan Warga | Plan realisasi dan rekom lurah camat start 24/06 | [5 empty] | 2022-10-06 | NOT YET RFI | 2022-03-31 | 2022-07-01 | Jul 22 | 106.8203 | -6.3234
JUX587 | PERJUANGANRAYA | 2022 | Batch 1 2022 - Mini Macro | Mini Macro |  | JABO INNER | JAKARTA UTARA | GO SITAC | RFI DONE | RFI DONE | FINISH | Plan Erection 28/04 Finish 29/04, RFI 30/04 | [5 empty] | 2022-10-06 | RFI DONE | 2022-04-01 | DONE | DONE | 106.9055 | -6.1362
JBX443 | KOSAMBIRANDU | 2022 | Batch 1 2022 - Mini Macro | Mini Macro |  | JABO INNER | JAKARTA BARAT | GO SITAC | RFI DONE | RFI |  |  |  |  | 2022-06-18 |  |  | 2022-10-06 | RFI DONE | 2022-04-02 | DONE | DONE | 106.7183 | -6.1818
JTX649 | BALAIRAKYAT | 2022 | Batch 1 2022 - Mini Macro | Mini Macro | MCP | JABO INNER | JAKARTA TIMUR | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI Done |  | 2022-03-08 | 2022-03-30 |  |  | 2022-10-06 | RFI DONE | 2022-04-03 | DONE | DONE | 106.9011 | -6.2252
JBX446 | SLTPN | 2022 | Batch 1 2022 - Mini Macro | Mini Macro |  | JABO INNER | JAKARTA BARAT | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-03-12 |  |  |  | 2022-10-06 | RFI DONE | 2022-04-04 | DONE | DONE | 106.6909 | -6.152
JBX447 | BOJONGINDAHRWBUAYA | 2022 | Batch 1 2022 - Mini Macro | Mini Macro |  | JABO INNER | JAKARTA BARAT | GO SITAC | RFI DONE | RFI |  |  |  |  | 2022-06-19 |  |  | 2022-10-06 | NOT YET RFI | 2022-04-05 | DONE | DONE | 106.7451 | -6.1598
BOO843 | PROFM | 2022 | Batch 1 2022 - B2S | B2S | B2S | JABO OUTER | KOTA BOGOR | GO SITAC | RFI DONE | RFI | NO ISSUE | Proses follow up nilai komersil dari pihak Hotel Swiss-Bell terkait kerjasama rooftop | [5 empty] | 2022-10-06 | NOT YET RFI | 2022-04-06 | 2022-07-04 | Jul 22 | 106.8143 | -6.6103
JTX646 | AGUNGSEDAYUCAKUNG | 2022 | Batch 1 2022 - B2S | B2S |  | JABO INNER | JAKARTA TIMUR | GO SITAC | DROP | DROP | Wajib MCP DKI, Kawasan Developer | DROP | [5 empty] | 2022-10-06 | NOT YET RFI | 2022-04-07 | RISK | RISK
JSZ047 | BRIGIFCIPEDAK | 2022 | Batch 1 2022 - B2S | B2S |  | JABO INNER | JAKARTA SELATAN | GO SITAC | RFI DONE | RFI DONE | FINISH | Plan Pengecoran pondasi 30/04 | [5 empty] | 2022-10-06 | RFI DONE | 2022-04-08 | DONE | DONE | 106.7993 | -6.3449
BKX896 | PONDOKMELATI BEKASI | 2022 | Batch 1 2022 - B2S | B2S | B2S | JABO OUTER | KOTA BEKASI | GO SITAC | RFI DONE | RFI | NO ISSUE | Issue warga yang terprovokasi dan ada masalah dengan LL. Plan hari solving problem ke ke warga yang terprovokator | [5 empty] | 2022-10-06 | NOT YET RFI | 2022-04-09 | 2022-07-09 | Jul 22 | 106.9386 | -6.3322
CBN631 | PERUMAHAN CITEUREP | 2022 | Batch 1 2022 - B2S | B2S | B2S | JABO OUTER | BOGOR | GO SITAC | RFI DONE | RFI DONE | FINISH |  |  | 2022-03-30 | 2022-04-25 |  |  | 44840 | RFI DONE | 2022-04-10 | DONE | DONE | 106.9033 | -6.5022
TGR558 | LAVON | 2022 | Batch 1 2022 - B2S | B2S | B2S | JABO OUTER | TANGERANG | GO SITAC | RFI DONE | RFI DONE | PROSES REKOM | RFI DONE | [5 empty] | 2022-10-06 | NOT YET RFI | 2022-04-11 | DONE | DONE | 106.5079 | -6.1962
TGR562 | PURIPERMAI3RAKSA | 2022 | Batch 1 2022 - B2S | B2S | B2S | JABO OUTER | TANGERANG | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI Done |  | 2022-03-10 | 2022-03-30 |  |  | 2022-10-06 | RFI DONE | 2022-04-12 | DONE | DONE | 106.4661 | -6.2472
JUX075 | SWASEMBADABARATJAKUT | CO 2021 | Batch 1 2022 - COLO | COLO | COLO | JABO INNER | JAKARTA UTARA | GO SITAC | RFI DONE | RFI DONE | FINISH | RFI Done |  | 2022-03-20 | 2022-04-01 |  |  |  | RFI DONE |  | DONE | DONE
BOX050 | RELOCPANGKALANRAYA3PTEL | 2022 | Batch 1 2022 - Mini Macro (Recovery) | Mini Macro |  | JABO OUTER | KOTA BOGOR | OG DRM | RFI DONE | RFI |  | Validasi kandidat T. Lahan Yayasan. Propose MCP 25m | [8 empty] | 2022-08-02 | Aug 22 | 106.807 | -6.5621
JSX711 | RELOCKEMANG | 2022 | Batch 1 2022 - Mini Macro (Recovery) | Mini Macro | MCP | JABO INNER | JAKARTA SELATAN | OG DRM | RFI DONE | RFI |  | IW Clear, menunggu disposisi PT POS Indonesia. Sirkuler di PT. POS Indonesia | [8 empty] | 2022-08-03 | Aug 22
JSX712 | RELOCBALAIKARTINI | 2022 | Batch 1 2022 - Mini Macro (Recovery) | Mini Macro | MCP | JABO INNER | JAKARTA SELATAN | OG DRM | CME - EXCAVATION | CME - ERECTION |  | Issue galian bersilang dengan kabel PLN. Diskusi terkait geser titik | [8 empty] | 2022-08-20 | Aug 22
JTX650 | RELOCCIPINANGTIMUR | 2022 | Batch 1 2022 - Mini Macro (Recovery) | Mini Macro | MCP | JABO INNER | JAKARTA TIMUR | OG DRM | RFI DONE | RFI |  | IW OG, proses IW sisa 2 KK. Target penyelesaian IW hari ini | [8 empty] | 2022-07-19 | Jul 22
TNX330 | RELOKJLNPEMBANGUNAN6 | 2022 | Batch 1 2022 - Mini Macro (Recovery) | Mini Macro |  | JABO OUTER | KOTA TANGERANG | OG DRM | RFI DONE | RFI |  | Proses finalisasi tanda tangan warga. Plan realisasi dan rekom start 24/06 | [8 empty] | 2022-07-21 | Jul 22
PPR010 | RELOCPLTONGKENG | 2022 | Batch 1 2022 - B2S (Recovery) | B2S | B2S | JABO INNER | KEPULAUAN SERIBU | GO SITAC | CME - ME ON GOING | RFI | [10 empty] | 2022-08-03 | Aug 22
Formulas:
Aging = TODAY()-[KOM Date]

## Reloct & Permanenisasi Site
Site ID | Site Name | Batch# Year | Batch | SOW | Regional | Residence | DRM Status | Current Progress Status | 26.04.2022 | PROBLEM ISSUE | ACTION PLAN | RFC Date | RFI Date | KOM Date | DRM Date | Aging | Target RFC | Target RFI
JSX177 | RELOCMNGUNSARKORO | 2021 | TSEL 2021 - RELOCATION SITE COLO | COLO | JABO INNER | JAKARTA SELATAN | Done | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | 2021-10-31 | 2021-12-21 | 2021-10-26 | 2021-10-26 | DONE | DONE | DONE
TNX325 | RELOCTAMANIMAMBONJOLSTP | 2021 | TSEL 2021 - RELOCATION SITE COLO | COLO | JABO OUTER | KOTA TANGERANG | Done | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | DONE | 2021-07-27 | 2021-05-06 | 2021-05-17 | DONE | DONE | DONE
BKX460 | RELOCOJEKJTBENING | 2021 | TSEL 2021 - RELOCATION SITE COLO | COLO MINI MACRO | JABO INNER | BEKASI | Done | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | DONE | 2021-06-07 | 2021-05-06 | 2021-05-17 | DONE | DONE | DONE
CBN470 | RELOCNATRARAYA | 2021 | TSEL 2021 - RELOCATION SITE COLO | COLO | JABO INNER | KAB. BOGOR | Done | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | DONE | 2021-08-02 | 2021-07-15 | 2021-07-16 | DONE | DONE | DONE
CKR365 | PERMANENLINTASSETU | 2021 | TSEL 2021 - PERMANENISASI SITE | COLO | JABO OUTER | KAB. BEKASI | Done | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | 2021-07-23 | 2021-08-06 | 2021-07-22 | 2021-07-23 | DONE | DONE | DONE
CBN624 | PERMANENJLTAPOSCITAPEN | 2021 | TSEL 2021 - PERMANENISASI SITE | COLO | JABO INNER | KAB. BOGOR | Done | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | 2021-07-23 | 2021-08-07 | 2021-07-22 | 2021-07-23 | DONE | DONE | DONE
JBX307 | RELOCDURIUTARA2 | 2021 | TSEL 2021 - RELOCATION SITE COLO | COLO | JABO INNER | JAKARTA BARAT | Done | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | 2021-09-15 | 2021-09-29 | 2021-09-10 | 2021-09-15 | DONE | DONE | DONE
JSX710 | RELOCRAGUNANRAYA | 2021 | TSEL 2021 - RELOCATION SITE COLO | COLO | JABO INNER | JAKARTA SELATAN | Done | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | 2021-10-31 | 2022-11-24 | 2021-10-26 | 2021-10-26 | DONE | DONE | DONE
TGR556 | RAWABURUNG | 2021 | TSEL 2021 - Add Colo | COLO | JABO OUTER | TANGERANG | Done | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | 2021-11-01 | 2021-11-22 | 2021-11-01 | 2021-11-05 | DONE | DONE | DONE
SRG295 | RELOCCIPARERANJANGJAYA | 2022 | TSEL 2022 - RELOCATION SITE COLO | COLO | JABO OUTER | SERANG | OG | RFI DONE | RFI DONE | NO ISSUE | RFI DONE | 2022-01-10 | 2022-01-18 | 2022-01-07 | 2022-01-10 | DONE | DONE | DONE
JPX248 | RELOCBURJALMAS | 2022 | TSEL 2022 - RELOCATION SITE COLO | COLO | JABO INNER | JAKARTA PUSAT | Done | ERECTION POLE | RFI DONE | OG Galian new Foundation | Plan Erection Done 24/06, RFI 25/06 | 2022-04-15 | OG | 2022-03-23 | 2022-03-24 | 197 | DONE | 2022-04-26
JUX075 | SWASEMBADABARATJAKUT | 2022 | TSEL 2022 - RELOCATION SITE COLO | COLO | JABO INNER | JAKARTA UTARA | Done | SITAC - CP Process |  | Issue Warga. Ada Provokator. Proses Pengawalan untuk mulai CME
Formulas:
Aging = TODAY()-[KOM Date]

## Ghost Protocol
Site ID | Site Name | Batch# Year | SOW | Regional | Residence | DRM Status | Current Progress Status | PROBLEM ISSUE | ACTION PLAN
JBX305 | RELOCSTADISKOTIK | 2021 | GP | JABO INNER | JAKARTA BARAT |  | CME PREPARATION | LAHAN CORPORATE
JSX966 | RELOCMENTENGATASL | 2021 | GP | JABO INNER | JAKARTA SELATAN |  | REHUNTING | PENOLAKAN WARGA | Rehunting titik, NOK RTPE. Last Cand C Near Existing TSEL 250m. Lahan yang sama dengan TSEL sudah dalam proses akad penjualan. Ada issue dengan warga sebelumnya
| RELOCPANGKALANRAYA3PTEL | 2021 | GP | JABO OUTER | KOTA BOGOR |  | Rehunting | PENOLAKAN WARGA | kandidat done Approve RTPE. Musyawarah warga TBD mengingat adanya musibah puting beliung. Dikejar jadwal soswar akhir minggu ini, tgl 05/02
| RELOC SUKARAJANAGRAK-PTI | 2021 | GP | JABO OUTER | BOGOR |  | Validasi | No Issue | Ijin Warga Kondusif, Kandidat Approval RTPE
PPR010 | RELOCPULAUTONGKENG | 2021 | GP | JABO INNER | KEPULAUAN SERIBU |  | BAN/BAK | LAHAN CORPORATE | Propose 2 titik kandidat, menolak untuk disewa, LL akan menjual lahan tersebut. Propose kandidat lahan fasum milik Pemkab Kep. Seribu (P. Bintang)
RELOCBURJALMAS
JBX450 | RELOCBANDENGANSLT | 2022 | GP | JABO INNER | JAKARTA UTARA |  | REHUNTING | LIMITED SPACE

## PKP
Site ID | Site Name | Batch# Year | Batch | SOW | Regional | Residence | DRM Status | Current Progress Status | 12.04.2022 | PROBLEM ISSUE | ACTION PLAN | RFC Date | RFI Date | KOM Date | DRM Date | Aging | Target RFC | Target RFI
JBX309 | GAGASEMANAN | 2021 | TSEL 2021 - PKP | COLO | JABO - INNER |  | Done | RFI DONE | RFI | NO ISSUE |  | DONE |  | 2021-07-17 | 2021-07-19 | DONE |  | DONE
JTX537 | RAYAPONCOL | 2021 | TSEL 2021 - PKP | COLO | JABO - INNER | JAKARTA UTARA | Done | RFI DONE | RFI | NO ISSUE |  | DONE | 2021-11-22 | 2021-07-17 | 2021-07-19 | DONE | DONE | DONE
CLG116 | JOMBANGMASIGIT | 2021 | TSEL 2021 - PKP | COLO | JABO - OUTER | SERANG | Done | RFI DONE | RFI | NO ISSUE |  | DONE |  | 2021-07-17 | 2021-07-19 | DONE | DONE | DONE
JBX313 | RELOCKOSAMBIBARU | 2021 | TSEL 2021 - PKP | COLO | JABO - INNER | JAKARTA UTARA | Done | RFI DONE | RFI | NO ISSUE |  |  |  | 2021-11-01 |  | DONE |  | DONE
JUX075 | SWASEMBADABARATJAKUT | 2021 | TSEL 2021 - PKP | COLO | JABO - INNER | JAKARTA UTARA | Done | DROP | CHANGE TO COLO | AMANDEMEN PKS | Change KKST, Released new KKST ke TBG, Follow up penambahan radius IW & amandemen PKS |  |  | 2021-07-17 | 2021-07-19 | 446 | 2022-03-12 | 2022-03-27
JSZ048 | RAGUNAN PASAR MINGGU | 2022 | TSEL 2022 - PKP | COLO | JABO - INNER | JAKARTA SELATAN | Done | RFI DONE | RFI DONE | FINISH | RFI DONE |  | 2022-04-14 |  |  | 44840 | DONE | DONE
JUX071 | PULAUREKLAMASI1 | 2021 | TSEL 2021 - PKP | COLO | JABO - INNER | JAKARTA UTARA | Done | DROP | DISMANTLE | LAHAN KAWASAN | Follow up ijin kerja released dari pihak Kawasan | DONE |  | 2021-07-28 | 2021-07-28 | 435 | DONE | TBD
Formulas:
Aging = TODAY()-[KOM Date]

## Summary
[11 empty] | Batch# Year | CO 2021 |  |  |  | Batch# Year | 2022
SOW ACTUAL | (All) | [9 empty] | Target RFI Month | (Multiple Items) |  |  |  | Batch | (Multiple Items)
Count of Site Name |  |  |  | Count of Site Name |  |  | Target RFI Month
Batch# Year | Regional | Status RFI | Total | Regional | Batch# Year | Current Progress Status | DONE | Jul 22 | Aug 22 | Grand Total | Regional | Current Progress Status | Site ID | Site Name | Target RFI | Regional | Site ID | Site Name | Current Progress Status | Target RFI | Action Plan
CO 2021 | JABO INNER | RFI DONE | 3 | JABO INNER | CO 2021 | RFI DONE | 3 |  |  | 3 | JABO OUTER | SITAC - IW CLEAR | TNX322 | BMTOPPO Ex PASARBARUKARAWACI | 2022-07-05 | JABO INNER | JPX281 | CEMPAKAWANGI | CME - GALIAN | 2022-07-01
|  | NOT YET RFI | 1 |  | CO 2021 Total |  | 3 |  |  | 3 |  | SITAC - BAN/BAK | CPT250 | PERMANENCOMBATLIVINGWORLD | 2022-07-24 |  | JSX711 | RELOCKEMANG | SITAC - IW CLEAR | 2022-08-03
| JABO OUTER | RFI DONE | 11 |  | 2022 | RFI DONE | 7 |  |  | 7 |  | CME - GALIAN | BOX049 | PERMANENCOMBATRAYASEMPLAK | 2022-07-08 |  | JSX712 | RELOCBALAIKARTINI | SITAC - REHUNTING | 2022-08-20
|  | NOT YET RFI | 5 |  |  | CME - GALIAN |  | 2 |  | 2 |  |  | BKX430 | VILLAGADINGHARAPAN Ex PERMANENCOMBATPERUMPTMBEKASI | 2022-07-05 |  | JTX650 | RELOCCIPINANGTIMUR | SITAC - IW CLEAR | 2022-07-19
CO 2021 Total |  |  | 20 |  |  | SITAC - IW CLEAR |  | 2 | 1 | 3 | JABO OUTER Total | [5 empty] | PPR010 | RELOCPLTONGKENG | SITAC - IW OG | 2022-08-03
2022_Percepatan | JABO OUTER | RFI DONE | 7 |  |  | SITAC - IW OG |  |  | 1 | 1 | Grand Total | [5 empty] | JUX594 | KAMALMUARAPENJARINGAN Ex ALAMINKRAMATJATI | CME - GALIAN | 2022-07-01
2022_Percepatan Total |  |  | 7 |  |  | SITAC - REHUNTING |  |  | 1 | 1 | [6 empty] | JSX717 | PEPAYAJAGAKARSA Ex PETOGOGANGANDARIA | SITAC - IW CLEAR | 2022-07-01
2022 | JABO INNER | RFI DONE | 5 |  | 2022 Total |  | 7 | 4 | 3 | 14 | [5 empty] | JABO INNER Total
|  | NOT YET RFI | 6 | JABO INNER Total |  |  | 10 | 4 | 3 | 17 | [5 empty] | JABO OUTER | BKX896 | PONDOKMELATI BEKASI | CME - BOWPLANK | 2022-07-09
| JABO OUTER | RFI DONE | 2 | JABO OUTER | CO 2021 | RFI DONE | 12 |  |  | 12 | [6 empty] | BOO843 | PROFM | SITAC - BAN/BAK | 2022-07-04
|  | NOT YET RFI | 3 |  |  | CME - GALIAN |  | 2 |  | 2 | [6 empty] | BOX050 | RELOCPANGKALANRAYA3PTEL | SITAC - IW OG | 2022-08-02
2022 Total |  |  | 16 |  |  | SITAC - IW CLEAR |  | 1 |  | 1 | [6 empty] | TNX330 | RELOKJLNPEMBANGUNAN6 | SITAC - IW CLEAR | 2022-07-21
Grand Total |  |  | 43 |  |  | SITAC - BAN/BAK |  | 1 |  | 1 | [5 empty] | JABO OUTER Total
[5 empty] | CO 2021 Total |  | 12 | 4 |  | 16 | [5 empty] | Grand Total
[5 empty] | 2022 | RFI DONE | 3 |  |  | 3
[6 empty] | CME - BOWPLANK |  | 1 |  | 1
[6 empty] | SITAC - IW CLEAR |  | 1 |  | 1
[6 empty] | SITAC - IW OG |  |  | 1 | 1
[6 empty] | SITAC - BAN/BAK |  | 1 |  | 1
[5 empty] | 2022 Total |  | 3 | 3 | 1 | 7
[5 empty] | 2022_Percepatan | RFI DONE | 7 |  |  | 7
[5 empty] | 2022_Percepatan Total |  | 7 |  |  | 7
|  |  |  | JABO OUTER Total |  |  | 22 | 7 | 1 | 30
|  |  |  | Grand Total |  |  | 32 | 11 | 4 | 47