## Sheet1
sonumb | site_id | site_id_opr | SiteName | sitename_opr | Site_Type | operator_id | COMPANY_ID | Mitra | No_FPKI_STIP | Tgl_FPKI_STIP | latitude | longitude | Address | regional_name | kabupaten_name | province_name | Height | Tahapan_Project | Status | Status_Dtl | SubmitDate | Cancel_Date | LeadPMSitac | PMSitac | SitacSPV | lead_pm | Project_Manager | WaspangName | Account_Manager | Supplier_Sitac | Supplier_CME | ssr_date | rfc_date | RFI_date | rfi_opr_date | BAPS_DATE | bak_date | iw_date | recom_date | IMB Date | soilhammer_date | pln_date | uf_date | ageing | rfi_projection | rfc_projection | bauk_projection | bauk_done | bauk_date | BAPS_NO | batch_field | PODateVendorSitac | PONumberVendorCME | PODateVendorCME | ProjectName | RentalHolidayPeriod | pono_tower | podate_tower | poinput_tower | sld_forecast | start_date_baps | end_date_baps | app_date | bouwplank_date | bouwplank_done | tower_foundation_date | tower_foundation_done | ATPDoneDate | BASTDate | TowerType | TowerHeight | FieldType | User_Number | RFL_Forecast | IMB_Forecast | SSTA_Forecast | PLNPermanen_Forecast | RFL STATUS | RFLDate | SSTA NUMBER | SSTA REMARKS | SSTA DATE | RECTIFICATION DATE | Tower Temporary ID | RFI Date Tower Temporary | IDPLN | Pln_On_Date | Power Source | BatchName | ShelterType | rfi_certificat_date | CLUSTER | RTCDesc | SSTASTatus | RFOADate | ATPOperatorDate | IntegrationDate | SoWCustomer | statusBaukActivity | POSoilDate | VendorPOSoil | FoundationDesignLayoutDate | AsPlannedDrawingDate | PKSNotarialDoneDate | RFIType | Date_ApprovalRFIARO | MaterialOnSiteDone | OTDR Done Date | ODP MMP Date | Pole FO Installation Date | SiteSurvey | RFITargetDate | LEN_Order | LEN_Implement | VendorMaintenance | ApprLeadAMDate
0030787730031 | 1139651003 | JAW-JK-TJP-0701 | PULAU REMPANG RELOCATION | PULAU REMPANG RELOCATION | NEW MCP NON FO | XL | TB | KLS | 060935/TBG-TB/XL/MKT/08/2022 | 44788 | -6.160838 | 106.887508 |  | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 25 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA |  |  | IHSAN PANDU WIJAYA |  |  | RYA YUDI ASTUTI | [14 empty] | 79 | 44897 | 44877 | [26 empty] | 1 | 44877 |  | 44933 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44905 |  |  |  | 44788.6379
0030787740031 | 1139661003 | JAW-JK-TJP-0684 | PLUIT MUTIARA RELOCATION | PLUIT MUTIARA RELOCATION | NEW MCP NON FO | XL | TB | KLS | 060936/TBG-TB/XL/MKT/08/2022 | 44788 | -6.099258 | 106.792938 |  | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 25 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA |  |  | IHSAN PANDU WIJAYA |  |  | RYA YUDI ASTUTI | [14 empty] | 79 | 44897 | 44877 | [26 empty] | 1 | 44877 |  | 44933 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44905 |  |  |  | 44788.6384
0030794620031 | 1324471003 | JAW-BT-TGR-0098 | JANTUNGGEUN_TANGERANG | JANTUNGGEUN_TANGERANG | NEW BUILD | XL | TB |  | 061903/TBG-TB/XL/MKT/09/2022 | 44817 | -6.345528 | 106.492389 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 50 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | RYA YUDI ASTUTI | [14 empty] | 50 | 44911 | 44892 | [26 empty] | 1 | 44892 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8658
0010802290011 | 1282181001 | CBN647 | CILAMEPABAMBONG | CILAMEPABAMBONG | NEW BUILD | TSEL | TB | BNP | 062996/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.629930 | 106.587170 | Kp. Cilamen II RT 002 RW 007 Desa Pabangbon Kecamatan Leuwiliang Kabupaten Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 62 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI |  |  | 44859.6801 |  |  |  |  | 44859.9313 | 44860.931 | 44864.9627 |  | 44863.8314 |  |  | 29 | 44901 | 44933 | [16 empty] | 44848 | 44861 | [8 empty] | 1 | 44933 | 45033.4492 | 44809 |  | RFL | 44865 |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Sub Urban |  | - |  |  |  | B2S | BAUK Operator Input | 44864.8167 | PT. TELECONSULT NUSANTARA | 44855 | 44855 | [7 empty] | 1280341001 - CILAMEPABAMBONG / 0010790620011 | 44781 |  |  |  | 44848.5168
0010802530011 | 1282301001 | PLR036 | CIRACAPUJUNGGENTENG | CIRACAPUJUNGGENTENG | NEW BUILD | TSEL | TB | DATATEL | 063020/TBG-TB/TSEL/MKT/10/2022 | 44838 | -7.330899 | 106.433851 | Kp. Kebon Waru RT 05 RW 03 Desa Gunung Batu Kecamatan Ciracap Kabupaten Sukabumi Provinsi Jawa Barat | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62.00 | CIP | SITAC | BAK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI |  |  | 44864.2864 | [11 empty] | 29 | 44901 | 44924 | [16 empty] | 44839 | [9 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Rural |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280401001 - CIRACAPUJUNGGENTENG / 0010790710011 | 44781 |  |  |  | 44839.5137
0010802600011 | 1282351001 | PLR026 | GIRIJAYADAMARRAJA | GIRIJAYADAMARRAJA | NEW BUILD | TSEL | TB | DATATEL | 063027/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.953539 | 106.723429 |  | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44924 | [26 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280291001 - GIRIJAYADAMARRAJA / 0010790570011 | 44781 |  |  |  | 44839.5134
0010802610011 | 1282361001 | PLR028 | SMAN1LENGKONGSUKABUMI | SMAN1LENGKONGSUKABUMI | NEW BUILD | TSEL | TB | ORLIE | 063028/TBG-TB/TSEL/MKT/10/2022 | 44838 | -7.133390 | 106.707470 | Kp. Ciganggem RT 008 RW 005 Desa Tegallega Kec Lengkong Kab. Sukabumi Prov. Jawa Barat | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI |  |  | 44858.6058 | 44863.7422 |  |  |  | 44858.679 | 44860.582 | 44862.5274 |  | 44861.5252 |  |  | 29 | 44901 | 44924 | [16 empty] | 44839 | 44893 | [8 empty] | 1 | 44924 | 45033.4523 | 44809 |  | RFL | 44865 |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Rural |  | - |  |  |  | B2S | BAUK Operator Input | 44864.7994 | PT. TELECONSULT NUSANTARA | 44845 | 44854 | [7 empty] | 1280271001 - SMAN1LENGKONGSUKABUMI / 0010790550011 | 44781 |  |  |  | 44839.5133
0030733540031 | 1276281003 | JAW-JB-BGR-0234 | BANTARJATI RELOCATION | BANTARJATI RELOCATION | NEW BUILD | XL | TB | TURANGGA | 051946/TBG-TB/XL/MKT/02/2022 | 44599 | -6.579992 | 106.818439 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA | MUHAMAD RINALDI ADITYA | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | SHERLY MAULANA | [14 empty] | 268 | 44893 | 44874 | [26 empty] | 1 | 44874 |  | 44827 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44749 |  |  |  | 44600.1959
0030778050031 | 1324211003 | JAW-BT-TNG-1513 | SASMITA PABUARAN | SASMITA PABUARAN | NEW MCP NON FO | XL | TB | MAJA | 059892/TBG-TB/XL/MKT/07/2022 | 44771 | -6.176328 | 106.621586 |  | JABODETABEK (INNER) | KOTA TANGERANG | BANTEN | 30 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI | [14 empty] | 96 | 44912 | 44893 | [26 empty] | 1 | 44893 |  | 44919 |  |  |  |  | - | [5 empty] | 1 |  |  | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44891 |  |  |  | 44771.7667
0010802490011 | 1282261001 | PLR015 | BUNIWANGIGEGERBITUNG | BUNIWANGIGEGERBITUNG | NEW BUILD | TSEL | TB | BNP | 063016/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.95657 | 107.01478 | Kp Tanjungsirna RT.25B RW 007, Desa Caringin, Kec. Gegerbitung, Kab.Sukabumi | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI |  |  | 44855.6904 | 44861.3734 |  |  |  | 44855.7822 | 44855.8598 | 44858.4392 | 44851 | 44858.8246 |  |  | 29 | 44901 | 44924 | [16 empty] | 44839 | 44851 | [8 empty] | 1 | 44924 | 45033.4478 | 44809 |  | RFL | 44865 |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Sub Urban |  | - |  |  |  | B2S | BAUK Operator Input | 44864.5987 | PT. TELECONSULT NUSANTARA | 44855 | 44854 | [7 empty] | 1280411001 - BUNIWANGIGEGERBITUNG / 0010790720011 | 44781 |  |  |  | 44839.514
0010789580011 | 1139871001 | JBX450 | RELOCBANDENGANSLT | RELOCBANDENGANSLT | NEW BUILD | TSEL | PKP | KLS | 061304/TBG-PKP/TSEL/MKT/09/2022 | 44809 | -6.13677 | 106.8004 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 25 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA |  |  | IHSAN PANDU WIJAYA |  |  | DEWI NOVIANI SETIYAZI | [14 empty] | 58 | 44905 | 44895 | [26 empty] | 1 | 44895 |  | 44957 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - PKP | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44929 |  |  |  | 44810.2985
0030786900031 | 1139621003 | JAW-JK-KYB-0238 | SEKOLAH KENCANA RELOCATION | SEKOLAH KENCANA RELOCATION | NEW MCP NON FO | XL | TB | KLS | 060852/TBG-TB/XL/MKT/08/2022 | 44785 | -6.277825 | 106.78795 |  | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 25 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA |  |  | IHSAN PANDU WIJAYA |  |  | RYA YUDI ASTUTI | [14 empty] | 82 | 44897 | 44877 | [26 empty] | 1 | 44877 |  | 44933 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44905 |  |  |  | 44785.593
0030787650031 | 1279841003 | JAW-JB-BKS-0687 | KEMANG PRATAMA 2 RELOCATION | KEMANG PRATAMA 2 RELOCATION | NEW BUILD | XL | TB | ROTUA | 060927/TBG-TB/XL/MKT/08/2022 | 44785 | -6.265069 | 106.994691 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 25 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA |  |  | IHSAN PANDU WIJAYA |  |  | RYA YUDI ASTUTI | [14 empty] | 82 | 44897 | 44877 | [26 empty] | 1 | 44877 |  | 44933 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44905 |  |  |  | 44785.758
0030794560031 | 1280601003 | JAW-JB-CKR-0129 | MUTIARAGADING_BEKASI | MUTIARAGADING_BEKASI | NEW BUILD | XL | TB | AULIA | 061897/TBG-TB/XL/MKT/09/2022 | 44817 | -6.147672 | 106.990519 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 40 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI | [14 empty] | 50 | 44898 | 44888 | [26 empty] | 1 | 44888 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8661
0030794580031 | 1324461003 | JAW-BT-PDG-0616 | SURAKARTA_PAGELARAN | SURAKARTA_PAGELARAN | NEW BUILD | XL | TB | TRITAMA | 061899/TBG-TB/XL/MKT/09/2022 | 44817 | -6.420139 | 105.879194 | Jl.Desa Surakarta, Kp.Walang, RT.004/RW.001 Desa Surakarta, Kec.Pagelaran Kabupaten Pandeglang, Provinsi Banten | JABODETABEK (OUTER) | PANDEGLANG | BANTEN | 72 | CIP | CME | TOWER FOUNDATION |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | RYA YUDI ASTUTI |  |  | 44840.4858 | 44852.7523 |  |  |  | 44841.6077 | 44845.7172 | 44847.6341 |  | 44846.7295 |  |  | 50 | 45057 | 44861 | [16 empty] | 44817 | 44846 | 44857.7465 | 44852 | 44858.8214 | [5 empty] | 1 | 44861 | 45033.4526 | 44965 |  | RFL | 44865 |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  | Sub Urban |  | - |  |  |  | B2S | BAUK Operator Input | 44848.5899 | PT. TELECONSULT NUSANTARA | 44845 | 44844 | [8 empty] | 44937 |  |  |  | 44817.8659
0010802340011 | 1324801001 | RKB092 | CIAKARGUNUNGKENCANA | CIAKARGUNUNGKENCANA | NEW BUILD | TSEL | TB | BKM | 063001/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.605692 | 106.085614 | Dusun Lebak Pasir RT 01/01 Desa Ciakar Kec. Gunung Kencana Kab. Lebak Banten | JABODETABEK (OUTER) | LEBAK | BANTEN | 62.00 | CIP | SITAC | BAK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | DEWI NOVIANI SETIYAZI |  |  | 44864.8029 | [11 empty] | 29 | 44901 | 44933 | [16 empty] | 44848 | [9 empty] | 1 | 44933 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Sub Urban |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1324261001 - CIAKARGUNUNGKENCANA / 0010790660011 | 44781 |  |  |  | 44848.5164
0010802550011 | 1324831001 | TGR574 | SINDANGSONO | SINDANGSONO | NEW BUILD | TSEL | TB | MAJA | 063022/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.177271 | 106.487814 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 52 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44924 | [26 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1324311001 - SINDANGSONO / 0010790780011 | 44781 |  |  |  | 44839.5131
0030001160031 | 1200721003 | JAW-JB-CKR-0350 | JLN CITANDUY RAYA BEKASI | JLN CITANDUY RAYA BEKASI | NEW BUILD | XL | PKP | No Mitra | 01294/TBG-PKP/XL/MKT/10/2022 | 44852 | -6.277989 | 107.184331 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA |  |  | IHSAN PANDU WIJAYA |  |  | RYA YUDI ASTUTI | [14 empty] | 15 | 45092 | 44938 | [26 empty] | 1 | 44938 |  | 45000 |  |  |  |  | - | [5 empty] | 1 |  | - | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44972 |  |  |  | 44853.415
0010802360011 | 1282221001 | CKR388 | VILLA SETU WANGI | VILLA SETU WANGI | NEW BUILD | TSEL | TB | AULIA | 063003/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.344466 | 107.046427 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44933 | [26 empty] | 1 | 44933 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280311001 - VILLA SETU WANGI / 0010790590011 | 44781 |  |  |  | 44848.5166
0010802380011 | 1324811001 | TGR579 | TANAHMERAHSEPATANTIMUR | TANAHMERAHSEPATANTIMUR | NEW BUILD | TSEL | TB | MAJA | 063005/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.111573 | 106.594207 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 42 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44933 | [26 empty] | 1 | 44933 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1324301001 - TANAHMERAHSEPATANTIMUR / 0010790770011 | 44781 |  |  |  | 44848.5162
0010802500011 | 1282271001 | PLR038 | PUNCAKBULUH | PUNCAKBULUH | NEW BUILD | TSEL | TB | TRITAMA | 063017/TBG-TB/TSEL/MKT/10/2022 | 44838 | -7.225366 | 106.644602 |  | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44924 | [26 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280421001 - PUNCAKBULUH / 0010790730011 | 44781 |  |  |  | 44839.5139
0010802540011 | 1324821001 | TGR571 | RANCAKALAPAPANONGAN | RANCAKALAPAPANONGAN | NEW BUILD | TSEL | TB | MAJA | 063021/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.290018 | 106.514425 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 52 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44924 | [26 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1324291001 - RANCAKALAPAPANONGAN / 0010790760011 | 44781 |  |  |  | 44839.5132
0010802560011 | 1282311001 | PLR029 | TBG LENGKONG | TBG LENGKONG | NEW BUILD | TSEL | TB | TRITAMA | 063023/TBG-TB/TSEL/MKT/10/2022 | 44838 | -7.1168 | 106.685971 |  | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44924 | [26 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280431001 - TBG LENGKONG / 0010790740011 | 44781 |  |  |  | 44839.5137
0010802590011 | 1282341001 | CKR383 | HARVESTCITYCLUSTERBARAT | HARVESTCITYCLUSTERBARAT | NEW BUILD | TSEL | TB | AULIA | 063026/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.38008 | 107.02081 | Kp. Sadang RT 02 RW 02 Desa Cikarageman, Kec. Setu, Kabupaten Bekasi Jawa Barat | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42.00 | CIP | SITAC | REKOM |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI |  |  | 44862.486 |  |  |  |  | 44865.4319 | 44866.4367 | [5 empty] | 29 | 44901 | 44924 | [16 empty] | 44839 | [9 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Urban |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280301001 - HARVESTCITYCLUSTERBARAT / 0010790580011 | 44781 |  |  |  | 44839.5134
0010754600011 | 1138421001 | JSX712 | RELOCBALAIKARTINI | RELOCBALAIKARTINI | NEW MCP NON FO | TSEL | TB | DROP | 056821/TBG-TB/TSEL/MKT/05/2022 | 44701 | -6.23562 | 106.82489 | Jl. Gatot Subroto Kuningan Barat, Kec. Mampang Prapatan, Kota Jakarta Selatan, Daerah Khusus Ibukota Jakarta | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 20 | CIP | SITAC | BAK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | DEWI NOVIANI SETIYAZI |  |  | 44831.5317 | [11 empty] | 166 | 44862 | 44873 | [16 empty] | 44701 | [9 empty] | 1 | 44873 |  | 44918 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - RELOCATION SITE | OUTDOOR |  | Urban |  | - |  |  |  | Minimacro | BAUK Operator Input | [12 empty] | 44785 |  |  |  | 44704.4664
0010802270011 | 1324781001 | RKB084 | SUKAMANAHRANGKASBITUNG | SUKAMANAHRANGKASBITUNG | NEW BUILD | TSEL | TB | KLS | 062994/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.323157 | 106.278095 | Lingkungan Kali Cikambuy Blok 6 Rt.1 Rw.3 Desa Sukamanah Kec. Rangkasbitung, Lebak | JABODETABEK (OUTER) | LEBAK | BANTEN | 62.00 | CIP | SITAC | IW |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | DEWI NOVIANI SETIYAZI |  |  | 44866.5797 |  |  |  |  | 44866.6656 | [6 empty] | 29 | 44901 | 44933 | [16 empty] | 44848 | [9 empty] | 1 | 44933 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Urban |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1324271001 - SUKAMANAHRANGKASBITUNG / 0010790670011 | 44781 |  |  |  | 44848.5165
0010802370011 | 1282231001 | CBN646 | SMAN1TENJOBOGOR | SMAN1TENJOBOGOR | NEW BUILD | TSEL | TB | BNP | 063004/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.348 | 106.4638 | Kp. Dukuhmalang RT 003 RW 01 Desa Cilaku Kecamatan Tenjo Kabupaten Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 62.00 | CIP | SITAC | BAK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI |  |  | 44863.8271 | [11 empty] | 29 | 44901 | 44933 | [16 empty] | 44848 | [9 empty] | 1 | 44933 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Sub Urban |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280351001 - SMAN1TENJOBOGOR / 0010790630011 | 44781 |  |  |  | 44848.5165
0030001170031 | 1200731003 | JAW-JB-BKS-0166 | PONDOK_GEDE_PERMAI | PONDOK_GEDE_PERMAI | NEW BUILD | XL | PKP | CMI | 01295/TBG-PKP/XL/MKT/10/2022 | 44852 | -6.301331 | 106.970511 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 42 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA |  |  | IHSAN PANDU WIJAYA |  |  | RYA YUDI ASTUTI | [14 empty] | 15 | 45092 | 44938 | [26 empty] | 1 | 44938 |  | 45000 |  |  |  |  | - | [5 empty] | 1 |  | - | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44972 |  |  |  | 44853.4147
0010802300011 | 1282191001 | PLR047 | PERMANENBUKITALGORITMA | PERMANENBUKITALGORITMA | NEW BUILD | TSEL | TB | TRITAMA | 062997/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.90761 | 106.70352 |  | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44933 | [26 empty] | 1 | 44933 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280391001 - PERMANENBUKITALGORITMA / 0010790700011 | 44781 |  |  |  | 44848.5168
0010802350011 | 1282211001 | PLR049 | PARUNGCIAMBAR | PARUNGCIAMBAR | NEW BUILD | TSEL | TB | ORLI | 063002/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.863020 | 106.754570 | Jl. Palasari km 2 RT. 03 RW. 01 Desa Palasari Hilir Kec. Parungkuda Kab. Sukabumi Jawa Barat | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI |  |  | 44858.6072 | 44863.7426 |  |  |  | 44858.6625 | 44860.5824 | 44861.7191 |  | 44862.327 |  |  | 29 | 44901 | 44933 | [16 empty] | 44848 | 44862 | [8 empty] | 1 | 44933 | 45033.4505 | 44809 |  | RFL | 44865 |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Rural |  | - |  |  |  | B2S | BAUK Operator Input | 44864.807 | PT. TELECONSULT NUSANTARA | 44844 | 44854 | [7 empty] | 1280281001 - PARUNGCIAMBAR / 0010790560011 | 44781 |  |  |  | 44848.5167
0010802520011 | 1282291001 | CBN656 | JALANRAYAJONGGOLCARIU | JALANRAYAJONGGOLCARIU | NEW BUILD | TSEL | TB | BNP | 063019/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.478524 | 107.072423 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 52 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44924 | [26 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280331001 - JALANRAYAJONGGOLCARIU / 0010790610011 | 44781 |  |  |  | 44839.5138
0010802570011 | 1282321001 | SKB914 | JMBATANMERAHSKB | JMBATANMERAHSKB | NEW BUILD | TSEL | TB | TRITAMA (Not Confirm) | 063024/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.957412 | 106.934337 |  | JABODETABEK (OUTER) | KOTA SUKABUMI | JAWA BARAT | 42 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44924 | [26 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280361001 - JMBATANMERAHSKB / 0010790640011 | 44781 |  |  |  | 44839.5135
0010802280011 | 1282171001 | PLR023 | GUNUNGWALATHEGARMANAH | GUNUNGWALATHEGARMANAH | NEW BUILD | TSEL | TB | DATATEL | 062995/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.934621 | 106.801691 | Kp. Manggis RT 03 RW 01 Desa Cimanggis Kecamatan Cicantayan Kabupaten Sukabumi Provinsi Jawa Barat | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62.00 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI |  |  | 44864.2922 |  |  |  |  | 44865.6016 | 44866.3992 | 44866.2349 |  | 44866.62 |  |  | 29 | 44901 | 44933 | [16 empty] | 44848 | [9 empty] | 1 | 44933 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Rural |  | - |  |  |  | B2S | BAUK Operator Input |  |  | 44865 | 44865 | [7 empty] | 1280381001 - GUNUNGWALATHEGARMANAH / 0010790690011 | 44781 |  |  |  | 44848.5169
0010802310011 | 1282201001 | PLR016 | TBG TANJUNGSARI | TBG TANJUNGSARI | NEW BUILD | TSEL | TB | BNP | 062998/TBG-TB/TSEL/MKT/10/2022 | 44838 | -7.219356 | 106.96934 | Kp. Mekarwangi RT 001 RW 005 Desa Tanjungsari Kecamatan Curugkembar Kabupaten Sukabumi | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI |  |  | 44863.1037 | 44864.8224 |  |  |  | 44863.469 | 44863.8075 | 44863.8123 | 44858 | 44863.8313 |  |  | 29 | 44901 | 44933 | [16 empty] | 44848 | 44862 | [8 empty] | 1 | 44933 | 45033.4398 | 44809 |  | RFL | 44865 |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Sub Urban |  | - |  |  |  | B2S | BAUK Operator Input |  |  | 44855 | 44855 | [7 empty] | 1280261001 - TBG TANJUNGSARI / 0010790540011 | 44781 |  |  |  | 44848.5167
0010802330011 | 1324791001 | RKB086 | JATIMULYARANGKASBITUNG | JATIMULYARANGKASBITUNG | NEW BUILD | TSEL | TB | BKM | 063000/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.354123 | 106.268866 |  | JABODETABEK (OUTER) | LEBAK | BANTEN | 42 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44933 | [26 empty] | 1 | 44933 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1324281001 - JATIMULYARANGKASBITUNG / 0010790680011 | 44781 |  |  |  | 44848.5164
0010802470011 | 1282241001 | PLR025 | GIRIJAYA | GIRIJAYA | NEW BUILD | TSEL | TB | TRITAMA | 063014/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.932495 | 106.73177 | Kp.Ciherang RT.001 RW.008 Desa Girijaya Kecamatan Warungkiara Kabupaten Sukabumi Provinsi Jawa Barat | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI |  |  | 44862.4002 |  |  |  |  | 44862.6278 | 44864.8126 | 44866.5864 |  | 44866.6198 |  |  | 29 | 44901 | 44924 | [16 empty] | 44839 | [9 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  | Sub Urban |  | - |  |  |  | B2S | BAUK Operator Input |  |  | 44866 | 44862 | [7 empty] | 1280441001 - GIRIJAYA / 0010790750011 | 44781 |  |  |  | 44839.5143
0010802510011 | 1282281001 | SKB913 | PERMANENSINDANGSARILEMBURSITU | PERMANENSINDANGSARILEMBURSITU | NEW BUILD | TSEL | TB | BNP | 063018/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.96145 | 106.914209 |  | JABODETABEK (OUTER) | KOTA SUKABUMI | JAWA BARAT | 42 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44924 | [26 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280371001 - PERMANENSINDANGSARILEMBURSITU / 0010790650011 | 44781 |  |  |  | 44839.5138
0030001150031 | 1200711003 | JAW-JB-CKR-0299 | PURI CIKARANG HIJAU | PURI CIKARANG HIJAU | NEW BUILD | XL | PKP |  | 01293/TBG-PKP/XL/MKT/10/2022 | 44852 | -6.251911 | 107.160481 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA |  |  | IHSAN PANDU WIJAYA |  |  | RYA YUDI ASTUTI | [14 empty] | 15 | 45092 | 44938 | [26 empty] | 1 | 44938 |  | 45000 |  |  |  |  | - | [5 empty] | 1 |  | - | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44972 |  |  |  | 44853.4151
0030002480031 | 1200941003 | JAW-JB-CKR-0279 | ALFAMART GRAND WISATA_1 | ALFAMART GRAND WISATA_1 | NEW BUILD | XL | PKP |  | 01988/TBG-PKP/XL/MKT/10/2022 | 44865 | -6.283111 | 107.044211 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 32 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA |  |  | IHSAN PANDU WIJAYA |  |  | RYA YUDI ASTUTI | [14 empty] | 2 | 45092 | 44950 | [26 empty] | 1 | 44950 |  | 45000 |  |  |  |  | - | [5 empty] | 1 |  |  | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44972 |  |  |  | 44865.69
0010802480011 | 1282251001 | PLR035 | TANGKOLOCIRACAP | TANGKOLOCIRACAP | NEW BUILD | TSEL | TB | TRITAMA | 063015/TBG-TB/TSEL/MKT/10/2022 | 44838 | -7.345476 | 106.517836 |  | JABODETABEK (OUTER) | SUKABUMI | JAWA BARAT | 62 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44924 | [26 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280251001 - TANGKOLOCIRACAP / 0010790530011 | 44781 |  |  |  | 44839.5142
0010802580011 | 1282331001 | CBN658 | PERMANENCIARUTENILIRCIBUNGBULANG | PERMANENCIARUTENILIRCIBUNGBULANG | NEW BUILD | TSEL | TB | BNP | 063025/TBG-TB/TSEL/MKT/10/2022 | 44838 | -6.53737 | 106.66961 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 62 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | DEWI NOVIANI SETIYAZI | [14 empty] | 29 | 44901 | 44924 | [26 empty] | 1 | 44924 |  | 44809 |  |  |  |  | - | [5 empty] | 1 |  | TSEL 2022 - BATCH#2 B2S | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [11 empty] | 1280321001 - PERMANENCIARUTENILIRCIBUNGBULANG / 0010790600011 | 44781 |  |  |  | 44839.5135
0030705690031 | 1274061003 | JAW-JB-CKR-0068 | PONDOK UNGU PERMAI RELOCATION | Pondok Ungu Permai Relocation | NEW BUILD | XL | TB | SS | 045223/TBG-TB/XL/MKT/09/2021 | 44447 | -6.179669 | 107.012981 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 32 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI | [14 empty] | 420 | 44890 | 44895 | [26 empty] | 1 | 44895 |  | 44799 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order 2021 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44595 |  |  |  | 44447.7001
0030739510031 | 1137591003 | JAW-JK-GGP-0444 | UTAMA_CENGKARENG_BARAT | UTAMA_CENGKARENG_BARAT | NEW MCP NON FO | XL | TB | KLS | 052955/TBG-TB/XL/MKT/03/2022 | 44629 | -6.14986 | 106.72295 | Jl Utama Raya, Cengkareng Barat, Kecamatan Cengkareng, Kota Jakarta Barat, Daerah Khusus Ibukota Jakarta | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 20 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI |  |  | 44827.6714 | 44833.4585 |  |  |  |  | 44832.4365 |  |  | 44832.4532 |  |  | 238 | 44849 | 44860 | [16 empty] | 44629 | [9 empty] | 1 | 44860 | 45001.5831 | 44806 |  | RFL | 44833 |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  | Sub Urban |  | - |  |  |  | B2S | BAUK Operator Input |  |  | 44834 | 44834 | [8 empty] | 44778 |  |  |  | 44629.4164
0030741690031 | 1137891003 | JAW-JK-GGP-0435 | JAW-JK-GGP-0435 | PETERNAKAN KAPUK RAYA RELOCATION | NEW MCP NON FO | XL | TB | KLS | 053355/TBG-TB/XL/MKT/03/2022 | 44643 | -6.1389 | 106.7594 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 20 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | SULAMTO |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | RYA YUDI ASTUTI | [14 empty] | 224 | 44883 | 44881 | [26 empty] | 1 | 44880 |  | 44855 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44793 |  |  |  | 44643.595
0030777160031 | 1279631003 | JAW-JB-CBI-0177 | CIKEAS SUKARAJA PANARAGAN | CIKEAS SUKARAJA PANARAGAN | NEW BUILD | XL | TB | BNP | 059769/TBG-TB/XL/MKT/07/2022 | 44760 | -6.590240 | 106.839810 | Kp. Sukaraja RT 01 RW 05 Desa Cikeas Kecamatan Sukaraja Kabupaten Bogor | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 42 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI |  |  | 44859.6817 | 44864.8221 |  |  |  | 44860.0516 | 44860.9324 | 44864.2755 |  | 44863.8312 |  |  | 107 | 44880 | 44860 | [16 empty] | 44760 | 44864 | [8 empty] | 1 | 44860 | 45033.4489 | 44908 |  | RFL | 44865 |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  | Sub Urban |  | - |  |  |  | B2S | BAUK Operator Input | 44864.8095 | PT. TELECONSULT NUSANTARA | 44855 | 44855 | [8 empty] | 44880 |  |  |  | 44760.486
0030778030031 | 1324201003 | JAW-BT-CPT-0513 | CIPUTAT TIMUR RENGAS | CIPUTAT TIMUR RENGAS | NEW MCP NON FO | XL | TB | DATATEL | 059890/TBG-TB/XL/MKT/07/2022 | 44771 | -6.277783 | 106.754406 |  | JABODETABEK (OUTER) | TANGERANG SELATAN | BANTEN | 30 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | RYA YUDI ASTUTI | [14 empty] | 96 | 44912 | 44895 | [26 empty] | 1 | 44895 |  | 44919 |  |  |  |  | - | [5 empty] | 1 |  |  | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44891 |  |  |  | 44771.7667
0030786910031 | 1139631003 | JAW-JK-KYB-0293 | KUNINGAN BARAT RELOCATION | KUNINGAN BARAT RELOCATION | NEW BUILD | XL | TB | KLS | 060853/TBG-TB/XL/MKT/08/2022 | 44785 | -6.23565 | 106.824211 |  | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 40 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA |  |  | IHSAN PANDU WIJAYA |  |  | RYA YUDI ASTUTI | [14 empty] | 82 | 44912 | 44873 | [26 empty] | 1 | 44873 |  | 44933 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44905 |  |  |  | 44785.5929
0030794470031 | 1324401003 | JAW-BT-RKB-0759 | LEBAKSANGKA_LEBAKGEDONG | LEBAKSANGKA_LEBAKGEDONG | NEW BUILD | XL | TB | TCMW | 061888/TBG-TB/XL/MKT/09/2022 | 44817 | -6.604928 | 106.410022 | Kp.Muhara RT.012 RW 002 Desa Ciladaeun Kecamatan Lebak Gedong Kabupaten Lebak Provinsi Banten | JABODETABEK (OUTER) | LEBAK | BANTEN | 72.00 | CIP | SITAC | BAK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | RYA YUDI ASTUTI |  |  | 44862.7493 | [11 empty] | 50 | 44879 | 44875 | [16 empty] | 44817 | [9 empty] | 1 | 44875 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  | Rural |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.866
0030794530031 | 1280581003 | JAW-JB-KWG-1094 | CIBOGO_KARAWANG | CIBOGO_KARAWANG | NEW BUILD | XL | TB | SSH | 061894/TBG-TB/XL/MKT/09/2022 | 44817 | -6.421239 | 107.364719 | Dusun Kaum Kp. Cibogo RT 005 RW 002 Desa Mulyasari Kecamatan Ciampel Kabupaten Karawang Provinsi Jawa Barat | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 52 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI |  |  | 44862.4697 |  |  |  |  | 44862.709 | 44862.7535 | 44866.4224 |  |  |  |  | 50 | 44883 | 44873 | [16 empty] | 44817 | [9 empty] | 1 | 44873 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  | Sub Urban |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8662
0030794540031 | 1324441003 | JAW-BT-TGR-0100 | DESA_CITUIS | DESA_CITUIS | NEW BUILD | XL | TB | MAJA | 061895/TBG-TB/XL/MKT/09/2022 | 44817 | -6.070697 | 106.564275 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 65 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI | [14 empty] | 50 | 44911 | 44881 | [26 empty] | 1 | 44881 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8659
0030794600031 | 1280611003 | JAW-JB-CKR-0114 | JABABEKA_RAWA_SUREN | JABABEKA_RAWA_SUREN | NEW BUILD | XL | TB | SS | 061901/TBG-TB/XL/MKT/09/2022 | 44817 | -6.2867 | 107.135731 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 30 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI | [14 empty] | 50 | 44898 | 44895 | [26 empty] | 1 | 44895 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8661
0030778060031 | 1139471003 | JAW-JK-KYB-0273 | JAGAKARSA LENTENG AGUNG | JAGAKARSA LENTENG AGUNG | NEW MCP NON FO | XL | TB | KLS | 059893/TBG-TB/XL/MKT/07/2022 | 44771 | -6.341708 | 106.838042 |  | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 30 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI | [14 empty] | 96 | 44912 | 44893 | [26 empty] | 1 | 44893 |  | 44919 |  |  |  |  | - | [5 empty] | 1 |  |  | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44891 |  |  |  | 44771.7667
0030795570031 | 1139981003 | JAW-JK-GGP-0439 | PALEM_SISIR | PALEM_SISIR | NEW MCP NON FO | XL | TB | KLS | 062050/TBG-TB/XL/MKT/09/2022 | 44819 | -6.127011 | 106.707017 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 25 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI | [14 empty] | 48 | 44898 | 44890 | [26 empty] | 1 | 44890 |  | 44967 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44939 |  |  |  | 44820.3851
0030794480031 | 1324411003 | JAW-BT-RKB-0756 | GIRIHARJA_CIPANAS | GIRIHARJA_CIPANAS | NEW BUILD | XL | TB | TCMW | 061889/TBG-TB/XL/MKT/09/2022 | 44817 | -6.56523 | 106.37647 | Kp. Cigebrok RT. 012 RW 003 Desa Giriharja Kecamatan Cipanas Kabupaten Lebak Provinsi Banten | JABODETABEK (OUTER) | LEBAK | BANTEN | 62 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | RYA YUDI ASTUTI |  |  | 44858.6005 | 44863.7384 |  |  |  | 44858.7714 | 44859.6762 | 44860.4099 |  | 44859.9586 |  |  | 50 | 44877 | 44863 | [16 empty] | 44817 | 44859 | [8 empty] | 1 | 44863 | 45033.4494 | 44965 |  | RFL | 44865 |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  | Rural |  | - |  |  |  | B2S | BAUK Operator Input | 44864.7484 | PT. TELECONSULT NUSANTARA | 44854 | 44858 | [8 empty] | 44937 |  |  |  | 44817.866
0030794490031 | 1280561003 | JAW-JB-BKS-0643 | PRIMA_HARAPAN_REGENSI | PRIMA_HARAPAN_REGENSI | NEW BUILD | XL | TB | SS | 061890/TBG-TB/XL/MKT/09/2022 | 44817 | -6.216986 | 107.012261 |  | JABODETABEK (OUTER) | KOTA BEKASI | JAWA BARAT | 25 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI | [14 empty] | 50 | 44898 | 44873 | [26 empty] | 1 | 44873 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8662
0030795560031 | 1139971003 | JAW-JK-GGP-0462 | HARAPAN_KITA | HARAPAN_KITA | NEW MCP NON FO | XL | TB | KLS | 062049/TBG-TB/XL/MKT/09/2022 | 44819 | -6.18075 | 106.801739 | Jl Aster no 52 RT 15 RW 01, Kelurahan Jati Pulo, Kecamatan Palmerah, Kota Jakarta Barat, DKI Jakarta | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 20 | CIP | SITAC | BAK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI |  |  | 44861.6465 | [11 empty] | 48 | 44911 | 44892 | [16 empty] | 44820 | [9 empty] | 1 | 44893 |  | 44967 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  | Sub Urban |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44939 |  |  |  | 44820.3863
0030778040031 | 1139461003 | JAW-JK-KYB-0276 | KERANJI CIGANJUR | KERANJI CIGANJUR | NEW MCP NON FO | XL | TB | DROP | 059891/TBG-TB/XL/MKT/07/2022 | 44771 | -6.337703 | 106.802817 |  | JABODETABEK (INNER) | JAKARTA SELATAN | DKI JAKARTA | 30 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI | [14 empty] | 96 | 44919 | 44881 | [26 empty] | 1 | 44881 |  | 44919 |  |  |  |  | - | [5 empty] | 1 |  |  | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44891 |  |  |  | 44771.7667
0030794630031 | 1324481003 | JAW-BT-TGR-0103 | CIRUMPAK_KRONJO | CIRUMPAK_KRONJO | NEW BUILD | XL | TB | MAJA | 061904/TBG-TB/XL/MKT/09/2022 | 44817 | -6.126569 | 106.443331 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 50 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | RYA YUDI ASTUTI | [14 empty] | 50 | 44918 | 44892 | [26 empty] | 1 | 44892 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8658
0030795770031 | 1139991003 | JA54 | SUMUR BATU KEMAYORAN | SUMUR BATU KEMAYORAN | NEW MCP NON FO | XL | PKP | KLS | 062077/TBG-PKP/XL/MKT/09/2022 | 44820 | -6.15889 | 106.86753 |  | JABODETABEK (INNER) | JAKARTA PUSAT | DKI JAKARTA | 25 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | RYA YUDI ASTUTI | [14 empty] | 47 | 44898 | 44892 | [26 empty] | 1 | 44892 |  | 44877 |  |  |  |  | - | [5 empty] | 1 |  |  | OUTDOOR |  |  |  | - |  |  |  | COLO | BAUK Operator Input | [12 empty] | 44849 |  |  |  | 44820.4513
0030794440031 | 1324381003 | JAW-BT-RKB-0755 | TEGAL_LUMBU | TEGAL_LUMBU | NEW BUILD | XL | TB | TCMW | 061885/TBG-TB/XL/MKT/09/2022 | 44817 | -6.81967 | 106.38351 | Kp.Tegal lumbu RT.01 RW.01 Desa Wanasari Kecamatan Cibeber Kabupaten Lebak Provinsi Banten | JABODETABEK (OUTER) | LEBAK | BANTEN | 62 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | RYA YUDI ASTUTI |  |  | 44858.6024 | 44863.7387 |  |  |  | 44859.4647 | 44859.9373 | 44860.413 |  | 44861.5298 |  |  | 50 | 44877 | 44863 | [16 empty] | 44817 | 44857 | [8 empty] | 1 | 44863 | 45033.4395 | 44965 |  | RFL | 44865 |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  | Rural |  | - |  |  |  | B2S | BAUK Operator Input | 44864.7554 | PT. TELECONSULT NUSANTARA | 44853 | 44850 | [8 empty] | 44937 |  |  |  | 44817.8661
0030794450031 | 1324391003 | JAW-BT-SRG-0055 | EXIT_TOL_JULANG_CIKANDE | EXIT_TOL_JULANG_CIKANDE | NEW BUILD | XL | TB | TRITAMA | 061886/TBG-TB/XL/MKT/09/2022 | 44817 | -6.178381 | 106.348031 |  | JABODETABEK (OUTER) | SERANG | BANTEN | 50 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | RYA YUDI ASTUTI | [14 empty] | 50 | 44911 | 44888 | [26 empty] | 1 | 44888 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8661
0030794520031 | 1280571003 | JAW-JB-CKR-0106 | CIJAMBE_BEKASI | CIJAMBE_BEKASI | NEW BUILD | XL | TB | AULIA | 061893/TBG-TB/XL/MKT/09/2022 | 44817 | -6.361689 | 107.1107 | Kp. Cijambe RT 10 RW 05 Desa Sukadami, Kec. Cikarang Selatan, Kabupaten Bekasi, Jawa Barat | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 42 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI |  |  | 44862.4826 |  |  |  |  | 44865.3951 | 44866.4271 | 44866.4713 |  |  |  |  | 50 | 44918 | 44894 | [16 empty] | 44817 | [9 empty] | 1 | 44894 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  | Urban |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8662
0030802620031 | 1140161003 | JAW-JK-GGP-0450 | HAWAIIAN_CENGKARENG_TIMUR | HAWAIIAN_CENGKARENG_TIMUR | NEW BUILD | XL | PKP | KLS | 063029/TBG-PKP/XL/MKT/10/2022 | 44838 | -6.130739 | 106.734389 |  | JABODETABEK (INNER) | JAKARTA BARAT | DKI JAKARTA | 20 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA |  |  | IHSAN PANDU WIJAYA |  |  | RYA YUDI ASTUTI | [14 empty] | 29 | 44988 | 44923 | [26 empty] | 1 | 44923 |  | 44896 |  |  |  |  | - | [5 empty] | 1 |  |  | OUTDOOR |  |  |  | - |  |  |  | COLO | BAUK Operator Input | [12 empty] | 44868 |  |  |  | 44838.6637
0030794550031 | 1280591003 | JAW-JB-CBI-0150 | CIJERUK_TAJUR_HALANG | CIJERUK_TAJUR_HALANG | NEW BUILD | XL | TB | BNP | 061896/TBG-TB/XL/MKT/09/2022 | 44817 | -6.65745 | 106.7912 |  | JABODETABEK (OUTER) | BOGOR | JAWA BARAT | 30 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI | [14 empty] | 50 | 44911 | 44895 | [26 empty] | 1 | 44895 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8662
0030794570031 | 1324451003 | JAW-BT-TGR-0102 | SONDOL_TANGERANG | SONDOL_TANGERANG | NEW BUILD | XL | TB | MAJA | 061898/TBG-TB/XL/MKT/09/2022 | 44817 | -6.123681 | 106.406789 |  | JABODETABEK (OUTER) | TANGERANG | BANTEN | 50 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | M ARIF HELMI | RYA YUDI ASTUTI | [14 empty] | 50 | 44898 | 44895 | [26 empty] | 1 | 44895 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8659
0030794610031 | 1280621003 | JAW-JB-CKR-0113 | CITANDUY_CIKARANG | CITANDUY_CIKARANG | NEW BUILD | XL | TB | DATATEL | 061902/TBG-TB/XL/MKT/09/2022 | 44817 | -6.322611 | 107.119153 |  | JABODETABEK (OUTER) | BEKASI | JAWA BARAT | 35 | CIP | PRE_SITAC | SSR/TSSR/ESR |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | RYA YUDI ASTUTI | [14 empty] | 50 | 44898 | 44892 | [26 empty] | 1 | 44892 |  | 44965 |  |  |  |  | - | [5 empty] | 1 |  | Commitment New Order B2S 2022-2024 XL | OUTDOOR |  |  |  | - |  |  |  | B2S | BAUK Operator Input | [12 empty] | 44937 |  |  |  | 44817.8661
0230789300231 | 1280041023 | IN20_JB_1451 | CIAMPEL KARAWANG | CIAMPEL KARAWANG | NEW BUILD | SMART8 | TB | ORLIE | 061255/TBG-TB/SMART8/MKT/08/2022 | 44802 | -6.40119 | 107.3585 | Dusun I Kp Parakan Terus Rt 003 Rw 002 Desa Kutapohaci Kec Ciampel Kab.Karawang, Jawa Barat | JABODETABEK (OUTER) | KARAWANG | JAWA BARAT | 52 | CIP | CME | DESIGNPACK & BOUWPLANK |  |  | IHSAN PANDU WIJAYA | FANDI KURNIAWAN SAPUTRA |  | IHSAN PANDU WIJAYA | FAZAR GANNY | MUHAMAD TAUFIQ IMMADUDIN | YUSTIA HARKAT |  |  | 44825.6877 | 44852.3799 |  |  |  | 44830.371 | 44831.4319 | 44847.6373 |  | 44845.805 |  |  | 65 | 44860 | 44880 | [16 empty] | 44804 | 44859 | [8 empty] | 1 | 44880 | 45033.4486 | 44950 |  | RFL | 44865 |  | - | [5 empty] | 1 |  |  | OUTDOOR |  | Urban |  | - |  |  |  | B2S | BAUK Operator Input | 44834.4686 | PT. TELECONSULT NUSANTARA | 44845 | 44846 | [8 empty] | 44922 |  |  |  | 44804.374