## AHENK1 (hidden)
| SOW BREAKDOWN | SOW BREAKDOWN |  | CURRENT PROGRESS CATEGORY | CURRENT PROGRESS CATEGORY |  | CURRENT PROGRESS CATEGORY
01 | 01.SPK propossed return | SPK propossed return | 01 | 01.SPK PROPOSSED RETURN | SPK PROPOSSED RETURN | 01 | SPK PROPOSSED RETURN
02 | 02.SPK returned | SPK returned | 02 | 02.SPK RETURNED | SPK RETURNED | 02 | SPK RETURNED
03 | 03.Survey ny start | Survey ny start | 03 | 03.SURVEY PROCESS | SURVEY PROCESS | 03 | SURVEY PROCESS
04 | 04.Survey OG | Survey OG | 03 | 03.SURVEY PROCESS | SURVEY PROCESS | 04 | HUNTING
05 | 05.Hunting OG | Hunting OG | 04 | 04.HUNTING | HUNTING | 05 | REHUNTING
06 | 06.Rehunting OG | Rehunting OG | 05 | 05.REHUNTING | REHUNTING | 06 | ERM PROCESS
07 | 07.ESR preparation | ESR preparation | 06 | 06.ERM PROCESS | ERM PROCESS | 07 | SITAC PROCESS
08 | 08.Under RNP review | Under RNP review | 06 | 06.ERM PROCESS | ERM PROCESS | 08 | GOVERNMENT PERMIT PROCESS
08 | 08.RNP review nok | RNP review nok | 06 | 06.ERM PROCESS | ERM PROCESS | 08 | GOVERNMENT PERMIT PROCESS
09 | 09.Under TNP review | Under TNP review | 06 | 06.ERM PROCESS | ERM PROCESS | 09 | CME HOLD
09 | 09.TNP review nok | TNP review nok | 06 | 06.ERM PROCESS | ERM PROCESS | 09 | CME HOLD
10 | 10.Under PWR review | Under PWR review | 06 | 06.ERM PROCESS | ERM PROCESS | 10 | CME PREPARATION
10 | 10.Under CIVIL review | Under CIVIL review | 06 | 06.ERM PROCESS | ERM PROCESS | 10 | CME PREPARATION
11 | 11.BAN / BAK Process | BAN / BAK Process | 07 | 07.SITAC PROCESS | SITAC PROCESS | 11 | BORE PILE OG
12 | 12.CP Process | CP Process | 07 | 07.SITAC PROCESS | SITAC PROCESS | 12 | EXCAVATION OG
13 | 13.Rekom L/C process | Rekom L/C process | 07 | 07.SITAC PROCESS | SITAC PROCESS | 13 | REBARING OG
14 | 14.Waiting Government disposition | Waiting Government disposition | 08 | 08.GOVERNMENT PERMIT PROCESS | GOVERNMENT PERMIT PROCESS | 14 | POURING CONCRETE OG
15 | 15.IMB Apply | IMB Apply | 08 | 08.GOVERNMENT PERMIT PROCESS | GOVERNMENT PERMIT PROCESS | 15 | CURRING TIME
16 | 16.IMB waiting survey | IMB waiting survey | 08 | 08.GOVERNMENT PERMIT PROCESS | GOVERNMENT PERMIT PROCESS | 16 | TOWER ERECTION OG
17 | 17.Waiting IPBP released | Waiting IPBP released | 08 | 08.GOVERNMENT PERMIT PROCESS | GOVERNMENT PERMIT PROCESS | 17 | RBS/BTS FOUNDATION OG
18 | 18.CME Hold | CME Hold | 09 | 09.CME HOLD | CME HOLD | 18 | F & Y OG
19 | 19.Mobilisasi dan Demobilisasi | Mobilisasi dan Demobilisasi | 10 | 10.CME PREPARATION | CME PREPARATION | 19 | MECHANICAL & ELECTRICAL OG
20 | 20.APD & Design Process | APD & Design Process | 10 | 10.CME PREPARATION | CME PREPARATION | 20 | SRFI
21 | 21.Bouwplank | Bouwplank | 10 | 10.CME PREPARATION | CME PREPARATION | 21 | RFI
22 | 22.Excavation | Excavation | 12 | 12.EXCAVATION OG | EXCAVATION OG
23 | 23.Bore pile Rebaring & Pouring | Bore pile Rebaring & Pouring | 11 | 11.BORE PILE OG | BORE PILE OG
24 | 24.Rebaring | Rebaring | 13 | 13.REBARING OG | REBARING OG
25 | 25.Pouring Concrete | Pouring Concrete | 14 | 14.POURING CONCRETE OG | POURING CONCRETE OG
26 | 26.Back Filling | Back Filling | 14 | 14.POURING CONCRETE OG | POURING CONCRETE OG
27 | 27.Curring Time | Curring Time | 15 | 15.CURRING TIME | CURRING TIME
28 | 28.Baseframe Installation (RT) | Baseframe Installation (RT) | 16 | 16.TOWER ERECTION OG | TOWER ERECTION OG
29 | 29.Erection | Erection | 16 | 16.TOWER ERECTION OG | TOWER ERECTION OG
30 | 30.VCT & HCT Instalation | VCT & HCT Instalation | 16 | 16.TOWER ERECTION OG | TOWER ERECTION OG
31 | 31.RBS/BTS Foundation | RBS/BTS Foundation | 17 | 17.RBS/BTS FOUNDATION OG | RBS/BTS FOUNDATION OG
32 | 32.F & Y process | F & Y process | 18 | 18.F & Y OG | F & Y OG
33 | 33.ME & Grounding system process | ME & Grounding system process | 19 | 19.MECHANICAL & ELECTRICAL OG | MECHANICAL & ELECTRICAL OG
34 | 34.Pemasangan & Instalasi Panel KWH & ACPDB | Pemasangan & Instalasi Panel KWH & ACPDB | 19 | 19.MECHANICAL & ELECTRICAL OG | MECHANICAL & ELECTRICAL OG
35 | 35.Pemasangan KWH Box dan pole | Pemasangan KWH Box dan pole | 19 | 19.MECHANICAL & ELECTRICAL OG | MECHANICAL & ELECTRICAL OG
36 | 36.PLN application | PLN application | 20 | 20.SRFI | SRFI
37 | 37.Power connection process | Power connection process | 20 | 20.SRFI | SRFI
38 | 38.RFI | RFI | 21 | 21.RFI | RFI
39 | 39.CME By XL | CME By XL | 21 | 21.CME By XL | CME By XL

## AHENK2 (hidden)
2017-01-01 | W | 01 | - | 2017 | W01-2017 | Jan-2017
2017-01-02 | W | 01 | - | 2017 | W01-2017 | Jan-2017
2017-01-03 | W | 01 | - | 2017 | W01-2017 | Jan-2017
2017-01-04 | W | 01 | - | 2017 | W01-2017 | Jan-2017
2017-01-05 | W | 01 | - | 2017 | W01-2017 | Jan-2017
2017-01-06 | W | 01 | - | 2017 | W01-2017 | Jan-2017
2017-01-07 | W | 02 | - | 2017 | W02-2017 | Jan-2017
2017-01-08 | W | 02 | - | 2017 | W02-2017 | Jan-2017
2017-01-09 | W | 02 | - | 2017 | W02-2017 | Jan-2017
2017-01-10 | W | 02 | - | 2017 | W02-2017 | Jan-2017
2017-01-11 | W | 02 | - | 2017 | W02-2017 | Jan-2017
2017-01-12 | W | 02 | - | 2017 | W02-2017 | Jan-2017
2017-01-13 | W | 02 | - | 2017 | W02-2017 | Jan-2017
2017-01-14 | W | 03 | - | 2017 | W03-2017 | Jan-2017
2017-01-15 | W | 03 | - | 2017 | W03-2017 | Jan-2017
2017-01-16 | W | 03 | - | 2017 | W03-2017 | Jan-2017
2017-01-17 | W | 03 | - | 2017 | W03-2017 | Jan-2017
2017-01-18 | W | 03 | - | 2017 | W03-2017 | Jan-2017
2017-01-19 | W | 03 | - | 2017 | W03-2017 | Jan-2017
2017-01-20 | W | 03 | - | 2017 | W03-2017 | Jan-2017
2017-01-21 | W | 04 | - | 2017 | W04-2017 | Jan-2017
2017-01-22 | W | 04 | - | 2017 | W04-2017 | Jan-2017
2017-01-23 | W | 04 | - | 2017 | W04-2017 | Jan-2017
2017-01-24 | W | 04 | - | 2017 | W04-2017 | Jan-2017
2017-01-25 | W | 04 | - | 2017 | W04-2017 | Jan-2017
2017-01-26 | W | 04 | - | 2017 | W04-2017 | Jan-2017
2017-01-27 | W | 04 | - | 2017 | W04-2017 | Jan-2017
2017-01-28 | W | 05 | - | 2017 | W05-2017 | Jan-2017
2017-01-29 | W | 05 | - | 2017 | W05-2017 | Jan-2017
2017-01-30 | W | 05 | - | 2017 | W05-2017 | Jan-2017
2017-01-31 | W | 05 | - | 2017 | W05-2017 | Feb-2017
2017-02-01 | W | 05 | - | 2017 | W05-2017 | Feb-2017
2017-02-02 | W | 05 | - | 2017 | W05-2017 | Feb-2017
2017-02-03 | W | 05 | - | 2017 | W05-2017 | Feb-2017
2017-02-04 | W | 06 | - | 2017 | W06-2017 | Feb-2017
2017-02-05 | W | 06 | - | 2017 | W06-2017 | Feb-2017
2017-02-06 | W | 06 | - | 2017 | W06-2017 | Feb-2017
2017-02-07 | W | 06 | - | 2017 | W06-2017 | Feb-2017
2017-02-08 | W | 06 | - | 2017 | W06-2017 | Feb-2017
2017-02-09 | W | 06 | - | 2017 | W06-2017 | Feb-2017
2017-02-10 | W | 06 | - | 2017 | W06-2017 | Feb-2017
2017-02-11 | W | 07 | - | 2017 | W07-2017 | Feb-2017
2017-02-12 | W | 07 | - | 2017 | W07-2017 | Feb-2017
2017-02-13 | W | 07 | - | 2017 | W07-2017 | Feb-2017
2017-02-14 | W | 07 | - | 2017 | W07-2017 | Feb-2017
2017-02-15 | W | 07 | - | 2017 | W07-2017 | Feb-2017
2017-02-16 | W | 07 | - | 2017 | W07-2017 | Feb-2017
2017-02-17 | W | 07 | - | 2017 | W07-2017 | Feb-2017
2017-02-18 | W | 08 | - | 2017 | W08-2017 | Feb-2017
2017-02-19 | W | 08 | - | 2017 | W08-2017 | Feb-2017
2017-02-20 | W | 08 | - | 2017 | W08-2017 | Feb-2017
2017-02-21 | W | 08 | - | 2017 | W08-2017 | Feb-2017
2017-02-22 | W | 08 | - | 2017 | W08-2017 | Feb-2017
2017-02-23 | W | 08 | - | 2017 | W08-2017 | Feb-2017
2017-02-24 | W | 08 | - | 2017 | W08-2017 | Feb-2017
2017-02-25 | W | 09 | - | 2017 | W09-2017 | Feb-2017
2017-02-26 | W | 09 | - | 2017 | W09-2017 | Feb-2017
2017-02-27 | W | 09 | - | 2017 | W09-2017 | Feb-2017
2017-02-28 | W | 09 | - | 2017 | W09-2017 | Mar-2017
2017-03-01 | W | 09 | - | 2017 | W09-2017 | Mar-2017
2017-03-02 | W | 09 | - | 2017 | W09-2017 | Mar-2017
2017-03-03 | W | 09 | - | 2017 | W09-2017 | Mar-2017
2017-03-04 | W | 10 | - | 2017 | W10-2017 | Mar-2017
2017-03-05 | W | 10 | - | 2017 | W10-2017 | Mar-2017
2017-03-06 | W | 10 | - | 2017 | W10-2017 | Mar-2017
2017-03-07 | W | 10 | - | 2017 | W10-2017 | Mar-2017
2017-03-08 | W | 10 | - | 2017 | W10-2017 | Mar-2017
2017-03-09 | W | 10 | - | 2017 | W10-2017 | Mar-2017
2017-03-10 | W | 10 | - | 2017 | W10-2017 | Mar-2017
2017-03-11 | W | 11 | - | 2017 | W11-2017 | Mar-2017
2017-03-12 | W | 11 | - | 2017 | W11-2017 | Mar-2017
2017-03-13 | W | 11 | - | 2017 | W11-2017 | Mar-2017
2017-03-14 | W | 11 | - | 2017 | W11-2017 | Mar-2017
2017-03-15 | W | 11 | - | 2017 | W11-2017 | Mar-2017
2017-03-16 | W | 11 | - | 2017 | W11-2017 | Mar-2017
2017-03-17 | W | 11 | - | 2017 | W11-2017 | Mar-2017
2017-03-18 | W | 12 | - | 2017 | W12-2017 | Mar-2017
2017-03-19 | W | 12 | - | 2017 | W12-2017 | Mar-2017
2017-03-20 | W | 12 | - | 2017 | W12-2017 | Mar-2017
2017-03-21 | W | 12 | - | 2017 | W12-2017 | Mar-2017
2017-03-22 | W | 12 | - | 2017 | W12-2017 | Mar-2017
2017-03-23 | W | 12 | - | 2017 | W12-2017 | Mar-2017
2017-03-24 | W | 12 | - | 2017 | W12-2017 | Mar-2017
2017-03-25 | W | 13 | - | 2017 | W13-2017 | Mar-2017
2017-03-26 | W | 13 | - | 2017 | W13-2017 | Mar-2017
2017-03-27 | W | 13 | - | 2017 | W13-2017 | Mar-2017
2017-03-28 | W | 13 | - | 2017 | W13-2017 | Mar-2017
2017-03-29 | W | 13 | - | 2017 | W13-2017 | Mar-2017
2017-03-30 | W | 13 | - | 2017 | W13-2017 | Mar-2017
2017-03-31 | W | 13 | - | 2017 | W13-2017 | Apr-2017
2017-04-01 | W | 14 | - | 2017 | W14-2017 | Apr-2017
2017-04-02 | W | 14 | - | 2017 | W14-2017 | Apr-2017
2017-04-03 | W | 14 | - | 2017 | W14-2017 | Apr-2017
2017-04-04 | W | 14 | - | 2017 | W14-2017 | Apr-2017
2017-04-05 | W | 14 | - | 2017 | W14-2017 | Apr-2017
2017-04-06 | W | 14 | - | 2017 | W14-2017 | Apr-2017
2017-04-07 | W | 14 | - | 2017 | W14-2017 | Apr-2017
2017-04-08 | W | 15 | - | 2017 | W15-2017 | Apr-2017
2017-04-09 | W | 15 | - | 2017 | W15-2017 | Apr-2017
2017-04-10 | W | 15 | - | 2017 | W15-2017 | Apr-2017
2017-04-11 | W | 15 | - | 2017 | W15-2017 | Apr-2017
2017-04-12 | W | 15 | - | 2017 | W15-2017 | Apr-2017
2017-04-13 | W | 15 | - | 2017 | W15-2017 | Apr-2017
2017-04-14 | W | 15 | - | 2017 | W15-2017 | Apr-2017
2017-04-15 | W | 16 | - | 2017 | W16-2017 | Apr-2017
2017-04-16 | W | 16 | - | 2017 | W16-2017 | Apr-2017
2017-04-17 | W | 16 | - | 2017 | W16-2017 | Apr-2017
2017-04-18 | W | 16 | - | 2017 | W16-2017 | Apr-2017
2017-04-19 | W | 16 | - | 2017 | W16-2017 | Apr-2017
2017-04-20 | W | 16 | - | 2017 | W16-2017 | Apr-2017
2017-04-21 | W | 16 | - | 2017 | W16-2017 | Apr-2017
2017-04-22 | W | 17 | - | 2017 | W17-2017 | Apr-2017
2017-04-23 | W | 17 | - | 2017 | W17-2017 | Apr-2017
2017-04-24 | W | 17 | - | 2017 | W17-2017 | Apr-2017
2017-04-25 | W | 17 | - | 2017 | W17-2017 | Apr-2017
2017-04-26 | W | 17 | - | 2017 | W17-2017 | Apr-2017
2017-04-27 | W | 17 | - | 2017 | W17-2017 | Apr-2017
2017-04-28 | W | 17 | - | 2017 | W17-2017 | Apr-2017
2017-04-29 | W | 18 | - | 2017 | W18-2017 | Apr-2017
2017-04-30 | W | 18 | - | 2017 | W18-2017 | May-2017
2017-05-01 | W | 18 | - | 2017 | W18-2017 | May-2017
2017-05-02 | W | 18 | - | 2017 | W18-2017 | May-2017
2017-05-03 | W | 18 | - | 2017 | W18-2017 | May-2017
2017-05-04 | W | 18 | - | 2017 | W18-2017 | May-2017
2017-05-05 | W | 18 | - | 2017 | W18-2017 | May-2017
2017-05-06 | W | 19 | - | 2017 | W19-2017 | May-2017
2017-05-07 | W | 19 | - | 2017 | W19-2017 | May-2017
2017-05-08 | W | 19 | - | 2017 | W19-2017 | May-2017
2017-05-09 | W | 19 | - | 2017 | W19-2017 | May-2017
2017-05-10 | W | 19 | - | 2017 | W19-2017 | May-2017
2017-05-11 | W | 19 | - | 2017 | W19-2017 | May-2017
2017-05-12 | W | 19 | - | 2017 | W19-2017 | May-2017
2017-05-13 | W | 20 | - | 2017 | W20-2017 | May-2017
2017-05-14 | W | 20 | - | 2017 | W20-2017 | May-2017
2017-05-15 | W | 20 | - | 2017 | W20-2017 | May-2017
2017-05-16 | W | 20 | - | 2017 | W20-2017 | May-2017
2017-05-17 | W | 20 | - | 2017 | W20-2017 | May-2017
2017-05-18 | W | 20 | - | 2017 | W20-2017 | May-2017
2017-05-19 | W | 20 | - | 2017 | W20-2017 | May-2017
2017-05-20 | W | 21 | - | 2017 | W21-2017 | May-2017
2017-05-21 | W | 21 | - | 2017 | W21-2017 | May-2017
2017-05-22 | W | 21 | - | 2017 | W21-2017 | May-2017
2017-05-23 | W | 21 | - | 2017 | W21-2017 | May-2017
2017-05-24 | W | 21 | - | 2017 | W21-2017 | May-2017
2017-05-25 | W | 21 | - | 2017 | W21-2017 | May-2017
2017-05-26 | W | 21 | - | 2017 | W21-2017 | May-2017
2017-05-27 | W | 22 | - | 2017 | W22-2017 | May-2017
2017-05-28 | W | 22 | - | 2017 | W22-2017 | May-2017
2017-05-29 | W | 22 | - | 2017 | W22-2017 | May-2017
2017-05-30 | W | 22 | - | 2017 | W22-2017 | May-2017
2017-05-31 | W | 22 | - | 2017 | W22-2017 | May-2017
2017-06-01 | W | 22 | - | 2017 | W22-2017 | May-2017
2017-06-02 | W | 22 | - | 2017 | W22-2017 | May-2017
2017-06-03 | W | 23 | - | 2017 | W23-2017 | Jun-2017
2017-06-04 | W | 23 | - | 2017 | W23-2017 | Jun-2017
2017-06-05 | W | 23 | - | 2017 | W23-2017 | Jun-2017
2017-06-06 | W | 23 | - | 2017 | W23-2017 | Jun-2017
2017-06-07 | W | 23 | - | 2017 | W23-2017 | Jun-2017
2017-06-08 | W | 23 | - | 2017 | W23-2017 | Jun-2017
2017-06-09 | W | 23 | - | 2017 | W23-2017 | Jun-2017
2017-06-10 | W | 24 | - | 2017 | W24-2017 | Jun-2017
2017-06-11 | W | 24 | - | 2017 | W24-2017 | Jun-2017
2017-06-12 | W | 24 | - | 2017 | W24-2017 | Jun-2017
2017-06-13 | W | 24 | - | 2017 | W24-2017 | Jun-2017
2017-06-14 | W | 24 | - | 2017 | W24-2017 | Jun-2017
2017-06-15 | W | 24 | - | 2017 | W24-2017 | Jun-2017
2017-06-16 | W | 24 | - | 2017 | W24-2017 | Jun-2017
2017-06-17 | W | 25 | - | 2017 | W25-2017 | Jun-2017
2017-06-18 | W | 25 | - | 2017 | W25-2017 | Jun-2017
2017-06-19 | W | 25 | - | 2017 | W25-2017 | Jun-2017
2017-06-20 | W | 25 | - | 2017 | W25-2017 | Jun-2017
2017-06-21 | W | 25 | - | 2017 | W25-2017 | Jun-2017
2017-06-22 | W | 25 | - | 2017 | W25-2017 | Jun-2017
2017-06-23 | W | 25 | - | 2017 | W25-2017 | Jun-2017
2017-06-24 | W | 26 | - | 2017 | W26-2017 | Jun-2017
2017-06-25 | W | 26 | - | 2017 | W26-2017 | Jun-2017
2017-06-26 | W | 26 | - | 2017 | W26-2017 | Jun-2017
2017-06-27 | W | 26 | - | 2017 | W26-2017 | Jun-2017
2017-06-28 | W | 26 | - | 2017 | W26-2017 | Jun-2017
2017-06-29 | W | 26 | - | 2017 | W26-2017 | Jun-2017
2017-06-30 | W | 26 | - | 2017 | W26-2017 | Jul-2017
2017-07-01 | W | 27 | - | 2017 | W27-2017 | Jul-2017
2017-07-02 | W | 27 | - | 2017 | W27-2017 | Jul-2017
2017-07-03 | W | 27 | - | 2017 | W27-2017 | Jul-2017
2017-07-04 | W | 27 | - | 2017 | W27-2017 | Jul-2017
2017-07-05 | W | 27 | - | 2017 | W27-2017 | Jul-2017
2017-07-06 | W | 27 | - | 2017 | W27-2017 | Jul-2017
2017-07-07 | W | 27 | - | 2017 | W27-2017 | Jul-2017
2017-07-08 | W | 28 | - | 2017 | W28-2017 | Jul-2017
2017-07-09 | W | 28 | - | 2017 | W28-2017 | Jul-2017
2017-07-10 | W | 28 | - | 2017 | W28-2017 | Jul-2017
2017-07-11 | W | 28 | - | 2017 | W28-2017 | Jul-2017
2017-07-12 | W | 28 | - | 2017 | W28-2017 | Jul-2017
2017-07-13 | W | 28 | - | 2017 | W28-2017 | Jul-2017
2017-07-14 | W | 28 | - | 2017 | W28-2017 | Jul-2017
2017-07-15 | W | 29 | - | 2017 | W29-2017 | Jul-2017
2017-07-16 | W | 29 | - | 2017 | W29-2017 | Jul-2017
2017-07-17 | W | 29 | - | 2017 | W29-2017 | Jul-2017
2017-07-18 | W | 29 | - | 2017 | W29-2017 | Jul-2017
2017-07-19 | W | 29 | - | 2017 | W29-2017 | Jul-2017
2017-07-20 | W | 29 | - | 2017 | W29-2017 | Jul-2017
2017-07-21 | W | 29 | - | 2017 | W29-2017 | Jul-2017
2017-07-22 | W | 30 | - | 2017 | W30-2017 | Jul-2017
2017-07-23 | W | 30 | - | 2017 | W30-2017 | Jul-2017
2017-07-24 | W | 30 | - | 2017 | W30-2017 | Jul-2017
2017-07-25 | W | 30 | - | 2017 | W30-2017 | Jul-2017
2017-07-26 | W | 30 | - | 2017 | W30-2017 | Jul-2017
2017-07-27 | W | 30 | - | 2017 | W30-2017 | Jul-2017
2017-07-28 | W | 30 | - | 2017 | W30-2017 | Jul-2017
2017-07-29 | W | 31 | - | 2017 | W31-2017 | Jul-2017
2017-07-30 | W | 31 | - | 2017 | W31-2017 | Jul-2017
2017-07-31 | W | 31 | - | 2017 | W31-2017 | Aug-2017
2017-08-01 | W | 31 | - | 2017 | W31-2017 | Aug-2017
2017-08-02 | W | 31 | - | 2017 | W31-2017 | Aug-2017
2017-08-03 | W | 31 | - | 2017 | W31-2017 | Aug-2017
2017-08-04 | W | 31 | - | 2017 | W31-2017 | Aug-2017
2017-08-05 | W | 32 | - | 2017 | W32-2017 | Aug-2017
2017-08-06 | W | 32 | - | 2017 | W32-2017 | Aug-2017
2017-08-07 | W | 32 | - | 2017 | W32-2017 | Aug-2017
2017-08-08 | W | 32 | - | 2017 | W32-2017 | Aug-2017
2017-08-09 | W | 32 | - | 2017 | W32-2017 | Aug-2017
2017-08-10 | W | 32 | - | 2017 | W32-2017 | Aug-2017
2017-08-11 | W | 32 | - | 2017 | W32-2017 | Aug-2017
2017-08-12 | W | 33 | - | 2017 | W33-2017 | Aug-2017
2017-08-13 | W | 33 | - | 2017 | W33-2017 | Aug-2017
2017-08-14 | W | 33 | - | 2017 | W33-2017 | Aug-2017
2017-08-15 | W | 33 | - | 2017 | W33-2017 | Aug-2017
2017-08-16 | W | 33 | - | 2017 | W33-2017 | Aug-2017
2017-08-17 | W | 33 | - | 2017 | W33-2017 | Aug-2017
2017-08-18 | W | 33 | - | 2017 | W33-2017 | Aug-2017
2017-08-19 | W | 34 | - | 2017 | W34-2017 | Aug-2017
2017-08-20 | W | 34 | - | 2017 | W34-2017 | Aug-2017
2017-08-21 | W | 34 | - | 2017 | W34-2017 | Aug-2017
2017-08-22 | W | 34 | - | 2017 | W34-2017 | Aug-2017
2017-08-23 | W | 34 | - | 2017 | W34-2017 | Aug-2017
2017-08-24 | W | 34 | - | 2017 | W34-2017 | Aug-2017
2017-08-25 | W | 34 | - | 2017 | W34-2017 | Aug-2017
2017-08-26 | W | 35 | - | 2017 | W35-2017 | Aug-2017
2017-08-27 | W | 35 | - | 2017 | W35-2017 | Aug-2017
2017-08-28 | W | 35 | - | 2017 | W35-2017 | Aug-2017
2017-08-29 | W | 35 | - | 2017 | W35-2017 | Aug-2017
2017-08-30 | W | 35 | - | 2017 | W35-2017 | Aug-2017
2017-08-31 | W | 35 | - | 2017 | W35-2017 | Sep-2017
2017-09-01 | W | 35 | - | 2017 | W35-2017 | Sep-2017
2017-09-02 | W | 36 | - | 2017 | W36-2017 | Sep-2017
2017-09-03 | W | 36 | - | 2017 | W36-2017 | Sep-2017
2017-09-04 | W | 36 | - | 2017 | W36-2017 | Sep-2017
2017-09-05 | W | 36 | - | 2017 | W36-2017 | Sep-2017
2017-09-06 | W | 36 | - | 2017 | W36-2017 | Sep-2017
2017-09-07 | W | 36 | - | 2017 | W36-2017 | Sep-2017
2017-09-08 | W | 36 | - | 2017 | W36-2017 | Sep-2017
2017-09-09 | W | 37 | - | 2017 | W37-2017 | Sep-2017
2017-09-10 | W | 37 | - | 2017 | W37-2017 | Sep-2017
2017-09-11 | W | 37 | - | 2017 | W37-2017 | Sep-2017
2017-09-12 | W | 37 | - | 2017 | W37-2017 | Sep-2017
2017-09-13 | W | 37 | - | 2017 | W37-2017 | Sep-2017
2017-09-14 | W | 37 | - | 2017 | W37-2017 | Sep-2017
2017-09-15 | W | 37 | - | 2017 | W37-2017 | Sep-2017
2017-09-16 | W | 38 | - | 2017 | W38-2017 | Sep-2017
2017-09-17 | W | 38 | - | 2017 | W38-2017 | Sep-2017
2017-09-18 | W | 38 | - | 2017 | W38-2017 | Sep-2017
2017-09-19 | W | 38 | - | 2017 | W38-2017 | Sep-2017
2017-09-20 | W | 38 | - | 2017 | W38-2017 | Sep-2017
2017-09-21 | W | 38 | - | 2017 | W38-2017 | Sep-2017
2017-09-22 | W | 38 | - | 2017 | W38-2017 | Sep-2017
2017-09-23 | W | 39 | - | 2017 | W39-2017 | Sep-2017
2017-09-24 | W | 39 | - | 2017 | W39-2017 | Sep-2017
2017-09-25 | W | 39 | - | 2017 | W39-2017 | Sep-2017
2017-09-26 | W | 39 | - | 2017 | W39-2017 | Sep-2017
2017-09-27 | W | 39 | - | 2017 | W39-2017 | Sep-2017
2017-09-28 | W | 39 | - | 2017 | W39-2017 | Sep-2017
2017-09-29 | W | 39 | - | 2017 | W39-2017 | Sep-2017
2017-09-30 | W | 39 | - | 2017 | W39-2017 | Sep-2017
2017-10-01 | W | 40 | - | 2017 | W40-2017 | Oct-2017
2017-10-02 | W | 40 | - | 2017 | W40-2017 | Oct-2017
2017-10-03 | W | 40 | - | 2017 | W40-2017 | Oct-2017
2017-10-04 | W | 40 | - | 2017 | W40-2017 | Oct-2017
2017-10-05 | W | 40 | - | 2017 | W40-2017 | Oct-2017
2017-10-06 | W | 40 | - | 2017 | W40-2017 | Oct-2017
2017-10-07 | W | 41 | - | 2017 | W41-2017 | Oct-2017
2017-10-08 | W | 41 | - | 2017 | W41-2017 | Oct-2017
2017-10-09 | W | 41 | - | 2017 | W41-2017 | Oct-2017
2017-10-10 | W | 41 | - | 2017 | W41-2017 | Oct-2017
2017-10-11 | W | 41 | - | 2017 | W41-2017 | Oct-2017
2017-10-12 | W | 41 | - | 2017 | W41-2017 | Oct-2017
2017-10-13 | W | 41 | - | 2017 | W41-2017 | Oct-2017
2017-10-14 | W | 42 | - | 2017 | W42-2017 | Oct-2017
2017-10-15 | W | 42 | - | 2017 | W42-2017 | Oct-2017
2017-10-16 | W | 42 | - | 2017 | W42-2017 | Oct-2017
2017-10-17 | W | 42 | - | 2017 | W42-2017 | Oct-2017
2017-10-18 | W | 42 | - | 2017 | W42-2017 | Oct-2017
2017-10-19 | W | 42 | - | 2017 | W42-2017 | Oct-2017
2017-10-20 | W | 42 | - | 2017 | W42-2017 | Oct-2017
2017-10-21 | W | 43 | - | 2017 | W43-2017 | Oct-2017
2017-10-22 | W | 43 | - | 2017 | W43-2017 | Oct-2017
2017-10-23 | W | 43 | - | 2017 | W43-2017 | Oct-2017
2017-10-24 | W | 43 | - | 2017 | W43-2017 | Oct-2017
2017-10-25 | W | 43 | - | 2017 | W43-2017 | Oct-2017
2017-10-26 | W | 43 | - | 2017 | W43-2017 | Oct-2017
2017-10-27 | W | 43 | - | 2017 | W43-2017 | Oct-2017
2017-10-28 | W | 44 | - | 2017 | W44-2017 | Oct-2017
2017-10-29 | W | 44 | - | 2017 | W44-2017 | Oct-2017
2017-10-30 | W | 44 | - | 2017 | W44-2017 | Oct-2017
2017-10-31 | W | 44 | - | 2017 | W44-2017 | Nov-2017
2017-11-01 | W | 44 | - | 2017 | W44-2017 | Nov-2017
2017-11-02 | W | 44 | - | 2017 | W44-2017 | Nov-2017
2017-11-03 | W | 44 | - | 2017 | W44-2017 | Nov-2017
2017-11-04 | W | 45 | - | 2017 | W45-2017 | Nov-2017
2017-11-05 | W | 45 | - | 2017 | W45-2017 | Nov-2017
2017-11-06 | W | 45 | - | 2017 | W45-2017 | Nov-2017
2017-11-07 | W | 45 | - | 2017 | W45-2017 | Nov-2017
2017-11-08 | W | 45 | - | 2017 | W45-2017 | Nov-2017
2017-11-09 | W | 45 | - | 2017 | W45-2017 | Nov-2017
2017-11-10 | W | 45 | - | 2017 | W45-2017 | Nov-2017
2017-11-11 | W | 46 | - | 2017 | W46-2017 | Nov-2017
2017-11-12 | W | 46 | - | 2017 | W46-2017 | Nov-2017
2017-11-13 | W | 46 | - | 2017 | W46-2017 | Nov-2017
2017-11-14 | W | 46 | - | 2017 | W46-2017 | Nov-2017
2017-11-15 | W | 46 | - | 2017 | W46-2017 | Nov-2017
2017-11-16 | W | 46 | - | 2017 | W46-2017 | Nov-2017
2017-11-17 | W | 46 | - | 2017 | W46-2017 | Nov-2017
2017-11-18 | W | 47 | - | 2017 | W47-2017 | Nov-2017
2017-11-19 | W | 47 | - | 2017 | W47-2017 | Nov-2017
2017-11-20 | W | 47 | - | 2017 | W47-2017 | Nov-2017
2017-11-21 | W | 47 | - | 2017 | W47-2017 | Nov-2017
2017-11-22 | W | 47 | - | 2017 | W47-2017 | Nov-2017
2017-11-23 | W | 47 | - | 2017 | W47-2017 | Nov-2017
2017-11-24 | W | 47 | - | 2017 | W47-2017 | Nov-2017
2017-11-25 | W | 48 | - | 2017 | W48-2017 | Nov-2017
2017-11-26 | W | 48 | - | 2017 | W48-2017 | Nov-2017
2017-11-27 | W | 48 | - | 2017 | W48-2017 | Nov-2017
2017-11-28 | W | 48 | - | 2017 | W48-2017 | Nov-2017
2017-11-29 | W | 48 | - | 2017 | W48-2017 | Nov-2017
2017-11-30 | W | 48 | - | 2017 | W48-2017 | Dec-2017
2017-12-01 | W | 48 | - | 2017 | W48-2017 | Dec-2017
2017-12-02 | W | 49 | - | 2017 | W49-2017 | Dec-2017
2017-12-03 | W | 49 | - | 2017 | W49-2017 | Dec-2017
2017-12-04 | W | 49 | - | 2017 | W49-2017 | Dec-2017
2017-12-05 | W | 49 | - | 2017 | W49-2017 | Dec-2017
2017-12-06 | W | 49 | - | 2017 | W49-2017 | Dec-2017
2017-12-07 | W | 49 | - | 2017 | W49-2017 | Dec-2017
2017-12-08 | W | 49 | - | 2017 | W49-2017 | Dec-2017
2017-12-09 | W | 50 | - | 2017 | W50-2017 | Dec-2017
2017-12-10 | W | 50 | - | 2017 | W50-2017 | Dec-2017
2017-12-11 | W | 50 | - | 2017 | W50-2017 | Dec-2017
2017-12-12 | W | 50 | - | 2017 | W50-2017 | Dec-2017
2017-12-13 | W | 50 | - | 2017 | W50-2017 | Dec-2017
2017-12-14 | W | 50 | - | 2017 | W50-2017 | Dec-2017
2017-12-15 | W | 50 | - | 2017 | W50-2017 | Dec-2017
2017-12-16 | W | 51 | - | 2017 | W51-2017 | Dec-2017
2017-12-17 | W | 51 | - | 2017 | W51-2017 | Dec-2017
2017-12-18 | W | 51 | - | 2017 | W51-2017 | Dec-2017
2017-12-19 | W | 51 | - | 2017 | W51-2017 | Dec-2017
2017-12-20 | W | 51 | - | 2017 | W51-2017 | Dec-2017
2017-12-21 | W | 51 | - | 2017 | W51-2017 | Dec-2017
2017-12-22 | W | 51 | - | 2017 | W51-2017 | Dec-2017
2017-12-23 | W | 52 | - | 2017 | W52-2017 | Dec-2017
2017-12-24 | W | 52 | - | 2017 | W52-2017 | Dec-2017
2017-12-25 | W | 52 | - | 2017 | W52-2017 | Dec-2017
2017-12-26 | W | 52 | - | 2017 | W52-2017 | Dec-2017
2017-12-27 | W | 52 | - | 2017 | W52-2017 | Dec-2017
2017-12-28 | W | 52 | - | 2017 | W52-2017 | Dec-2017
2017-12-29 | W | 52 | - | 2017 | W52-2017 | Dec-2017
2017-12-30 | W | 52 | - | 2017 | W52-2017 | Dec-2017
2017-12-31 | W | 52 | - | 2017 | W52-2017 | Dec-2017
2018-01-01 | W | 01 | - | 2018 | W01-2018 | Jan-2018
2018-01-02 | W | 01 | - | 2018 | W01-2018 | Jan-2018
2018-01-03 | W | 01 | - | 2018 | W01-2018 | Jan-2018
2018-01-04 | W | 01 | - | 2018 | W01-2018 | Jan-2018
2018-01-05 | W | 01 | - | 2018 | W01-2018 | Jan-2018
2018-01-06 | W | 01 | - | 2018 | W01-2018 | Jan-2018
2018-01-07 | W | 02 | - | 2018 | W02-2018 | Jan-2018
2018-01-08 | W | 02 | - | 2018 | W02-2018 | Jan-2018
2018-01-09 | W | 02 | - | 2018 | W02-2018 | Jan-2018
2018-01-10 | W | 02 | - | 2018 | W02-2018 | Jan-2018
2018-01-11 | W | 02 | - | 2018 | W02-2018 | Jan-2018
2018-01-12 | W | 02 | - | 2018 | W02-2018 | Jan-2018
2018-01-13 | W | 02 | - | 2018 | W02-2018 | Jan-2018
2018-01-14 | W | 03 | - | 2018 | W03-2018 | Jan-2018
2018-01-15 | W | 03 | - | 2018 | W03-2018 | Jan-2018
2018-01-16 | W | 03 | - | 2018 | W03-2018 | Jan-2018
2018-01-17 | W | 03 | - | 2018 | W03-2018 | Jan-2018
2018-01-18 | W | 03 | - | 2018 | W03-2018 | Jan-2018
2018-01-19 | W | 03 | - | 2018 | W03-2018 | Jan-2018
2018-01-20 | W | 03 | - | 2018 | W03-2018 | Jan-2018
2018-01-21 | W | 04 | - | 2018 | W04-2018 | Jan-2018
2018-01-22 | W | 04 | - | 2018 | W04-2018 | Jan-2018
2018-01-23 | W | 04 | - | 2018 | W04-2018 | Jan-2018
2018-01-24 | W | 04 | - | 2018 | W04-2018 | Jan-2018
2018-01-25 | W | 04 | - | 2018 | W04-2018 | Jan-2018
2018-01-26 | W | 04 | - | 2018 | W04-2018 | Jan-2018
2018-01-27 | W | 04 | - | 2018 | W04-2018 | Jan-2018
2018-01-28 | W | 05 | - | 2018 | W05-2018 | Jan-2018
2018-01-29 | W | 05 | - | 2018 | W05-2018 | Jan-2018
2018-01-30 | W | 05 | - | 2018 | W05-2018 | Jan-2018
2018-01-31 | W | 05 | - | 2018 | W05-2018 | Jan-2018
2018-02-01 | W | 05 | - | 2018 | W05-2018 | Feb-2018
2018-02-02 | W | 05 | - | 2018 | W05-2018 | Feb-2018
2018-02-03 | W | 05 | - | 2018 | W05-2018 | Feb-2018
2018-02-04 | W | 06 | - | 2018 | W06-2018 | Feb-2018
2018-02-05 | W | 06 | - | 2018 | W06-2018 | Feb-2018
2018-02-06 | W | 06 | - | 2018 | W06-2018 | Feb-2018
2018-02-07 | W | 06 | - | 2018 | W06-2018 | Feb-2018
2018-02-08 | W | 06 | - | 2018 | W06-2018 | Feb-2018
2018-02-09 | W | 06 | - | 2018 | W06-2018 | Feb-2018
2018-02-10 | W | 06 | - | 2018 | W06-2018 | Feb-2018
2018-02-11 | W | 07 | - | 2018 | W07-2018 | Feb-2018
2018-02-12 | W | 07 | - | 2018 | W07-2018 | Feb-2018
2018-02-13 | W | 07 | - | 2018 | W07-2018 | Feb-2018
2018-02-14 | W | 07 | - | 2018 | W07-2018 | Feb-2018
2018-02-15 | W | 07 | - | 2018 | W07-2018 | Feb-2018
2018-02-16 | W | 07 | - | 2018 | W07-2018 | Feb-2018
2018-02-17 | W | 07 | - | 2018 | W07-2018 | Feb-2018
2018-02-18 | W | 08 | - | 2018 | W08-2018 | Feb-2018
2018-02-19 | W | 08 | - | 2018 | W08-2018 | Feb-2018
2018-02-20 | W | 08 | - | 2018 | W08-2018 | Feb-2018
2018-02-21 | W | 08 | - | 2018 | W08-2018 | Feb-2018
2018-02-22 | W | 08 | - | 2018 | W08-2018 | Feb-2018
2018-02-23 | W | 08 | - | 2018 | W08-2018 | Feb-2018
2018-02-24 | W | 08 | - | 2018 | W08-2018 | Feb-2018
2018-02-25 | W | 09 | - | 2018 | W09-2018 | Feb-2018
2018-02-26 | W | 09 | - | 2018 | W09-2018 | Feb-2018
2018-02-27 | W | 09 | - | 2018 | W09-2018 | Feb-2018
2018-02-28 | W | 09 | - | 2018 | W09-2018 | Feb-2018
2018-03-01 | W | 09 | - | 2018 | W09-2018 | Mar-2018
2018-03-02 | W | 09 | - | 2018 | W09-2018 | Mar-2018
2018-03-03 | W | 09 | - | 2018 | W09-2018 | Mar-2018
2018-03-04 | W | 10 | - | 2018 | W10-2018 | Mar-2018
2018-03-05 | W | 10 | - | 2018 | W10-2018 | Mar-2018
2018-03-06 | W | 10 | - | 2018 | W10-2018 | Mar-2018
2018-03-07 | W | 10 | - | 2018 | W10-2018 | Mar-2018
2018-03-08 | W | 10 | - | 2018 | W10-2018 | Mar-2018
2018-03-09 | W | 10 | - | 2018 | W10-2018 | Mar-2018
2018-03-10 | W | 10 | - | 2018 | W10-2018 | Mar-2018
2018-03-11 | W | 11 | - | 2018 | W11-2018 | Mar-2018
2018-03-12 | W | 11 | - | 2018 | W11-2018 | Mar-2018
2018-03-13 | W | 11 | - | 2018 | W11-2018 | Mar-2018
2018-03-14 | W | 11 | - | 2018 | W11-2018 | Mar-2018
2018-03-15 | W | 11 | - | 2018 | W11-2018 | Mar-2018
2018-03-16 | W | 11 | - | 2018 | W11-2018 | Mar-2018
2018-03-17 | W | 11 | - | 2018 | W11-2018 | Mar-2018
2018-03-18 | W | 12 | - | 2018 | W12-2018 | Mar-2018
2018-03-19 | W | 12 | - | 2018 | W12-2018 | Mar-2018
2018-03-20 | W | 12 | - | 2018 | W12-2018 | Mar-2018
2018-03-21 | W | 12 | - | 2018 | W12-2018 | Mar-2018
2018-03-22 | W | 12 | - | 2018 | W12-2018 | Mar-2018
2018-03-23 | W | 12 | - | 2018 | W12-2018 | Mar-2018
2018-03-24 | W | 12 | - | 2018 | W12-2018 | Mar-2018
2018-03-25 | W | 13 | - | 2018 | W13-2018 | Mar-2018
2018-03-26 | W | 13 | - | 2018 | W13-2018 | Mar-2018
2018-03-27 | W | 13 | - | 2018 | W13-2018 | Mar-2018
2018-03-28 | W | 13 | - | 2018 | W13-2018 | Mar-2018
2018-03-29 | W | 13 | - | 2018 | W13-2018 | Mar-2018
2018-03-30 | W | 13 | - | 2018 | W13-2018 | Mar-2018
2018-03-31 | W | 13 | - | 2018 | W13-2018 | Mar-2018
2018-04-01 | W | 14 | - | 2018 | W14-2018 | Apr-2018
2018-04-02 | W | 14 | - | 2018 | W14-2018 | Apr-2018
2018-04-03 | W | 14 | - | 2018 | W14-2018 | Apr-2018
2018-04-04 | W | 14 | - | 2018 | W14-2018 | Apr-2018
2018-04-05 | W | 14 | - | 2018 | W14-2018 | Apr-2018
2018-04-06 | W | 14 | - | 2018 | W14-2018 | Apr-2018
2018-04-07 | W | 14 | - | 2018 | W14-2018 | Apr-2018
2018-04-08 | W | 15 | - | 2018 | W15-2018 | Apr-2018
2018-04-09 | W | 15 | - | 2018 | W15-2018 | Apr-2018
2018-04-10 | W | 15 | - | 2018 | W15-2018 | Apr-2018
2018-04-11 | W | 15 | - | 2018 | W15-2018 | Apr-2018
2018-04-12 | W | 15 | - | 2018 | W15-2018 | Apr-2018
2018-04-13 | W | 15 | - | 2018 | W15-2018 | Apr-2018
2018-04-14 | W | 15 | - | 2018 | W15-2018 | Apr-2018
2018-04-15 | W | 16 | - | 2018 | W16-2018 | Apr-2018
2018-04-16 | W | 16 | - | 2018 | W16-2018 | Apr-2018
2018-04-17 | W | 16 | - | 2018 | W16-2018 | Apr-2018
2018-04-18 | W | 16 | - | 2018 | W16-2018 | Apr-2018
2018-04-19 | W | 16 | - | 2018 | W16-2018 | Apr-2018
2018-04-20 | W | 16 | - | 2018 | W16-2018 | Apr-2018
2018-04-21 | W | 16 | - | 2018 | W16-2018 | Apr-2018
2018-04-22 | W | 17 | - | 2018 | W17-2018 | Apr-2018
2018-04-23 | W | 17 | - | 2018 | W17-2018 | Apr-2018
2018-04-24 | W | 17 | - | 2018 | W17-2018 | Apr-2018
2018-04-25 | W | 17 | - | 2018 | W17-2018 | Apr-2018
2018-04-26 | W | 17 | - | 2018 | W17-2018 | Apr-2018
2018-04-27 | W | 17 | - | 2018 | W17-2018 | Apr-2018
2018-04-28 | W | 17 | - | 2018 | W17-2018 | Apr-2018
2018-04-29 | W | 18 | - | 2018 | W18-2018 | Apr-2018
2018-04-30 | W | 18 | - | 2018 | W18-2018 | Apr-2018
2018-05-01 | W | 18 | - | 2018 | W18-2018 | May-2018
2018-05-02 | W | 18 | - | 2018 | W18-2018 | May-2018
2018-05-03 | W | 18 | - | 2018 | W18-2018 | May-2018
2018-05-04 | W | 18 | - | 2018 | W18-2018 | May-2018
2018-05-05 | W | 18 | - | 2018 | W18-2018 | May-2018
2018-05-06 | W | 19 | - | 2018 | W19-2018 | May-2018
2018-05-07 | W | 19 | - | 2018 | W19-2018 | May-2018
2018-05-08 | W | 19 | - | 2018 | W19-2018 | May-2018
2018-05-09 | W | 19 | - | 2018 | W19-2018 | May-2018
2018-05-10 | W | 19 | - | 2018 | W19-2018 | May-2018
2018-05-11 | W | 19 | - | 2018 | W19-2018 | May-2018
2018-05-12 | W | 19 | - | 2018 | W19-2018 | May-2018
2018-05-13 | W | 20 | - | 2018 | W20-2018 | May-2018
2018-05-14 | W | 20 | - | 2018 | W20-2018 | May-2018
2018-05-15 | W | 20 | - | 2018 | W20-2018 | May-2018
2018-05-16 | W | 20 | - | 2018 | W20-2018 | May-2018
2018-05-17 | W | 20 | - | 2018 | W20-2018 | May-2018
2018-05-18 | W | 20 | - | 2018 | W20-2018 | May-2018
2018-05-19 | W | 20 | - | 2018 | W20-2018 | May-2018
2018-05-20 | W | 21 | - | 2018 | W21-2018 | May-2018
2018-05-21 | W | 21 | - | 2018 | W21-2018 | May-2018
2018-05-22 | W | 21 | - | 2018 | W21-2018 | May-2018
2018-05-23 | W | 21 | - | 2018 | W21-2018 | May-2018
2018-05-24 | W | 21 | - | 2018 | W21-2018 | May-2018
2018-05-25 | W | 21 | - | 2018 | W21-2018 | May-2018
2018-05-26 | W | 21 | - | 2018 | W21-2018 | May-2018
2018-05-27 | W | 22 | - | 2018 | W22-2018 | May-2018
2018-05-28 | W | 22 | - | 2018 | W22-2018 | May-2018
2018-05-29 | W | 22 | - | 2018 | W22-2018 | May-2018
2018-05-30 | W | 22 | - | 2018 | W22-2018 | May-2018
2018-05-31 | W | 22 | - | 2018 | W22-2018 | May-2018
2018-06-01 | W | 22 | - | 2018 | W22-2018 | Jun-2018
2018-06-02 | W | 22 | - | 2018 | W22-2018 | Jun-2018
2018-06-03 | W | 23 | - | 2018 | W23-2018 | Jun-2018
2018-06-04 | W | 23 | - | 2018 | W23-2018 | Jun-2018
2018-06-05 | W | 23 | - | 2018 | W23-2018 | Jun-2018
2018-06-06 | W | 23 | - | 2018 | W23-2018 | Jun-2018
2018-06-07 | W | 23 | - | 2018 | W23-2018 | Jun-2018
2018-06-08 | W | 23 | - | 2018 | W23-2018 | Jun-2018
2018-06-09 | W | 23 | - | 2018 | W23-2018 | Jun-2018
2018-06-10 | W | 24 | - | 2018 | W24-2018 | Jun-2018
2018-06-11 | W | 24 | - | 2018 | W24-2018 | Jun-2018
2018-06-12 | W | 24 | - | 2018 | W24-2018 | Jun-2018
2018-06-13 | W | 24 | - | 2018 | W24-2018 | Jun-2018
2018-06-14 | W | 24 | - | 2018 | W24-2018 | Jun-2018
2018-06-15 | W | 24 | - | 2018 | W24-2018 | Jun-2018
2018-06-16 | W | 24 | - | 2018 | W24-2018 | Jun-2018
2018-06-17 | W | 25 | - | 2018 | W25-2018 | Jun-2018
2018-06-18 | W | 25 | - | 2018 | W25-2018 | Jun-2018
2018-06-19 | W | 25 | - | 2018 | W25-2018 | Jun-2018
2018-06-20 | W | 25 | - | 2018 | W25-2018 | Jun-2018
2018-06-21 | W | 25 | - | 2018 | W25-2018 | Jun-2018
2018-06-22 | W | 25 | - | 2018 | W25-2018 | Jun-2018
2018-06-23 | W | 25 | - | 2018 | W25-2018 | Jun-2018
2018-06-24 | W | 26 | - | 2018 | W26-2018 | Jun-2018
2018-06-25 | W | 26 | - | 2018 | W26-2018 | Jun-2018
2018-06-26 | W | 26 | - | 2018 | W26-2018 | Jun-2018
2018-06-27 | W | 26 | - | 2018 | W26-2018 | Jun-2018
2018-06-28 | W | 26 | - | 2018 | W26-2018 | Jun-2018
2018-06-29 | W | 26 | - | 2018 | W26-2018 | Jun-2018
2018-06-30 | W | 26 | - | 2018 | W26-2018 | Jun-2018
2018-07-01 | W | 27 | - | 2018 | W27-2018 | Jul-2018
2018-07-02 | W | 27 | - | 2018 | W27-2018 | Jul-2018
2018-07-03 | W | 27 | - | 2018 | W27-2018 | Jul-2018
2018-07-04 | W | 27 | - | 2018 | W27-2018 | Jul-2018
2018-07-05 | W | 27 | - | 2018 | W27-2018 | Jul-2018
2018-07-06 | W | 27 | - | 2018 | W27-2018 | Jul-2018
2018-07-07 | W | 27 | - | 2018 | W27-2018 | Jul-2018
2018-07-08 | W | 28 | - | 2018 | W28-2018 | Jul-2018
2018-07-09 | W | 28 | - | 2018 | W28-2018 | Jul-2018
2018-07-10 | W | 28 | - | 2018 | W28-2018 | Jul-2018
2018-07-11 | W | 28 | - | 2018 | W28-2018 | Jul-2018
2018-07-12 | W | 28 | - | 2018 | W28-2018 | Jul-2018
2018-07-13 | W | 28 | - | 2018 | W28-2018 | Jul-2018
2018-07-14 | W | 28 | - | 2018 | W28-2018 | Jul-2018
2018-07-15 | W | 29 | - | 2018 | W29-2018 | Jul-2018
2018-07-16 | W | 29 | - | 2018 | W29-2018 | Jul-2018
2018-07-17 | W | 29 | - | 2018 | W29-2018 | Jul-2018
2018-07-18 | W | 29 | - | 2018 | W29-2018 | Jul-2018
2018-07-19 | W | 29 | - | 2018 | W29-2018 | Jul-2018
2018-07-20 | W | 29 | - | 2018 | W29-2018 | Jul-2018
2018-07-21 | W | 29 | - | 2018 | W29-2018 | Jul-2018
2018-07-22 | W | 30 | - | 2018 | W30-2018 | Jul-2018
2018-07-23 | W | 30 | - | 2018 | W30-2018 | Jul-2018
2018-07-24 | W | 30 | - | 2018 | W30-2018 | Jul-2018
2018-07-25 | W | 30 | - | 2018 | W30-2018 | Jul-2018
2018-07-26 | W | 30 | - | 2018 | W30-2018 | Jul-2018
2018-07-27 | W | 30 | - | 2018 | W30-2018 | Jul-2018
2018-07-28 | W | 30 | - | 2018 | W30-2018 | Jul-2018
2018-07-29 | W | 31 | - | 2018 | W31-2018 | Jul-2018
2018-07-30 | W | 31 | - | 2018 | W31-2018 | Jul-2018
2018-07-31 | W | 31 | - | 2018 | W31-2018 | Jul-2018
2018-08-01 | W | 31 | - | 2018 | W31-2018 | Aug-2018
2018-08-02 | W | 31 | - | 2018 | W31-2018 | Aug-2018
2018-08-03 | W | 31 | - | 2018 | W31-2018 | Aug-2018
2018-08-04 | W | 31 | - | 2018 | W31-2018 | Aug-2018
2018-08-05 | W | 32 | - | 2018 | W32-2018 | Aug-2018
2018-08-06 | W | 32 | - | 2018 | W32-2018 | Aug-2018
2018-08-07 | W | 32 | - | 2018 | W32-2018 | Aug-2018
2018-08-08 | W | 32 | - | 2018 | W32-2018 | Aug-2018
2018-08-09 | W | 32 | - | 2018 | W32-2018 | Aug-2018
2018-08-10 | W | 32 | - | 2018 | W32-2018 | Aug-2018
2018-08-11 | W | 32 | - | 2018 | W32-2018 | Aug-2018
2018-08-12 | W | 33 | - | 2018 | W33-2018 | Aug-2018
2018-08-13 | W | 33 | - | 2018 | W33-2018 | Aug-2018
2018-08-14 | W | 33 | - | 2018 | W33-2018 | Aug-2018
2018-08-15 | W | 33 | - | 2018 | W33-2018 | Aug-2018
2018-08-16 | W | 33 | - | 2018 | W33-2018 | Aug-2018
2018-08-17 | W | 33 | - | 2018 | W33-2018 | Aug-2018
2018-08-18 | W | 33 | - | 2018 | W33-2018 | Aug-2018
2018-08-19 | W | 34 | - | 2018 | W34-2018 | Aug-2018
2018-08-20 | W | 34 | - | 2018 | W34-2018 | Aug-2018
2018-08-21 | W | 34 | - | 2018 | W34-2018 | Aug-2018
2018-08-22 | W | 34 | - | 2018 | W34-2018 | Aug-2018
2018-08-23 | W | 34 | - | 2018 | W34-2018 | Aug-2018
2018-08-24 | W | 34 | - | 2018 | W34-2018 | Aug-2018
2018-08-25 | W | 34 | - | 2018 | W34-2018 | Aug-2018
2018-08-26 | W | 35 | - | 2018 | W35-2018 | Aug-2018
2018-08-27 | W | 35 | - | 2018 | W35-2018 | Aug-2018
2018-08-28 | W | 35 | - | 2018 | W35-2018 | Aug-2018
2018-08-29 | W | 35 | - | 2018 | W35-2018 | Aug-2018
2018-08-30 | W | 35 | - | 2018 | W35-2018 | Aug-2018
2018-08-31 | W | 35 | - | 2018 | W35-2018 | Aug-2018
2018-09-01 | W | 35 | - | 2018 | W35-2018 | Sep-2018
2018-09-02 | W | 36 | - | 2018 | W36-2018 | Sep-2018
2018-09-03 | W | 36 | - | 2018 | W36-2018 | Sep-2018
2018-09-04 | W | 36 | - | 2018 | W36-2018 | Sep-2018
2018-09-05 | W | 36 | - | 2018 | W36-2018 | Sep-2018
2018-09-06 | W | 36 | - | 2018 | W36-2018 | Sep-2018
2018-09-07 | W | 36 | - | 2018 | W36-2018 | Sep-2018
2018-09-08 | W | 36 | - | 2018 | W36-2018 | Sep-2018
2018-09-09 | W | 37 | - | 2018 | W37-2018 | Sep-2018
2018-09-10 | W | 37 | - | 2018 | W37-2018 | Sep-2018
2018-09-11 | W | 37 | - | 2018 | W37-2018 | Sep-2018
2018-09-12 | W | 37 | - | 2018 | W37-2018 | Sep-2018
2018-09-13 | W | 37 | - | 2018 | W37-2018 | Sep-2018
2018-09-14 | W | 37 | - | 2018 | W37-2018 | Sep-2018
2018-09-15 | W | 37 | - | 2018 | W37-2018 | Sep-2018
2018-09-16 | W | 38 | - | 2018 | W38-2018 | Sep-2018
2018-09-17 | W | 38 | - | 2018 | W38-2018 | Sep-2018
2018-09-18 | W | 38 | - | 2018 | W38-2018 | Sep-2018
2018-09-19 | W | 38 | - | 2018 | W38-2018 | Sep-2018
2018-09-20 | W | 38 | - | 2018 | W38-2018 | Sep-2018
2018-09-21 | W | 38 | - | 2018 | W38-2018 | Sep-2018
2018-09-22 | W | 38 | - | 2018 | W38-2018 | Sep-2018
2018-09-23 | W | 39 | - | 2018 | W39-2018 | Sep-2018
2018-09-24 | W | 39 | - | 2018 | W39-2018 | Sep-2018
2018-09-25 | W | 39 | - | 2018 | W39-2018 | Sep-2018
2018-09-26 | W | 39 | - | 2018 | W39-2018 | Sep-2018
2018-09-27 | W | 39 | - | 2018 | W39-2018 | Sep-2018
2018-09-28 | W | 39 | - | 2018 | W39-2018 | Sep-2018
2018-09-29 | W | 39 | - | 2018 | W39-2018 | Sep-2018
2018-09-30 | W | 40 | - | 2018 | W40-2018 | Sep-2018
2018-10-01 | W | 40 | - | 2018 | W40-2018 | Oct-2018
2018-10-02 | W | 40 | - | 2018 | W40-2018 | Oct-2018
2018-10-03 | W | 40 | - | 2018 | W40-2018 | Oct-2018
2018-10-04 | W | 40 | - | 2018 | W40-2018 | Oct-2018
2018-10-05 | W | 40 | - | 2018 | W40-2018 | Oct-2018
2018-10-06 | W | 40 | - | 2018 | W40-2018 | Oct-2018
2018-10-07 | W | 41 | - | 2018 | W41-2018 | Oct-2018
2018-10-08 | W | 41 | - | 2018 | W41-2018 | Oct-2018
2018-10-09 | W | 41 | - | 2018 | W41-2018 | Oct-2018
2018-10-10 | W | 41 | - | 2018 | W41-2018 | Oct-2018
2018-10-11 | W | 41 | - | 2018 | W41-2018 | Oct-2018
2018-10-12 | W | 41 | - | 2018 | W41-2018 | Oct-2018
2018-10-13 | W | 41 | - | 2018 | W41-2018 | Oct-2018
2018-10-14 | W | 42 | - | 2018 | W42-2018 | Oct-2018
2018-10-15 | W | 42 | - | 2018 | W42-2018 | Oct-2018
2018-10-16 | W | 42 | - | 2018 | W42-2018 | Oct-2018
2018-10-17 | W | 42 | - | 2018 | W42-2018 | Oct-2018
2018-10-18 | W | 42 | - | 2018 | W42-2018 | Oct-2018
2018-10-19 | W | 42 | - | 2018 | W42-2018 | Oct-2018
2018-10-20 | W | 42 | - | 2018 | W42-2018 | Oct-2018
2018-10-21 | W | 43 | - | 2018 | W43-2018 | Oct-2018
2018-10-22 | W | 43 | - | 2018 | W43-2018 | Oct-2018
2018-10-23 | W | 43 | - | 2018 | W43-2018 | Oct-2018
2018-10-24 | W | 43 | - | 2018 | W43-2018 | Oct-2018
2018-10-25 | W | 43 | - | 2018 | W43-2018 | Oct-2018
2018-10-26 | W | 43 | - | 2018 | W43-2018 | Oct-2018
2018-10-27 | W | 43 | - | 2018 | W43-2018 | Oct-2018
2018-10-28 | W | 44 | - | 2018 | W44-2018 | Oct-2018
2018-10-29 | W | 44 | - | 2018 | W44-2018 | Oct-2018
2018-10-30 | W | 44 | - | 2018 | W44-2018 | Oct-2018
2018-10-31 | W | 44 | - | 2018 | W44-2018 | Oct-2018
2018-11-01 | W | 44 | - | 2018 | W44-2018 | Nov-2018
2018-11-02 | W | 44 | - | 2018 | W44-2018 | Nov-2018
2018-11-03 | W | 44 | - | 2018 | W44-2018 | Nov-2018
2018-11-04 | W | 45 | - | 2018 | W45-2018 | Nov-2018
2018-11-05 | W | 45 | - | 2018 | W45-2018 | Nov-2018
2018-11-06 | W | 45 | - | 2018 | W45-2018 | Nov-2018
2018-11-07 | W | 45 | - | 2018 | W45-2018 | Nov-2018
2018-11-08 | W | 45 | - | 2018 | W45-2018 | Nov-2018
2018-11-09 | W | 45 | - | 2018 | W45-2018 | Nov-2018
2018-11-10 | W | 45 | - | 2018 | W45-2018 | Nov-2018
2018-11-11 | W | 46 | - | 2018 | W46-2018 | Nov-2018
2018-11-12 | W | 46 | - | 2018 | W46-2018 | Nov-2018
2018-11-13 | W | 46 | - | 2018 | W46-2018 | Nov-2018
2018-11-14 | W | 46 | - | 2018 | W46-2018 | Nov-2018
2018-11-15 | W | 46 | - | 2018 | W46-2018 | Nov-2018
2018-11-16 | W | 46 | - | 2018 | W46-2018 | Nov-2018
2018-11-17 | W | 46 | - | 2018 | W46-2018 | Nov-2018
2018-11-18 | W | 47 | - | 2018 | W47-2018 | Nov-2018
2018-11-19 | W | 47 | - | 2018 | W47-2018 | Nov-2018
2018-11-20 | W | 47 | - | 2018 | W47-2018 | Nov-2018
2018-11-21 | W | 47 | - | 2018 | W47-2018 | Nov-2018
2018-11-22 | W | 47 | - | 2018 | W47-2018 | Nov-2018
2018-11-23 | W | 47 | - | 2018 | W47-2018 | Nov-2018
2018-11-24 | W | 47 | - | 2018 | W47-2018 | Nov-2018
2018-11-25 | W | 48 | - | 2018 | W48-2018 | Nov-2018
2018-11-26 | W | 48 | - | 2018 | W48-2018 | Nov-2018
2018-11-27 | W | 48 | - | 2018 | W48-2018 | Nov-2018
2018-11-28 | W | 48 | - | 2018 | W48-2018 | Nov-2018
2018-11-29 | W | 48 | - | 2018 | W48-2018 | Nov-2018
2018-11-30 | W | 48 | - | 2018 | W48-2018 | Nov-2018
2018-12-01 | W | 48 | - | 2018 | W48-2018 | Dec-2018
2018-12-02 | W | 49 | - | 2018 | W49-2018 | Dec-2018
2018-12-03 | W | 49 | - | 2018 | W49-2018 | Dec-2018
2018-12-04 | W | 49 | - | 2018 | W49-2018 | Dec-2018
2018-12-05 | W | 49 | - | 2018 | W49-2018 | Dec-2018
2018-12-06 | W | 49 | - | 2018 | W49-2018 | Dec-2018
2018-12-07 | W | 49 | - | 2018 | W49-2018 | Dec-2018
2018-12-08 | W | 49 | - | 2018 | W49-2018 | Dec-2018
2018-12-09 | W | 50 | - | 2018 | W50-2018 | Dec-2018
2018-12-10 | W | 50 | - | 2018 | W50-2018 | Dec-2018
2018-12-11 | W | 50 | - | 2018 | W50-2018 | Dec-2018
2018-12-12 | W | 50 | - | 2018 | W50-2018 | Dec-2018
2018-12-13 | W | 50 | - | 2018 | W50-2018 | Dec-2018
2018-12-14 | W | 50 | - | 2018 | W50-2018 | Dec-2018
2018-12-15 | W | 50 | - | 2018 | W50-2018 | Dec-2018
2018-12-16 | W | 51 | - | 2018 | W51-2018 | Dec-2018
2018-12-17 | W | 51 | - | 2018 | W51-2018 | Dec-2018
2018-12-18 | W | 51 | - | 2018 | W51-2018 | Dec-2018
2018-12-19 | W | 51 | - | 2018 | W51-2018 | Dec-2018
2018-12-20 | W | 51 | - | 2018 | W51-2018 | Dec-2018
2018-12-21 | W | 51 | - | 2018 | W51-2018 | Dec-2018
2018-12-22 | W | 51 | - | 2018 | W51-2018 | Dec-2018
2018-12-23 | W | 52 | - | 2018 | W52-2018 | Dec-2018
2018-12-24 | W | 52 | - | 2018 | W52-2018 | Dec-2018
2018-12-25 | W | 52 | - | 2018 | W52-2018 | Dec-2018
2018-12-26 | W | 52 | - | 2018 | W52-2018 | Dec-2018
2018-12-27 | W | 52 | - | 2018 | W52-2018 | Dec-2018
2018-12-28 | W | 52 | - | 2018 | W52-2018 | Dec-2018
2018-12-29 | W | 52 | - | 2018 | W52-2018 | Dec-2018
2018-12-30 | W | 52 | - | 2018 | W52-2018 | Dec-2018
2018-12-31 | W | 52 | - | 2018 | W52-2018 | Dec-2018
ULK | W | ULK |  | ULK | ULK | ULK
Done | W | Done | - | Done | Done | Done
2019-01-01 | W | 01 | - | 2019 | W01-2019 | Jan-2019
2019-01-02 | W | 01 | - | 2019 | W01-2019 | Jan-2019
2019-01-03 | W | 01 | - | 2019 | W01-2019 | Jan-2019
2019-01-04 | W | 01 | - | 2019 | W01-2019 | Jan-2019
2019-01-05 | W | 01 | - | 2019 | W01-2019 | Jan-2019
2019-01-06 | W | 02 | - | 2019 | W02-2019 | Jan-2019
2019-01-07 | W | 02 | - | 2019 | W02-2019 | Jan-2019
2019-01-08 | W | 02 | - | 2019 | W02-2019 | Jan-2019
2019-01-09 | W | 02 | - | 2019 | W02-2019 | Jan-2019
2019-01-10 | W | 02 | - | 2019 | W02-2019 | Jan-2019
2019-01-11 | W | 02 | - | 2019 | W02-2019 | Jan-2019
2019-01-12 | W | 02 | - | 2019 | W02-2019 | Jan-2019
2019-01-13 | W | 03 | - | 2019 | W03-2019 | Jan-2019
2019-01-14 | W | 03 | - | 2019 | W03-2019 | Jan-2019
2019-01-15 | W | 03 | - | 2019 | W03-2019 | Jan-2019
2019-01-16 | W | 03 | - | 2019 | W03-2019 | Jan-2019
2019-01-17 | W | 03 | - | 2019 | W03-2019 | Jan-2019
2019-01-18 | W | 03 | - | 2019 | W03-2019 | Jan-2019
2019-01-19 | W | 03 | - | 2019 | W03-2019 | Jan-2019
2019-01-20 | W | 04 | - | 2019 | W04-2019 | Jan-2019
2019-01-21 | W | 04 | - | 2019 | W04-2019 | Jan-2019
2019-01-22 | W | 04 | - | 2019 | W04-2019 | Jan-2019
2019-01-23 | W | 04 | - | 2019 | W04-2019 | Jan-2019
2019-01-24 | W | 04 | - | 2019 | W04-2019 | Jan-2019
2019-01-25 | W | 04 | - | 2019 | W04-2019 | Jan-2019
2019-01-26 | W | 04 | - | 2019 | W04-2019 | Jan-2019
2019-01-27 | W | 05 | - | 2019 | W05-2019 | Jan-2019
2019-01-28 | W | 05 | - | 2019 | W05-2019 | Jan-2019
2019-01-29 | W | 05 | - | 2019 | W05-2019 | Jan-2019
2019-01-30 | W | 05 | - | 2019 | W05-2019 | Jan-2019
2019-01-31 | W | 05 | - | 2019 | W05-2019 | Jan-2019
2019-02-01 | W | 05 | - | 2019 | W05-2019 | Feb-2019
2019-02-02 | W | 05 | - | 2019 | W05-2019 | Feb-2019
2019-02-03 | W | 06 | - | 2019 | W06-2019 | Feb-2019
2019-02-04 | W | 06 | - | 2019 | W06-2019 | Feb-2019
2019-02-05 | W | 06 | - | 2019 | W06-2019 | Feb-2019
2019-02-06 | W | 06 | - | 2019 | W06-2019 | Feb-2019
2019-02-07 | W | 06 | - | 2019 | W06-2019 | Feb-2019
2019-02-08 | W | 06 | - | 2019 | W06-2019 | Feb-2019
2019-02-09 | W | 06 | - | 2019 | W06-2019 | Feb-2019
2019-02-10 | W | 07 | - | 2019 | W07-2019 | Feb-2019
2019-02-11 | W | 07 | - | 2019 | W07-2019 | Feb-2019
2019-02-12 | W | 07 | - | 2019 | W07-2019 | Feb-2019
2019-02-13 | W | 07 | - | 2019 | W07-2019 | Feb-2019
2019-02-14 | W | 07 | - | 2019 | W07-2019 | Feb-2019
2019-02-15 | W | 07 | - | 2019 | W07-2019 | Feb-2019
2019-02-16 | W | 07 | - | 2019 | W07-2019 | Feb-2019
2019-02-17 | W | 08 | - | 2019 | W08-2019 | Feb-2019
2019-02-18 | W | 08 | - | 2019 | W08-2019 | Feb-2019
2019-02-19 | W | 08 | - | 2019 | W08-2019 | Feb-2019
2019-02-20 | W | 08 | - | 2019 | W08-2019 | Feb-2019
2019-02-21 | W | 08 | - | 2019 | W08-2019 | Feb-2019
2019-02-22 | W | 08 | - | 2019 | W08-2019 | Feb-2019
2019-02-23 | W | 08 | - | 2019 | W08-2019 | Feb-2019
2019-02-24 | W | 09 | - | 2019 | W09-2019 | Feb-2019
2019-02-25 | W | 09 | - | 2019 | W09-2019 | Feb-2019
2019-02-26 | W | 09 | - | 2019 | W09-2019 | Feb-2019
2019-02-27 | W | 09 | - | 2019 | W09-2019 | Feb-2019
2019-02-28 | W | 09 | - | 2019 | W09-2019 | Feb-2019
2019-03-01 | W | 09 | - | 2019 | W09-2019 | Mar-2019
2019-03-02 | W | 09 | - | 2019 | W09-2019 | Mar-2019
2019-03-03 | W | 10 | - | 2019 | W10-2019 | Mar-2019
2019-03-04 | W | 10 | - | 2019 | W10-2019 | Mar-2019
2019-03-05 | W | 10 | - | 2019 | W10-2019 | Mar-2019
2019-03-06 | W | 10 | - | 2019 | W10-2019 | Mar-2019
2019-03-07 | W | 10 | - | 2019 | W10-2019 | Mar-2019
2019-03-08 | W | 10 | - | 2019 | W10-2019 | Mar-2019
2019-03-09 | W | 10 | - | 2019 | W10-2019 | Mar-2019
2019-03-10 | W | 11 | - | 2019 | W11-2019 | Mar-2019
2019-03-11 | W | 11 | - | 2019 | W11-2019 | Mar-2019
2019-03-12 | W | 11 | - | 2019 | W11-2019 | Mar-2019
2019-03-13 | W | 11 | - | 2019 | W11-2019 | Mar-2019
2019-03-14 | W | 11 | - | 2019 | W11-2019 | Mar-2019
2019-03-15 | W | 11 | - | 2019 | W11-2019 | Mar-2019
2019-03-16 | W | 11 | - | 2019 | W11-2019 | Mar-2019
2019-03-17 | W | 12 | - | 2019 | W12-2019 | Mar-2019
2019-03-18 | W | 12 | - | 2019 | W12-2019 | Mar-2019
2019-03-19 | W | 12 | - | 2019 | W12-2019 | Mar-2019
2019-03-20 | W | 12 | - | 2019 | W12-2019 | Mar-2019
2019-03-21 | W | 12 | - | 2019 | W12-2019 | Mar-2019
2019-03-22 | W | 12 | - | 2019 | W12-2019 | Mar-2019
2019-03-23 | W | 12 | - | 2019 | W12-2019 | Mar-2019
2019-03-24 | W | 13 | - | 2019 | W13-2019 | Mar-2019
2019-03-25 | W | 13 | - | 2019 | W13-2019 | Mar-2019
2019-03-26 | W | 13 | - | 2019 | W13-2019 | Mar-2019
2019-03-27 | W | 13 | - | 2019 | W13-2019 | Mar-2019
2019-03-28 | W | 13 | - | 2019 | W13-2019 | Mar-2019
2019-03-29 | W | 13 | - | 2019 | W13-2019 | Mar-2019
2019-03-30 | W | 13 | - | 2019 | W13-2019 | Mar-2019
2019-03-31 | W | 14 | - | 2019 | W14-2019 | Mar-2019
2019-04-01 | W | 14 | - | 2019 | W14-2019 | Apr-2019
2019-04-02 | W | 14 | - | 2019 | W14-2019 | Apr-2019
2019-04-03 | W | 14 | - | 2019 | W14-2019 | Apr-2019
2019-04-04 | W | 14 | - | 2019 | W14-2019 | Apr-2019
2019-04-05 | W | 14 | - | 2019 | W14-2019 | Apr-2019
2019-04-06 | W | 14 | - | 2019 | W14-2019 | Apr-2019
2019-04-07 | W | 15 | - | 2019 | W15-2019 | Apr-2019
2019-04-08 | W | 15 | - | 2019 | W15-2019 | Apr-2019
2019-04-09 | W | 15 | - | 2019 | W15-2019 | Apr-2019
2019-04-10 | W | 15 | - | 2019 | W15-2019 | Apr-2019
2019-04-11 | W | 15 | - | 2019 | W15-2019 | Apr-2019
2019-04-12 | W | 15 | - | 2019 | W15-2019 | Apr-2019
2019-04-13 | W | 15 | - | 2019 | W15-2019 | Apr-2019
2019-04-14 | W | 16 | - | 2019 | W16-2019 | Apr-2019
2019-04-15 | W | 16 | - | 2019 | W16-2019 | Apr-2019
2019-04-16 | W | 16 | - | 2019 | W16-2019 | Apr-2019
2019-04-17 | W | 16 | - | 2019 | W16-2019 | Apr-2019
2019-04-18 | W | 16 | - | 2019 | W16-2019 | Apr-2019
2019-04-19 | W | 16 | - | 2019 | W16-2019 | Apr-2019
2019-04-20 | W | 16 | - | 2019 | W16-2019 | Apr-2019
2019-04-21 | W | 17 | - | 2019 | W17-2019 | Apr-2019
2019-04-22 | W | 17 | - | 2019 | W17-2019 | Apr-2019
2019-04-23 | W | 17 | - | 2019 | W17-2019 | Apr-2019
2019-04-24 | W | 17 | - | 2019 | W17-2019 | Apr-2019
2019-04-25 | W | 17 | - | 2019 | W17-2019 | Apr-2019
2019-04-26 | W | 17 | - | 2019 | W17-2019 | Apr-2019
2019-04-27 | W | 17 | - | 2019 | W17-2019 | Apr-2019
2019-04-28 | W | 18 | - | 2019 | W18-2019 | Apr-2019
2019-04-29 | W | 18 | - | 2019 | W18-2019 | Apr-2019
2019-04-30 | W | 18 | - | 2019 | W18-2019 | Apr-2019
2019-05-01 | W | 18 | - | 2019 | W18-2019 | May-2019
2019-05-02 | W | 18 | - | 2019 | W18-2019 | May-2019
2019-05-03 | W | 18 | - | 2019 | W18-2019 | May-2019
2019-05-04 | W | 18 | - | 2019 | W18-2019 | May-2019
2019-05-05 | W | 19 | - | 2019 | W19-2019 | May-2019
2019-05-06 | W | 19 | - | 2019 | W19-2019 | May-2019
2019-05-07 | W | 19 | - | 2019 | W19-2019 | May-2019
2019-05-08 | W | 19 | - | 2019 | W19-2019 | May-2019
2019-05-09 | W | 19 | - | 2019 | W19-2019 | May-2019
2019-05-10 | W | 19 | - | 2019 | W19-2019 | May-2019
2019-05-11 | W | 19 | - | 2019 | W19-2019 | May-2019
2019-05-12 | W | 20 | - | 2019 | W20-2019 | May-2019
2019-05-13 | W | 20 | - | 2019 | W20-2019 | May-2019
2019-05-14 | W | 20 | - | 2019 | W20-2019 | May-2019
2019-05-15 | W | 20 | - | 2019 | W20-2019 | May-2019
2019-05-16 | W | 20 | - | 2019 | W20-2019 | May-2019
2019-05-17 | W | 20 | - | 2019 | W20-2019 | May-2019
2019-05-18 | W | 20 | - | 2019 | W20-2019 | May-2019
2019-05-19 | W | 21 | - | 2019 | W21-2019 | May-2019
2019-05-20 | W | 21 | - | 2019 | W21-2019 | May-2019
2019-05-21 | W | 21 | - | 2019 | W21-2019 | May-2019
2019-05-22 | W | 21 | - | 2019 | W21-2019 | May-2019
2019-05-23 | W | 21 | - | 2019 | W21-2019 | May-2019
2019-05-24 | W | 21 | - | 2019 | W21-2019 | May-2019
2019-05-25 | W | 21 | - | 2019 | W21-2019 | May-2019
2019-05-26 | W | 22 | - | 2019 | W22-2019 | May-2019
2019-05-27 | W | 22 | - | 2019 | W22-2019 | May-2019
2019-05-28 | W | 22 | - | 2019 | W22-2019 | May-2019
2019-05-29 | W | 22 | - | 2019 | W22-2019 | May-2019
2019-05-30 | W | 22 | - | 2019 | W22-2019 | May-2019
2019-05-31 | W | 22 | - | 2019 | W22-2019 | May-2019
2019-06-01 | W | 22 | - | 2019 | W22-2019 | Jun-2019
2019-06-02 | W | 23 | - | 2019 | W23-2019 | Jun-2019
2019-06-03 | W | 23 | - | 2019 | W23-2019 | Jun-2019
2019-06-04 | W | 23 | - | 2019 | W23-2019 | Jun-2019
2019-06-05 | W | 23 | - | 2019 | W23-2019 | Jun-2019
2019-06-06 | W | 23 | - | 2019 | W23-2019 | Jun-2019
2019-06-07 | W | 23 | - | 2019 | W23-2019 | Jun-2019
2019-06-08 | W | 23 | - | 2019 | W23-2019 | Jun-2019
2019-06-09 | W | 24 | - | 2019 | W24-2019 | Jun-2019
2019-06-10 | W | 24 | - | 2019 | W24-2019 | Jun-2019
2019-06-11 | W | 24 | - | 2019 | W24-2019 | Jun-2019
2019-06-12 | W | 24 | - | 2019 | W24-2019 | Jun-2019
2019-06-13 | W | 24 | - | 2019 | W24-2019 | Jun-2019
2019-06-14 | W | 24 | - | 2019 | W24-2019 | Jun-2019
2019-06-15 | W | 24 | - | 2019 | W24-2019 | Jun-2019
2019-06-16 | W | 25 | - | 2019 | W25-2019 | Jun-2019
2019-06-17 | W | 25 | - | 2019 | W25-2019 | Jun-2019
2019-06-18 | W | 25 | - | 2019 | W25-2019 | Jun-2019
2019-06-19 | W | 25 | - | 2019 | W25-2019 | Jun-2019
2019-06-20 | W | 25 | - | 2019 | W25-2019 | Jun-2019
2019-06-21 | W | 25 | - | 2019 | W25-2019 | Jun-2019
2019-06-22 | W | 25 | - | 2019 | W25-2019 | Jun-2019
2019-06-23 | W | 26 | - | 2019 | W26-2019 | Jun-2019
2019-06-24 | W | 26 | - | 2019 | W26-2019 | Jun-2019
2019-06-25 | W | 26 | - | 2019 | W26-2019 | Jun-2019
2019-06-26 | W | 26 | - | 2019 | W26-2019 | Jun-2019
2019-06-27 | W | 26 | - | 2019 | W26-2019 | Jun-2019
2019-06-28 | W | 26 | - | 2019 | W26-2019 | Jun-2019
2019-06-29 | W | 26 | - | 2019 | W26-2019 | Jun-2019
2019-06-30 | W | 27 | - | 2019 | W27-2019 | Jun-2019
2019-07-01 | W | 27 | - | 2019 | W27-2019 | Jul-2019
2019-07-02 | W | 27 | - | 2019 | W27-2019 | Jul-2019
2019-07-03 | W | 27 | - | 2019 | W27-2019 | Jul-2019
2019-07-04 | W | 27 | - | 2019 | W27-2019 | Jul-2019
2019-07-05 | W | 27 | - | 2019 | W27-2019 | Jul-2019
2019-07-06 | W | 27 | - | 2019 | W27-2019 | Jul-2019
2019-07-07 | W | 28 | - | 2019 | W28-2019 | Jul-2019
2019-07-08 | W | 28 | - | 2019 | W28-2019 | Jul-2019
2019-07-09 | W | 28 | - | 2019 | W28-2019 | Jul-2019
2019-07-10 | W | 28 | - | 2019 | W28-2019 | Jul-2019
2019-07-11 | W | 28 | - | 2019 | W28-2019 | Jul-2019
2019-07-12 | W | 28 | - | 2019 | W28-2019 | Jul-2019
2019-07-13 | W | 28 | - | 2019 | W28-2019 | Jul-2019
2019-07-14 | W | 29 | - | 2019 | W29-2019 | Jul-2019
2019-07-15 | W | 29 | - | 2019 | W29-2019 | Jul-2019
2019-07-16 | W | 29 | - | 2019 | W29-2019 | Jul-2019
2019-07-17 | W | 29 | - | 2019 | W29-2019 | Jul-2019
2019-07-18 | W | 29 | - | 2019 | W29-2019 | Jul-2019
2019-07-19 | W | 29 | - | 2019 | W29-2019 | Jul-2019
2019-07-20 | W | 29 | - | 2019 | W29-2019 | Jul-2019
2019-07-21 | W | 30 | - | 2019 | W30-2019 | Jul-2019
2019-07-22 | W | 30 | - | 2019 | W30-2019 | Jul-2019
2019-07-23 | W | 30 | - | 2019 | W30-2019 | Jul-2019
2019-07-24 | W | 30 | - | 2019 | W30-2019 | Jul-2019
2019-07-25 | W | 30 | - | 2019 | W30-2019 | Jul-2019
2019-07-26 | W | 30 | - | 2019 | W30-2019 | Jul-2019
2019-07-27 | W | 30 | - | 2019 | W30-2019 | Jul-2019
2019-07-28 | W | 31 | - | 2019 | W31-2019 | Jul-2019
2019-07-29 | W | 31 | - | 2019 | W31-2019 | Jul-2019
2019-07-30 | W | 31 | - | 2019 | W31-2019 | Jul-2019
2019-07-31 | W | 31 | - | 2019 | W31-2019 | Jul-2019
2019-08-01 | W | 31 | - | 2019 | W31-2019 | Aug-2019
2019-08-02 | W | 31 | - | 2019 | W31-2019 | Aug-2019
2019-08-03 | W | 31 | - | 2019 | W31-2019 | Aug-2019
2019-08-04 | W | 32 | - | 2019 | W32-2019 | Aug-2019
2019-08-05 | W | 32 | - | 2019 | W32-2019 | Aug-2019
2019-08-06 | W | 32 | - | 2019 | W32-2019 | Aug-2019
2019-08-07 | W | 32 | - | 2019 | W32-2019 | Aug-2019
2019-08-08 | W | 32 | - | 2019 | W32-2019 | Aug-2019
2019-08-09 | W | 32 | - | 2019 | W32-2019 | Aug-2019
2019-08-10 | W | 32 | - | 2019 | W32-2019 | Aug-2019
2019-08-11 | W | 33 | - | 2019 | W33-2019 | Aug-2019
2019-08-12 | W | 33 | - | 2019 | W33-2019 | Aug-2019
2019-08-13 | W | 33 | - | 2019 | W33-2019 | Aug-2019
2019-08-14 | W | 33 | - | 2019 | W33-2019 | Aug-2019
2019-08-15 | W | 33 | - | 2019 | W33-2019 | Aug-2019
2019-08-16 | W | 33 | - | 2019 | W33-2019 | Aug-2019
2019-08-17 | W | 33 | - | 2019 | W33-2019 | Aug-2019
2019-08-18 | W | 34 | - | 2019 | W34-2019 | Aug-2019
2019-08-19 | W | 34 | - | 2019 | W34-2019 | Aug-2019
2019-08-20 | W | 34 | - | 2019 | W34-2019 | Aug-2019
2019-08-21 | W | 34 | - | 2019 | W34-2019 | Aug-2019
2019-08-22 | W | 34 | - | 2019 | W34-2019 | Aug-2019
2019-08-23 | W | 34 | - | 2019 | W34-2019 | Aug-2019
2019-08-24 | W | 34 | - | 2019 | W34-2019 | Aug-2019
2019-08-25 | W | 35 | - | 2019 | W35-2019 | Aug-2019
2019-08-26 | W | 35 | - | 2019 | W35-2019 | Aug-2019
2019-08-27 | W | 35 | - | 2019 | W35-2019 | Aug-2019
2019-08-28 | W | 35 | - | 2019 | W35-2019 | Aug-2019
2019-08-29 | W | 35 | - | 2019 | W35-2019 | Aug-2019
2019-08-30 | W | 35 | - | 2019 | W35-2019 | Aug-2019
2019-08-31 | W | 35 | - | 2019 | W35-2019 | Aug-2019
2019-09-01 | W | 36 | - | 2019 | W36-2019 | Sep-2019
2019-09-02 | W | 36 | - | 2019 | W36-2019 | Sep-2019
2019-09-03 | W | 36 | - | 2019 | W36-2019 | Sep-2019
2019-09-04 | W | 36 | - | 2019 | W36-2019 | Sep-2019
2019-09-05 | W | 36 | - | 2019 | W36-2019 | Sep-2019
2019-09-06 | W | 36 | - | 2019 | W36-2019 | Sep-2019
2019-09-07 | W | 36 | - | 2019 | W36-2019 | Sep-2019
2019-09-08 | W | 37 | - | 2019 | W37-2019 | Sep-2019
2019-09-09 | W | 37 | - | 2019 | W37-2019 | Sep-2019
2019-09-10 | W | 37 | - | 2019 | W37-2019 | Sep-2019
2019-09-11 | W | 37 | - | 2019 | W37-2019 | Sep-2019
2019-09-12 | W | 37 | - | 2019 | W37-2019 | Sep-2019
2019-09-13 | W | 37 | - | 2019 | W37-2019 | Sep-2019
2019-09-14 | W | 37 | - | 2019 | W37-2019 | Sep-2019
2019-09-15 | W | 38 | - | 2019 | W38-2019 | Sep-2019
2019-09-16 | W | 38 | - | 2019 | W38-2019 | Sep-2019
2019-09-17 | W | 38 | - | 2019 | W38-2019 | Sep-2019
2019-09-18 | W | 38 | - | 2019 | W38-2019 | Sep-2019
2019-09-19 | W | 38 | - | 2019 | W38-2019 | Sep-2019
2019-09-20 | W | 38 | - | 2019 | W38-2019 | Sep-2019
2019-09-21 | W | 38 | - | 2019 | W38-2019 | Sep-2019
2019-09-22 | W | 39 | - | 2019 | W39-2019 | Sep-2019
2019-09-23 | W | 39 | - | 2019 | W39-2019 | Sep-2019
2019-09-24 | W | 39 | - | 2019 | W39-2019 | Sep-2019
2019-09-25 | W | 39 | - | 2019 | W39-2019 | Sep-2019
2019-09-26 | W | 39 | - | 2019 | W39-2019 | Sep-2019
2019-09-27 | W | 39 | - | 2019 | W39-2019 | Sep-2019
2019-09-28 | W | 39 | - | 2019 | W39-2019 | Sep-2019
2019-09-29 | W | 40 | - | 2019 | W40-2019 | Sep-2019
2019-09-30 | W | 40 | - | 2019 | W40-2019 | Sep-2019
2019-10-01 | W | 40 | - | 2019 | W40-2019 | Oct-2019
2019-10-02 | W | 40 | - | 2019 | W40-2019 | Oct-2019
2019-10-03 | W | 40 | - | 2019 | W40-2019 | Oct-2019
2019-10-04 | W | 40 | - | 2019 | W40-2019 | Oct-2019
2019-10-05 | W | 40 | - | 2019 | W40-2019 | Oct-2019
2019-10-06 | W | 41 | - | 2019 | W41-2019 | Oct-2019
2019-10-07 | W | 41 | - | 2019 | W41-2019 | Oct-2019
2019-10-08 | W | 41 | - | 2019 | W41-2019 | Oct-2019
2019-10-09 | W | 41 | - | 2019 | W41-2019 | Oct-2019
2019-10-10 | W | 41 | - | 2019 | W41-2019 | Oct-2019
2019-10-11 | W | 41 | - | 2019 | W41-2019 | Oct-2019
2019-10-12 | W | 41 | - | 2019 | W41-2019 | Oct-2019
2019-10-13 | W | 42 | - | 2019 | W42-2019 | Oct-2019
2019-10-14 | W | 42 | - | 2019 | W42-2019 | Oct-2019
2019-10-15 | W | 42 | - | 2019 | W42-2019 | Oct-2019
2019-10-16 | W | 42 | - | 2019 | W42-2019 | Oct-2019
2019-10-17 | W | 42 | - | 2019 | W42-2019 | Oct-2019
2019-10-18 | W | 42 | - | 2019 | W42-2019 | Oct-2019
2019-10-19 | W | 42 | - | 2019 | W42-2019 | Oct-2019
2019-10-20 | W | 43 | - | 2019 | W43-2019 | Oct-2019
2019-10-21 | W | 43 | - | 2019 | W43-2019 | Oct-2019
2019-10-22 | W | 43 | - | 2019 | W43-2019 | Oct-2019
2019-10-23 | W | 43 | - | 2019 | W43-2019 | Oct-2019
2019-10-24 | W | 43 | - | 2019 | W43-2019 | Oct-2019
2019-10-25 | W | 43 | - | 2019 | W43-2019 | Oct-2019
2019-10-26 | W | 43 | - | 2019 | W43-2019 | Oct-2019
2019-10-27 | W | 44 | - | 2019 | W44-2019 | Oct-2019
2019-10-28 | W | 44 | - | 2019 | W44-2019 | Oct-2019
2019-10-29 | W | 44 | - | 2019 | W44-2019 | Oct-2019
2019-10-30 | W | 44 | - | 2019 | W44-2019 | Oct-2019
2019-10-31 | W | 44 | - | 2019 | W44-2019 | Oct-2019
2019-11-01 | W | 44 | - | 2019 | W44-2019 | Nov-2019
2019-11-02 | W | 44 | - | 2019 | W44-2019 | Nov-2019
2019-11-03 | W | 45 | - | 2019 | W45-2019 | Nov-2019
2019-11-04 | W | 45 | - | 2019 | W45-2019 | Nov-2019
2019-11-05 | W | 45 | - | 2019 | W45-2019 | Nov-2019
2019-11-06 | W | 45 | - | 2019 | W45-2019 | Nov-2019
2019-11-07 | W | 45 | - | 2019 | W45-2019 | Nov-2019
2019-11-08 | W | 45 | - | 2019 | W45-2019 | Nov-2019
2019-11-09 | W | 45 | - | 2019 | W45-2019 | Nov-2019
2019-11-10 | W | 46 | - | 2019 | W46-2019 | Nov-2019
2019-11-11 | W | 46 | - | 2019 | W46-2019 | Nov-2019
2019-11-12 | W | 46 | - | 2019 | W46-2019 | Nov-2019
2019-11-13 | W | 46 | - | 2019 | W46-2019 | Nov-2019
2019-11-14 | W | 46 | - | 2019 | W46-2019 | Nov-2019
2019-11-15 | W | 46 | - | 2019 | W46-2019 | Nov-2019
2019-11-16 | W | 46 | - | 2019 | W46-2019 | Nov-2019
2019-11-17 | W | 47 | - | 2019 | W47-2019 | Nov-2019
2019-11-18 | W | 47 | - | 2019 | W47-2019 | Nov-2019
2019-11-19 | W | 47 | - | 2019 | W47-2019 | Nov-2019
2019-11-20 | W | 47 | - | 2019 | W47-2019 | Nov-2019
2019-11-21 | W | 47 | - | 2019 | W47-2019 | Nov-2019
2019-11-22 | W | 47 | - | 2019 | W47-2019 | Nov-2019
2019-11-23 | W | 47 | - | 2019 | W47-2019 | Nov-2019
2019-11-24 | W | 48 | - | 2019 | W48-2019 | Nov-2019
2019-11-25 | W | 48 | - | 2019 | W48-2019 | Nov-2019
2019-11-26 | W | 48 | - | 2019 | W48-2019 | Nov-2019
2019-11-27 | W | 48 | - | 2019 | W48-2019 | Nov-2019
2019-11-28 | W | 48 | - | 2019 | W48-2019 | Nov-2019
2019-11-29 | W | 48 | - | 2019 | W48-2019 | Nov-2019
2019-11-30 | W | 48 | - | 2019 | W48-2019 | Nov-2019
2019-12-01 | W | 49 | - | 2019 | W49-2019 | Dec-2019
2019-12-02 | W | 49 | - | 2019 | W49-2019 | Dec-2019
2019-12-03 | W | 49 | - | 2019 | W49-2019 | Dec-2019
2019-12-04 | W | 49 | - | 2019 | W49-2019 | Dec-2019
2019-12-05 | W | 49 | - | 2019 | W49-2019 | Dec-2019
2019-12-06 | W | 49 | - | 2019 | W49-2019 | Dec-2019
2019-12-07 | W | 49 | - | 2019 | W49-2019 | Dec-2019
2019-12-08 | W | 50 | - | 2019 | W50-2019 | Dec-2019
2019-12-09 | W | 50 | - | 2019 | W50-2019 | Dec-2019
2019-12-10 | W | 50 | - | 2019 | W50-2019 | Dec-2019
2019-12-11 | W | 50 | - | 2019 | W50-2019 | Dec-2019
2019-12-12 | W | 50 | - | 2019 | W50-2019 | Dec-2019
2019-12-13 | W | 50 | - | 2019 | W50-2019 | Dec-2019
2019-12-14 | W | 50 | - | 2019 | W50-2019 | Dec-2019
2019-12-15 | W | 51 | - | 2019 | W51-2019 | Dec-2019
2019-12-16 | W | 51 | - | 2019 | W51-2019 | Dec-2019
2019-12-17 | W | 51 | - | 2019 | W51-2019 | Dec-2019
2019-12-18 | W | 51 | - | 2019 | W51-2019 | Dec-2019
2019-12-19 | W | 51 | - | 2019 | W51-2019 | Dec-2019
2019-12-20 | W | 51 | - | 2019 | W51-2019 | Dec-2019
2019-12-21 | W | 51 | - | 2019 | W51-2019 | Dec-2019
2019-12-22 | W | 52 | - | 2019 | W52-2019 | Dec-2019
2019-12-23 | W | 52 | - | 2019 | W52-2019 | Dec-2019
2019-12-24 | W | 52 | - | 2019 | W52-2019 | Dec-2019
2019-12-25 | W | 52 | - | 2019 | W52-2019 | Dec-2019
2019-12-26 | W | 52 | - | 2019 | W52-2019 | Dec-2019
2019-12-27 | W | 52 | - | 2019 | W52-2019 | Dec-2019
2019-12-28 | W | 52 | - | 2019 | W52-2019 | Dec-2019
2019-12-29 | W | 53 | - | 2019 | W53-2019 | Dec-2019
2019-12-30 | W | 53 | - | 2019 | W53-2019 | Dec-2019
2019-12-31 | W | 53 | - | 2019 | W53-2019 | Dec-2019
2020-01-01 | W | 01 | - | 2020 | W01-2020 | Jan-2020
2020-01-02 | W | 01 | - | 2020 | W01-2020 | Jan-2020
2020-01-03 | W | 01 | - | 2020 | W01-2020 | Jan-2020
2020-01-04 | W | 01 | - | 2020 | W01-2020 | Jan-2020
2020-01-05 | W | 02 | - | 2020 | W02-2020 | Jan-2020
2020-01-06 | W | 02 | - | 2020 | W02-2020 | Jan-2020
2020-01-07 | W | 02 | - | 2020 | W02-2020 | Jan-2020
2020-01-08 | W | 02 | - | 2020 | W02-2020 | Jan-2020
2020-01-09 | W | 02 | - | 2020 | W02-2020 | Jan-2020
2020-01-10 | W | 02 | - | 2020 | W02-2020 | Jan-2020
2020-01-11 | W | 02 | - | 2020 | W02-2020 | Jan-2020
2020-01-12 | W | 03 | - | 2020 | W03-2020 | Jan-2020
2020-01-13 | W | 03 | - | 2020 | W03-2020 | Jan-2020
2020-01-14 | W | 03 | - | 2020 | W03-2020 | Jan-2020
2020-01-15 | W | 03 | - | 2020 | W03-2020 | Jan-2020
2020-01-16 | W | 03 | - | 2020 | W03-2020 | Jan-2020
2020-01-17 | W | 03 | - | 2020 | W03-2020 | Jan-2020
2020-01-18 | W | 03 | - | 2020 | W03-2020 | Jan-2020
2020-01-19 | W | 04 | - | 2020 | W04-2020 | Jan-2020
2020-01-20 | W | 04 | - | 2020 | W04-2020 | Jan-2020
2020-01-21 | W | 04 | - | 2020 | W04-2020 | Jan-2020
2020-01-22 | W | 04 | - | 2020 | W04-2020 | Jan-2020
2020-01-23 | W | 04 | - | 2020 | W04-2020 | Jan-2020
2020-01-24 | W | 04 | - | 2020 | W04-2020 | Jan-2020
2020-01-25 | W | 04 | - | 2020 | W04-2020 | Jan-2020
2020-01-26 | W | 05 | - | 2020 | W05-2020 | Jan-2020
2020-01-27 | W | 05 | - | 2020 | W05-2020 | Jan-2020
2020-01-28 | W | 05 | - | 2020 | W05-2020 | Jan-2020
2020-01-29 | W | 05 | - | 2020 | W05-2020 | Jan-2020
2020-01-30 | W | 05 | - | 2020 | W05-2020 | Jan-2020
2020-01-31 | W | 05 | - | 2020 | W05-2020 | Jan-2020
2020-02-01 | W | 05 | - | 2020 | W05-2020 | Feb-2020
2020-02-02 | W | 06 | - | 2020 | W06-2020 | Feb-2020
2020-02-03 | W | 06 | - | 2020 | W06-2020 | Feb-2020
2020-02-04 | W | 06 | - | 2020 | W06-2020 | Feb-2020
2020-02-05 | W | 06 | - | 2020 | W06-2020 | Feb-2020
2020-02-06 | W | 06 | - | 2020 | W06-2020 | Feb-2020
2020-02-07 | W | 06 | - | 2020 | W06-2020 | Feb-2020
2020-02-08 | W | 06 | - | 2020 | W06-2020 | Feb-2020
2020-02-09 | W | 07 | - | 2020 | W07-2020 | Feb-2020
2020-02-10 | W | 07 | - | 2020 | W07-2020 | Feb-2020
2020-02-11 | W | 07 | - | 2020 | W07-2020 | Feb-2020
2020-02-12 | W | 07 | - | 2020 | W07-2020 | Feb-2020
2020-02-13 | W | 07 | - | 2020 | W07-2020 | Feb-2020
2020-02-14 | W | 07 | - | 2020 | W07-2020 | Feb-2020
2020-02-15 | W | 07 | - | 2020 | W07-2020 | Feb-2020
2020-02-16 | W | 08 | - | 2020 | W08-2020 | Feb-2020
2020-02-17 | W | 08 | - | 2020 | W08-2020 | Feb-2020
2020-02-18 | W | 08 | - | 2020 | W08-2020 | Feb-2020
2020-02-19 | W | 08 | - | 2020 | W08-2020 | Feb-2020
2020-02-20 | W | 08 | - | 2020 | W08-2020 | Feb-2020
2020-02-21 | W | 08 | - | 2020 | W08-2020 | Feb-2020
2020-02-22 | W | 08 | - | 2020 | W08-2020 | Feb-2020
2020-02-23 | W | 09 | - | 2020 | W09-2020 | Feb-2020
2020-02-24 | W | 09 | - | 2020 | W09-2020 | Feb-2020
2020-02-25 | W | 09 | - | 2020 | W09-2020 | Feb-2020
2020-02-26 | W | 09 | - | 2020 | W09-2020 | Feb-2020
2020-02-27 | W | 09 | - | 2020 | W09-2020 | Feb-2020
2020-02-28 | W | 09 | - | 2020 | W09-2020 | Feb-2020
2020-02-29 | W | 09 | - | 2020 | W09-2020 | Feb-2020
2020-03-01 | W | 10 | - | 2020 | W10-2020 | Mar-2020
2020-03-02 | W | 10 | - | 2020 | W10-2020 | Mar-2020
2020-03-03 | W | 10 | - | 2020 | W10-2020 | Mar-2020
2020-03-04 | W | 10 | - | 2020 | W10-2020 | Mar-2020
2020-03-05 | W | 10 | - | 2020 | W10-2020 | Mar-2020
2020-03-06 | W | 10 | - | 2020 | W10-2020 | Mar-2020
2020-03-07 | W | 10 | - | 2020 | W10-2020 | Mar-2020
2020-03-08 | W | 11 | - | 2020 | W11-2020 | Mar-2020
2020-03-09 | W | 11 | - | 2020 | W11-2020 | Mar-2020
2020-03-10 | W | 11 | - | 2020 | W11-2020 | Mar-2020
2020-03-11 | W | 11 | - | 2020 | W11-2020 | Mar-2020
2020-03-12 | W | 11 | - | 2020 | W11-2020 | Mar-2020
2020-03-13 | W | 11 | - | 2020 | W11-2020 | Mar-2020
2020-03-14 | W | 11 | - | 2020 | W11-2020 | Mar-2020
2020-03-15 | W | 12 | - | 2020 | W12-2020 | Mar-2020
2020-03-16 | W | 12 | - | 2020 | W12-2020 | Mar-2020
2020-03-17 | W | 12 | - | 2020 | W12-2020 | Mar-2020
2020-03-18 | W | 12 | - | 2020 | W12-2020 | Mar-2020
2020-03-19 | W | 12 | - | 2020 | W12-2020 | Mar-2020
2020-03-20 | W | 12 | - | 2020 | W12-2020 | Mar-2020
2020-03-21 | W | 12 | - | 2020 | W12-2020 | Mar-2020
2020-03-22 | W | 13 | - | 2020 | W13-2020 | Mar-2020
2020-03-23 | W | 13 | - | 2020 | W13-2020 | Mar-2020
2020-03-24 | W | 13 | - | 2020 | W13-2020 | Mar-2020
2020-03-25 | W | 13 | - | 2020 | W13-2020 | Mar-2020
2020-03-26 | W | 13 | - | 2020 | W13-2020 | Mar-2020
2020-03-27 | W | 13 | - | 2020 | W13-2020 | Mar-2020
2020-03-28 | W | 13 | - | 2020 | W13-2020 | Mar-2020
2020-03-29 | W | 14 | - | 2020 | W14-2020 | Mar-2020
2020-03-30 | W | 14 | - | 2020 | W14-2020 | Mar-2020
2020-03-31 | W | 14 | - | 2020 | W14-2020 | Mar-2020
2020-04-01 | W | 14 | - | 2020 | W14-2020 | Apr-2020
2020-04-02 | W | 14 | - | 2020 | W14-2020 | Apr-2020
2020-04-03 | W | 14 | - | 2020 | W14-2020 | Apr-2020
2020-04-04 | W | 14 | - | 2020 | W14-2020 | Apr-2020
2020-04-05 | W | 15 | - | 2020 | W15-2020 | Apr-2020
2020-04-06 | W | 15 | - | 2020 | W15-2020 | Apr-2020
2020-04-07 | W | 15 | - | 2020 | W15-2020 | Apr-2020
2020-04-08 | W | 15 | - | 2020 | W15-2020 | Apr-2020
2020-04-09 | W | 15 | - | 2020 | W15-2020 | Apr-2020
2020-04-10 | W | 15 | - | 2020 | W15-2020 | Apr-2020
2020-04-11 | W | 15 | - | 2020 | W15-2020 | Apr-2020
2020-04-12 | W | 16 | - | 2020 | W16-2020 | Apr-2020
2020-04-13 | W | 16 | - | 2020 | W16-2020 | Apr-2020
2020-04-14 | W | 16 | - | 2020 | W16-2020 | Apr-2020
2020-04-15 | W | 16 | - | 2020 | W16-2020 | Apr-2020
2020-04-16 | W | 16 | - | 2020 | W16-2020 | Apr-2020
2020-04-17 | W | 16 | - | 2020 | W16-2020 | Apr-2020
2020-04-18 | W | 16 | - | 2020 | W16-2020 | Apr-2020
2020-04-19 | W | 17 | - | 2020 | W17-2020 | Apr-2020
2020-04-20 | W | 17 | - | 2020 | W17-2020 | Apr-2020
2020-04-21 | W | 17 | - | 2020 | W17-2020 | Apr-2020
2020-04-22 | W | 17 | - | 2020 | W17-2020 | Apr-2020
2020-04-23 | W | 17 | - | 2020 | W17-2020 | Apr-2020
2020-04-24 | W | 17 | - | 2020 | W17-2020 | Apr-2020
2020-04-25 | W | 17 | - | 2020 | W17-2020 | Apr-2020
2020-04-26 | W | 18 | - | 2020 | W18-2020 | Apr-2020
2020-04-27 | W | 18 | - | 2020 | W18-2020 | Apr-2020
2020-04-28 | W | 18 | - | 2020 | W18-2020 | Apr-2020
2020-04-29 | W | 18 | - | 2020 | W18-2020 | Apr-2020
2020-04-30 | W | 18 | - | 2020 | W18-2020 | Apr-2020
2020-05-01 | W | 18 | - | 2020 | W18-2020 | May-2020
2020-05-02 | W | 18 | - | 2020 | W18-2020 | May-2020
2020-05-03 | W | 19 | - | 2020 | W19-2020 | May-2020
2020-05-04 | W | 19 | - | 2020 | W19-2020 | May-2020
2020-05-05 | W | 19 | - | 2020 | W19-2020 | May-2020
2020-05-06 | W | 19 | - | 2020 | W19-2020 | May-2020
2020-05-07 | W | 19 | - | 2020 | W19-2020 | May-2020
2020-05-08 | W | 19 | - | 2020 | W19-2020 | May-2020
2020-05-09 | W | 19 | - | 2020 | W19-2020 | May-2020
2020-05-10 | W | 20 | - | 2020 | W20-2020 | May-2020
2020-05-11 | W | 20 | - | 2020 | W20-2020 | May-2020
2020-05-12 | W | 20 | - | 2020 | W20-2020 | May-2020
2020-05-13 | W | 20 | - | 2020 | W20-2020 | May-2020
2020-05-14 | W | 20 | - | 2020 | W20-2020 | May-2020
2020-05-15 | W | 20 | - | 2020 | W20-2020 | May-2020
2020-05-16 | W | 20 | - | 2020 | W20-2020 | May-2020
2020-05-17 | W | 21 | - | 2020 | W21-2020 | May-2020
2020-05-18 | W | 21 | - | 2020 | W21-2020 | May-2020
2020-05-19 | W | 21 | - | 2020 | W21-2020 | May-2020
2020-05-20 | W | 21 | - | 2020 | W21-2020 | May-2020
2020-05-21 | W | 21 | - | 2020 | W21-2020 | May-2020
2020-05-22 | W | 21 | - | 2020 | W21-2020 | May-2020
2020-05-23 | W | 21 | - | 2020 | W21-2020 | May-2020
2020-05-24 | W | 22 | - | 2020 | W22-2020 | May-2020
2020-05-25 | W | 22 | - | 2020 | W22-2020 | May-2020
2020-05-26 | W | 22 | - | 2020 | W22-2020 | May-2020
2020-05-27 | W | 22 | - | 2020 | W22-2020 | May-2020
2020-05-28 | W | 22 | - | 2020 | W22-2020 | May-2020
2020-05-29 | W | 22 | - | 2020 | W22-2020 | May-2020
2020-05-30 | W | 22 | - | 2020 | W22-2020 | May-2020
2020-05-31 | W | 23 | - | 2020 | W23-2020 | May-2020
2020-06-01 | W | 23 | - | 2020 | W23-2020 | Jun-2020
2020-06-02 | W | 23 | - | 2020 | W23-2020 | Jun-2020
2020-06-03 | W | 23 | - | 2020 | W23-2020 | Jun-2020
2020-06-04 | W | 23 | - | 2020 | W23-2020 | Jun-2020
2020-06-05 | W | 23 | - | 2020 | W23-2020 | Jun-2020
2020-06-06 | W | 23 | - | 2020 | W23-2020 | Jun-2020
2020-06-07 | W | 24 | - | 2020 | W24-2020 | Jun-2020
2020-06-08 | W | 24 | - | 2020 | W24-2020 | Jun-2020
2020-06-09 | W | 24 | - | 2020 | W24-2020 | Jun-2020
2020-06-10 | W | 24 | - | 2020 | W24-2020 | Jun-2020
2020-06-11 | W | 24 | - | 2020 | W24-2020 | Jun-2020
2020-06-12 | W | 24 | - | 2020 | W24-2020 | Jun-2020
2020-06-13 | W | 24 | - | 2020 | W24-2020 | Jun-2020
2020-06-14 | W | 25 | - | 2020 | W25-2020 | Jun-2020
2020-06-15 | W | 25 | - | 2020 | W25-2020 | Jun-2020
2020-06-16 | W | 25 | - | 2020 | W25-2020 | Jun-2020
2020-06-17 | W | 25 | - | 2020 | W25-2020 | Jun-2020
2020-06-18 | W | 25 | - | 2020 | W25-2020 | Jun-2020
2020-06-19 | W | 25 | - | 2020 | W25-2020 | Jun-2020
2020-06-20 | W | 25 | - | 2020 | W25-2020 | Jun-2020
2020-06-21 | W | 26 | - | 2020 | W26-2020 | Jun-2020
2020-06-22 | W | 26 | - | 2020 | W26-2020 | Jun-2020
2020-06-23 | W | 26 | - | 2020 | W26-2020 | Jun-2020
2020-06-24 | W | 26 | - | 2020 | W26-2020 | Jun-2020
2020-06-25 | W | 26 | - | 2020 | W26-2020 | Jun-2020
2020-06-26 | W | 26 | - | 2020 | W26-2020 | Jun-2020
2020-06-27 | W | 26 | - | 2020 | W26-2020 | Jun-2020
2020-06-28 | W | 27 | - | 2020 | W27-2020 | Jun-2020
2020-06-29 | W | 27 | - | 2020 | W27-2020 | Jun-2020
2020-06-30 | W | 27 | - | 2020 | W27-2020 | Jun-2020
2020-07-01 | W | 27 | - | 2020 | W27-2020 | Jul-2020
2020-07-02 | W | 27 | - | 2020 | W27-2020 | Jul-2020
2020-07-03 | W | 27 | - | 2020 | W27-2020 | Jul-2020
2020-07-04 | W | 27 | - | 2020 | W27-2020 | Jul-2020
2020-07-05 | W | 28 | - | 2020 | W28-2020 | Jul-2020
2020-07-06 | W | 28 | - | 2020 | W28-2020 | Jul-2020
2020-07-07 | W | 28 | - | 2020 | W28-2020 | Jul-2020
2020-07-08 | W | 28 | - | 2020 | W28-2020 | Jul-2020
2020-07-09 | W | 28 | - | 2020 | W28-2020 | Jul-2020
2020-07-10 | W | 28 | - | 2020 | W28-2020 | Jul-2020
2020-07-11 | W | 28 | - | 2020 | W28-2020 | Jul-2020
2020-07-12 | W | 29 | - | 2020 | W29-2020 | Jul-2020
2020-07-13 | W | 29 | - | 2020 | W29-2020 | Jul-2020
2020-07-14 | W | 29 | - | 2020 | W29-2020 | Jul-2020
2020-07-15 | W | 29 | - | 2020 | W29-2020 | Jul-2020
2020-07-16 | W | 29 | - | 2020 | W29-2020 | Jul-2020
2020-07-17 | W | 29 | - | 2020 | W29-2020 | Jul-2020
2020-07-18 | W | 29 | - | 2020 | W29-2020 | Jul-2020
2020-07-19 | W | 30 | - | 2020 | W30-2020 | Jul-2020
2020-07-20 | W | 30 | - | 2020 | W30-2020 | Jul-2020
2020-07-21 | W | 30 | - | 2020 | W30-2020 | Jul-2020
2020-07-22 | W | 30 | - | 2020 | W30-2020 | Jul-2020
2020-07-23 | W | 30 | - | 2020 | W30-2020 | Jul-2020
2020-07-24 | W | 30 | - | 2020 | W30-2020 | Jul-2020
2020-07-25 | W | 30 | - | 2020 | W30-2020 | Jul-2020
2020-07-26 | W | 31 | - | 2020 | W31-2020 | Jul-2020
2020-07-27 | W | 31 | - | 2020 | W31-2020 | Jul-2020
2020-07-28 | W | 31 | - | 2020 | W31-2020 | Jul-2020
2020-07-29 | W | 31 | - | 2020 | W31-2020 | Jul-2020
2020-07-30 | W | 31 | - | 2020 | W31-2020 | Jul-2020
2020-07-31 | W | 31 | - | 2020 | W31-2020 | Jul-2020
2020-08-01 | W | 31 | - | 2020 | W31-2020 | Aug-2020
2020-08-02 | W | 32 | - | 2020 | W32-2020 | Aug-2020
2020-08-03 | W | 32 | - | 2020 | W32-2020 | Aug-2020
2020-08-04 | W | 32 | - | 2020 | W32-2020 | Aug-2020
2020-08-05 | W | 32 | - | 2020 | W32-2020 | Aug-2020
2020-08-06 | W | 32 | - | 2020 | W32-2020 | Aug-2020
2020-08-07 | W | 32 | - | 2020 | W32-2020 | Aug-2020
2020-08-08 | W | 32 | - | 2020 | W32-2020 | Aug-2020
2020-08-09 | W | 33 | - | 2020 | W33-2020 | Aug-2020
2020-08-10 | W | 33 | - | 2020 | W33-2020 | Aug-2020
2020-08-11 | W | 33 | - | 2020 | W33-2020 | Aug-2020
2020-08-12 | W | 33 | - | 2020 | W33-2020 | Aug-2020
2020-08-13 | W | 33 | - | 2020 | W33-2020 | Aug-2020
2020-08-14 | W | 33 | - | 2020 | W33-2020 | Aug-2020
2020-08-15 | W | 33 | - | 2020 | W33-2020 | Aug-2020
2020-08-16 | W | 34 | - | 2020 | W34-2020 | Aug-2020
2020-08-17 | W | 34 | - | 2020 | W34-2020 | Aug-2020
2020-08-18 | W | 34 | - | 2020 | W34-2020 | Aug-2020
2020-08-19 | W | 34 | - | 2020 | W34-2020 | Aug-2020
2020-08-20 | W | 34 | - | 2020 | W34-2020 | Aug-2020
2020-08-21 | W | 34 | - | 2020 | W34-2020 | Aug-2020
2020-08-22 | W | 34 | - | 2020 | W34-2020 | Aug-2020
2020-08-23 | W | 35 | - | 2020 | W35-2020 | Aug-2020
2020-08-24 | W | 35 | - | 2020 | W35-2020 | Aug-2020
2020-08-25 | W | 35 | - | 2020 | W35-2020 | Aug-2020
2020-08-26 | W | 35 | - | 2020 | W35-2020 | Aug-2020
2020-08-27 | W | 35 | - | 2020 | W35-2020 | Aug-2020
2020-08-28 | W | 35 | - | 2020 | W35-2020 | Aug-2020
2020-08-29 | W | 35 | - | 2020 | W35-2020 | Aug-2020
2020-08-30 | W | 36 | - | 2020 | W36-2020 | Aug-2020
2020-08-31 | W | 36 | - | 2020 | W36-2020 | Aug-2020
2020-09-01 | W | 36 | - | 2020 | W36-2020 | Sep-2020
2020-09-02 | W | 36 | - | 2020 | W36-2020 | Sep-2020
2020-09-03 | W | 36 | - | 2020 | W36-2020 | Sep-2020
2020-09-04 | W | 36 | - | 2020 | W36-2020 | Sep-2020
2020-09-05 | W | 36 | - | 2020 | W36-2020 | Sep-2020
2020-09-06 | W | 37 | - | 2020 | W37-2020 | Sep-2020
2020-09-07 | W | 37 | - | 2020 | W37-2020 | Sep-2020
2020-09-08 | W | 37 | - | 2020 | W37-2020 | Sep-2020
2020-09-09 | W | 37 | - | 2020 | W37-2020 | Sep-2020
2020-09-10 | W | 37 | - | 2020 | W37-2020 | Sep-2020
2020-09-11 | W | 37 | - | 2020 | W37-2020 | Sep-2020
2020-09-12 | W | 37 | - | 2020 | W37-2020 | Sep-2020
2020-09-13 | W | 38 | - | 2020 | W38-2020 | Sep-2020
2020-09-14 | W | 38 | - | 2020 | W38-2020 | Sep-2020
2020-09-15 | W | 38 | - | 2020 | W38-2020 | Sep-2020
2020-09-16 | W | 38 | - | 2020 | W38-2020 | Sep-2020
2020-09-17 | W | 38 | - | 2020 | W38-2020 | Sep-2020
2020-09-18 | W | 38 | - | 2020 | W38-2020 | Sep-2020
2020-09-19 | W | 38 | - | 2020 | W38-2020 | Sep-2020
2020-09-20 | W | 39 | - | 2020 | W39-2020 | Sep-2020
2020-09-21 | W | 39 | - | 2020 | W39-2020 | Sep-2020
2020-09-22 | W | 39 | - | 2020 | W39-2020 | Sep-2020
2020-09-23 | W | 39 | - | 2020 | W39-2020 | Sep-2020
2020-09-24 | W | 39 | - | 2020 | W39-2020 | Sep-2020
2020-09-25 | W | 39 | - | 2020 | W39-2020 | Sep-2020
2020-09-26 | W | 39 | - | 2020 | W39-2020 | Sep-2020
2020-09-27 | W | 40 | - | 2020 | W40-2020 | Sep-2020
2020-09-28 | W | 40 | - | 2020 | W40-2020 | Sep-2020
2020-09-29 | W | 40 | - | 2020 | W40-2020 | Sep-2020
2020-09-30 | W | 40 | - | 2020 | W40-2020 | Sep-2020
2020-10-01 | W | 40 | - | 2020 | W40-2020 | Oct-2020
2020-10-02 | W | 40 | - | 2020 | W40-2020 | Oct-2020
2020-10-03 | W | 40 | - | 2020 | W40-2020 | Oct-2020
2020-10-04 | W | 41 | - | 2020 | W41-2020 | Oct-2020
2020-10-05 | W | 41 | - | 2020 | W41-2020 | Oct-2020
2020-10-06 | W | 41 | - | 2020 | W41-2020 | Oct-2020
2020-10-07 | W | 41 | - | 2020 | W41-2020 | Oct-2020
2020-10-08 | W | 41 | - | 2020 | W41-2020 | Oct-2020
2020-10-09 | W | 41 | - | 2020 | W41-2020 | Oct-2020
2020-10-10 | W | 41 | - | 2020 | W41-2020 | Oct-2020
2020-10-11 | W | 42 | - | 2020 | W42-2020 | Oct-2020
2020-10-12 | W | 42 | - | 2020 | W42-2020 | Oct-2020
2020-10-13 | W | 42 | - | 2020 | W42-2020 | Oct-2020
2020-10-14 | W | 42 | - | 2020 | W42-2020 | Oct-2020
2020-10-15 | W | 42 | - | 2020 | W42-2020 | Oct-2020
2020-10-16 | W | 42 | - | 2020 | W42-2020 | Oct-2020
2020-10-17 | W | 42 | - | 2020 | W42-2020 | Oct-2020
2020-10-18 | W | 43 | - | 2020 | W43-2020 | Oct-2020
2020-10-19 | W | 43 | - | 2020 | W43-2020 | Oct-2020
2020-10-20 | W | 43 | - | 2020 | W43-2020 | Oct-2020
2020-10-21 | W | 43 | - | 2020 | W43-2020 | Oct-2020
2020-10-22 | W | 43 | - | 2020 | W43-2020 | Oct-2020
2020-10-23 | W | 43 | - | 2020 | W43-2020 | Oct-2020
2020-10-24 | W | 43 | - | 2020 | W43-2020 | Oct-2020
2020-10-25 | W | 44 | - | 2020 | W44-2020 | Oct-2020
2020-10-26 | W | 44 | - | 2020 | W44-2020 | Oct-2020
2020-10-27 | W | 44 | - | 2020 | W44-2020 | Oct-2020
2020-10-28 | W | 44 | - | 2020 | W44-2020 | Oct-2020
2020-10-29 | W | 44 | - | 2020 | W44-2020 | Oct-2020
2020-10-30 | W | 44 | - | 2020 | W44-2020 | Oct-2020
2020-10-31 | W | 44 | - | 2020 | W44-2020 | Oct-2020
2020-11-01 | W | 45 | - | 2020 | W45-2020 | Nov-2020
2020-11-02 | W | 45 | - | 2020 | W45-2020 | Nov-2020
2020-11-03 | W | 45 | - | 2020 | W45-2020 | Nov-2020
2020-11-04 | W | 45 | - | 2020 | W45-2020 | Nov-2020
2020-11-05 | W | 45 | - | 2020 | W45-2020 | Nov-2020
2020-11-06 | W | 45 | - | 2020 | W45-2020 | Nov-2020
2020-11-07 | W | 45 | - | 2020 | W45-2020 | Nov-2020
2020-11-08 | W | 46 | - | 2020 | W46-2020 | Nov-2020
2020-11-09 | W | 46 | - | 2020 | W46-2020 | Nov-2020
2020-11-10 | W | 46 | - | 2020 | W46-2020 | Nov-2020
2020-11-11 | W | 46 | - | 2020 | W46-2020 | Nov-2020
2020-11-12 | W | 46 | - | 2020 | W46-2020 | Nov-2020
2020-11-13 | W | 46 | - | 2020 | W46-2020 | Nov-2020
2020-11-14 | W | 46 | - | 2020 | W46-2020 | Nov-2020
2020-11-15 | W | 47 | - | 2020 | W47-2020 | Nov-2020
2020-11-16 | W | 47 | - | 2020 | W47-2020 | Nov-2020
2020-11-17 | W | 47 | - | 2020 | W47-2020 | Nov-2020
2020-11-18 | W | 47 | - | 2020 | W47-2020 | Nov-2020
2020-11-19 | W | 47 | - | 2020 | W47-2020 | Nov-2020
2020-11-20 | W | 47 | - | 2020 | W47-2020 | Nov-2020
2020-11-21 | W | 47 | - | 2020 | W47-2020 | Nov-2020
2020-11-22 | W | 48 | - | 2020 | W48-2020 | Nov-2020
2020-11-23 | W | 48 | - | 2020 | W48-2020 | Nov-2020
2020-11-24 | W | 48 | - | 2020 | W48-2020 | Nov-2020
2020-11-25 | W | 48 | - | 2020 | W48-2020 | Nov-2020
2020-11-26 | W | 48 | - | 2020 | W48-2020 | Nov-2020
2020-11-27 | W | 48 | - | 2020 | W48-2020 | Nov-2020
2020-11-28 | W | 48 | - | 2020 | W48-2020 | Nov-2020
2020-11-29 | W | 49 | - | 2020 | W49-2020 | Nov-2020
2020-11-30 | W | 49 | - | 2020 | W49-2020 | Nov-2020
2020-12-01 | W | 49 | - | 2020 | W49-2020 | Dec-2020
2020-12-02 | W | 49 | - | 2020 | W49-2020 | Dec-2020
2020-12-03 | W | 49 | - | 2020 | W49-2020 | Dec-2020
2020-12-04 | W | 49 | - | 2020 | W49-2020 | Dec-2020
2020-12-05 | W | 49 | - | 2020 | W49-2020 | Dec-2020
2020-12-06 | W | 50 | - | 2020 | W50-2020 | Dec-2020
2020-12-07 | W | 50 | - | 2020 | W50-2020 | Dec-2020
2020-12-08 | W | 50 | - | 2020 | W50-2020 | Dec-2020
2020-12-09 | W | 50 | - | 2020 | W50-2020 | Dec-2020
2020-12-10 | W | 50 | - | 2020 | W50-2020 | Dec-2020
2020-12-11 | W | 50 | - | 2020 | W50-2020 | Dec-2020
2020-12-12 | W | 50 | - | 2020 | W50-2020 | Dec-2020
2020-12-13 | W | 51 | - | 2020 | W51-2020 | Dec-2020
2020-12-14 | W | 51 | - | 2020 | W51-2020 | Dec-2020
2020-12-15 | W | 51 | - | 2020 | W51-2020 | Dec-2020
2020-12-16 | W | 51 | - | 2020 | W51-2020 | Dec-2020
2020-12-17 | W | 51 | - | 2020 | W51-2020 | Dec-2020
2020-12-18 | W | 51 | - | 2020 | W51-2020 | Dec-2020
2020-12-19 | W | 51 | - | 2020 | W51-2020 | Dec-2020
2020-12-20 | W | 52 | - | 2020 | W52-2020 | Dec-2020
2020-12-21 | W | 52 | - | 2020 | W52-2020 | Dec-2020
2020-12-22 | W | 52 | - | 2020 | W52-2020 | Dec-2020
2020-12-23 | W | 52 | - | 2020 | W52-2020 | Dec-2020
2020-12-24 | W | 52 | - | 2020 | W52-2020 | Dec-2020
2020-12-25 | W | 52 | - | 2020 | W52-2020 | Dec-2020
2020-12-26 | W | 52 | - | 2020 | W52-2020 | Dec-2020
2020-12-27 | W | 53 | - | 2020 | W53-2020 | Dec-2020
2020-12-28 | W | 53 | - | 2020 | W53-2020 | Dec-2020
2020-12-29 | W | 53 | - | 2020 | W53-2020 | Dec-2020
2020-12-30 | W | 53 | - | 2020 | W53-2020 | Dec-2020
2020-12-31 | W | 53 | - | 2020 | W53-2020 | Dec-2020
RFS | W | RFS | - | 2020 | RFS | RFS
TBD | W | TBD | - | 2020 | TBD | TBD
2021-01-01 | W | 01 | - | 2021 | W01-2021 | Jan-2021
2021-01-02 | W | 01 | - | 2021 | W01-2021 | Jan-2021
2021-01-03 | W | 02 | - | 2021 | W02-2021 | Jan-2021
2021-01-04 | W | 02 | - | 2021 | W02-2021 | Jan-2021
2021-01-05 | W | 02 | - | 2021 | W02-2021 | Jan-2021
2021-01-06 | W | 02 | - | 2021 | W02-2021 | Jan-2021
2021-01-07 | W | 02 | - | 2021 | W02-2021 | Jan-2021
2021-01-08 | W | 02 | - | 2021 | W02-2021 | Jan-2021
2021-01-09 | W | 02 | - | 2021 | W02-2021 | Jan-2021
2021-01-10 | W | 03 | - | 2021 | W03-2021 | Jan-2021
2021-01-11 | W | 03 | - | 2021 | W03-2021 | Jan-2021
2021-01-12 | W | 03 | - | 2021 | W03-2021 | Jan-2021
2021-01-13 | W | 03 | - | 2021 | W03-2021 | Jan-2021
2021-01-14 | W | 03 | - | 2021 | W03-2021 | Jan-2021
2021-01-15 | W | 03 | - | 2021 | W03-2021 | Jan-2021
2021-01-16 | W | 03 | - | 2021 | W03-2021 | Jan-2021
2021-01-17 | W | 04 | - | 2021 | W04-2021 | Jan-2021
2021-01-18 | W | 04 | - | 2021 | W04-2021 | Jan-2021
2021-01-19 | W | 04 | - | 2021 | W04-2021 | Jan-2021
2021-01-20 | W | 04 | - | 2021 | W04-2021 | Jan-2021
2021-01-21 | W | 04 | - | 2021 | W04-2021 | Jan-2021
2021-01-22 | W | 04 | - | 2021 | W04-2021 | Jan-2021
2021-01-23 | W | 04 | - | 2021 | W04-2021 | Jan-2021
2021-01-24 | W | 05 | - | 2021 | W05-2021 | Jan-2021
2021-01-25 | W | 05 | - | 2021 | W05-2021 | Jan-2021
2021-01-26 | W | 05 | - | 2021 | W05-2021 | Jan-2021
2021-01-27 | W | 05 | - | 2021 | W05-2021 | Jan-2021
2021-01-28 | W | 05 | - | 2021 | W05-2021 | Jan-2021
2021-01-29 | W | 05 | - | 2021 | W05-2021 | Jan-2021
2021-01-30 | W | 05 | - | 2021 | W05-2021 | Jan-2021
2021-01-31 | W | 06 | - | 2021 | W06-2021 | Jan-2021
2021-02-01 | W | 06 | - | 2021 | W06-2021 | Feb-2021
2021-02-02 | W | 06 | - | 2021 | W06-2021 | Feb-2021
2021-02-03 | W | 06 | - | 2021 | W06-2021 | Feb-2021
2021-02-04 | W | 06 | - | 2021 | W06-2021 | Feb-2021
2021-02-05 | W | 06 | - | 2021 | W06-2021 | Feb-2021
2021-02-06 | W | 06 | - | 2021 | W06-2021 | Feb-2021
2021-02-07 | W | 07 | - | 2021 | W07-2021 | Feb-2021
2021-02-08 | W | 07 | - | 2021 | W07-2021 | Feb-2021
2021-02-09 | W | 07 | - | 2021 | W07-2021 | Feb-2021
2021-02-10 | W | 07 | - | 2021 | W07-2021 | Feb-2021
2021-02-11 | W | 07 | - | 2021 | W07-2021 | Feb-2021
2021-02-12 | W | 07 | - | 2021 | W07-2021 | Feb-2021
2021-02-13 | W | 07 | - | 2021 | W07-2021 | Feb-2021
2021-02-14 | W | 08 | - | 2021 | W08-2021 | Feb-2021
2021-02-15 | W | 08 | - | 2021 | W08-2021 | Feb-2021
2021-02-16 | W | 08 | - | 2021 | W08-2021 | Feb-2021
2021-02-17 | W | 08 | - | 2021 | W08-2021 | Feb-2021
2021-02-18 | W | 08 | - | 2021 | W08-2021 | Feb-2021
2021-02-19 | W | 08 | - | 2021 | W08-2021 | Feb-2021
2021-02-20 | W | 08 | - | 2021 | W08-2021 | Feb-2021
2021-02-21 | W | 09 | - | 2021 | W09-2021 | Feb-2021
2021-02-22 | W | 09 | - | 2021 | W09-2021 | Feb-2021
2021-02-23 | W | 09 | - | 2021 | W09-2021 | Feb-2021
2021-02-24 | W | 09 | - | 2021 | W09-2021 | Feb-2021
2021-02-25 | W | 09 | - | 2021 | W09-2021 | Feb-2021
2021-02-26 | W | 09 | - | 2021 | W09-2021 | Feb-2021
2021-02-27 | W | 09 | - | 2021 | W09-2021 | Feb-2021
2021-02-28 | W | 10 | - | 2021 | W10-2021 | Feb-2021
2021-03-01 | W | 10 | - | 2021 | W10-2021 | Mar-2021
2021-03-02 | W | 10 | - | 2021 | W10-2021 | Mar-2021
2021-03-03 | W | 10 | - | 2021 | W10-2021 | Mar-2021
2021-03-04 | W | 10 | - | 2021 | W10-2021 | Mar-2021
2021-03-05 | W | 10 | - | 2021 | W10-2021 | Mar-2021
2021-03-06 | W | 10 | - | 2021 | W10-2021 | Mar-2021
2021-03-07 | W | 11 | - | 2021 | W11-2021 | Mar-2021
2021-03-08 | W | 11 | - | 2021 | W11-2021 | Mar-2021
2021-03-09 | W | 11 | - | 2021 | W11-2021 | Mar-2021
2021-03-10 | W | 11 | - | 2021 | W11-2021 | Mar-2021
2021-03-11 | W | 11 | - | 2021 | W11-2021 | Mar-2021
2021-03-12 | W | 11 | - | 2021 | W11-2021 | Mar-2021
2021-03-13 | W | 11 | - | 2021 | W11-2021 | Mar-2021
2021-03-14 | W | 12 | - | 2021 | W12-2021 | Mar-2021
2021-03-15 | W | 12 | - | 2021 | W12-2021 | Mar-2021
2021-03-16 | W | 12 | - | 2021 | W12-2021 | Mar-2021
2021-03-17 | W | 12 | - | 2021 | W12-2021 | Mar-2021
2021-03-18 | W | 12 | - | 2021 | W12-2021 | Mar-2021
2021-03-19 | W | 12 | - | 2021 | W12-2021 | Mar-2021
2021-03-20 | W | 12 | - | 2021 | W12-2021 | Mar-2021
2021-03-21 | W | 13 | - | 2021 | W13-2021 | Mar-2021
2021-03-22 | W | 13 | - | 2021 | W13-2021 | Mar-2021
2021-03-23 | W | 13 | - | 2021 | W13-2021 | Mar-2021
2021-03-24 | W | 13 | - | 2021 | W13-2021 | Mar-2021
2021-03-25 | W | 13 | - | 2021 | W13-2021 | Mar-2021
2021-03-26 | W | 13 | - | 2021 | W13-2021 | Mar-2021
2021-03-27 | W | 13 | - | 2021 | W13-2021 | Mar-2021
2021-03-28 | W | 14 | - | 2021 | W14-2021 | Mar-2021
2021-03-29 | W | 14 | - | 2021 | W14-2021 | Mar-2021
2021-03-30 | W | 14 | - | 2021 | W14-2021 | Mar-2021
2021-03-31 | W | 14 | - | 2021 | W14-2021 | Mar-2021
2021-04-01 | W | 14 | - | 2021 | W14-2021 | Apr-2021
2021-04-02 | W | 14 | - | 2021 | W14-2021 | Apr-2021
2021-04-03 | W | 14 | - | 2021 | W14-2021 | Apr-2021
2021-04-04 | W | 15 | - | 2021 | W15-2021 | Apr-2021
2021-04-05 | W | 15 | - | 2021 | W15-2021 | Apr-2021
2021-04-06 | W | 15 | - | 2021 | W15-2021 | Apr-2021
2021-04-07 | W | 15 | - | 2021 | W15-2021 | Apr-2021
2021-04-08 | W | 15 | - | 2021 | W15-2021 | Apr-2021
2021-04-09 | W | 15 | - | 2021 | W15-2021 | Apr-2021
2021-04-10 | W | 15 | - | 2021 | W15-2021 | Apr-2021
2021-04-11 | W | 16 | - | 2021 | W16-2021 | Apr-2021
2021-04-12 | W | 16 | - | 2021 | W16-2021 | Apr-2021
2021-04-13 | W | 16 | - | 2021 | W16-2021 | Apr-2021
2021-04-14 | W | 16 | - | 2021 | W16-2021 | Apr-2021
2021-04-15 | W | 16 | - | 2021 | W16-2021 | Apr-2021
2021-04-16 | W | 16 | - | 2021 | W16-2021 | Apr-2021
2021-04-17 | W | 16 | - | 2021 | W16-2021 | Apr-2021
2021-04-18 | W | 17 | - | 2021 | W17-2021 | Apr-2021
2021-04-19 | W | 17 | - | 2021 | W17-2021 | Apr-2021
2021-04-20 | W | 17 | - | 2021 | W17-2021 | Apr-2021
2021-04-21 | W | 17 | - | 2021 | W17-2021 | Apr-2021
2021-04-22 | W | 17 | - | 2021 | W17-2021 | Apr-2021
2021-04-23 | W | 17 | - | 2021 | W17-2021 | Apr-2021
2021-04-24 | W | 17 | - | 2021 | W17-2021 | Apr-2021
2021-04-25 | W | 18 | - | 2021 | W18-2021 | Apr-2021
2021-04-26 | W | 18 | - | 2021 | W18-2021 | Apr-2021
2021-04-27 | W | 18 | - | 2021 | W18-2021 | Apr-2021
2021-04-28 | W | 18 | - | 2021 | W18-2021 | Apr-2021
2021-04-29 | W | 18 | - | 2021 | W18-2021 | Apr-2021
2021-04-30 | W | 18 | - | 2021 | W18-2021 | Apr-2021
2021-05-01 | W | 18 | - | 2021 | W18-2021 | May-2021
2021-05-02 | W | 19 | - | 2021 | W19-2021 | May-2021
2021-05-03 | W | 19 | - | 2021 | W19-2021 | May-2021
2021-05-04 | W | 19 | - | 2021 | W19-2021 | May-2021
2021-05-05 | W | 19 | - | 2021 | W19-2021 | May-2021
2021-05-06 | W | 19 | - | 2021 | W19-2021 | May-2021
2021-05-07 | W | 19 | - | 2021 | W19-2021 | May-2021
2021-05-08 | W | 19 | - | 2021 | W19-2021 | May-2021
2021-05-09 | W | 20 | - | 2021 | W20-2021 | May-2021
2021-05-10 | W | 20 | - | 2021 | W20-2021 | May-2021
2021-05-11 | W | 20 | - | 2021 | W20-2021 | May-2021
2021-05-12 | W | 20 | - | 2021 | W20-2021 | May-2021
2021-05-13 | W | 20 | - | 2021 | W20-2021 | May-2021
2021-05-14 | W | 20 | - | 2021 | W20-2021 | May-2021
2021-05-15 | W | 20 | - | 2021 | W20-2021 | May-2021
2021-05-16 | W | 21 | - | 2021 | W21-2021 | May-2021
2021-05-17 | W | 21 | - | 2021 | W21-2021 | May-2021
2021-05-18 | W | 21 | - | 2021 | W21-2021 | May-2021
2021-05-19 | W | 21 | - | 2021 | W21-2021 | May-2021
2021-05-20 | W | 21 | - | 2021 | W21-2021 | May-2021
2021-05-21 | W | 21 | - | 2021 | W21-2021 | May-2021
2021-05-22 | W | 21 | - | 2021 | W21-2021 | May-2021
2021-05-23 | W | 22 | - | 2021 | W22-2021 | May-2021
2021-05-24 | W | 22 | - | 2021 | W22-2021 | May-2021
2021-05-25 | W | 22 | - | 2021 | W22-2021 | May-2021
2021-05-26 | W | 22 | - | 2021 | W22-2021 | May-2021
2021-05-27 | W | 22 | - | 2021 | W22-2021 | May-2021
2021-05-28 | W | 22 | - | 2021 | W22-2021 | May-2021
2021-05-29 | W | 22 | - | 2021 | W22-2021 | May-2021
2021-05-30 | W | 23 | - | 2021 | W23-2021 | May-2021
2021-05-31 | W | 23 | - | 2021 | W23-2021 | May-2021
2021-06-01 | W | 23 | - | 2021 | W23-2021 | Jun-2021
2021-06-02 | W | 23 | - | 2021 | W23-2021 | Jun-2021
2021-06-03 | W | 23 | - | 2021 | W23-2021 | Jun-2021
2021-06-04 | W | 23 | - | 2021 | W23-2021 | Jun-2021
2021-06-05 | W | 23 | - | 2021 | W23-2021 | Jun-2021
2021-06-06 | W | 24 | - | 2021 | W24-2021 | Jun-2021
2021-06-07 | W | 24 | - | 2021 | W24-2021 | Jun-2021
2021-06-08 | W | 24 | - | 2021 | W24-2021 | Jun-2021
2021-06-09 | W | 24 | - | 2021 | W24-2021 | Jun-2021
2021-06-10 | W | 24 | - | 2021 | W24-2021 | Jun-2021
2021-06-11 | W | 24 | - | 2021 | W24-2021 | Jun-2021
2021-06-12 | W | 24 | - | 2021 | W24-2021 | Jun-2021
2021-06-13 | W | 25 | - | 2021 | W25-2021 | Jun-2021
2021-06-14 | W | 25 | - | 2021 | W25-2021 | Jun-2021
2021-06-15 | W | 25 | - | 2021 | W25-2021 | Jun-2021
2021-06-16 | W | 25 | - | 2021 | W25-2021 | Jun-2021
2021-06-17 | W | 25 | - | 2021 | W25-2021 | Jun-2021
2021-06-18 | W | 25 | - | 2021 | W25-2021 | Jun-2021
2021-06-19 | W | 25 | - | 2021 | W25-2021 | Jun-2021
2021-06-20 | W | 26 | - | 2021 | W26-2021 | Jun-2021
2021-06-21 | W | 26 | - | 2021 | W26-2021 | Jun-2021
2021-06-22 | W | 26 | - | 2021 | W26-2021 | Jun-2021
2021-06-23 | W | 26 | - | 2021 | W26-2021 | Jun-2021
2021-06-24 | W | 26 | - | 2021 | W26-2021 | Jun-2021
2021-06-25 | W | 26 | - | 2021 | W26-2021 | Jun-2021
2021-06-26 | W | 26 | - | 2021 | W26-2021 | Jun-2021
2021-06-27 | W | 27 | - | 2021 | W27-2021 | Jun-2021
2021-06-28 | W | 27 | - | 2021 | W27-2021 | Jun-2021
2021-06-29 | W | 27 | - | 2021 | W27-2021 | Jun-2021
2021-06-30 | W | 27 | - | 2021 | W27-2021 | Jun-2021
2021-07-01 | W | 27 | - | 2021 | W27-2021 | Jul-2021
2021-07-02 | W | 27 | - | 2021 | W27-2021 | Jul-2021
2021-07-03 | W | 27 | - | 2021 | W27-2021 | Jul-2021
2021-07-04 | W | 28 | - | 2021 | W28-2021 | Jul-2021
2021-07-05 | W | 28 | - | 2021 | W28-2021 | Jul-2021
2021-07-06 | W | 28 | - | 2021 | W28-2021 | Jul-2021
2021-07-07 | W | 28 | - | 2021 | W28-2021 | Jul-2021
2021-07-08 | W | 28 | - | 2021 | W28-2021 | Jul-2021
2021-07-09 | W | 28 | - | 2021 | W28-2021 | Jul-2021
2021-07-10 | W | 28 | - | 2021 | W28-2021 | Jul-2021
2021-07-11 | W | 29 | - | 2021 | W29-2021 | Jul-2021
2021-07-12 | W | 29 | - | 2021 | W29-2021 | Jul-2021
2021-07-13 | W | 29 | - | 2021 | W29-2021 | Jul-2021
2021-07-14 | W | 29 | - | 2021 | W29-2021 | Jul-2021
2021-07-15 | W | 29 | - | 2021 | W29-2021 | Jul-2021
2021-07-16 | W | 29 | - | 2021 | W29-2021 | Jul-2021
2021-07-17 | W | 29 | - | 2021 | W29-2021 | Jul-2021
2021-07-18 | W | 30 | - | 2021 | W30-2021 | Jul-2021
2021-07-19 | W | 30 | - | 2021 | W30-2021 | Jul-2021
2021-07-20 | W | 30 | - | 2021 | W30-2021 | Jul-2021
2021-07-21 | W | 30 | - | 2021 | W30-2021 | Jul-2021
2021-07-22 | W | 30 | - | 2021 | W30-2021 | Jul-2021
2021-07-23 | W | 30 | - | 2021 | W30-2021 | Jul-2021
2021-07-24 | W | 30 | - | 2021 | W30-2021 | Jul-2021
2021-07-25 | W | 31 | - | 2021 | W31-2021 | Jul-2021
2021-07-26 | W | 31 | - | 2021 | W31-2021 | Jul-2021
2021-07-27 | W | 31 | - | 2021 | W31-2021 | Jul-2021
2021-07-28 | W | 31 | - | 2021 | W31-2021 | Jul-2021
2021-07-29 | W | 31 | - | 2021 | W31-2021 | Jul-2021
2021-07-30 | W | 31 | - | 2021 | W31-2021 | Jul-2021
2021-07-31 | W | 31 | - | 2021 | W31-2021 | Jul-2021
2021-08-01 | W | 32 | - | 2021 | W32-2021 | Aug-2021
2021-08-02 | W | 32 | - | 2021 | W32-2021 | Aug-2021
2021-08-03 | W | 32 | - | 2021 | W32-2021 | Aug-2021
2021-08-04 | W | 32 | - | 2021 | W32-2021 | Aug-2021
2021-08-05 | W | 32 | - | 2021 | W32-2021 | Aug-2021
2021-08-06 | W | 32 | - | 2021 | W32-2021 | Aug-2021
2021-08-07 | W | 32 | - | 2021 | W32-2021 | Aug-2021
2021-08-08 | W | 33 | - | 2021 | W33-2021 | Aug-2021
2021-08-09 | W | 33 | - | 2021 | W33-2021 | Aug-2021
2021-08-10 | W | 33 | - | 2021 | W33-2021 | Aug-2021
2021-08-11 | W | 33 | - | 2021 | W33-2021 | Aug-2021
2021-08-12 | W | 33 | - | 2021 | W33-2021 | Aug-2021
2021-08-13 | W | 33 | - | 2021 | W33-2021 | Aug-2021
2021-08-14 | W | 33 | - | 2021 | W33-2021 | Aug-2021
2021-08-15 | W | 34 | - | 2021 | W34-2021 | Aug-2021
2021-08-16 | W | 34 | - | 2021 | W34-2021 | Aug-2021
2021-08-17 | W | 34 | - | 2021 | W34-2021 | Aug-2021
2021-08-18 | W | 34 | - | 2021 | W34-2021 | Aug-2021
2021-08-19 | W | 34 | - | 2021 | W34-2021 | Aug-2021
2021-08-20 | W | 34 | - | 2021 | W34-2021 | Aug-2021
2021-08-21 | W | 34 | - | 2021 | W34-2021 | Aug-2021
2021-08-22 | W | 35 | - | 2021 | W35-2021 | Aug-2021
2021-08-23 | W | 35 | - | 2021 | W35-2021 | Aug-2021
2021-08-24 | W | 35 | - | 2021 | W35-2021 | Aug-2021
2021-08-25 | W | 35 | - | 2021 | W35-2021 | Aug-2021
2021-08-26 | W | 35 | - | 2021 | W35-2021 | Aug-2021
2021-08-27 | W | 35 | - | 2021 | W35-2021 | Aug-2021
2021-08-28 | W | 35 | - | 2021 | W35-2021 | Aug-2021
2021-08-29 | W | 36 | - | 2021 | W36-2021 | Aug-2021
2021-08-30 | W | 36 | - | 2021 | W36-2021 | Aug-2021
2021-08-31 | W | 36 | - | 2021 | W36-2021 | Aug-2021
2021-09-01 | W | 36 | - | 2021 | W36-2021 | Sep-2021
2021-09-02 | W | 36 | - | 2021 | W36-2021 | Sep-2021
2021-09-03 | W | 36 | - | 2021 | W36-2021 | Sep-2021
2021-09-04 | W | 36 | - | 2021 | W36-2021 | Sep-2021
2021-09-05 | W | 37 | - | 2021 | W37-2021 | Sep-2021
2021-09-06 | W | 37 | - | 2021 | W37-2021 | Sep-2021
2021-09-07 | W | 37 | - | 2021 | W37-2021 | Sep-2021
2021-09-08 | W | 37 | - | 2021 | W37-2021 | Sep-2021
2021-09-09 | W | 37 | - | 2021 | W37-2021 | Sep-2021
2021-09-10 | W | 37 | - | 2021 | W37-2021 | Sep-2021
2021-09-11 | W | 37 | - | 2021 | W37-2021 | Sep-2021
2021-09-12 | W | 38 | - | 2021 | W38-2021 | Sep-2021
2021-09-13 | W | 38 | - | 2021 | W38-2021 | Sep-2021
2021-09-14 | W | 38 | - | 2021 | W38-2021 | Sep-2021
2021-09-15 | W | 38 | - | 2021 | W38-2021 | Sep-2021
2021-09-16 | W | 38 | - | 2021 | W38-2021 | Sep-2021
2021-09-17 | W | 38 | - | 2021 | W38-2021 | Sep-2021
2021-09-18 | W | 38 | - | 2021 | W38-2021 | Sep-2021
2021-09-19 | W | 39 | - | 2021 | W39-2021 | Sep-2021
2021-09-20 | W | 39 | - | 2021 | W39-2021 | Sep-2021
2021-09-21 | W | 39 | - | 2021 | W39-2021 | Sep-2021
2021-09-22 | W | 39 | - | 2021 | W39-2021 | Sep-2021
2021-09-23 | W | 39 | - | 2021 | W39-2021 | Sep-2021
2021-09-24 | W | 39 | - | 2021 | W39-2021 | Sep-2021
2021-09-25 | W | 39 | - | 2021 | W39-2021 | Sep-2021
2021-09-26 | W | 40 | - | 2021 | W40-2021 | Sep-2021
2021-09-27 | W | 40 | - | 2021 | W40-2021 | Sep-2021
2021-09-28 | W | 40 | - | 2021 | W40-2021 | Sep-2021
2021-09-29 | W | 40 | - | 2021 | W40-2021 | Sep-2021
2021-09-30 | W | 40 | - | 2021 | W40-2021 | Sep-2021
2021-10-01 | W | 40 | - | 2021 | W40-2021 | Oct-2021
2021-10-02 | W | 40 | - | 2021 | W40-2021 | Oct-2021
2021-10-03 | W | 41 | - | 2021 | W41-2021 | Oct-2021
2021-10-04 | W | 41 | - | 2021 | W41-2021 | Oct-2021
2021-10-05 | W | 41 | - | 2021 | W41-2021 | Oct-2021
2021-10-06 | W | 41 | - | 2021 | W41-2021 | Oct-2021
2021-10-07 | W | 41 | - | 2021 | W41-2021 | Oct-2021
2021-10-08 | W | 41 | - | 2021 | W41-2021 | Oct-2021
2021-10-09 | W | 41 | - | 2021 | W41-2021 | Oct-2021
2021-10-10 | W | 42 | - | 2021 | W42-2021 | Oct-2021
2021-10-11 | W | 42 | - | 2021 | W42-2021 | Oct-2021
2021-10-12 | W | 42 | - | 2021 | W42-2021 | Oct-2021
2021-10-13 | W | 42 | - | 2021 | W42-2021 | Oct-2021
2021-10-14 | W | 42 | - | 2021 | W42-2021 | Oct-2021
2021-10-15 | W | 42 | - | 2021 | W42-2021 | Oct-2021
2021-10-16 | W | 42 | - | 2021 | W42-2021 | Oct-2021
2021-10-17 | W | 43 | - | 2021 | W43-2021 | Oct-2021
2021-10-18 | W | 43 | - | 2021 | W43-2021 | Oct-2021
2021-10-19 | W | 43 | - | 2021 | W43-2021 | Oct-2021
2021-10-20 | W | 43 | - | 2021 | W43-2021 | Oct-2021
2021-10-21 | W | 43 | - | 2021 | W43-2021 | Oct-2021
2021-10-22 | W | 43 | - | 2021 | W43-2021 | Oct-2021
2021-10-23 | W | 43 | - | 2021 | W43-2021 | Oct-2021
2021-10-24 | W | 44 | - | 2021 | W44-2021 | Oct-2021
2021-10-25 | W | 44 | - | 2021 | W44-2021 | Oct-2021
2021-10-26 | W | 44 | - | 2021 | W44-2021 | Oct-2021
2021-10-27 | W | 44 | - | 2021 | W44-2021 | Oct-2021
2021-10-28 | W | 44 | - | 2021 | W44-2021 | Oct-2021
2021-10-29 | W | 44 | - | 2021 | W44-2021 | Oct-2021
2021-10-30 | W | 44 | - | 2021 | W44-2021 | Oct-2021
2021-10-31 | W | 45 | - | 2021 | W45-2021 | Oct-2021
2021-11-01 | W | 45 | - | 2021 | W45-2021 | Nov-2021
2021-11-02 | W | 45 | - | 2021 | W45-2021 | Nov-2021
2021-11-03 | W | 45 | - | 2021 | W45-2021 | Nov-2021
2021-11-04 | W | 45 | - | 2021 | W45-2021 | Nov-2021
2021-11-05 | W | 45 | - | 2021 | W45-2021 | Nov-2021
2021-11-06 | W | 45 | - | 2021 | W45-2021 | Nov-2021
2021-11-07 | W | 46 | - | 2021 | W46-2021 | Nov-2021
2021-11-08 | W | 46 | - | 2021 | W46-2021 | Nov-2021
2021-11-09 | W | 46 | - | 2021 | W46-2021 | Nov-2021
2021-11-10 | W | 46 | - | 2021 | W46-2021 | Nov-2021
2021-11-11 | W | 46 | - | 2021 | W46-2021 | Nov-2021
2021-11-12 | W | 46 | - | 2021 | W46-2021 | Nov-2021
2021-11-13 | W | 46 | - | 2021 | W46-2021 | Nov-2021
2021-11-14 | W | 47 | - | 2021 | W47-2021 | Nov-2021
2021-11-15 | W | 47 | - | 2021 | W47-2021 | Nov-2021
2021-11-16 | W | 47 | - | 2021 | W47-2021 | Nov-2021
2021-11-17 | W | 47 | - | 2021 | W47-2021 | Nov-2021
2021-11-18 | W | 47 | - | 2021 | W47-2021 | Nov-2021
2021-11-19 | W | 47 | - | 2021 | W47-2021 | Nov-2021
2021-11-20 | W | 47 | - | 2021 | W47-2021 | Nov-2021
2021-11-21 | W | 48 | - | 2021 | W48-2021 | Nov-2021
2021-11-22 | W | 48 | - | 2021 | W48-2021 | Nov-2021
2021-11-23 | W | 48 | - | 2021 | W48-2021 | Nov-2021
2021-11-24 | W | 48 | - | 2021 | W48-2021 | Nov-2021
2021-11-25 | W | 48 | - | 2021 | W48-2021 | Nov-2021
2021-11-26 | W | 48 | - | 2021 | W48-2021 | Nov-2021
2021-11-27 | W | 48 | - | 2021 | W48-2021 | Nov-2021
2021-11-28 | W | 49 | - | 2021 | W49-2021 | Nov-2021
2021-11-29 | W | 49 | - | 2021 | W49-2021 | Nov-2021
2021-11-30 | W | 49 | - | 2021 | W49-2021 | Nov-2021
2021-12-01 | W | 49 | - | 2021 | W49-2021 | Dec-2021
2021-12-02 | W | 49 | - | 2021 | W49-2021 | Dec-2021
2021-12-03 | W | 49 | - | 2021 | W49-2021 | Dec-2021
2021-12-04 | W | 49 | - | 2021 | W49-2021 | Dec-2021
2021-12-05 | W | 50 | - | 2021 | W50-2021 | Dec-2021
2021-12-06 | W | 50 | - | 2021 | W50-2021 | Dec-2021
2021-12-07 | W | 50 | - | 2021 | W50-2021 | Dec-2021
2021-12-08 | W | 50 | - | 2021 | W50-2021 | Dec-2021
2021-12-09 | W | 50 | - | 2021 | W50-2021 | Dec-2021
2021-12-10 | W | 50 | - | 2021 | W50-2021 | Dec-2021
2021-12-11 | W | 50 | - | 2021 | W50-2021 | Dec-2021
2021-12-12 | W | 51 | - | 2021 | W51-2021 | Dec-2021
2021-12-13 | W | 51 | - | 2021 | W51-2021 | Dec-2021
2021-12-14 | W | 51 | - | 2021 | W51-2021 | Dec-2021
2021-12-15 | W | 51 | - | 2021 | W51-2021 | Dec-2021
2021-12-16 | W | 51 | - | 2021 | W51-2021 | Dec-2021
2021-12-17 | W | 51 | - | 2021 | W51-2021 | Dec-2021
2021-12-18 | W | 51 | - | 2021 | W51-2021 | Dec-2021
2021-12-19 | W | 52 | - | 2021 | W52-2021 | Dec-2021
2021-12-20 | W | 52 | - | 2021 | W52-2021 | Dec-2021
2021-12-21 | W | 52 | - | 2021 | W52-2021 | Dec-2021
2021-12-22 | W | 52 | - | 2021 | W52-2021 | Dec-2021
2021-12-23 | W | 52 | - | 2021 | W52-2021 | Dec-2021
2021-12-24 | W | 52 | - | 2021 | W52-2021 | Dec-2021
2021-12-25 | W | 52 | - | 2021 | W52-2021 | Dec-2021
2021-12-26 | W | 53 | - | 2021 | W53-2021 | Dec-2021
2021-12-27 | W | 53 | - | 2021 | W53-2021 | Dec-2021
2021-12-28 | W | 53 | - | 2021 | W53-2021 | Dec-2021
2021-12-29 | W | 53 | - | 2021 | W53-2021 | Dec-2021
2021-12-30 | W | 53 | - | 2021 | W53-2021 | Dec-2021
2021-12-31 | W | 53 | - | 2021 | W53-2021 | Dec-2021
2022-01-01 | W | 01 | - | 2022 | W01-2022 | Jan-2022
2022-01-02 | W | 02 | - | 2022 | W02-2022 | Jan-2022
2022-01-03 | W | 02 | - | 2022 | W02-2022 | Jan-2022
2022-01-04 | W | 02 | - | 2022 | W02-2022 | Jan-2022
2022-01-05 | W | 02 | - | 2022 | W02-2022 | Jan-2022
2022-01-06 | W | 02 | - | 2022 | W02-2022 | Jan-2022
2022-01-07 | W | 02 | - | 2022 | W02-2022 | Jan-2022
2022-01-08 | W | 02 | - | 2022 | W02-2022 | Jan-2022
2022-01-09 | W | 03 | - | 2022 | W03-2022 | Jan-2022
2022-01-10 | W | 03 | - | 2022 | W03-2022 | Jan-2022
2022-01-11 | W | 03 | - | 2022 | W03-2022 | Jan-2022
2022-01-12 | W | 03 | - | 2022 | W03-2022 | Jan-2022
2022-01-13 | W | 03 | - | 2022 | W03-2022 | Jan-2022
2022-01-14 | W | 03 | - | 2022 | W03-2022 | Jan-2022
2022-01-15 | W | 03 | - | 2022 | W03-2022 | Jan-2022
2022-01-16 | W | 04 | - | 2022 | W04-2022 | Jan-2022
2022-01-17 | W | 04 | - | 2022 | W04-2022 | Jan-2022
2022-01-18 | W | 04 | - | 2022 | W04-2022 | Jan-2022
2022-01-19 | W | 04 | - | 2022 | W04-2022 | Jan-2022
2022-01-20 | W | 04 | - | 2022 | W04-2022 | Jan-2022
2022-01-21 | W | 04 | - | 2022 | W04-2022 | Jan-2022
2022-01-22 | W | 04 | - | 2022 | W04-2022 | Jan-2022
2022-01-23 | W | 05 | - | 2022 | W05-2022 | Jan-2022
2022-01-24 | W | 05 | - | 2022 | W05-2022 | Jan-2022
2022-01-25 | W | 05 | - | 2022 | W05-2022 | Jan-2022
2022-01-26 | W | 05 | - | 2022 | W05-2022 | Jan-2022
2022-01-27 | W | 05 | - | 2022 | W05-2022 | Jan-2022
2022-01-28 | W | 05 | - | 2022 | W05-2022 | Jan-2022
2022-01-29 | W | 05 | - | 2022 | W05-2022 | Jan-2022
2022-01-30 | W | 06 | - | 2022 | W06-2022 | Jan-2022
2022-01-31 | W | 06 | - | 2022 | W06-2022 | Jan-2022
2022-02-01 | W | 06 | - | 2022 | W06-2022 | Feb-2022
2022-02-02 | W | 06 | - | 2022 | W06-2022 | Feb-2022
2022-02-03 | W | 06 | - | 2022 | W06-2022 | Feb-2022
2022-02-04 | W | 06 | - | 2022 | W06-2022 | Feb-2022
2022-02-05 | W | 06 | - | 2022 | W06-2022 | Feb-2022
2022-02-06 | W | 07 | - | 2022 | W07-2022 | Feb-2022
2022-02-07 | W | 07 | - | 2022 | W07-2022 | Feb-2022
2022-02-08 | W | 07 | - | 2022 | W07-2022 | Feb-2022
2022-02-09 | W | 07 | - | 2022 | W07-2022 | Feb-2022
2022-02-10 | W | 07 | - | 2022 | W07-2022 | Feb-2022
2022-02-11 | W | 07 | - | 2022 | W07-2022 | Feb-2022
2022-02-12 | W | 07 | - | 2022 | W07-2022 | Feb-2022
2022-02-13 | W | 08 | - | 2022 | W08-2022 | Feb-2022
2022-02-14 | W | 08 | - | 2022 | W08-2022 | Feb-2022
2022-02-15 | W | 08 | - | 2022 | W08-2022 | Feb-2022
2022-02-16 | W | 08 | - | 2022 | W08-2022 | Feb-2022
2022-02-17 | W | 08 | - | 2022 | W08-2022 | Feb-2022
2022-02-18 | W | 08 | - | 2022 | W08-2022 | Feb-2022
2022-02-19 | W | 08 | - | 2022 | W08-2022 | Feb-2022
2022-02-20 | W | 09 | - | 2022 | W09-2022 | Feb-2022
2022-02-21 | W | 09 | - | 2022 | W09-2022 | Feb-2022
2022-02-22 | W | 09 | - | 2022 | W09-2022 | Feb-2022
2022-02-23 | W | 09 | - | 2022 | W09-2022 | Feb-2022
2022-02-24 | W | 09 | - | 2022 | W09-2022 | Feb-2022
2022-02-25 | W | 09 | - | 2022 | W09-2022 | Feb-2022
2022-02-26 | W | 09 | - | 2022 | W09-2022 | Feb-2022
2022-02-27 | W | 10 | - | 2022 | W10-2022 | Feb-2022
2022-02-28 | W | 10 | - | 2022 | W10-2022 | Feb-2022
2022-03-01 | W | 10 | - | 2022 | W10-2022 | Mar-2022
2022-03-02 | W | 10 | - | 2022 | W10-2022 | Mar-2022
2022-03-03 | W | 10 | - | 2022 | W10-2022 | Mar-2022
2022-03-04 | W | 10 | - | 2022 | W10-2022 | Mar-2022
2022-03-05 | W | 10 | - | 2022 | W10-2022 | Mar-2022
2022-03-06 | W | 11 | - | 2022 | W11-2022 | Mar-2022
2022-03-07 | W | 11 | - | 2022 | W11-2022 | Mar-2022
2022-03-08 | W | 11 | - | 2022 | W11-2022 | Mar-2022
2022-03-09 | W | 11 | - | 2022 | W11-2022 | Mar-2022
2022-03-10 | W | 11 | - | 2022 | W11-2022 | Mar-2022
2022-03-11 | W | 11 | - | 2022 | W11-2022 | Mar-2022
2022-03-12 | W | 11 | - | 2022 | W11-2022 | Mar-2022
2022-03-13 | W | 12 | - | 2022 | W12-2022 | Mar-2022
2022-03-14 | W | 12 | - | 2022 | W12-2022 | Mar-2022
2022-03-15 | W | 12 | - | 2022 | W12-2022 | Mar-2022
2022-03-16 | W | 12 | - | 2022 | W12-2022 | Mar-2022
2022-03-17 | W | 12 | - | 2022 | W12-2022 | Mar-2022
2022-03-18 | W | 12 | - | 2022 | W12-2022 | Mar-2022
2022-03-19 | W | 12 | - | 2022 | W12-2022 | Mar-2022
2022-03-20 | W | 13 | - | 2022 | W13-2022 | Mar-2022
2022-03-21 | W | 13 | - | 2022 | W13-2022 | Mar-2022
2022-03-22 | W | 13 | - | 2022 | W13-2022 | Mar-2022
2022-03-23 | W | 13 | - | 2022 | W13-2022 | Mar-2022
2022-03-24 | W | 13 | - | 2022 | W13-2022 | Mar-2022
2022-03-25 | W | 13 | - | 2022 | W13-2022 | Mar-2022
2022-03-26 | W | 13 | - | 2022 | W13-2022 | Mar-2022
2022-03-27 | W | 14 | - | 2022 | W14-2022 | Mar-2022
2022-03-28 | W | 14 | - | 2022 | W14-2022 | Mar-2022
2022-03-29 | W | 14 | - | 2022 | W14-2022 | Mar-2022
2022-03-30 | W | 14 | - | 2022 | W14-2022 | Mar-2022
2022-03-31 | W | 14 | - | 2022 | W14-2022 | Mar-2022
2022-04-01 | W | 14 | - | 2022 | W14-2022 | Apr-2022
2022-04-02 | W | 14 | - | 2022 | W14-2022 | Apr-2022
2022-04-03 | W | 15 | - | 2022 | W15-2022 | Apr-2022
2022-04-04 | W | 15 | - | 2022 | W15-2022 | Apr-2022
2022-04-05 | W | 15 | - | 2022 | W15-2022 | Apr-2022
2022-04-06 | W | 15 | - | 2022 | W15-2022 | Apr-2022
2022-04-07 | W | 15 | - | 2022 | W15-2022 | Apr-2022
2022-04-08 | W | 15 | - | 2022 | W15-2022 | Apr-2022
2022-04-09 | W | 15 | - | 2022 | W15-2022 | Apr-2022
2022-04-10 | W | 16 | - | 2022 | W16-2022 | Apr-2022
2022-04-11 | W | 16 | - | 2022 | W16-2022 | Apr-2022
2022-04-12 | W | 16 | - | 2022 | W16-2022 | Apr-2022
2022-04-13 | W | 16 | - | 2022 | W16-2022 | Apr-2022
2022-04-14 | W | 16 | - | 2022 | W16-2022 | Apr-2022
2022-04-15 | W | 16 | - | 2022 | W16-2022 | Apr-2022
2022-04-16 | W | 16 | - | 2022 | W16-2022 | Apr-2022
2022-04-17 | W | 17 | - | 2022 | W17-2022 | Apr-2022
2022-04-18 | W | 17 | - | 2022 | W17-2022 | Apr-2022
2022-04-19 | W | 17 | - | 2022 | W17-2022 | Apr-2022
2022-04-20 | W | 17 | - | 2022 | W17-2022 | Apr-2022
2022-04-21 | W | 17 | - | 2022 | W17-2022 | Apr-2022
2022-04-22 | W | 17 | - | 2022 | W17-2022 | Apr-2022
2022-04-23 | W | 17 | - | 2022 | W17-2022 | Apr-2022
2022-04-24 | W | 18 | - | 2022 | W18-2022 | Apr-2022
2022-04-25 | W | 18 | - | 2022 | W18-2022 | Apr-2022
2022-04-26 | W | 18 | - | 2022 | W18-2022 | Apr-2022
2022-04-27 | W | 18 | - | 2022 | W18-2022 | Apr-2022
2022-04-28 | W | 18 | - | 2022 | W18-2022 | Apr-2022
2022-04-29 | W | 18 | - | 2022 | W18-2022 | Apr-2022
2022-04-30 | W | 18 | - | 2022 | W18-2022 | Apr-2022
2022-05-01 | W | 19 | - | 2022 | W19-2022 | May-2022
2022-05-02 | W | 19 | - | 2022 | W19-2022 | May-2022
2022-05-03 | W | 19 | - | 2022 | W19-2022 | May-2022
2022-05-04 | W | 19 | - | 2022 | W19-2022 | May-2022
2022-05-05 | W | 19 | - | 2022 | W19-2022 | May-2022
2022-05-06 | W | 19 | - | 2022 | W19-2022 | May-2022
2022-05-07 | W | 19 | - | 2022 | W19-2022 | May-2022
2022-05-08 | W | 20 | - | 2022 | W20-2022 | May-2022
2022-05-09 | W | 20 | - | 2022 | W20-2022 | May-2022
2022-05-10 | W | 20 | - | 2022 | W20-2022 | May-2022
2022-05-11 | W | 20 | - | 2022 | W20-2022 | May-2022
2022-05-12 | W | 20 | - | 2022 | W20-2022 | May-2022
2022-05-13 | W | 20 | - | 2022 | W20-2022 | May-2022
2022-05-14 | W | 20 | - | 2022 | W20-2022 | May-2022
2022-05-15 | W | 21 | - | 2022 | W21-2022 | May-2022
2022-05-16 | W | 21 | - | 2022 | W21-2022 | May-2022
2022-05-17 | W | 21 | - | 2022 | W21-2022 | May-2022
2022-05-18 | W | 21 | - | 2022 | W21-2022 | May-2022
2022-05-19 | W | 21 | - | 2022 | W21-2022 | May-2022
2022-05-20 | W | 21 | - | 2022 | W21-2022 | May-2022
2022-05-21 | W | 21 | - | 2022 | W21-2022 | May-2022
2022-05-22 | W | 22 | - | 2022 | W22-2022 | May-2022
2022-05-23 | W | 22 | - | 2022 | W22-2022 | May-2022
2022-05-24 | W | 22 | - | 2022 | W22-2022 | May-2022
2022-05-25 | W | 22 | - | 2022 | W22-2022 | May-2022
2022-05-26 | W | 22 | - | 2022 | W22-2022 | May-2022
2022-05-27 | W | 22 | - | 2022 | W22-2022 | May-2022
2022-05-28 | W | 22 | - | 2022 | W22-2022 | May-2022
2022-05-29 | W | 23 | - | 2022 | W23-2022 | May-2022
2022-05-30 | W | 23 | - | 2022 | W23-2022 | May-2022
2022-05-31 | W | 23 | - | 2022 | W23-2022 | May-2022
2022-06-01 | W | 23 | - | 2022 | W23-2022 | Jun-2022
2022-06-02 | W | 23 | - | 2022 | W23-2022 | Jun-2022
2022-06-03 | W | 23 | - | 2022 | W23-2022 | Jun-2022
2022-06-04 | W | 23 | - | 2022 | W23-2022 | Jun-2022
2022-06-05 | W | 24 | - | 2022 | W24-2022 | Jun-2022
2022-06-06 | W | 24 | - | 2022 | W24-2022 | Jun-2022
2022-06-07 | W | 24 | - | 2022 | W24-2022 | Jun-2022
2022-06-08 | W | 24 | - | 2022 | W24-2022 | Jun-2022
2022-06-09 | W | 24 | - | 2022 | W24-2022 | Jun-2022
2022-06-10 | W | 24 | - | 2022 | W24-2022 | Jun-2022
2022-06-11 | W | 24 | - | 2022 | W24-2022 | Jun-2022
2022-06-12 | W | 25 | - | 2022 | W25-2022 | Jun-2022
2022-06-13 | W | 25 | - | 2022 | W25-2022 | Jun-2022
2022-06-14 | W | 25 | - | 2022 | W25-2022 | Jun-2022
2022-06-15 | W | 25 | - | 2022 | W25-2022 | Jun-2022
2022-06-16 | W | 25 | - | 2022 | W25-2022 | Jun-2022
2022-06-17 | W | 25 | - | 2022 | W25-2022 | Jun-2022
2022-06-18 | W | 25 | - | 2022 | W25-2022 | Jun-2022
2022-06-19 | W | 26 | - | 2022 | W26-2022 | Jun-2022
2022-06-20 | W | 26 | - | 2022 | W26-2022 | Jun-2022
2022-06-21 | W | 26 | - | 2022 | W26-2022 | Jun-2022
2022-06-22 | W | 26 | - | 2022 | W26-2022 | Jun-2022
2022-06-23 | W | 26 | - | 2022 | W26-2022 | Jun-2022
2022-06-24 | W | 26 | - | 2022 | W26-2022 | Jun-2022
2022-06-25 | W | 26 | - | 2022 | W26-2022 | Jun-2022
2022-06-26 | W | 27 | - | 2022 | W27-2022 | Jun-2022
2022-06-27 | W | 27 | - | 2022 | W27-2022 | Jun-2022
2022-06-28 | W | 27 | - | 2022 | W27-2022 | Jun-2022
2022-06-29 | W | 27 | - | 2022 | W27-2022 | Jun-2022
2022-06-30 | W | 27 | - | 2022 | W27-2022 | Jun-2022
2022-07-01 | W | 27 | - | 2022 | W27-2022 | Jul-2022
2022-07-02 | W | 27 | - | 2022 | W27-2022 | Jul-2022
2022-07-03 | W | 28 | - | 2022 | W28-2022 | Jul-2022
2022-07-04 | W | 28 | - | 2022 | W28-2022 | Jul-2022
2022-07-05 | W | 28 | - | 2022 | W28-2022 | Jul-2022
2022-07-06 | W | 28 | - | 2022 | W28-2022 | Jul-2022
2022-07-07 | W | 28 | - | 2022 | W28-2022 | Jul-2022
2022-07-08 | W | 28 | - | 2022 | W28-2022 | Jul-2022
2022-07-09 | W | 28 | - | 2022 | W28-2022 | Jul-2022
2022-07-10 | W | 29 | - | 2022 | W29-2022 | Jul-2022
2022-07-11 | W | 29 | - | 2022 | W29-2022 | Jul-2022
2022-07-12 | W | 29 | - | 2022 | W29-2022 | Jul-2022
2022-07-13 | W | 29 | - | 2022 | W29-2022 | Jul-2022
2022-07-14 | W | 29 | - | 2022 | W29-2022 | Jul-2022
2022-07-15 | W | 29 | - | 2022 | W29-2022 | Jul-2022
2022-07-16 | W | 29 | - | 2022 | W29-2022 | Jul-2022
2022-07-17 | W | 30 | - | 2022 | W30-2022 | Jul-2022
2022-07-18 | W | 30 | - | 2022 | W30-2022 | Jul-2022
2022-07-19 | W | 30 | - | 2022 | W30-2022 | Jul-2022
2022-07-20 | W | 30 | - | 2022 | W30-2022 | Jul-2022
2022-07-21 | W | 30 | - | 2022 | W30-2022 | Jul-2022
2022-07-22 | W | 30 | - | 2022 | W30-2022 | Jul-2022
2022-07-23 | W | 30 | - | 2022 | W30-2022 | Jul-2022
2022-07-24 | W | 31 | - | 2022 | W31-2022 | Jul-2022
2022-07-25 | W | 31 | - | 2022 | W31-2022 | Jul-2022
2022-07-26 | W | 31 | - | 2022 | W31-2022 | Jul-2022
2022-07-27 | W | 31 | - | 2022 | W31-2022 | Jul-2022
2022-07-28 | W | 31 | - | 2022 | W31-2022 | Jul-2022
2022-07-29 | W | 31 | - | 2022 | W31-2022 | Jul-2022
2022-07-30 | W | 31 | - | 2022 | W31-2022 | Jul-2022
2022-07-31 | W | 32 | - | 2022 | W32-2022 | Jul-2022
2022-08-01 | W | 32 | - | 2022 | W32-2022 | Aug-2022
2022-08-02 | W | 32 | - | 2022 | W32-2022 | Aug-2022
2022-08-03 | W | 32 | - | 2022 | W32-2022 | Aug-2022
2022-08-04 | W | 32 | - | 2022 | W32-2022 | Aug-2022
2022-08-05 | W | 32 | - | 2022 | W32-2022 | Aug-2022
2022-08-06 | W | 32 | - | 2022 | W32-2022 | Aug-2022
2022-08-07 | W | 33 | - | 2022 | W33-2022 | Aug-2022
2022-08-08 | W | 33 | - | 2022 | W33-2022 | Aug-2022
2022-08-09 | W | 33 | - | 2022 | W33-2022 | Aug-2022
2022-08-10 | W | 33 | - | 2022 | W33-2022 | Aug-2022
2022-08-11 | W | 33 | - | 2022 | W33-2022 | Aug-2022
2022-08-12 | W | 33 | - | 2022 | W33-2022 | Aug-2022
2022-08-13 | W | 33 | - | 2022 | W33-2022 | Aug-2022
2022-08-14 | W | 34 | - | 2022 | W34-2022 | Aug-2022
2022-08-15 | W | 34 | - | 2022 | W34-2022 | Aug-2022
2022-08-16 | W | 34 | - | 2022 | W34-2022 | Aug-2022
2022-08-17 | W | 34 | - | 2022 | W34-2022 | Aug-2022
2022-08-18 | W | 34 | - | 2022 | W34-2022 | Aug-2022
2022-08-19 | W | 34 | - | 2022 | W34-2022 | Aug-2022
2022-08-20 | W | 34 | - | 2022 | W34-2022 | Aug-2022
2022-08-21 | W | 35 | - | 2022 | W35-2022 | Aug-2022
2022-08-22 | W | 35 | - | 2022 | W35-2022 | Aug-2022
2022-08-23 | W | 35 | - | 2022 | W35-2022 | Aug-2022
2022-08-24 | W | 35 | - | 2022 | W35-2022 | Aug-2022
2022-08-25 | W | 35 | - | 2022 | W35-2022 | Aug-2022
2022-08-26 | W | 35 | - | 2022 | W35-2022 | Aug-2022
2022-08-27 | W | 35 | - | 2022 | W35-2022 | Aug-2022
2022-08-28 | W | 36 | - | 2022 | W36-2022 | Aug-2022
2022-08-29 | W | 36 | - | 2022 | W36-2022 | Aug-2022
2022-08-30 | W | 36 | - | 2022 | W36-2022 | Aug-2022
2022-08-31 | W | 36 | - | 2022 | W36-2022 | Aug-2022
2022-09-01 | W | 36 | - | 2022 | W36-2022 | Sep-2022
2022-09-02 | W | 36 | - | 2022 | W36-2022 | Sep-2022
2022-09-03 | W | 36 | - | 2022 | W36-2022 | Sep-2022
2022-09-04 | W | 37 | - | 2022 | W37-2022 | Sep-2022
2022-09-05 | W | 37 | - | 2022 | W37-2022 | Sep-2022
2022-09-06 | W | 37 | - | 2022 | W37-2022 | Sep-2022
2022-09-07 | W | 37 | - | 2022 | W37-2022 | Sep-2022
2022-09-08 | W | 37 | - | 2022 | W37-2022 | Sep-2022
2022-09-09 | W | 37 | - | 2022 | W37-2022 | Sep-2022
2022-09-10 | W | 37 | - | 2022 | W37-2022 | Sep-2022
2022-09-11 | W | 38 | - | 2022 | W38-2022 | Sep-2022
2022-09-12 | W | 38 | - | 2022 | W38-2022 | Sep-2022
2022-09-13 | W | 38 | - | 2022 | W38-2022 | Sep-2022
2022-09-14 | W | 38 | - | 2022 | W38-2022 | Sep-2022
2022-09-15 | W | 38 | - | 2022 | W38-2022 | Sep-2022
2022-09-16 | W | 38 | - | 2022 | W38-2022 | Sep-2022
2022-09-17 | W | 38 | - | 2022 | W38-2022 | Sep-2022
2022-09-18 | W | 39 | - | 2022 | W39-2022 | Sep-2022
2022-09-19 | W | 39 | - | 2022 | W39-2022 | Sep-2022
2022-09-20 | W | 39 | - | 2022 | W39-2022 | Sep-2022
2022-09-21 | W | 39 | - | 2022 | W39-2022 | Sep-2022
2022-09-22 | W | 39 | - | 2022 | W39-2022 | Sep-2022
2022-09-23 | W | 39 | - | 2022 | W39-2022 | Sep-2022
2022-09-24 | W | 39 | - | 2022 | W39-2022 | Sep-2022
2022-09-25 | W | 40 | - | 2022 | W40-2022 | Sep-2022
2022-09-26 | W | 40 | - | 2022 | W40-2022 | Sep-2022
2022-09-27 | W | 40 | - | 2022 | W40-2022 | Sep-2022
2022-09-28 | W | 40 | - | 2022 | W40-2022 | Sep-2022
2022-09-29 | W | 40 | - | 2022 | W40-2022 | Sep-2022
2022-09-30 | W | 40 | - | 2022 | W40-2022 | Sep-2022
2022-10-01 | W | 40 | - | 2022 | W40-2022 | Oct-2022
2022-10-02 | W | 41 | - | 2022 | W41-2022 | Oct-2022
2022-10-03 | W | 41 | - | 2022 | W41-2022 | Oct-2022
2022-10-04 | W | 41 | - | 2022 | W41-2022 | Oct-2022
2022-10-05 | W | 41 | - | 2022 | W41-2022 | Oct-2022
2022-10-06 | W | 41 | - | 2022 | W41-2022 | Oct-2022
2022-10-07 | W | 41 | - | 2022 | W41-2022 | Oct-2022
2022-10-08 | W | 41 | - | 2022 | W41-2022 | Oct-2022
2022-10-09 | W | 42 | - | 2022 | W42-2022 | Oct-2022
2022-10-10 | W | 42 | - | 2022 | W42-2022 | Oct-2022
2022-10-11 | W | 42 | - | 2022 | W42-2022 | Oct-2022
2022-10-12 | W | 42 | - | 2022 | W42-2022 | Oct-2022
2022-10-13 | W | 42 | - | 2022 | W42-2022 | Oct-2022
2022-10-14 | W | 42 | - | 2022 | W42-2022 | Oct-2022
2022-10-15 | W | 42 | - | 2022 | W42-2022 | Oct-2022
2022-10-16 | W | 43 | - | 2022 | W43-2022 | Oct-2022
2022-10-17 | W | 43 | - | 2022 | W43-2022 | Oct-2022
2022-10-18 | W | 43 | - | 2022 | W43-2022 | Oct-2022
2022-10-19 | W | 43 | - | 2022 | W43-2022 | Oct-2022
2022-10-20 | W | 43 | - | 2022 | W43-2022 | Oct-2022
2022-10-21 | W | 43 | - | 2022 | W43-2022 | Oct-2022
2022-10-22 | W | 43 | - | 2022 | W43-2022 | Oct-2022
2022-10-23 | W | 44 | - | 2022 | W44-2022 | Oct-2022
2022-10-24 | W | 44 | - | 2022 | W44-2022 | Oct-2022
2022-10-25 | W | 44 | - | 2022 | W44-2022 | Oct-2022
2022-10-26 | W | 44 | - | 2022 | W44-2022 | Oct-2022
2022-10-27 | W | 44 | - | 2022 | W44-2022 | Oct-2022
2022-10-28 | W | 44 | - | 2022 | W44-2022 | Oct-2022
2022-10-29 | W | 44 | - | 2022 | W44-2022 | Oct-2022
2022-10-30 | W | 45 | - | 2022 | W45-2022 | Oct-2022
2022-10-31 | W | 45 | - | 2022 | W45-2022 | Oct-2022
2022-11-01 | W | 45 | - | 2022 | W45-2022 | Nov-2022
2022-11-02 | W | 45 | - | 2022 | W45-2022 | Nov-2022
2022-11-03 | W | 45 | - | 2022 | W45-2022 | Nov-2022
2022-11-04 | W | 45 | - | 2022 | W45-2022 | Nov-2022
2022-11-05 | W | 45 | - | 2022 | W45-2022 | Nov-2022
2022-11-06 | W | 46 | - | 2022 | W46-2022 | Nov-2022
2022-11-07 | W | 46 | - | 2022 | W46-2022 | Nov-2022
2022-11-08 | W | 46 | - | 2022 | W46-2022 | Nov-2022
2022-11-09 | W | 46 | - | 2022 | W46-2022 | Nov-2022
2022-11-10 | W | 46 | - | 2022 | W46-2022 | Nov-2022
2022-11-11 | W | 46 | - | 2022 | W46-2022 | Nov-2022
2022-11-12 | W | 46 | - | 2022 | W46-2022 | Nov-2022
2022-11-13 | W | 47 | - | 2022 | W47-2022 | Nov-2022
2022-11-14 | W | 47 | - | 2022 | W47-2022 | Nov-2022
2022-11-15 | W | 47 | - | 2022 | W47-2022 | Nov-2022
2022-11-16 | W | 47 | - | 2022 | W47-2022 | Nov-2022
2022-11-17 | W | 47 | - | 2022 | W47-2022 | Nov-2022
2022-11-18 | W | 47 | - | 2022 | W47-2022 | Nov-2022
2022-11-19 | W | 47 | - | 2022 | W47-2022 | Nov-2022
2022-11-20 | W | 48 | - | 2022 | W48-2022 | Nov-2022
2022-11-21 | W | 48 | - | 2022 | W48-2022 | Nov-2022
2022-11-22 | W | 48 | - | 2022 | W48-2022 | Nov-2022
2022-11-23 | W | 48 | - | 2022 | W48-2022 | Nov-2022
2022-11-24 | W | 48 | - | 2022 | W48-2022 | Nov-2022
2022-11-25 | W | 48 | - | 2022 | W48-2022 | Nov-2022
2022-11-26 | W | 48 | - | 2022 | W48-2022 | Nov-2022
2022-11-27 | W | 49 | - | 2022 | W49-2022 | Nov-2022
2022-11-28 | W | 49 | - | 2022 | W49-2022 | Nov-2022
2022-11-29 | W | 49 | - | 2022 | W49-2022 | Nov-2022
2022-11-30 | W | 49 | - | 2022 | W49-2022 | Nov-2022
2022-12-01 | W | 49 | - | 2022 | W49-2022 | Dec-2022
2022-12-02 | W | 49 | - | 2022 | W49-2022 | Dec-2022
2022-12-03 | W | 49 | - | 2022 | W49-2022 | Dec-2022
2022-12-04 | W | 50 | - | 2022 | W50-2022 | Dec-2022
2022-12-05 | W | 50 | - | 2022 | W50-2022 | Dec-2022
2022-12-06 | W | 50 | - | 2022 | W50-2022 | Dec-2022
2022-12-07 | W | 50 | - | 2022 | W50-2022 | Dec-2022
2022-12-08 | W | 50 | - | 2022 | W50-2022 | Dec-2022
2022-12-09 | W | 50 | - | 2022 | W50-2022 | Dec-2022
2022-12-10 | W | 50 | - | 2022 | W50-2022 | Dec-2022
2022-12-11 | W | 51 | - | 2022 | W51-2022 | Dec-2022
2022-12-12 | W | 51 | - | 2022 | W51-2022 | Dec-2022
2022-12-13 | W | 51 | - | 2022 | W51-2022 | Dec-2022
2022-12-14 | W | 51 | - | 2022 | W51-2022 | Dec-2022
2022-12-15 | W | 51 | - | 2022 | W51-2022 | Dec-2022
2022-12-16 | W | 51 | - | 2022 | W51-2022 | Dec-2022
2022-12-17 | W | 51 | - | 2022 | W51-2022 | Dec-2022
2022-12-18 | W | 52 | - | 2022 | W52-2022 | Dec-2022
2022-12-19 | W | 52 | - | 2022 | W52-2022 | Dec-2022
2022-12-20 | W | 52 | - | 2022 | W52-2022 | Dec-2022
2022-12-21 | W | 52 | - | 2022 | W52-2022 | Dec-2022
2022-12-22 | W | 52 | - | 2022 | W52-2022 | Dec-2022
2022-12-23 | W | 52 | - | 2022 | W52-2022 | Dec-2022
2022-12-24 | W | 52 | - | 2022 | W52-2022 | Dec-2022
2022-12-25 | W | 53 | - | 2022 | W53-2022 | Dec-2022
2022-12-26 | W | 53 | - | 2022 | W53-2022 | Dec-2022
2022-12-27 | W | 53 | - | 2022 | W53-2022 | Dec-2022
2022-12-28 | W | 53 | - | 2022 | W53-2022 | Dec-2022
2022-12-29 | W | 53 | - | 2022 | W53-2022 | Dec-2022
2022-12-30 | W | 53 | - | 2022 | W53-2022 | Dec-2022
2022-12-31 | W | 53 | - | 2022 | W53-2022 | Dec-2022
Formulas:
ULK = WEEKNUM([ULK])
ULK = 0&WEEKNUM([ULK])

## SUMMARY
Status | (Multiple Items)
TECH PART | (All)
REGION XL | (All)
Count of SITE NAME XL |  |  |  |  | RFI REV. (W)
CME BY | SOW | CURRENT PROGRESS | PROBLEM CLASS | SPK DURATION (RANGE) | W10-2022 | W18-2022 | W19-2022 | W20-2022 | W21-2022 | W22-2022 | W23-2022 | W24-2022 | W26-2022 | W31-2022 | W36-2022 | TBD | Grand Total
TBG | COLO | 07.ESR preparation | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 2 | 2
|  | 08.Under RNP review | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 5 | 5
|  |  |  | 31 - 60 days | [11 empty] | 3 | 3
|  |  | NEED STRENGTENING (NY PARALEL) | < 30 days | [11 empty] | 1 | 1
|  |  | RND NOK: CHANGE DESIGN | 31 - 60 days | [11 empty] | 2 | 2
|  | 09.Under TNP review | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 1 | 1
|  | 10.Under CIVIL review | NEED STRENGTENING PARALEL | < 30 days | [11 empty] | 1 | 1
|  | 10.Under PWR review | CURRENTLY NO ISSUE | 31 - 60 days | [11 empty] | 33 | 33
|  |  | NEED STRENGTENING (NY PARALEL) | 31 - 60 days | [11 empty] | 5 | 5
|  | 19.Mobilisasi dan Demobilisasi | CURRENTLY NO ISSUE | < 30 days | [5 empty] | 1 | [6 empty] | 1
|  |  | NEED STRENGTENING (NY PARALEL) | < 30 days | [9 empty] | 1 |  |  | 1
|  |  |  | 31 - 60 days | [11 empty] | 1 | 1
|  |  | EXTEND TOWER (NY PARALEL) | 31 - 60 days | [9 empty] | 1 | 1 |  | 2
|  |  | NEED TOWER SST (NY PARALEL) | 31 - 60 days | [11 empty] | 1 | 1
|  | 31.RBS/BTS Foundation | CURRENTLY NO ISSUE | < 30 days | [5 empty] | 1 | [6 empty] | 1
|  |  | NEED STRENGTENING (NY PARALEL) & RND NOK: NEED 50M | 61 - 90 days | [7 empty] | 1 |  |  |  |  | 1
|  |  | NEED STRENGTENING (NY PARALEL) & COMMCASE | < 30 days | [6 empty] | 1 | [5 empty] | 1
|  |  | EXTEND TOWER (NY PARALEL) | 31 - 60 days | [9 empty] | 1 |  |  | 1
|  |  | NEED STRENGTENING PARALEL & COMMCASE | 61 - 90 days |  | 1 | [10 empty] | 1
|  | 36.PLN application | COMMCASE | 61 - 90 days | [11 empty] | 1 | 1
|  |  | CURRENTLY NO ISSUE | 61 - 90 days |  | 1 | [9 empty] | 7 | 8
|  |  | NEED STRENGTENING (NY PARALEL) | 61 - 90 days | [6 empty] | 1 | 2 |  |  |  |  | 3
|  |  | NEED STRENGTENING PARALEL | 31 - 60 days | [7 empty] | 1 |  |  |  |  | 1
|  |  | KWH KOSONG | 61 - 90 days |  |  |  |  | 6 |  |  | 5 |  |  |  |  | 11
|  |  | STR DONE | 61 - 90 days |  | 1 |  |  | 1 | [6 empty] | 4 | 6
|  |  | NEED STRENGTENING PARALEL, OVERBLAST | 61 - 90 days |  | 1 | [10 empty] | 1
|  |  | STR DONE, OVERBLAST | 61 - 90 days | [5 empty] | 2 | [6 empty] | 2
|  |  | OVB | 61 - 90 days | [5 empty] | 1 | [6 empty] | 1
|  | 37.Power connection process | COMMCASE | 61 - 90 days |  |  |  |  | 1 | [7 empty] | 1
|  |  | CURRENTLY NO ISSUE | 31 - 60 days |  |  |  | 1 | [8 empty] | 1
|  |  | NEED STRENGTENING PARALEL | 31 - 60 days |  | 1 | [10 empty] | 1
|  |  |  | 61 - 90 days |  | 1 | [10 empty] | 1
|  |  | KWH KOSONG | 61 - 90 days | [7 empty] | 4 |  |  |  |  | 4
|  |  | WAITING EXTEND TOWER, RFI&STR DONE | 61 - 90 days |  |  |  |  | 1 | [7 empty] | 1
|  |  | STR DONE | 61 - 90 days |  | 2 | [10 empty] | 2
|  |  | NEED STRENGTENING PARALEL, OVB | 61 - 90 days | [5 empty] | 1 | [6 empty] | 1
| COLO Total |  |  |  |  | 8 |  | 1 | 9 | 6 | 2 | 13 |  | 3 | 1 | 67 | 110
| B2S | 03.Survey ny start | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 6 | 6
|  |  | PROPOSED TO COLO | < 30 days | [11 empty] | 4 | 4
|  |  | PROPOSE TO COLO | < 30 days | [11 empty] | 2 | 2
|  | 04.Survey OG | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 3 | 3
|  |  |  | 31 - 60 days | [11 empty] | 1 | 1
|  |  | PROPOSE TO COLO | 31 - 60 days | [11 empty] | 1 | 1
|  |  | SAR ON TN KOMODO | < 30 days | [11 empty] | 3 | 3
|  | 05.Hunting OG | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 1 | 1
|  | 06.Rehunting OG | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 5 | 5
|  |  |  | 31 - 60 days | [11 empty] | 7 | 7
|  |  |  | 61 - 90 days | [11 empty] | 1 | 1
|  |  |  | 91 - 120 days | [11 empty] | 4 | 4
|  |  | NEAR EXISTING XL | 91 - 120 days | [11 empty] | 1 | 1
|  |  | HARDSITAC NO FREE SPACE | 61 - 90 days | [11 empty] | 1 | 1
|  |  | HARDSITAC LACK OF FREE SPACE | 91 - 120 days | [11 empty] | 1 | 1
|  |  | NO POWER, TBG PROPOSE SOLAR CELL | 31 - 60 days | [11 empty] | 2 | 2
|  |  | CELL PLAN ISSUE | 31 - 60 days | [11 empty] | 1 | 1
|  | 08.RNP review nok | CURRENTLY NO ISSUE | 91 - 120 days | [11 empty] | 1 | 1
|  | 08.Under RNP review | COMMCASE | 31 - 60 days | [11 empty] | 1 | 1
|  |  | CURRENTLY NO ISSUE | 31 - 60 days | [11 empty] | 3 | 3
|  |  |  | 91 - 120 days | [11 empty] | 1 | 1
|  |  | PENOLAKAN WARGA | 91 - 120 days | [11 empty] | 1 | 1
|  |  | ISSUE PERUNTUKAN LAHAN UNTUK BENDUNGAN | 91 - 120 days | [11 empty] | 1 | 1
|  | 09.Under TNP review | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 2 | 2
|  |  |  | 31 - 60 days | [11 empty] | 2 | 2
|  |  | PROPOSE CHANGE TO COLO | 31 - 60 days | [11 empty] | 1 | 1
|  | 11.BAN / BAK Process | SITE NO POWER | 91 - 120 days | [11 empty] | 1 | 1
|  |  | HARDSITAC CORPORATE LONSUM | 91 - 120 days | [11 empty] | 1 | 1
|  | 12.CP Process | COMMCASE | 91 - 120 days | [11 empty] | 1 | 1
|  |  | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 7 | 7
|  |  |  | 121 - 150 days |  |  |  |  | 1 | [7 empty] | 1
|  |  |  | 31 - 60 days | [11 empty] | 34 | 34
|  |  |  | 61 - 90 days | [11 empty] | 1 | 1
|  |  |  | 91 - 120 days | [11 empty] | 10 | 10
|  |  | PENOLAKAN WARGA | > 150 days |  |  | 1 | [9 empty] | 1
|  |  | RND NOK | 31 - 60 days | [11 empty] | 1 | 1
|  |  | NO POWER, TBG PROPOSE SOLAR CELL | 31 - 60 days | [11 empty] | 2 | 2
|  |  | PERGUB ISSUE | 31 - 60 days | [11 empty] | 1 | 1
|  | 13.Rekom L/C process | CURRENTLY NO ISSUE | 31 - 60 days | [11 empty] | 8 | 8
|  |  |  | 91 - 120 days | [11 empty] | 8 | 8
|  |  | NO POWER, TBG PROPOSE SOLAR CELL | 31 - 60 days | [11 empty] | 1 | 1
|  |  | LAHAN CORPORATE SUCOFINDO | 91 - 120 days | [11 empty] | 1 | 1
|  | 16.IMB waiting survey | CURRENTLY NO ISSUE | 31 - 60 days | [11 empty] | 5 | 5
|  | 19.Mobilisasi dan Demobilisasi | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 1 | 1
|  |  |  | > 150 days | [11 empty] | 2 | 2
|  |  |  | 31 - 60 days | [11 empty] | 1 | 1
|  |  |  | 91 - 120 days | [11 empty] | 4 | 4
|  |  | WAIT PSB | 91 - 120 days | [11 empty] | 2 | 2
|  |  | RFI COMBAT | 61 - 90 days | [11 empty] | 1 | 1
|  | 20.APD & Design Process | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 2 | 2
|  |  |  | 31 - 60 days | [11 empty] | 4 | 4
|  | 21.Bouwplank | CURRENTLY NO ISSUE | 31 - 60 days | [11 empty] | 2 | 2
|  |  |  | 91 - 120 days | [11 empty] | 4 | 4
|  | 22.Excavation | CURRENTLY NO ISSUE | 31 - 60 days | [11 empty] | 11 | 11
|  |  |  | 61 - 90 days | [11 empty] | 1 | 1
|  |  |  | 91 - 120 days | [11 empty] | 2 | 2
|  |  | WAIT PSB | 31 - 60 days | [11 empty] | 1 | 1
|  | 23.Bore pile Rebaring & Pouring | CURRENTLY NO ISSUE | 31 - 60 days | [7 empty] | 1 |  |  |  |  | 1
|  |  |  | 91 - 120 days | [7 empty] | 1 |  |  |  | 3 | 4
|  | 24.Rebaring | CURRENTLY NO ISSUE | 31 - 60 days | [11 empty] | 2 | 2
|  |  |  | 91 - 120 days | [11 empty] | 4 | 4
|  |  | WAIT PSB | 31 - 60 days | [11 empty] | 1 | 1
|  | 25.Pouring Concrete | KKOP ISSUE | 31 - 60 days | [7 empty] | 1 |  |  |  |  | 1
|  | 26.Back Filling | CURRENTLY NO ISSUE | 91 - 120 days | [6 empty] | 2 |  |  |  |  | 2 | 4
|  | 27.Curring Time | CURRENTLY NO ISSUE | 31 - 60 days | [6 empty] | 1 |  |  |  |  | 3 | 4
|  |  |  | 91 - 120 days | [11 empty] | 3 | 3
|  | 29.Erection | COMMCASE | < 30 days | [11 empty] | 1 | 1
|  |  |  | 91 - 120 days | [11 empty] | 1 | 1
|  |  | CURRENTLY NO ISSUE | 31 - 60 days |  |  |  |  | 2 |  | 1 | 1 |  |  |  | 3 | 7
|  |  |  | 91 - 120 days |  |  |  | 1 | 1 |  | 2 | 1 |  |  |  | 21 | 26
|  | 33.ME & Grounding system process | CURRENTLY NO ISSUE | 91 - 120 days | [11 empty] | 2 | 2
|  | 36.PLN application | CURRENTLY NO ISSUE | 31 - 60 days |  | 2 |  |  | 1 | [7 empty] | 3
|  |  |  | 91 - 120 days |  | 1 |  |  | 2 |  | 1 |  | 2 |  |  | 6 | 12
|  |  | WAIT SURVEY PLN | 31 - 60 days | [7 empty] | 1 |  |  |  |  | 1
|  | 37.Power connection process | COMMCASE | < 30 days | [11 empty] | 1 | 1
|  |  | CURRENTLY NO ISSUE | 31 - 60 days | [11 empty] | 1 | 1
|  |  |  | 91 - 120 days | [6 empty] | 1 |  |  |  |  | 3 | 4
|  |  | WAIT PSB | 31 - 60 days | [11 empty] | 2 | 2
|  |  |  | 91 - 120 days | [11 empty] | 14 | 14
| B2S Total |  |  |  |  | 3 | 1 | 1 | 7 |  | 8 | 6 | 2 |  |  | 250 | 278
TBG Total | [5 empty] | 11 | 1 | 2 | 16 | 6 | 10 | 19 | 2 | 3 | 1 | 317 | 388
XL | COLO | 01.SPK propossed return | CAA PROPOSE RETURN | 31 - 60 days | [11 empty] | 1 | 1
|  | 07.ESR preparation | CURRENTLY NO ISSUE | < 30 days | [11 empty] | 1 | 1
|  | 19.Mobilisasi dan Demobilisasi | CURRENTLY NO ISSUE | > 150 days | 1 | [11 empty] | 1
|  |  |  | 31 - 60 days | [11 empty] | 2 | 2
|  |  | PERMANENISASI | > 150 days | 1 | [11 empty] | 1
|  |  | EID WAIT PO | 91 - 120 days | [11 empty] | 2 | 2
|  | 35.Pemasangan KWH Box dan pole | COMMCASE | > 150 days | 1 | [11 empty] | 1
|  | 37.Power connection process | CURRENTLY NO ISSUE | > 150 days | 2 | [11 empty] | 2
|  |  |  | 121 - 150 days | 1 | [11 empty] | 1
|  |  | GO SRFI | > 150 days | 1 | [11 empty] | 1
| COLO Total |  |  |  | 7 | [10 empty] | 6 | 13
XL Total |  |  |  |  | 7 | [10 empty] | 6 | 13
Grand Total |  |  |  |  | 7 | 11 | 1 | 2 | 16 | 6 | 10 | 19 | 2 | 3 | 1 | 323 | 401

## Sheet3 (hidden)
SOW | B2S
PROGRESS SUMMARY | (All)
Count of SITE ID XL |  | RFI (M)
Status | CURRENT PROGRESS | TBD | Feb-2022 | Mar-2022 | Grand Total
ACTIVE - BLITZKRIEG 2021 [NEW] | 02.SPK returned | 7 |  | 1 | 8
| 06.Rehunting OG | 1 |  |  | 1
| 12.CP Process | 1 |  |  | 1
| 20.APD & Design Process | 4 |  |  | 4
ACTIVE - BLITZKRIEG 2021 [NEW] Total |  | 13 |  | 1 | 14
RELOCATION | 02.SPK returned | 1 |  |  | 1
| 12.CP Process |  | 1 |  | 1
RELOCATION Total |  | 1 | 1 |  | 2
Grand Total |  | 14 | 1 | 1 | 16

## Sheet7 (hidden)
Sonumb | SITE ID TP | SITE NAME TP | Site_Type | STIPCategory | Operator_ID
30701400031 | 60165109 | SELARAS PINANG JBI | COLO | STIP 1 | XL
30701220031 | 60347109 | AGUS SALIM JBI | COLO | STIP 1 | XL
30701290031 | 60239109 | JAMBI10 | COLO | STIP 1 | XL
30696340031 | 100343104 | JL_SAMRATULANGI | COLO | STIP 1 | XL
30701460031 | 100213104 | PSR_PRINGSEWU | COLO | STIP 1 | XL
30701810031 | 100060110 | KALIBENING | COLO | STIP 1 | XL
30701410031 | 100184104 | KALIANDA_KOTA | COLO | STIP 1 | XL
30701710031 | T000821 | SUKAMAJU | COLO | STIP 1 | XL
30701700031 | 1012982003 | IBS YOSODADI | COLO | STIP 1 | XL
30705590031 | 717512007 | IBS TALANG BETUTU SUKARAMI | COLO | STIP 1 | XL
30701110031 | 71065109 | SUMSEL2G179 | COLO | STIP 1 | XL
30701040031 | 70734109 | SUKOMORO 3 | COLO | STIP 1 | XL
30701120031 | 71030109 | JAMBI2G59 | COLO | STIP 1 | XL
30701310031 | 70710109 | KELAPA RAYA 2 | COLO | STIP 1 | XL
30701260031 | 70743109 | OKI14 | COLO | STIP 1 | XL
30700940031 | 717522007 | IBS PERUM HANDAYANI | COLO | STIP 1 | XL
30701060031 | 70773109 | BETUTU LAMA | COLO | STIP 1 | XL
30701730031 | TBG05_SSM132 | PERUM TLG. KELAPA | COLO | STIP 1 | XL
30705650031 | 71041109 | ENIM2014_3G1 | COLO | STIP 1 | XL
30701270031 | 71048109 | SUMSEL2G08 | COLO | STIP 1 | XL
30701050031 | 70977109 | KENTEN KERAMAT | COLO | STIP 1 | XL
30696150031 | 60415109 | JAMBI2G37 | COLO | STIP 1 | XL
30696010031 | 70534109 | KAYUARA SEKAYU | COLO | STIP 1 | XL
30696330031 | 80126104 | GUNUNG TAJAM | COLO | STIP 1 | XL

## Sheet6 (hidden)
PROJECT NAME | CURRENT SITE ID NE | CURRENT SITE NAME NE | CME BY | SOW | STO DECLARED ACTUAL (D) | SACME SUMMARY | RFI PLAN DATE
RORO JONGRANG 2021 [NEW] | SUM-AC-JTH-0741 | LAM_KAWE | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-KIS-1901 | TELADAN_PELITA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JB-SOR-4227 | CIMAUNG_MEKARSARI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JB-NPH-4233 | PADALARANG_CIPEUNDEUY | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1256 | SUKOMORO_PALEMBANG_BETUNG | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1257 | TALANG_BULUH | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1258 | SUKOMORO_ALHIDAYAH | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1260 | SUKOMORO_PANGKALAN_BENTENG | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1261 | BANYUASINIII_PANGKALAN_BALAI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1262 | SUKOMORO_BOM_BARLAN | TBG | COLO | 2021-10-04 | 04. CME OG | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-BYW-4148 | SONGGON SUMBERBULU KOESNO REJO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-RI-BLS-1135 | DURI_BARAT | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-KNR-4282 | SELOPURO SELOPURO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-BDW-3619 | JAMBESARI DARUS SHOLAH JAMBESARI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-BDW-3622 | TAMANAN WONOSUKO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-BDW-3623 | MAESAN TANAH WULAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JB-CMS-4235 | JATINAGARA_BAYASARI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JB-CJR-4244 | KADUPANDAK_SUKARAHARJA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JB-SBR-4245 | DEPOK_KEJUDEN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JB-SBR-4246 | SUMBER_KENANGA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2249 | SAMBIREJO_TIMUR_MEDAN_BATANGKUIS | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2257 | KUTALIMBARU_SAWIT_REJO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2259 | DELI_TUA_MEKAR_SARI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2269 | TEMBUNG_PEMBANGUNAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2271 | LIMAU_MANIS | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2278 | BERINGIN_SIDODADI_RAMUNIA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JB-GRT-4250 | SINGAJAYA_GIRIMUKTI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JB-GRT-4251 | BANJARWANGI_KADONGDONG | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-GSK-4332 | KEDAMEAN TULUNG | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-RI-RGT-0976 | PANGKALANKASAI_LINTAS_SUMATERA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-JMR-5123 | BALUNG KARANG SEMANDING | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-JMR-5127 | UMBULSARI SUKORENO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-JBG-4167 | TEMBELANG KEDUNGLOSARI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-JBG-4175 | TEMBELANG PULO GEDANG | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-JBG-4177 | JOMBANG SUMBERJO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-JBG-4178 | BARENG NGRIMBI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-JBG-4179 | JOMBANG SENGON | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-RI-BKN-1159 | BANGKINANG_KOTA_LANGGINI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-KDR-4322 | PLEMAHAN TEGOWANGI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-KDR-4324 | KEPUNG DAMARWULAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-LA-BDL-1128 | CAMPANG_RAYA_SOETTA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-LA-BDL-1130 | TIMUR_SUKAMAJU_REMARTADINATA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-KR-BTM-0606 | TIBAN_BARU | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-JA-JMB-0502 | PAAL_LIMA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-JA-JMB-0503 | SIJENJANG | TBG | COLO | 2021-10-04 | 04. CME OG | #REF!
RORO JONGRANG 2021 [NEW] | SUM-JA-JMB-0504 | TENGAH_ULU_GEDONG | TBG | COLO | 2021-10-04 | 04. CME OG | #REF!
RORO JONGRANG 2021 [NEW] | SUM-JA-JMB-0507 | LEGOK | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-LA-MET-1128 | METRO_UTARA_BANJAR_SARI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SB-PAD-0879 | KOTO_TANGAH_LUBUK_BUAYA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-PLG-1271 | ALANGLEBAR_TALANG_KELAPA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-PLG-1273 | TALANG_KELAPA_JALAN_BYPASS | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-PLG-1274 | SAKO_SAKO | TBG | COLO | 2021-10-04 | 04. CME OG | #REF!
RORO JONGRANG 2021 [NEW] | SUL-ST-PAL-1123 | PALU_UTARA_TAIPA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUL-ST-PAL-1124 | MANTIKULORE_TALISE | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-PSN-4127 | PURWOREJO WIROGUNAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-AKK-2215 | RANTAU_SELATAN_SIGAMBAL | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-LMG-4294 | LOPANG KEMBANGBAHU | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-LA-KLA-1121 | KALIANDA_KALIANDA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-MJY-4141 | MEJAYAN BANGUNSARI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-MJY-4142 | DOLOPO KRADINAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4397 | KEPANJEN ARDIREJO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4398 | TIRTOYUDO GADUNGSARI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4401 | TULUSBESAR TUMPANG | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4403 | NGAJUM NGASEM | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4407 | NGEMBAL WAJAK | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4411 | KALIPARE ARJOWILANGUN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4414 | TAJINAN PURWOSEKAR | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-MRE-1229 | KEPUR | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-SKY-1238 | SIMPANG_BAYAT | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-NJK-4250 | PACE BABADAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-NGW-3667 | WIDODAREN KEDUNGGUDEL | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-NGW-3672 | KENDAL PATALAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-NGW-3676 | JURUREJO NGAWI | TBG | COLO | 2021-10-04 | 04. CME OG | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-NGW-3677 | NGAWI GRUDO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-KAG-1243 | KUTARAYA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-PMK-4237 | BATUMARMAR PANGERREMAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-PNG-4290 | BABADAN LEMBAH | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-PNG-4293 | JENANGAN SETONO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-PNG-4295 | SUKOREJO BANGUNREJO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-PNG-4298 | SAMBIT BANCANGAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-LA-PRW-1123 | PRINGSEWU_UTARA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-SPG-4230 | KETAPANG PANCOR | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-SPG-4231 | BANYUATES TEROSAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-SPG-4232 | KETAPANG PAOPALELAOK | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-SPG-4233 | SOKOBANAH BIRA TIMUR | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-RI-SAK-1157 | SIAK_KAMPUNG_REMPAK | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-SDA-4315 | JABON KEDUNGREJO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-SDA-4316 | TANGGULANGIN KALITENGAH | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-PMS-2236 | TANAH_JAWA_PARBALOGAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-PMS-2238 | SIANTAR_PAMATANG_SIMALUNGUN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-PMS-2239 | GUNUNG_MALIGAS_KARANG_ANYAR | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JB-SNG-4264 | CIKAUM_KAWUNGANTEN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-TRK-4263 | TRENGGALEK DAWUHAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-TRK-4264 | POGALAN GEMBLEB | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-TBN-4070 | BANCAR BANCAR | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-TLG-4243 | KALIDAWIR DOMASAN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-TLG-4245 | KAUMAN KALANGBRET | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JB-CMS-4280 | CISAGA_MEKARMUKTI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JB-CMS-4284 | TAMBAKSARI_SUKASARI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-STB-2215 | SELESAI_PEKAN_SELESAI | TBG | COLO | 2021-10-04 | 04. CME OG | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-STB-2218 | PERK_TANJUNG__BERINGIN | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-STB-2219 | PEKAN_SELESAI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-JA-SNT-0710 | SUNGAI_GELAM_SUMBER_AGUNG | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | KAL-KS-BJB-1113 | LANDASAN_ULIN_SELATAN | TBG | COLO | 2021-10-04 | 04. CME OG | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SS-MRE-1233 | TANJUNG_ENIM_LINTAS_TENGAH | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-LA-MET-1131 | METRO_TIMUR_YOSODADI | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | KAL-KS-MRH-1116 | ANTAR_JAYA | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4406 | NGANTANG MULYOREJO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2296 | SUNGGAL_MEDAN_KRIO | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2290 | LUBUK_PAKAM_TANJUNG_GARBUS_I | TBG | COLO | 2021-10-04 | 05. S-RFI | #REF!

## Sheet5 (hidden)
[12 empty] | RFI TARGET BASED ON SLA (SLA) |  |  | SOFT-RFI PLAN |  |  | RFI PLAN (TP COMMITMENT) | [5 empty] | RFI REVISE PLAN
SITE ID XL | SITE NAME XL | SOW | CME BY | REGION XL | REGIONAL TBG | PROVINCE | KABUPATEN | SPK NO. | SPK DATE | SPK DURATION (DAY) | SPK DURATION (RANGE) | RFI TARGET (D) | RFI TARGET (W) | RFI TARGET (M) | SOFT RFI PLAN (D) | SOFT RFI PLAN (W) | SOFT RFI PLAN (M) | RFI (D) | RFI (W) | RFI (M) | . | . | . | RFI REV. (D) | RFI REV. (W) | RFI REV. (M)
JAW-YO-SMN-0060 | BERBAH PIYUNGAN JOGOTIRTO | COLO | TBG | CENTRAL | JATENG | DI Yogyakarta | Kab. Sleman | 6617408 | 2021-08-03 | 37 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-03 | FALSE | 12 | 2021-09-15 | W38-2021 | Sep-2021
JAW-JB-SOR-4411 | CIMEKAR_MARGAMULYA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung | 6617407 | 2021-08-03 | 29 | < 30 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | FALSE | -1 | 2021-09-02 | W36-2021 | Sep-2021
JAW-JI-BJN-4290 | SUGIHWARAS_GLAGAHAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6617407 | 2021-08-03 | 48 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-03 | FALSE | 18 | 2021-09-21 | W39-2021 | Sep-2021
JAW-JI-SMP-4293 | GULUKGULUK_KETAWANGLAOK | COLO | TBG | East | JATIM | Jawa Timur | Kab. Sumenep | 6617407 | 2021-08-03 | 48 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-03 | FALSE | 18 | 2021-09-21 | W39-2021 | Sep-2021
SUM-SU-PSP-2161 | HUTARAJA_MUARA_BATANG | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Tapanuli Selatan | 6617407 | 2021-08-03 | 37 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | FALSE | -1 | 2021-09-02 | W36-2021 | Sep-2021
JAW-JI-KNR-4191 | BINANGUN_BIROWO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Blitar | 6617406 | 2021-08-03 | 41 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-03 | FALSE | 11 | 2021-09-14 | W38-2021 | Sep-2021
SUL-SN-PKJ-1402 | MARANG_PUNRANGA | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Pangkajene Kepulauan | 6617407 | 2021-08-03 | 34 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | FALSE | -1 | 2021-09-02 | W36-2021 | Sep-2021
SUM-SS-MPR-1254 | CUTNYAKDIEN_SUMBER_MULYO | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617407 | 2021-08-03 | 31 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | FALSE | -1 | 2021-09-02 | W36-2021 | Sep-2021
JAW-JB-MJL-4125 | MALAUSMA_LEBAKWANGI_GELORA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Majalengka | 6617406 | 2021-08-03 | 34 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | FALSE | -1 | 2021-09-02 | W36-2021 | Sep-2021
JAW-JI-LMJ-4235 | YOSOWILANGUN_WOTGALIH | COLO | TBG | East | JATIM | Jawa Timur | Kab. Lumajang | 6617406 | 2021-08-26 | 35 | 31 - 60 days | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | 2021-09-03 | FALSE | 23 | 2021-09-26 | W40-2021 | Sep-2021
JAW-JB-CMS-4109 | LAKBOK_CINTAJAYA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Ciamis | 6617415 | 2021-08-04 | 33 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | FALSE | -1 | 2021-09-03 | W36-2021 | Sep-2021
JAW-JB-SBR-4158 | GUNUNGJATI_JADIMULYA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Cirebon | 6617413 | 2021-08-04 | 33 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | FALSE | -1 | 2021-09-03 | W36-2021 | Sep-2021
JAW-JB-IDM-4118 | BONGAS_BONGAS | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Indramayu | 6617413 | 2021-08-04 | 33 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | FALSE | -1 | 2021-09-03 | W36-2021 | Sep-2021
SUM-KR-RAN-0613 | BUNGURAN_SELATAN_CEMAGA | COLO | TBG | West | SUMBAGTENG | Kepulauan Riau | Kab. Natuna | 6617413 | 2021-08-04 | 49 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-04 | FALSE | 17 | 2021-09-21 | W39-2021 | Sep-2021
SUM-KR-RAN-0612 | BATU_GAJAH | COLO | TBG | West | SUMBAGTENG | Kepulauan Riau | Kab. Natuna | 6617413 | 2021-08-04 | 44 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | 2021-09-04 | FALSE | 13 | 2021-09-17 | W38-2021 | Sep-2021
JAW-JI-KNR-4184 | KESAMBEN_PAGERGUNUNG | COLO | TBG | East | JATIM | Jawa Timur | Kab. Blitar | 6617411 | 2021-08-04 | 40 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-04 | FALSE | 11 | 2021-09-15 | W38-2021 | Sep-2021
JAW-JT-PWD-0024 | SENTRAL GENTENG TEGALSUMUR | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Grobogan | 6616739 | 2021-07-12 | 59 | 31 - 60 days | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-12 | W33-2021 | Aug-2021 | 2021-08-11 | W33-2021 | Aug-2021 | 2021-09-06 | FALSE | -26 | 2021-08-11 | W33-2021 | Aug-2021
SUL-SN-MSB-1435 | BAEBUNTA_LARA | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Luwu Utara | 6617435 | 2021-08-06 | 35 | 31 - 60 days | 2021-09-05 | W37-2021 | Sep-2021 | 2021-09-06 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-09-06 | FALSE | 4 | 2021-09-10 | W37-2021 | Sep-2021
JAW-JT-RBG-1787 | TELON WORO | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Rembang | 6616739 | 2021-07-12 | 60 | 31 - 60 days | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-12 | W33-2021 | Aug-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-09-07 | FALSE | 3 | 2021-09-10 | W37-2021 | Sep-2021
SUM-RI-DUM-1145 | RATU_SIMA | COLO | TBG | West | SUMBAGTENG | Riau | Kota Dumai | 6617453 | 2021-08-09 | 28 | < 30 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | FALSE | 1 | 2021-09-08 | W37-2021 | Sep-2021
SUM-SS-SKY-1237 | SEKAYU_KAYUARA | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Banyuasin | 6617454 | 2021-08-09 | 30 | < 30 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | FALSE | 1 | 2021-09-08 | W37-2021 | Sep-2021
JAW-JB-SBR-4248 | SUMBER_PASALAKAN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Cirebon | 6617456 | 2021-08-09 | 32 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | 2021-09-07 | FALSE | 6 | 2021-09-13 | W38-2021 | Sep-2021
JAW-JB-CMS-4236 | PURWADADI_PADARINGAN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Ciamis | 6617454 | 2021-08-09 | 32 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | 2021-09-07 | FALSE | 6 | 2021-09-13 | W38-2021 | Sep-2021
JAW-JB-SMD-4268 | TANJUNGSARI_KADAKAJAYA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Sumedang | 6617454 | 2021-08-09 | 32 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | 2021-09-07 | FALSE | 6 | 2021-09-13 | W38-2021 | Sep-2021
JAW-JB-SOR-4228 | MAJALAYA_PADAULUN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung | 6617454 | 2021-08-09 | 35 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | 2021-09-07 | FALSE | 6 | 2021-09-13 | W38-2021 | Sep-2021
SUM-SU-LBP-2286 | KOTASAN | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617453 | 2021-08-09 | 37 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-16 | W38-2021 | Sep-2021 | 2021-09-07 | FALSE | 9 | 2021-09-16 | W38-2021 | Sep-2021
JAW-JB-SOR-4230 | SOREANG_CINGCIN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung | 6617456 | 2021-08-09 | 36 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | 2021-09-07 | FALSE | 10 | 2021-09-17 | W38-2021 | Sep-2021
SUM-RI-PKK-1154 | PANGKALAN_KERINCI_BARAT | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Pelalawan | 6617456 | 2021-08-09 | 38 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | 2021-09-07 | FALSE | 10 | 2021-09-17 | W38-2021 | Sep-2021
SUM-BB-TDN-0531 | KACANG_BOTOR_BANDARA | COLO | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kab. Belitung | 6617453 | 2021-08-09 | 49 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-28 | W40-2021 | Sep-2021 | 2021-09-07 | FALSE | 21 | 2021-09-30 | W40-2021 | Sep-2021
SUM-SS-MPR-1249 | SEMENDAWAI_TIMUR_TULUNGHARAPAN | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617459 | 2021-08-10 | 34 | 31 - 60 days | 2021-09-09 | W37-2021 | Sep-2021 | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-08 | FALSE | 6 | 2021-09-14 | W38-2021 | Sep-2021
JAW-JT-KRG-2132 | MOJOGEDANG SEWUREJO | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Karanganyar | 6617408 | 2021-08-03 | 44 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-10 | FALSE | 4 | 2021-09-14 | W38-2021 | Sep-2021
JAW-JT-PBG-1232 | PAGERANDONG MREBET | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purbalingga | 6617408 | 2021-08-03 | 41 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-10 | FALSE | 4 | 2021-09-14 | W38-2021 | Sep-2021
JAW-JT-JPA-0705 | BENTENG PORTUGIS BANDUNGHARJO | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Jepara | 6617408 | 2021-08-03 | 37 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-10 | FALSE | -8 | 2021-09-02 | W36-2021 | Sep-2021
JAW-JT-PWR-1670 | PANDANREJO KALIGESING | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purworejo | 6617416 | 2021-08-04 | 47 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-10 | FALSE | 11 | 2021-09-21 | W39-2021 | Sep-2021
JAW-JT-PBG-1231 | BUNGKANEL KARANGANYAR | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purbalingga | 6617414 | 2021-08-04 | 37 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-10 | FALSE | 4 | 2021-09-14 | W38-2021 | Sep-2021
JAW-JI-GSK-4324 | MENGANTI_BOTENG | COLO | TBG | East | JATIM | Jawa Timur | Kab. Gresik | 6617493 | 2021-08-13 | 42 | 31 - 60 days | 2021-09-12 | W38-2021 | Sep-2021 | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-28 | W40-2021 | Sep-2021 | 2021-09-11 | FALSE | 17 | 2021-09-28 | W40-2021 | Sep-2021
JAW-JI-PNG-4282 | SAWOO_GROGOL | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ponorogo | 6617493 | 2021-08-13 | 47 | 31 - 60 days | 2021-09-12 | W38-2021 | Sep-2021 | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2021-09-11 | FALSE | 19 | 2021-09-30 | W40-2021 | Sep-2021
JAW-JI-BTU-4120 | BUMIAJI_BUMIAJI | COLO | TBG | East | JATIM | Jawa Timur | Kota Batu | 6617492 | 2021-08-13 | 48 | 31 - 60 days | 2021-09-12 | W38-2021 | Sep-2021 | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-28 | W40-2021 | Sep-2021 | 2021-09-11 | FALSE | 17 | 2021-09-28 | W40-2021 | Sep-2021
JAW-JT-KRG-2147 | PEMERINTAH REJOSARI | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Karanganyar | 6617408 | 2021-08-03 | 51 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-13 | FALSE | 8 | 2021-09-21 | W39-2021 | Sep-2021
JAW-JB-SPA-4181 | PAGERAGEUNG_PUTERAN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Tasikmalaya | 6617406 | 2021-08-03 | 52 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2021-09-13 | FALSE | 17 | 2021-09-30 | W40-2021 | Sep-2021
KAL-KB-SRY-0813 | SUNGAIKAKAP_PUNGGUR_KECIL | COLO | TBG | JABO | KALIMANTAN | Kalimantan Barat | Kab. Kubu Raya | 6617413 | 2021-08-04 | 36 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-13 | FALSE | -10 | 2021-09-03 | W36-2021 | Sep-2021
SUM-JA-JMB-0487 | PAAL_MERAH_EKAJAYA | COLO | TBG | West | SUMBAGSEL | Jambi | Kota Jambi | 6617506 | 2021-08-16 | 35 | 31 - 60 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-20 | W39-2021 | Sep-2021 | 2021-09-14 | FALSE | 6 | 2021-09-20 | W39-2021 | Sep-2021
SUM-SS-IDL-1239 | PARIT | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Ilir | 6617506 | 2021-08-16 | 24 | < 30 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | FALSE | 1 | 2021-09-15 | W38-2021 | Sep-2021
SUM-RI-PBR-1163 | TEBING_TINGGI_OKURA | COLO | TBG | West | SUMBAGTENG | Riau | Kota Pekanbaru | 6617506 | 2021-08-16 | 39 | 31 - 60 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-14 | FALSE | 7 | 2021-09-21 | W39-2021 | Sep-2021
JAW-JT-BYL-0242 | KETITANG NOGOSARI | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Boyolali | 6617408 | 2021-08-03 | 44 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | 2021-10-22 | FALSE | -35 | 2021-09-17 | W38-2021 | Sep-2021
JAW-JT-BNR-0267 | AJIBARANG SECANG BINORONG | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Banjarnegara | 6617416 | 2021-08-04 | 37 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-09-10 | TRUE |  | 2021-09-10 | W37-2021 | Sep-2021
KAL-KT-KSN-0433 | LUWUK_KANAN | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Tengah | Kab. Katingan | 6617413 | 2021-08-04 | 55 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | TRUE |  | 2021-09-25 | W39-2021 | Sep-2021
SUM-SB-SRK-0856 | BANJA_LOWEH | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Lima Puluh Kota | 6617506 | 2021-08-16 | 39 | 31 - 60 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | TRUE |  | 2021-09-14 | W38-2021 | Sep-2021
SUM-SB-PYH-0842 | KAPALO_KOTO | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kota Payakumbuh | 6617506 | 2021-08-16 | 37 | 31 - 60 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | TRUE |  | 2021-09-14 | W38-2021 | Sep-2021
JAW-JT-WNG-2776 | SENDANGMULYO TIRTOMOYO | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Wonogiri | 6617432 | 2021-08-06 | 41 | 31 - 60 days | 2021-09-05 | W37-2021 | Sep-2021 | 2021-09-05 | W37-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | #N/A | #N/A |  | 2021-09-17 | W38-2021 | Sep-2021
SUM-BE-AGM-0205 | KOTA_BANI | COLO | TBG | West | LAMPUNG | Bengkulu | Kab. Bengkulu Utara | 6617547 | 2021-08-26 | 34 | 31 - 60 days | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | #N/A | #N/A |  | 2021-09-25 | W39-2021 | Sep-2021
SUM-BE-AGM-0209 | PASAR_BEMBAH | COLO | TBG | West | LAMPUNG | Bengkulu | Kab. Bengkulu Utara | 6617547 | 2021-08-26 | 34 | 31 - 60 days | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | #N/A | #N/A |  | 2021-09-25 | W39-2021 | Sep-2021
BAL-BA-MGW-1549 | ABIANSEMAL_MEKAR BHUANA | COLO | TBG | East | BALINUSRA | Bali | Kab. Badung | 6617564 | 2021-08-27 | 32 | 31 - 60 days | 2021-09-26 | W40-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | #N/A | #N/A |  | 2021-09-26 | W40-2021 | Sep-2021

## Sheet4 (hidden)
PROJECT NAME | CURRENT SITE ID NE | Regional | CURRENT SITE NAME NE | CME BY | SOW | STO DECLARED ACTUAL (D) | SACME SUMMARY | RFI PLAN DATE
RORO JONGRANG 2021 [NEW] | SUM-SU-AKK-2215 | #REF! | RANTAU_SELATAN_SIGAMBAL | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-RI-BLS-1135 | #REF! | DURI_BARAT | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-RI-SAK-1157 | #REF! | SIAK_KAMPUNG_REMPAK | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JB-NPH-4233 | #REF! | PADALARANG_CIPEUNDEUY | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JB-CMS-4235 | #REF! | JATINAGARA_BAYASARI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JB-SBR-4246 | #REF! | SUMBER_KENANGA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JB-GRT-4250 | #REF! | SINGAJAYA_GIRIMUKTI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JB-GRT-4251 | #REF! | BANJARWANGI_KADONGDONG | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-JMR-5127 | #REF! | UMBULSARI SUKORENO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-LA-BDL-1128 | #REF! | CAMPANG_RAYA_SOETTA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4398 | #REF! | TIRTOYUDO GADUNGSARI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-NGW-3677 | #REF! | NGAWI GRUDO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-SDA-4315 | #REF! | JABON KEDUNGREJO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JB-SNG-4264 | #REF! | CIKAUM_KAWUNGANTEN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-TRK-4263 | #REF! | TRENGGALEK DAWUHAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-JBG-4177 | #REF! | JOMBANG SUMBERJO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4411 | #REF! | KALIPARE ARJOWILANGUN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1256 | #REF! | SUKOMORO_PALEMBANG_BETUNG | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1257 | #REF! | TALANG_BULUH | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1258 | #REF! | SUKOMORO_ALHIDAYAH | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1260 | #REF! | SUKOMORO_PANGKALAN_BENTENG | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1261 | #REF! | BANYUASINIII_PANGKALAN_BALAI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-JBG-4175 | #REF! | TEMBELANG PULO GEDANG | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-KDR-4322 | #REF! | PLEMAHAN TEGOWANGI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-JA-JMB-0502 | #REF! | PAAL_LIMA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-JA-JMB-0507 | #REF! | LEGOK | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-PLG-1271 | #REF! | ALANGLEBAR_TALANG_KELAPA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-MJY-4142 | #REF! | DOLOPO KRADINAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4401 | #REF! | TULUSBESAR TUMPANG | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-MRE-1229 | #REF! | KEPUR | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-SKY-1238 | #REF! | SIMPANG_BAYAT | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-KAG-1243 | #REF! | KUTARAYA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-TBN-4070 | #REF! | BANCAR BANCAR | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-TLG-4245 | #REF! | KAUMAN KALANGBRET | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-JA-SNT-0710 | #REF! | SUNGAI_GELAM_SUMBER_AGUNG | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2249 | #REF! | SAMBIREJO_TIMUR_MEDAN_BATANGKUIS | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-PMS-2236 | #REF! | TANAH_JAWA_PARBALOGAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-PMS-2239 | #REF! | GUNUNG_MALIGAS_KARANG_ANYAR | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-AC-JTH-0741 | #REF! | LAM_KAWE | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JB-SOR-4227 | #REF! | CIMAUNG_MEKARSARI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JB-CJR-4244 | #REF! | KADUPANDAK_SUKARAHARJA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JB-SBR-4245 | #REF! | DEPOK_KEJUDEN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2271 | #REF! | LIMAU_MANIS | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-JMR-5123 | #REF! | BALUNG KARANG SEMANDING | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-LA-BDL-1130 | #REF! | TIMUR_SUKAMAJU_REMARTADINATA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-JA-JMB-0504 | #REF! | TENGAH_ULU_GEDONG | TBG | COLO | 2021-10-04 | 04. CME OG
RORO JONGRANG 2021 [NEW] | SUM-LA-MET-1128 | #REF! | METRO_UTARA_BANJAR_SARI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-LMG-4294 | #REF! | LOPANG KEMBANGBAHU | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-LA-KLA-1121 | #REF! | KALIANDA_KALIANDA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-MJY-4141 | #REF! | MEJAYAN BANGUNSARI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-NGW-3676 | #REF! | JURUREJO NGAWI | TBG | COLO | 2021-10-04 | 04. CME OG
RORO JONGRANG 2021 [NEW] | JAW-JI-PNG-4295 | #REF! | SUKOREJO BANGUNREJO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-LA-PRW-1123 | #REF! | PRINGSEWU_UTARA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-SDA-4316 | #REF! | TANGGULANGIN KALITENGAH | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JB-CMS-4280 | #REF! | CISAGA_MEKARMUKTI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JB-CMS-4284 | #REF! | TAMBAKSARI_SUKASARI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-STB-2218 | #REF! | PERK_TANJUNG__BERINGIN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-LA-MET-1131 | #REF! | METRO_TIMUR_YOSODADI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-STB-2219 | #REF! | PEKAN_SELESAI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2259 | #REF! | DELI_TUA_MEKAR_SARI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2269 | #REF! | TEMBUNG_PEMBANGUNAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-PLG-1273 | #REF! | TALANG_KELAPA_JALAN_BYPASS | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2296 | #REF! | SUNGGAL_MEDAN_KRIO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2290 | #REF! | LUBUK_PAKAM_TANJUNG_GARBUS_I | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2257 | #REF! | KUTALIMBARU_SAWIT_REJO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-LBP-2278 | #REF! | BERINGIN_SIDODADI_RAMUNIA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-PMS-2238 | #REF! | SIANTAR_PAMATANG_SIMALUNGUN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | KAL-KS-BJB-1113 | #REF! | LANDASAN_ULIN_SELATAN | TBG | COLO | 2021-10-04 | 04. CME OG
RORO JONGRANG 2021 [NEW] | KAL-KS-MRH-1116 | #REF! | ANTAR_JAYA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-PKB-1262 | #REF! | SUKOMORO_BOM_BARLAN | TBG | COLO | 2021-10-04 | 04. CME OG
RORO JONGRANG 2021 [NEW] | SUM-SS-PLG-1274 | #REF! | SAKO_SAKO | TBG | COLO | 2021-10-04 | 04. CME OG
RORO JONGRANG 2021 [NEW] | SUM-SU-KIS-1901 | #REF! | TELADAN_PELITA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-RI-RGT-0976 | #REF! | PANGKALANKASAI_LINTAS_SUMATERA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-RI-BKN-1159 | #REF! | BANGKINANG_KOTA_LANGGINI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUL-ST-PAL-1123 | #REF! | PALU_UTARA_TAIPA | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUL-ST-PAL-1124 | #REF! | MANTIKULORE_TALISE | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-BDW-3623 | #REF! | MAESAN TANAH WULAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-GSK-4332 | #REF! | KEDAMEAN TULUNG | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-JBG-4178 | #REF! | BARENG NGRIMBI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-JA-JMB-0503 | #REF! | SIJENJANG | TBG | COLO | 2021-10-04 | 04. CME OG
RORO JONGRANG 2021 [NEW] | JAW-JI-TLG-4243 | #REF! | KALIDAWIR DOMASAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SS-MRE-1233 | #REF! | TANJUNG_ENIM_LINTAS_TENGAH | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SU-STB-2215 | #REF! | SELESAI_PEKAN_SELESAI | TBG | COLO | 2021-10-04 | 04. CME OG
RORO JONGRANG 2021 [NEW] | JAW-JI-BYW-4148 | #REF! | SONGGON SUMBERBULU KOESNO REJO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-KNR-4282 | #REF! | SELOPURO SELOPURO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-BDW-3619 | #REF! | JAMBESARI DARUS SHOLAH JAMBESARI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-BDW-3622 | #REF! | TAMANAN WONOSUKO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-JBG-4167 | #REF! | TEMBELANG KEDUNGLOSARI | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-JBG-4179 | #REF! | JOMBANG SENGON | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-KDR-4324 | #REF! | KEPUNG DAMARWULAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-PSN-4127 | #REF! | PURWOREJO WIROGUNAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4397 | #REF! | KEPANJEN ARDIREJO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4403 | #REF! | NGAJUM NGASEM | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4407 | #REF! | NGEMBAL WAJAK | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4414 | #REF! | TAJINAN PURWOSEKAR | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-NJK-4250 | #REF! | PACE BABADAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-NGW-3667 | #REF! | WIDODAREN KEDUNGGUDEL | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-NGW-3672 | #REF! | KENDAL PATALAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-PMK-4237 | #REF! | BATUMARMAR PANGERREMAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-PNG-4290 | #REF! | BABADAN LEMBAH | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-PNG-4293 | #REF! | JENANGAN SETONO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-PNG-4298 | #REF! | SAMBIT BANCANGAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-SPG-4230 | #REF! | KETAPANG PANCOR | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-SPG-4231 | #REF! | BANYUATES TEROSAN | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-SPG-4232 | #REF! | KETAPANG PAOPALELAOK | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-SPG-4233 | #REF! | SOKOBANAH BIRA TIMUR | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-TRK-4264 | #REF! | POGALAN GEMBLEB | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | JAW-JI-KPN-4406 | #REF! | NGANTANG MULYOREJO | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-KR-BTM-0606 | #REF! | TIBAN_BARU | TBG | COLO | 2021-10-04 | 05. S-RFI
RORO JONGRANG 2021 [NEW] | SUM-SB-PAD-0879 | #REF! | KOTO_TANGAH_LUBUK_BUAYA | TBG | COLO | 2021-10-04 | 05. S-RFI

## BAGAN (hidden)
MIN : 1 | MIN : -1 | MIN: 13
AVG: 9 | AVG : 3 | AVG : 23
MAX: 21 | MAX: 6 | MAX : 53
SPK
STO
STIP
RFI

## Sheet2 (hidden)
Site Id XL | Site Name XL | Site Id TBG | Site Name Tbg | Regional | req sk pln | RFI Commitment
SUM-SU-PMS-2236 | TANAH_JAWA_PARBALOGAN | 020277104 | RTANAHJAWA | SUMATERA UTARA | 2021-08-18 | 2021-10-15
SUM-SU-LBP-2249 | SAMBIREJO_TIMUR_MEDAN_BATANGKUIS | 020255104 | PS_7_BTG_KUIS | SUMATERA UTARA | 2021-09-04 | 2021-10-15
SUM-SU-PMS-2239 | GUNUNG_MALIGAS_KARANG_ANYAR | 020268104 | KARANG_SARI | SUMATERA UTARA | 2021-08-18 | 2021-10-15
JAW-JI-KNR-4282 | SELOPURO SELOPURO | 160633104 | SELOPURO_KOTA | JAWA TIMUR | 2021-09-04 | 2021-10-15
JAW-JI-BYW-4148 | SONGGON SUMBERBULU KOESNO REJO | 160693104 | SUMBERBULU | JAWA TIMUR | 2021-09-04 | 2021-10-15
JAW-JB-SBR-4246 | SUMBER_KENANGA | 121027104 | KARANGMULYA | JAWA BARAT | 2021-09-04 | 2021-10-15
JAW-JB-SNG-4264 | CIKAUM_KAWUNGANTEN | 121343104 | KAWUNGANTEN | JAWA BARAT | 2021-09-04 | 2021-10-15
JAW-JI-BDW-3619 | JAMBESARI DARUS SHOLAH JAMBESARI | 164067104 | JAMBESARI - RELOC | JAWA TIMUR | 2021-09-04 | 2021-10-15
SUM-LA-BDL-1128 | CAMPANG_RAYA_SOETTA | 100343104 | JL_SAMRATULANGI | LAMPUNG | 2021-08-18 | 2021-10-15
JAW-JB-CMS-4235 | JATINAGARA_BAYASARI | 121435104 | JATINEGARA | JAWA BARAT | 2021-08-18 | 2021-10-15
JAW-JI-NGW-3667 | WIDODAREN KEDUNGGUDEL | 160862104 | BANYUBIRU_NWI | JAWA TIMUR | 2021-09-04 | 2021-10-15
JAW-JB-GRT-4250 | SINGAJAYA_GIRIMUKTI | 121098104 | NODAL BANJARWANGI | JAWA BARAT | 2021-08-18 | 2021-10-15
JAW-JB-GRT-4251 | BANJARWANGI_KADONGDONG | 122372109 | WANGUNJAYA-BANJARWANGI | JAWA BARAT | 2021-08-18 | 2021-10-15
JAW-JB-NPH-4233 | PADALARANG_CIPEUNDEUY | 122406109 | KOTABARU - BALEPARE ( BTS HOTEL ) | JAWA BARAT | 2021-08-18 | 2021-10-15
JAW-JI-TRK-4264 | POGALAN GEMBLEB | 162223109 | GEMBLEB TRENGGALEK | JAWA TIMUR | 2021-09-04 | 2021-10-15
JAW-JI-JBG-4167 | TEMBELANG KEDUNGLOSARI | 160479104 | KALIKEJAMBON | JAWA TIMUR | 2021-09-04 | 2021-10-15
JAW-JI-PNG-4298 | SAMBIT BANCANGAN | 162143109 | TAMANSARI PONOROGO | JAWA TIMUR | 2021-08-18 | 2021-10-15
JAW-JI-PNG-4290 | BABADAN LEMBAH | 164120107 | BANYUDONO PONOROGO | JAWA TIMUR | 2021-09-04 | 2021-10-15
JAW-JI-KDR-4324 | KEPUNG DAMARWULAN | 164108107 | BESOWO KEPUNG | JAWA TIMUR | 2021-09-04 | 2021-10-15
SUM-LA-PRW-1123 | PRINGSEWU_UTARA | 100213104 | PSR_PRINGSEWU | LAMPUNG | 2021-08-18 | 2021-10-20
SUM-LA-KLA-1121 | KALIANDA_KALIANDA | 100184104 | KALIANDA_KOTA | LAMPUNG | 2021-09-04 | 2021-10-20
SUM-JA-JMB-0503 | SIJENJANG | 60083104 | KUMPEH | SUMBAGSEL | 2021-10-04 | 2021-10-30
KAL-KS-BJB-1113 | LANDASAN_ULIN_SELATAN | 220246109 | PLAN MACRO CLUSTER (WBB BANJARMASIN) 30 | KALIMANTAN SELATAN | 2021-10-04 | 2021-10-30
SUL-ST-PAL-1124 | MANTIKULORE_TALISE | 260008109 | SKP UNISMUH EX PLE2 | SULAWESI TENGAH | 2021-10-04 | 2021-10-30
SUL-ST-PAL-1123 | PALU_UTARA_TAIPA | 260135109 | TAIPA | SULAWESI TENGAH | 2021-10-04 | 2021-10-30
JAW-JI-JBG-4179 | JOMBANG SENGON | 164235104 | JOMBATAN_JMB | JAWA TIMUR | 2021-09-04
JAW-JI-KPN-4403 | NGAJUM NGASEM | 161818109 | NGASEM MALANG | JAWA TIMUR | 2021-09-04
JAW-JI-SPG-4232 | KETAPANG PAOPALELAOK | 160197104 | LAR LAR | JAWA TIMUR | 2021-09-04
JAW-JB-SBR-4245 | DEPOK_KEJUDEN | 120642104 | GETASAN | JAWA BARAT | 2021-09-04
JAW-JI-BDW-3622 | TAMANAN WONOSUKO | 162198109 | TAMANAN3 | JAWA TIMUR | 2021-09-04
JAW-JI-SPG-4231 | BANYUATES TEROSAN | 160198104 | TEROSAN | JAWA TIMUR | 2021-09-04
JAW-JI-SPG-4230 | KETAPANG PANCOR | 160219104 | BIRA BARAT | JAWA TIMUR | 2021-09-04
JAW-JI-PMK-4237 | BATUMARMAR PANGERREMAN | 160462104 | TAMBERULAOK | JAWA TIMUR | 2021-09-04
JAW-JI-PNG-4293 | JENANGAN SETONO | 162124109 | KADIPATEN PONOROGO | JAWA TIMUR | 2021-09-04
JAW-JI-PSN-4127 | PURWOREJO WIROGUNAN | 161903109 | POHJENTREK | JAWA TIMUR | 2021-09-04
JAW-JI-KPN-4397 | KEPANJEN ARDIREJO | 161819109 | ADIMULYA | JAWA TIMUR | 2021-09-04
JAW-JI-KPN-4406 | NGANTANG MULYOREJO | 161862109 | TURIREJO | JAWA TIMUR | 2021-09-04
JAW-JI-KPN-4407 | NGEMBAL WAJAK | 161790109 | JAMBESARI | JAWA TIMUR | 2021-09-04
JAW-JI-NGW-3672 | KENDAL PATALAN | 160151104 | KENDAL | JAWA TIMUR | 2021-09-04
SUM-LA-BDL-1130 | TIMUR_SUKAMAJU_REMARTADINATA | T000821 | SUKAMAJU | LAMPUNG | 2021-09-04
JAW-JI-SPG-4233 | SOKOBANAH BIRA TIMUR | 160218104 | TOBAI TIMUR | JAWA TIMUR | 2021-08-18
JAW-JI-NJK-4250 | PACE BABADAN | 161779109 | MLANDANGAN | JAWA TIMUR | 2021-09-04
JAW-JI-KPN-4414 | TAJINAN PURWOSEKAR | 160009102 | NGAWONGGO | JAWA TIMUR | 2021-08-18
SUM-KR-BTM-0606 | TIBAN_BARU | 050486103 | MEKAR TAMAN SARI - RELOC | KEPULAUAN RIAU | 2021-09-04
JAW-JB-CMS-4280 | CISAGA_MEKARMUKTI | 1263631023 | CISAGA CIAMIS | JAWA BARAT | 2021-09-04
KAL-KS-MRH-1116 | ANTAR_JAYA | 220009109 | ANTAR JAYA | KALIMANTAN SELATAN | 2021-10-04
JAW-JB-CJR-4244 | KADUPANDAK_SUKARAHARJA | 1270682004 | IBS SUKARAHARJA / CIANJUR | JAWA BARAT | 2021-09-04
JAW-JB-CMS-4284 | TAMBAKSARI_SUKASARI | 125398126 | SITUMANDALA-RANCAH | JAWA BARAT | 2021-09-04
JAW-JB-SOR-4227 | CIMAUNG_MEKARSARI | 125419126 | MEKARSARI-CIMAUNG | JAWA BARAT | 2021-09-04
SUM-SU-STB-2218 | PERK_TANJUNG__BERINGIN | 022011109 | KEBUN LADA -2 | SUMBAGUT | 2021-09-04
SUM-SU-STB-2215 | SELESAI_PEKAN_SELESAI | 021291109 | SC-BJ1507G | SUMBAGUT | 2021-09-04
SUM-SU-STB-2219 | PEKAN_SELESAI | 022014109 | SMA 1 SELESAI | SUMBAGUT | 2021-09-04
SUM-SU-LBP-2296 | SUNGGAL_MEDAN_KRIO | 022061109 | TAMBAK CEKUR | SUMBAGUT | 2021-09-04
SUM-SU-LBP-2290 | LUBUK_PAKAM_TANJUNG_GARBUS_I | 0226992001 | IBS MULIOREJO | SUMBAGUT | 2021-09-04
SUM-SU-PMS-2238 | SIANTAR_PAMATANG_SIMALUNGUN | 021739109 | JLN HULAKMA SINAGA | SUMBAGUT | 2021-09-04
SUM-SU-LBP-2257 | KUTALIMBARU_SAWIT_REJO | 021236109 | SAWIT_REJO | SUMBAGUT | 2021-09-04
SUM-SS-PLG-1274 | SAKO_SAKO |  |  |  | 2021-10-04
SUM-SU-LBP-2269 | TEMBUNG_PEMBANGUNAN | 0226822007 | IBS MED0117 | SUMBAGUT | 2021-09-04
SUM-SU-LBP-2259 | DELI_TUA_MEKAR_SARI | 021411109 | TERATAI PATUMBAK | SUMBAGUT | 2021-09-04
SUM-SS-PLG-1271 | ALANGLEBAR_TALANG_KELAPA | 070710109 | KELAPA RAYA 2 | SUMBAGSEL | 2021-09-04
SUM-SU-AKK-2215 | RANTAU_SELATAN_SIGAMBAL | 021276109 | PERDAMAIAN2 | SUMBAGUT | 2021-08-18
SUM-SU-LBP-2271 | LIMAU_MANIS | 021211109 | BANGUN_REJO_2 | SUMBAGUT | 2021-09-04
SUM-SU-LBP-2278 | BERINGIN_SIDODADI_RAMUNIA | 022231109 | API_DUSUN VIIA KARANG ANYAR | SUMBAGUT | 2021-09-04
SUM-SS-SKY-1238 | SIMPANG_BAYAT | 071030109 | JAMBI2G59 | SUMBAGSEL | 2021-09-04
SUM-SU-KIS-1901 | TELADAN_PELITA | 021918109 | PELITA 2 GG SAUDARA | SUMBAGUT | 2021-10-04
SUM-SS-PKB-1256 | SUKOMORO_PALEMBANG_BETUNG | 070734109 | SUKOMORO 3 | SUMBAGSEL | 2021-09-04
SUM-SS-PKB-1262 | SUKOMORO_BOM_BARLAN | 0717512007 | IBS TALANG BETUTU SUKARAMI | SUMBAGSEL | 2021-10-04
SUM-SB-PAD-0879 | KOTO_TANGAH_LUBUK_BUAYA | 030433109 | PAD MC 58 / LUBUK GADING PERMAI | SUMBAGTENG | 2021-08-18
SUM-SS-PKB-1258 | SUKOMORO_ALHIDAYAH | 070773109 | BETUTU LAMA | SUMBAGSEL | 2021-09-04
SUM-SS-PKB-1260 | SUKOMORO_PANGKALAN_BENTENG | 0717522007 | IBS PERUM HANDAYANI | SUMBAGSEL | 2021-09-04
SUM-SS-MRE-1233 | TANJUNG_ENIM_LINTAS_TENGAH | 071041109 | ENIM2014_3G1 | SUMBAGSEL | 2021-10-04
SUM-SS-PKB-1261 | BANYUASINIII_PANGKALAN_BALAI | 071048109 | SUMSEL2G08 | SUMBAGSEL | 2021-09-04
SUM-SS-PKB-1257 | TALANG_BULUH | 070977109 | KENTEN KERAMAT | SUMBAGSEL | 2021-09-04
SUM-SS-MRE-1229 | KEPUR | 071065109 | SUMSEL2G179 | SUMBAGSEL | 2021-09-04
SUM-SS-KAG-1243 | KUTARAYA | 070743109 | OKI14 | SUMBAGSEL | 2021-09-04
SUM-RI-RGT-0976 | PANGKALANKASAI_LINTAS_SUMATERA | 040932109 | SIMPANG EMPAT BELILAS | SUMBAGTENG | 2021-09-04
SUM-RI-BLS-1135 | DURI_BARAT | 040851109 | SITE MANDAU | SUMBAGTENG | 2021-09-04
SUM-JA-SNT-0710 | SUNGAI_GELAM_SUMBER_AGUNG | 060415109 | JAMBI2G37 | SUMBAGSEL | 2021-08-18
SUM-AC-JTH-0741 | LAM_KAWE | 010362109 | PRADA / TBG_NAD117-PINEUNG | SUMBAGUT | 2021-09-04
SUM-LA-MET-1131 | METRO_TIMUR_YOSODADI | 1012982003 | IBS YOSODADI | LAMPUNG | 2021-09-04
SUM-JA-JMB-0504 | TENGAH_ULU_GEDONG | 060165109 | SELARAS PINANG JBI | SUMBAGSEL | 2021-08-18
SUM-JA-JMB-0507 | LEGOK | 060239109 | JAMBI10 | SUMBAGSEL | 2021-09-04
SUM-JA-JMB-0502 | PAAL_LIMA | 060347109 | AGUS SALIM JBI | SUMBAGSEL | 2021-09-04
SUM-RI-BKN-1159 | BANGKINANG_KOTA_LANGGINI | 0415232001 | IBS BANGKINANG | SUMBAGTENG | 2021-09-04
JAW-JI-JMR-5127 | UMBULSARI SUKORENO | 163958109 | SUKORENOUMBULSARI | JATIM | 2021-09-04
JAW-JI-TRK-4263 | TRENGGALEK DAWUHAN | 163717126 | DAWUHANTRENGGALEK | JATIM | 2021-09-04
JAW-JI-NGW-3677 | NGAWI GRUDO | 163433109 | TRUNOJOYO 2 | JATIM | 2021-09-04
JAW-JI-KPN-4398 | TIRTOYUDO GADUNGSARI | 1647592001 | IBS GN JIDOR/KALIGADUNG | JATIM | 2021-09-04
JAW-JI-SDA-4315 | JABON KEDUNGREJO | 163610126 | KEDUNGREJO JABON | JATIM | 2021-09-04
JAW-JI-JBG-4175 | TEMBELANG PULO GEDANG | 1649472001 | IBS PULO GEDANG | JATIM | 2021-09-04
JAW-JI-KPN-4401 | TULUSBESAR TUMPANG | 162699109 | PERTIGAANTUMPANGTBG | JATIM | 2021-09-04
JAW-JI-GSK-4332 | KEDAMEAN TULUNG | 161342102 | PULO | JATIM | 2021-09-04
JAW-JI-JBG-4178 | BARENG NGRIMBI | 163728126 | SUMBERKEPUHLENGKONG | JATIM | 2021-09-04
JAW-JI-JMR-5123 | BALUNG KARANG SEMANDING | 162648109 | KARANGDUREN2TBG | JATIM | 2021-08-18
JAW-JI-TLG-4243 | KALIDAWIR DOMASAN | 1651702004 | IBS TANJUNGUNUT | JATIM | 2021-09-04
JAW-JI-MJY-4141 | MEJAYAN BANGUNSARI | TBG03_EJ127 | CARUBAN | JATIM | #REF!
JAW-JI-LMG-4294 | LOPANG KEMBANGBAHU | 164015109 | LOPANGKEMBANGBAHU | JATIM | #REF!
JAW-JI-PNG-4295 | SUKOREJO BANGUNREJO | 163977109 | BANGUNREJO SUKOREJO | JATIM | #REF!
JAW-JI-SDA-4316 | TANGGULANGIN KALITENGAH | 1650362001 | IBS KALITENGAH_SDA_SDA | JATIM | #REF!
JAW-JI-TLG-4245 | KAUMAN KALANGBRET | 1649832007 | IBS WILIS TULUNGAGUNG | JATIM | #REF!
JAW-JI-TBN-4070 | BANCAR BANCAR | 1648622004 | IBS BANCAR | JATIM | #REF!
JAW-JI-MJY-4142 | DOLOPO KRADINAN | 163438109 | BABADAN 4 | JATIM | #REF!
JAW-JI-NGW-3676 | JURUREJO NGAWI | 1650712001 | IBS SC_EJ_INFILL48 | JATIM | #REF!
JAW-JI-BDW-3623 | MAESAN TANAH WULAN | 163526126 | TANAHWULAN MAESAN | JATIM | #REF!
JAW-JI-KDR-4322 | PLEMAHAN TEGOWANGI | 1647422004 | IBS PLEMAHAN PAGU | JATIM | #REF!

## Sheet1 (hidden)
Colo | Range | Point |  | BTS
1 | <20 | 10 |  | 1 | <20 | 10
21 | 21-30 | 6 |  | 91 | 21-30 | 6
31 | 31-60 | 4 |  | 121 | 31-60 | 4
61 | >60 | 1 |  | 151 | >60 | 1
|  |  | 10 | 10

## DATA
Copyright@HENK2020 |  | 376 | [13 empty] | 401 | [18 empty] | diisi stlh STO
[29 empty] | RFI TARGET BASED ON SLA (SLA) |  |  | SOFT-RFI PLAN |  |  | RFI PLAN (TP COMMITMENT) |  |  | RFI REVISE PLAN |  |  | TRANSPORT TYPE, SK PLN & MOS PLAN | [5 empty] | ACTUAL DATE OF IMPLEMENTATION |  |  |  |  | ACTUAL MOS & UNLOCK |  |  | DAILY UPDATE BY TP
NO | TP PROJECT CODE | SITE ID XL | Sonumb | SITE ID TP | SITE NAME TP | Status | COMPANY ID | SSR Longitude | SSR Latitude | Proposed RF Height | RF AZIMUTH | PROJECT YEAR | PROJECT NAME | SITE ADDRESS | TECH PART | SITE ID XL | SITE NAME XL | SOW | CME BY | REGION XL | REGIONAL TBG | PROVINCE | KABUPATEN | SPK NO. | SPK DATE | SPK RECEIVE ON EMAIL | SPK DURATION (DAY) | SPK DURATION (RANGE) | RFI TARGET (D) | RFI TARGET (W) | RFI TARGET (M) | SOFT RFI PLAN (D) | SOFT RFI PLAN (W) | SOFT RFI PLAN (M) | RFI (D) | RFI (W) | RFI (M) | RFI REV. (D) | RFI REV. (W) | RFI REV. (M) | TRANSPORT TYPE | PSB PLN SUBMITTED | PSB PLN RECEIVED | PLN ID | KVA | PLAN MOS | STO DATE | CME START | SOFT RFI | RFI | RFI Actual (W) | MOS | UNLOCK | SIMPLY MILESTONE | CURRENT PROGRESS | PROGRESS SUMMARY | PROBLEM CLASS | DETAIL PROBLEM | apr target | xx | yy
811 |  | JAW-JI-SDA-4068 | 30571410031 | 1643181003 | TAMAN_BOHAR | SPK RETURN | TB | 112.7082 | -7.3784 | 30 | 0/210/300 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-SDA-4068 | TAMAN_BOHAR | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [5 empty] | 2021-04-05 | [7 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 02.07.20 : MOM propose return, hard kandidat, terkait isu regulasi ketinggian tower 02.07.20 : IW clear 29.06.20 : 25.06.20 : XL meminta untuk segera start CME minggu depan 19.06.20 : perubahan type transport dari FO menjadi MW, need req SK PLN 22.06.20 : 18.06.20 : plan start CME 2 minggu kedepan, plan RFI end of July 15.06.20 : IW ongoing eks lahan TSEL 2016 fail IW, propose reduce ketinggian (rooftop) 11.06.20 : 08.06.20 : IW clear, renego biaya sitac, isu warga luar radius 04.06.20 : IW clear, renego biaya sitac 01.06.20 : 28.05.20 : 25.05.20 : 14.05.20 : IW clear, renego biaya sitac 08.05.20 : 30.04.20 : 23.04.20 : 16.04.20 : IW clear, renego biaya sitac 09.04.20 : 02.04.20 : 25.03.20 : renego BAN LL tetap di harga awal , resubmit Capex, proses review eskalasi sitac 19.03.20 : 11.03.20 : IW clear, proses renego dan validasi biaya sitac 28.02.20 : Kand A = IW Clear, plan soswar nego permintaan warga (nego biaya sitac terlalu tinggi) 20.02.20 : 19.02.20 : Kand A = IW Clear , proses mediasi besaran Fasum , target Isolve 22.2.20 13.02.20 : 06.02.20 : Kand A, B = Rehunting, Candidate A B RF NOK 04.02.20 : Kand A, B = submit A 112.70838 -7.378853 54.96 GF Pole 20 Perda antar tower Kab Sidoarjo with justification below B 112.70852 -7.378244 43.73 GF Pole 20 Perda antar tower Kab Sidoarjo with justification below
882 |  | SUM-SU-SDK-2203 |  |  |  | SPK RETURN BY XL |  | 98.4388 | 2.6985 | 50 | 40/120/280 | 2020 | JEDI 2020 [NEW] |  | HTI | SUM-SU-SDK-2203 | KUTA GUGUNG | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. DAIRI | 6614551 | 2020-03-13 |  | 776 | > 150 days | 2020-04-12 | W16-2020 | Apr-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2021-01-05 | [7 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 30.04.20 : SPK return by XL karena perubahan plan sesuai email Bu Anggie 28 Apr 23.04.20 : 16.04.20 : 09.04.20 : 25.03.20 : under RNP review HTI
883 |  | SUM-SU-PRR-2118 |  |  |  | SPK RETURN BY XL |  | 98.8594 | 2.4443 | 50 | 40/130/300 | 2020 | JEDI 2020 [NEW] |  | HTI | SUM-SU-PRR-2118 | PASARAN I | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. SAMOSIR | 6614551 | 2020-03-13 |  | 776 | > 150 days | 2020-04-12 | W16-2020 | Apr-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2021-01-05 | [7 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 30.04.20 : SPK return by XL karena perubahan plan sesuai email Bu Anggie 28 Apr 23.04.20 : 16.04.20 : 09.04.20 : 25.03.20 : under RNP review HTI
880 |  | SUM-SU-BLG-2120 |  |  |  | SPK RETURN BY XL |  | 99.2041 | 2.3471 | 50 | 30/180/250 | 2020 | JEDI 2020 [NEW] |  | HTI | SUM-SU-BLG-2120 | PARDOMUAN | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. TOBA SAMOSIR | 6614551 | 2020-03-13 |  | 776 | > 150 days | 2020-04-12 | W16-2020 | Apr-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2020-12-23 | [7 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 30.04.20 : SPK return by XL karena perubahan plan sesuai email Bu Anggie 28 Apr 23.04.20 : 16.04.20 : 09.04.20 : 25.03.20 : under RNP review HTI
906 |  | JAW-JB-SNG-3958 |  |  |  | SPK RETURN BY XL |  | 107.6435 | -6.2656 | 40 | 100/180/290 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JB-SNG-3958 | JAYAMUKTI_BLANAKAN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUBANG | 6614550 | 2020-03-13 |  | 776 | > 150 days | 2020-04-12 | W16-2020 | Apr-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2020-10-12 | [7 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 23.04.20 : 09.04.20 : cancel karena double dengan ID JAW-JB-SNG-3746.
881 |  | SUM-AC-SGI-0707 |  |  |  | SPK RETURN BY XL |  | 95.8834 | 5.4262 | 40 | 70/160/350 | 2020 | JEDI 2020 [NEW] |  | HTI | SUM-AC-SGI-0707 | MEE | COLO | TBG | WEST | SUMBAGUT | Aceh | KAB. PIDIE | 6614551 | 2020-03-13 |  | 776 | > 150 days | 2020-04-12 | W16-2020 | Apr-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2020-09-15 | [7 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 30.04.20 : SPK return by XL karena perubahan plan sesuai email Bu Anggie 28 Apr 23.04.20 : 16.04.20 : 09.04.20 : 25.03.20 : under RNP review HTI
893 |  | SUM-SU-PSP-2151 |  |  |  | SPK RETURN BY XL |  | 99.2694 | 1.4422 | 50 | 160/250/310 | 2020 | JEDI 2020 [NEW] |  | HTI | SUM-SU-PSP-2151 | MOMPANG | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KOTA PADANGSIDIMPUAN | 6614688 | 2020-04-23 |  | 735 | > 150 days | 2020-05-23 | W21-2020 | May-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2020-08-04 | [7 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 08.05.20 : SPK return by XL karena perubahan plan XL (email Bu Anggie)
|  | SUL-SN-PRE-1590 |  | 280348109 | TBG LA GALIGO PARE | RELOCATION | SKP | 119°39.0.07'E | 3°59.42.9'S | 30 | 80/220/320 |  |  |  | CAA | SUL-SN-PRE-1590 | BUKIT INDAH RELOCATION | COLO | XL | East | SULAWESI | Sulawesi Selatan | Kota Pare Pare | 6618129 | 2022-03-16 | 2022-03-16 | 43 | 31 - 60 days | 2022-04-15 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN | CAA PROPOSE RETURN | 18:04:22: CAA PROPOSE RETURN 16:03:22: SPK RECEIVED |  | 401
819 |  | JAW-JI-SMP-4275-RETURN |  |  |  | SPK RETURN |  | 114°36.2.3'null | 5°4.14.23'S | 72 | 90/210/330 |  |  |  | HTI | JAW-JI-SMP-4275-RETURN | MASALEMBU KARAMIAN | B2S | TBG | EAST | JATIM | Jawa Timur | Kab. Sumenep | 6616297 | 2020-10-02 |  | 573 | > 150 days | 2021-03-01 | W10-2021 | Mar-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 19.10.20 : propose return 15.10.20 : NOM berada di pulau dengan jarak 213km dari daratan madura, potensi community secure namun ada isu keterbatasan daya pembangkit menggunakan BBM, proses memastikan legalitas lahan BPN 12.10.20 : 08.10.20 : hunting 05.10.20 : assessment & prepare hunting 02.10.20 : SPK B2 S release
907 |  | BAL-BA-MGW-1473 |  |  |  | SPK RETURN BY XL |  |  | 171476126 | 35 | 70/150/320 | 2019 | ORION [NEW] |  | HTI | BAL-BA-MGW-1473 | TAMAN AYU GIRI ASRI | COLO | TBG | EAST | BALINUSRA | Bali | BADUNG | 6614639 | 2020-04-13 |  | 745 | > 150 days | 2020-05-13 | W20-2020 | May-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 30.04.20 : RND NOK mas, tower too low, RND butuh 30 meter, tower existing hanya 18
815 |  | JAW-JK-CKG-0710-RETURN |  |  |  | SPK RETURN |  | 106.8854 | -6.2323 | 50 | 90/210/330 |  |  |  | EID | JAW-JK-CKG-0710-RETURN | CIPINANG MUARA RELOCATION | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | Jakarta Timur | 6614467 | 2020-02-07 |  | 811 | > 150 days | 2020-07-06 | W28-2020 | Jul-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN
898 |  | JAW-JT-SGN-1842 |  |  |  | SPK RETURN BY XL |  | 110.8723 | -7.3743 | 50 | 15/90/180/260 |  |  |  | EID | JAW-JT-SGN-1842 | Nganti Gemolong | COLO |  | CENTRAL | JATENG | Jawa Tengah | SRAGEN | 6614397 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN
905 |  | JAW-JT-PBG-1249 |  |  |  | SPK RETURN BY XL |  | 109.5426 | -7.3988 | 50 | 90/225/305 |  |  |  | EID | JAW-JT-PBG-1249 | TIMBANG PURBALINGGA | COLO |  | CENTRAL | JATENG | Jawa Tengah | PURBALINGGA | 6614397 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 24.02.20 : RND Not OK, propose return 06.02.20 : 30.01.20 : under review RND
795 |  | JAW-BT-TNG-1467 | 30572590031 | 1317781003 | JL INDUSTRI JATAKE | SPK RETURN | TB | 106.5679 | -6.1988 | 35 | 90/210/330 |  |  |  | EID | JAW-BT-TNG-1467 | JL INDUSTRI JATAKE | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [13 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 14.09.20 : 03.09.20 : MOM : XL PROPOSE RETURN SPK, team SS Poses BAN dengan LL 03.09.20 : REKOM LURCAM, Waiting REKOM PUPR 31.08.20 : 27.08.20 : REKOM L/C, Waiting REKOM PUPR 24.08.20 :17.08.20 : 13.08.20 : Proses REKOM PUPR untuk Start CME 10.08.20 : 06.08.20 : Rekom Camat, memerlukan rekomendasi dari REKOM PUPR, site outcell 03.08.20 : 30.07.20 : OG Collect dokumen SITAC 23.07.20 : Commcase Solved, OG Collect dokumen kepemilikan LL & Warga 20.07.20 : Mediasi pertama belum menemui titik temu, plan mediasi kedua melibatkan Lurah, MUSPIKA, dan tokoh masyarkat 16.07.20 : 13.07.20 : 09.07.20 : MOM : masih koordinasi dengan pemda utk 25m, tangkot, outcell, plan minggu depan diundang presentasi oleh pemda/PUPR, IW clear 06.07.20 : 02.07.20 : IW clear, proses pengajuan ke PEMDA Tinggi 25m (area Tangkot), target solve dengan Pemda minggu depan, plan CME start paling lambat 9 jul 20/weekly minggu depan, plan SRFI W1 Aug (8 Aug 20) 29.06.20 : 25.06.20 : Cand Approved, proses negosiasi ke PEMDA Tinggi 25m, paralel pengambilan foto panoramic by drone, paralel proses rekom. plan Start CME paling lambat senin 29 Jun 2020 22.06.20 : 18.06.20 : IW on going, plan RFC end of June 15.06.20 : 11.06.20 : IW clear 08.06.20 : rehunting 04.06.20 : 01.06.20 : plan submit kand 4 jun. 28.05.20 : 25.05.20 : 30.04.20 : Rehunting OG, propose return by XL krn durasi 108 hari (MoM 30 Apr 20) 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : IW on going 12.03.20 : rehunting 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
796 |  | JAW-JB-CBI-0070 | 30572100031 | 1260911003 | KANDANG RODA SENTUL | SPK RETURN | TB | 106.8411 | -6.5212 | 50 | 20/105/310 |  |  |  | EID | JAW-JB-CBI-0070 | Kandang Roda Sentul | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 01.SPK propossed return | 01.SPK PROPOSSED RETURN |  | 17.09.20 : MOM, SPK drop/return by XL 17.09.20 : IW Clear, proses PKS dengan Yayasan Pakuan Bogor 14.09.20 : 10.09.20 : IW Clear, proses PKS dengan Yayasan Pakuan Bogor 07.09.20 : IW proses kembali ke kandidat B 03.09.20 : Proses PKS dengan pihak Yayasan Pakuan Bogor, plan PKS clear minggu ini 31.08.20 : 27.08.20 : Proses PKS dengan pihak Yayasan Pakuan Bogor 24.08.20 : 17.08.20 : 13.08.20 : 10.08.20 : 06.08.20 : paralel submit kandidat baru (cand C 106.84380 -6.52105) under RNP review, plan minggu depan bouwplank kand B 03.08.20 : 30.07.20 : 23.07.20 : IW Ulang kurang 1 kk, Yayasan Pakuan Bogor. 20.07.20 : Lokasi bergeser terkait issue Cell Plan, IW Ulang kurang 1 kk, Yayasan Pakuan Bogor. Ketua yayasan sedang keluar kota, baru bisa ditemui hari Jumat tgl 17/0716.07.20 : 13.07.20 : 09.07.20 : MOM : IW on going, outcell, harus di geser, plan IW clear titik pergeseran di minggu ini 06.07.20 : 02.07.20 : IW clear, proses rekom, ada perubahan cellplan yang informasinya akan release besok, jika cell plan masih ok maka plan rekom selesai 10 jul, plan start CME 15 jul, plan RFI 12 aug 29.06.20 : on going rekom 25.06.20 : IW clear, besok realisasi, tower SST 42m 22.06.20 : 18.06.20 : IW on going, Plan IW Done Jun 2020 15.06.20 : BAK 11.06.20 : rehunting, plan IW done jun 20, sudah ada kandidat (plan re-IW) 08.06.20 : 04.06.20 : 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : IW on going 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : IW on going 25.03.20 : 19.03.20 : 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 27.01.20 : kand A = TNP OK 38 0.3 177.22 24.01.20 : kand A = RND OK 40 21.01.20 : Kand A = submit kand A (154m) propose tower 154m di 106°50'25.83"E 6°31'20.88"S 106.840508° -6.522467°
684 |  | SUM-SB-PAD-0882 |  |  |  | RORO JONGRANG 2021 [NEW] |  | 100°22.44.44'E | 0°57.43.52'S | 28 | 10/90/170 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Sultan Syahrir No.114 / Jl. Pasar Baru 1 No.1, Kel. Koto Baru Nan XX, Kec. Lubuk Begalung, Kota Padang, Prov. Sumatera Barat | HTI | SUM-SB-PAD-0882 | PADANG_SELATAN_SEBERANG_PADANG | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kota Padang | 6617456 | 2021-09-07 |  | 233 | > 150 days | 2021-10-07 | W41-2021 | Oct-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | SPK RECALL (menunggu approval region dan msa untuk redesign ke site 309742001) | 09:08:2021: 08:22:2021: 08:18:2021: NEED REVIEW RNP HUWAWEI, ERM PROSES 08:16:2021: 08:09:2021 : SPK COLO RELEASED, ERM PROSES
713 |  | SUL-SN-MKS-1582 |  |  |  | RORO JONGRANG 2021 [NEW] |  | 119°31.38.75'E | 5°7.58.58'S | 40 | 120/230/350 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Kemuliaan Bangkala Utara, Kel. Tamalanrea RT.02 RW.018, Kec. Tamalanrea, Kota Makasar Prov. Sulawesi Selatan | HTI | SUL-SN-MKS-1582 | KOTIPA_RAYA_PACCERAKKANG | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kota Makassar | 6617556 | 2021-08-30 |  | 241 | > 150 days | 2021-09-29 | W40-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | RND NOK : FAR FROM NOM | 02:02:22: RETURN BY XL 09:12:21: PROPOSE RETURN BY XL 08:12:21-02:12:2021 : PROPOSE RETURN XL, Beda TP ID 01:12:21-28:11:21: NEED CONFIRM XL, GO OR NOT GOT? STATUS DI LMS ESR SUBMITTED 22:09:21:13:09:21: 08:09:21: ERM RESULD RND NOK FAR FROM NOM 30:08:21: ERM PROSES
|  | JAW-BT-RKB-0786 |  | 1321352003 | SUWAKAN | BP2022 | TB | 106°1.15.96'E | 6°30.35.17'S | 70 | 90/210/330 | 2022 |  |  | EID | JAW-BT-RKB-0786 | MEKARJAYA_CILELES | COLO | TBG | JABO | JABODETABEK | Banten | Kab. Lebak | 6618124 | 2022-03-16 | 2022-03-16 | 43 | 31 - 60 days | 2022-04-15 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | NOK BY XL : CHANGE PLAN | 19:04:22: NOK BY XL, CHANGE PLAN, RETURN BY XL 17:04:22-20:03:22: ERM PROCESS 16:03:22: SPK RECEIVED
661 |  | SUM-SU-AKK-2216 |  |  |  | RORO JONGRANG 2021 [NEW] |  | 99°52.14.3'E | 2°4.20.66'N | 50 | 70/180/320 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Tapa Dusun Rejo Mulio, Kel. Perdamean, Kec. Rantau Selatan, Kab. Labuhanbatu Utara, Prov. Sumatera Utara | HTI | SUM-SU-AKK-2216 | DANAU_BALAI | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu | 6617556 | 2021-08-30 |  | 241 | > 150 days | 2021-09-29 | W40-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | Drop by TBG (HARD COMMCASE) | 08:30:2021: ERM PROSES
786 |  | SUM-BB-PGP-0537 |  |  |  | RORO JONGRANG 2021 [NEW] |  | 106°6.42.23'E | 2°6.16.7'S | 20 | 80/170/340 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Jend. Sudirman, Kel. Gabek I RT. 03 RW. 01, Kec. Gabek, Kota Pangkal Pinang Prov. Kepulauan Bangka Belitung | HTI | SUM-BB-PGP-0537 | GABEK_DUA | COLO | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kota Pangkal Pinang | 6617547 | 2021-08-26 |  | 245 | > 150 days | 2021-09-25 | W39-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | Drop by TBG (HARD COMMCASE)
660 |  | SUM-SU-LBP-2295 |  |  |  | RORO JONGRANG 2021 [NEW] |  | 98°40.20.39'E | 3°30.49.93'N | 29 | 20/95/280 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Medan - Namorambe LK VIII, Desa Kedai Durian, Kec. Deli Tua, Kab. Deli Serdang, Sumut | HTI | SUM-SU-LBP-2295 | HAMPARAN_PERAK_SEI_BAHARU | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617489 | 2021-08-13 |  | 258 | > 150 days | 2021-09-12 | W38-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | DROP BY XL RND NOK : NEAR EXISTING XL | 13:09:21: DROP BY XL 08:09:21: RND NOK : NEAR EXISTING 22:08:21: 18:08:21: NEED REVIEW RNP HUWAWEI, ERM PROSES 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
780 |  | JAW-JI-GSK-4336 |  |  |  | RORO JONGRANG 2021 [NEW] |  | 112°37.28.56'E | 7°11.28.5'S | 40 | 5/165/270 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Mayjend Sungkono No.24, Gulomantung Kec. Kebomas, Kab. Gresik Prov. Jawa Timur | HTI | JAW-JI-GSK-4336 | KEBOMAS KEBOMAS | COLO | TBG | East | JATIM | Jawa Timur | Kab. Gresik | 6617456 | 2021-08-09 |  | 262 | > 150 days | 2021-09-08 | W37-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | RND NOK : NEED 40 METER | 04:10:21- 08:09:21: RND NOK NEED 40 M 22:08:21: 18:08:21: NEED REVIEW RNP HUWAWEI, ERM PROSES 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
779 |  | JAW-JI-NJK-4249 |  |  |  | RORO JONGRANG 2021 [NEW] |  | 111°54.0.43'E | 7°35.44.7'S | 30 | 60/190/275 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Widas 1, Ds. Begadung RT04 RW03 Kec. Nganjuk, Kab. Nganjuk Prov. Jawa Timur | HTI | JAW-JI-NJK-4249 | NGANJUK KAUMAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Nganjuk | 6617453 | 2021-08-09 |  | 262 | > 150 days | 2021-09-08 | W37-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | RND NOK : FAR FROM NOM | 04:10:21-29:09:21-08:09:21: RND NOK FAR FROM NOM 22:08:21: 18:08:21: NEED REVIEW RNP HUWAWEI, ERM PROSES 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
595 |  | JAW-BT-TNG-1520 | 30684860031 | TBG03_BTN233 | TANGERANG | ACTIVE - RELOCATION | TB | 106°37.37.88'E | 6°10.8.22'S | 45 | 90/210/330 | 2021 |  | Jl. Aipda KS Tubun No.18, Kel. Pasar Baru Kec Tangerang, Kota Tangerang Prov. Banten | EID | JAW-BT-TNG-1520 | KAMPUNG KOANG RELOCATION | COLO | TBG | JABO | JABODETABEK (INNER) | Banten | Kota Tangerang | 6617212 | 2021-05-29 |  | 334 | > 150 days | 2021-06-28 | W27-2021 | Jun-2021 | 2021-06-25 | W26-2021 | Jun-2021 | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | RETURN BY XL | 31:10:21-26:10:21: Dismantle, need email dismantle by XL 20:10:21-21.06.2021 : Power Connection Prosess, Need Confirmasi connect PLN by XL 08:10:2021: SRFI CONNECT PLN HOLD BY XL 06.17.2021 : ME OG 06.14.2021 : RBS & BTS Foundation 06.10.2021 : Mobilisasi dan Demobilisasi Team
NEW SPK |  | SUM-BE-TAS-0214 | 30735460031 | 090170109 | BENGKULU2014_2G5 | BP2022 | TB | 102°21.23.18'E | 3°53.59.25'S | 50 | 20/150/310 | 2022 | New site 2022 - P2 | Jl. Raya Bengkulu Seluma No. 61, Desa Babatan RT. 01, Kec. Sukaraja Kab. Seluma Prov. Bengkulu | HTI | SUM-BE-TAS-0214 | SUKARAJA_BABATAN | COLO | TBG | West | SUMBAGSEL | Bengkulu | Kab. Seluma | 6617991 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-02 | 2022-02-03 |  |  |  | 2022-04-07 | [6 empty] | NY STIP, ERM PROCESS | 02.SPK returned | 02.SPK RETURNED | RETURN BY XL | 20:04:22: SPK RETURN BY XL ON EMAIL 07:04:22: SPK RETURN BY XL 06:04:22-03:04:22: WAIT STRENGTENING & PLN CONNECTION 30:03:22-27:03:22: ME OG 23:03:22-09:03:22: BTS PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22-06:02:22: RND NOK NEED 50 METER 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
|  | JAW-JT-BLA-0129 |  |  |  | BP2022 | TB | 111°21.46.74'E | 7°10.50.84'S | 60 | 110/220/300 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-BLA-0129 | BLORA_RANDUBLATUNG | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Blora | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 02.SPK returned | 02.SPK RETURNED | RETURN BY XL CHANGE TO COLO | RETURN BY XL, CHANGE TO COLO 21:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED
NEW SPK |  | SUM-AC-STB-2233 | 30734850031 | 022026109 | STUNGKIT -3 | BP2022 | TB | 98°21.57.96'E | 3°40.41.99'N | 40 | 20/210/300 | 2022 | New site 2022 - P2 | Jl. Stungkit, Dusun III, Desa Stungkit, Kec. Wampu, Kab. Langkat, Prov. Sumatera Utara | HTI | SUM-AC-STB-2233 | WAMPU_STUNGKIT | COLO | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6617991 | 2022-01-28 | 2022-01-28 | 53 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 |  |  | 2022-03-22 | W13-2022 |  |  | STIP RELEASED, GO CME | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL DUE TO CHANGE SITE ID | 04:04:22: RFI BUT RETURN BY XL DUE TO CHANGE SITE ID 22:03:22: RFIN 20:03:22: SRFI 16:03:22-13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-AC-STB-2230 | 30734560031 | 022016109 | LADA HULU | BP2022 | TB | 98°25.41.16'E | 3°48.46.98'N | 50 | 30/160/240 | 2022 | New site 2022 - P2 | Jl. Penggabungan, Dusun VI, Desa Baru Pasar 8, Kec. Hinai, Kab. Langkat, Prov. Sumatera Utara | HTI | SUM-AC-STB-2230 | BARU_PASAR_VIII | COLO | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6617991 | 2022-01-28 | 2022-01-28 | 61 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-01 | 2022-02-02 | 122150561096 |  |  | 2022-03-22 |  |  | 2022-03-30 | W14-2022 |  |  | STIP RELEASED, GO CME | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL DUE TO CHANGE SITE ID | 04:04:22: RFI BUT RETURN BY XL DUE TO CHANGE SITE ID 30:03:22: RFIN 27:03:22-23:03:22-20:03:22: SRFI 16:03:22-13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-AC-STB-2239 | 30734660031 | TBG05_NSM178 | KUALA MADU | BP2022 | BK | 98°30.11.88'E | 3°42.49.0'N | 50 | 0/130/230 | 2022 | New site 2022 - P2 | Jl. Amarta Karang Rejo Langkat Sumatera Utara Sumatera Utara | HTI | SUM-AC-STB-2239 | STABAT_KARANG_REJO | COLO | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6617980 | 2022-01-28 | 2022-01-28 | 61 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-01 | 2022-02-02 | 122140915415 |  |  | 2022-03-22 |  | 2022-03-22 | 2022-03-30 | W14-2022 |  |  | STIP RELEASED, GO CME | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL DUE TO CHANGE SITE ID | 04:04:22: RFI BUT RETURN BY XL DUE TO CHANGE SITE ID 30:03:22: RFIN 27:03:22-23:03:22-20:03:22: SRFI 16:03:22-13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-AC-STB-2232 | 30734530031 | 022236109 | API_SELOTONG SECANGGANG | BP2022 | TB | 98°33.33.12'E | 3°52.9.98'N | 50 | 100/210/300 | 2022 | New site 2022 - P1 | Jl. Besat Selotong / Jl. Tambak, Dusun I, Desa Selotong, Kec. Secanggang, Kab. Langkat, Prov. Sumatera Utara | HTI | SUM-AC-STB-2232 | SELOTONG | COLO | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6617991 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-04-10 | W16-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 |  | 2022-04-04 |  |  |  |  | STIP RELEASED, GO CME | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL DUE TO CHANGE SITE ID | 04:04:22: RETURN BY XL DUE TO CHANGE SITE ID 04:03:22: SRFIN 03:04:22-30:03:22: PLN 27:03:22-16:03:22: ME PARALEL STRENGTENING 1603:22-09:03:22: BTS PONDASI OG, PARALEL STRENGTENING 06:03:22-16:02:22: READY TO STO 13:02:22-09:02:22: READY TO DECLARE STO 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-AC-STB-2225 | 30734900031 | 022021109 | HINAI KIRI HULU | BP2022 | TB | 98°27.46.15'E | 3°49.35.15'N | 50 | 10/140/280 | 2022 | New site 2022 - P2 | JL. Caraka , Dusun II , Desa Hinai Kanan, Kec. Hinai, Kab. Langkat, Prov. Sumatera Utara. | HTI | SUM-AC-STB-2225 | HINAI_KANAN | COLO | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6617991 | 2022-01-28 | 2022-01-28 | 62 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 |  | 2022-02-01 | 2022-02-02 | MG |  |  | 2022-03-22 |  |  | 2022-03-31 | W14-2022 |  |  | STIP RELEASED, GO CME | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL DUE TO CHANGE SITE ID | 04:04:22: RFI BUT RETURN BY XL DUE TO CHANGE SITE ID 31:03:22: RFIN 30:03:22-23:03:22: SRFI 20:03:22-16:03:22: SRFI, WAIT STO & PLN 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-AC-STB-2229 | 30735160031 | 022012109 | SICANGGANG HINAI | BP2022 | TB | 98°29.25.08'E | 3°51.36.0'N | 50 | 100/210/280 | 2022 | New site 2022 - P2 | Lingkungan VII, Kel. Hinai Kiri, Kec. Secanggang, Kab. Langkat, Prov. Sumatera Utara | HTI | SUM-AC-STB-2229 | HINAI_KIRI | COLO | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6617991 | 2022-01-28 | 2022-01-28 | 62 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 |  |  | 2022-03-31 | W14-2022 |  |  | STIP RELEASED, GO CME | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL DUE TO CHANGE SITE ID | 04:04:22: RFI BUT RETURN BY XL DUE TO CHANGE SITE ID 31:03:22: RFIN 30:03:22-23:03:22: SRFI 20:03:22-16:03:22: SRFI, WAIT STO & PLN 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK B2S |  | JAW-BT-TGR-0109 |  |  |  | BP2022 | TB | 106°26.8.39'E | 6°16.51.79'S | 50 | 90/220/350 | 2022-2024 | COMMITMENT NEW ORDER B2S 2022-2024 |  | EID | JAW-BT-TGR-0109 | JEUNGJING_CISOKA | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Tangerang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [5 empty] | 2022-03-09 | [6 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | SPK RETURN CHAGE TO COLO 06:02:22-04:02:22: PRIORITY CANDIDATE A 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
|  | JAW-JT-TMG-2680 |  |  |  | BP2022 | TB | 110°2.13.42'E | 7°14.50.27'S | 70 | 40/150/280 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-TMG-2680 | DLIMOYO_TEMANGGUNG | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Temanggung | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 02.SPK returned | 02.SPK RETURNED | RETURN BY XL CHANGE TO COLO | RETURN BY XL, CHANGE TO COLO 21:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED
950 |  | SUL-ST-LWK-1068 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 122°20.14.0'E | 1°27.10.09'S | 60 | 0/120/220 | 2021 |  |  | HTI | SUL-ST-LWK-1068 | TOILI | B2S | TBG | EAST | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617749 | 2021-10-25 |  | 185 | > 150 days | 2022-03-24 | W13-2022 | Mar-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [5 empty] | 2022-02-25 | [7 empty] | 02.SPK returned | 02.SPK RETURNED | CURRENTLY NO ISSUE | 24:11:21: NEW SPK RELEASED PENGGANTI TO SITE ID TP 260297109 21:11:21-10:11:21-03:11:21: CHANGE PLAN PROPOSE TO COLO 31:10:21: SURVEY OG, PLAN SUBMIT KANDIDAT W 1 NOV
|  | KAL-KT-KLK-0696 | 30720680031 | 210239109 | TB_DWK | NEW SITE 2022-REPEATER | SKP | 114°4.51.82'E | 0°50.38.08'S | 60 | 157/260 | 2021 | NEW SITE 2022-REPEATER |  | HTI | KAL-KT-KLK-0696 | REPEATER JAKATAN PARI | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Tengah | Kab. Kapuas | 6617861 | 2021-12-02 |  | 40 | 31 - 60 days | 2022-01-01 | W01-2022 | Jan-2022 | TBD | TBD | TBD | 2022-01-21 | W04-2022 | Jan-2022 | 2022-01-21 | W04-2022 | Jan-2022 | MW | 2021-12-16 |  |  |  |  | 2021-12-13 |  |  | 2022-01-11 | W03-2022 |  |  |  | 02.SPK returned | 02.SPK RETURNED | CLOSED - RFI DONE | 11:01:22: RFIN BUT SPK RETURN 09:01:22: SRFI, PLN CONNECTION & PARALEL PKS PLN BY CORPORATE 05:02:22-02:01:22: ME OG, REGIST PLN & PARALEL PKS KE CORPORATE 29:12:21-26:12:21: PONDASI RBS OG 22:12:21-15:12:21: STO DECLARED, CME PREPARATION 12:12:21: NEED REVIEW TNP 08:12:21-05:12:21: ERM PROCESS, NEED REVIEW RNP
854 |  | JAW-JI-SBY-4337 | 30571350031 | 1643121003 | RUNGKUT_MDKNAYU | SPK RETURN BY XL | TB | 112.8041 | -7.3298 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-SBY-4337 | RUNGKUT_MDKNAYU | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA SURABAYA | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [5 empty] | 2021-03-29 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 22.06.20 : email SPK return by XL karena antenna too low, isu perda max ijin ketinggian tower, status di TR sudah return (remark antena too low) 18.06.20 : kand NOT OK by RND karena propose tinggi tower too low (antena too low) 15.06.20 : IW clear, waiting approval opr (reduce ketinggian menara) 11.06.20 : propose RT 2 lantai+stacking 4m+pole 6m = 17 m, need review RND terkait propose ketinggian 08.06.20 : IW clear 04.06.20 : IW on going, paralel rehunting kand alternatif 28.05.20 : 25.05.20 : rehunting 14.05.20 : 08.05.20 : 30.04.20 : rehunting 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting, ketinggian yang diminta XL 20m. Propose ketinggian ke LL atau rehunting di gedung yang tinggi 19.03.20 : validasi RND 12.03.20 : need approval kandidat, TNP validation, propose reduce ketinggian 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 31.01.20 : Kand A = submit A 112.80358 -7.330136 RT 9m + Pole 6m, Perda Kota Surabaya utk area Rungkut max RT+pole 6m, Total ketinggian 15mAgl
820 |  | SUL-SA-TMH-0423 | 30613480031 | 2404831003 | TOMOHON_UTARA | SPK RETURN | TB | 124°50.4.37'E | 1°20.36.55'N | 50 | 165/260/350 | 2020 | JEDI 2020 [NEW] |  | HTI | SUL-SA-TMH-0423 | TOMOHON_UTARA | B2S | TBG | EAST | SULAWESI | Sulawesi Utara | Kota Tomohon | 6616486 | 2020-11-19 |  | 525 | > 150 days | 2021-04-18 | W17-2021 | Apr-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [5 empty] | 2021-03-05 | [7 empty] | 02.SPK returned | 02.SPK RETURNED | Restricted Area (GOWA) | 11.01.21 : email SPK return 1 Dec 23.11.20 : hunting, isu NOM berada di restricted area (IMB tidak bisa release) 19.11.20 : SPK release
812 |  | JAW-JI-SDA-4067 | 30571400031 | 1643171003 | TAMAN_GELURAN | SPK RETURN | TB | 112.6961 | -7.3683 | 30 | 60/200/300 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-SDA-4067 | TAMAN_GELURAN | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2021-03-05 | [7 empty] | 02.SPK returned | 02.SPK RETURNED | Terdapat hystory hard comcase di SAR NOM | 30.04.20 : rehunting 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : rehunting 19.03.20 : IW on going, need approval kandidat 12.03.20 : rehunting 13.02.20 : email Return SPK 10 feb 20 sesuai Surat permohonan perpanjangan waktu SPK B2S ke LM XL, Reason return karena terdapat history hard comcase di NOM 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 04.02.20 : Kand A = submit A 112.69219 -7.370028 470.59 RT 8 Pole 6 Perda antar tower Kab Sidoarjo with justification & Panoramic attached
802 |  | JAW-JI-SBY-4339 | 30571360031 | 1643131003 | MULYOREJO_KEJAWAN_PUTIH_TAMBAK | SPK RETURN | TB | 112.8099 | -7.2813 | 30 | 0/160/280 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-SBY-4339 | MULYOREJO_KEJAWAN_PUTIH_TAMBAK | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA SURABAYA | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2021-02-05 | [7 empty] | 02.SPK returned | 02.SPK RETURNED | Area Developer (Pakuwon) | 30.04.20 : rehunting 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : 19.03.20 : 12.03.20 : rehunting 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 31.01.20 : Kand A = submit A 112.807683 -7.278589 RT 12 + Pole 6 Total ketinggian 18mAgl, Perda Kota Surabaya utk area Rungkut max RT+pole 6m,
891 |  | SUM-SS-PLG-1175 |  |  |  | SPK RETURN BY XL |  | 104.7856 | -2.9458 | 30 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jalan Brigjen H. Hasan Kasim Rt. 044 Rw. 09 Kel. Bukit Sangkal Kec. Kalidoni, Palembang - Sumatera Selatan | HTI | SUM-SS-PLG-1175 | BUKIT SANGKAL_KALIDONI | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | KOTA PALEMBANG | 6614396 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2021-02-03 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.01.20 : email Return by XL, Teknik, Antenna too low 24.01.20 : email pengmebalian SPK by Markering karena Drop by XL (RND NOK -> ANTENNA TOO LOW)
892 |  | SUM-SU-STB-2187 |  |  |  | SPK RETURN BY XL |  | 98.3216 | 3.8961 | 50 | 60/150/310 | 2020 | JEDI 2020 [NEW] |  | HTI | SUM-SU-STB-2187 | BULUH TELANG | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | LANGKAT | 6614850 | 2020-07-06 |  | 661 | > 150 days | 2020-08-05 | W32-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [5 empty] | 2021-01-20 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 27.08.20 : email SPK return by XL (Pak Yanse), Return Category Technical , Return By XL, Remark Antenna Height Too Low 30.07.20 : drop by XL, RND--> antena too low 23.07.20 : 23.07.20 : RND not OK, RND meminta 50m 17.07.20 : UNDER REVIEW RND HUAWEI
909 |  | SUM-SB-LBB-0822 |  |  |  | SPK RETURN BY XL |  | 100.4746 | -0.31565 | 50 | 140/200/340 | 2020 | JEDI 2020 [NEW] |  | HTI | SUM-SB-LBB-0822 | KOTO TINGGI_AGAM | COLO | TBG | WEST | SUMBAGTENG | Sumatera Barat | KAB. AGAM | 6614850 | 2020-07-06 |  | 661 | > 150 days | 2020-08-05 | W32-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [5 empty] | 2020-12-21 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 17.07.20 : ERM DROP BY XL, reason Sectoral blocking 06.07.20 : SPK release
875 |  | SUM-SU-SRH-2047 | 30595830031 | 0223871003 | SIMPANG TIGA PEKAN | SPK RETURN BY XL | TB | 98.959 | 3.568 | 30 | 90/190/330 | 2020 | JEDI 2020 [NEW] |  | HTI | SUM-SU-SRH-2047 | SIMPANG TIGA PEKAN | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KAB. SERDANG BEDAGAI | 6614816 | 2020-07-01 |  | 666 | > 150 days | 2020-11-28 | W48-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [5 empty] | 2020-12-16 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 15.07.20 : email return SPK, return karena hard kandidat (penolakan warga/community issue) 14.07.20 : arahan RND XL ke Sekolah Yayasan Perguruan Setia Budi Abadi rooftop kandidat 98.958650° 3.567426°, namun tidak mendapat ijin pihak yayasan/sekolah karena dpt mengganggu kegiatan belajar dan tdk dapat dikontrolnya jika ada penolakan warga. SPK potensi return karena NOM XL tetap berada pada titik combat existing. 13.07.20 : hasil survey : • Tepat di Lokasi NOM (Koordinat : 3.568 ; 98.9589722) terdapat Combat XL yang sudah berdiri namun kondisi tidak On Air (informasi dikarenakan mendapatkan penolakan dari warga) • Jarak ke site Eksisting TBG  308 m • Jarak ke site Eksisting XL  867 m Problem Identification : • Area sekitar NOM banyak terdapat Sarang Walet yang menjadi mata pencaharian warga sekitar dan warga berkeberatan terhadap adanya Tower karena merasa sinyal frekuensi tower menggangu burung walet tsb • Faktor lain bunyi BTS Tower membuat burung Walet menjadi takut kembali ke sarang • Hasil pertemuan dengan Kepala Dusun setempat menjelaskan bahwa warga setempat (khususnya warga Desa Simpang Tiga) menolak pendirian tower (file terlampir) Alternatif Solusi : • Plan A adalah Colo ke site Eksisting TBG, Site Kota Galuh 020583109 Koordinat : 3.56720 ; 98.96047 • Plan B adalah propose kandidat diluar area Desa Simpang Tiga (diluar area highlight merah) untuk menghindari penolakan warga 03.07.20 : Propose colo NOT OK by RND XL (Pak Doddy), remark : mendekat ke existing, lebih baik survey dekat NOM dahulu. 02.07.20 : propose Colo to existing site 020583109 KOTA GALUH 98.95689 3.56615 (309.3m ) Rooftop 25m + pole 12m 01.07.20 : SPK release
912 |  | JAW-JI-KNR-4268 |  |  |  | SPK RETURN BY XL |  | 112.3284 | -8.0637 | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-KNR-4268 | WLINGI BABADAN | COLO | TBG | EAST | JATIM | Jawa Timur | BLITAR | 6614847 | 2020-07-06 |  | 661 | > 150 days | 2020-08-05 | W32-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [5 empty] | 2020-12-08 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 17.07.20 : ERM DROP BY XL, antena too low 06.07.20 : SPK release
800 |  | JAW-JI-SDA-4083 | 30571520031 | 1643291003 | KRIAN_SIDOMOJO | SPK RETURN | TB | 112.5866 | -7.3914 | 40 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Dsn. Tundungan RT 03 RW 02 Desa Sidomojo Kec. Krian Kab. Sidoarjo Prov. Jawa Timur | HTI | JAW-JI-SDA-4083 | KRIAN_SIDOMOJO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [5 empty] | 2020-12-08 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 21.09.20 : email return by system, hard kandidat 17.09.20 : Site return by XL 10.09.20 : 07.09.20 : start CME paling lambat minggu ini 10 sept 20 03.09.20 : proses fu perijinan, plan start CME minggu depan 31.08.20 : 27.08.20 : 24.08.20 : belum dapat start CME, msh butuh mediasi dng Muspika desa, plan start CME di awal bulan Sep 17.08.20 : 13.08.20 : plan start CME 20 Aug 20 (minggu depan) 10.08.20 : proses design, plan start CME 12 Aug 06.08.20 : plan start CME 12 Aug 03.08.20 : 23.07.20 : plan start CME 28 jul 13.07.20 : 02.07.20 : proses perijinan, plan start CME W2 Juli 29.06.20 : plan start CME W2 Juli or drop 25.06.20 : plan start CME minggu depan 22.06.20 : proses soiltest, proses perijinan, plan start CME awal July, plan RFI end July 18.06.20 : proses perijinan, plan start CME awal July, plan RFI end July 15.06.20 : request soiltest, proses perijinan 11.06.20 : 08.06.20 : 04.06.20 : IW clear,realisasi IW 01.06.20 : 28.05.20 : 25.05.20 : 14.05.20 : IW clear, renego biaya sitac 08.05.20 : 30.04.20 : 23.04.20 : 16.04.20 : IW clear, renego biaya sitac 09.04.20 : 02.04.20 : 25.03.20 : 19.03.20 : IW clear, proses renego kompensasi 11.03.20 : IW clear, proses renego dan validasi biaya sitac 28.02.20 : 26.02.20 :kand -7.393194,112.58481, IW clear 26 KK 24.02.20 : IW Clear 20.02.20 : IW On going 13.02.20 : IW on going 06.02.20 : Kand C = Candidate C Submit 27.01.20 : kand A = 112.58667 -7.3915 11.36 GF SST 42 kand B = 112.58644 -7.3919722 65.89 GF SST 42
902 |  | JAW-JI-NJK-3911 |  |  |  | SPK RETURN BY XL |  | 112.0469 | -7.626 | 40 | 30/170/270 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-NJK-3911 | NGRONGGOT_KALORAN | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. NGANJUK | 6614391 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2020-11-25 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 28.01.20 : email Return by XL, Teknik, Antenna too low
858 |  | JAW-JB-SOR-3838 | 30590150031 | 1262061003 | SOREANG_SOREANG | SPK RETURN BY XL | TB | 107.5197 | -7.0331 | 30 | 0/110/250 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JB-SOR-3838 | SOREANG_SOREANG | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614612 | 2020-04-03 |  | 755 | > 150 days | 2020-08-31 | W36-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2020-09-16 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 08.05.20 : email SPK RETURN BY XL karena perubahan plan (email Pak Sony) 30.04.20 : hunting perluasan SAR ke 4 arah berbeda plan submit Sabtu tgl 3 Mei 23.04.20 : 16.04.20 : validasi kandidat 09.04.20 : 06.04.20 : Hunting
895 |  | JAW-JB-SOR-3682 |  |  |  | SPK RETURN BY XL |  | 107.6208 | -7.059 | 30 | 90/180/320 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JB-SOR-3682 | BAROS_ARJASARI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614391 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2020-08-11 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 28.01.20 : email Return by XL, Teknik, Sectoral Blocking
886 |  | SUM-SS-PLG-1172 |  |  |  | SPK RETURN BY XL |  | 104.8507 | -2.9365 | 40 | 30/200/300 | 2020 | JEDI 2020 [NEW] |  | HTI | SUM-SS-PLG-1172 | KARYA MULIA | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | KOTA PALEMBANG | 6614396 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2020-06-15 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.01.20 : email Return by XL, Teknik, Antenna too low 24.01.20 : email pengmebalian SPK by Markering karena Drop by XL (RND NOK -> ANTENNA TOO LOW)
894 |  | JAW-JB-NPH-3750 |  |  |  | SPK RETURN BY XL |  | 107.359 | -6.9742 | 40 | 90/210/330 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JB-NPH-3750 | GIRIMUKTI_CIPONGKOR | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614387 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [6 empty] | 2020-05-13 | [7 empty] | 02.SPK returned | 02.SPK RETURNED |  | 28.01.20 : email Return by XL, Teknik, Sectoral Blocking 24.01.20 : email pengembalian SPK by Markering karena Drop by XL (RND NOK -> SECTORAL BLOCKING)
|  | JAW-JT-KRG-2129 | 30743120031 | 1451321003 | KARANGANYAR JATIYOSO LALUNG | BP2022 | TB | 110°56.41.3'E | 7°37.10.53'S | 50 | 10/110/190/280 | 2022 | Newsite 2021 |  | EID | JAW-JT-KRG-2129 | KARANGANYAR JATIYOSO LALUNG | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Karanganyar | 6618174 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 02.SPK returned | 02.SPK RETURNED | CHANGED TO COLO PKP | RETURNED CHANGED TO COLO PKP 13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED
|  | JAW-JK-TJP-0720 |  |  |  |  | TB | 106°55.17.38'E | 6°6.37.73'S | 25 | 90/210/330 | 2022 |  |  | EID | JAW-JK-TJP-0720 | CACING CILINCING RELOCATION | B2S | TBG | Jabodetabek | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Utara | 6618152 | 2022-03-24 | 2022-03-24 | 35 | 31 - 60 days | 2022-08-21 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | 29:03:22: SPK CHANGE TO COLO RECEIVED 24:03:22: SPK RECEIVED
|  | JAW-BT-RKB-0786 |  |  |  | BP2022 | TB | 106°0.21.41'E | 6°30.36.26'S | 60 | 90/190/340 | 2022 | Newsite 2022 - B2 |  | EID | JAW-BT-RKB-0786 | MEKARJAYA_CILELES | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Lebak | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | PROPOSE CHANGE TO COLO | 16:03:22: DROP, CHANGE TO COLO 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED
89 COLO |  | KAL-KT-PPS-0708 |  | 210515126 | MULIA SARI | BP2022 | TB | 114°10.3.11'E | 2°59.12.52'S | 50 | 180/250/320 | 2022 | Newsite 2022 - B2 | Desa Badirih RT 03 RW 02, Kec. Maliku, Kab. Pulang Pisau Prov. Kalimantan Tengah | HTI | KAL-KT-PPS-0708 | BADIRIH_MALIKU | COLO | TBG | Central | KALIMANTAN | Kalimantan Tengah | Kab. Pulang Pisau | 6618079 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-24 | 2022-03-25 | [11 empty] | 02.SPK returned | 02.SPK RETURNED | ANTENA HEIGH TOO LOW, XL PROPOSE RETURN | 01:04:22: SPK RETURN 31:03:22: ANTENA HEIGH TOO LOW, XL PROPOSE RETURN 30:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED
|  | JAW-JT-BNR-0272 |  |  |  | BP2022 | TB | 109°42.43.2'E | 7°19.40.08'S | 70 | 80/170/320 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-BNR-0272 | SIJERUK_BANJARNEGARA | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Banjarnegara | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 02.SPK returned | 02.SPK RETURNED | RETURN BY XL CHANGE TO COLO | RETURN BY XL, CHANGE TO COLO 21:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED
|  | SUM-SU-AKK-2244 | 30740210031 | 0229301003 | BILAH_BARAT_KAMPUNG_BARU | BP2022 | TB | 99°48.42.19'E | 2°8.44.98'N | 50 | 90/220/330 | 2022 | Newsite 2022 - B2 |  | HTI | SUM-SU-AKK-2244 | BILAH_BARAT_KAMPUNG_BARU | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu | 6618109 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SPK RETURN | 02.SPK returned | 02.SPK RETURNED | IMB TIDAK BISA TERBIT | 22:03:22: SPK RETURN ISSUE LABUHAN BATU IMB TIDAK BISA TERBIT 23:03:22-13:03:22: TBG PROPOSE RETURN, ISSUE LABUHAN BATU IMB TIDAK BISA TERBIT 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED
|  | SUM-SU-LMP-2237 |  |  |  | BP2022 | TB | 99°25.39.29'E | 3°9.49.18'N | 50 | 130/220/340 | 2022 | Newsite 2022 - B2 |  | HTI | SUM-SU-LMP-2237 | PERKEBUNAN_DOLOK | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Batu Bara | 6618109 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | 09:03:22: SPK RETURN CHANGE TO COLO 07:03:22: SPK RECEIVED
|  | JAW-BT-TGR-0114 |  | 1321752004 |  | BP2022 | TB | 106°36.2.02'E | 6°5.18.96'S | 40 | 0/120/240 | 2022 | Newsite 2022 - P2 |  | EID | JAW-BT-TGR-0114 | RAWA_BONI_PAKUHAJI | COLO | TBG | JABO | JABODETABEK | Banten | Kab. Tangerang | 6618135 | 2022-03-18 | 2022-03-18 | 41 | 31 - 60 days | 2022-04-17 | W17-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | NOK BY XL : CHANGE PLAN | 19:04:22: NOK BY XL, CHANGE PLAN, RETURN BY XL 17:04:22-20:03:22: ERM PROCESS 16:03:22: SPK RECEIVED
|  | JAW-BT-TGR-0114 |  |  |  | BP2022 | TB | 106°36.3.18'E | 6°5.7.5'S | 50 | 0/120/240 | 2022 | Newsite 2022 - P2 |  | EID | JAW-BT-TGR-0114 | RAWA_BONI_PAKUHAJI | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Tangerang | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | CHANGE TO COLO 16:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED
568 |  | SUM-SB-ARS-0852 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 100° 40' 33.18" E | 1° 1' 37.45" S | 60 | 60/150/280 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Simpang SMPN 4 Jorong Koto Ateh, Nagari Aia Batumbuk, Kec. Gunung Talang, Kab. Solok, Prov. Sumatera Barat | HTI | SUM-SB-ARS-0852 | AIA_BATUMBUAK | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Solok | 6617506 | 2021-08-16 |  | 255 | > 150 days | 2021-09-15 | W38-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL | 21:04:22: SPK RETURN BY XL, NY POTENTIAL TO ADD RPEATER 20:04:22-28:11:21: NEED CONFIRM XL, GO OR NOT GOT? STATUS DI LMS ESR SUBMITTED 22:09:21: 19:09:21:15:09:21: 13:09:21: ERM REJECTION 08:09:21: 30:08:21:22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21 : SPK COLO RELEASED, ERM PROSESS
569 |  | SUM-SB-PNN-0801 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 100° 23' 33.48" E | 1° 7' 52.47" S | 50 | 210/340 | 2021 | BLITZKRIEG 2021 [NEW] | RT 03 RW 01 Kel. Teluk Kabung Bungus Selatan Kec. Teluk Kabung | HTI | SUM-SB-PNN-0801 | BATUGUNCANG_SUNGAI_PINANG | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Pesisir Selatan | 6617506 | 2021-08-16 |  | 255 | > 150 days | 2021-09-15 | W38-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL | 21:04:22: SPK RETURN BY XL, NY POTENTIAL TO ADD RPEATER 20:04:22-28:11:21: NEED CONFIRM XL, GO OR NOT GOT? STATUS DI LMS ESR SUBMITTED 22:09:21: 19:09:21:15:09:21: 13:09:21: ERM REJECTION 08:09:21: 30:08:21:22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21 : SPK COLO RELEASED, ERM PROSESS
|  | JAW-JK-GGP-0453 |  |  |  | BP2022 | TB | 106°47.0.01'E | 6°12.23.61'S | 25 | 90/210/330 | 2022 - 2024 | COMMITMENT NEW ORDER B2S 2022-2024 |  | EID | JAW-JK-GGP-0453 | RAWA BELONG BANGO RELOCATION | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Jakarta Barat | 6618001 | 2022-01-31 | 2022-01-31 | 87 | 61 - 90 days | 2022-06-30 | W27-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | 02:02:22: SPK RETURN, CHANGE COLO TO PKP 31:01:22: SPK RELEASED
|  | SUM-KR-BTM-0607 | 30744080031 |  |  | BP2022 | TB | 103°55.30.83'E | 1°2.31.09'N | 41 | 110/240/340 | 2022 | Newsite 2021 - H2 |  | HTI | SUM-KR-BTM-0607 | BATU_AJI_TANJUNG_UNCANG | B2S | TBG | West | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6618203 | 2022-04-08 | 2022-04-11 | 20 | < 30 days | 2022-09-05 | W37-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 02.SPK returned | 02.SPK RETURNED | RETURN BY XL CHANGE TO COLO | 22:04:22: SPK RETURN BY XL DUE TO CHANGE TO COLO 20:04:22-19:04:22: PARALEL IW ON GOING SITEPERMANENISASI COMBAT BATAM AREA 17:04:22-13:04:22: IW OG 10:04:22: VALIDASI RNP TNP 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED
NEW SPK |  | JAW-JT-JPA-0710 |  | 1441472004 | IBS SOWAN LOR | BP2022 | TB | 110°40.15.24'E | 6°41.4.06'S | 68 | 20/100/190 | 2022-2024 | COMMITMENT NEW ORDER COLO 2022-2024 | Desa Sowan Lor RT.013 RW.003 Kec.Kedung, Kab.Jepara Prov. Jawa Tengah | EID | JAW-JT-JPA-0710 | SOWAN_LOR_JEPARA | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Jepara | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-02 | [12 empty] | 02.SPK returned | 02.SPK RETURNED | CHANGE KANDIDAT TO WANUSOBO | 07:02:22: CHANGE CANDIDATE TO WANUSOBO 06:02:22-30:01:22: ESR REVIEW, NEED REVIEW RNP EID 28:01:22: SPK RELEASED
NEW SPK |  | SUM-SS-MRD-1002 | #N/A | 70269104 | TANJUNG_KARI | BP2022 | SMI | 103°39.53.28'E | 4°28.40.91'S | 65 | 25/160/265 | 2022 | New site 2022 - P2 | Desa Tanjung Kari, Kec. Pulau Beringin, Kab. OKU Selatan Prov. Sumatera Selatan | HTI | SUM-SS-MRD-1002 | TANJUNG_KARI | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Se | 6617988 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-01 | 2022-02-02 | [10 empty] | NY STIP, ERM PROCESS | 02.SPK returned | 02.SPK RETURNED | RETURN BY XL | 07:04:22: SPK RETURN BY XL, FAR FROM NOM 06:04:22-06:02:22: RND NOK FAR FROM NOM 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-SS-MRD-1011 | #N/A | 71087109 | SUNGAI ARE | BP2022 | TB | 103°30.56.48'E | 4°29.9.38'S | 65 | 100/240/335 | 2022 | New site 2022 - P2 | Desa Simpang Luas Kec Sungai Are Kab OKU Selatan | HTI | SUM-SS-MRD-1011 | SIMPANG_LUAS | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Se | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-01 | 2022-02-02 | [10 empty] | NY STIP, ERM PROCESS | 02.SPK returned | 02.SPK RETURNED | RETURN BY XL | 20:04:22: SPK RETURN BY XL ON EMAIL 07:04:22: SPK RETURN BY XL 06:04:22-06:02:22: TNP NOK : NOT LOS 23:02:22-09:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-SS-MRD-1014 | #N/A | 71086109 | SINDANG DANAU | BP2022 | TB | 103°33.44.1'E | 4°27.6.7'S | 65 | 15/100/200 | 2022 | New site 2022 - P2 | Desa Ulu Danau Kec. Sindang Danau OKU SUMSEL | HTI | SUM-SS-MRD-1014 | PEMATANG_DANAU | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Se | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-01 | 2022-02-02 | [10 empty] | NY STIP, ERM PROCESS | 02.SPK returned | 02.SPK RETURNED | RETURN BY XL | 20:04:22: SPK RETURN BY XL ON EMAIL 07:04:22: SPK RETURN BY XL 06:04:22-06:02:22: TNP NOK : NOT LOS 23:02:22-09:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-SS-MRD-1008 | #N/A | 71393109 | DESA TANJUNG BULAN ULU | BP2022 | TB | 103°36.22.18'E | 4°29.31.7'S | 40 | 120/290 | 2022 | New site 2022 - P2 | Dusun I Desa Tanjung Bulan Kec. Pilau Beringin Kab. Ogan Komering Ulu Selatan Prov. Sumatra Selatan | HTI | SUM-SS-MRD-1008 | TANJUNG_BULAN_ULU | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Se | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-01 | 2022-02-02 | [10 empty] | NY STIP, ERM PROCESS | 02.SPK returned | 02.SPK RETURNED | RETURN BY XL | 20:04:22: SPK RETURN BY XL ON EMAIL 07:04:22: SPK RETURN BY XL 06:04:22-06:02:22: TNP NOK : NOT LOS 23:02:22-09:02:22: NEED REVIEW TNP ALITA 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK B2S |  | SUM-AC-STB-2235 | 30730340031 | 0229081003 | PERTUMBUKAN | BP2022 | TB | 98°23.44.16'E | 3°42.49.0'N | 60 | 0/80/270 | 2022 | New site 2022 - P2 | Dusun I, Desa Pertumbukan, Kec. Wampu, Kab. Langkat, Provinsi Sumatera Utara | HTI | SUM-AC-STB-2235 | PERTUMBUKAN | B2S | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 2022-02-25 | 2022-03-02 | [10 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL DUE TO CHANGE SITE ID | 06:04:22: RETURN BY XL DUE TO CHANGE SITE ID 03:04:22-30:03:22: PREPARE ERECTION 27:03:22-23:03:22: LEAN CONCRETE 20:03:22: MOBDEMOB 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: REKOM DONE 06:03:22-28:02:22: REKOM OG 23:02:22-16:02:22: IW CLEAR 13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | SUM-AC-STB-2231 | 30730330031 | 0229071003 | SECANGGANG_KARANG_GADING | BP2022 | TB | 98°34.35.47'E | 3°50.4.25'N | 50 | 80/160/300 | 2022 | New site 2022 - P2 | Dusun VI Merbau Rintis | HTI | SUM-AC-STB-2231 | SECANGGANG_KARANG_GADING | B2S | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 2022-02-25 | 2022-03-02 | [10 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL DUE TO CHANGE SITE ID | 06:04:22: RETURN BY XL DUE TO CHANGE SITE ID 03:04:22-30:03:22: PREPARE ERECTION 27:03:22-23:03:22: EXCAVATION 20:03:22: MOBDEMOB 16:03:22: RFC 13:03:22: PERMIT OG 09:03:22: REKOM DONE 06:03:22-28:02:22: REKOM OG 23:02:22-16:02:22: IW CLEAR 13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-BT-TGR-0113 | 30729540031 |  |  | BP2022 | TB | 106°41.56.07'E | 6°3.22.25'S | 40 | 0/90/180/270 | 2022-2024 | COMMITMENT NEW ORDER B2S 2022-2024 |  | EID | JAW-BT-TGR-0113 | SALEMBARAN_JAYA_KOSAMBI | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Tangerang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SPK RETURN | 02.SPK returned | 02.SPK RETURNED | ISSUE KAWASAN PIK | 08:02:22: SPK PROPOSED RETURN BY TBG, ISSUE KAWASAN PIK 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | SUM-SU-AKK-2238 | 30729650031 |  |  | BP2022 | TB | 99°51.21.81'E | 2°3.52.46'N | 50 | 50/150/290 | 2022-2024 | COMMITMENT NEW ORDER B2S 2022-2024 |  | HTI | SUM-SU-AKK-2238 | KELURAHAN_UJUNG_BANDAR | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SPK RETURN | 02.SPK returned | 02.SPK RETURNED | OUTCELL LABUHAN BATU (IMB TIDAK BISA TERBIT) | 09:02:22: SPK RETURN OUTCELL LABUHAN BATU, IMB TIDAK BISA TERBIT 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | SUM-SU-AKK-2241 | 30729660031 |  |  | BP2022 | TB | 99°49.46.6'E | 2°6.45.54'N | 50 | 50/16/260 | 2022-2024 | COMMITMENT NEW ORDER B2S 2022-2024 |  | HTI | SUM-SU-AKK-2241 | KELURAHAN_PADANG_MATINGGI | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SPK RETURN | 02.SPK returned | 02.SPK RETURNED | OUTCELL LABUHAN BATU (IMB TIDAK BISA TERBIT) | 09:02:22: SPK RETURN OUTCELL LABUHAN BATU, IMB TIDAK BISA TERBIT 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | SUM-SU-AKK-2246 | 30729760031 |  |  | BP2022 | TB | 99°50.28.64'E | 2°6.7.28'N | 50 | 100/200/290 | 2022-2024 | COMMITMENT NEW ORDER B2S 2022-2024 |  | HTI | SUM-SU-AKK-2246 | KELURAHAN_SIOLDENGAN | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SPK RETURN | 02.SPK returned | 02.SPK RETURNED | OUTCELL LABUHAN BATU (IMB TIDAK BISA TERBIT) | 09:02:22: SPK RETURN OUTCELL LABUHAN BATU, IMB TIDAK BISA TERBIT 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | SUM-SU-SRH-2249 |  |  |  | BP2022 | TB | 99°1.21.0'E | 3°19.15.2'N | 50 | 0/90/260 | 2022-2024 | COMMITMENT NEW ORDER B2S 2022-2024 |  | HTI | SUM-SU-SRH-2249 | KERAPUH | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Serdang Bedagai | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | CHANGE TO COLO DENGAN ID & SITE NAME SAMA 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-JT-BYL-0359 |  |  |  | BP2022 | TB | 110°30.0.0'E | 7°25.10.06'S | 50 | 60/150/270 | 2022-2024 | COMMITMENT NEW ORDER B2S 2022-2024 |  | EID | JAW-JT-BYL-0359 | BOYOLALI_AMPEL | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Boyolali | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | CHANGE TO COLO DENGAN ID & SITE NAME SAMA 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-JT-TMG-2675 |  |  |  | BP2022 | TB | 110°13.53.86'E | 7°21.38.31'S | 70 | 70/170/290 | 2022-2024 | COMMITMENT NEW ORDER B2S 2022-2024 |  | EID | JAW-JT-TMG-2675 | TEMANGGUNG_KRANGGAN | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Temanggung | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | CHANGE TO COLO DENGAN ID & SITE NAME SAMA 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | SUL-SN-PLP-1344 | 30733970031 |  |  | BP2022 | TB | 120°12.53.47'E | 3°5.7.52'S | 60 | 50/210/300 | 2022 | New site 2022 - P2 |  | HTI | SUL-SN-PLP-1344 | TIROMANDA_BUA | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Luwu | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | 11:02:22:SPK RETURN CHANGE TO COLO 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | SUL-SN-WNS-0979 | 30733980031 |  |  | BP2022 | TB | 119°58.54.03'E | 4°19.47.4'S | 60 | 40/150/240 | 2022 | New site 2022 - P2 |  | HTI | SUL-SN-WNS-0979 | KELURAHAN_UJUNG_LILIRILAU | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Soppeng | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | 11:02:22:SPK RETURN CHANGE TO COLO 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-BT-TGR-0111 | 30729370031 |  |  | BP2022 | TB | 106°34.55.21'E | 6°17.42.68'S | 40 | 0/90/200 | 2022-2024 | New site 2022 - P1 |  | EID | JAW-BT-TGR-0111 | STPI_PLP_KEMUNING | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Tangerang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL | 14:02:22: SPK RETURN BY XL DUE TO CHANGE DESIGN 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-JB-CKR-0126 | 30729400031 |  |  | BP2022 | TB | 107°9.3.05'E | 6°20.47.28'S | 40 | 0/90/180/270 | 2022 | New site 2022 - P2 |  | EID | JAW-JB-CKR-0126 | DAMAR_CIBATU | B2S | TBG | Jabodetabek | JABODETABEK | Jawa Barat | Kab. Bekasi | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL | 14:02:22: SPK RETURN BY XL DUE TO CHANGE DESIGN 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-BT-SRG-0056 | 30729510031 |  |  | BP2022 | TB | 106°19.54.84'E | 6°10.51.68'S | 30 | 20/140/285 | 2022 | New site 2022 - P2 |  | EID | JAW-BT-SRG-0056 | MODERN_NAMBO_ILIR | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Serang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL | 14:02:22: SPK RETURN BY XL DUE TO CHANGE DESIGN 13:02:22-04:02:22: CANDIDATE NOK, REHUNTING 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-JB-CKR-0120 | 30729620031 |  |  | BP2022 | TB | 107°10.29.06'E | 6°18.21.78'S | 30 | 10/170/270 | 2022 | New site 2022 - P2 |  | EID | JAW-JB-CKR-0120 | THAMRIN_JABABEKA | B2S | TBG | Jabodetabek | JABODETABEK | Jawa Barat | Kab. Bekasi | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL | 14:02:22: SPK RETURN BY XL DUE TO CHANGE DESIGN 13:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-BT-TGR-0096 | 30729290031 |  |  | BP2022 | TB | 106°33.55.08'E | 6°15.39.33'S | 40 | 30/180/325 | 2022 | New site 2022 - P1 |  | EID | JAW-BT-TGR-0096 | CURUG_WETAN | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Tangerang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL | 14:02:22: SPK RETURN BY XL DUE TO CHANGE DESIGN 13:02:22: IW OG 09:02:22-04:02:22: CANDIDATE OK 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-BT-SRG-0053 | 30729490031 |  |  | BP2022 | TB | 106°16.18.52'E | 6°9.26.13'S | 40 | 90/210/330 | 2022 | New site 2022 - P2 |  | EID | JAW-BT-SRG-0053 | KUSAMBI_CAWANG | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Serang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL | 14:02:22: SPK RETURN BY XL DUE TO CHANGE DESIGN 13:02:22: IW OG 09:02:22-04:02:22: CANDIDATE OK 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-BT-TGR-0120 | 30729330031 |  |  | BP2022 | TB | 106°40.51.99'E | 6°5.9.8'S | 30 | 90/220/350 | 2022 | New site 2022 - P2 |  | EID | JAW-BT-TGR-0120 | BELIMBING_CENGKLONG | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Tangerang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL | 14:02:22: SPK RETURN BY XL DUE TO CHANGE DESIGN 13:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-JK-GGP-0459 |  |  |  | BP2022 | TB | 106°44.50.49'E | 6°8.12.51'S | 30 | 10/100/170/250 | 2022-2024 | COMMITMENT NEW ORDER B2S 2022-2024 |  | EID | JAW-JK-GGP-0459 | KEBON_JAHE_KAPUK | B2S | TBG | Jabodetabek | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | SPK RETURN CHANGE TO COLO 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | KAL-KT-KLK-0704 | 30730160031 | 2107401003 | TAMBAN_LUAR_BATAGUH | BP2022 | TB | 114°22.19.2'E | 3°10.59.16'S | 65 | 65/150/250 | 2022-2024 | New site 2022 - P1 |  | HTI | KAL-KT-KLK-0704 | TAMBAN_LUAR_BATAGUH | B2S | TBG | Central | KALIMANTAN | Kalimantan Tengah | Kab. Kapuas | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 02.SPK returned | 02.SPK RETURNED | RETURN BY XL | 13:04:22: SITE RETURN BY XL DUE TO CELL PLAN ISSUE 10:04:22: REHUNTING 06:04:22-05:04:22: RNP NOK 03:04:22-24:03:22: VALIDASI RNP TNP 23:03:22-28:02:22: REHUNTING 23:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-BT-TGR-0110 |  |  |  | BP2022 | TB | 106°27.6.57'E | 6°14.34.97'S | 50 | 0/110/220 | 2022-2024 | COMMITMENT NEW ORDER B2S 2022-2024 |  | EID | JAW-BT-TGR-0110 | PETE_TEGAL_SARI | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Tangerang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | CHANGE TO COLO | SPK RETURN CHANGE TO COLO 06:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | SUL-SN-MLL-01572 | 30730250031 | 2817571003 | BAYONDO_TOMONI | BP2022 | TB | 120°48.54.31'E | 2°32.7.67'S | 60 | 0/180/270 | 2022 | New site 2022 - P2 |  | HTI | SUL-SN-MLL-01572 | BAYONDO_TOMONI | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Luwu Timur | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RETURN BY XL | 02.SPK returned | 02.SPK RETURNED | DROP BY XL RE-DESIGN | 23:03:22: SPK DROP BY XL DUE TO RE-DESIGN 23:03:22-14:03:22: REHUNTING 13:03:22: VALIDASI RNP TNP 12:03:22: REHUNTING 09:03:22: VALIDASI RNP TNP 06:03:22-28:02:22: VALIDASI RNP TNP -> REHUNTING 23:02:22-20:02:22: REHUNTING 16:02:22: IW OG 14:02:22-13:02:22: IW FAILED, UNDER RNP TNP REVIEW 09:02:22: IW OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
|  | SUM-SU-AKK-2206 | 30725580031 |  |  | BP2022 | TB | 99°50.35.38'E | 2°7.30.06'N | 60 | 90/180/270 | 2021 |  |  | HTI | SUM-SU-AKK-2206 | RANTAU_UTARA_PULOPADANG | B2S | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu | 6617944 | 2022-01-24 |  | 94 | 91 - 120 days | 2022-06-23 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SPK RETURN | 02.SPK returned | 02.SPK RETURNED | OUTCELL LABUHAN BATU (IMB TIDAK BISA TERBIT) | 09:02:22: SPK RETURN OUTCELL LABUHAN BATU, IMB TIDAK BISA TERBIT 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
|  | JAW-JB-BKS-0646 |  |  |  |  | TB | 106°57.55.01'E | 6°16.44.0'S | 35 | 40/170/250 | 2021 |  |  | EID | JAW-JB-BKS-0646 | SUBUR JATI ASIH RELOCATION | B2S | TBG | JABO | JABODETABEK | Jawa Barat | Kota Bekasi | 6617895 | 2021-12-22 |  | 127 | 121 - 150 days | 2022-05-21 | W21-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | SPK RETURN BY XL | 23:12:21: SPK RETURN BY XL DUE TO CHANGE PLAN 22:12:21: NEW SPK B2S
|  | KAL-KT-KLK-0698 |  | 210286109 | BATU KOTAM |  | SKP | 114°5.55.25'E | 1°6.10.73'S | 68 | 31/268 | 2021 |  |  | HTI | KAL-KT-KLK-0698 | REPEATER TUMBANG TUKUN | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Tengah | Kab. Kapuas | 6617882 | 2021-12-12 |  | 137 | 121 - 150 days | 2022-01-11 | W03-2022 | Jan-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2021-12-28 | [12 empty] | 02.SPK returned | 02.SPK RETURNED | PLN ISSUE (NO PLN) | 11:01:22: SPK RETURN BY XL 12:01:22-26:12:21: NEED REVIEW&APPROVAL POWER XL (ESKALASI BUDGET), ACTUAL TIDAK ADA PLN 22:12:21: NEED REVIEW TNP ALITA 19:12:21-12:12:21: NEW SPK, NEED REVIEW POWER HUAWEI
|  | JAW-JB-BDG-4084 |  | TBG06_WJ086 | SARIJADI |  | PMS | 107°34.27.16'E | 6°52.39.61'S | 38 | 70/190/280 | 2021 |  |  | HTI | JAW-JB-BDG-4084 | SARIMANIS | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kota Bandung | 6617811 | 2021-11-23 |  | 156 | > 150 days | 2021-12-23 | W52-2021 | Dec-2021 | 2021-10-08 | W41-2021 | Oct-2021 | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | CURRENTLY NO ISSUE | 24:11:21: SPK RETURN, HARDCOMCASE 24:11:21: ERM PROCESS
952 |  | SUL-ST-LWK-1069 | 30714650031 | 2604981003 | KINTOM_SAMADOYA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 122°39.39.78'E | 1°9.18.4'S | 60 | 20/220/300 | 2021 |  |  | HTI | SUL-ST-LWK-1069 | KINTOM_SAMADOYA | B2S | TBG | EAST | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617749 | 2021-10-25 |  | 185 | > 150 days | 2022-03-24 | W13-2022 | Mar-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | CURRENTLY NO ISSUE | 11:11:21: DROP BY XL, CHANGE PLAN XL (NEAR EXISTING) 10:11:21-07:11:21: CANDIDAT VERIFICATION OG 03:11:21-31:10:21: SURVEY OG, PLAN SUBMIT KANDIDAT W1 NOV
946 |  | SUL-ST-LWK-1082 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 122°49.9.42'E | 0°56.4.78'S | 60 | 70/180/260 | 2021 |  |  | HTI | SUL-ST-LWK-1082 | LUWUK_KILONGAN_PERMAI | B2S | TBG | EAST | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617749 | 2021-10-25 |  | 185 | > 150 days | 2022-03-24 | W13-2022 | Mar-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | CURRENTLY NO ISSUE | 24:11:21: SPK COLO PENGGANTI, CHANGE TO SITE ID TP 260093104 21:11:21-10:11:21-03:11:21: CHANGE PLAN PROPOSE TO COLO 31:10:21: SURVEY OG, PLAN SUBMIT KANDIDAT W 1 NOV
937 |  | NUS-NB-DPU-5103 | 30714520031 | 1806871003 | TAMBORA AXL | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 117°48.33.12'E | 8°11.9.53'S | 50 | 60/160/270 | 2021 | BLITZKRIEG 2021 [NEW] |  | ALT | NUS-NB-DPU-5103 | TAMBORA AXL | B2S | TBG | EAST | BALINUSRA | Nusa Tenggara Barat | Kab. Dompu | 6617733 | 2021-10-21 |  | 189 | > 150 days | 2022-03-20 | W13-2022 | Mar-2022 | TBD | TBD | TBD | 2022-03-20 | W13-2022 | Mar-2022 | 2022-03-20 | W13-2022 | Mar-2022 | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | ISSUE PERMIT | 20:12:21: SPK RETURN OLEH XL KARENA KENDALA PERIZINAN KOMINFO 19:12:21-01:12:21: NEED ARAHAN XL PERGESERAN NOM, KARENA KENDALA PERIZINAN KOMINFO (COVERAGE GESER 4KM DARI EXISTING) 28:11:21: WAIT ARAHAN XL TERKAIT KENDALA PERIZINAN KOMINFO (COVERAGE GESER 4KM DARI EXISTING) 24:11:21: RNP TNP OK, TERKENDALA PERIZINAN KOMINFO PLAN PEMBANGUNAN TOWER BAKTI (UNDER KOMINFO) SEJAK 2018, COVERAGE GESER 4KM DARI EXISTING 21:11:21: Under review TNP 17:11:21-10:11:21: UNDER REVIEW RNP&TNP 07:11:21-03:11:21: OG ESR UPLOAD 7 NOV, PARALEL VERIF KANDIDAT 8 NOV 31:10:21: SURVEY DONE, PLAN SUBMIT CANDIDAT 1 NOV 2021 27:10:21 - 24:10:21: NEW SPK NEW BUILT, HUNTING PROSES, PLAN SUBMIT KANDIDAT 4 NOV 2021
940.2 |  | SUM-RI-PBR-1164 | 30714540031 | 0416231003 | RUMBAI_PESISIR_LEMBAHDAMAI | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 101°26.0.6'E | 0°35.28.35'N | 50 | 90/180/300 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | SUM-RI-PBR-1164 | RUMBAI_PESISIR_LEMBAHdAMAI | B2S | TBG | WEST | SUMBAGTENG | Riau | Kota Pekanbaru | 6617734 | 2021-10-21 |  | 189 | > 150 days | 2022-03-20 | W13-2022 | Mar-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 02.SPK returned | 02.SPK RETURNED | LAHAN CORPORATE | SPK RETURN 21:02:22: ARAHAN XL PRPOSED RETURN KARENA SUDAH TIDAK BISA KELUAR NOM PERTAMINA KARENA SUDAH DIKELILINGI TOWER XL 20:02:22-02:02:22: ARAHAN XL PRPOSED RETURN KARENA SUDAH TIDAK BISA KELUAR NOM PERTAMINA KARENA SUDAH DIKELILINGI TOWER XL 26:01:22-15:12:21: SUDAH TIDAK TERDAPAT LAHAN UNTUK ROOFTOP & POLE PADA RADIUS NOM, ON PROCESS CONFIRM XL 12:12:21-08:12:21: OG SURVEY LAHAN UNTUK ROOFTOP/POLE, XL REJECT PERGESERAN NOM KARENA SUDAH DIKELILINGI TOWER XL 05:12:21-01:12:21: NEED APPROVAL PERGESERAN NOM, KARENA PERTAMINA MENOLAK KERJASAMA SEWA LAHAN PEMBANGUNAN TOWER 28:11:21-14:11:21: PROCESS FU KE PERTAMINA TRKAIT SURAT KERJASAMA, TARGET RELEASED 29 NOV, TERKENDALA PERUBAHAN RE-STRUKTURISASI PT CPI KE PT PERTAMINA HULU ROKAN, SIRCULAR PKS OG INTERNAL PERTAMINA 10:11:21-31:10:21: SITE BERADA DI LAHAN PERTAMINA, SUDAH MENGAJUKAN SURAT TERKAIT KERJASAMA DENGAN PERTAMINA, MENUNGGU SURAT JAWABAN DARI PERTAMINA, PLAN JAWABAN RELEASED 7 NOV 24:10:21: NEW SPK NEW BUILT, HUNTING PROSES, PLAN SUBMIT KANDIDAT 4 NOV 2021
932 |  | KAL-KS-BJM-0976 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 114°38.0.06'E | 3°19.44.93'S | 40 | 15/80/235 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | KAL-KS-BJM-0976 | BANJARMASIN_TIMUR | COLO | TBG | Central | KALIMANTAN | Kalimantan Selatan | Kota Banjarmasin | 6617642 | 2021-09-23 |  | 217 | > 150 days | 2021-10-23 | W43-2021 | Oct-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | HARD COMMCASE | 17:10:21-06:10:21-26:09:21: SPK NEW RELEASED, ERM PROSES
653 |  | JAW-JI-SBY-4434 | 30705920031 | 1654021003 | BUKIT PAKIS SURABAYA RELOCATION | RELOCATION | TB | 112°42.26.5'E | 7°17.49.3'S | 25 | 100/220/340 | 2021 | RELOCATION |  | HTI | JAW-JI-SBY-4434 | BUKIT PAKIS SURABAYA RELOCATION | B2S | TBG | East | JATIM | Jawa Timur | Kota Surabaya | 6617613 | 2021-09-08 |  | 232 | > 150 days | 2022-02-05 | W06-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | CURRENTLY NO ISSUE | 28:10:21: SPK RETURN BY XL CHANGE PLAN 27:10:21: cand B, proses validasi , blm dI review sm Planing XL, issue nya ada redesign planing 23:10:21: KANDIDAT FAIL LEGAL LAHAN, REHUNTING OG, PLAN SUBMIT VALIDASI 26 OCT 21 20:10:21-17:10:21: FINALISASI TERKAIT MASALAH SEWA LAHAN, PEMILIK LAHAN MEMINTA SESUAI DENGAN EXISTING PLAN CLEAR 24 OKTOBER 13:10:21: 06:10:21-29:09:21: UNDER REVIEW TIM LM XL, TERKAIT REGULASI TINGGI TOWER SESUAI DENGAN PERDA DAERAH SETEMPAT 26:09:21 - 22:09:21: SUBMIT KANDIDAT DONE, UNDER REVIEW RNP 19:09:21: 15:09:21: 13:09:21: HUNTING OG, PLAN SUBMIT KANDIDAT 17 SEP
538 |  | JAW-JB-DPK-0495 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 106°46.24.85'E | 6°21.47.02'S | 45 | 90/210/330 | 2021 | RELOCATION | Jl. Limo Poncol, Kel. Limo RT.02 RW.02, Kec. Limo, Kota Depok Prov. Jawa Barat | HTI | JAW-JB-DPK-0495 | RAYA LIMO RELOCATION | COLO | TBG | JABO | JABAR | Jawa Barat | Kota Depok | 6617539 | 2021-08-25 |  | 246 | > 150 days | 2021-09-24 | W39-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | DROP BY TBG TOWER RELOCATE | 08:30:2021: NEED REVIEW RND EID 08:25:2021: SPK COLO RELEASED, SUBMIT ERM PROSES
537 |  | JAW-JB-CKR-0090 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 107°11.5.68'E | 6°19.18.59'S | 42 | 80/200/320 | 2021 |  | Kel. Sertajaya Kp. Bugelsalam RT.001 RW.003, Kec. Cikarang Timur, Kab. Bekasi Prov. Jawa Barat | EID | JAW-JB-CKR-0090 | JALAN TEGAL DANAS | COLO | TBG | JABO | JABAR | Jawa Barat | Kab. Bekasi | 6617497 | 2021-08-13 |  | 258 | > 150 days | 2021-09-12 | W38-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | SPK RECALL (Tower Guyed Mast. Plan permanenisasi max 20m, terlalu rendah.) | 22:08:21: NEED REVIEW RNP EID 18:08:21: ERM PROSES, NEED REVIEW RNP HTI, OUTCELL 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
519 |  | JAW-JK-KSU-1132 | 30696360031 | 1134551003 | PULAU BIDADARI | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 106°44.48.41'E | 6°2.8.12'S | 40 | 120/210/300 | 2021 |  |  | EID | JAW-JK-KSU-1132 | PULAU BIDADARI | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | Kab. Adm. Kep. Seribu | 6617480 | 2021-08-12 |  | 259 | > 150 days | 2022-01-09 | W03-2022 | Jan-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 09:01:2021: SPK RETURN KARENA ISSUE PERUBAHAN DESIGN RND 08:25:2021: SURVEY OG, KORDINASI TERKAIT PENYEWAAN GENSET KEPADA PIHAK PT MARINA ANCOL, APAKAH BISA PROVIDE HYBRID POWER SYSTEM 08:22:2021: 08:18:2021: HUNTING OG
516 |  | JAW-JT-SKT-2148 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 110°49.47.41'E | 7°32.47.96'S | 35 | 30/200/300 | 2021 |  |  | EID | JAW-JT-SKT-2148 | KADIPIRO BANJARSARI | B2S | TBG | CENTRAL | JATENG | Jawa Tengah | Kota Surakarta | 6617448 | 2021-08-09 |  | 262 | > 150 days | 2022-01-06 | W02-2022 | Jan-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 08:10:2021 : SPK RETURN BY XL PERUBAHAN DESIGN 08:09:2021 : SPK NEW BUILD RELEASED
539 |  | JAW-JI-JBG-4170 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 112°19.23.2'E | 7°38.7.69'S | 50 | 10/180/280 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Sumberboto, Dsn. Mojoduwur RT 01 – RW 01,Ds. Mojoduwur, Kec. Mojowarno | HTI | JAW-JI-JBG-4170 | MOJOWARNO MOJODUWUR | COLO | TBG | East | JATIM | Jawa Timur | Kab. Jombang | 6617454 | 2021-08-09 |  | 262 | > 150 days | 2021-09-08 | W37-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | DROP BY XL, RND NOK XL EXISTED | 08:30:2021:08:22:2021: 08:18:2021: NEED REVIEW RNP HUWAWEI, ERM PROSES 08:16:2021: 08:09:2021 : SPK COLO RELEASED, ERM PROSES
517 |  | JAW-JT-TGL-2614 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 109°10.14.38'E | 6°58.46.13'S | 50 | 30/85/200/285 | 2021 |  |  | EID | JAW-JT-TGL-2614 | PANGKAH TONGGARA | B2S | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Tegal | 6617448 | 2021-08-09 |  | 262 | > 150 days | 2022-01-06 | W02-2022 | Jan-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 08:10:2021 : SPK RETURN BY XL PERUBAHAN DESIGN 08:09:2021 : SPK NEW BUILD RELEASED
518 |  | JAW-JT-TGL-2608 | 30697670031 | 1447531003 | TUBUN PAKEMBARAN | ACTIVE - BLITZKRIEG 2021 [NEW] | PKP | 109°8.5.21'E | 6°59.4.31'S | 35 | 80/155/270/350 | 2021 |  |  | EID | JAW-JT-TGL-2608 | TUBUN PAKEMBARAN | B2S | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Tegal | 6617448 | 2021-08-09 |  | 262 | > 150 days | 2022-01-06 | W02-2022 | Jan-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 08:10:2021 : SPK RETURN BY XL PERUBAHAN DESIGN 08:09:2021 : SPK NEW BUILD RELEASED
554 |  | NUS-NT-SOE-0356 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 124°23.6.32'E | 10°7.54.41'S | 50.00.00 | 30/160/250 | 2021 |  | Dusun II Desa Keufatu, Raya Kualin-Kolbano,Rt.12/Rw.06, Kec. Kualin, Kab. Timur Tengah Selatan Prov. Nusa Tengara Timur | ALT | NUS-NT-SOE-0356 | KUALIN | COLO | TBG | East | BALINUSRA | Nusa Tenggara Timur | Kab Timor Tengah Selatan | 6617409 | 2021-08-03 |  | 268 | > 150 days | 2021-09-02 | W36-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | DROP BY XL ISSUE RND NOK CHANGE DESIGN | 09:06:2021: DROP BY XL ISSUE CHANGE DESIGN RND NOK : CHANGE DESIGN 08:22:2021: 08:16:2021: 08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES
536 |  | JAW-JB-TSM-4183 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 108°11.24.22'E | 7°20.23.96'S | 40.00.00 | 80/150/300 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Kenanga (Perumahan Situ Gede), Kel. Linggajaya RT.002 RW.001 Kec. Mangkubumi, Kota Tasikmalaya Prov. Jawa Barat | HTI | JAW-JB-TSM-4183 | MANGKUBUMI_ALMERIA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kota Tasikmalaya | 6617407 | 2021-08-03 |  | 268 | > 150 days | 2021-09-02 | W36-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | DROP BY TBG TOWER DISMANTLE | 08:22:2021: 08:16:2021: 08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES
557 |  | KAL-KT-KLP-0489 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 112°11.15.36'E | 2°3.0.86'S | 60.00.00 | 10/120/210 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Desa Sukamandang Kec. Seruyan tengah kab. Seruyan, Kalteng | HTI | KAL-KT-KLP-0489 | SERUYAN_TENGAH_SUKAMANDANG | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Tengah | Kab. Seruyan | 6617407 | 2021-08-03 |  | 268 | > 150 days | 2021-09-02 | W36-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | TNP NOK : SITE NOT LOS | 06:09:21: ERM REJECTION, TNP NOK, SITE NOT LOS 30:08:21:22:08:21: 16:08:21: 16:08:21: 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
555 |  | NUS-NT-SOE-0357 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 124°13.16.28'E | 9°55.22.87'S | 50.00.00 | 0/90/270 | 2021 |  | Desa Hane RT002 RW001, Kec. Batu Putih, Kab. Timur Tengah Selatan Prov. Nusa Tengara Timur | ALT | NUS-NT-SOE-0357 | SOETIGA | COLO | TBG | East | BALINUSRA | Nusa Tenggara Timur | Kab Timor Tengah Selatan | 6617409 | 2021-08-03 |  | 268 | > 150 days | 2021-09-02 | W36-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | DROP BY XL ISSUE RND NOK CHANGE DESIGN | 09:06:2021: DROP BY XL ISSUE CHANGE DESIGN RND NOK : CHANGE DESIGN 08:22:2021: 08:16:2021: 08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES
553 |  | NUS-NT-KPG-0297 |  |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 123°36.22.46'E | 10°2.26.52'S | 50.00.00 | 40/190/340 | 2021 |  | Kel. Sulamu Rt.007 Rw.003, Kec. Sulamu, Kab. Kupang Prov. Nusa Tengara Timur | ALT | NUS-NT-KPG-0297 | SULAMU | COLO | TBG | East | BALINUSRA | Nusa Tenggara Timur | Kab. Kupang | 6617409 | 2021-08-03 |  | 268 | > 150 days | 2021-09-02 | W36-2021 | Sep-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | DROP BY XL ISSUE RND NOK CHANGE DESIGN | 09:06:2021: DROP BY XL ISSUE CHANGE DESIGN RND NOK : CHANGE DESIGN 08:22:2021: 08:16:2021: 08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES
511 |  | SUL-SN-SGM-1259 | 30600260031 | 2811111003 | LEMBANGPARANG | ACTIVE - BLITZKRIEG | PKP | E°24.42.84'E | S°14.48.84'S | 40 | 90/210/330 | 2021 | JEDI 2020 [NEW] |  | HTI | SUL-SN-SGM-1259 | TINGGIMAE_BAROMBONG | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Gowa | 6617124 | 2021-03-22 |  | 402 | > 150 days | 2021-04-21 | W17-2021 | Apr-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 03.05.21 : SPK return by XL
505 |  | JAW-JB-CBI-0120 | 30681660031 | 1268142003 | IBS GUNUNG SINDUR | ACTIVE - BLITZKRIEG | TB | E°39.31.5'E | S°23.4.24'S | 35 | 60/240/350 | 2021 |  | Desa Gunung Sindur Kp. Gunung Sindur RT.003 RW.010, Kec. Gunung Sindur, Kab. Bogor Prov. Jawa Barat | EID | JAW-JB-CBI-0120 | BOGOR RUMPIN SUKAMULYA | COLO | TBG | JABO |  | Jawa Barat | Kab. Bogor | 6617048 | 2021-03-18 |  | 406 | > 150 days | 2021-04-17 | W16-2021 | Apr-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  |  |  | 1268142003 | [10 empty] | 02.SPK returned | 02.SPK RETURNED |  | 03.05.21 : SPK return by XL
510 |  | JAW-JB-CKR-0041 |  |  |  | ACTIVE - BLITZKRIEG |  | E°4.48.58'E | S°19.19.06'S | 30 | 10/200/270 | 2021 |  |  | EID | JAW-JB-CKR-0041 | Gandamekar Cikarang | COLO | TBG | JABO |  | Jawa Barat | Kab. Bekasi | 6616881 | 2021-03-18 |  | 406 | > 150 days | 2021-04-17 | W16-2021 | Apr-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 03.05.21 : SPK return by XL
507 |  | KAL-KB-BEK-0750 |  |  |  | ACTIVE - BLITZKRIEG |  | E°30.54.04'E | N°58.31.59'N | 60 | 50/250/350 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | KAL-KB-BEK-0750 | LUMAR_LAMOLDA | COLO | TBG | JABO |  | Kalimantan Barat | Kab. Bengkayang | 6616738 | 2021-03-18 |  | 406 | > 150 days | 2021-04-17 | W16-2021 | Apr-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 03.05.21 : SPK return by XL
509 |  | SUM-SS-PKB-1250 |  |  |  | ACTIVE - BLITZKRIEG |  | E°4.17.83'E | S°41.54.24'S | 60 | 30/90/250 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | SUM-SS-PKB-1250 | MARGO_MULYO_20 | COLO | TBG | West |  | Sumatera Selatan | Kab. Banyuasin | 6616829 | 2021-03-18 |  | 406 | > 150 days | 2021-04-17 | W16-2021 | Apr-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 03.05.21 : SPK return by XL
821 |  | JAW-JB-BDG-4200 | 30615190031 | 1263811003 | PAMEKAR RAYA PANGHEGAR PERMAI RELOCATION | SPK RETURN | TB | 107°41.50.93'E | 6°55.43.94'S | 30 | 90/210/330 |  | RELOCATION |  | HTI | JAW-JB-BDG-4200 | PAMEKAR RAYA PANGHEGAR PERMAI RELOCATION | B2S | TBG | CENTRAL | JABAR | Jawa Barat | Kota Bandung | 6616554 | 2020-12-07 |  | 507 | > 150 days | 2021-05-06 | W19-2021 | May-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 21.12.20 : SPK drop by TBG, remarks Hard Candidate Kota Bandung tinggi tower maksimal 20m (email Pak Rudi 21 Oct) 21.12.20 : survey og 07.12.20 : SPK release
879 |  | JAW-JT-SLT-2140 | 30617710031 | 1437151003 | KALICACING SALATIGA | SPK RETURN BY XL | TB | 110°30.0.44'E | 7°19.50.05'S | 40 | 0/100/180/290 |  |  |  | EID | JAW-JT-SLT-2140 | Kalicacing Salatiga | B2S | TBG | CENTRAL | JATENG | Jawa Tengah | Kota Salatiga | 6616538 | 2020-12-03 |  | 511 | > 150 days | 2021-05-02 | W19-2021 | May-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [13 empty] | 02.SPK returned | 02.SPK RETURNED | Perda Issue (Ketinggian Menara) | 26.02.21 : SPK return by XL remark Re-design (email 25-Feb-21) 22.02.21 : propose joint survey RND 18.02.21 : rekomendasi ketinggian dari diskominfo max 21 m, kand F IW CLEAR -> RND NOK 01.02.21 : IW OG, isu perda ketinggian menara max 20m 28.01.21 : kand D failed, IW OG kandidat E 21.01.21 : IW minus 2KK, plan IW clear minggu ini 18.01.21 : 14.01.21 : 07.01.21 : kand D RF TX OK, IW ongoing 04.01.21 : under RNP review 28.12.20 : hunting candidate A 21.12.20 : survey og 03.12.20 : SPK release
878 |  | KAL-KS-BJM-0872 | 30617660031 | 2208431003 | SUNGAI LULUT_TENGAH | SPK RETURN BY XL | TB | 114°38.21.82'null | 3°19.34.69'S | 40 | 90/200/280 | 2020 | JEDI 2020 [NEW] | Jl. Sungai Lulut Dalam, Kel. Sungai Lulut Rt.008 Rw.001, Kec. Banjarmasin Timur, Kota Banjarmasin Prov. Kalimantan Selatan | HTI | KAL-KS-BJM-0872 | SUNGAI LULUT_TENGAH | B2S | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | Kota Banjarmasin | 6616535 | 2020-12-02 |  | 512 | > 150 days | 2021-05-01 | W18-2021 | May-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | SPK return by XL | 05.04.21 : SRFI 29.03.21 : 23.03.21 : erection ongoing 18.03.21 : pouring OG 15.03.21 : cerucuk pondasi done, plan cor 16 Mar, issue SPK return by XL 08.03.21 : bouwplank, CME preparation 01.03.21 : plan CME start 4 Maret 25.02.21 : rekom camat done, APD OG, plan CME start W1 Mar 22.02.21 : 18.02.21 : plan rekom camat done 20Feb 15.02.21 : rekom lurah done, rekom camat estimasi penyelesaian W4 Feb 08.02.21 : IW clear, rekom OG plan finisih W2 Feb 28.01.21 : plan IW clear W2 Feb 21.01.21 : IW minus 1 warga, lokasi site terdampak banjir Kalsel 14.01.21 : 11.01.21 : 04.01.21 : 28.12.20 : 21.12.20 : 17.12.20 : kand B OK, IW ongoing
917 |  | JAW-JB-CMS-3993 |  |  |  | SPK RETURN BY XL |  | 108°22.33.2'E | 7°5.32.06'S | 60 | 90/210/330 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JB-CMS-3993 | CISAYONG_TASIK_RELOCATION | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Ciamis | 6616398 | 2020-11-19 |  | 525 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 26.11.20 : SPK return by XL remark perubahan desain (email 25 November) 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
916 |  | JAW-JI-SBY-4373-RETURN |  |  |  | SPK RETURN BY XL |  | 112°44.37.07'E | 7°19.6.82'S | 34 | 90/210/330 |  |  |  |  | JAW-JI-SBY-4373-RETURN | JEMURWONOSARI_RELOCATION | COLO |  | East | JATIM | Jawa Timur | Kota Surabaya | 6616398 | 2020-11-19 |  | 525 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 19.11.20 : SPK return, remarks perubahan desain RND 13.11.20 : SPK release
918 |  | JAW-JB-CMH-3992 |  |  |  | SPK RETURN BY XL |  | 107°31.42.89'E | 6°52.28.34'S | 26 | 90/210/330 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JB-CMH-3992 | PANEMBAKAN_UTARA_BANDUNG_RELOCATION | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kota Cimahi | 6616398 | 2020-11-19 |  | 525 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 26.11.20 : SPK return by XL remark perubahan desain (email 25 November( 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
915 |  | JAW-BT-CPT-0454 |  |  |  | SPK RETURN BY XL |  | 106°42.24.91'E | 6°17.46.03'S | 25 | 90/210/330 |  |  |  | EID | JAW-BT-CPT-0454 | Sumatra Dalam Ciputat | COLO |  | JABO | JABODETABEK (OUTER) | Banten | Kota Tangerang Selatan | 6616458 | 2020-11-13 |  | 531 | > 150 days | 2020-12-13 | W51-2020 | Dec-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 19.11.20 : SPK return, remarks perubahan desain RND 13.11.20 : SPK release
818 |  | KAL-KS-PLI-0931-RETURN |  |  |  | SPK RETURN |  | 115°1.35.78'null | 3°41.26.07'S | 72 | 90/210/330 |  |  |  | HTI | KAL-KS-PLI-0931-RETURN | SIMPANG EMPAT JORONG | B2S | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | Kab. Tanah Laut | 6616297 | 2020-10-02 |  | 573 | > 150 days | 2021-03-01 | W10-2021 | Mar-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | Hard Candidate | 22.10.20 : 19.10.20 : propose return 15.10.20 : NOM berada di puncak bukit konservasi, not recommended. titik terdekat yang possible diakuisisi sedang dimintakan akses masuk ke PT. GMK + 15 KM dari NOM 12.10.20 : 08.10.20 : Hunting, NOM berada di kawasan hutan 05.10.20 : assessment & prepare hunting 02.10.20 : SPK B2S release
877 |  | JAW-JK-TJP-0621 | 30572280031 | 1127821003 | DUFAN MARINA | SPK RETURN BY XL | TB | 106°49.49.39'E | 6°7.31.13'S | 30 | 50/140/300 |  |  |  | EID | JAW-JK-TJP-0621 | DUFAN MARINA | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6616288 | 2020-10-01 |  | 574 | > 150 days | 2021-02-28 | W10-2021 | Feb-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | Hard Candidate | 19.04.21 : SPK return by XL email by Pak David EID, ESR LMS has been deleted 04.03.21 : MoM 04/3, SPK propossed return by XL 04.03.21 : IW failed, rehunting 22.02.21 : 18.02.21 : plan IW clear 25 Feb, kandidat rooftop 11.02.21 : kand C proses perijinan pengecekan zonasi menara, estimasi 2 minggu (18 Feb) 08.02.21 : kand C RND OK, proses negosiasi dgn LL 28.01.21 : plan submit kandidat 30 Jan 21.01.21 : 18.01.21 : 14.01.21 : kandidat failed, proses negosiasi kandidat ruko 90m dari NOM (area discovery Ancol) 07.01.21 : 10.12.20 : isu blocking ketua RT/RW 07.12.20 : 03.12.20 : kembali ke kand yang pernah approved, proses IW ongoing 19.11.20 : 16.11.20 : proses follow up dinas PU terkait penggunaan lahan fasum 12.11.20 : 09.11.20 : 05.11.20 : rehunting 01.10.20 : SPK reaktivasi release
914 |  | JAW-JI-SMP-4277-RETURN |  |  |  | SPK RETURN BY XL |  | 114°24.58.14'null | 5°34.5.2'S | 50 | 90/210/330 |  |  |  | HTI | JAW-JI-SMP-4277-RETURN | MASALEMBU SUKAJERUK | COLO | TBG | EAST | JATIM | Jawa Timur | Kab. Sumenep | 6616271 | 2020-09-25 |  | 580 | > 150 days | 2020-10-25 | W44-2020 | Oct-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 02.11.20 : return by XL 26.10.20 : 22.10.20 : prepare dok STO 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : waiting review TNP ALITA 01.10.20 : ERM process
913 |  | SUM-JA-MBN-0482 (RETURN REVISI COMMITMENT SPK) |  |  |  | SPK RETURN BY XL |  | 102°59.52.73'null | 1°52.47.1'S | 50 | 90/210/330 |  |  |  | HTI | SUM-JA-MBN-0482 (RETURN REVISI COMMITMENT SPK) | DURIAN LUNCUK | COLO | TBG | WEST | SUMBAGSEL | Jambi | Kab. Batanghari | 6616141 | 2020-08-28 |  | 608 | > 150 days | 2020-09-27 | W40-2020 | Sep-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED
817 |  | JAW-JK-TJP-0640 | 30600240031 | 1129131003 | KALIBARU CILINCING | SPK RETURN | PKP | 106°55.42.55'null | 6°6.3.2'S | 21 | 0/140/280 |  |  |  | EID | JAW-JK-TJP-0640 | Kalibaru Cilincing | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | Kota Adm. Jakarta Utara | 6616138 | 2020-08-28 |  | 608 | > 150 days | 2021-01-25 | W05-2021 | Jan-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | Hard Candidate | 21.01.21 : email pengembalian SPK dari PKP (18-Jan-21) remarks OVER DURASI 14.01.21 : 17.12.20 : hunting kandidat 07.12.20 : target penyelesaian 14 Dec 26.11.20 : proses perubahan STIP (reloc to PKP) 19.11.20 : 24.09.20 : 21.09.20 : 14.09.20 : 10.09.20 : 07.09.20 : Hunting
816 |  | JAW-JK-TJP-0640 (RETURN PERUBAHAN COMMITMENT SPK) |  |  |  | SPK RETURN |  | 0°0.0.0'null | 0°0.0.0'null |  | 0/140/280 |  |  |  | EID | JAW-JK-TJP-0640 (RETURN PERUBAHAN COMMITMENT SPK) | Kalibaru Cilincing | B2S | TBG | JABO |  | DKI Jakarta | Kota Adm. Jakarta Utara | 6616089 | 2020-08-26 |  | 610 | > 150 days | 2021-01-23 | W04-2021 | Jan-2021 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED
824 |  | JAW-BT-TNG-2111-RETURN |  |  |  | SPK RETURN - CME by XL (RELOCATION) |  | 106°38.38.08'null | 6°10.16.68'S | 18 | 0/90/180/270 |  |  |  | EID | JAW-BT-TNG-2111-RETURN | SHOAIB ABDUL AZIZ Relocation | COLO |  | JABO |  | Banten | Kota Tangerang | 6615567 | 2020-08-18 |  | 618 | > 150 days | 2020-09-17 | W38-2020 | Sep-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 07.09.20 : Hunting
823 |  | JAW-JI-KNR-4253-RETURN |  |  |  | SPK RETURN - CME by XL (RELOCATION) |  | 112.2222 | -8.1467 | 41 | 0/60/300 |  |  |  | HTI | JAW-JI-KNR-4253-RETURN | KANIGORO_SATREYAN | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. BLITAR | 6614897 | 2020-07-15 |  | 652 | > 150 days | 2020-08-14 | W33-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 18.09.20 : CME BY XL, lacking PO CME, PO PLN released, plan RFI 29 oct 20
876 |  | JAW-JI-KNR-4253-RETURN |  |  |  | SPK RETURN - CME by XL (RELOCATION) |  | 112.2222 | -8.1467 | 50 | 0/60/300 |  |  |  | HTI | JAW-JI-KNR-4253-RETURN | KANIGORO_SATREYAN | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. BLITAR | 6614889 | 2020-07-14 |  | 653 | > 150 days | 2020-12-11 | W50-2020 | Dec-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 15.07.20 : propose colo to site 164105107 SATREYAN KANIGORO yang hanya berjarak 6m dari existing site TBG, RND OK CHANGE TO COLO, SPK return by TBG and waiting SPK COLO
822 |  | JAW-JI-KPN-4378-RETURN |  |  |  | SPK RETURN - CME by XL (RELOCATION) |  | 112.5712 | -7.8721 | 48 | 90/210/330 |  | RELOCATION |  | HTI | JAW-JI-KPN-4378-RETURN | TAWANG ARGO RELOCATION | COLO | TBG | EAST | JATIM | Jawa Timur | Malang | 6614896 | 2020-07-14 |  | 653 | > 150 days | 2020-08-13 | W33-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 30.07.20 : under review RND HTI
910 |  | SUM-SS-PKB-1241 |  |  |  | SPK RETURN BY XL |  | 105.0577 | -2.6086 | 50 | 15/180/290 |  |  |  | HTI | SUM-SS-PKB-1241 | DAMAR WULAN | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | BANYUASIN | 6614850 | 2020-07-06 |  | 661 | > 150 days | 2020-08-05 | W32-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 26.08.20 : email return by system, Return by XL, ANTENNA HEIGHT TOO LOW 17.07.20 : ERM DROP BT XL, antenna too low 06.07.20 : SPK release
911 |  | JAW-JI-SMP-4277-RETURN |  |  |  | SPK RETURN BY XL |  | 114.4162 | -5.5682 | 50 | 160/250/310 |  |  |  | HTI | JAW-JI-SMP-4277-RETURN | MASALEMBU SUKAJERUK | COLO | TBG | EAST | JATIM | Jawa Timur | Sumenep | 6614848 | 2020-07-06 |  | 661 | > 150 days | 2020-08-05 | W32-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 07.08.20 : email RETURN BY XL karena SITE ISOLATED ( REPEATER NOT READY) 06.08.20 : 03.08.20 : 30.07.20 : 23.07.20 : 13.07.20 : 09.07.20 : 02.07.20 : under review TNP ALITA 29.06.20 : ERM on going 23.06.20 : SPK Release 23 jun 20
856 |  | KAL-KI-SMR-0770 | 30595670031 | 2314731003 | SEMPAJA_SAMARINDA UTARA | SPK RETURN BY XL | TB | 117.1649 | -0.44505 | 35 | 30/150/300 | 2020 | JEDI 2020 [NEW] | Jl.PM.Noor Kel.Sempaja Selatan Kec. Samarinda Utara Kota Samarinda Prov. Kalimantan Timur | HTI | KAL-KI-SMR-0770 | SEMPAJA_SAMARINDA UTARA | B2S | TBG | JABO | KALIMANTAN | Kalimantan Timur | KOTA SAMARINDA | 6614816 | 2020-07-01 |  | 666 | > 150 days | 2020-11-28 | W48-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [13 empty] | 02.SPK returned | 02.SPK RETURNED | Hard Candidate | 11.02.21 : Hard candidate, high aging, Return by XL 11.02.21 : arahan rehunting 117.164177°, -0.443963° di lahan developer (tidak disewakan) 14.01.21 : note -> target RFC Feb, target RFI akhir Mar 2021 16.11.20 : rehunting, submit kand B inSAR NOK karena sectoral blocking 09.11.20 : 05.11.20 : negosiasi dengan pihak developer gagal. Plan 7 Nov koordinasi dengan UPTD dinas perikanan terkait sewa lahan 02.11.20 : 29.10.20 : 26.10.20 : kembali ke kandidat A (belum ada jawaban dari dinas Perikanan terkait pengajuan kerjasama), dirut developer OK, proses negosiasi sewa lahan dengan owner 22.10.20 : 19.10.20 : 15.10.20 : 12.10.20 : menunggu feedback surat pengajuan kerja sama (untuk survey) dengan dinas perikanan 08.10.20 : 05.10.20 : 01.10.20 : proses rehunting di lahan Dinas Pertanian (kemungkinan outSAR karena di luar lahan developer PT Sarindo), prepare submit kandidat 28.09.20 : 24.09.20 : RND not ok denagn kedua kand tersebut karena dekat existing XL dan target coverage tidak bisa di dapatkan 22.09.20 : Terdapat 2 existing TBG di dekat NOM yaitu Bumi_Sempaja2 (belum ada tenant XL, SST 42m, jarak 761m) dan SENGKOTEK_1, MCP 18m jarak 600.34m, propose colo ke existing TBG rejected by planning XL 21.09.20 : IW on going 14.09.20 : 07.09.20 : isu high price sewa lahan, dari sisi planning XL tidak bisa perluasan SAR atau reNOM karena dekat existing XL 03.09.20 : plan hari ini surat jawabn dari PT.Sarindo akan diterima 31.08.20 : 27.08.20 : 24.08.20 : menunggu feedbak/jawaban dr PT.Sarindo menegnai pengajuan harga yg diberikan TBG 17.08.20 : 13.08.20 : proses negosiasi harga sewa dgn PT Sarindo (memaksimalkan kandidat A) 13.08.20 : 06.08.20 : menunggu konfirmasi terkait sewa lahan dr PT Sarindo (Kamis 6 Jul), arahan Pak Felix SPK direturn terlebih dahulu karena NOM dekat dengan existing XL 03.08.20 : 30.07.20 : Need arahan hunting karena kandidat A terkendala proses negosiasi harga dgn PT Sarindo (memakan waktu lama) dan lokasi NOM berada di lahan developer + dekat exisiting tower TBG 23.07.20 : kandidat A TNP approved dgn MW 41m dan dia 0.6m, menunggu surat balasan PT. Sarindo untuk melanjutkan proses IW 20.07.20 : kandidat A koordinat 117.165472, -0.443583 propose SST 42 waiting RNP review 16.07.20 : rehunting karena beberapa kand yang didapat, LL nya menolak di sewakan. 13.07.20 : 09.07.20 : hunting 01.07.20 : SPK release
874 |  | KAL-KS-BJM-0928-RETURN |  |  |  | SPK RETURN BY XL |  | 114.6066 | -3.2975 | 30 | 0/120/240 |  |  |  | HTI | KAL-KS-BJM-0928-RETURN | SURGI MUFTI_TIMURLAUT | B2S | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | KOTA BANJARMASIN | 6614816 | 2020-07-01 |  | 666 | > 150 days | 2020-11-28 | W48-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 03.07.20 : Propose colo approved by RND XL (Pak Doddy), SPK Change to Colo 02.07.20 : propose Colo to existing site 220380109 SUNGAI ANDAI 114.60844 -3.29462 ( 383.40m ) GF SST 42m 01.07.20 : SPK release
873 |  | JAW-JB-CBI-0108-RETURN |  |  |  | SPK RETURN BY XL |  | 106.8 | -6.5197 | 30 | 90/190/330 |  |  |  | EID | JAW-JB-CBI-0108-RETURN | BOJONG_GEDE_RAYA | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614778 | 2020-06-24 |  | 673 | > 150 days | 2020-11-21 | W47-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.06.20 : SPK Release 24 jun 20, SPK return change SoW to SPK colo
828 |  | JAW-JB-BGR-0227 | 30595440031 | 1262201003 | CILEUKSA SUKAJAYA | SPK RETURN BY XL | TB | 106.4464 | -6.5952 | 40 | 10/115/205 |  |  |  | EID | JAW-JB-BGR-0227 | Cileuksa Sukajaya | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614778 | 2020-06-24 |  | 673 | > 150 days | 2020-11-21 | W47-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 25.02.21 : SPK return by XL remark Re-design (Email 25-Feb-21) 17.12.20 : SPK returned by XL (email konfirmasi Pak Siro RND XL) 19.11.20 : 12.11.20 : rehunting di lahan perkebunan, namun isu IMB tidak bisa release 09.11.20 : 05.11.20 : 02.11.20 : 26.10.20 : 22.10.20 : 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 : need arahan rehunting, NOM berada di kawasan rawan bencana 05.10.20 : 01.10.20 : rehunting kand D 28.09.20 : kand C NOK by RND 24.09.20 : NOM berada di Camp penampungan warga korban Banjir bandang dan longsor 21.09.20 : 18.09.20 : rehunting 17.09.20 : IW on going, NOM berada dikawasan rawan bencana longsor dan banjir 14.09.20 : 10.09.20 : 07.09.20 : IW on going 03.09.20 : 31.08.20 : 27.08.20 : JR SITAC, Daerah rawan bencana 24.08.20 : 18.08.20 : 17.08.20 : propose Colo RND NOK karena jarak terlalu jauh (3.7km), tidak bisa reloct NOM, proses rehunting 13.08.20 : need arahan hunting, propose Colo site exisiting TBG (120312104) karena area NOM berada di camp pemukiman warga terdampak bencana air bah dan longsor Jan 20 (pergerakan tanah rawan longsor dan kepemilikan lahan tidak jelas), JR submit tanggal 10 Aug 10.08.20 : 06.08.20 : kandidat A koordinat OK, RND request tower SST 52, TNP review 03.08.20 : 30.07.20 : 27.07.20 : rehunting 20.07.20 : 16.07.20 : 13.07.20 : 02.07.20 : 29.06.20 : hunting 24.06.20 : SPK Release 24 jun 20
836 |  | JAW-JB-BGR-0218 | 30595390031 | 1262151003 | JALAN RAYA SUKAMAKMUR | SPK RETURN BY XL | TB | 107.0224 | -6.5413 | 40 | 130/205/280 |  |  |  | EID | JAW-JB-BGR-0218 | Jalan Raya Sukamakmur | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614778 | 2020-06-24 |  | 673 | > 150 days | 2020-11-21 | W47-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 21.07.20 : SPK return by XL karena perubahan plan XL 20.07.20 : kandidat A koordinat 107.02281, -6.54221 propose SST 42 menunggu review RND (submit kandidat 15 Jul) 16.07.20 :13.07.20 : 02.07.20 : 29.06.20 : hunting 24.06.20 : SPK Release 24 jun 20
872 |  | JAW-JB-BGR-0226-RETURN |  |  |  | SPK RETURN BY XL |  | 107.0565 | -6.5575 | 50 | 135/240/340 |  |  |  | EID | JAW-JB-BGR-0226-RETURN | Sukadamai Sukamakmur Bogor | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614778 | 2020-06-24 |  | 673 | > 150 days | 2020-11-21 | W47-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.06.20 : SPK Release 24 jun 20, SPK return change SoW to SPK colo
870 |  | SUM-SU-BLG-2130-RETURN |  |  |  | SPK RETURN BY XL |  | 99.0735 | 2.3481 | 40 | 80/180/240 |  |  |  | HTI | SUM-SU-BLG-2130-RETURN | BALIGE LUMBAN BULBUL | B2S | TBG | WEST | SUMBAGUT | Sumatera Utara | TOBA SAMOSIR | 6614769 | 2020-06-23 |  | 674 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 25.06.20 : RND XL (Pak Doddy) OK CHANGE TO COLO, need change SPK Colo 24.06.20 : propose colo dg jarak 286m ke 22309123 BALIGE 1, GF SST 26m 23.06.20 : SPK Release 23 jun 20
908 |  | JAW-JI-SPG-4221 |  |  |  | SPK RETURN BY XL |  | 113.1528 | -7.1066 | 50 | 90/210/330 |  | RELOCATION |  | HTI | JAW-JI-SPG-4221 | GUNUNG MUNCIK RELOCATION | COLO | TBG | EAST | JATIM | Jawa Timur | Kab. Sampang | 6614777 | 2020-06-23 |  | 674 | > 150 days | 2020-07-23 | W30-2020 | Jul-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.07.20 : SPK return by XL (email Bu Anggie) karena perubahan design dan plan XL 23.07.20 : 13.07.20 : 09.07.20 : 02.07.20 : under review TNP CAA 29.06.20 : ERM on going 23.06.20 : SPK Release 23 jun 20
871 |  | JAW-JK-CKG-0714 |  |  |  | SPK RETURN BY XL |  | 106.9246 | -6.1692 | 30 | 85/180/315 |  |  |  | EID | JAW-JK-CKG-0714 | INFEKSI CAKUNG CAKUNG | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | Jakarta Timur | 6614768 | 2020-06-23 |  | 674 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 23.06.20 : SPK Release 23 jun 20, propose return by RND XL (Pak Siro) karena change plan, confirm return by Pak maulana dengan remarks “Drop by XL change plan”.
840 |  | JAW-JK-TJP-0680 | 30594990031 | 1128761003 | KAMPUNG BETING KOJA | SPK RETURN BY XL | TB | 106.9204 | -6.1192 | 30 | 75/160/290 |  |  |  | EID | JAW-JK-TJP-0680 | KAMPUNG BETING KOJA | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | Jakarta Utara | 6614768 | 2020-06-23 |  | 674 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.08.20 : email SPK return by XL (Bu Anggie) Dikarenakan adanya perubahan design & plan XL 18.08.20 : 17.08.20 : TNP OK , MW height 20m/0.3 , IW ongoing 10.08.20 : 06.08.20 : kandidat C OK RF 20m, proses review TNP 03.08.20 : submit kandidat baru, kandidat C koordinat 106.92101 -6.11936, under RNP review 30.07.20 : 27.07.20 : kandidat B approved by RND XL untuk ketinggian 20m, proses sumbit validasi TNP 20.07.20 : kandidat B koordinat OK, menunggu konfirmasi Pak Siro untuk ketinggian 20m 16.07.20 : submit kandidat B koordinat 106.92043, -6.11902 menunggu review RND 13.07.20 : 09.07.20 : RND not OK kand A, rehunting 08.07.20 : submit kand A 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20, confirm by RND XL (Pak Siro) untuk lanjut di ketinggian 20m sesuai regulasi pemerintah
869 |  | SUM-AC-KTN-0376-RETURN |  |  |  | SPK RETURN BY XL |  | 97.8262 | 3.4428 | 50 | 70/110/310 |  |  |  | HTI | SUM-AC-KTN-0376-RETURN | KUTA CINGKAM I | B2S | TBG | WEST | SUMBAGUT | Aceh | ACEH TENGGARA | 6614769 | 2020-06-23 |  | 674 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 25.06.20 : RND XL (Pak Doddy) OK CHANGE TO COLO, need change SPK Colo 24.06.20 : propose colo dg jarak 1165m ke site 10135104 SP_TG_JNGR GREEN FIELD SST 72 23.06.20 : SPK Release 23 jun 20
846 |  | JAW-JI-PCT-4234 | 30595120031 | 1644441003 | LOROK PACITAN RELOCATION | SPK RETURN BY XL | TB | 111.3203 | -8.21733333333333 | 50 | 90/210/330 |  | RELOCATION |  | HTI | JAW-JI-PCT-4234 | LOROK PACITAN RELOCATION | B2S | TBG | EAST | JATIM | Jawa Timur | Pacitan | 6614774 | 2020-06-23 |  | 674 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | NOM berada di existing site XL yang hard comcase (radius isu dari NOM lebih dari 500m) | 27.08.20 : email return by system, hard kandidat 17.08.20 : propose return karena isu hardcomcase existing site XL 13.08.20 : 10.08.20 : need perluasan SAR, hasil hunting dan arahan pemdes area dgn status lahan dan IW clear jarak 600m dr NOM 06.08.20 : proses rehunting di area NOM 03.08.20 : 30.07.20 : 27.07.20 : proses re-validasi kandidat A dengan melampirkan JR (NOM memiliki histori hardcommcase), menunggu review RNP 23.07.20 : 20.07.20 : kandidat A NOK karena terlalu jauh dari NOM, rehunting 16.07.20 : submit kand A, koordinat kand 600an m dr NOM karena NOM berada di existing XL yang comcase. Radius NOM yang terdampak comcase lebih dari 500m. Kand ini juga atas arahan muspika dan desa, untuk menghindasi pelebaran case yang terjadi. 13.07.20 : 29.06.20 : Hunting 23.06.20 : SPK Release 23 jun 20
793 |  | NUS-NB-GRG-4540-RETURN |  |  |  | SPK RETURN |  | 116.0821 | -8.5469 | 30 | 0/120/240 |  |  |  | HTI | NUS-NB-GRG-4540-RETURN | GUNUNGSARI_JATISELA | B2S | TBG | EAST | BALINUSRA | Nusa Tenggara Barat | KAB. LOMBOK BARAT | 6614769 | 2020-06-23 |  | 674 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [13 empty] | 02.SPK returned | 02.SPK RETURNED | Penolakan warga dalam radius 200m dari NOM | SPK RETURN sudah digantikan dengan SPK BARU REAKTIVASI 06.08.20 : 03.08.20 : 30.07.20 : kandidat A NOK karena terlalu jauh dari NOM, review pak Felix suggest SPK direturn 27.07.20 : 23.06.20 : under review RNP, validasi ulang kandidat A dengan pertimbangan IW Clear 16.07.20 : lokasi NOM mendapat penolakan warga dengan radius 200m, plan hari ini submit kandidat B 13.07.20 : 09.07.20 : rehunting 10.07.20 : RND not OK A karena dekat existing, need rehunting SAR <150m 09.07.20 : submit kand A 09.07.20 : sudah ada 1 kandidat dan sedang di verifikasi, plan di ajukan validasinya ke XL besok 02.07.20 : 29.06.20 : Hunting 23.06.20 : SPK Release 23 jun 20
868 |  | KAL-KS-PLI-0931-RETURN |  |  |  | SPK RETURN |  | 115.0266 | -3.6906 | 72 | 0 |  |  |  | HTI | KAL-KS-PLI-0931-RETURN | SIMPANG EMPAT JORONG | B2S | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | Tanah Laut | 6614666 | 2020-04-17 |  | 741 | > 150 days | 2020-09-14 | W38-2020 | Sep-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 18.04.20 : SPK reject by Marketing TBG 17.04.20 : SPK di recall XL/tidak jadi di assign ke TBG karena salah assign atau salah plan XL (email Mba Dibby XL)
867 |  | KAL-KS-MTP-0930-RETURN |  |  |  | SPK RETURN BY XL |  | 114.5222 | -3.4989 | 50 | 0/90/180 |  |  |  | HTI | KAL-KS-MTP-0930-RETURN | BAKAMBAT | B2S | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | Banjar | 6614568 | 2020-03-19 |  | 770 | > 150 days | 2020-08-16 | W34-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 26.03.20 : RND OK change to Colo dengan propose top tower, tower 42m permanen, SPK RETURN, CHANGE TO COLO 25.03.20 : 20.03.20 : propose change to colo ke 220733109 TBG_DSLABATMUARA jarak 204m, status masih GM dengan plan RFI permanent W4 May SST 42m (IMB clear), space availabel for XL 40m. Req Xl (pak Doddy) di 50m. Sedang dipertimbangkan kembali
829 |  | JAW-JI-LMG-4278 | 30588010031 | 1644031003 | DESA PASI KARANGBINANGUN | SPK RETURN BY XL | TB | 112.4555 | -7.0573 | 50 | 90/200/270 |  |  |  | HTI | JAW-JI-LMG-4278 | DESA PASI KARANGBINANGUN | B2S | TBG | EAST | JATIM | Jawa Timur | Lamongan | 6614568 | 2020-03-19 |  | 770 | > 150 days | 2020-08-16 | W34-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 22.04.20 : email konfirmasi return by XL (Bu Endang) karena ada perubahan plan XL 16.04.20 : rehunting 09.04.20 : 02.04.20 : rehunting 25.03.20 : hunting
831 |  | JAW-JB-NPH-3707 | 30587440031 | 1261821003 | GARUNGGANG | SPK RETURN BY XL | TB | 107.4771 | -6.8741 | 40 | 100/190/280 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JB-NPH-3707 | GARUNGGANG | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614560 | 2020-03-16 |  | 773 | > 150 days | 2020-08-13 | W33-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 08.09.20 : email return by system, titik nom berada di Kawasan perumahan Kota Baru Parahyangan, dan warga radius perumahan semua menolak 08.08.20 : email return dari XL 20.07.20 : 16.07.20 : gagal IW, SPK propose return 13.07.20 : IW clear kand F 11.07.20 : review TNP OK kandidat F (107.4764 -6.8744639 107°28'35''E 6°52'28.07''S) SST 42m 09.07.20 : IW on going, plan IW clear minggu ini 10 jul 02.07.20 : rehunting, NOM di dalam kawasan kota baru parahyangan (XL propose di dalam kompleks, karena kalau di luar near existing XL), propose return by XL karena hard kandidat (tidak memungkinkan membangun tower di dalam kompleks Kota Baru Parahyangan karena mendapat penolakan pihak komplek) 30.06.20 : change transport type menjadi MW, request SK PSB PLN untuk continue PLN Connectionnya 29.06.20 : rehunting 25.06.20 : 22.06.20 : 18.06.20 : 15.06.20 : Kandidat C RNP NOK. Plan submit kandidat senin 15/06/2020 11.06.20 : IW 300 kk 08.06.20 : 04.06.20 : proses revalidasi ulang, kandidat sesuai arahan XL 01.06.20 : 29.05.20 : proses revalidasi ulang 28.05.20 : 25.05.20 : 14.05.20 : IW on going plan clear 18 May 08.05.20 : 30.04.20 : IW OG Plan ada potensi Penolakan Warga Paralel rehunting plan submit kandidat tgl 2 Mei 23.04.20 : 16.04.20 : IW on going 09.04.20 : 02.04.20 : 25.03.20 : IW on Going, plan IW clear tgl 3 april
848 |  | KAL-KB-MPW-0702-RETURN |  |  |  | SPK RETURN BY XL |  | 109.3395 | 0.47282 | 40 | 30/100/300 |  |  |  | HTI | KAL-KB-MPW-0702-RETURN | MENJALIN | B2S | TBG | JABO | KALIMANTAN | Kalimantan Barat | KAB. LANDAK | 6614554 | 2020-03-13 |  | 776 | > 150 days | 2020-08-10 | W33-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 23.03.20 : SPK DROPED by XL karena perubahan ID XL, dan di release New SPK no. 6614705 tgl 12 May dengan ID KAL-KB-NBA-0710 MENJALIN 18.03.20 : Submit Kandidat A Lat. 0,47319 Long. 109,33904 to HO 20.03.20 : Kand A Reject TNP namun masih menunggu NOM arahan dari XL
852 |  | JAW-JB-CBI-0065 | 30587400031 | 1261811003 | PURA GUNUNG SALAK PERMANEN | SPK RETURN BY XL | TB | 106.7359 | -6.6681 | 40 | 90/210/330 |  |  |  | EID | JAW-JB-CBI-0065 | PURA GUNUNG SALAK Permanen | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614553 | 2020-03-13 |  | 776 | > 150 days | 2020-08-10 | W33-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 11.08.20 : email SPK return by XL, Category Return Community Issue, Return By XL 06.08.20 : MOM : SPK propose drop oleh XL karena durasi 06.08.20 : IW on going Sisa 1 Kk (tanah kosong), paralel submit kandidat baru E,F,H,I under RNP review 03.08.20 : 30.07.20 : IW On Going, Terkendala 1 Kk (tanah kosong) 23.07.20 : Re-IW On Going kand A, 23kk, clear 19kk, 4kk plan dilakukan door to door, Plan IW Clear 26/07 20.07.20 : IW On Going, masih dikejar untuk mendapatkan persetujuan 1kk, paralel sedang di Re IW kandidat A 16.07.20 : 13.07.20 : IW On Going, masih dikejar untuk mendapatkan persetujuan 1kk 09.07.20 : MOM : IW On Going, masih dikejar untuk mendapatkan persetujuan 1kk 06.07.20 : 02.07.20 : IW on going kurang 1 kk, plan IW clear sabtu 4 juli, plan start CME 10 jul, plan RFI 10 aug 20 29.06.20 : 25.06.20 : validasi RND kandidat B approved RF 40m OK, Plan IW Done Jun 2020 22.06.20 : 18.06.20 : 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20 08.06.20 : need arahan karena tidak mendapatkan persetujuan dari pihak PURA GUNUNG SALAK untuk membangun menara di dalam kawasan Pura. 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review 28.05.20 : 25.05.20 : rehunting 15.05.20 : 14.05.20 : 08.05.20 : rehunting 30.04.20 : rehunting 23.04.20 : 16.04.20 : rehunting 09.04.20 : 02.04.20 : rehunting 25.03.20 : hunting
855 |  | SUM-SU-PMS-2191 | 30587360031 | 0223691003 | SEI MANGKEI_BOSAR | SPK RETURN BY XL | TB | 99.3443 | 3.132626 | 40 | 90/240/300 | 2020 | JEDI 2020 [NEW] |  | HTI | SUM-SU-PMS-2191 | SEI MANGKEI_BOSAR | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KAB. SIMALUNGUN | 6614554 | 2020-03-13 |  | 776 | > 150 days | 2020-08-10 | W33-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 30.04.20 : 28.04.20 : SPK return by XL karena adanya perubahan plan (email Bu Anggie) 23.04.20 : TNP review 16.04.20 : menunggu surat balasan KIM/PTPN, proses sirkuler 09.04.20 : belum ada balasan dari KIM 06.04.20 : KIM meminta diajukan surat ulang oleh TBG, plan kamis 9 PAril surat baru dapat dimasukkan karena menyesuaikan jadwal masuk Pic KIM, balasan surat nantinya digunakan sebagai evidence ke XL. 02.04.20 : 30.03.20 : info CMI tidak pernah ada pengajuan kerjasama ke PT. KIM tetapi hanya ke PTPN, akan di carikan evidence menegnai pengajuan kerjasama CMI seperti yang telah disampaikan KIM. 29.03.20 : NOM berada di Kawasan Industri Simalungun (KIM), dan saat ini pihak KIM tidak mau mengeluarkan izin dan menerima permohonan kerjasama dari TBG karena sebelumnya sudah pernah dilakukan joint survey dan sudah keluar harga ke kontraktor PT. CMI untuk titik NOM yang sama, Harus ada surat penarikan kerjasama dari CMI 25.03.20 : hunting
866 |  | SUM-SU-KBJ-2074-RETURN |  |  |  | SPK RETURN BY XL |  | 98.5137 | 3.2208 | 40 | 10/90/290 |  |  |  | HTI | SUM-SU-KBJ-2074-RETURN | SEMANGAT GUNUNG | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KAB. KARO | 6614554 | 2020-03-13 |  | 776 | > 150 days | 2020-08-10 | W33-2020 | Aug-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED
612 |  | JAW-JB-TSM-3372 | 30581600031 | 1261591003 | CIHIDEUNG TUGURAJA | ACTIVE - ORION | TB | 108.213 | -7.3333 | 30 | 90/210/330 | 2019 | ORION [NEW] | Kel. Tuguraja Gn. Kembang RT.03 RW.04 Kec. Cihideung, Kota Tasikmalaya Prov. Jawa Barat | HTI | JAW-JB-TSM-3372 | CIHIDEUNG TUGURAJA | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA TASIKMALAYA | 6614473 | 2020-02-13 |  | 805 | > 150 days | 2020-07-12 | W29-2020 | Jul-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | COMMCASE | 08:30:2021:25.02.21 : SPK propossed return by XL 25.02.21 : Community issue kand E 18.02.21 : propose reloc NOM (prepare JR) 08.02.21 : 04.02.21 : 28.01.21 : kand E RND OK, plan IW clear 8 Feb 14.01.21 : note -> target RFC Feb, target RFI akhir Mar 2021 11.01.21 : 03.12.20 : kand E IW clear (kandidat arahan tokoh masyarakat sekitar untuk menjauh dari area commcase), under RND XL review 26.11.20 : 23.11.20 : 19.11.20 : cand E NOK, proses penyelesaian commcase pada kandidat yang sebelumnya telah approved, plan issue solved W4 Nov 16.11.20 : kand D NOK, proses rehunting telah dilakukan sesuai arahan dan inSAR namun masih terkendala penolakan warga. Propose kandidat baru (kand E 250m dari NOM) under RNP review 12.11.20 : 09.11.20 : kand C masih commcase (penolakan warga), paralel mengajukan validasi kandidat D dengan propose tower SST 42, target IW CLEAR 12 Nov apabila masih belum ada progress maka akan direturn 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : 22.10.20 : ada pergeseran kandidat karena penolakan warga -> IMB tidak bisa release 19.10.20 : pengkondisian warga, hari ini plan start CME 15.10.20 : IW on going 12.10.20 : 08.10.20 : 05.10.20 : IW on going, plan IW clear kamis 8 oct 20 01.10.20 : IW on going 28.09.20 : 24.09.20 : 21.09.20 : 17.09.20 : 14.09.20 : 10.09.20 : Permit kota tasik, CME start setelah IMB release, sebelumnya sudah start CME (galian) tetapi di demo warga 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : Permit kota tasik, CME start setelah IMB release, sebelumnya sudah start CME (galian) tetapi di demo warga, plan kamis depan start CME 24.08.20 : 17.08.20 : plan start CME minggu ini 13.08.20 : cihideung masih belum mulai CME nya, terkait issue comcase warga di luar radius, plan besok mob demob, plan start CME Sabtu 06.08.20 : plan CME start minggu depan 12 Aug 20 03.08.20 : 27.07.20 : 23.07.20 : plan CME start minggu depan 20.07.20 : 16.07.20 : 13.07.20 : proses perijinan 09.07.20 : plan rekom done minggu ini 10 jul, plan start proses perijinan minggu depan 13 jul, start CME setelah proses perijinan plan 20 jul 06.07.20 : 02.07.20 : proses bayar realisasi IW dan paralel rekom, plan RFC W2 Juli, plan APD done minggu ini, Plan RFI W2 Aug (14 Aug 20) 29.06.20 : 25.06.20 : 22.06.20 : 18.06.20 : IW clear, proses eskalasi sitac, 15.06.20 : waiting TX validation cand C, paralel IW CLEAR 11.06.20 : 08.06.20 : RND OK, TNP review 07.06.20 : submit new kandidat 04.06.20 : Rehunting plan submit kandidat tgl 6 Juni 01.06.20 : 29.05.20 : Kandidat NOK Rehunting plan submit tgl 4 juni 28.05.20 : plan submit kand C jumat 29 may 20 26.05.20 : kandidat B not approve, karena dekat dengan existing. 25.05.20 : 22.05.20 : RND review 19.05.20 : submit kand B 14.05.20 : validasi kand Not OK, proses rehunting 08.05.20 : rehunting, plan submit kand hari ini 30.04.20 : rehunting 23.04.20 : 16.04.20 : rehunting 09.04.20 : rehunting 02.04.20 : 25.03.20 : rehunting 19.03.20 : rehunting 12.03.20 : rehunting 20.02.20 : hunting, on going survey 13.02.20 : SPK released
890 |  | JAW-JI-JBG-4141 [RETURN] |  |  |  | SPK RETURN BY XL |  | 112.3231 | -7.6355 | 40 | 90/210/330 |  |  |  | HTI | JAW-JI-JBG-4141 [RETURN] | Sumber Boto | COLO | TBG | EAST | JATIM | Jawa Timur | Kab. Jombang | 6614453 | 2020-01-31 |  | 818 | > 150 days | 2020-03-01 | W10-2020 | Mar-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 13.02.20 : SPK RETURN, change entity comppany to SKP CME BY XL 06.02.20 : ERM, under review Power, CME by XL
885 |  | JAW-JB-DPK-0438 |  |  |  | SPK RETURN BY XL |  | 106.7503 | -6.3939 | 42 | 10/110/190/280 |  |  |  | EID | JAW-JB-DPK-0438 | Bojongsari Sawangan | COLO |  | JABO | JABODETABEK (INNER) | Jawa Barat | KOTA DEPOK | 6614397 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | RND not OK | 13.02.20 : email return by XL-EID 04.02.20 : hasil ERM DROP by XL karena RND NOK -> ANTENNA TOO LOW
889 |  | JAW-JB-CMH-8077 |  |  |  | SPK RETURN BY XL |  | 107.5516 | -6.8577 | 30 | 0/120/240 |  |  | Kp. Kamarung Rt05/04 Citeurep - Cimahi- Cimahi | HTI | JAW-JB-CMH-8077 | CITEUREUP | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KOTA CIMAHI | 6614396 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.01.20 : email Return by XL, Teknik, Near existing XL 24.01.20 : email pengembalian SPK by Markering karena Drop by XL (RND NOK -> Near Existing)
897 |  | JAW-JI-LMG-4277 |  |  |  | SPK RETURN BY XL |  | 112.37 | -7.1737 | 50 | 90/200/270 |  |  |  | HTI | JAW-JI-LMG-4277 | KEMBANGBAHU_LOPANG | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. LAMONGAN | 6614396 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.01.20 : email Return by XL, Teknik, Antenna too low 24.01.20 : email pengembalian SPK by Markering karena Drop by XL (RND NOK -> ANTENNA TOO LOW)
849 |  | JAW-JK-CKG-0662 | 30573640031 | 1127961003 | NYIUR PONDOK KELAPA | SPK RETURN BY XL | TB | 106.9264 | -6.2393 | 30 | 0/90/180/280 |  |  | Jl. Tipar No.28, Kel. Pondok Kelapa RT.04 RW.007 Kec. Duren Sawit, Kota Jakarta Timur Prov. DKI Jakarta | EID | JAW-JK-CKG-0662 | Nyiur Pondok Kelapa | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614397 | 2020-01-15 |  | 834 | > 150 days | 2020-06-13 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 13.08.20 : 11.08.20 : email SPK return, Failed legal aspect 10.08.20 : 06.08.20 : MOM : SPK propose drop oleh XL karena durasi 06.08.20 : 03.08.20 : 30.07.20 : 27.07.20 : 23.07.20 : 20.07.20 : Poin2 yang dimintakan LL, sedang di review ke legal TBG, sudah clear review dari legal 16.07.20 : IW clear, proses eskalasi sitac 13.07.20 : 09.07.20 : MOM : ada isu poin PKS dg LL, malam ini pertemusan 06.07.20 : 02.07.20 : rekom process, plan start CME 8 juli, plan RFI 5 Aug 29.06.20 : IW clear 25.06.20 : IW kurang 1 kk, pole MCP 20m 25.06.20 : paralel submit kandidat G propose MCP 25 , RNP NOK near existing, Plan IW Done Jun 2020 22.06.20 : 18.06.20 : kand F NOK terlalu dekat existing, plan kembali ke kand E yg ada penolakan warga luar radius, plan start CME end of Jun 15.06.20 : 11.06.20 : IW clear 08.06.20 : 04.06.20 : 01.06.20 : 29.05.20 : paralel validasi kand alternatif, waiting TNP review 28.05.20 : 25.05.20 : 08.05.20 : 30.04.20 : IW on going 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : 25.03.20 : IW on going 19.03.20 : validasi RND 20.02.20 : kand A = kandidat A, waiting approval menjadi MCP 20m 13.02.20 : 06.02.20 : Kand A = Candidate A Submit 17.01.20 : hasil assessment PDI done (email arief), proses input STIP 1 B2S
904 |  | JAW-JI-MGT-4130 |  |  |  | SPK RETURN BY XL |  | 111.2707 | -7.6316 | 50 | 0/120/240 |  |  |  | HTI | JAW-JI-MGT-4130 | PANEKAN_SUMBERDODOL | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. MAGETAN | 6614396 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.01.20 : email Return by XL, Teknik, Antenna too low 24.01.20 : email pengembalian SPK by Markering karena Drop by XL (RND NOK -> ANTENNA TOO LOW)
899 |  | JAW-JK-KYB-0106 |  |  |  | SPK RETURN BY XL |  | 106.8237 | -6.2554 | 25 | 0/90/180/270 |  |  |  | EID | JAW-JK-KYB-0106 | PASAR WARUNG BUNCIT | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614397 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 28.01.20 : email Return by XL, Teknik, Antenna too low
903 |  | NUS-NT-KPG-0251 |  |  |  | SPK RETURN BY XL |  | 123.617 | -10.1695 | 40 | 50/155/250 |  |  |  | ALT | NUS-NT-KPG-0251 | Rafael Oepoi | COLO |  | EAST | BALINUSRA | Nusa Tenggara Timur | Kota Kupang | 6614398 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.01.20 : email pengembalian SPK oleh XL (email Sherli) karena adanya perubahan plan XL (Antenna too low)
853 |  | JAW-JK-CKG-0436 | 30573630031 | 1127951003 | RAWABOLA KELAPA DUA | SPK RETURN BY XL | TB | 106.8885 | -6.3509 | 30 | 0/90/190320 |  |  |  | EID | JAW-JK-CKG-0436 | Rawabola Kelapa Dua | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614397 | 2020-01-15 |  | 834 | > 150 days | 2020-06-13 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 02.03.20 : email CANCEL SPK BY XL (Bu Anggie) karena perubahan plan XL 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Candidate A Submit 17.01.20 : hasil assessment PDI done (email arief), propose change to colo (email sherly), proses input STIP 1 B2S
884 |  | SUM-LA-GDT-1045-RETURN |  |  |  | SPK RETURN BY XL |  | 105.2036 | -5.4302 | 50 | 90/240/310 |  |  |  | HTI | SUM-LA-GDT-1045-RETURN | TALANG MULYA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. PESAWARAN | 6614391 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 28.01.20 : email Return by XL, Teknik, Sectoral Blocking
887 |  | JAW-JB-SOR-3935 |  |  |  | SPK RETURN BY XL |  | 107.8716 | -6.9642 | 40 | 0/120/240 |  |  |  | HTI | JAW-JB-SOR-3935 | TANJUNGWANGI_CINULANG | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614391 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 28.01.20 : email Return by XL, Teknik, Sectoral Blocking
888 |  | JAW-JB-SBM-2108 |  |  |  | SPK RETURN BY XL |  | 107.0246 | -6.8843 | 40 | 90/190/270 |  |  |  | EID | JAW-JB-SBM-2108 | TITISAN SUKALARANG | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | SUKABUMI | 6614392 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 21.01.20 : email penarikan/pembatalan SPK oleh XL (Bu Anggie) karena adanya perubahan plan XL
900 |  | JAW-JB-CBI-0091 |  |  |  | SPK RETURN BY XL |  | 106.9182 | -6.4361 | 36 | 100/270/350 |  |  |  | EID | JAW-JB-CBI-0091 | Vaksindo Gunung Putri | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614397 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | RND not OK | 13.02.20 : email return by XL-EID 04.02.20 : hasil ERM DROP by XL karena RND NOK -> ANTENNA TOO LOW
901 |  | JAW-JB-SBR-3784 |  |  |  | SPK RETURN BY XL |  | 108.5076 | -6.7014 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JB-SBR-3784 | WERU LOR_WERU | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. CIREBON | 6614396 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.01.20 : email Return by XL, Teknik, Antenna too low 24.01.20 : email pengembalian SPK by Markering karena Drop by XL (RND NOK -> ANTENNA TOO LOW)
896 |  | JAW-JT-SGN-1837 | 30619830031 | 1437321003 | YOS SUDARSO SRAGEN | SPK RETURN BY XL | PKP | 111.0218 | -7.4245 | 50 | 40/185/290 |  |  |  | EID | JAW-JT-SGN-1837 | Yos Sudarso Sragen | COLO |  | CENTRAL | JATENG | Jawa Tengah | SRAGEN | 6614397 | 2020-01-15 |  | 834 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 28.01.20 : email Return by XL, Teknik, Antenna too low
825 |  | JAW-JI-BTU-4111 | 30571140031 | 1642911003 | BATU_SONGGOKERTO | SPK RETURN BY XL | TB | 112.4972 | -7.8643 | 30 | 0/100/290 | 2020 | JEDI 2020 [NEW] | Jl. Raya Songgoriti No. 24 Desa Songgokerto Kecamatan Batu Kota Batu | HTI | JAW-JI-BTU-4111 | BATU_SONGGOKERTO | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA BATU | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [13 empty] | 02.SPK returned | 02.SPK RETURNED | IMB NY Release | 11.02.21 : area MORATORIUM, high aging, return by XL 11.01.21 : isu IMB NY release Kota Batu Malang, pihak RT/RW belum bisa memberikan rekomendasi karena belum ada acuan perda terkait pembangunan menara telekomunikasi 17.12.20 : estimasi terbit produk perijinan Jan 2021 10.12.20 : 07.12.20 : 03.12.20 : surat resmi KPKNL sudah relase, proses perijinan dengan PEMDA terkait release IMB (issue rekomendasi RT/RW setempat), estimasi penyelesaian 11 Dec 30.11.20 : 19.11.20 : 12.11.20 : sudah dilakukan survey tgl 7 Nov, dari sisi koordinat clear, menunggu surat resmi pihak KPKNL (estimasi 2 minggu), target IW clear W5 Nov, RFC W1 Dec 09.11.20 : 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : surat jawaban dari BPPP akan diproses setelah survey KPKNL yg dilaksanakan pada W1 Nov 22.10.20 : 19.10.20 : plan hari ini survey dari KPKNL ke dinas BPPP, untuk pengecekan lahan yang diserwa karena terkait asset negara 15.10.20 : lahan di BPPP (aaproved), sudah dilakukan joint survey menggukan tower 52m, menunggu jawaban persetujuan sewa lahan dari KPKML 12.10.20 : 08.10.20 : sign kepala balai done, tetapi cand di geser sekitar 100m ke atas/utara, kand geser akan diajukan kembali validasinya setelah secure BPN Final pemaparam akhir september cand masuk pwrluasan area agro 05.10.20 : 01.10.20 : 28.09.20 : proses sign direktur balai penelitian. IW tambah radius 10 m (1 RM, 2 tanah kosong), plan minggu ini clear, start CME setelah submit OSS 24.09.20 : review TNP OK kand B H: 50 0.6 80.29 per 23 sep 23.09.20 : submit review TNP kand B Tower 52m, wait sign direktur balai penelitian. IW tambah radius 10 m (1 RM, 2 tanah kosong), plan minggu depan clear, start CME setelah submit OSS 21.09.20 : 17.09.20 : submit review TNP kand B Tower 52m, proses koordinasi dengan pihak BALITBANG, plan minggu depan start CME 10.09.20 : 09.09.20 : proses nego ketinggian tower, RND request 50m, kondisi aktual pihak BALITBANG hanya mengizinkan max 42m 07.09.20 : 03.09.20 : RND request 52m karena blocking sectoral. plan senin/selasa ada keputusan apakah bisa lanjut 52m atau drop 31.08.20 : Reaktivasi SPK, validasi kand paralel IW clear 25.06.20 : status di TR belum update return 22.06.20 : email SPK return by XL karena isu perijinan 15.06.20 : plan joint survey, perluasan SAR dan reloc NOM, per Meeting XL 11 jun XL meminta return SPK karena isu perijinan 11.06.20 : propose return 08.06.20 : rehunting 04.06.20 : 28.05.20 : 25.05.20 : rehunting 14.05.20 : 08.05.20 : 30.04.20 : rehunting 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : 25.03.20 : rehunting 19.03.20 : 12.03.20 : rehunting 28.02.20 : 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
826 |  | JAW-JI-SDA-4077-RETURN |  |  |  | SPK RETURN BY XL |  | 112.7329 | -7.4268 | 30 | 0/120/240 |  |  |  | HTI | JAW-JI-SDA-4077-RETURN | BUDURAN_SIDOMULYO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 28.01.20 : email Return by XL, Redesign, Propose COLO to site DEMANG
827 |  | JAW-JK-TJP-0620 | 30571860031 | 1127681003 | CEMPAKA RAYA CAKUNG | SPK RETURN BY XL | TB | 106.9171 | -6.1389 | 30 | 0/90/180/270 |  |  |  | EID | JAW-JK-TJP-0620 | Cempaka Raya Cakung | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 02.03.20 : email CANCEL SPK BY XL (Bu Anggie) karena perubahan plan XL 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
830 |  | JAW-JK-KYB-0099 | 30571780031 | 1127631003 | GANG HAJI JOKO | SPK RETURN BY XL | TB | 106.8373 | -6.3277 | 25 | 0/90/180 |  |  |  | EID | JAW-JK-KYB-0099 | Gang Haji Joko | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 02.03.20 : email CANCEL SPK BY XL (Bu Anggie) karena perubahan plan XL 20.02.20 : IW on going 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
832 |  | JAW-BT-CPT-0462 | 30572430031 | 1317621003 | HIJAU LESTARI PISANGAN | SPK RETURN BY XL | TB | 106.7516 | -6.3215 | 35 | 90/210/330 |  |  |  | EID | JAW-BT-CPT-0462 | HIJAU LESTARI PISANGAN | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 21.02.20 : email return by System (EID) 20.02.20 : CANCEL SPK sesuai email Bu Anggie karena adanya perubahan plan XL (RETURN BY XL) 19.02.20 : rehunting, makesure regulasi tangsel 06.02.20 : Hunting kandidat
864 |  | JAW-JK-CKG-0247-RETURN |  |  |  | SPK RETURN BY XL |  | 106.8971 | -6.3203 | 30 | 30/100/210/290 |  |  |  | EID | JAW-JK-CKG-0247-RETURN | Jalan Beringin Raya | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 16.01.20 : CHANGE TO COLO 15.01.20 : propose change to colo (email Rudi), konfirmasi OK Change to Colo dari XL (Pak Siro)
865 |  | JAW-JK-GGP-0526-RETURN |  |  |  | SPK RETURN BY XL |  | 106.6983 | -6.1709 | 30 | 90/180/270 |  |  |  | EID | JAW-JK-GGP-0526-RETURN | Jalan Haji Aseni | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA BARAT | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 16.01.20 : CHANGE TO COLO 15.01.20 : propose change to colo (email Rudi), konfirmasi OK Change to Colo dari XL (Pak Siro)
833 |  | JAW-BT-TNG-1453 | 30573410031 | 1317821003 | JALAN KAKAP CIBODAS | SPK RETURN BY XL | TB | 106.6109 | -6.2045 | 30 | 20/150/220 |  |  |  | EID | JAW-BT-TNG-1453 | Jalan Kakap Cibodas | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.02.20 : email penarikan SPK dari XL (bu Anggie) karena perubahan plan XL 14.02.20 : Return by XL Due to perubahan plan XL 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 16.01.20 : Proses input STIP 1 B2S 15.01.20 : propose change to colo (email Rudi), konfirmasi NOK dari XL (Pak Siro)
834 |  | JAW-JK-TJP-0625-RETURN |  |  |  | SPK RETURN BY XL |  | 106.7606 | -6.1281 | 30 | 60/180/270 |  |  |  | EID | JAW-JK-TJP-0625-RETURN | Jalan Pantai Indah Selatan 2 | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | lahan corporate PIK | 13.08.20 : SITE SUDAH RETURN BY XL 22 JULI (email Pak Yanse), Category Return Permit, Return By XL, Remark Site ini berada di area PIK. dan belum ada serah terima dari PIK ke Pemda 10.08.20 : 06.08.20 : Proses rekomendasi RW, untuk pemanfaatan lahan fasum 03.08.20 : 30.07.20 : 23.07.20 : 20.07.20 : Proses penyerahan lahan developer ke Fasum 16.07.20 : 13.07.20 : 09.07.20 : 06.07.20 : 02.07.20 : plan CME start minggu depan, plan RFI 5 AUg 29.06.20 : 25.06.20 : Plan IW Done Jun 2020 22.06.20 : 18.06.20 : kawasan PIK, isu pihak PIK belum hand over fasum ke Pemda, dikhawatirkan jd isu PIK saat hand over ke Pemda, menunggu jawaban/konfirmasi PIK atas pengajuan titik kand (PIK sedang menunggu konfirmasi dr Pemda apakah keberadaan tower jd isu atau tidak) 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20 08.06.20 : 04.06.20 : 28.05.20 : 25.05.20 : 08.05.20 : 30.04.20 : IW on going 30.04.20 : IW on going 23.04.20 : TNP review 16.04.20 : under review RND 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 validasi RND 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°45'44.15"E 6°07'42.42"S/106.762264 -6.12845 OK, Center Antenna 20m
835 |  | JAW-JK-GGP-0525 | 30573450031 | 1127921003 | JALAN PULAU PANTARA | SPK RETURN BY XL | TB | 106.7412 | -6.1724 | 30 | 15/80/150/290 |  |  |  | EID | JAW-JK-GGP-0525 | Jalan Pulau Pantara | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA BARAT | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 02.03.20 : email CANCEL SPK BY XL (Bu Anggie) karena perubahan plan XL 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 16.01.20 : Proses input STIP 1 B2S 15.01.20 : propose change to colo (email Rudi), konfirmasi NOK dari XL (Pak Siro)
837 |  | JAW-JK-KYB-0108 | 30572340031 | 1127851003 | JALAN RUKUN PASMING | SPK RETURN BY XL | TB | 106.8537 | -6.27 | 25 | 0/90/180/240 |  |  |  | EID | JAW-JK-KYB-0108 | Jalan Rukun Pasming | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 02.03.20 : email CANCEL SPK BY XL (Bu Anggie) karena perubahan plan XL 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
838 |  | JAW-BT-TNG-1462 | 30573460031 | 1317841003 | JL CIPTO MANGUNKUSOMO SUDIMARA TIMUR | SPK RETURN BY XL | TB | 106.7168 | -6.2357 | 35 | 90/210/330 |  |  |  | EID | JAW-BT-TNG-1462 | JL CIPTO MANGUNKUSOMO SUDIMARA TIMUR | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 20.02.20 : CANCEL SPK sesuai email Bu Anggie karena adanya perubahan plan XL (RETURN BY XL) 19.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 16.01.20 : Proses input STIP 1 B2S 15.01.20 : propose change to colo (email Rudi), konfirmasi NOK dari XL (Pak Siro)
839 |  | JAW-BT-TGR-0061 | 30572620031 | 1317811003 | JL TELESONIC PASIRJAYA | SPK RETURN BY XL | TB | 106.5582 | -6.2014 | 35 | 90/210/330 |  |  | JL. Manggarai Utara 2 RT.01, RW 04 Kel. Manggarai Kec. Tebet Jakarta Selatan | EID | JAW-BT-TGR-0061 | JL TELESONIC PASIRJAYA | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 13.08.20 : 10.08.20 : 04.08.20 : RETURN BY XL, remarks : community permit, IW Fail, ada 2 gudang kosong yang masih belum mendapatkan persetujuan, karena belum beroperasi semenjak PSBB ditetapkan 03.08.20 : 30.07.20 : 23.07.20 : Ada 2 gudang kosong yang masih belum mendapatkan persetujuan, karena belum beroperasi semenjak PSBB ditetapkan 27.07.20 : email return 20.07.20 : 16.07.20 : 13.07.20 : IW on going, Ada 2 gudang kosong yang masih belum mendapatkan persetujuan 09.07.20 : MOM : IW kurang 2 gudang kosong yg belum ketemu pemiliknya 06.07.20 : 02.07.20 : plan IW done 10 juli, plan start CME 14 juli, plan SRFI 6 aug 29.06.20 : 25.06.20 : IW kurang 1 (pabrik), plan IW clear Jun 2020 22.06.20 : 18.06.20 : IW on going, plan RFC end of June 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20 08.06.20 : 04.06.20 : 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : Rehunting OG 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : IW on going 25.03.20 : 19.03.20 : 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = RND OK 35
861 |  | JAW-JB-CBI-0083-RETURN |  |  |  | SPK RETURN BY XL |  | 106.7224 | -6.4796 | 50 | 70/150/250/330 |  |  |  | EID | JAW-JB-CBI-0083-RETURN | Kahuripan Kemang | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 16.01.20 : CHANGE TO COLO 15.01.20 : propose change to colo (email Rudi), konfirmasi OK Change to Colo dari XL (Pak Siro)
841 |  | JAW-BT-TNG-1468 | 30572600031 | 1317791003 | KARANGSARI NEGLASARI | SPK RETURN BY XL | TB | 106.6368 | -6.1586 | 35 | 150/270/330 |  |  |  | EID | JAW-BT-TNG-1468 | KARANGSARI NEGLASARI | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 13.08.20 : 11.08.20 : email SPK return, Category Return Government Permit, Return By , Remark Candidate di lahan dinas kesehatan. Permit kepala dinas belum release 10.08.20 : 06.08.20 : MOM : SPK propose drop oleh XL karena durasi 06.08.20 : IW on going kurang 1 kk, plan clear 10 Aug, , lahan dinas kesehatan, OG proses IW dari kepala Dinas Kesehatan Kota Tangerang 03.08.20 : 30.07.20 : Proses Ijin Warga, sisa 3kk belum memberikan persetujuan, belum memberikan persetujuan setuju atau tidak 23.07.20 : 20.07.20 : Proses Ijin Warga, sisa 3kk belum memberikan persetujuan, kesibukan kerja dan sering ke luar kota 16.07.20 : 13.07.20 : Proses Ijin Warga, 3kk belum memberikan persetujuan 09.07.20 : MOM : Ijin Warga, 3kk belum memberikan persetujuan 06.07.20 : 02.07.20 : plan IW done 7 juli, plan start CME 13 jul, plan SRFI 10 Aug 29.06.20 : IW clear 25.06.20 : IW kurang 3 kk dari 13 kk, SST 42m 22.06.20 : 18.06.20 : kandidat C RND OK, IW on going, plan RFC end of June 15.06.20 : 11.06.20 : IW clear 08.06.20 : 04.06.20 : 01.06.20 : IW on going, proses negosiasi harga 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : IW on going 23.04.20 : TNP review 16.04.20 : under review RND 09.04.20 : 02.04.20 : IW on going 25.03.20 : 19.03.20 : 11.03.20 : 20.02.20 : 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
842 |  | JAW-BT-TNG-1469 | 30572610031 | 1317801003 | KEDAUNG WETAN | SPK RETURN BY XL | TB | 106.6233 | -6.1353 | 35 | 90/180/270/340 |  |  |  | EID | JAW-BT-TNG-1469 | KEDAUNG WETAN | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.02.20 : email penarikan SPK dari XL (bu Anggie) karena perubahan plan XL 14.02.20 : Return by XL Due to perubahan plan XL 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 16.01.20 : Proses input STIP 1 B2S 15.01.20 : propose change to colo (email Rudi), konfirmasi NOK dari XL (Pak Siro)
843 |  | JAW-BT-TNG-1457 | 30572030031 | 1317421003 | KEDAUNG WETAN NEGLASARI | SPK RETURN BY XL | TB | 106.6265 | -6.1252 | 35 | 20/140/250/320 |  |  |  | EID | JAW-BT-TNG-1457 | Kedaung Wetan Neglasari | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 13.08.20 : 10.08.20 : 04.08.20 : email return by XL, Category Return Government Permit , Return By XL, Remark Rekomendasi KKOP tidak diijnkan untuk dibangun 03.08.20 : 30.07.20 : rekomendasi KKOP tidak diijnkan untuk dibangun pole MCP, karena kandidat lurus dengan jalun run way sejauh 1.4 km 23.07.20 : Rekomendasi KKOP tidak diijnkan untuk dibangun pole MCP, karena kandidat lurus dengan jalur run way sejauh 1.4 km 20.07.20 : 16.07.20 : 13.07.20 : proses rekom KKOP 09.07.20 : MOM : start CME menunggu rekom KKOP, plan rekom done minggu depan, rekom KKOP terkait rekom ketinggian tower ok/not 20m 02.07.20 : camat minta dilengkapi dengan rekom KKOP, plan rekom KKOP done 3 juli, plan start CME minggu depan 8 juli, plan SRFI W1 Aug (8 Aug 2)) 29.06.20 : 25.06.20 : proses rekom, camat minta dilengkapi dengan rekom KKOP, tim sedang fu ke KKOP 22.06.20 : 18.06.20 : realisasi IW, on going rekom process 15.06.20 : 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : IW on going 04.06.20 : IW on going 01.06.20 : 29.05.20 : waiting RND review, paralel IW on going 28.05.20 : 25.05.20 : 22.05.20 : RND review 30.04.20 : Rehunting OG, propose return krn durasi 108 hari (MoM 30 Apr 20) 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 25.03.20 : rehunting 19.03.20 : rehunting 12.03.20 : rehunting 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
844 |  | JAW-JK-TJP-0616 | 30571930031 | 1127731003 | KOMPLEK GREEN GARDEN | SPK RETURN BY XL | TB | 106.9492 | -6.1524 | 30 | 20/100/180/260 |  |  |  | EID | JAW-JK-TJP-0616 | Komplek Green Garden | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 30.07.20 : email return by XL, Category Return Others, Return By XL, Remark change RND plan 23.07.20 : email SPK return from XL (Bu Anggie) dengan reason adanya perubahan design XL 22.07.20 : kandidat F yang diajukan propose MCP 25, namun RND request ketinggian RF 30m, TBG hanya dapat membangun max 25m, need approval RND XL untuk ketinggian 25m, Rekomendasi dari PEMDA untuk ketinggian pole maksimal di 25m 20.07.20 : Rekomendasi dari PEMDA untuk ketinggian pole maksimal di 25m, need validasi dan approval XL 16.07.20 : 13.07.20 : 09.07.20 : MOM : Perda max 20m, propose 25m (titik OK), tetapi XL masih minta 30m, meeting minggu depan keputusannya ok/nok 30m, IW 25m clear. 06.07.20 : 02.07.20 : IW clear, Propose RND masih 30m, max propose TBG25m dan sedang pengajuan ke Pemda, plan RFI W1 Aug/8 Aug 20 29.06.20 : IW clear 25.06.20 : hasil validasi kandidat E NOK, kandidat F koordinat OK request 30m, Plan RFC Jun 2020 22.06.20 : 18.06.20 : proses IW on going, kand 300m diluar komplek, XL propose 30m, Perda 20m dan diusahakan 25m (need konfirmasi RND XL) 15.06.20 : 11.06.20 : IW clear 08.06.20 : IW on going 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review, paralel on going IW 28.05.20 : 25.05.20 : 21.05.20 : IW on going 14.05.20 : TNP ok C, tower 25 30.04.20 : Rehunting OG, propose return krn durasi 108 hari (MoM 30 Apr 20) 23.04.20 : 16.04.20 : Rehunting Lahan Private, high price 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : 12.03.20 : waiting RND validation 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
845 |  | BAL-BA-MGW-1523 | 30570930031 | 1717281003 | KUTA_UTARA_TIBUBENENG | SPK RETURN BY XL | TB | 115.1682 | -8.6157 | 25 | 0/120/240 | 2020 | JEDI 2020 [NEW] |  | HTI | BAL-BA-MGW-1523 | KUTA_UTARA_TIBUBENENG | B2S | TBG | EAST | BALINUSRA | Bali | KAB. BADUNG | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | isu cell plan/perda, tidak di ijinkan membangun tower di cellplan yang sudah ada existing tower, propose colo ke existing MCP TBG not OK by RND | 04.06.20 : email return by XL karena isu Perizinan (Pemerintah) / Isu Cell Plan 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 05.02.20 : Kand A = not approved by RND 30.02.20 : Kand A = proposes colo not approved, rehunting dekat NOM 28.02.20 : Kand A = submit A 115.16298 -8.61785 620.16 GF MCP 18 Propose colo to Site MCP Existing TBG Cellplan & Perbup Badung propose ke site existing dikarenakan dititik nominal sudah ada site existing, dan sesuai Perbup No.31 Tahun 2018, BAB IV Pasal 7 Ayat 3, menyatakan bahwa ini, “Apabila dalam 1 (satu) zona terdapat lebih dari 1 (satu) menara sebelum Peraturan Bupati ini ditetapkan,maka menara-menara tersebut dapat terus dimanfaatkan sebagai menara telekomunikasi sepanjang masih menjalankan kewajiban sebagai sarana pendukung dalam layanan telekomunikasi seluler kepada masyarakat dan/atau memberikan manfaat kepada pemerintah dalam layanan Smart City Terpadu”, dengan kata lain tidak dijinkannya membangun menara/MCP existing jika sudah ada existing didalam zona cellplan yang ada.
847 |  | JAW-BT-TNG-1463 | 30572560031 | 1317751003 | MAULANA HASANUDIN CIPONDOH MAKMUR | SPK RETURN BY XL | TB | 106.678 | -6.18 | 35 | 90/210/330 |  |  |  | EID | JAW-BT-TNG-1463 | MAULANA HASANUDIN CIPONDOH MAKMUR | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 24.02.20 : email penarikan SPK dari XL (bu Anggie) karena perubahan plan XL 14.02.20 : Return by XL Due to perubahan plan XL 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 16.01.20 : Proses input STIP 1 B2S 15.01.20 : propose change to colo (email Rudi), konfirmasi NOK dari XL (Pak Siro)
850 |  | JAW-JI-LMJ-4225-RETURN |  |  |  | SPK RETURN BY XL |  | 113.0588 | -8.1174 | 50 | 30/180/270 |  |  |  | HTI | JAW-JI-LMJ-4225-RETURN | PASRUJAMBE_PASRUJAMBE | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. LUMAJANG | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 16.01.20 : CHANGE TO COLO, konfirmasi OK Change to Colo oleh XL (Pak Brovisa) 15.01.20 : propose to XL change to colo (email rudi)
863 |  | JAW-BT-CPT-0448 |  |  |  | SPK RETURN BY XL |  | 106.7484 | -6.2701 | 25 | 0/70/190/270 |  |  |  | EID | JAW-BT-CPT-0448 | Pinguin Pondok Aren | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 20.01.20 : email Surat Pengembalian SPK by Marketing ke LM XL 17.01.20 : email konfirmasi SPK return by Marketing & XL 16.01.20 : XL (Pak Siro) confirm agar SPK B2S di return (redesign by Planning XL), karena berdasarkan hasil assessment site ini berdekatan dengan site existing XL yang colo ke TBG yaitu (BINTARO UTAMA RELOCATION-JAW-BT-TGR-2010) kurang lebih jarak nya 278 mtr dari NOM .
851 |  | JAW-BT-CPT-0476-RETURN |  |  |  | SPK RETURN BY XL |  | 106.7662 | -6.3313 | 35 | 45/130/200/330 |  |  |  | EID | JAW-BT-CPT-0476-RETURN | Pondok Cabe Raya | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 13.08.20 : 11.08.20 : email SPK return by XL, Category Return Government Permit , Return By XL, Remark ijin Rekomendasi dari KKOP hanya tinggi 5m 10.08.20 : 06.08.20 : MOM : SPK propose drop oleh XL karena isu perijinan/rekomendasi tinggi tower KKOP dan durasi 06.08.20 : 03.08.20 : 30.07.20 : 23.07.20 : Rekomendasi dari KKOP 5m, lokasi site berada di samping runway PONDOK CABE 20.07.20 : 16.07.20 : 13.07.20 : proses rekom KKOP 09.07.20 : MOM : need rekom ketinggian KKOP, titik di sebelah runway bandara pondok cabe, IW clear, CME start wait rekom KKOP release 02.07.20 : proses rekom, paralel hammertest, plan design done 8 juli, plan start cme 12 juli, plan SRFI 3 Aug 29.06.20 : 25.06.20 : proses rekom, camat minta dilengkapi dengan rekom KKOP, plan start CME minggu depan setelah rekom camat release 22.06.20 : 18.06.20 : IW clear, on going realisasi IW, plan start CME akhir bulan 15.06.20 : 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : IW on going 04.06.20 : 28.05.20 : 25.05.20 : 08.05.20 : 30.04.20 : Negosiasi BAN 23.04.20 : 16.04.20 : Proses negosiasi BAN 09.04.20 : kandidat A, propose rooftop, IW 80% 02.04.20 : under review RND 31.03.20 : submit kand 25.03.20 : rehunting 19.03.20 : 19.03.20 : Rehunting 11.03.20 : 20.02.20 : rehunting, makesure regulasi tangsel06.02.20 : Hunting kandidat
857 |  | JAW-JK-CKG-0708 | 30571870031 | 1127691003 | SMA 64 CIPAYUNG | SPK RETURN BY XL | TB | 106.892 | -6.3276 | 30 | 25/100/210/290 |  |  |  | EID | JAW-JK-CKG-0708 | SMA 64 Cipayung | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 02.03.20 : email CANCEL SPK BY XL (Bu Anggie) karena perubahan plan XL 20.02.20 : Hunting, hard sitac, commcase imbas Bali Tower 06.02.20 : Hunting kandidat
859 |  | JAW-BT-TNG-1455 | 30572390031 | 1317591003 | SUNAN KALIJAGA PESANGGRAHAN | SPK RETURN BY XL | TB | 106.7273 | -6.2277 | 30 | 90/160/250/320 |  |  |  | EID | JAW-BT-TNG-1455 | Sunan Kalijaga Pesanggrahan | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 03.04.20 : email return by system 24.02.20 : email penarikan SPK dari XL (bu Anggie) karena perubahan plan XL 14.02.20 : Return by XL Due to perubahan plan XL 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 16.01.20 : Proses input STIP 1 B2S 15.01.20 : propose change to colo (email Rudi), konfirmasi NOK dari XL (Pak Siro)
860 |  | JAW-BT-TNG-1458-RETURN |  |  |  | SPK RETURN BY XL |  | 106.6492 | -6.1935 | 35 | 0/90/180/270 |  |  |  | EID | JAW-BT-TNG-1458-RETURN | Taman Golf Boulevard | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | Lahan corporate MODERNLAND | 04.08.20 : email SPK return, Category Return Community Issue, Return By XL 10.08.20 : 06.08.20 : proses pendekatan IW 1 kk, paralel rehunting kand alternatif 03.08.20 : 30.07.20 : 23.07.20 : IW Failed, 1 Warga menolak memberikan tanda tangan IW, Proses submit permohonan kerjasama dengan pihak MODERNLAND 20.07.20 : 16.07.20 : 13.07.20 : 09.07.20 : MOM : IW kurang 1 kk sepadan tower, warga orang Mahkamah Agung 06.07.20 : 02.07.20 : plan IW done 7 juli, plan rekom 10 juli, plan start CME 13 jul, plan SRFI 6 Aug 29.06.20 : 25.06.20 : IW kurang 1 kk, pole 25m 22.06.20 : 18.06.20 : kembali ke kandidat awal, IW on going, Plan IW Done Jun 2020 15.06.20 : 11.06.20 : IW clear (proses PKS) 08.06.20 : rehunting 04.06.20 : 01.06.20 : masih menunggu jawaban dari MODERNLAND, alternatif propose re-NOM 28.05.20 : 25.05.20 : 15.05.20 : 14.05.20 : 08.05.20 : Proses persetujuan permohonan kerjasama 30.04.20 : Rehunting Site 23.04.20 : 16.04.20 : IW on going, Proses persetujuan permohonan kerjasama kawasan Modernland 09.04.20 : 02.04.20 : 25.03.20 : IW on going, Terbatasnya lahan yang disewakan 19.03.20 : proses BAN BAK 12.03.20 : Kawasan modernland 11.03.20 : 20.02.20 : hunting, Hunting, NOM berada di kawasan modernland 06.02.20 : Hunting kandidat
862 |  | JAW-JI-SDA-4069-RETURN |  |  |  | SPK RETURN BY XL |  | 112.7257 | -7.3637 | 25 | 0/120/240 |  |  |  | HTI | JAW-JI-SDA-4069-RETURN | WARUSDA_PEPELEGI | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 28.01.20 : email Return by XL, Redesign, Propose Colo ke site TBG Mawae Legi (B2S masih CME on going, plan start CME B2S 20 Feb, plan RFI 20 Mar 20))
787 |  | JAW-JI-SDA-4076 | 30571460031 | 1643231003 | BUDURAN_SIDOKEPUNG | SPK RETURN | TB | 112.6978 | -7.4306 | 30 | 0/120/240 |  |  |  | HTI | JAW-JI-SDA-4076 | BUDURAN_SIDOKEPUNG | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | Terdapat hystory hard comcase di SAR NOM | 25.05.20 : SPK return di system XL 13 feb 20 22.05.20 : IW on going 08.05.20 : propose return by XL 30.04.20 : IW on going 23.04.20 : 16.04.20 : 09.04.20 : IW on going 02.04.20 : 19.03.20 : IW OG, CAND APPROVED OPR 28.02.20 : 27.02.20 : 07°25'49.84"S 112°42'06.66"E, IW 26 KK kurang 18 KK. 13.02.20 : email Return SPK 10 feb 20 sesuai Surat permohonan perpanjangan waktu SPK B2S ke LM XL, Reason return karena terdapat history hard comcase di NOM 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : Kand A = RND OK 30 70/150/310 30Jan20 : Ok candidate A, tower 32 28.01.20 : Kand A = submit A 112.69837 -7.4309444, propose tower 32m
788 |  | JAW-JI-SDA-4075 | 30571450031 | 1643221003 | BUDURAN_SIDOKERTO | SPK RETURN | TB | 112.7122 | -7.4341 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-SDA-4075 | BUDURAN_SIDOKERTO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 22.06.20 : email SPK return by XL karena isu hard comcase/hard sitac, status di TR sudah return (remark hard candidat) 18.06.20 : sudah dilakukan joint survey dengan regional operator (sales dan planning), untuk masuk area yang mendekati NOM masih belum bisa/tidak bisa menerima orang luar, propose return karena hard sitac dan lockdown covid 19 15.06.20 : plan hunting outSAR 08.06.20 : 04.06.20 : 01.06.20 : plan submit kandidat 4 jun 28.05.20 : 25.05.20 : rehunting 15.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : rehunting 23.04.20 : 16.04.20 : rehunting 09.04.20 : 02.04.20 : rehunting 25.03.20 : rehunting 19.03.20 : 20.02.20 : 13.02.20 : 06.02.20 : Hunting kandidat 17.01.20 : Markering akan input STIP 1 B2S 16.01.20 : konfirmasi NOK oleh XL (Pak Brovisa) 15.01.20 : propose to XL change to colo (email rudi)
789 |  | JAW-JK-TJP-0621-RETURN |  |  |  | SPK RETURN |  | 106.8304 | -6.1253 | 30 | 50/140/300 |  |  |  | EID | JAW-JK-TJP-0621-RETURN | Dufan Marina | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 11.06.20 : rehunting, need re-NOM, actual status di Tower rental sudah return 08.06.20 : 04.06.20 : 01.06.20 : plan submit kand 4 jun. 28.05.20 : 25.05.20 : rehunting 14.05.20 : 08.05.20 : rehunting 30.04.20 : rehunting 23.04.20 : 16.04.20 : Rehunting Site, NOM berada di lahan Kawasa ANCOL, IBS sudah ber PKS dengan pihak kawasan 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting, NOM berada di lahan Kawasa ANCOL, IBS sudah ber PKS dengan pihak kawasan 19.03.20 : proses BAN BAK, validasi RND 12.03.20 : Lahan kawasan Dufan 11.03.20 : 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
790 |  | JAW-JK-CKG-0668 (RETURN) |  |  |  | SPK RETURN |  | 106.8625 | -6.2941 | 30 | 50/120/210/340 |  |  | JL. H. Ali Gang Mundu II RT.04 RW.04 Kel. Tengah Kec. Keramat Jati Kota Jakarta Timur | EID | JAW-JK-CKG-0668 (RETURN) | Gang Induk Pasar Rebo | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | Propose RND min 25M | 10.09.20 : SPK B2S RETURN diganti dengan SPK COLO reaktivasi yg release 4 sep 20 03.09.20 : 31.08.20 : 27.08.20 : 19.08.20 : SRFIN sent, cek status SPK return atau aktif 30.07.20 : 09.07.20 : 06.07.20 : IW clear, need propose reaktivasi 11.06.20 : rehunting, plan IW done jun 20, sudah ada kandidat (plan re-IW), actual status di Tower rental sudah return 08.06.20 : rehunting 04.06.20 : 01.06.20 : plan submit kand 4 jun. 28.05.20 : 25.05.20 : 30.04.20 : Rehunting OG, propose return by XL krn durasi 108 hari (MoM 30 Apr 20) 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 25.03.20 : rehunting 19.03.20 : rehunting 12.03.20 : rehunting 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
791 |  | JAW-JI-SDA-4074 | 30571440031 | 1643211003 | GEDANGAN_BANGAH | SPK RETURN | TB | 112.7224 | -7.3798 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-SDA-4074 | GEDANGAN_BANGAH | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | Terdapat hystory hard comcase di SAR NOM | 25.05.20 : SPK return di system XL 13 feb 20 22.05.20 : IW on going 08.05.20 : propose return by XL 30.04.20 : IW on going 23.04.20 : 16.04.20 : 09.04.20 : IW on going 02.04.20 : IW on going 19.03.20 : 11.03.20 : rehunting 13.02.20 : email Return SPK 10 feb 20 sesuai Surat permohonan perpanjangan waktu SPK B2S ke LM XL, Reason return karena terdapat history hard comcase di NOM 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : Kand A = RND OK 30 80/170/315 30Jan20 : Ok candidate A, tower 32 28.01.20 : Kand A = submit A 112.7223 -7.3800861, propose tower 32m
792 |  | JAW-JI-SDA-4073 | 30573480031 | 1643481003 | GEDANGAN_KETAJEN | SPK RETURN | TB | 112.7355 | -7.3935 | 30 | 0/180/270 | 2020 | JEDI 2020 [NEW] | Puri Surya Jaya C1 NO.07 Pasadena, Kel. Ketajen Kec. Gedangan, Kab. Sidoarjo Prov. Jawa Timur | HTI | JAW-JI-SDA-4073 | GEDANGAN_KETAJEN | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | isu perijinan, Perda membatasi max ketinggian hanya 20m sehingga tidak memenuhi requirement/propose RND | 30.04.20 : rehunting, status RETURN SPK by system per 13 feb 20 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : rehunting 19.03.20 : IW on going, need approval kandidat 12.03.20 : rehunting 13.02.20 : email Return SPK 10 feb 20 sesuai Surat permohonan perpanjangan waktu SPK B2S ke LM XL, Reason return karena isu perijinan, Perda membatasi max ketinggian hanya 20m sehingga tidak memenuhi requirement/propose RND 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 17.01.20 : Markering akan input STIP 1 B2S 16.01.20 : info dari tim Jatim site PURI SURYAJAYA TBG sudah dismantle dan reloc ke Puri Suya jaya Reloc 15.01.20 : propose to XL change to colo (email rudi)
794 |  | JAW-JK-CKG-0669-RETURN |  |  |  | SPK RETURN |  | 106.8583 | -6.3171 | 30 | 0/90/180/270 |  |  |  | EID | JAW-JK-CKG-0669-RETURN | Jalan R. A. Fadillah | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 30.07.20 : 09.07.20 : 06.07.20 : 11.06.20 : IW clear (proses PKS), actual status di Tower rental sudah return, need propose reaktivasi 08.06.20 : rehunting 04.06.20 : 01.06.20 : plan submit kand 4 jun. 28.05.20 : 25.05.20 : 30.04.20 : Rehunting OG, propose return by XL krn durasi 108 hari (MoM 30 Apr 20) 23.04.20 : 16.04.20 : Rehunting site NOM berada disekitar lahan Kompleks KOPASSUS 09.04.20 : kand NOK 02.04.20 : 25.03.20 : rehunting 19.03.20 : rehunting 12.03.20 : waiting RND validation 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
797 |  | JAW-JI-SBY-8279 (RETURN) |  |  |  | SPK RETURN |  | 112.7809 | -7.2278 | 30 | 0/120/240 |  |  |  | HTI | JAW-JI-SBY-8279 (RETURN) | KENJERAN_TANAH_KALI_KEDINDING | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA SURABAYA | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 31.08.20 : Reaktivasi dengan NEW SPK B2S use old STIP B2S, validasi kand paralel IW clear 25.06.20 : status di TR belum update return 22.06.20 : email SPK return by XL karena isu perijinan 15.06.20 : NEED APP OPR regulasi max 20m, plan perluasan SAR, per Meeting XL 11 jun XL meminta return (isu regulasi ketinggian sesuai Perda) 11.06.20 : propose return 08.06.20 : NEED APP OPR, IW OG , REDUCE KETINGGIAN / OUTSAR 04.06.20 : 28.05.20 : 25.05.20 : rehunting 14.05.20 : 08.05.20 : 30.04.20 : rehunting 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 11.03.20 : IW on going, propose reduce ketinggian 20.02.20 : Kand A = Mediasi dengan yayasan done , proses nego sewa lahan , JR drone , extend Menara masjid 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 31.01.20 : Kand A = submit A 112.781419 -7.227581 RT 9 + Pole 6. Total ketinggian 15mAgl, Perda Kota Surabaya utk area Rungkut max RT+pole 6m,
798 |  | JAW-JI-BLT-1913-RETURN |  |  |  | SPK RETURN |  | 112.1675 | -8.1022 | 30 | 50/140/280 |  |  |  | HTI | JAW-JI-BLT-1913-RETURN | KEPANJEN_KIDUL_KEPANJENKIDUL | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA BLITAR | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 31.08.20 : Reaktivasi dengan NEW SPK B2S 25.06.20 : status di TR belum update return 22.06.20 : email SPK return by XL karena isu ketinggian sesuai Perda (isu perijinan) 18.06.20 : sudah dilakukan joint survey dengan pihak regional XL (sales & planning), kandidat terakhir sesuai arahan XL IW failed, propose return karena isu ketinggian sesuai Perda (isu perijinan) 15.06.20 : rehunting, need JR issue pembatasan ketinggian menara, ketinggian kand tower not OK dan terkendala isu ketinggian Perda 11.06.20 : 08.06.20 : IW on going, isu regulasi 04.06.20 : 28.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : IW on going, isu regulasi 23.04.20 : 16.04.20 : IW on going, isu regulasi 09.04.20 : 02.04.20 : 25.03.20 : Menunggu hasil dari perizinan Pole 6m. Tidak ada lahan lagi yang bisa di eksekusi padat penduduk / Perijinan Minta Struktur Gambar Bangunan 19.03.20 : 11.03.20 : IW on going 14.03.20 : A / S : 8°06'06.80" E : 112°10'05.78" / rooftop / Menunggu hasil dari perizinan Pole 6m. 09.03.20 : Propose lahan yang secure , koordinasi dengan dinas , propose pole 6 m , stacking 7 m , ( proses pemaparan di dinas terkait IW pole 6 m ) , target 15.3.20 28.02.20 : 24.02.20 : cand A, Rofftop, IW blm sign, perwali blitar RT 10, exsisting bangunan 7, cand B LL di luar negeri , rehunting cand C 20.02.20 : IW OG , kurang 1 KK , anak LL 13.02.20 : IW on going, Propose Rofftop , 2 lantai , staking 2 lantai ( 3,5 x2 ) + pole 9 ( need perwali ketinggian max pole 10m 06.02.20 : kand A = validasi done, Candidate A RF TX OK
799 |  | JAW-JI-SDA-4065 | 30571390031 | 1643161003 | KRIAN_KRATON | SPK RETURN | TB | 112.5587 | -7.41 | 40 | 90/180/270 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-SDA-4065 | KRIAN_KRATON | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 22.06.20 : email SPK return by XL karena isu hard comcase/hard sitac, status di TR sudah return (remark hard candidat) 15.06.20 : 11.06.20 : propose return 08.06.20 : rehunting, need arahan XL 04.06.20 : 28.05.20 : 25.05.20 : rehunting 14.05.20 : 08.05.20 : 30.04.20 : rehunting 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : rehunting 25.03.20 : 19.03.20 : IW on going 11.03.20 : rehunting 28.02.20 : 25.02.20 : kand A = IW Clear, re nego BAN 20.02.20 : kand A = IW On going 13.02.20 : kand A = IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 27.01.20 : kand A = 112.55822 -7.4092222 101.27 GF SST 42
801 |  | JAW-BT-CPT-0464 | 30572450031 | 1317641003 | MENTENG BINTARO | SPK RETURN | TB | 106.7296 | -6.2784 | 35 | 90/210/330 |  |  |  | EID | JAW-BT-CPT-0464 | MENTENG BINTARO | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 13.08.20 : 11.08.20 : email SPK return,Category Return Government Permit, Return By XL, Remark Canditate di lahan Fasos Pemkot. Permit government not release 10.08.20 : 06.08.20 : MOM : SPK propose drop oleh XL karena isu proses perijinan dan durasi 06.08.20 : Proses follow up rekomendasi penggunaan lahan Fasum PEMKOT, saat ini sedang dilakukan komunikasi dengan 3 SKPD : PUPR, KOMINFO, LINGKUNGAN 03.08.20 : 30.07.20 : 23.07.20 : 20.07.20 : Proses follow up rekomendasi penggunaan lahan Fasum PEMKOT 16.07.20 : 13.07.20 : IW Clear, menggunakan lahan Fasum Tangsel 09.07.20 : MOM : IW clear/no IW, menggunakan lahan fasum, plan rekom PUPR minggu depan, MCP 20m, plan CME start rabu 15 jul 06.07.20 : 02.07.20 : IW on going kurang 1 kk karena belum berhasil ditemui, plan IW clear minggu ini, plan rekom minggu depan, plan start CME akhir minggu depan 12 jul 20, plan RFI W2 Aug/15 aug 20 29.06.20 : 25.06.20 : IW minus 1 kk tanah kosong, plan Pic TBG Jumat 26 jun akan ke lokasi menemui 1 warga pemilik lahan kosong yang telah diketahui keberadaannya, plan IW done paling lambat Senin 29 Juni or drop by XL 22.06.20 : 18.06.20 : kembali ke kandidat awal, IW on going 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20, , sudah ada kandidat (plan re-IW) 08.06.20 : 04.06.20 : 01.06.20 : IW clear, proses negosiasi harga 28.05.20 : 25.05.20 : 08.05.20 : 30.04.20 : Negosiasi BAN 23.04.20 : 16.04.20 : IW Clear, kandidat A BAN, Negosiasi BAN 09.04.20 : iw clear 02.04.20 : 02.04.20 : IW on going 25.03.20 : TNP review 19.03.20 : validasi RND 20.02.20 : rehunrting, makesure regulasi tangsel 06.02.20 : Hunting kandidat
803 |  | JAW-JK-TJP-0627 | 30572060031 | 1127781003 | PADEMANGAN TANJUNG PRIOK | SPK RETURN | TB | 106.8529 | -6.1211 | 25 | 0/80/180/270 |  |  |  | EID | JAW-JK-TJP-0627 | Pademangan Tanjung Priok | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED |  | 11.06.20 : rehunting, need re-NOM , actual status di Tower rental sudah return 08.06.20 : 04.06.20 : 01.06.20 : plan submit kand 4 jun. 28.05.20 : 25.05.20 : rehunting 14.05.20 : 08.05.20 : rehunting 30.04.20 : rehunting 23.04.20 : 16.04.20 : Rehunting Site, NOM berada di lahan Kawasa ANCOL, IBS sudah ber PKS dengan pihak kawasan 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : validasi RND 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°51'11.57"E 6°07'15.74"S/106.853214 -6.121039 OK, Center Antenna 20m
804 |  | JAW-JI-SBY-4340 | 30571370031 | 1643141003 | PAKAL_SBYPAKAL | SPK RETURN | TB | 112.6205 | -7.2496 | 30 | 90/230/330 |  |  |  | HTI | JAW-JI-SBY-4340 | PAKAL_SBYPAKAL | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA SURABAYA | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | Area Developer (Citraland) | 30.04.20 : rehunting 23.04.20 : 16.04.20 : 09.04.20 : validasi NOK 02.04.20 : 19.03.20 : IW OG, JR REDUCE KETINGGIAN 12.03.20 : rehunting 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 31.01.20 : Kand A = submit A 112.622917 -7.248444 RT 9.5 + Pole 6. Total ketinggian 15.5mAgl, Perda Kota Surabaya utk area Rungkut max RT+pole 6m,
805 |  | JAW-JI-SDA-4072 | 30571430031 | 1643201003 | SEDATI_SEDATI_GEDE | SPK RETURN | TB | 112.7567 | -7.3741 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl. Jend. Wahono By Pass Juanda, Desa Sedati Gede Kec.Sedati, Kab.Sidoarjo Prov.Jawa Timur | HTI | JAW-JI-SDA-4072 | SEDATI_SEDATI_GEDE | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | isu perijinan, Perda membatasi max ketinggian hanya 20m sehingga tidak memenuhi requirement/propose RND | 30.04.20 : rehunting 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : rehunting 19.03.20 : IW on going, need approval kandidat 11.03.20 : 13.02.20 : email Return SPK 10 feb 20 sesuai Surat permohonan perpanjangan waktu SPK B2S ke LM XL, Reason return karena isu perijinan, Perda membatasi max ketinggian hanya 20m sehingga tidak memenuhi requirement/propose RND 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
806 |  | JAW-JI-SDA-4081 | 30571500031 | 1643271003 | SIDOARJO_BLURU_KIDUL | SPK RETURN | TB | 112.7292 | -7.4536 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-SDA-4081 | SIDOARJO_BLURU_KIDUL | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | isu perijinan, Perda membatasi max ketinggian hanya 20m sehingga tidak memenuhi requirement/propose RND | 30.04.20 : rehunting 23.04.20 : 16.04.20 : rehunting 09.04.20 : 02.04.20 : 19.03.20 : 11.03.20 : rehunting 13.02.20 : email Return SPK 10 feb 20 sesuai Surat permohonan perpanjangan waktu SPK B2S ke LM XL, Reason return karena isu perijinan, Perda membatasi max ketinggian hanya 20m sehingga tidak memenuhi requirement/propose RND 06.02.20 : Hunting kandidat
807 |  | JAW-JI-SDA-4080 | 30571490031 | 1643261003 | SIDOARJO_BULUSIDOKARE | SPK RETURN | TB | 112.7261 | -7.461 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-SDA-4080 | SIDOARJO_BULUSIDOKARE | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | isu perijinan, Perda membatasi max ketinggian hanya 20m sehingga tidak memenuhi requirement/propose RND | 25.05.20 : SPK return di system XL 13 feb 20 14.05.20 : IW on going 08.05.20 : 30.04.20 : propose site MCP atau RT 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : IW on going 19.03.20 : rehunting 13.02.20 : email Return SPK 10 feb 20 sesuai Surat permohonan perpanjangan waktu SPK B2S ke LM XL, Reason return karena isu perijinan, Perda membatasi max ketinggian hanya 20m sehingga tidak memenuhi requirement/propose RND 06.02.20 : kand B = validasi done, Candidate C RF TX OK 30.01.20 : Kand B = RND OK 30 15/90/280 30Jan20 : Ok candidate A, tower 32 28.01.20 : Kand A = submit A 112.72714 -7.4618139, propose MCP 18m Kand B = submit B 112.72614 -7.4613944, propose SST 32m
808 |  | JAW-JI-SDA-4078 | 30571470031 | 1643241003 | SIDOARJO_SUKO | SPK RETURN | TB | 112.6861 | -7.449 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-SDA-4078 | SIDOARJO_SUKO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | isu perijinan, Perda membatasi max ketinggian hanya 20m sehingga tidak memenuhi requirement/propose RND | 30.04.20 : rehunting 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 19.03.20 : 12.03.20 : rehunting 13.02.20 : email Return SPK 10 feb 20 sesuai Surat permohonan perpanjangan waktu SPK B2S ke LM XL, Reason return karena isu perijinan, Perda membatasi max ketinggian hanya 20m sehingga tidak memenuhi requirement/propose RND 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 04.02.20 : Kand A = submit A 112.68689 -7.448081 130.22 RT 8 Pole 6 Perda antar tower Kab Sidoarjo with justification below
809 |  | JAW-BT-TNG-1456 (RETURN) |  |  |  | SPK RETURN |  | 106.6411 | -6.2129 | 35 | 30/150/290 |  |  |  | EID | JAW-BT-TNG-1456 (RETURN) | SMPN 14 Tangerang | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED | Propose RND min 25M | 24.09.20 : REKOM LURCAM OG 13.08.20 : 11.08.20 : email SPK return by XL, Category Return Government Permit, Return By XL, Remark Permit from government not release 10.08.20 : 06.08.20 : MOM : SPK propose drop oleh XL karena isu proses perijinan dan durasi 06.08.20 : Follow up rekomendasi hasil Presentasi Teknis, target minggu depan release 03.08.20 : 30.07.20 : Follow up rekomendasi hasil Presentasi Teknis 23.07.20 : 20.07.20 : Presentasi Teknis done dengan PEMKOT, Follow up rekomendasi hasil Presentasi Teknis, Plan Released tgl 22/07 16.07.20 : 13.07.20 : 09.07.20 : MOM : IW clear, proses perijinan tangkot outcell belum clear, plan CME start minggu depan 06.07.20 : 02.07.20 : IW clear, proses pengajuan ke PEMDA Tinggi 25m (area Tangkot), target solve dengan Pemda minggu depan, plan CME start paling lambat 9 jul 20/weekly minggu depan, plan SRFI W1 Aug (8 Aug 20) 29.06.20 : 25.06.20 : Cand Approved, proses negosiasi ke PEMDA Tinggi 25m, paralel pengambilan foto panoramic by drone, paralel proses rekom. plan Start CME paling lambat senin 29 Jun 2020 22.06.20 : 18.06.20 : Done IW, proses rekom 15.06.20 : 11.06.20 : proses validasi, paralel IW clear 08.06.20 : RND review 04.06.20 : 01.06.20 : IW on going 28.05.20 : 25.05.20 : 21.05.20 : IW on going 14.05.20 : TNP ok B, tower 25 30.04.20 : Rehunting OG, propose return krn durasi 108 hari (MoM 30 Apr 20) 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : IW on going 12.03.20 : rehunting 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
810 |  | JAW-BT-TGR-0022 | 30572010031 | 1317401003 | TAMAN KOTA TANGERANG | SPK RETURN | TB | 106.4856 | -6.27 | 35 | 55/180/280 |  |  |  | EID | JAW-BT-TGR-0022 | Taman Kota Tangerang | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 30.07.20 : 09.07.20 : 25.06.20 : XL propose return dulu dan dapat diajukan reaktivasi jika progress sudah clear, status TR belum return 22.06.20 : 18.06.20 : area perkantoran bupati Tangerang, terkendala saat PSBB ASN WFH, sempat cari kand B diluar area perkantoran. Skrg proses fu kembali kand A (area perkantoran Bupati). XL propose return dulu dan akan diajukan reaktivasi jika progress sudah clear 15.06.20 : 11.06.20 : Proses kerjasama corporate 08.06.20 : rehunting 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review 28.05.20 : 25.05.20 : 15.05.20 : IW on going 14.05.20 : 08.05.20 : rehunting 30.04.20 : Rehunting OG 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : under review RND 25.03.20 : rehunting 19.03.20 : rehunting 12.03.20 : rehunting 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 24.01.20 : kand A = RND NOT OK near existing
813 |  | JAW-JK-TJP-0622 (RETURN) |  |  |  | SPK RETURN |  | 106.8344 | -6.1311 | 25 | 0/90/160 |  |  | R.E MARTADINATA RT.01 RW.013 Kel. PADEMANGAN BARTA KEC.PADEMANGAN KOTA.JAKARTA UTARA | EID | JAW-JK-TJP-0622 (RETURN) | Tol Pelabuhan Ancol | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6614368 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 02.SPK returned | 02.SPK RETURNED |  | 17.09.20 : SPK B2S RETURN diganti dengan SPK COLO reaktivasi yg release 4 sep 20 09.07.20 : 06.07.20 : 18.06.20 : Propose reaktivasi SPK, progress start excavation 11.06.20 : excavation, actual status di Tower rental sudah return 08.06.20 : 04.06.20 : 01.06.20 : sudah galian, plan balik ke galian awal (ada pipa PDAM 4) geser ada pipa GAS --> prosesredesign dg borepile, sudah diajukan 28.05.20 : 25.05.20 : 21.05.20 : 18.05.20 : kand D RND NOK krn near existing, paralel penyelesaian comcase site sebelumnya 16.05.20 : submit kand D, pindah lokasi karena comcase 14.05.20 : excavation geser titik, galian pondasi ketemu pipa gas 08.05.20 : excavation on going 30.04.20 : preparation start CME 23.04.20 : 16.04.20 : Plan Start CME 17/04 09.04.20 : IW clear, RT RW, Lurah Clear, Plan start CME 15/04 02.04.20 : under review RND 25.03.20 : Candidat NOK, Rehunting 19.03.20 : validasi RND 20.02.20 : rehunting 06.02.20 : Hunting kandidat
814 |  | JAW-JI-SDA-4079 | 30571480031 | 1643251003 | TULANGAN_GRABAGAN | SPK RETURN | TB | 112.6299 | -7.4431 | 40 | 0/120/240 | 2020 | JEDI 2020 [NEW] |  | HTI | JAW-JI-SDA-4079 | TULANGAN_GRABAGAN | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 02.SPK returned | 02.SPK RETURNED | Lower due to Perda Jarak min Antar Tower, Terdapat hystory hard comcase di SAR NOM | 25.05.20 : SPK return di system XL 13 feb 20 14.05.20 : 08.05.20 : 30.04.20 : IW clear 23.04.20 : 16.04.20 : 09.04.20 : iw on going 02.04.20 : 19.03.20 : IW clear need approval cand 13.02.20 : email Return SPK 10 feb 20 sesuai Surat permohonan perpanjangan waktu SPK B2S ke LM XL, Reason return karena terdapat history hard comcase di NOM 06.02.20 : kand B = validasi done, Candidate C RF TX OK 30.01.20 : Kand B = RND 40 115/220/340 30Jan20 : Ok candidate B, tower 42 28.01.20 : Kand A = submit A 112.6301 -7.4426528, propose MCP 18m, Lower due to Perda Jarak min Antar Tower Kand B = submit B 112.63353 -7.4397028, propose SST 42m, Out SAR due to Perda Jarak min Antar Tower
473 |  | JAW-JB-CBN-3822 | 30571030031 | 1260821003 | LARANGAN_HARJAMUKTI | ACTIVE | TB | 108.5669 | -6.7496 | 30 | 200/270/340 | 2020 | JEDI 2020 [NEW] | Jl. Ciremai Raya GG Kamal II RT 001 RW 019 Kel. Larangan Kec. Harjamukti, Kota Cirebon Prov. Jawa Barat | HTI | JAW-JB-CBN-3822 | LARANGAN_HARJAMUKTI | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA CIREBON | 6614369 | 2020-01-13 |  | 836 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | FO | [13 empty] | 02.SPK returned | 02.SPK RETURNED | COMMCASE | 25.02.21 : SPK propossed return by XL 25.02.21 : propose kand I existing TBG minaret 32, RND NOK 25.02.21 : SPK propossed return by XL 22.02.21 : kand existing TBG under RNP review 18.02.21 : kandidate alternatif (kand H) RND NOK, arahan rehunting dari RND terdapat existing TBG ± 200m dari titik arahan 04.02.21 : 28.01.21 : plan IW clear 8 Feb 11.01.21 : IW ongoing, perlu dilakukan pendekatan untuk meminimalisasi penolakan warga 26.11.20 : plan IW clear 27 Nov, plan CME start W1 Dec 19.11.20 : proses penyelesaian commcase warga luar radius di kandidat terakhir (cand D), target issue solved W4 Nov 16.11.20 : plan CME start W3 12.11.20 : 09.11.20 : 05.11.20 : target solved minggu depan, dilanjutkan proses soiltest 02.11.20 : 26.10.20 : 22.10.20 : 19.10.20 : proses nego eskalasi 15.10.20 : target clear hari ini, lanjut proses eskalasi sitac 12.10.20 : proses negosiasi kompensasi permintaan mobil ambulance 08.10.20 : IW clear, proses eskalasi sitac 05.10.20 : IW kurang 1 warga, plan besok finalisasi IW 01.10.20 : Finalisasi iw lg cek perizinan utk lahan yg tidak ada pemilik nya 28.09.20 : plan start CME rabu 30 sep 20 terkendala karena adanya isu site di demo warga (proses penyelesaian) 24.09.20 : 21.09.20 : proses sidang fatwa masih ditunda 17.09.20 : plan sidang fatwa hari ini 14.09.20 : plan sidang fatwa kamis 17 sep, plan joint survey jumat 18 sep 10.09.20 : plan sidang fatwa jumat 11 sep, plan survey selasa 15 sep 07.09.20 : 03.09.20 : start CME masih menunggu sidang fatwa 31.08.20 : 27.08.20 : plan sidang fatwa minggu depan (rabu depan) dan start CME setelah survey, sebelumnya ada isu LSM sehingga sidang fatwa di mundur 24.08.20 : menunggu jadwal sidang fatwa, start CME setelah sidang fatwa, plan start CME 28 Aug 17.08.20 : 13.08.20 : CME start menunggu konfirmasi hasil sidang fatwa 10.08.20 : 06.08.20 : RFC, proses perijinan, start CME setelah sidang fatwa, plan jadwal sidang Fatwah Rabu depan 12 Aug 20 03.08.20 : 30.07.20 : realisasi IW dan rekom done, plan RFC hari ini 27.07.20 : realisasi IW & rekom 23.07.20 : proses rekom, plan start CME awal Aug (3 aug), on going soiltest,
|  | JAW-JB-CBI-0157 | 30743250031 | 1267852003 | IBS KAHURIPAN KLAPANUNGGAL | BP2022 | TB | 106°58.37.34'E | 6°26.29.87'S | 50 | 100/220/310 |  |  | Desa Cikahuripan Kp. Cipari RT.022 RW.009, Kec. Klapanunggal, Kab. Bogor Prov. Jawa Barat | EID | JAW-JB-CBI-0157 | CIKAHURIPAN_BOGOR | COLO | TBG | Jabodetabek | JABODETABEK | Jawa Barat | Kab. Bogor | 6618138 | 2022-03-18 | 2022-03-21 | 40 | 31 - 60 days | 2022-04-17 | W17-2022 | Apr-2022 | TBD | TBD | TBD | 2022-05-13 | W20-2022 | May-2022 | 2022-05-13 | W20-2022 | May-2022 | MW | 2022-04-14 | 2022-04-14 | 538657399675 | 10.6 |  | 2022-04-13 |  |  | 2022-04-27 |  |  |  | CME | 38.RFI | 21.RFI | NEED STRENGTENING (NY PARALEL) | 27:04:22: RFIN 24:04:22-14:04:22: PONDASI OG, STR NY PARALEL 13:04:22: STO 12:04:22-23:03:22: ERM PROCESS 21:03:22: SPK REECIVED |  | 406 | 393 TBG
NEW SPK B2S |  | JAW-JB-CJR-4335 | 30730470031 | 1276241003 | CIPANAS_CIPANAS | BP2022 | TB | 107°2.16.41'E | 6°44.25.48'S | 40 | 90/180/270 | 2022 | New site 2022 - P1 | Kp. Panagan RT.13/19 Desa Cipanas Kec. Cipanas Kab. Cianjur | HTI | JAW-JB-CJR-4335 | CIPANAS_CIPANAS | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Cianjur | 6617949 | 2022-01-25 | 2022-01-28 | 92 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-04-10 | 2022-04-11 | MG |  |  | 2022-04-25 |  |  | 2022-04-27 |  |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 27:04:22: RFIN 26:04:22: CONFIRM BP EDIT 6.6 24:04:22: WAIT CONFIRM XL UPGRADE TO 16.5 KVA DUE TO PERLUASAN JARINGAN 20:04:22: ERECTION 17:04:22: POURING 13:04:22: REBARRING 10:04:22: REKOM 06:04:22-27:03:22: REKOM OG 23:03:22-20:03:22: IW CLEAR 16:03:22: IW OG 13:03:22: VALIDASI RNP TNP 09:03:22: REHUNTING 06:03:22: IW OG 28:02:22: VALIDASI RNP TNP 23:02:22-05:02:22: IW OG 02:02:22: UNDER TNP REVIEW 30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr | 406 | 393 TBG
|  | JAW-JB-NPH-4383 | 30739980031 | 1276981003 | CIPONGKOR_BARANANGSIANG | BP2022 | TB | 107°19.44.17'E | 6°54.20.69'S | 50 | 40/160/300 | 2022 | Newsite 2022 - P2 | Kp. Pasir Salak RT.04 RW.07 Desa Baranangsiang Kec. Cipongkor Kab. Bandung Barat | HTI | JAW-JB-NPH-4383 | CIPONGKOR_BARANANGSIANG | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Bandung Barat | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-31 | 2022-04-01 |  |  |  | 2022-04-12 | [6 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22-20:04:22: PLN 17:04:22-14:04:22: ERECTION 10:04:22: REBARRING 06:04:22-27:03:22: REKOM OG 23:03:22-20:03:22: IW CLEAR 16:03:22-15:03:22: IW OG 13:03:22: VALIDASI RNP TNP 12:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED | apr | 401 | 388 TBG
|  |  |  | 1446542023 | IBS MENDURAN |  | TB | 110°53.42.5'E | 7°4.41.77'S | 40 | 90/210/330 |  |  |  | NOKIA | JAW-JT-PWD-3388 | PUTAT PURWODADI GROBOGAN RELOCATION | COLO | XL | Central | JATENG | Jawa Tengah | Kab. Grobogan | 6618218 | 2022-04-26 | 2022-04-26 | 2 | < 30 days | 2022-05-26 | W22-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 07.ESR preparation | 06.ERM PROCESS | CURRENTLY NO ISSUE | 26:04:22: SPK RECEIVED |  | 401
NEW SPK |  | JAW-BT-TGR-0095 | 30735170031 | 131225109 | LIONAIRWANAKERTA | BP2022 | SKP | 106°29.36.42'E | 6°11.28.03'S | 36 | 5/110/220 | 2022 | New site 2022 - P1 | Desa Wanakerta Kp. Sarongge RT.02 RW.06 Kec. Sindang Jaya , Kab. Tangerang Prov. Banten | EID | JAW-BT-TGR-0095 | LION_AIR_WANAKERTA | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Tangerang | 6617984 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-23 | W17-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 |  | 10.6 |  | 2022-03-09 | [6 empty] | CME | 37.Power connection process | 20.SRFI | STR DONE | 27:04:22: WAIT RFIN 24:04:22: ME OG 20:04:22-03:04:22: PONDASI OG & PERKUATAN (PLAN START 7 APR) 30:03:22-09:03:22: PERKUATAN OG 06:03:22-16:02:22: READY TO STO 13:02:22-09:02:22: NEED REVIEW CIVIL EID 07:02:22-06:02:22: NEED REVIEW RNP EID 04:02:22: NEW SPK RELEASED | apr | 401 | 388 TBG
NEW SPK |  | JAW-BT-TGR-0106 | 30733990031 | 131236109 | TELAGABESTARI | BP2022 | SKP | 106°29.10.82'E | 6°11.50.78'S | 30 | 50/140/300 | 2022 | New site 2022 - P1 | Desa Talaga Kp. Sikluk RT.2 RW.4 Kec. Cikupa, Kab. Tangerang Prov. Banten | EID | JAW-BT-TGR-0106 | TELAGA_BESTARI | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Tangerang | 6617984 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-22 | W17-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-17 |  | 10.6 |  | 2022-02-08 | [6 empty] | CME | 37.Power connection process | 20.SRFI | STR DONE | 27:04:22: WAIT RFIN 24:04:22: PONDASI OG 20:04:22: STR DONE 19 apr 17:04:22-16:02:22: PONDASI OG PARALEL PERKUATAN 13:02:22: PERKUATAN OG 09:02:22: CME PREPARATION 07:02:22: NEED REVIEW POWER EID 06:02:22-30:01:22: ESR REVIEW, NEED REVIEW RNP EID 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
NEW SPK |  | JAW-JT-KLN-0930 | 30736050031 | 1443812004 | IBS SOL0095 | BP2022 | TB | 110°33.43.88'E | 7°45.5.72'S | 39 | 0/150/260 | 2022-2024 | New site 2022 - P1 | Desa Ceporan Dusun Kebonagung RT.1 RW.3 kec. Gantiwarno, Kab. Klaten Prov. Jawa Tengah | NOKIA | JAW-JT-KLN-0930 | CEPORAN_KLATEN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Klaten | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-07 | W15-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 |  | 11 |  | 2022-03-08 | [6 empty] | CME | 36.PLN application | 20.SRFI | STR DONE | 28:04:22: RFI, WAIT RFIN 24:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-23:03:22: PLN CONNECTION & STR NY PARALEL 20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB, PARALEL STRENGTENING 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
NEW SPK |  | JAW-JT-KJN-1002 | 30736000031 | 143142104 | BLIGO_KAJ | BP2022 | SKP | 109°39.12.02'E | 6°55.59.16'S | 39 | 60/180/300 | 2022 | New site 2022 - P2 | Kel.Sapugarut Gang 1 RT.007 RW.003 Kec.Buaran, Kab.Pekalongan Prov. Jawa Tengah | NOKIA | JAW-JT-KJN-1002 | BLIGO_PEKALONGAN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Pekalongan | 6617984 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 |  | 11 |  | 2022-03-09 | [6 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: RFI, WAIT RFIN 24:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI, PLN CONENCTION 23:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
NEW SPK |  | JAW-JT-KRG-2154 | 30735780031 | 140161109 | GONILAN UTARA | BP2022 | TB | 110°46.5.99'E | 7°31.39.79'S | 26 | 0/120/240 | 2022-2024 | New site 2022 - P1 | Desa Gedongan - Tanon Lor RT.02 RW.01 Kec. Colomadu, Kab. Karanganyar Prov. Jawa Tengah | NOKIA | JAW-JT-KRG-2154 | GONILAN_UTARA | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Karanganyar | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-07 | W15-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 |  | 11 |  | 2022-03-09 | [6 empty] | CME | 36.PLN application | 20.SRFI | NEED STRENGTENING PARALEL, OVERBLAST | 28:04:22: RFI, WAIT RFIN 24:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-23:03:22: PLN CONNECTION 20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-20:02:22: NEED REVIEW CIVIL 16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
|  | JAW-JI-PMK-4238 | 30740030031 | 1655131003 | PALENGAAN_REK_KERREK | BP2022 | TB | 113°26.49.63'E | 7°5.26.06'S | 50 | 0/120/240 | 2022 | Newsite 2022 - P1 | Dsn Mor Oloh RT 003 RW 004 Desa Rek Kerrek Kec. Palengaan Kab. Pamekasan Prov. Jawa Timur | HTI | JAW-JI-PMK-4238 | PALENGAAN_REK_KERREK | B2S | TBG | East | JATIM | Jawa Timur | Kab. Pamekasan | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-04-11 | 2022-04-13 |  |  |  | 2022-04-14 | [6 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: SRFI 24:04:22: ERECTION 20:04:22-17:04:22: CURRING TIME 13:04:22: EXCAVATION 10:04:22-30:03:22: REKOM 27:03:22-23:03:22: IW CLEAR 20:03:22-16:03:22: IW OG 15:03:22-14:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED | apr | 401 | 388 TBG
NEW SPK B2S |  | JAW-JI-JBG-5135 | 30730420031 | 1654801003 | PERAK_PLOSOGENUK | BP2022 | TB | 112°10.32.56'E | 7°32.9.06'S | 50 | 75/235/300 | 2022 | New site 2022 - P2 | RT 03 RW 01 Dusun Karangasem Desa Karangdagangan Kec. Bandar Kedungmulyo Kab. Jombang | HTI | JAW-JI-JBG-5135 | PERAK_PLOSOGENUK | B2S | TBG | East | JATIM | Jawa Timur | Kab. Jombang | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-07 | 2022-03-15 |  |  |  | 2022-04-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22-24:04:22: SRFI 20:04:22-17:04:22: CURRING TIME 13:04:22-10:04:22: REBARRING 03:04:22: SOIL TETS OG 30:03:22-20:03:22: REALISASI IW 16:03:22-28:02:22: IW CLEAR 23:02:22-22:02:22: IW OG 20:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr | 401 | 388 TBG
NEW SPK |  | KAL-KS-MTP-1117 | 30734200031 | T002435 | HCPTSK034-172402 | BP2022 | SKP | 114°51.19.8'E | 3°25.25.54'S | 30 | 80/225/315 | 2022 | New site 2022 - P2 | Jl. Irigasi Tanjung Rema Barat, Kec. Martapura, Kab.Banjar Baru | HTI | KAL-KS-MTP-1117 | TANJUNG_REMA_DARAT_MARTAPURA | COLO | TBG | Central | KALIMANTAN | Kalimantan Selatan | Kab. Banjar | 6617983 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 |  |  |  | 2022-03-21 |  | 2022-03-21 |  |  |  |  | CME | 37.Power connection process | 20.SRFI | NEED STRENGTENING PARALEL | 28:04:22: RFI 29 24:04:22-21:03:22: SRFIN 20:03:22: ME OG, PARALEL STRENGTENING 16:03:22-09:03:22: BTS PONDASI OG PARALEL STRENGTENING 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
NEW SPK |  | SUM-SU-MDN-2234 | 30734720031 | 0225632007 | IBS KRAKATAU UJUNG | BP2022 | TB | 98°40.39.54'E | 3°38.5.44'N | 40 | 90/210/280 | 2022 | New site 2022 - P1 | Gg. Mufakat No. 5, Jl. Perwira, Lingkungan VIII, Kelurahan Pulo Brayan Bengkel, Kecamatan Medan Timur, Kota Medan, Provinsi Sumatera Utara | HTI | SUM-SU-MDN-2234 | PB_BENGKEL_BARU | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kota Medan | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 | [6 empty] | CME | 31.RBS/BTS Foundation | 17.RBS/BTS FOUNDATION OG | NEED STRENGTENING PARALEL & COMMCASE | 28:04:22: PROSES PONDASI 24:04:22-20:04:22: COMMCASE 17:04:22-30:03:22: PONDASI OG & PERKUATAN 27:03:22-23:03:22: CONTINUE CME 20:03:22-09:03:22: BTS PONDASI OG, PARALEL STRENGTENING, COMCASE 06:03:22-13:02:22: READY TO STO 09:02:22-07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
89 COLO |  | SUM-SU-GNT-1543 | 30741770031 | 21273109 | BATUTAMBUN | BP2022 | TB | 99°35.56.76'E | 1°31.2.39'N | 50 | 120/200/290 | 2022 | Newsite 2022 - B2 | Desa Batu Tambun, Gunung Tua,Paluta.Sumut | HTI | SUM-SU-GNT-1543 | PAGARAN_SINGKAM | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Padang Lawas Utara | 6618079 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-24 | 2022-03-25 |  |  |  | 2022-03-24 | [6 empty] | CME | 37.Power connection process | 20.SRFI | NEED STRENGTENING PARALEL | 28:04:22: RFI, WAIT RFIN 24:04:22-30:03:22: PONDASI OG & PERKUATAN PARALEL 27:03:22: PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr | 401 | 388 TBG
652 |  | JAW-JB-CKR-0068 | 30705690031 | 1274061003 | PONDOK UNGU PERMAI RELOCATION | RELOCATION | TB | 107°0.46.73'E | 6°10.46.81'S | 30 | 90/120/330 | 2021 | RELOCATION |  | EID | JAW-JB-CKR-0068 | Pondok Ungu Permai Relocation | B2S | TBG | JABO | JABODETABEK | Jawa Barat | Kota Bekasi | 6617601 | 2021-09-07 |  | 233 | > 150 days | 2022-02-04 | W06-2022 | Feb-2022 | 2021-12-20 | W52-2021 | Dec-2021 | 2022-02-04 | W06-2022 | Feb-2022 | 2022-05-05 | W19-2022 | May-2022 | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | PENOLAKAN WARGA | 28:04:22-23:03:22: IW OG 20:03:22-23:02:22: VALIDASI RNP TNP, KANDIDAT C REJECT WARGA, PARALEL IW 20:02:22: PLAN PENYELESAIAN HARI INI, PLAN B SUBMIT KANDIDAT ATLERNATIF 16:02:22: PLAN BERTEMU RW DAN SOSWAR TGL 17 13:02:22: PROSES MEDIASI DENGAN RW 09:02:22-23:01:22: PROCESS COLLECT DOKUMEN IW 19:01:22: OG IW CLEAR, FINALISASI IW 19 JAN 18:01:22: SUBMIT KANDIDAT D, GESER 15M DARI KANDIDAT C UNTUK MENGHINDARI WARGA YG KURANG SETUJU 16:01:22: IW FAILED, REHUNTING 12:01:22-09:01:22: ISSUE WARGA LUAR RADIUS, KARENA BERADA DI LAHAN CLUSTER, PLAN SOLVED 15 JAN 05:01:22-02:01:22: PLAN FINALISASI WARGA 6 JAN 22 29:12:21-26:12:21: IW OG 35KK 23:12:21: OG SURVEY IW 22:12:21: WAIT FEEDBACK VALIDASI TNP KANDIDAT C 21:12:21: VALIDASI RNP TNP KANDIDAT C KARENA KANDIDAT B REJECT WARGA, RNP OK 19:12:21-15:12:21: IW OG 8 KK (4 KK DKM, 2 KK PERUSAHAAN KECIL) 12:12:21: TNP OK, IW OG 08:12:21-07:12:21: RNP OK KANDIDAT B, TNP VALIDATION 06:12:21: RNP TNP VALIDATION 05:12:21-24:11:21: REJECT WARGA, REHUNTING OG, PLAN SUBMIT KANDIDAT 9 DEC 21:11:21: 2 KK SUDAH BISA DITEMUI, SUDAH ADA DISKUSI DGN RT RW, PLAN TTD DALAM MINGGU INI, YG 1 KK MASIH DICARI, PLAN IW CLEAR 25 NOV 21 17:11:21-14:11:21: IW OG, 1 KK PEMILIK RUKO SUDAH KETEMU, SISA 3 KK RUKO YANG BELUM KETEMU, POSISINYA DISEWA & YANG MENEMPATI RUKO TSB ADALAH PEGAWAI2NYA, PLAN 17 NOV 21 RT RT & TBG AKAN MENDATANGI KE 3 RUKO TSB, MAX NEXT WEEK IW CLEAR 10:10:21 - 23:10:21: IW OG, SOSWAR DONE, MASIH KURANG 4 KK PLAN CLEAR W2 NOV 20:10:21-13:10:21: VALIDASI DONE, IW OG, 23 KK PLAN SOSWAR 18 OCT, PLAN IW CLEAR END OF OKTOBER 06:10:21: UNDER REVIEW RNP XL PAK BUDI LUMANTO, KANDIDAT NEAR EXISTING 04:10:21-26:09:21: REHUNTING KANDIDAT SESUAI ARAHAN DARI TIM RNP XL, PLAN SUBMIT KANDIDAT MENUNGGU SURAT KERJASAMA DENGAN PASAR MODERN TERKAIT PEMANFAATAN LAHAN UNTUK PEMBANGUNAN TOWER 22:09:21: KANDIDAT DONE SUBMIT, UNDER REVIEW RNP 19:09:21: 15:09:21: SUBMIT KANDIDAT, REVIEW UNDER RNP 13:09:21: SPK RELEASED 7 SEP HUNTING OG |  | 401 | 388 TBG
|  | SUM-SU-LMP-2237 | 30741720031 | 227511023 | BATUBARA LIMAPULUH | BP2022 | TB | 99°25.36.98'E | 3°9.42.84'N | 50 | 130/220/340 |  | Newsite 2022 - B2 | JALAN LINTAS SUMATERA DUSUN I PT.PP LONDON SUMATERA DESA PERKEBUNAN DOLOK KECAMATAN LIMA PULUH KABUPATEN BATUBARA PROVINSI SUMATERA UTARA | HTI | SUM-SU-LMP-2237 | PERKEBUNAN_DOLOK | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Batu Bara | 6618121 | 2022-03-09 | 2022-03-09 | 50 | 31 - 60 days | 2022-04-08 | W15-2022 | Apr-2022 | TBD | TBD | TBD | 2022-05-08 | W20-2022 | May-2022 | 2022-05-08 | W20-2022 | May-2022 | MW | 2022-03-24 | 2022-03-25 |  |  |  | 2022-03-23 |  | 2022-04-04 |  |  |  |  | CME | 37.Power connection process | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: RFI, WAIT RFIN 24:04:22-04:03:22: SRFIN 03:04:22-30:03:22: PONDASI OG 27:03:22-23:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-PTI-1431 |  |  |  | X RELOC TBG | TB | 110°59.12.19'E | 6°31.44.26'S | 50 | 90/210/330 | 2022 | RELOCATION |  |  | JAW-JT-PTI-1431 | NGABLAK PATI RELOCATION | B2S | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Pati | 6618155 | 2022-03-28 | 2022-03-28 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [14 empty] | 04.Survey OG | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 30:03:22: MITRA ASSIGNMENT 28:03:22: SPK RECEIVED
|  | JAW-JT-PWD-0596 |  |  |  | X RELOC BY TP | TB | 110°52.45.95'E | 7°4.6.78'S | 70 | 90/210/330 |  |  |  | EID | JAW-JT-PWD-0596 | PUTAT PURWODADI RELOCATION | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Grobogan | 6618143 | 2022-03-22 | 2022-03-22 | 37 | 31 - 60 days | 2022-08-19 | W34-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 04.Survey OG | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 10:04:22-27:03:22: SURVEY OG 23:03:22-22:03:22: SPK RECEIVED
NEW SPK B2S |  | SUM-LA-KTB-1149 | 30729780031 | 1014571003 | ABUNG_TINGGI_ULAK_RENGAS | BP2022 | TB | 104°36.45.22'E | 4°52.48.11'S | 60 | 105/125/300 | 2022 | New site 2022 - P2 | Sari Rejo RT.004 RW.004 Desa Ulak Rengas Kecamatan Abung Tinggi Kabupaten Lampung Utara Provinsi Lampung | HTI | SUM-LA-KTB-1149 | ABUNG_TINGGI_ULAK_RENGAS | B2S | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Utara | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-13 | W20-2022 | May-2022 | 2022-05-13 | W20-2022 | May-2022 | MW | 2022-02-25 | 2022-03-02 |  |  |  | 2022-04-25 | [6 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-20:04:22: ERECTION 17:04:22-10:06:22: ERECTION HOLD 06:04:22: ERECTION 03:04:22-27:03:22: REBARRING 23:03:22-06:03:22: REKOM 28:02:22-23:02:22: IW CLEAR 20:02:22-16:02:22: IW OG 15:02:22-11:02:22: IW FAILED, NEW CANDIATE UNDER RNP TNP 09:02:22: IW OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK |  | SUM-SU-LMP-2233 | 30736180031 | 0226092001 | IBS TANJUNG GADING | BP2022 | TB | 99°20.42.5'E | 3°18.5.58'N | 50 | 60/190/270 | 2022 | New site 2022 - P2 | Jl. Medan - Kisaran KM.100 Simpang Benteng, Desa Sipare-pare, Kecamatan Air Putih, Kabupaten Batu Bara, Provinsi Sumatera Utara | HTI | SUM-SU-LMP-2233 | SEI_SUKA_TANJUNG_GADING | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Batu Bara | 6617992 | 2022-01-28 | 2022-01-28 | 67 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-01 | 2022-02-02 | 121160508259 |  |  | 2022-03-22 |  |  | 2022-04-05 |  |  |  | CME | 37.Power connection process | 20.SRFI | WAITING EXTEND TOWER, RFI&STR DONE | 28:04:22-05:04:22: RFIN but wait EXTEND (STR DONE, WAIT EXTEND) 03:04:22-23:03:22: SRFI, PLN CONNECTION 16:03:22: ME OG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL HUAWEI 13:02:22: NEED REVIEW TNP ALITA 09:02:22: RND NOK NEED 45 METER 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
NEW SPK |  | SUM-SU-MDN-2235 | 30734760031 | 0226272007 | IBS JL MAWAR | BP2022 | TB | 98°39.39.62'E | 3°39.46.74'N | 30 | 90/180/260 | 2022 | New site 2022 - P2 | Jl Mawar Link 27, Kelurahan Tanjung Mulia, Kecamatan Medan Deli, Kota Medan, Provinsi Sumatera Utara | HTI | SUM-SU-MDN-2235 | TANJUNG_MULIA_HILIR | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kota Medan | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 | [6 empty] | CME | 37.Power connection process | 20.SRFI | COMMCASE | 28:04:22-20:04:22: COMMCASE 17:04:22-30:03:22: PONDASI OG 27:03:22-23:03:22: CONTINUE CME 20:03:22-09:03:22: BTS PONDASI OG, PARALEL STRENGTENING, COMCASE 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
NEW SPK |  | SUM-LA-LIW-1097 | 30734430031 | 100238104 | BDR_BARU_LIWA | BP2022 | SMI | 104°3.7.2'E | 4°58.5.84'S | 65 | 95/170/350 | 2022 | New site 2022 - P2 | Jl. Raya Lintas Barat, Kec. Sukau, Kab. Lampung Barat Prov. Lampung | HTI | SUM-LA-LIW-1097 | SUKAU_BANDAR_BARU | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Barat | 6617990 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-02 | 2022-02-03 |  |  |  | 2022-03-22 |  | 2022-04-02 |  |  |  |  | CME | 36.PLN application | 20.SRFI | KWH KOSONG | 28:04:22-02:04:22: SRFIN 30:03:22: PLN 27:03:22-16:03:22: ME OG KWH KOSONG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-MPR-1276 | 30734280031 | 071388109 | DESA KARANG MENJANGAN | BP2022 | TB | 104°50.30.52'E | 3°56.56.54'S | 50 | 105/205/320 | 2022 | New site 2022 - P2 | Karang Menjangan RT.003 RW.002 Desa Karang Menjangan, Kec. Semendawai Timur, Kab. Ogan Komering Ulu Timur, Prov. Sumatra Selatan | HTI | SUM-SS-MPR-1276 | KARANG_MENJANGAN | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 |  | 2022-04-02 |  |  |  |  | CME | 36.PLN application | 20.SRFI | KWH KOSONG | 28:04:22-02:04:22: SRFIN 30:03:22: PLN 27:03:22-20:03:22: ME OG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JI-PMK-4239 | 30740020031 | 1655121003 | TLANAKAN_MANGAR | BP2022 | TB | 113°23.27.36'E | 7°11.39.09'S | 50 | 30/160/270 | 2022 | Newsite 2022 - P1 | Dusun Klerker RT 001 RW 003 Desa Mangar Kec. Tlanakan Kab. Pamekasan Prov. Jawa Timur | HTI | JAW-JI-PMK-4239 | TLANAKAN_MANGAR | B2S | TBG | East | JATIM | Jawa Timur | Kab. Pamekasan | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-04-11 | 2022-04-13 |  |  |  | 2022-04-12 | [6 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: SRFI 24:04:22: ME OG 20:04:22-17:04:22: CURRING TIME 13:04:22: EXCAVATION 10:04:22-03:04:22: REKOM OG 30:03:22-25:03:22: IW OG 23:03:22-14:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-MPR-1272 | 30734750031 | 071191109 | SEMENDAWAI SUKU III | BP2022 | TB | 104°41.13.67'E | 4°0.42.7'S | 60 | 80/220/295 | 2022 | New site 2022 - P2 | Jl. Taman Harjo RT 003 RW 002 Desa Taman Harjo Kecamatan Semendawai Suku III, Kab. Oku Timur | HTI | SUM-SS-MPR-1272 | TAMAN_HARJO | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | KWH KOSONG | 28:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 08:02:22: NEED REVIEW TNP ALITA 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-MPR-1259 | 30734310031 | 070813109 | TERUKIS RAHAYU OKUT | BP2022 | TB | 104°19.43.54'E | 4°17.36.13'S | 40 | 45/130/245 | 2022 | New site 2022 - P2 | Jl. Merdeka, Kel. Sungai Tuha Jaya RT 01 RW 01, Kec. Martapura, Kab. OKU Timur Prov. Sumatera Selatan | HTI | SUM-SS-MPR-1259 | SUNGAI_TUHA_JAYA | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | KWH KOSONG | 28:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-16:02:22: STO RECALL 13:02:22-09:02:22: CME PREPARATION 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22-02:02:22: NEED REVIEW TNP ALITA 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-MPR-1270 | 30734190031 | 070159104 | TUGUMULYO_BELITANG | BP2022 | SKP | 104°37.21.5'E | 4°4.36.44'S | 65 | 50/180/350 | 2022 | New site 2022 - P2 | Jl. Tugumulyo, RT/RW 02/07, Kec. Belitang Madang Raya, Kab. OKU Timur, Propinsi Sumatra Selatan | HTI | SUM-SS-MPR-1270 | BELITANG_MADANG_RAYA_TUGU_MULYO | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617983 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | KWH KOSONG | 28:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-MPR-1268 | 30734250031 | 070139104 | TUGUMULYO_BELITANG | BP2022 | SKP | 104°39.1.87'E | 4°4.50.38'S | 60 | 100/180/350 | 2022 | New site 2022 - P2 | Jl. Tugumulyo, RT/RW 02/07, Kec. Belitang Madang Raya, Kab. OKU Timur, Propinsi Sumatra Selatan | HTI | SUM-SS-MPR-1268 | TULUS_AYU | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617983 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | KWH KOSONG | 28:04:22-30:03:22: PLN 27:03:22-23:03:22: ME OG 20:03:22-16:03:22: ME OG, WAIT STO 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | JAW-JT-PBG-1223 | 30735950031 | 140733104 | KARANGREJA | BP2022 | SMI | 109°20.44.77'E | 7°13.15.56'S | 70 | 60/230/300 | 2022 | New site 2022 - P2 | Desa Gondang RT 03/01, Kec. Karangreja, Kab. Purbalingga Prov. Jawa Tengah | NOKIA | JAW-JT-PBG-1223 | PURBALINGGA_KARANGREJA | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Purbalingga | 6617989 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-23 | W17-2022 | Apr-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-02 | 2022-03-14 |  | 11 |  | 2022-03-09 | [6 empty] | CME | 36.PLN application | 20.SRFI | STR DONE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI & STR NY PARALEL 23:03:22-20:03:22: ME OG 16:03:22-09:03:22: PONDASI OG & PERKUATAN 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
921 |  | JAW-JB-CKR-0069 |  |  |  | X RELOC TBG |  | 107.0728 | 6.2053 | 50 | 30/100/190/280 |  |  |  | EID | JAW-JB-CKR-0069 | VILLA MUTIARA TAMBUN RELOCATION | B2S | TBG | JABO | JABODETABEK (INNER) | Jawa Barat | Bekasi | 6614861 | 2020-07-07 |  | 660 | > 150 days | 2020-12-04 | W49-2020 | Dec-2020 | 2020-12-03 | W49-2020 | Dec-2020 | 2020-12-03 | W49-2020 | Dec-2020 | 2020-12-03 | W49-2020 | Dec-2020 | MW | [13 empty] | 04.Survey OG | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 03.08.20 : Hunting by Asset (Reloc TBG)
922 |  | JAW-JK-CKG-0723 |  |  |  | X RELOC TBG |  | 106.8475 | -6.3428 | 31 | 90/210/330 |  |  |  | EID | JAW-JK-CKG-0723 | GARUDA KALISARI RELOCATION | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | Jakarta Timur | 6614901 | 2020-07-21 |  | 646 | > 150 days | 2020-12-18 | W51-2020 | Dec-2020 | 2020-12-10 | W50-2020 | Dec-2020 | 2020-12-17 | W51-2020 | Dec-2020 | 2020-12-17 | W51-2020 | Dec-2020 | MW | [5 empty] | 2022-03-09 | [7 empty] | 05.Hunting OG | 04.HUNTING | CURRENTLY NO ISSUE | 0
NEW SPK B2S |  | SUL-SN-MSB-1555 | 30730320031 | 2817601003 | SALULEMO_SUKAMAJU | BP2022 | TB | 120°29.16.48'E | 2°35.51.76'S | 60 | 1/90/260 | 2022 | New site 2022 - P2 | Dusun Mattirowalie, Desa Saptamarga, Kec. Sukamaju, Kab. Luwu Utara Prop. Sulawesi Selatan | HTI | SUL-SN-MSB-1555 | SALULEMO_SUKAMAJU | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Luwu Utara | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-20 | W21-2022 | May-2022 | 2022-05-20 | W21-2022 | May-2022 | MW | 2022-02-25 | 2022-03-02 |  |  |  | 2022-03-25 | [6 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: PLN 20:04:22-13:04:22: CURRING 10:04:22-30:03:22: REBARRING 27:03:22-20:03:22: BOUWPLANK 16:03:22-09:03:22: RFC, CME PREPARATION 06:03:22: WAIT APD, SOIL TEST DONE 28:02:22-20:02:22: REKOM OG 16:02:22: IW CLEAR 13:02:22: IW OG 09:02:22: VALIDASI RNP TNP OG 08:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
919 |  | JAW-JT-SGN-1843 | 30596580031 | 142776104 | PLUPUH - RELOC | X ACTIVE - RELOCATION (By Asset 2019) | SMI | [6 empty] | Desa Sambirejo Kp. Sambirejo RT.13 Kec. Plupuh, Kab. Sragen Prov. Jawa Tengah | EID | JAW-JT-SGN-1843 | PLUPUH SRAGEN RELOCATION | COLO |  | CENTRAL | JATENG |  |  | 6614108 | 2019-08-12 |  | 990 | > 150 days | 2019-09-11 | W37-2019 | Sep-2019 |  |  |  | TBD | TBD | TBD |  |  |  | MW | [13 empty] | 05.Hunting OG | 04.HUNTING | CURRENTLY NO ISSUE | 0
|  | JAW-JB-CMS-4296 | 30739750031 | 1276871003 | NASOL | BP2022 | TB | 108°17.9.6'E | 7°16.13.26'S | 50 | 160/250/340 | 2022 | Newsite 2022 - B2 | Dusun Sigung 1 RT.34 RW.11 Desa Nasol Kec. Cikoneng Kab. Ciamis | HTI | JAW-JB-CMS-4296 | NASOL | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Ciamis | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-05-20 | W21-2022 | May-2022 | 2022-05-20 | W21-2022 | May-2022 | MW | 2022-04-10 | 2022-04-11 |  |  |  | 2022-04-20 | [6 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-20:04:22: ERECTION 17:04:22: POURING 13:04:22: REBARRING 10:04:22: REKOM 06:04:22-15:03:22: IW OG 13:03:22: VALIDASI RNP TNP 12:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-NPH-4382 | 30739900031 | 1276941003 | LEMBANG_CIBODAS | BP2022 | TB | 107°40.3.94'E | 6°49.37.2'S | 50 | 0/90/270 | 2022 | Newsite 2022 - P1 | Kp. Sukamulya Rt. 001 Rw. 002 Desa. Cibodas Kec. Lembang Kab Bandung Barat Provinsi Jawa Barat | HTI | JAW-JB-NPH-4382 | LEMBANG_CIBODAS | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Bandung Barat | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-05-20 | W21-2022 | May-2022 | 2022-05-20 | W21-2022 | May-2022 | MW | 2022-04-11 | 2022-04-13 |  |  |  | 2022-04-20 | [6 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERECTION 20:04:22: CURRING 17:04:22: REBARRING 13:04:22: BOUWPLANK 10:04:22: REKOM 06:04:22-27:03:22: IW OG 23:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SA-TNN-0433 | 30730620031 | 2405961003 | MAKALISUNG_KOMBI | BP2022 | TB | 125°1.57.67'E | 1°16.55.66'N | 60 | 40/130/260 | 2022 | New site 2022 - P2 | Jaga I Desa Makalisung Kec. Kombi Kab. Minahasa Prov. Sulawesi Utara | HTI | SUL-SA-TNN-0433 | MAKALISUNG_KOMBI | B2S | TBG | East | SULAWESI | Sulawesi Utara | Kab. Minahasa | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-20 | W21-2022 | May-2022 | 2022-05-20 | W21-2022 | May-2022 | MW | 2022-02-25 | 2022-03-02 |  |  |  | 2022-03-28 | [6 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERECTION 20:04:22-17:04:22: PREPARE ERECTION 13:04:22-10:04:22: CURRING 06:04:22-20:03:22: REBARRING 16:03:22-06:03:22: WAIT APD, SOIL TEST DONE 28:02:22: REKOM DONE 23:02:22-20:02:22: REKOM OG 16:02:22: IW CLEAR 13:02:22: IW OG 09:02:22: VALIDASI RNP TNP OG 08:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | BAL-BA-GIN-1493 | 30730680031 | 1719131003 | GIANYAR RELOCATION | RELOCATION | TB | 115°20.33.76'E | 8°32.19.71'S | 40 | 110/240/320 | 2022 | RELOCATION - XL | Lingk. Samplangan RT./RW. -/- Kel. Samplangan Kec. Gianyar | CAA | BAL-BA-GIN-1493 | GIANYAR RELOCATION | B2S | TBG | EAST | BALINUSRA | Bali | Kab. Gianyar | 6618002 | 2022-01-31 | 2022-01-31 | 87 | 61 - 90 days | 2022-06-30 | W27-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-31 | 2022-04-01 | MG | [5 empty] | 2022-04-28 |  |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 28:04:22: RFIN 24:04:22: PLN OG 20:04:22-14:04:22: ERECTION 10:04:22: BACKFILL 06:04:22-03:04:22: EXCAVATION 30:03:22: BOUWPLANK 27:03:22-11:03:22: SUBMIT KANDIDAT B UNDER RNP & TNP 09:03:22-14:02:22: VALIDASI RNP TNP, PARALEL IW 13:02:22-02:02:22: SURVEY OG 31:01:22: SPK RELEASED |  | 406 | 393 TBG
|  | JAW-JI-JMR-5132 | 30739870031 | 1655091003 | SILO_SUMBERJATI | BP2022 | TB | 113°52.30.0'E | 8°11.7.87'S | 50 | 115/220/300 | 2022 | Newsite 2022 - P1 | Dusun Krajan RT 02 RW 09,Desa Sumberjati Kecamatan Silo Kabupaten Jember | HTI | JAW-JI-JMR-5132 | SILO_SUMBERJATI | B2S | TBG | East | JATIM | Jawa Timur | Kab. Jember | 6618108 | 2022-03-07 | 2022-03-07 | 51 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-04-11 | 2022-04-13 | mg |  |  | 2022-04-22 |  |  | 2022-04-27 |  |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 27:04:22: RFIN 24:04:22: ERECTON 20:04:22-18:04:22: POURING 13:04:22: EXCAVATION 10:04:22-03:04:22: SOIL TEST OG 30:03:2: IW CLEAR 27:03:22-25:03:22: VALIDASI RNP TNP 23:03:22-17:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED | apr | 406 | 393 TBG
|  | JAW-JI-NGW-3683 | 30740060031 | 1655151003 | KENDAL_SIDOREJO | BP2022 | TB | 111°17.21.66'E | 7°33.0.65'S | 50 | 65/170/315 | 2022 | Newsite 2022 - P2 | Dusun Playaran RT 04 RW 05 Desa Kendal Kecamatan Kendal Kab Ngawi Prov Jatim | HTI | JAW-JI-NGW-3683 | KENDAL_SIDOREJO | B2S | TBG | East | JATIM | Jawa Timur | Kab. Ngawi | 6618108 | 2022-03-07 | 2022-03-07 | 51 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | mg |  |  | 2022-04-08 |  |  | 2022-04-27 |  |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 27:04:22: RFIN 24:04:22: SRFI 20:04:22-17:04:22: ME 13:04:22-10:04:22: ERECTION 06:04:22: CURRING 03:04:22-30:03:22: REBARRING 27:03:22: EXCAVATION 23:03:22-20:03:22: REKOM DONE, SOIL TEST DONE, WAIT APD 16:03:22: IW OG 16:03:22:-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED | apr | 406 | 393 TBG
|  | JAW-YO-BTL-0136 | 30721690031 | 1510031003 | SONOSEWU RELOCATION | RELOCATION | TB | 110°20.42.03'E | 7°48.35.55'S | 30 | 90/210/330 | 2021 | RELOCATION - PROTELINDO | Nitiprayan RT 001 RW – Kelurahan Ngestiharjo Kapanewon Kecamatan Kasihan Kabupaten Bantul Provinsi DIY | EID | JAW-YO-BTL-0136 | SONOSEWU RELOCATION | B2S | TBG | CENTRAL | JATENG | DI Yogyakarta | Kab. Bantul | 6617886 | 2021-12-16 |  | 133 | 121 - 150 days | 2022-05-15 | W21-2022 | May-2022 | TBD | TBD | TBD | 2022-03-28 | W14-2022 | Mar-2022 | 2022-05-20 | W21-2022 | May-2022 | MW | 2022-02-21 | [11 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: IW OG 20:04:22-19:04:22: VALIDASI 17:04:22: IW OG 13:04:22-06:04:22: EXCAVATION 03:04:22-30:03:22: BOUWPLANK 27:03:22-16:03:22: IW OG 15:03:22-15:03:22: VALIDASI KANDIDAT E 13:03:22-23:02:22: IW OG 21:02:22: COMCASE WARGA LUAR RADIUS, UNDER VALIDASI RNP TNP 20:02:22-16:02:22: PREPARE CME 13:02:22-26:01:22: REKOM OG 23:01:22: IW CLEAR, WAITING IW REALIZATION 19:01:22: REJECT WARGA KANDIDAT B, KANDIDAT C APPROVED IW CLEAR 16:01:22: IW OG (KURANG 3 KK) 12:01:22-10:01:22: TNP RNP KANDIDAT B OK, IW OG 09:01:22: IW FAILED, OG VALIDATION NEW CANDIDATE 05:01:22-26:12:21: IW OG 23KK (16 KK DONE, 10 KK OG) 23:12:21: UNDER TNP REVIEW, TNP OK, CONTINUE TO CP PROCESS 22:12:21: REVIEW RNP TNP OG 19:12:21-16:12:21: NEW SPK B2S |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SN-PLP-1342 | 30730610031 | 2817641003 | BUNTU_AWO'_WALENRANG_UTARA | BP2022 | TB | 120°8.3.49'E | 2°47.0.09'S | 60 | 0/10/280 | 2022 | New site 2022 - P2 | Desa Marabuana, Kec. Walenrang Utara , Kab. Luwu Prov. Sulawesi Selatan | HTI | SUL-SN-PLP-1342 | BUNTU_AWO'_WALENRANG_UTARA | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Luwu | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-20 | W21-2022 | May-2022 | 2022-05-20 | W21-2022 | May-2022 | MW | 2022-02-25 | 2022-03-02 |  |  |  | 2022-04-07 | [6 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22-24:04:22: RFI, WAIT RFIN 20:04:22-13:04:22: CURRING 10:04:22-06:04:22: BACKFILLING 03:04:22-20:03:22: REBARRING 16:03:22-06:03:22: WAIT APD, SOIL TEST DONE 28:02:22-23:02:22: REKOM OG 20:02:22: IW CLEAR 16:02:22-13:02:22: IW OG 09:02:22: RNP TNP OG -> IW OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUM-SU-LBP-2263 | 30744850031 | 21220109 | SUMBER_MELATI_DISKI | BP2022 | TB | 98°32.30.12'E | 3°36.21.24'N | 41 | 80/190/320 | 2022 | Newsite 2021 - H2 | Jl. Serba Jadi, Desa Sumber Melati Diski, Kec. Sunggal, Kab. Deli Serdang, Prov. Sumatera Utara | HTI | SUM-SU-LBP-2263 | SUNGGAL_SEI_SEMAYANG | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6618173 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-05-05 | W19-2022 | May-2022 | TBD | TBD | TBD | 2022-05-25 | W22-2022 | May-2022 | 2022-05-25 | W22-2022 | May-2022 |  | 2022-04-10 | 2022-04-11 |  |  |  | 2022-04-19 | [6 empty] | RFC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22-20:04:22: PREPARE CME 19:04:22: STO DECLARE 17:04:22-10:04:22: ERM PROCESS 06:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-SS-PLG-1244 | 30747830031 | 70516109 | KOLONEL ARDIAN PLG | BP2022 | SKP | 104°43.44.4'E | 2°55.58.37'S | 30 | 20/110/180 | 2022 | Newsite 2021 | Jl. Sukarela No. 674 RT 012 / 004 Kel. Sukarami, Kec. Sukarami, Kota Palembang, Prop. Sumsel | HTI | SUM-SS-PLG-1244 | SUKARAMI_SUKAJAYA | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kota Palembang | 6618172 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-05-05 | W19-2022 | May-2022 | TBD | TBD | TBD | 2022-05-25 | W22-2022 | May-2022 | 2022-05-25 | W22-2022 | May-2022 |  | need rev alamatsite 10 apr 22 | 2022-04-13 |  |  |  | 2022-04-19 | [6 empty] | CME | 31.RBS/BTS Foundation | 17.RBS/BTS FOUNDATION OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: PONDASI OG 20:04:22: PREPARE CME 19:04:22: STO DECLARE 17:04:22-10:04:22: ERM PROCESS 06:04:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK |  | SUL-SN-BAR-1314 | 30734400031 | 2815082001 | IBS PASAR PIKAE | BP2022 | TB | 119°39.46.22'E | 4°11.56.83'S | 60 | 70/210/340 | 2022 | New site 2022 - P2 | Dusun Lanrae, Desa Nepo, Kecamatan Mallusetasi, Kabupaten Barru, Provinsi Sulawesi Selatan | HTI | SUL-SN-BAR-1314 | NEPO_MALLUSETASI | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Barru | 6617991 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-05-25 | W22-2022 | May-2022 | MW | 2022-02-02 | 2022-02-03 |  |  |  | 2022-03-21 | [6 empty] | CME | 37.Power connection process | 20.SRFI | NEED STRENGTENING PARALEL, OVB | 28:04:22-24:04:22-30:03:22: PLN 27:03:22-13:03:22: PARALEL STRENGTENING 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
NEW SPK |  | JAW-JT-BYL-0260 | 30735810031 | 1442672010 | IBS ZSLO_0909 | BP2022 | TB | 110°41.45.6'E | 7°28.12.79'S | 39 | 50/180/300 | 2022-2024 | New site 2022 - P1 | Desa Jagoan - Karang Pilang RT.005 RW.001 Kec.Sambi, Kab.Boyolali Prov. Jawa Tengah | NOKIA | JAW-JT-BYL-0260 | BOYOLALI_SAMBI | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Boyolali | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-07 | W15-2022 | Apr-2022 | 2022-05-27 | W22-2022 | May-2022 | MW | 2022-02-02 | 2022-03-14 |  | 11 |  | 2022-03-08 | [6 empty] | CME | 36.PLN application | 20.SRFI | STR DONE, OVERBLAST | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-23:03:22: PLN CONNECTION 20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-20:02:22: NEED REVIEW CIVIL 16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
NEW SPK |  | JAW-JT-BTG-0230 | 30736080031 | 1433422001 | MILINGAN BATANG | BP2022 | TB | 109°44.34.22'E | 6°53.36.1'S | 45 | 60/180/300 | 2022-2024 | New site 2022 - P1 | Desa Klidang Lor RT.02 RW.02, Kec. Batang, Kab. Batang Prov. Jawa Tengah | NOKIA | JAW-JT-BTG-0230 | MILINGAN_BATANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Batang | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-22 | W17-2022 | Apr-2022 | 2022-05-27 | W22-2022 | May-2022 | MW | 2022-02-02 | 2022-03-14 |  | 11 |  | 2022-03-08 | [6 empty] | CME | 36.PLN application | 20.SRFI | STR DONE, OVERBLAST | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-06:04:22: SRFI & STR 03:04:22: ME OG & PERKUATAN 30:03:22-09:03:22: COMMCASE & PERKUATAN 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
NEW SPK |  | JAW-JT-KJN-0997 | 30735980031 | 141235109 | PEKAJANGAN | BP2022 | SKP | 109°39.13.97'E | 6°56.58.88'S | 50 | 90/190/280 | 2022 | New site 2022 - P1 | Gang 7 Pekajangan, Kec. Kedungwuni, Kab. Pekalongan, Prov. Jawa Tengah | NOKIA | JAW-JT-KJN-0997 | PEKAJANGAN_PEKALONGAN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Pekalongan | 6617984 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-05-27 | W22-2022 | May-2022 | MW | 2022-02-02 | 2022-03-14 |  | 11 |  | 2022-03-09 | [6 empty] | CME | 36.PLN application | 20.SRFI | OVB | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI, PLN CONENCTION 23:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr | 401 | 388 TBG
|  | SUL-SN-MKS-1582 | 30743210031 | 2814762004 | IBS MKS_TDDINFILL_43 | BP2022 | TB | 119°30.36.83'E | 5°7.47.17'S | 30 | 110/180/325 | 2022 | Newsite 2021 - H2 | Jl. Satelit 3 No.87 Telkomas RT.004 RW.006, Kelurahan Paccerakkang (dahulu kelurahan Daya), Kecamatan Biringkanaya, Kota Makassar, Provinsi Sulawesi Selatan | HTI | SUL-SN-MKS-1582 | KOTIPA_RAYA_PACCERAKKANG | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kota Makassar | 6618173 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-05-05 | W19-2022 | May-2022 | TBD | TBD | TBD | 2022-05-30 | W23-2022 | May-2022 | 2022-05-30 | W23-2022 | May-2022 |  | 2022-04-10 | 2022-04-11 |  |  |  | 2022-04-11 | 2022-05-26 | [5 empty] | CME | 31.RBS/BTS Foundation | 17.RBS/BTS FOUNDATION OG | NEED STRENGTENING (NY PARALEL) & COMMCASE | 28:04:22-24:04:22: COMMCASE 20:04:22-17:04:22: PONDASI OG 13:04:22: MOBDEMOB 12:04:22: STO 11 APR 10:04:22-06:05:22: RNP NOK FAR FROM NOM 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JI-BJN-4309 | 30739950031 | 1655101003 | MALO_KEDUNGREJO | BP2022 | TB | 111°42.36.0'E | 7°5.59.64'S | 50 | 90/140/300 | 2022 | Newsite 2022 - P2 | Tinawun RT 006 RW 003 Desa Tinawun Kec. Malo Kab. Bojonegoro Prov. Jawa Timur | HTI | JAW-JI-BJN-4309 | MALO_KEDUNGREJO | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-05-30 | W23-2022 | May-2022 | 2022-05-30 | W23-2022 | May-2022 | MW | 2022-04-11 | 2022-04-13 |  |  |  | 2022-04-20 | [6 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: SRFI 24:04:22: ERECTION 20:04:22-17:04:22: CURRING TIME 13:04:22: EXCAVATION 10:04:22-03:04:22: REKOM OG 30:03:22-23:03:22: IW OG 20:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-MRE-1237 | 30735420031 | 0717562001 | IBS DESA SIDOMULYO | BP2022 | TB | 103°53.34.8'E | 3°29.52.55'S | 60 | 35/130/220 | 2022 | New site 2022 - P2 | Desa Fajar Indah, Kecamatan Gunung Megang, Kabupaten Muara Enim, Provinsi Sumatera Selatan | HTI | SUM-SS-MRE-1237 | PAJAR_INDAH | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Muara Enim | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-31 | W23-2022 | May-2022 | 2022-05-31 | W23-2022 | May-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | NEED STRENGTENING (NY PARALEL) | 28:04:22-06:04:22: PLN & STR 03:04:22: ME OG & STRENGTENING 30:03:22-27:03:22: STRENGTENING 23:03:22-20:03:22: ME OG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: RND NOK NEED 60 METER 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SN-BAR-1313 | 30730170031 | 2817551003 | LALABATA_TANETE_RILAU | BP2022 | TB | 119°35.15.46'E | 4°31.6.68'S | 60 | 20/110/210 | 2022 | New site 2022 - P1 | DUSUN ALUPPANGNGE RT 02 DESA CORAWALI KECAMATAN TANETE RILAU KABUPATEN BARRU PROPINSI SULAWESI SELATAN | HTI | SUL-SN-BAR-1313 | LALABATA_TANETE_RILAU | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Barru | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-31 | W23-2022 | May-2022 | 2022-05-31 | W23-2022 | May-2022 | MW | 2022-03-02 | 2022-03-18 |  |  |  | 2022-04-14 | [6 empty] | CME | 26.Back Filling | 14.POURING CONCRETE OG | CURRENTLY NO ISSUE | 28:04:22: BACKFILL 24:04:22: CURRING 20:04:22-13:04:22: REBARRING 10:04:22-06:04:22: BOUWPLANK 03:04:22-23:03:22: PROSES PERIZINAN 20:03:22-28:02:22: REKOM OG 23:02:22-16:02:22: IW OG 13:02:22-09:02:22: IW OG 07:02:22: REVIEW RNP TNP OG, RNP OK KANDIDAT AC, PRIORITY A, IW OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | KAL-KS-PLI-1113 | 30740970031 | 2209891003 | BENTOK_DARAT_BATI_BATI | BP2022 | TB | 114°50.20.4'E | 3°34.7.68'S | 60 | 20/155/270 | 2022 | Newsite 2022 - B2 | Jl Krasik RT 002 RW 001, Desa Bentok Darat, Kecamatan Bati-bati, Kabupaten Tanah Laut , Propinsi Kalimantan Selatan | HTI | KAL-KS-PLI-1113 | BENTOK_DARAT_BATI_BATI | B2S | TBG | East | KALIMANTAN | Kalimantan Selatan | Kab. Tanah Laut | 6618133 | 2022-03-17 | 2022-03-17 | 42 | 31 - 60 days | 2022-08-14 | W34-2022 | Aug-2022 | TBD | TBD | TBD | 2022-05-31 | W23-2022 | May-2022 | 2022-05-31 | W23-2022 | May-2022 | MW | 2022-04-26 |  |  |  |  | 2022-04-20 | [6 empty] | CME | 27.Curring Time | 15.CURRING TIME | CURRENTLY NO ISSUE | 28:04:22: CURRING 24:04:22: REBARRING 20:04:22-18:04:22: EXCAVATION 17:04:22-13:04:22: MOBDEMOB 10:04:22-04:04:22: REKOM 03:04:22-23:03:22: SURVEY OG 20:03:22: MITRA ASSIGNMENT 17:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-BKN-1168 | 30730000031 | 0416611003 | RIMBA_BERINGIN | BP2022 | TB | 100°55.11.27'E | 0°37.52.13'N | 50 | 90/270/350 | 2022 | New site 2022 - P2 | Desa Sukaramai Kecamatan Tapung Hulu Kabupaten Kampar Provinsi Riau | HTI | SUM-RI-BKN-1168 | RIMBA_BERINGIN | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Kampar | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-31 | W23-2022 | May-2022 | 2022-05-31 | W23-2022 | May-2022 | MW | 2022-02-25 | 2022-03-03 |  |  |  | 2022-04-22 | [6 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-14:03:22: BACKFILLING 10:04:22: REBARRING 06:04:22: EXCAVATION 03:04:22-27:03:22: LAND CLEARING & BOUWPLANK 23:03:22-16:03:22: RFC 13:03:22-09:03:22: REKOM OG 06:03:22-28:02:22: IW CLEAR 23:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-BT-PDG-0619 | 30729590031 | 1323081003 | MEKARWANGI_SODONG | BP2022 | TB | 105°58.48.72'E | 6°24.39.52'S | 50 | 20/170/270 | 2022 | New site 2022 - P2 | Kp. Ganjur Desa SODONG, RT 07 RW 04, Kec Saketi Pandeglang Banten | EID | JAW-BT-PDG-0619 | MEKARWANGI_SODONG | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Pandeglang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-31 | W23-2022 | May-2022 | 2022-05-31 | W23-2022 | May-2022 | MW | 2022-03-31 | 2022-04-05 |  | 6.6 |  | 2022-04-27 | [6 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-17:04:22: PREPARE ERECTION 13:04:22: POURING 10:04:22-03:04:22: EXCAVATION 30:03:22: BOUWPLANK 27:03:22-20:03:22: LAND CLEARING 16:03:22-28:02:22: REKOM OG 23:02:22: IW CLEAR & PARALEL COLLECT DOKUMEN 22:02:22: IW OG 20:02:22: UNDER RNP TNP 16:02:22-13:02:22: REHUNTING RNP NOK 09:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-BKN-1170 | 30730100031 | 0416641003 | KIJANG_REJO | BP2022 | TB | 101°2.56.4'E | 0°43.50.71'N | 50 | 0/130/240 | 2022 | New site 2022 - P2 | Jalan Kenari RT.02 RW.01 Dusun I Sidomukti, Desa Kijang Rejo, Kecamatan Tapung, Kabupaten Kampar, Provinsi Riau | HTI | SUM-RI-BKN-1170 | KIJANG_REJO | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Kampar | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-31 | W23-2022 | May-2022 | 2022-05-31 | W23-2022 | May-2022 | MW | 2022-03-21 | 2022-03-23 |  |  |  | 2022-04-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: PLN 24:04:22: ERECTION 20:04:22: BACKFILL 17:04:22: REBARRING 13:04:22-10:04:22: BOREPILE 06:04:22: EXCAVATION 03:04:22-27:03:22: LAND CLEARING & BOUWPLANK 23:03:22-20:03:22: MOBDEMOB 16:03:22: REKOM OG 13:03:22-09:03:22: IW CLEAR 06:03:22-01:02:22: IW OG 28:02:22: UNDER RNP TNP 23:02:22-16:02:22: REHUNTING 13:02:22-11:02:22: VALIDASI RNP TNP 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JK-KYB-0296 | 30729190031 | 1136811003 | SAWO_KECI_BUKIT_DURI | BP2022 | TB | 106°51.27.67'E | 6°13.18.23'S | 25 | 70/210/320 | 2022-2024 | New site 2022 - P1 | Jalan Sawo Kecik I RT 001 RW 007, Kelurahan Bukit Duri, Kecamatan Tebet, Jakarta Selatan, DKI Jakarta | EID | JAW-JK-KYB-0296 | SAWO_KECI_BUKIT_DURI | B2S | TBG | Jabodetabek | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Selatan | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-31 | W23-2022 | May-2022 | 2022-05-31 | W23-2022 | May-2022 | MW | need revised nama PM | 2022-04-14 |  | 6.6 | 2022-04-20 | 2022-04-27 | [6 empty] | CME | 37.Power connection process | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: SRFI 24:04:22: PONDASI OG 20:04:22: ERECTION 17:04:22-13:04:22: CURRING 10:04:22-06:04:22: REBARRING 03:04:22-27:03:22: EXCAVATION 27:03:22-25:03:22: PROPOSE MCP 23:03:22-20:03:22: EXCAVATION OG 16:03:22-06:03:22: REKOM OG 28:02:22: IW CLEAR & PARALEL COLLECT DOC 23:02:22-16:02:22: IW OG 13:02:22-03:02:22: VALIDASI RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-DUM-1155 | 30729880031 | 0416561003 | KELURAHAN_LUBUK_GAUNG | BP2022 | TB | 101°20.25.61'E | 1°46.19.02'N | 50 | 10/90/190 | 2022 | New site 2022 - P2 | Jalan Raya Mampu Jaya Kelurahan Lubuk Gaung RT 019 Kecamatan Sungai Sembilan Kota Dumai Provinsi Riau | HTI | SUM-RI-DUM-1155 | KELURAHAN_LUBUK_GAUNG | B2S | TBG | West | SUMBAGTENG | Riau | Kota Dumai | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-31 | W23-2022 | May-2022 | 2022-05-31 | W23-2022 | May-2022 | MW | 2022-02-25 | 2022-03-03 |  |  |  | 2022-04-22 | [6 empty] | CME | 26.Back Filling | 14.POURING CONCRETE OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: BACKFILL 20:04:22-13:04:22: CURRING 10:04:22: REBARRING 06:04:22: EXCAVATION 03:04:22-27:03:22: LAND CLEARING & BOUWPLANK 23:03:22: RFC 20:03:22-09:03:22: REKOM OG 06:03:22-28:02:22: IW CLEAR 23:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-BTA-1097 | 30736300031 | 071437109 | BELIMBING | BP2022 | TB | 104°18.49.54'E | 3°57.42.73'S | 60 | 5/190/315 | 2022 | New site 2022 - P2 | Dusun IV, Desa Durian, Kec. Peninjauan, Kab. Ogan Komering Ulu, Prov. Sumatera Selatan | HTI | SUM-SS-BTA-1097 | PENINJAUAN_DURIAN | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | NEED STRENGTENING (NY PARALEL) | 28:04:22-06:04:22: SRFI & STR 03:04:22: ME OG & STRENGTENING 30:03:22-27:03:22: STRENGTENING 23:03:22-09:03:22: BTS PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW POWER 13:02:22-09:02:22: RND NOK NEED 50 METER 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-BTA-1092 | 30736290031 | 071403109 | SUKA PINDAH OKU | BP2022 | TB | 104°29.45.6'E | 3°47.5.64'S | 50 | 50/120/200 | 2022 | New site 2022 - P2 | Dusun IV RT.000 RW.000 Desa Suka Pindah, Kec. Kedaton Peninjauan Raya, Kab. Ogan Komering Ulu, Prov. Sumatera Selatan | HTI | SUM-SS-BTA-1092 | SUKA_PINDAH | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | NEED STRENGTENING (NY PARALEL) | 28:04:22-30:03:22: PLN & STR NY PARALEL (WAITING PERMIT STR) 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW POWER 13:02:22-09:02:22: RND NOK NEED 50 METER 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-MPR-1286 | 30741710031 | 71476109 | API_KARANG MANIK BELITANG | BP2022 | TB | 104°48.29.41'E | 4°2.22.16'S | 50 | 30/210/260 | 2022 | New site 2022 - P2 | Karang Manik Belitang RT 009 RW 002 Desa Karang Manik Kec. Belitang II Kab. OKU TIMUR Prov. Sumatera Selatan | HTI | SUM-SS-MPR-1286 | KARANG_MANIK | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 | [6 empty] | CME | 31.RBS/BTS Foundation | 17.RBS/BTS FOUNDATION OG | NEED STRENGTENING (NY PARALEL) & RND NOK: NEED 50M | 28:04:22-03:04:22: PONDASI OG & PERKUATAN 30:03:22-23:03:22:PREPARE CME 20:03:22: READY TO DECLARE STO, REPALACE GM TO SST 52 09:03:22:NEED REVIEW CIVIL EID 06:03:22: NEED REVIEW TNP 23:02:22-09:02:22: RND NOK NEED 50 METER 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-RPT-1107 | 30735080031 | 070073104 | REMBAN | BP2022 | SKP | 102°49.1.2'E | 2°38.41.71'S | 60 | 110.250/350 | 2022 | New site 2022 - P2 | Simpang Desa, Desa Lubuk Kemang Lama, Kec. Rawas Ulu, Kab. Musi Rawas Utara, Sumsel | HTI | SUM-SS-RPT-1107 | LUBUK_KEMANG | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas Utara | 6617983 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 |  | 2022-04-02 |  |  |  |  | CME | 36.PLN application | 20.SRFI | KWH KOSONG | 28:04:22-02:04:22: SRFIN 30:03:22: PLN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22-07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-RPT-1103 | 30735040031 | 070144109 | E_LUBUK LINGGAU UTARA-0 | BP2022 | SKP | 102°44.45.6'E | 2°38.2.4'S | 60 | 40/250/330 | 2022 | New site 2022 - P2 | Kampung limo , Desa Sungai Baung, Kec. Rawas Ulu, Kab. Lubuk Linggau | HTI | SUM-SS-RPT-1103 | SUNGAI_BAUNG | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas Utara | 6617983 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 |  | 2022-04-05 |  |  |  |  | CME | 36.PLN application | 20.SRFI | KWH KOSONG | 28:04:22-05:04:22: SRFIN 03:04:22-30:03:22: PLN 27:03:22-16:03:22: ME OG KWH KOSONG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW POWER HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JB-CMS-4289 | 30739940031 | 1276971003 | NAGARAJAYA | BP2022 | TB | 108°24.44.24'E | 7°7.41.5'S | 50 | 105/240/320 | 2022 | Newsite 2022 - B2 | Dusun Gardu RT19 RW 05 Desa Nagarapageuh Kec Panawangan Kab Ciamis | HTI | JAW-JB-CMS-4289 | NAGARAJAYA | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Ciamis | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-04-10 | 2022-04-11 |  |  |  | 2022-04-21 | [6 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-20:04:22: POURING 17:04:22: REBARRING 13:04:22: BOUWPLANK 10:04:22: REKOM 06:04:22-22:03:22: IW OG 21:03:22: VALIDASI RNP TNP 20:03:22: REHUNTING 16:03:22-12:03:22: VALIDASI RNP TNP -> RNP NOK, REHUNTING 13:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-SOR-4418 | 30740460031 | 1277041003 | PAMOYANAN_LEBAK | BP2022 | TB | 107°41.38.35'E | 6°52.46.49'S | 50 | 125/255/355 | 2022 | Newsite 2022 - B2 | Sekesalam RT 001 RW 008 Desa Sindanglaya Kecamatan Cimenyan Kabupaten Bandung | HTI | JAW-JB-SOR-4418 | PAMOYANAN_LEBAK | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Bandung | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-04-10 | 2022-04-11 |  |  |  | 2022-04-21 | [6 empty] | CME | 25.Pouring Concrete | 14.POURING CONCRETE OG | KKOP ISSUE | 28:04:22: POURING 24:04:22: EXCAVATION 20:04:22-10:04:22: REKOM (KKOP ISSUE) 06:04:22-27:03:22: REKOM OG 23:03:22-15:03:22: IW OG 13:03:22: VALIDASI RNP TNP 12:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-BTA-1084 | 30734070031 | 071064109 | SUMSEL2014_2G15 | BP2022 | TB | 104°28.37.6'E | 3°54.6.44'S | 65 | 75/185/270 | 2022 | New site 2022 - P2 | Jl. Poros, Blok G Dsn. III, Ds. Tanjung Makmur, Kab. Ogan Komering Ulu, Prov. Sumatera Selatan | HTI | SUM-SS-BTA-1084 | TANJUNG_MAKMUR | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 |  | 2022-03-27 |  |  |  |  | CME | 37.Power connection process | 20.SRFI | KWH KOSONG | 28:04:22-27:03:22: SRFIN 23:03:22: SRFI 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-BTA-1096 | 30734040031 | 071401109 | PENINJAUAN 2 | BP2022 | TB | 104°24.38.63'E | 3°51.36.14'S | 50 | 60/160/255 | 2022 | New site 2022 - P2 | Dusun IV RT.002 Desa Saung Naga, Kec. Peninjauan, Kab. Ogan Komering Ulu, Prov. Sumatera Selatan | HTI | SUM-SS-BTA-1096 | SAUNG_NAGA | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 |  | 2022-03-27 |  |  |  |  | CME | 37.Power connection process | 20.SRFI | KWH KOSONG | 28:04:22-27:03:22: SRFIN 23:03:22: SRFI 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-BTA-1085 | 30735520031 | 070141109 | LUBUK TANJUNG | BP2022 | SKP | 104°18.29.41'E | 3°48.26.6'S | 65 | 5/130/225 | 2022 | New site 2022 - P2 | Jl. Blok F, Desa Mekartijaya, Kec. Peninjauan, Kab. Ogan Komering Ulu, Prov. Sumatera Selatan | HTI | SUM-SS-BTA-1085 | PENINJAUAN_MAKARTI_JAYA | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu | 6617983 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 |  | 2022-03-27 |  |  |  |  | CME | 37.Power connection process | 20.SRFI | KWH KOSONG | 28:04:22-27:03:22: SRFIN 23:03:22: SRFI 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-BE-CRP-0192 | 30734860031 | 090285101 | KARANG ANYAR PAL VIII | BP2022 | TB | 102°28.26.4'E | 3°22.24.78'S | 40 | 115/215/320 | 2022 | New site 2022 - P2 | Jl. Lintas Curup - Muara Aman, Gang Dahlia, Dusun I, Desa PAL VIII, Kec. Bermani Ulu Raya, Kab. Rejang Lebong Prov. Bengkulu | HTI | SUM-BE-CRP-0192 | BERMANI_ULU_RAYA_PALVIII | COLO | TBG | West | SUMBAGSEL | Bengkulu | Kab. Rejang Lebong | 6617991 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-02 | 2022-02-03 |  |  |  | 2022-03-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | KWH KOSONG | 28:04:22-30:03:22: PLN 27:03:22-16:03:22: ME OG KWH KOSONG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW POWER HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-MPR-1273 | 30734260031 | 071276109 | TAMAN AGUNG | BP2022 | TB | 104°39.43.16'E | 4°0.26.32'S | 65 | 70/170/270 | 2022 | New site 2022 - P2 | Kampung I, TR.01 / RW 01. Desa Mojorahayu, Kec. Semendawai Suku III, Kab. OKU Timur, Prov. Sumatera Selatan | HTI | SUM-SS-MPR-1273 | MARGODADI | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | KWH KOSONG | 28:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK |  | SUM-BE-CRP-0181 | 30734410031 | 090244109 | RIMBO RECAP | BP2022 | TB | 102°29.46.28'E | 3°30.6.23'S | 60 | 20/80/280 | 2022 | New site 2022 - P2 | Jl. Desa Puguk Lalang, Dusun I Desa Puguk Lalang, Kec. Curup Selatan, Kab. Rejang Lebong Prov. Bengkulu | HTI | SUM-BE-CRP-0181 | PUNGGUK_LALANG | COLO | TBG | West | SUMBAGSEL | Bengkulu | Kab. Rejang Lebong | 6617991 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-02 | 2022-02-03 |  |  |  | 2022-03-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | KWH KOSONG | 28:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 08:02:22: NEED REVIEW TNP ALITA 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SB-PLJ-0775 | 30730020031 | 0311141003 | EMPAT_KOTO_PULAU_PUNJUNG | BP2022 | TB | 101°30.26.15'E | 0°56.36.47'S | 50 | 10/200/270 | 2022 | New site 2022 - P2 | JORONG KUBANG PANJANG, NAGARI EMPAT KOTO PULAU PUNJUNG, KEC. PULAU PUNJUNG, KAB. DHARMASRAYA PROVINSI SUMATERA BARAT | HTI | SUM-SB-PLJ-0775 | EMPAT_KOTO_PULAU_PUNJUNG | B2S | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Dharmasraya | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-03-21 | 2022-03-23 |  |  |  | 2022-04-14 | [6 empty] | CME | 23.Bore pile Rebaring & Pouring | 11.BORE PILE OG | CURRENTLY NO ISSUE | 28:04:22-17:04:22: BOREPILE 13:04:22-10:04:22-20:03:22: MOBDEMOB 16:03:22: DESIGN OG 13:03:22-06:03:22: IW CLEAR 28:02:22-16:02:22: IW OG 13:02:22-11:02:22: VALIDASI RNP TNP 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK |  | SUM-SS-BTA-1093 | 30734060031 | 071402109 | DESA BUNGLAI | BP2022 | TB | 104°25.58.22'E | 3°50.29.18'S | 40 | 55/255/290 | 2022 | New site 2022 - P2 | Desa Bunglai RT.009, Desa Bunglai, Kec. Kedaton Peninjauan Raya, Kab. Ogan Komering Ulu, Prop. Sumatera Selatan | HTI | SUM-SS-BTA-1093 | BUNGLAI | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu | 6617992 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 |  |  |  | 2022-03-22 |  | 2022-03-27 |  |  |  |  | CME | 37.Power connection process | 20.SRFI | KWH KOSONG | 2804:22-27:03:22: SRFIN 23:03:22: SRFI 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SB-SRK-0944 | 30729940031 | 0311131003 | HARAU_LUBUAK_BATINGKOK | BP2022 | TB | 100°38.9.56'E | 0°10.11.14'S | 50 | 100/180/260 | 2022 | New site 2022 - P2 | Jorong Koto Tangah, Nagari Lubuak Batingkok, Kec.Harau, Kab.Lima Puluh Kota, Prov.Sumatera Barat | HTI | SUM-SB-SRK-0944 | HARAU_LUBUAK_BATINGKOK | B2S | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Lima Puluh Kota | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-25 | 2022-03-03 |  |  |  | 2022-04-14 | [6 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERECTION 20:04:22: CURRING 17:04:22: REBARRING 13:04:22-27:03:22: LAND CLEARING & BOUWPLANK 23:03:22-13:03:22: RFC 09:03:22: REKOM OG 06:03:22-28:02:22: IW CLEAR 23:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JB-MJL-4128 | 30739760031 | 1276881003 | MEKARRAHARJA | BP2022 | TB | 108°17.9.6'E | 6°58.27.73'S | 50 | 115/205/310 | 2022 | Newsite 2022 - B2 | Blok. Sukamandi Rt 02 Rw 01 Desa Mekarraharja Kecamatan Talaga Kab. Majalengka Propinsi Jawa Barat | HTI | JAW-JB-MJL-4128 | MEKARRAHARJA | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Majalengka | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-04-11 | 2022-04-13 |  |  |  | 2022-04-25 | [6 empty] | CME | 36.PLN application | 20.SRFI | WAIT SURVEY PLN | 28:04:22-24:04:22: ERECTION 20:04:22: POURING 17:04:22-13:04:22: EXCAVATION 10:04:22: REKOM 06:04:22-15:03:22: IW OG 13:03:22: VALIDASI RNP TNP 12:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | SUM-JA-MRT-0213 | 30741780031 | 60103104 | BETUNG_BEDARAH | BP2022 | SMI | 102°39.40.18'E | 1°33.40.79'S | 55 | 20/100/290 | 2022 | Newsite 2022 - B2 | Desa Betung Berdarah Timur Rt 015 Rw 004, Kec. Tebo Ilir, Kab. Tebo, Prov. Jambi | HTI | SUM-JA-MRT-0213 | BETUNG_BEDARAH_TIMUR | COLO | TBG | West | SUMBAGSEL | Jambi | Kab. Tebo | 6618086 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-03-24 | 2022-03-25 |  |  |  | 2022-03-23 | [6 empty] | CME | 36.PLN application | 20.SRFI | NEED STRENGTENING PARALEL | 28:04:22-24:04:22: PLN 20:04:22-17:04:22: ME OG 13:04:22-07:04:22: PARALEL STR, PONDASI OG 06:04:22-04:04:22: COMMCASE 03:04:22: PONDASI OG & PERKUATAN 30:03:22-23:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-RI-PRP-1109 | 30740100031 | 0416941003 | RAMBAH_SAMO_MARGA_MULYA | BP2022 | TB | 100°22.52.62'E | 0°46.59.53'N | 60 | 0/90/150 | 2022 | Newsite 2022 - P2 | Dusun Mekar Sari Rt 012 Rw 004 Desa Marga Mulya Kecamatan Rambah Samo Kab. Rokan Hulu Provinsi Riau | HTI | SUM-RI-PRP-1109 | RAMBAH_SAMO_MARGA_MULYA | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Rokan Hulu | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-06-07 | W24-2022 | Jun-2022 | 2022-06-07 | W24-2022 | Jun-2022 | MW | 2022-04-10 | 2022-04-11 |  |  |  | 2022-04-22 | [6 empty] | CME | 23.Bore pile Rebaring & Pouring | 11.BORE PILE OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: BOREPILE 20:04:22-06:04:22: BOUWPLANK 03:04:22: REKOM 30:03:22-23:03:22: IW CLEAR 22:03:22: IW OG 20:03:22-13:03:22: VALIDASI RNP TNP OG 09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SN-BAN-0963 | 30730230031 | 2817561003 | BONTO_MACCINI_SINOA | BP2022 | TB | 119°55.28.33'E | 5°29.54.05'S | 60 | 40/150/320 | 2022 | New site 2022 - P2 | Desa Bonto Maccini Kec. Sinoa Kab. Bantaeng Prov. Sulawesi Selatan | HTI | SUL-SN-BAN-0963 | BONTO_MACCINI_SINOA | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Bantaeng | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-06-24 | W26-2022 | Jun-2022 | 2022-06-24 | W26-2022 | Jun-2022 | MW | 2022-02-25 | 2022-03-02 |  |  |  | 2022-03-23 | [6 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: RFI, WAIT RFIN 24:04:22: PLN 20:04:22-17:04:22: PREPARE ERECTION 13:04:22-06:04:22: CURRING 03:04:22-20:03:22: REBARRING 16:03:22-09:03:22: REKOM OG 06:03:22: IW OG 28:02:22: VALIDASI RNP TNP KANDIDAT BERGESER 45M 23:02:22: REKOM OG 20:02:22: IW CLEAR 16:02:22-13:02:22: IW OG 09:02:22: RNP TNP OG -> IW OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SN-PLP-1338 | 30733960031 | 2817691003 | LALONG_WALENRANG | BP2022 | TB | 120°7.53.92'E | 2°51.19.67'S | 60 | 50/140/310 | 2022-2024 | New site 2022 - P1 | Jl. Poros Palopo-Masamba Desa Lalong Kec. Walenrang Kab. Luwu Prop. Sulsel | HTI | SUL-SN-PLP-1338 | LALONG_WALENRANG | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Luwu | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-06-24 | W26-2022 | Jun-2022 | 2022-06-24 | W26-2022 | Jun-2022 | MW | 2022-03-07 | 2022-03-15 |  |  |  | 2022-03-22 | [6 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: RFI, WAIT RFIN 24:04:22-20:04:22: ERECTION 13:04:22-10:04:22: CURRING 06:04:22-03:04:22: CURRING 30:03:22: REBARRING 27:03:22-20:03:22: BOUWPLANK 16:03:22-06:03:22: WAIT APD, SOIL TEST DONE 28:02:22-23:02:22: REKOM OG 22:02:22: VALIDASI TNP RNP, IW FAILED 20:02:22: IW CLEAR 16:02:22-13:02:22: VALIDASI RNP TNP OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | BAL-BA-DPR-1520 | 30744890031 | 170852109 | IMANBONJOL2 | BP2022 | TB | 115°11.47.65'E | 8°41.33.76'S | 25 | 10/150/250 | 2022 | Newsite 2021 | Jl. Tukad Baru, Kepaon, Kota Denpasar Prov. Bali | HTI | BAL-BA-DPR-1520 | DENPASARSELATAN_PEMOGAN | COLO | TBG | East | BALINUSRA | Bali | Kota Denpasar | 6618173 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-05-05 | W19-2022 | May-2022 | TBD | TBD | TBD | 2022-07-25 | W31-2022 | Jul-2022 | 2022-07-25 | W31-2022 | Jul-2022 |  | 2022-04-10 | 2022-04-11 |  |  |  | 2022-04-20 | [6 empty] | RFC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | NEED STRENGTENING (NY PARALEL) | 28:04:22-24:04:22: STR ON GOING NY PARALEL 20:04:22: STO DECLARED, PERKUATAN NY ORDERED 20:04:22-10:04:22: ERM PROCESS 06:04:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | SUM-JA-BKO-0371 |  | 60478109 | PASAR ATAS BANGKO 2 | BP2022 | TB | 102°14.49.2'E | 2°5.55.97'S | 50 | 50/200/280 | 2022 | Newsite 2022 - B2 | Dusun Kungkai RT.11 Desa Kungkai Kec.Bangko Kab.Merangin Prov.Jambi | HTI | SUM-JA-BKO-0371 | BANGKO_KUNGKAI | COLO | TBG | West | SUMBAGSEL | Jambi | Kab. Merangin | 6618079 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-07-30 | W31-2022 | Jul-2022 | 2022-07-30 | W31-2022 | Jul-2022 | MW | 2022-03-24 | 2022-03-25 |  |  |  | 2022-04-11 | [6 empty] | NY STIP | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | EXTEND TOWER (NY PARALEL) | 28:04:22-17:04:22: EXTEND TOWER, WAIT PERMIT 13:04:22: MOBDEMOB 12:04:22: STO 11 APR 10:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-SS-MBL-1213 | 30744830031 | 71390109 | SUKARENA SUKAKARYA | BP2022 | TB | 103°13.58.8'E | 3°12.45.29'S | 60 | 40/210/300 |  | Newsite 2022 - P2 | Dusun Bhakti Mulya RT.002, Desa Sukarena, Kec. Sukakarya, Kab. Musi Rawas, Prov. Sumatera Selatan | HTI | SUM-SS-MBL-1213 | SUKARENA | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas | 6618111 | 2022-03-07 | 2022-03-09 | 52 | 31 - 60 days | TBD | TBD | TBD | TBD | TBD | TBD | 2022-07-30 | W31-2022 | Jul-2022 | 2022-07-30 | W31-2022 | Jul-2022 | MW | 2022-03-24 | 2022-03-25 |  |  |  | 2022-04-20 | [6 empty] | CME | 31.RBS/BTS Foundation | 17.RBS/BTS FOUNDATION OG | EXTEND TOWER (NY PARALEL) | 28:04:22-24:04:22: PONDASI OG 20:04:22: STO ANNOUNCE 13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | SUM-SU-GNT-1542 | 30743230031 | 21272109 | SIGAMA | BP2022 | TB | 99°37.49.44'E | 1°29.45.46'N | 40 | 60/170/280 | 2022 | Newsite 2022 - B2 | Jl. Lintas Simp Portibi Desa saba tahul tahul Kec , Padang Bolak Kab Padang lawas utara | HTI | SUM-SU-GNT-1542 | SABA_BANGUNAN | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Padang Lawas Utara | 6618079 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-08-31 | W36-2022 | Aug-2022 | 2022-08-31 | W36-2022 | Aug-2022 | MW | 2022-03-24 | 2022-03-25 |  |  |  | 2022-04-12 | [6 empty] | RFC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | EXTEND TOWER (NY PARALEL) | 28:04:22-14:04:22: WAIT PERMIT EXTEND TOWER 3 M 13:04:22: STO DECLARE 10:04:22: RND NOK, NEED EXTEND TOWER 06:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK |  | JAW-JT-PWD-0044 | 30735820031 | 1441582004 | IBS LOGENDER | BP2022 | TB | 111°6.43.06'E | 7°8.5.28'S | 59 | 10/90/180 | 2022 | New site 2022 - P1 | Desa Tuko, Logender RT.001 RW.011 Kec. Pulokulon, Kab. Grobogan Prov. Jawa Tengah | NOKIA | JAW-JT-PWD-0044 | LOGENDER_GROBOGAN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Grobogan | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-02 | [11 empty] | CME | 36.PLN application | 20.SRFI | STR DONE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI & STR NY PARALEL 23:03:22: ME 20:03:22: WAIT PSB & NEED REVIEW POWER 13:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW RNP EID 07:02:22: SPK REEASED |  | 401 | 388 TBG
NEW SPK |  | JAW-JT-PWD-0046 | 30735840031 | 1442202007 | IBS IBS_PHASE 4C_1029_CJA | BP2022 | TB | 110°43.26.4'E | 7°4.39.32'S | 49 | 60/180/320 | 2022 | New site 2022 - P2 | Desa Latak RT.003 RW.002 Kec. Godong, Kab. Grobogan Prov. Jawa Tengah | NOKIA | JAW-JT-PWD-0046 | LATAK_GROBOGAN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Grobogan | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-02 | [11 empty] | CME | 36.PLN application | 20.SRFI | STR DONE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI & STR NY PARALEL 23:03:22: ME 20:03:22: WAIT PSB & NEED REVIEW POWER 13:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW RNP EID 07:02:22: SPK REEASED |  | 401 | 388 TBG
NEW SPK |  | JAW-JT-DMK-0620 | 30735830031 | 1443512004 | IBS KEDUNGWARU KIDUL | BP2022 | TB | 110°47.20.4'E | 6°49.32.74'S | 39 | 40/130/320 | 2022 | New site 2022 - P2 | Desa Kedungwaru kidul RT.05 RW.03 Kec. Karanganyar, Kab. Demak Prov. Jawa Tengah | NOKIA | JAW-JT-DMK-0620 | KEDUNGWARU_KIDUL | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Demak | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-02 | [11 empty] | CME | 36.PLN application | 20.SRFI | STR DONE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI & STR NY PARALEL 23:03:22: ME 20:03:22: WAIT PSB & NEED REVIEW POWER 13:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW RNP EID 07:02:22: SPK REEASED |  | 401 | 388 TBG
NEW SPK |  | JAW-JT-PWD-0045 | 30735880031 | 142754126 | RAYA BLORA-PURWODADI | BP2022 | TB | 111°7.8.62'E | 7°4.57.54'S | 30 | 30/120/270 | 2022-2024 | New site 2022 - P1 | Desa Dapurno Dusun Pengkol RT.003 Rw.005 Kec. Wirosari, Kab. Grobogan Prov. Jawa Tengah | NOKIA | JAW-JT-PWD-0045 | GROBOGAN_WIROSARI | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Grobogan | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-02 | [11 empty] | CME | 36.PLN application | 20.SRFI | STR DONE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI & STR NY PARALEL 23:03:22: ME 20:03:22: WAIT PSB & NEED REVIEW POWER 13:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW RNP EID 07:02:22: SPK REEASED |  | 401 | 388 TBG
|  |  |  | 1128271023 |  |  | TB | 106°42.55.48'E | 6°7.12.97'S | 25 | 90/210/330 |  |  |  | EID | JAW-JK-GGP-0440 | PERMATA_TEGAL_ALUR | COLO | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618221 | 2022-04-26 | 2022-04-26 | 2 | < 30 days | 2022-05-26 | W22-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 08.Under RNP review | 06.ERM PROCESS | NEED STRENGTENING (NY PARALEL) | 28:04:22: ESR PROCESS 26:04:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-BT-RKB-0762 |  | 131619109 | API_HARJAWANA | BP2022 | TB | 106°2.3.95'E | 6°28.40.8'S | 42 | 50/210/290 | 2022 | Newsite 2022 - B2 | Desa Gunungsari Kp. Cicadas RT.002 RW.002 Kec. Banjarsari, Kab. Lebak Prov. Banten | EID | JAW-BT-RKB-0762 | HARJAWANA_LEBAK | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | 2022-04-28 |  | 10.6 |  | 2022-04-27 | [6 empty] | NY STIP | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | NEED STRENGTENING (NY PARALEL) | 28:04:22: MOBDEMOB 24:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-BT-RKB-0760 |  | 131630109 | API_SARAGENICIMARGA | BP2022 | TB | 106°7.45.37'E | 6°27.10.69'S | 42 | 10/100/220 | 2022 | Newsite 2022 - B2 | Desa Jayasari Kp. Ranca Gede RT.009 RW.002 Kec. Cimarga, Kab. Lebak Prov. Banten | EID | JAW-BT-RKB-0760 | SARAGENI_CIMARGA | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | 2022-04-28 |  | 10.6 |  | 2022-04-27 | [6 empty] | NY STIP | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | NEED TOWER SST (NY PARALEL) | 28:04:22: MOBDEMOB 24:04:22-20:04:22: ESR PROCESS 17:04:22-16:03:22: ERM REJECTION 15:03:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-TMG-2681 | 30741470031 | 140839104 | BEJEN | BP2022 | SMI | 110°5.6.0'E | 7°7.6.67'S | 65 | 40/120/210/320 | 2022 | Newsite 2022 - B2 | Jl. Weleri - Parakan, RT. 4 / RW. 1 Dsn. Demangan, Ds. Bejen, Kec. Bejen, Kab. Temanggung Prov. Jawa Tengah | NOKIA | JAW-JT-TMG-2681 | BEJEN TEMANGGUNG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Temanggung | 6618090 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | NEED STRENGTENING (NY PARALEL) | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-JPA-0712 |  | 1441362004 | IBS BANDUNG MAYONG | BP2022 | TB | 110°47.2.4'E | 6°41.21.19'S | 69 | 40/120/250 | 2022 | Newsite 2022 - B2 | Desa Bandung RT.001 RW.001 Kec.Mayong, Kab.Jepara Prov. Jawa Tengah | NOKIA | JAW-JT-JPA-0712 | BANDUNG_MAYONG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Jepara | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | NEED STRENGTENING (NY PARALEL) | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-PWT-0590 |  | 1445332007 | IBS BATURADEN | BP2022 | TB | 109°14.27.6'E | 7°19.50.7'S | 49 | 40/200/290 | 2022 | Newsite 2022 - B2 | Desa Karang Salam RT.03 RW.01 Kec. Baturaden, Kab. Banyumas Prov. Jawa Tengah | NOKIA | JAW-JT-PWT-0590 | KARANGSALAM_BANYUMAS | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Banyumas | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | NEED STRENGTENING (NY PARALEL) | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-JPA-0710 | 30736040031 | 141681109 | WANUSOBO | BP2022 | SKP | 110°40.17.0'E | 6°41.3.62'S | 68 | 20/100/190 | 2022 | New site 2022 - P1 | Desa Sowan Lor Dusun Sowan Lor RT.10 RW.03 Kec.Kedung, Kab.Jepara Prov. Jawa Tengah | NOKIA | JAW-JT-JPA-0710 | SOWAN_LOR_JEPARA | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Jepara | 6618032 | 2022-02-08 | 2022-02-08 | 79 | 61 - 90 days | 2022-03-10 | W11-2022 | Mar-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-08 | [11 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-07:04:22: NO NEED STR 06:04:22-27:03:22: SRFI & STR NY PARALEL 23:03:22: ME 20:03:22-09:03:22: PONDASI OG 06:02:22-16:02:22: NEED REVIEW POWER 13:02:22-09:02:22: NEED REVIEW TNP HUAWEI 08:02:22: SPK RECEIVED 8 FEB 22 |  | 401 | 388 TBG
89 COLO |  | JAW-JT-SKH-1880 | 30741600031 | 141858109 | NGADIREJO KARTOSURO | BP2022 | TB | 110°45.6.41'E | 7°34.3.9'S | 34 | 40/160/310 | 2022 | Newsite 2022 - B2 | Desa Gumpang Dusun Sayangan RT.003 RW.001 Kec. Kartasura, Kab. Sukoharjo Prov. Jawa Tengah | NOKIA | JAW-JT-SKH-1880 | NGADIREJO_KARTOSURO | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Sukoharjo | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | NEED STRENGTENING (NY PARALEL) | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-PWD-0043 | 30741590031 | 1445112007 | IBS KALISARI | BP2022 | TB | 111°8.23.86'E | 7°8.3.01'S | 69 | 60/170/330 | 2022 | Newsite 2022 - B2 | Desa Kalisari Dukuh Pulorejo RT.01 RW.04 Kec. Kradenan, Kab. Grobogan Prov. Jawa Tengah | NOKIA | JAW-JT-PWD-0043 | KLAMPOK_PULOREJO | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Grobogan | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | NEED STRENGTENING (NY PARALEL) | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30733380031 | T002941 |  |  | SKP | 120°12.39.92'E | 3°5.32.1'S | 70 | 50/210/300 |  |  |  | HTI | SUL-SN-PLP-1344 | TIROMANDA_BUA | COLO | TBG | EAST | SULAWESI | Sulawesi Selatan | Kab. Luwu | 6618222 | 2022-04-26 | 2022-04-26 | 2 | < 30 days | 2022-05-26 | W22-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 07.ESR preparation | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22: ERM PROCESS 26:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30733390031 | 2816131023 |  |  | TB | 119°58.39.07'E | 4°19.51.67'S | 50 | 40/150/240 |  |  |  | HTI | SUL-SN-WNS-0979 | KELURAHAN_UJUNG_LILIRILAU | COLO | TBG | EAST | SULAWESI | Sulawesi Selatan | Kab. Soppeng | 6618223 | 2022-04-26 | 2022-04-26 | 2 | < 30 days | 2022-05-26 | W22-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22: ERM PROCESS 26:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30744080031 | 507011001 |  |  | TB | 103°55.30.83'E | 1°2.31.09'N | 41 | 110/240/340 |  |  |  | HTI | SUM-KR-BTM-0607 | BATU_AJI_TANJUNG_UNCANG | COLO | TBG | West | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6618223 | 2022-04-26 | 2022-04-26 | 2 | < 30 days | 2022-05-26 | W22-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22: ESR PROCESS 26:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-SU-TBT-2307 |  | 20612109 | KASAU | RELOCATION | TB | 99°9.50.94'E | 3°19.49.58'N | 30 | 90/200/310 |  |  | Jl. Datuk Bandar Kajum No. 20 Kelurahan Tebing TInggi lama Kecamatan Tebing Tinggi Kota | CAA | SUM-SU-TBT-2307 | TEBING TINGGI RELOCATION | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | Kota Tebing Tinggi | 6618182 | 2022-04-05 | 2022-04-06 | 23 | < 30 days | 2022-05-05 | W19-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 2022-04-10 | 2022-03-12 | [10 empty] | NY STIP | 09.Under TNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-10:04:22: ERM PROCESS 06:04:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-PTI-1429 | 30741580031 | 142764126 | PAGENDISAN WINONG | BP2022 | TB | 111°6.51.16'E | 6°47.47.18'S | 37 | 0/170/280 | 2022 | Newsite 2022 - B2 | Desa Tanggel RT.06 RW.02 Kec. Winong, Kab. Pati Prov. Jawa Tengah | NOKIA | JAW-JT-PTI-1429 | PANGENDISAN_WINONG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Pati | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-KLN-0932 | 30741540031 | 1436451023 | JUWIRING KLATEN | BP2022 | TB | 110°45.23.36'E | 7°40.4.51'S | 59 | 110/210/300 | 2022 | Newsite 2022 - B2 | Desa Tlogorandu Dusun Kemiri RT.03 RW.05 Kec. Juwiring, Kab. Klaten Prov. Jawa Tengah | NOKIA | JAW-JT-KLN-0932 | JUWIRING_KLATEN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Klaten | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-BNR-0271 | 30741480031 | 140549104 | BANJARNEGARATM | BP2022 | SMI | 109°43.23.74'E | 7°23.32.82'S | 43 | 70/150/320 | 2022 | Newsite 2022 - B2 | Jl. Tentara Pelajar, Kel. Sokanandi Rt.04 RW.02 Kec. Banjarnegara, Kab. Banjarnegara Prov. Jawa Tengah | NOKIA | JAW-JT-BNR-0271 | JALAN_TENTARA_PELAJAR | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Banjarnegara | 6618084 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-WNG-2764 | 30741610031 | 141132109 | GIRIWARNO WONOGIRI | BP2022 | TB | 111°4.5.77'E | 7°45.34.45'S | 60 | 60/180/300 | 2022 | Newsite 2022 - B2 | Desa Giriwarno, Ngluwak RT/RW:01/08, Kec. Girimarto, Kab. Wonogiri Prov. Jawa Tengah | NOKIA | JAW-JT-WNG-2764 | GIRIWARNO_WONOGIRI | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Wonogiri | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-TMG-2677 | 30741630031 | 140262104 | GONDANGWAYANG | BP2022 | SKP | 110°8.37.21'E | 7°14.42.68'S | 63 | 120/210/290 | 2022 | Newsite 2022 - B2 | Desa Gondang Wayang RT.07 RW.02 Kec. Kedu, Kab. Temanggung Prov. Jawa Tengah | NOKIA | JAW-JT-TMG-2677 | GONDANGWAYANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Temanggung | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-PWT-0585 | 30741490031 | 140781104 | PANUSUPAN_CILONGOK | BP2022 | SMI | 109°9.50.76'E | 7°26.56.51'S | 63 | 100/180/290 | 2022 | Newsite 2022 - B2 | Desa Panusupan RT.02 RW.01 Kec. Cilongok, Kab. Banyumas Prov. Jawa Tengah | NOKIA | JAW-JT-PWT-0585 | JALAN_RAYA_JATISABA | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Banyumas | 6618084 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-KLN-0925 | 30741500031 | 141089109 | TROSO KLATEN | BP2022 | TB | 110°38.53.88'E | 7°39.38.27'S | 60 | 0/90/210 | 2022 | Newsite 2022 - B2 | Desa Kunden Dukuh Mertan RT.08 RW.04 Kec. Karanganom, Kab. Klaten Prov. Jawa Tengah | NOKIA | JAW-JT-KLN-0925 | TROSO_KLATEN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Klaten | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-MKD-1124 |  | 140038109 | KRASAK | BP2022 | TB | 110°6.11.23'E | 7°33.32.0'S | 54 | 30/120/300 | 2022 | Newsite 2022 - B2 | Dsn Gejiwan, Desa Krasak, Kec. Salaman, Kab. Magelang Prov. Jawa Tengah | NOKIA | JAW-JT-MKD-1124 | KRASAK_MAGELANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-RBG-1780 |  | 1445372007 | IBS MANTINGAN | BP2022 | TB | 111°25.17.62'E | 6°51.50.83'S | 69 | 0/70/260 | 2022 | Newsite 2022 - B2 | Jl. Rembang - Blora, Desa Mantingan RT.02 RW.02 Kec. Bulu, Kab. Rembang Prov. Jawa Tengah | NOKIA | JAW-JT-RBG-1780 | REMBANG_BULU | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Rembang | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-KJN-1010 |  | 1436321023 | TALUN PEKALONGAN | BP2022 | TB | 109°43.53.33'E | 7°0.16.24'S | 49 | 90/260/340 | 2022 | Newsite 2022 - B2 | Desa Krompeng Dukuh Kemlaten RT.02 RW.03 Kec.Talun, Kab.Pekalongan Prov. Jawa Tengah | NOKIA | JAW-JT-KJN-1010 | TALUN_PEKALONGAN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Pekalongan | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-CLP-0559 |  | 1445451004 | KARANGTENGAH_SAMPANG | BP2022 | TB | 109°10.31.87'E | 7°33.53.93'S | 39 | 0/100/190 | 2022 | Newsite 2022 - B2 | Jl. Kantil, Desa Karangtengah RT.004 RW.012 Kec. Sampang, Kab. Cilacap Prov. Jawa Tengah | NOKIA | JAW-JT-CLP-0559 | KARANGTENGAH_SAMPANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Cilacap | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-BLA-0130 |  | 142761126 | JATIREJO JEPON | BP2022 | TB | 111°28.11.53'E | 6°55.20.1'S | 37 | 20/180/300 | 2022 | Newsite 2022 - B2 | Jl. Sayuran, Kel. Bacem RT.007 RW.001 Kec. Jepon, Kab. Blora Prov. Jawa Tengah | NOKIA | JAW-JT-BLA-0130 | JATIREJO_JEPON | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Blora | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-DMK-0622 |  | 140357109 | DESA MUTIH | BP2022 | TB | 110°39.22.14'E | 6°46.55.7'S | 65 | 120/210/280 | 2022 | Newsite 2022 - B2 | Jl. Dsn Jetak, Desa Mutih Kec. Wedung, Kab. Demak Prov. Jawa Tengah | NOKIA | JAW-JT-DMK-0622 | DESA_MUTIH_DEMAK | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Demak | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-KJN-0999 |  | 1433801001 | RANDUMUKTIWAREN | BP2022 | TB | 109°34.36.05'E | 6°57.36.4'S | 40 | 90/240/330 | 2022 | Newsite 2022 - B2 | Desa Purworejo Dk. Talok RT.001 RW.006 Kec. Sragi, Kab. Pekalongan Prov. Jawa Tengah | NOKIA | JAW-JT-KJN-0999 | RANDUMUKTIWAREN_PEKALONGAN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Pekalongan | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-SLT-2135 |  | 1440712003 | IBS SMG_TDDINFILL_11 | BP2022 | TB | 110°30.2.95'E | 7°20.47.44'S | 36 | 90/230/310 | 2022 | Newsite 2022 - B2 | Jl. Ringansari No.7, Kel. Tegalrejo RT.006 RW.04 Kec. Argomulyo, Kota Salatiga Prov. Jawa Tengah | NOKIA | JAW-JT-SLT-2135 | TEGALREJO KOTA SALATIGA | COLO | TBG | Central | JATENG | Jawa Tengah | Kota Salatiga | 6618089 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-SLT-2134 |  | 141867109 | YUDISTIRA SALATIGA | BP2022 | TB | 110°29.19.0'E | 7°20.31.67'S | 38 | 60/220/320 | 2022 | Newsite 2022 - B2 | Jl. Irawan No.74 Kr.Alit, Kel. Dukuh Rt.01 Rw.005 Kec. Sidomukti, Kota Salatiga Prov. Jawa Tengah | NOKIA | JAW-JT-SLT-2134 | DUKUH SIDOMUKTI | COLO | TBG | Central | JATENG | Jawa Tengah | Kota Salatiga | 6618089 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-KJN-0992 |  | 140460104 | KEBONSARI | BP2022 | SKP | 109°40.39.83'E | 6°57.56.02'S | 50 | 40/140/280 | 2022 | Newsite 2022 - B2 | Desa Kebonsari Kec.Karangdadap, Kab.Pekalongan Prov. Jawa Tengah | NOKIA | JAW-JT-KJN-0992 | KEBONSARI_PEKALONGAN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Pekalongan | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-CLP-0562 |  | 140220104 | SIDASARI | BP2022 | SKP | 108°45.41.29'E | 7°21.24.62'S | 66 | 40/140/290 | 2022 | Newsite 2022 - B2 | Desa Mulyasari RT01 RW13 Kec. Majenang, Kab. Cilacap Prov. Jawa Tengah | NOKIA | JAW-JT-CLP-0562 | SIDASARI_CILACAP | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Cilacap | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-KJN-1001 |  | 140462104 | ROGOSELO | BP2022 | SKP | 109°39.49.97'E | 7°2.53.88'S | 45 | 60/220/300 | 2022 | Newsite 2022 - B2 | Desa Rogoselo Dukuh Sawahan Kec.Doro, Kab.Pekalongan Prov. Jawa Tengah | NOKIA | JAW-JT-KJN-1001 | ROGOSELO_PEKALONGAN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Pekalongan | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-PBG-1222 |  | 140203104 | KRAMAT | BP2022 | SKP | 109°27.17.17'E | 7°16.3.4'S | 66 | 100/210/330 | 2022 | Newsite 2022 - B2 | Desa Tanjung Mulih Kp. Kramat RT.02 RW.01 Kec. Karangmoncol Kabupaten Purbalingga., Kab. Purbalingga Prov. Jawa Tengah | NOKIA | JAW-JT-PBG-1222 | KRAMAT_PURBALINGGA | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Purbalingga | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-UNR-2555 |  | T002834 | PLAUT | BP2022 | SKP | 110°36.33.77'E | 7°23.28.39'S | 56 | 0/120/250 | 2022 | Newsite 2022 - B2 | Desa Kuripan Dusun Krasak Sari RT.07 RW.07 Kec. Susukan, Kab. Semarang Prov. Jawa Tengah | NOKIA | JAW-JT-UNR-2555 | PLAUT_SEMARANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Semarang | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-BTG-0224 |  | 140294104 | BATIOMBO | BP2022 | SKP | 109°49.4.55'E | 7°0.21.85'S | 66 | 70/170/320 | 2022 | Newsite 2022 - B2 | Desa Kluwih Kec.Bandar, Kab.Batang Prov. Jawa Tengah | NOKIA | JAW-JT-BTG-0224 | BATIOMBO_BATANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Batang | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-RBG-1781 |  | 140228104 | TELOGODUWUR | BP2022 | SKP | 111°30.10.44'E | 6°51.14.76'S | 61 | 50/220/320 | 2022 | Newsite 2022 - B2 | Desa Tegaldowo Rt.11 RW./IIKec. Gunem, Kab. Rembang Prov. Jawa Tengah | NOKIA | JAW-JT-RBG-1781 | TELOGODUWUR_REMBANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Rembang | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-YO-WNO-0018 |  | 150036109 | JETIS SAPTOSARI | BP2022 | TB | 110°29.14.24'E | 8°2.7.8'S | 65 | 120/200/280 | 2022 | Newsite 2022 - B2 | Kel.Jetis Dusun Temanggung RT.04 RW.02 Kec.Saptosari, Kab.Gunung Kidul Prov. DI Yogyakarta | NOKIA | JAW-YO-WNO-0018 | JETIS SAPTOSARI | COLO | TBG | Central | JATENG | DI Yogyakarta | Kab. Gunungkidul | 6618089 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-KRG-2155 |  | 142677109 | KARANGANYAR4 | BP2022 | TB | 110°57.53.6'E | 7°36.2.05'S | 35 | 40/120/320 | 2022 | Newsite 2022 - B2 | Kel. Bejen - Tegalsari RT.005 RW.008 Kec. Karanganyar, Kab. Karanganyar Prov. Jawa Tengah | NOKIA | JAW-JT-KRG-2155 | CANGKANG_KARANGANYAR | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Karanganyar | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS,LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-KRG-2149 |  | 140261104 | JATIYOSO-TAWANGMANGU | BP2022 | SKP | 111°6.21.53'E | 7°41.26.41'S | 70 | 110/210/300 | 2022 | Newsite 2022 - B2 | Desa Beruk-Turus RT.002 RW.008 Kec. Jatiyoso, Kab. Karanganyar Prov. Jawa Tengah | NOKIA | JAW-JT-KRG-2149 | JATIYOSO_TAWANGMANGU | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Karanganyar | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: ESR PROCESS,LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-MKD-1125 | 30741520031 | 140043109 | SONOREJO | BP2022 | TB | 110°18.38.7'E | 7°28.58.08'S | 70 | 90/210/330 | 2022 | Newsite 2022 - B2 | Jl. Raya Desa Sonorejo, Kec. Candimulya, Kab. Magelang Prov. Jawa Tengah | NOKIA | JAW-JT-MKD-1125 | SONOREJO_MAGELANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-CLP-0564 | 30741510031 | 1443462004 | IBS CINYAWANG | BP2022 | TB | 108°45.28.04'E | 7°33.46.91'S | 39 | 120/200/340 | 2022 | Newsite 2022 - B2 | Desa Cinyawang Dusun Bangkirlega RT.003 RW.011 Kec. Patimuan, Kab. Cilacap Prov. Jawa Tengah | NOKIA | JAW-JT-CLP-0564 | CINYAWANG_CILACAP | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Cilacap | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-MKD-1141 | 30741620031 | 140278104 | SENDANGSONO | BP2022 | SKP | 110°14.33.32'E | 7°38.8.38'S | 70 | 30/120/300 | 2022 | Newsite 2022 - B2 | Desa Gleoran RT 02 RW 01 Kel. Sambeng, Kec. Borobudur, Kab. Magelang Prov. Jawa Tengah | NOKIA | JAW-JT-MKD-1141 | SENDANGSONO_MAGELANG_BOROBUDUR | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-YO-SMN-0075 | 30741530031 | 150255109 | MAGUWOHARJO 2 | BP2022 | TB | 110°26.16.58'E | 7°46.28.52'S | 27 | 0/120/240 | 2022 | Newsite 2022 - B2 | Jl. Sambilegi Lor, Kel.Maguwoharjo RT.07 RW.55 Kec.Depok, Kab.Sleman Prov. DI Yogyakarta | NOKIA | JAW-YO-SMN-0075 | MAGUWOHARJO_SLEMAN | COLO | TBG | Central | JATENG | DI Yogyakarta | Kab. Sleman | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-YO-WNO-0016 | 30741550031 | 1508281001 | WONODOYO | BP2022 | TB | 110°43.4.01'E | 7°57.11.7'S | 59 | 0/120/240 | 2022 | Newsite 2022 - B2 | Kel.Umbul Rejo - Silingi RT.006 RW.001 Kec.Ponjong, Kab.Gunung Kidul Prov. DI Yogyakarta | NOKIA | JAW-YO-WNO-0016 | WONODOYO_GUNUNGKIDUL | COLO | TBG | Central | JATENG | DI Yogyakarta | Kab. Gunungkidul | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-RBG-1773 | 30741560031 | 1441722004 | IBS KEPOHAGUNG PAMOTAN | BP2022 | TB | 111°25.19.2'E | 6°46.14.34'S | 59 | 30/170/290 | 2022 | Newsite 2022 - B2 | Desa Kepohagung RT.004 RW.001 Kec. Pamotan, Kab. Rembang Prov. Jawa Tengah | NOKIA | JAW-JT-RBG-1773 | KEPOHAGUNG_PAMOTAN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Rembang | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-KLN-0927 | 30741570031 | 140109109 | KALIMANGU TUGU (TEGALREJO KLATEN) | BP2022 | TB | 110°40.29.86'E | 7°46.20.78'S | 63 | 60/210/310 | 2022 | Newsite 2022 - B2 | Desa Gunung Gajah, Dusun Gamping, Kec. Bayat, Kab. Klaten Prov. Jawa Tengah | NOKIA | JAW-JT-KLN-0927 | KALIMANGU_TUGU_KLATEN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Klaten | 6618080 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-MKD-1128 | 30740720031 | 140274104 | PARIPURNO | BP2022 | SKP | 110°8.53.02'E | 7°36.48.74'S | 63 | 50/170/320 | 2022 | Newsite 2022 - B2 | Desa Paripurno, Kalisat RT.01 RW.05 Kec. Salaman, Kab. Magelang Prov. Jawa Tengah | NOKIA | JAW-JT-MKD-1128 | PARIPURNO_MAGELANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-MKD-1138 | 30740730031 | 140276104 | NGARGORETNO | BP2022 | SKP | 110°11.26.12'E | 7°37.9.01'S | 70 | 100/270/350 | 2022 | Newsite 2022 - B2 | Jl. Raya Karanganyar, Desa Karanganyar Dusun Ngadiwinata RT.02 RW.04 Kec. Borobudur, Kab. Magelang Prov. Jawa Tengah | NOKIA | JAW-JT-MKD-1138 | NGARGORETNO_MAGELANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | ESR | 10.Under PWR review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK |  | JAW-JT-CLP-0565 | 30735790031 | 1446482023 | IBS AMN | BP2022 | TB | 109°1.11.89'E | 7°42.13.07'S | 35 | 60/180/270 | 2022 | New site 2022 - P1 | Jl. Kendeng No. 307 RT. 07 RW. 15, Kelurahan Sidanegara, Kecamatan Cilacap Tengah, Kabupaten Cilacap, Provinsi Jawa Tengah | NOKIA | JAW-JT-CLP-0565 | JALAN_KENDENG_CILACAP | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Cilacap | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-02 | [11 empty] | CME | 36.PLN application | 20.SRFI | COMMCASE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI 23:03:22-16:03:22: COMCASE 13:03:22-09:03:22: PROSES IZIN KE LL 06:03:22-16:02:22: NEED REVIEW POWER 13:02:22-09:02:22: NEED REVIEW TNP HUAWEI 06:02:22-30:01:22: ESR REVIEW, NEED REVIEW RNP EID 28:01:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JT-BYL-0359 | 30736030031 | 1448111001 | NGADIROJO AMPEL | BP2022 | TB | 110°29.54.1'E | 7°25.7.72'S | 62 | 90/210/330 | 2022 | New site 2022 - P2 | DK Margosari RT 001 RW 06 Desa Ngadirojo Kecamatan Gladagsari Kabupaten Boyolali Provinsi Jawa Tengah | NOKIA | JAW-JT-BYL-0359 | BOYOLALI_AMPEL | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Boyolali | 6618025 | 2022-02-04 | 2022-02-07 | 83 | 61 - 90 days | 2022-03-06 | W11-2022 | Mar-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-08 | [11 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI, PLN 23:03:22: ME 20:03:22: WAIT PSB & NEED REVIEW POWER 13:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW RNP EID 07:02:22: SPK REEASED |  | 401 | 388 TBG
NEW SPK |  | JAW-JT-PWD-0048 | 30735850031 | 1433781001 | PEPETEGOWANU | BP2022 | TB | 110°39.14.54'E | 7°1.23.09'S | 39 | 60/150/320 | 2022 | New site 2022 - P2 | Desa Pepe Dusun Pepe Krajan RT.002 RW.002 Kec. Tegowanu, Kab. Grobogan Prov. Jawa Tengah | NOKIA | JAW-JT-PWD-0048 | PEPETEGOWANU_GROBOGAN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Grobogan | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-02 | [11 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI, PLN 23:03:22: ME 20:03:22-09:03:22: PONDASI OG 06:02:22-16:02:22: NEED REVIEW POWER 13:02:22-09:02:22: NEED REVIEW TNP HUAWEI 08:02:22: SPK RECEIVED 8 FEB 22 |  | 401 | 388 TBG
NEW SPK |  | JAW-JT-BTG-0234 | 30735860031 | 141853109 | DLISEN LIMPUNG | BP2022 | TB | 109°55.40.15'E | 7°0.29.09'S | 60 | 80/180/340 | 2022 | New site 2022 - P2 | Desa Babadan Dk.Banaran RT.01 RW.03 Kec.Limpung, Kab.Batang Prov. Jawa Tengah | NOKIA | JAW-JT-BTG-0234 | DLISEN_LIMPUNG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Batang | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-02 | [11 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI, PLN 23:03:22: ME 20:03:22-09:03:22: PONDASI OG 06:02:22-16:02:22: NEED REVIEW POWER 13:02:22-09:02:22: NEED REVIEW TNP HUAWEI 08:02:22: SPK RECEIVED 8 FEB 22 |  | 401 | 388 TBG
NEW SPK |  | JAW-JT-DMK-0625 | 30736070031 | 141144109 | TPI BONANG | BP2022 | TB | 110°33.11.48'E | 6°49.52.36'S | 34 | 110/230/310 | 2022-2024 | New site 2022 - P1 | Desa Morodemak RT.07 RW.02 Kec. Bonang, Kab. Demak Prov. Jawa Tengah | NOKIA | JAW-JT-DMK-0625 | BONANG_DEMAK | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Demak | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-02 | [11 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI, PLN 23:03:22: ME 20:03:22-09:03:22: PONDASI OG 06:02:22-16:02:22: NEED REVIEW POWER 13:02:22-09:02:22: NEED REVIEW TNP HUAWEI 08:02:22: SPK RECEIVED 8 FEB 22 |  | 401 | 388 TBG
|  | JAW-JT-TMG-2675 | 30736020031 | 1447521023 | NGUWET_KRANGGAN | BP2022 | TB | 110°13.55.16'E | 7°21.56.16'S | 62 | 90/210/330 |  | New site 2022 - P1 | TENGAHAN RT 003 RW 003 DESA NGUWET KECAMATAN KRANGGAN KABUPATEN TEMANGGUNG PROINSI JAWA TENGAH | NOKIA | JAW-JT-TMG-2675 | TEMANGGUNG_KRANGGAN | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Temanggung | 6618025 | 2022-02-04 | 2022-02-07 | 83 | 61 - 90 days | 2022-03-06 | W11-2022 | Mar-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-08 | [11 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI, PLN 23:03:22: ME 20:03:22-09:03:22: PONDASI OG 06:02:22-16:02:22: NEED REVIEW POWER 13:02:22-09:02:22: NEED REVIEW TNP HUAWEI 08:02:22: SPK RECEIVED 8 FEB 22 |  | 401 | 388 TBG
NEW SPK |  | JAW-JT-KJN-1009 | 30735870031 | 142914109 | API_PASIRSARI PEKALONGAN | BP2022 | TB | 109°37.33.67'E | 6°54.19.44'S | 50 | 60/180/300 | 2022 | New site 2022 - P2 | Jl. Parkit GG. 8, Kel. Dadirejo, Kec. Tirto, Kab. Pekalongan Prov. Jawa Tengah | NOKIA | JAW-JT-KJN-1009 | PASIRSARI_PEKALONGAN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Pekalongan | 6617993 | 2022-01-28 | 2022-01-28 | 90 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-02 | [11 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-30:03:22: PONDASI OG 27:03:22-09:03:22: MOBDEMOB, STACKING 06:03:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-BNR-0274 |  | 141644109 | RAKIT2 | BP2022 | SKP | 109°32.27.82'E | 7°25.47.42'S | 58 | 60/230/330 | 2022 | Newsite 2022 - B2 | Jl. Raya Adi Pasir, Desa Adi Pasir RT.01 RW.01 Kec. Rakit, Kab. Banjarnegara Prov. Jawa Tengah | NOKIA | JAW-JT-BNR-0274 | JALAN_RAYA_RAKIT | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Banjarnegara | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 08.Under RNP review | 06.ERM PROCESS | RND NOK: CHANGE DESIGN | 28:04:22-20:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-22:03:22: RND NOK: CHANGE DESIGN 20:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-MKD-1139 |  | 140282104 | TANGGULREJO | BP2022 | SKP | 110°8.6.79'E | 7°33.29.92'S | 41 | 70/200/340 | 2022 | Newsite 2022 - B2 | Jl. Desa Jengkeling RT 05 RW 04, Dusun Jengkeling, Desa Banjar Harjo Kec. Salaman, Kab. Magelang Prov. Jawa Tengah | NOKIA | JAW-JT-MKD-1139 | TANGGULREJO_MAGELANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 08.Under RNP review | 06.ERM PROCESS | RND NOK: CHANGE DESIGN | 28:04:22-20:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-22:03:22: RND NOK: CHANGE DESIGN 20:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
89 COLO |  | JAW-JT-MKD-1122 |  | 141222109 | PANDEKAN | BP2022 | SKP | 110°8.17.34'E | 7°24.42.08'S | 69 | 30/180/270 | 2022 | Newsite 2022 - B2 | Desa Wonoroto Dusun Krajan RT.01 RW.01 Kec. Windusari, Kab. Magelang Prov. Jawa Tengah | NOKIA | JAW-JT-MKD-1122 | PANDEKAN_MAGELANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6618083 | 2022-03-11 | 2022-03-11 | 48 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-20:04:22: ESR PROCESS, LMS CHANGE TO NOKIA 13:04:22-22:03:22: RND NOK: CHANGE DESIGN 20:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  |  | 1446411023 | BLORA RANDUBLATUNG | BP2022 | TB | 111°21.24.26'E | 7°10.37.45'S | 60 | 110/220/300 | 2022 | Newsite 2022 - B2 | Tlogo Rt 002-RW.001, Desa.Plosorejo, Kec. Randublatung, Kab. Blora. Provinsi Jawa Tengah | NOKIA | JAW-JT-BLA-0129 | BLORA_RANDUBLATUNG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Blora | 6618196 | 2022-04-07 | 2022-04-22 | 21 | < 30 days | 2022-05-07 | W19-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERM PROCESS 22:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-BB-KBA-0544 | 30739790031 | 0804421003 | LUBUK_PABRIK | BP2022 | TB | 106°38.52.22'E | 2°34.28.71'S | 50 | 50/240/340 | 2022 | Newsite 2022 - B2 | Jl. Saipul RT.003 Dusun II Desa Lubuk Pabrik, Kecamatan Lubuk Besar, Kabupaten Bangka Tengah, Provinsi Kepulauan Bangka Belitung. | HTI | SUM-BB-KBA-0544 | LUBUK_PABRIK | B2S | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kab. Bangka Tengah | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-31 | 2022-04-01 | [10 empty] | RFC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: APD 24:04:22: BOUPLANK 20:04:22-10:04:22: SOIL TEST 06:04:22: REKOM 03:04:22: IW OG 30:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | NUS-NB-SEL-5390 | 30739800031 | 1806921003 | AIKMEL_LENEK_LAUK | BP2022 | TB | 116°32.17.89'E | 8°35.42.64'S | 50 | 40/120/220 | 2022 | Newsite 2022 - B2 | Dusun Asmalang RT.04, Desa Lenek Lauk, Kec.Lenek, Kab. Lombok Timur, Prop. Nusa Tenggara Barat | HTI | NUS-NB-SEL-5390 | AIKMEL_LENEK_LAUK | B2S | TBG | East | BALINUSRA | Nusa Tenggara Barat | Kab. Lombok Timur | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 20.APD & Design Process | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: APD 24:04:22: REKOM OG 17:04:22: IW CLEAR 13:04:22-06:04:22: VALIDASI RNP TNP -> IW OG 03:04:22-18:03:22: IW OG 17:03:22: VALIDASI RNP TNP 16:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-BE-KPH-0202 | 30742640031 | 0903491003 | PADANG_LEKAT | BP2022 | TB | 102°34.48.92'E | 3°39.24.39'S | 50 | 90/160/300 | 2022 | Newsite 2021 | Jalan Desa Tebat Monok Kampung 5 Desa Tebat Monok Kecamatan Kepahiang Kabupaten Kepahiang Provinsi Bengkulu | HTI | SUM-BE-KPH-0202 | PADANG_LEKAT | B2S | TBG | West | SUMBAGSEL | Bengkulu | Kab. Kepahiang | 6618175 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 2022-04-28 | [11 empty] | SITAC | 20.APD & Design Process | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: APD 24:04:22-21:04:22: IW 20:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-SS-LLG-1237 | 30742620031 | 0719461003 | EKA_MARGA | BP2022 | TB | 102°56.13.43'E | 3°14.52.22'S | 50 | 30/110/250 | 2022 | Newsite 2021 | RT.04 Kelurahan Eka Marga Kecamatan Lubuk Linggau Selatan II Kota Lubuk Linggau Propinsi Sumatera Selatan | HTI | SUM-SS-LLG-1237 | EKA_MARGA | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kota Lubuk Linggau | 6618175 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 2022-04-28 | [11 empty] | SITAC | 20.APD & Design Process | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: APD 24:04:22-21:04:22: IW 20:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-BE-CRP-0185 | 30730190031 | 0903421003 | CURUPTIMUR_KARANGANYAR | BP2022 | TB | 102°32.5.19'E | 3°27.14.71'S | 50 | 50/180/280 | 2022 | New site 2022 - P2 | Dusun 3 Desa Kesambe Lama, Kecamatan Curup Timur, Kabupaten Rejang Lebong, Provinsi Bengkulu | HTI | SUM-BE-CRP-0185 | CURUPTIMUR_KARANGANYAR | B2S | TBG | West | SUMBAGSEL | Bengkulu | Kab. Rejang Lebong | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | 2022-03-15 | [10 empty] | CME | 26.Back Filling | 14.POURING CONCRETE OG | CURRENTLY NO ISSUE | 28:04:22: BACKFILL 24:04:22: POURING 20:04:22-17:04:22: REBARRING 13:04:22-10:04:22: EXCAVATION 06:04:22: BOUWPLANK 03:04:22-27:03:22: PREPARE CME 23:03:22-16:03:22: REKOM 13:03:22-06:03:22: IW CLEAR 28:02:22-16:02:22-13:02:22: IW OG 09:02:22: VALIDASI RNP TNP OG 08:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-UJT-0951 | 30729850031 | 0416531003 | TELUKNILAP | BP2022 | TB | 100°38.19.13'E | 2°0.26.91'N | 60 | 30/130/320 | 2022 | New site 2022 - P2 | Jl. Jend. Sudirman RT.003 RW.004 Dusun Karya Nyata Kepenghuluan Teluk Nilap Kecamatan Kubu Babussalam Kabupaten Rokan Hilir Provinsi Riau | HTI | SUM-RI-UJT-0951 | TELUKNILAP | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Rokan Hilir | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-03 | [10 empty] | CME | 23.Bore pile Rebaring & Pouring | 11.BORE PILE OG | CURRENTLY NO ISSUE | 28:04:22: BACKFILL 24:04:22-13:04:22: BOREPILE 10:04:22: EXCAVATION 06:04:22: BOUWPLANK 03:04:22-13:03:22: RFC 09:03:22: SOIL TEST 06:03:22-28:02:22: IW CLEAR 23:02:22-13:02:22: IW OG 09:02:22: VALIDASI RNP TNP OG 08:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SS-MPR-1284 | 30729770031 | 0719121003 | JAYAPURA_BUNGA_MAYANG | BP2022 | TB | 104°16.48.0'E | 4°27.9.0'S | 60 | 80/130/330 | 2022 | New site 2022 - P2 | Bunga Mayang RT.014 RW.001 Desa Bunga Mayang, Kecamatan Jayapura, Kabupaten Ogan Komering Ulu Timur, Provinsi Sumatera Selatan | HTI | SUM-SS-MPR-1284 | JAYAPURA_BUNGA_MAYANG | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | 2022-03-15 | [10 empty] | CME | 26.Back Filling | 14.POURING CONCRETE OG | CURRENTLY NO ISSUE | 28:04:22: BACKFILL 24:04:22-13:04:22: REBARRING 10:04:22: EXCAVATION 06:04:22-27:03:22: PREPARE CME 23:03:22-16:03:22: REKOM 13:03:22-06:03:22: IW CLEAR 01:03:22: VALIDASI RNP TNP 28:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUM-RI-PRP-1112 | 30740110031 | 0416951003 | LANGKITIN | BP2022 | TB | 100°24.38.09'E | 0°48.58.75'N | 50 | 40/100/270 | 2022 | Newsite 2022 - P2 | Langkitin Rt 007 / Rw 004 Desa Langkitin Kecamatan Rambah Samo Kabupaten Rokan Hulu Provinsi Riau | HTI | SUM-RI-PRP-1112 | LANGKITIN | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Rokan Hulu | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-10 | 2022-04-11 | [10 empty] | CME | 21.Bouwplank | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: BOUWPLANK 03:04:22: REKOM 30:03:22-23:03:22: IW CLEAR 20:03:22-11:03:22: IW OG 10:03:22: VALIDASI RNP TNP 09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SB-SPE-0821 | 30729840031 | 0311121003 | JL_TUANGKU_IMAM_BONJOL | BP2022 | TB | 99°50.6.62'E | 0°6.11.97'N | 50 | 10/290/260 | 2022 | New site 2022 - P2 | Jorong Kampung Cubadak, Nagari Lingkuang Aua, Kecamatan Pasaman, Kabupaten Pasaman Barat, Provinsi Sumatera Barat | HTI | SUM-SB-SPE-0821 | JL_TUANGKU_IMAM_BONJOL | B2S | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Pasaman Barat | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | [11 empty] | RFC | 21.Bouwplank | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: BOUWPLANK 24:04:22-20:04:22: RFC 17:04:22-06:04:22: REKOM 03:04:22-01:04:22: IW OG 30:03:22: VALIDASI RNP TNP 27:03:22-16:03:22: IW OG 14:03:22: VALIDASI RNP TNP 13:03:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JK-GGP-0443 | 30739560031 | 1137631003 | WIJAYA_KUSUMA_GROGOL | BP2022 | TB | 106°46.33.41'E | 6°8.58.33'S | 25 | 40/200/290 | 2022 | Newsite 2022 - B2 | Kp Baru RT 013 RW 05, Kelurahan Wijaya Kesuma, Kecamatan Grogol Petamburan, Kota Jakarta Barat, DKI Jakarta | EID | JAW-JK-GGP-0443 | WIJAYA_KUSUMA_GROGOL | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 |  |  | 10.6 | 2022-04-27 | [7 empty] | PRESITAC | 27.Curring Time | 15.CURRING TIME | CURRENTLY NO ISSUE | 28:04:22: CURRING 24:04:22-13:04:22: VALIDASI 10:04:22-03:04:22: IW CLEAR 30:03:22-09:02:22: SURVEY OG 07:02:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SS-RPT-1104 | 30729960031 | 0719141003 | KRANI_JAYA | BP2022 | TB | 102°54.6.2'E | 2°30.49.44'S | 60 | 90/160/350 | 2022 | New site 2022 - P2 | Dusun 4 Desa Jadimulya Kecamatan Nibung Kabupaten Musi Rawas Provinsi Sumatra Selatan | HTI | SUM-SS-RPT-1104 | KRANI_JAYA | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas Utara | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-02 | [10 empty] | CME | 27.Curring Time | 15.CURRING TIME | CURRENTLY NO ISSUE | 28:04:22: CURRING 24:04:22-17:04:22: REBARRING 13:04:22-10:04:22: EXCAVATION 06:04:22-03:04:22: PREPARE CME 30:03:22-27:03:22: REKOM OG 23:03:22-06:03:22: REKOM 28:02:22: IW CLEAR 23:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SS-RPT-1109 | 30729980031 | 0719161003 | RUPIT_NOMAN_BARU | BP2022 | TB | 102°49.50.75'E | 2°48.45.02'S | 60 | 30/230/320 | 2022 | New site 2022 - P2 | Kampung 7 Desa Noman Baru, Kecamatan Rupit, Kabupaten Musi Rawas Utara, Provinsi Sumatera Selatan | HTI | SUM-SS-RPT-1109 | RUPIT_NOMAN_BARU | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas Utara | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | 2022-03-15 | [10 empty] | CME | 27.Curring Time | 15.CURRING TIME | CURRENTLY NO ISSUE | 28:04:22: CURRING 24:04:22-17:04:22: REBARRING 13:04:22-10:04:22: EXCAVATION 06:04:22-27:03:22: PREPARE CME 23:03:22-16:03:22: REKOM 13:03:22-06:03:22: IW CLEAR 01:03:22: UNDER RNP TNP REVIEW, PERGESERAN KANDIDAT 28:02:22-16:02:22: IW OG 13:02:22-11:02:22: VALIDASI RNP TNP 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JK-GGP-0445 | 30739490031 | 1137581003 | PASAR_BERSIH_CENGKARENG | BP2022 | TB | 106°44.25.7'E | 6°8.17.61'S | 25 | 90/210/330 | 2022 | Newsite 2022 - B2 | Jl. Raya Boulevard RT 004 RW 014, Kel. Cengkareng Timur, Kec. Cengkareng, Jakarta Barat, DKI Jakarta | EID | JAW-JK-GGP-0445 | PASAR_BERSIH_CENGKARENG | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW |  |  | PLN NY | PLN NY | null | [7 empty] | RFC | 27.Curring Time | 15.CURRING TIME | CURRENTLY NO ISSUE | 28:04:22: CURRING 24:04:22-20:04:22: CME PREPARATION 17:04:22-03:04:22: IW CLEAR 30:03:22-09:02:22: SURVEY OG 07:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-BT-SRG-0061 | 30739500031 | 1323271003 | PEKIJING_GEDEG_KALANGANYAR | BP2022 | TB | 106°6.16.03'E | 6°7.29.28'S | 60 | 80/150/240/350 | 2022 | Newsite 2022 - B2 | Kp.Pekijing RT.007/RW.008 Kelurahan Kalanganyar, Kecamatan Taktakan, Kota Serang, Provinsi Banten | EID | JAW-BT-SRG-0061 | PEKIJING_GEDEG_KALANGANYAR | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Serang | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | 2022-04-28 |  | 6.6 | 2022-04-26 | [7 empty] | CME | 27.Curring Time | 15.CURRING TIME | CURRENTLY NO ISSUE | 28:04:22: CURRING 24:04:22-20:04:22: POURING 17:04:22-13:04:22: RFC 10:04:22-03:04:22: IW CLEAR 30:03:22-20:03:22: IW OG 16:03:22-13:03:22: VALIDASI RNP TNP OG 12:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-BB-MGR-0525 | 30730490031 | 0804371003 | DAMAR_AIR_KELIK | BP2022 | TB | 108°7.51.15'E | 2°42.31.48'S | 60 | 0/110/340 | 2022 | New site 2022 - P2 | Jl. Bandara-Manggar, RT.015, RW. 005, Dusun Air Lanci, Desa Air Kelik, Kecamatan Damar, Kabupaten Belitung Timur, Provinsi Kepulauan Bangka Belitung | HTI | SUM-BB-MGR-0525 | DAMAR_AIR_KELIK | B2S | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kab. Belitung Timur | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-02 | [10 empty] | CME | 27.Curring Time | 15.CURRING TIME | CURRENTLY NO ISSUE | 28:04:22: CURRING 24:04:22-20:04:22: REBARRING 17:04:22-10:04:22: BOUWPLANK 06:04:22: EXCAVATION 03:04:22-27:03:22: PREPARE CME 23:03:22-09:03:22: REKOM 06:02:22-23:02:22: IW CLEAR 20:02:22-16:02:22: IW OG 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-PKK-1155 | 30729930031 | 0416581003 | KELURAHAN_PANGKALAN_KERINCI_TIMUR | BP2022 | TB | 101°52.9.15'E | 0°22.48.97'N | 50 | 90/170/350 | 2022 | New site 2022 - P2 | Jalan Datuk Bandar RT.001 RW.004 Kel. Pangkalan Kerinci Timur Kec. Pangkalan Kerinci Kab. Pelalawan Provinsi Riau | HTI | SUM-RI-PKK-1155 | KELURAHAN_PANGKALAN_KERINCI_TIMUR | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Pelalawan | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-10 | 2022-04-11 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22: BACKFILL 20:04:2217:04:22: REBARRING 13:04:22: EXCAVATION 10:04:22-06:04:22: BOUWPLANK 03:04:22-20:03:22: REKOM OG 16:03:22-09:03:22: IW CLEAR 06:03:22-23:02:22: IW OG 20:02:22-16:02:22: VALIDASI RNP TNP OG 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JB-NPH-4381 | 30740000031 | 1277001003 | CIPENDEUY_STADION_SUKABETAH | BP2022 | TB | 107°23.19.22'E | 6°43.52.65'S | 50 | 135/240/330 | 2022 | Newsite 2022 - P1 | Kp. Sukabetah Rt. 003 Rw. 011 Desa. Ciharahas Kec. Cipeundeuy Kab Bandung Barat Provinsi Jawa Barat | HTI | JAW-JB-NPH-4381 | CIPENDEUY_STADION_SUKABETAH | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Bandung Barat | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-11 | 2022-04-13 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22: CURRING 20:04:22: REBARRING 17:04:22-13:04:22: REKOM 10:04:22-05:04:22: UNDER TNP 03:04:22-27:03:22: REHUNTING 23:03:22-13:03:22: IW OG 11:03:22: VALIDASI RNP TNP 09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-SRH-2244 | 30729750031 | 0228961003 | CITAMAN_JERNIH | BP2022 | TB | 98°57.24.93'E | 3°33.30.4'N | 50 | 40/170/260 | 2022 | New site 2022 - P1 | Jalan Merak Dusun VI, Desa Citaman Jernih, Kecamatan Perbaungan, Kabupaten Serdang Bedagai, Provinsi Sumatera Utara | HTI | SUM-SU-SRH-2244 | CITAMAN_JERNIH | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Serdang Bedagai | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | 2022-03-15 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22: CURRING TIME 20:04:22-17:04:22: EXCAVATION 13:04:22 BOUWPLANK 10:04:22-06:04:22: MOBDEMOB PREPARE CME 03:04:22-23:03:22: PERMIT OG 20:03:22-09:03:22: REKOM 06:03:22-23:02:22: IW CLEAR 20:02:22-13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-SRH-2248 | 30729800031 | 0228991003 | LUBUK_SABAN | BP2022 | TB | 99°1.43.13'E | 3°36.38.69'N | 50 | 40/170/280 | 2022 | New site 2022 - P2 | Dusun V Desa Lubuk Saban Kecamatan Pantai Cermin Kabupaten Serdang Bedagai Provinsi Sumatera Utara | HTI | SUM-SU-SRH-2248 | LUBUK_SABAN | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Serdang Bedagai | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-31 | 2022-04-01 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-: CURRING 20:04:22-17:04:22: EXCAVATION 13:04:22-10:04:22: BOUWPLANK 06:04:22-16:03:22: REKOM 13:03:22-06:03:22: IW CLEAR 28:02:22-13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-LMP-2231 | 30729690031 | 0228911003 | LAUT_TADOR_TANJUNG_SERI | BP2022 | TB | 99°18.25.16'E | 3°19.22.37'N | 40 | 0/190/270 | 2022 | New site 2022 - P2 | Jl. Pasar mati, dusun VI, desa tanjung seri, kecamatan lau tador, kabupaten batu bara | HTI | SUM-SU-LMP-2231 | LAUT_TADOR_TANJUNG_SERI | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Batu Bara | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-08 | 2022-03-09 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | COMMCASE | 28:04:22: ERECTION 24:04:22: CURRING 20:04:22-17:04:22: REBARRING 13:04:22-10:04:22: EXCAVATION 06:04:22: BOUWPLANK 03:04:22-13:03:22: PERMIT OG 09:03:22-06:03:22: REKOM OG 28:02:22-20:02:22: IW CLEAR 16:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-BT-RKB-0766 | 30729380031 | 1322981003 | CIGOONG_SELATAN_CIKULUR | BP2022 | TB | 106°11.22.31'E | 6°23.21.02'S | 70 | 70/170/300 | 2022 | New site 2022 - P2 | KP.SELAPANJANG RT.009/003 KEL.CIGOONG SELATAN KEC.CIKULUR | EID | JAW-BT-RKB-0766 | CIGOONG_SELATAN_CIKULUR | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 3/7/2022, resend 28 apr 22 |  |  | 10.6 | 2022-04-20 | [7 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22: POURING 20:04:22: REBARRING 17:04:22-13:04:22: EXCAVATION 10:04:22-03:04:22: RFC 30:03:22-06:03:22: REKOM OG 28:02:22: IW CLEAR & PARALEL COLLECT DOC 23:02:22-16:02:22: IW OG 13:02:22-03:02:22: VALIDASI RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JI-KDR-4344 | 30740140031 | 1655161003 | NGADILUWIH_REMBANG | BP2022 | TB | 111°59.42.0'E | 7°53.16.91'S | 50 | 40/170/260 | 2022 | Newsite 2022 - P2 | Dusun Mitiran RT.002 RW.007 Desa Rembang Kecamatan Ngadiluwih Kabupaten Kediri Provinsi Jawa Timur | HTI | JAW-JI-KDR-4344 | NGADILUWIH_REMBANG | B2S | TBG | East | JATIM | Jawa Timur | Kab. Kediri | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22: POURING 20:04:22-17:04:22: REBARRING 13:04:22: EXCAVATION 10:04:22-03:04:22: IW CLEAR 30:03:22-15:03:22: IW OG 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-BT-PDG-0618 | 30729210031 | 1322891003 | BANYUBIRU_TEMBONG | BP2022 | TB | 105°50.54.89'E | 6°20.2.04'S | 50 | 60/240/320 | 2022 | New site 2022 - P2 | Kp. Galaya RT 005 RW 003 Desa Tembong, Kec. Carita Kab Pandeglang, Provinsi Banten | EID | JAW-BT-PDG-0618 | BANYUBIRU_TEMBONG | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Pandeglang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-14 | 2022-04-14 |  | 6.6 | [8 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22: REBARRING 20:04:22: EXCAVATION 17:04:22-13:04:22: REBARRING 10:04:22-20:03:22: RFC, MOBDEMOB 16:03:22-06:03:22: REKOM OG 28:02:22: IW CLEAR & PARALEL COLLECT DOC 23:02:22-22:02:22: IW OG 20:02:22: UNDER RNP TNP 16:02:22-13:02:22: REHUNTING RNP NOK 09:02:22-06:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-SRH-2243 | 30729680031 | 0228901003 | PEMATANG_GUNTUNG | BP2022 | TB | 99°7.36.93'E | 3°32.47.07'N | 50 | 10/110/210 | 2022 | New site 2022 - P1 | Dusun II Desa Pematang Guntung, Kecamatan Teluk Mengkudu, Kabupaten Serdang Bedagai, Provinsi Sumatera Utara | HTI | SUM-SU-SRH-2243 | PEMATANG_GUNTUNG | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Serdang Bedagai | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | 2022-03-15 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22: REBARRING 20:04:22-17:04:22: EXCAVATION 13:04:22 BOUWPLANK 10:04:22-06:04:22: MOBDEMOB PREPARE CME 03:04:22-23:03:22: PERMIT OG 20:03:22-13:03:22: REKOM 09:03:22-20:02:22: IW CLEAR 16:02:22-13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-BB-MGR-0530 | 30730200031 | 0804361003 | KELAPA_KAMPIT_MENTAWAK | BP2022 | TB | 108°2.50.8'E | 2°42.13.95'S | 50 | 0/100/260 | 2022 | New site 2022 - P1 | Jl. Parit Kemang,RT.002, RW. 001, Dusun Bukit Durian, Desa Mentawak,Kecamatan Kelapa Kampit,Kabupaten Belitung Timur, Provinsi Kepulauan Bangka Belitung | HTI | SUM-BB-MGR-0530 | KELAPA_KAMPIT_MENTAWAK | B2S | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kab. Belitung Timur | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-02 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-06:04:22: PREPARE ERECTION 03:04:22: BOUWPLANK 30:03:22-27:03:22: PREPARE CME 23:03:22-06:03:22: REKOM 28:02:22-23:02:22: IW CLEAR 20:02:22: IW OG 18:02:22: VALIDASI RNP TNP OG, REJECT WARGA 16:02:22-13:02:22: IW OG 09:02:22: VALIDASI RNP TNP OG 08:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-BT-RKB-0763 | 30729350031 | 1322951003 | CITRA_MAJA_RAYA | BP2022 | TB | 106°22.52.32'E | 6°20.4.3'S | 50 | 60/150/270 | 2022 | New site 2022 - P2 | Kp. Maja Lembuh RT.002/003 Kelurahan Curug Badak Kecamatan Maja Kab. Lebak | EID | JAW-BT-RKB-0763 | CITRA_MAJA_RAYA | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 |  |  | 6.6 | 2022-04-20 | [7 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-13:04:22: EXCAVATION 10:04:22-20:03:22: REKOM OG 16:03:22-06:03:22: VALIDASI RNP TNP OG & IW CLEAR 28:02:22: IW CLEAR & PARALEL COLLECT DOC 23:02:22-20:02:22: IW OG 16:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SS-MRD-1004 | 30730070031 | 0719181003 | AIR_RUPIK | BP2022 | TB | 103°55.4.8'E | 4°46.42.49'S | 65 | 110/260/355 | 2022 | New site 2022 - P2 | RT 003 RW 002 Desa Air Rupik Kecamatan Banding Agung Kabupaten Ogan Komering Ulu Selatan Provinsi Sumatera Selatan | HTI | SUM-SS-MRD-1004 | AIR_RUPIK | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Se | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-02 | 2022-03-18 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-17:04:22: CURRING TIME 13:04:22-10:04:22: REBARRING 06:04:22-03:04:22: EXCA 30:03:22-27:03:22: PREPARE CME 23:03:22-06:03:22: REKOM 28:02:22: IW CLEAR 23:02:22: IW OG 21:02:22: VALIDASI RNP TNP 20:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-LA-KLA-1141 | 30730120031 | 1014591003 | TANJUNG_BINTANG_LEMATANG | BP2022 | TB | 105°20.47.67'E | 5°24.45.55'S | 60 | 10/150/230 | 2022 | New site 2022 - P2 | Jl. H. Antaya Dusun 02 Kaliasin RT.004 Desa Kaliasin, Kecamatan Tanjung Bintang Lematang, Kabupaten Lampung Selatan, Provinsi Lampung | HTI | SUM-LA-KLA-1141 | TANJUNG_BINTANG_LEMATANG | B2S | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Selatan | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-31 | 2022-04-01 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-20:04:22: CURRING 17:04:22-13:04:22: REBARRING 10:04:22: EXCAVATION 06:04:22: BOUWPLANK 03:04:22: PREPARE CME 30:03:22-27:03:22: REKOM OG 23:03:22-22:03:22: IW OG 21:03:22: VALIDAIS RNP TNP PERGESERAN KANDIDAT 20:03:22: IW CLEAR 16:03:22-14:03:22: VALIDASI RNP TNP 13:03:22: REHUNTING 09:03:22: IW CLEAR 06:03:22: IW OG 01:03:22: VALIDASI RNP TNP 28:02:22-23:02:22: IW OG 21:02:22: VALIDASI RNP TNP 20:02:22: IW OG 16:02:22: IW FAILED, VALIDASI RNP TNP 15:02:22-13:02:22: IW OG 09:02:22: VALIDASI RNP TNP OG 08:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SS-MPR-1280 | 30730110031 | 0719201003 | WANASARI OGAN | BP2022 | TB | 104°51.50.27'E | 3°48.29.86'S | 60 | 150/210/325 | 2022 | New site 2022 - P2 | Desa Wanasari, Kecamatan Semendawai Timur, Kabupaten Ogan Komering Ulu Timur, Provinsi Sumatera Selatan | HTI | SUM-SS-MPR-1280 | WANASARI | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-21 | 2022-03-23 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-20:04:22: CURRING 17:04:22-13:04:22: REBARRING 10:04:22: EXCAVATION 06:04:22-03:04:22: PREPARE CME 30:03:22-16:03:22: REKOM 13:03:22-09:03:22: IW CLEAR 06:03:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-BE-TAS-0219 | 30730290031 | 0903431003 | PADANG_PERI | BP2022 | TB | 102°47.6.0'E | 4°16.37.7'S | 60 | 15/120/220 | 2022 | New site 2022 - P2 | Jl. Raya Manna - Bengkulu Dusun I Desa Padang Peri, Kecamatan Semidang Alas Maras, Kabupaten Seluma, Provinsi Bengkulu | HTI | SUM-BE-TAS-0219 | PADANG_PERI | B2S | TBG | West | SUMBAGSEL | Bengkulu | Kab. Seluma | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | 2022-03-15 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-20:04:22: CURRING 17:04:22-17:04:22: BOREPILE REBARRING 13:04:22-10:04:22: EXCAVATION 06:04:22: BOUWPLANK 03:04:2227:03:22: PREPARE CME 23:03:22-06:03:22: REKOM 28:02:22-16:02:22-13:02:22: IW OG 09:02:22: VALIDASI RNP TNP OG 08:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-BE-TAS-0218 | 30730360031 | 0903441003 | SERIAN_BANDUNG | BP2022 | TB | 102°48.7.2'E | 4°20.45.49'S | 60 | 25/100/240 | 2022 | New site 2022 - P2 | Jl. Raya Manna - Bengkulu, Desa Serian Bandung, Kecamatan Semidang Alas Maras, Kabupaten Seluma, Provinsi Bengkulu | HTI | SUM-BE-TAS-0218 | SERIAN_BANDUNG | B2S | TBG | West | SUMBAGSEL | Bengkulu | Kab. Seluma | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-31 | 2022-04-01 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-20:04:22: CURRING 17:04:22-17:04:22: REBARRING 13:04:22-10:04:22: EXCAVATION 06:04:22: BOUWPLANK 03:04:22: PREPARE CME 30:03:22-27:03:22: DESIGN OG 23:03:22-16:03:22: REKOM 13:03:22-11:03:22: VALIDASI RNP TNP -> IW OG 09:03:22-06:03:22: REHUNTING, IW FAILED 28:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-BT-PDG-0623 | 30739450031 | 1323231003 | TAMANJAYA_SUMUR | BP2022 | TB | 105°30.21.88'E | 6°46.38.26'S | 60 | 0/80/190 | 2022 | Newsite 2022 - B2 | Kp. Peundeuy RT 001 RW 004 Desa Taman Jaya, Kec. Sumur, Kab Pandeglang Prov. Banten | EID | JAW-BT-PDG-0623 | TAMANJAYA_SUMUR | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Pandeglang | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | 2022-04-28 |  | 10.6 | 2022-04-27 | [7 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22: ERECTION 24:04:22-20:04:22: POURING 13:04:22: EXCAVATION 10:04:22-03:04:22: IW CLEAR 30:03:22-27:03:22: IW OG 23:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  |  | 140219104 | SIJERUKTBG | BP2022 | SKP | 109°42.42.8'E | 7°19.49.26'S | 60 | 80/170/320 | 2022 | Newsite 2022 - B2 | Desa Kalilunjar Dsn. Kalilunjar RT.01 RW.01 Kec. Banjarmangu, Kab. Banjarnegara Prov. Jawa Tengah | NOKIA | JAW-JT-BNR-0272 | SIJERUK_BANJARNEGARA | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Banjarnegara | 6618197 | 2022-04-07 | 2022-04-22 | 21 | < 30 days | 2022-05-07 | W19-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERM PROCESS 22:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  |  | 1448171001 | KRAMAT TEGALREJO | BP2022 | TB | 110°1.41.12'E | 7°14.45.85'S | 60 | 40/150/280 | 2022 | Newsite 2022 - B2 | KULON NGGANEN RT 001 RW 007 DESA TEGALREJO KECAMATAN NGADIREJO KABUPATEN TEMANGGUNG | NOKIA | JAW-JT-TMG-2680 | DLIMOYO_TEMANGGUNG | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Temanggung | 6618196 | 2022-04-07 | 2022-04-22 | 21 | < 30 days | 2022-05-07 | W19-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERM PROCESS 22:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | KAL-KT-PPS-0709 | 30739740031 | 2107531003 | MULYASARI_PANDIH_BATU | BP2022 | TB | 114°6.31.01'E | 3°2.52.41'S | 65 | 100/245/325 | 2022 | Newsite 2022 - B2 | Desa Mulyasari RT.001 RW.001 Kecamatan Pandih Batu Kabupaten Pulang Pisau Provinsi Kalimantan Tengah | HTI | KAL-KT-PPS-0709 | MULYASARI_PANDIH_BATU | B2S | TBG | Central | KALIMANTAN | Kalimantan Tengah | Kab. Pulang Pisau | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | [11 empty] | RFC | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCA 24:04:22: MOBDEMOB 20:04:22-06:04:22: REKOM 04:03:22: IW CLEAR 03:04:22-16:03:22: SURVEY OG 13:03:22; MITRA ASSIGNMENT 09:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | KAL-KT-PPS-0707 | 30739730031 | 2107521003 | TALIO_MUARA_PANDIH_BATU | BP2022 | TB | 114°5.41.5'E | 3°5.17.36'S | 50 | 105/235/330 | 2022 | Newsite 2022 - B2 | Desa Talio Hulu RT.004 RW.001 Kecamatan Pandih Batu Kabupaten Pulang Pisau Provinsi Kalimantan Tengah | HTI | KAL-KT-PPS-0707 | TALIO_MUARA_PANDIH_BATU | B2S | TBG | Central | KALIMANTAN | Kalimantan Tengah | Kab. Pulang Pisau | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | [11 empty] | RFC | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCA 24:04:22: MOBDEMOB 20:04:22-06:04:22: REKOM 04:03:22: IW CLEAR 03:04:22-16:03:22: SURVEY OG 13:03:22; MITRA ASSIGNMENT 09:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JT-TGL-2623 | 30739690031 | 1450931003 | TEGAL_LEBAKSIU | BP2022 | TB | 109°6.38.87'E | 7°1.49.48'S | 60 | 30/140/230 | 2022 | Newsite 2022 - P2 |  | NOKIA | JAW-JT-TGL-2623 | TEGAL_LEBAKSIU | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Tegal | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | RFC | 22.Excavation | 12.EXCAVATION OG | WAIT PSB | 28:04:22: EXCA 24:04:22: MOBDEMOB 20:04:22-17:04:22: REKOM LMS CHANGE TO NOKIA 13:04:22: REKOM 10:04:22-16:03:22: IW OG 15:03:22-14:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JK-GGP-0438 | 30739590031 | 1137651003 | WARU_KALI_DERES | BP2022 | TB | 106°41.55.9'E | 6°8.48.5'S | 25 | 90/210/330 | 2022 | Newsite 2022 - B2 | CITRA GARDEN I Blok B-2/15 Kelurahan Kalideres Kecamatan Kalideres Kota Jakarta Barat DKI Jakarta | EID | JAW-JK-GGP-0438 | WARU_KALI_DERES | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 |  |  | 10.6 | 2022-04-27 | [7 empty] | SITAC | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCA 24:04:22-20:04:22: REKOM OG 13:04:22-03:04:22: IW OG 30:03:22-09:02:22: SURVEY OG 07:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JI-KDR-4347 | 30740180031 | 1655181003 | PAPAR_DAWUHAN_KIDUL | BP2022 | TB | 112°5.28.93'E | 7°43.5.56'S | 50 | 25/115/285 | 2022 | Newsite 2022 - P2 | Dusun Kalangbong RT. 002 RW. 003 Desa Dawuhan Kidul Kecamatan Papar Kabupaten Kediri Propinsi Jawa Timur | HTI | JAW-JI-KDR-4347 | PAPAR_DAWUHAN_KIDUL | B2S | TBG | East | JATIM | Jawa Timur | Kab. Kediri | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCA 24:04:22-30:03:22: IW OG 27:03:22-25:03:22: VALIDASI RNP TNP 23:03:22-16:03:22: IW OG 15:03:22-15:03:22: UNDER TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-BT-PDG-0629 | 30739460031 | 1323241003 | SIKULAN_JIPUT | BP2022 | TB | 105°53.58.48'E | 6°19.3.77'S | 70 | 30/180/270 | 2022 | Newsite 2022 - B2 | Kp. Kadu Bangban RT 001 RW 009 Desa Sikulan, Kec. Jiput Kab Pandeglang Prov. Banten | EID | JAW-BT-PDG-0629 | SIKULAN_JIPUT | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Pandeglang | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW |  |  | PLN NY | PLN NY | null | [7 empty] | CME | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCA, ROCK SOIL 24:04:22-13:04:22: RFC 10:04:22-03:04:22: IW CLEAR 30:03:22-23:03:22: IW OG 21:02:22: VALIDASI RNP TNP 20:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | NUS-NB-WHO-5383 | 30729160031 | 1806881003 | LAJU_LANGGUDU | BP2022 | TB | 118°43.45.16'E | 8°42.34.71'S | 60 | 50/190/290 | 2022 | New site 2022 - P2 | Dusun Sumber Sari RT.10 RW.04 Desa Laju, Kec. Langgudu, Kab. Bima, Prop. Nusa Tenggara Barat | ALT | NUS-NB-WHO-5383 | LAJU_LANGGUDU | B2S | TBG | East | BALINUSRA | Nusa Tenggara Barat | Kab. Bima | 6617947 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-31 | 2022-04-04 | [10 empty] | CME | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCAVATION 24:04:22: BOUWPLANK 20:04:22-14:04:22: MATERIAL DELIVERY 10:06:22: BOUWPLANK & DELIVERY MATERIAL 06:04:22: BOUWPLANK 03:04:22: PERMIT 16:03:22: REKOM OG 13:03:22-09:03:22: IW CLEAR 06:03:22-06:03:22: IW OG KURANG 4 KK 28:02:22-23:02:22: SOSWAR OG 20:02:22-13:02:22: IW OG 09:02:22-03:02:22: VALIDASI RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | NUS-NB-WHO-5382 | 30730890031 | 1806891003 | KOWO_WERA | BP2022 | TB | 119°0.23.07'E | 8°31.58.84'S | 60 | 30/180/300 | 2022 | New site 2022 - P2 | Jl. Lintas Sape - Wera Dusun Kowo Timur RT.07 RW.03, Desa Kowo, Kecamatan Sape, Kabupaten Bima, Propinsi Nusa Tenggara Barat | ALT | NUS-NB-WHO-5382 | KOWO_WERA | B2S | TBG | East | BALINUSRA | Nusa Tenggara Barat | Kab. Bima | 6617947 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-31 | 2022-04-04 | [10 empty] | CME | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCAVATION 24:04:22: BOUWPLANK 20:04:22-14:04:22: MATERIAL DELIVERY 10:06:22: BOUWPLANK & DELIVERY MATERIAL 06:04:22: BOUWPLANK 27:03:22: REKOM 23:03:22-20:03:22: IW CLEAR 16:03:22: IW OG 13:03:22-09:03:22: IW FAILED, REHUNTING 06:03:22-22:02:22: IW OG 20:02:22-17:02:22: VALIDASI RNP TNP OG 16:02:22-14:02:22: REHUNTING RNP NOK 13:02:22-09:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | NUS-NT-KPG-0307 | 30730900031 | 1910651003 | ENO_SABU | BP2022 | TB | 123°35.6.6'E | 10°13.22.51'S | 50 | 70/160/350 | 2022 | New site 2022 - P2 | Fatukoa, RT.011 RW.003, Kelurahan Fatukoa Kecamatan Maulafa, Kota Kupang, Propinsi Nusa Tenggara Timur | ALT | NUS-NT-KPG-0307 | ENO_SABU | B2S | TBG | EAST | BALINUSRA | Nusa Tenggara Timur | Kota Kupang | 6618010 | 2022-02-02 | 2022-02-02 | 85 | 61 - 90 days | 2022-07-02 | W27-2022 | Jul-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | [11 empty] | RFC | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCAVATION 24:04:22: RFC 10:04:22: REKOM 06:04:22-03:04:22: IW CLEAR 30:03:22-27:03:22: IW OG 23:03:22-22:03:22: VALIDASI RNP TNP KANDIDAT B 20:03:22: IW OG -1 KK 16:03:22: IW OG, -2 KK 13:03:22-06:03:22: IW FAIL, REHUNTING 28:02:22-22:02:22: IW OG 20:02:22-16:02:22: VALIDASI RNP TNP 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | NUS-NB-SEL-5388 | 30739850031 | 1806931003 | PRINGGABAYA_GUNUNG_MALANG | BP2022 | TB | 116°41.37.67'E | 8°27.3.02'S | 50 | 20/140/220 | 2022 | Newsite 2022 - B2 | Dsn. Leper RT.006 RW. 002 Desa Gunung Malang Kec. Pringgabaya Kab. Lombok Timur Provinsi Nusa Tenggara Barat. | HTI | NUS-NB-SEL-5388 | PRINGGABAYA_GUNUNG_MALANG | B2S | TBG | East | BALINUSRA | Nusa Tenggara Barat | Kab. Lombok Timur | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCAVATION 24:04:22-17:04:22: REKOM 13:04:22-03:04:22: IW CLEAR 30:03:22-23:03:22: IW OG 21:03:22: VALIDASI RNP TNP 20:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | NUS-NB-SEL-5389 | 30739930031 | 1806941003 | LABUHAN_PANDAN_SAMBELIA | BP2022 | TB | 116°43.16.08'E | 8°23.26.17'S | 50 | 60/180/290 | 2022 | Newsite 2022 - B2 | Dsn. Labuan Pandan RT.001 RW. 000 Desa Labuhan Pandan Kec. Sambelia Kab. Lombok Timur. | HTI | NUS-NB-SEL-5389 | LABUHAN_PANDAN_SAMBELIA | B2S | TBG | East | BALINUSRA | Nusa Tenggara Barat | Kab. Lombok Timur | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCAVATION 24:04:22-17:04:22: REKOM 13:04:22-10:04:22: IW CLEAR 06:04:22: IW OG 04:04:22: VALIDASI RNP TNP 03:04:22-22:03:22: IW OG 20:03:22-18:03:22: VALIDASI RNP TNP 16:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | BAL-BA-TAB-1960 | 30739960031 | 1721091003 | BATURITI_ANGSERI | BP2022 | TB | 115°9.8.38'E | 8°21.25.35'S | 60 | 50/160/240 | 2022 | Newsite 2022 - P2 | Br. Dinas Bugbugan Sari Desa Senganan Kecamatan Penebel Kabupaten Tabanan Provinsi Bali | HTI | BAL-BA-TAB-1960 | BATURITI_ANGSERI | B2S | TBG | East | BALINUSRA | Bali | Kab. Tabanan | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCAVATION 24:04:22-17:04:22: REKOM 13:04:22-12:04:22: VALIDASI RNP TNP -> IW 10:04:22-03:04:22: IW CLEAR 30:03:22-27:03:22-16:03:22: IW OG 15:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-SB-BSK-0863 | 30740240031 | 0311221003 | TANAH_DATAR_PARIANGAN | BP2022 | TB | 100°29.36.5'E | 0°27.18.5'S | 60 | 30/170/320 | 2022 | Newsite 2022 - B2 | Jorong Pariangan Nagari Pariangan Kecamatan Pariangan Kabupaten Tanah Datar Provinsi Sumatera Utara | HTI | SUM-SB-BSK-0863 | TANAH_DATAR_PARIANGAN | B2S | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Tanah Datar | 6618109 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 |  |  |  |  | 2022-04-25 | [6 empty] | RFC | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22: EXCVATION 24:04:22: MOBDEMOB 20:04:22-17:04:22: DESIGN OG 13:04:22-10:04:22: REKOM 06:04:22: IW GOG 03:04:22-30:03:22: VALIDASI RNP TNP 27:03:22 REHUNTING 23:03:22-20:03:22: IW OG 16:03:22-11:03:22: VALIDASI RNP TNP OG 09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
924 |  | JAW-JK-CKG-0710 |  |  |  | X RELOC TBG |  | 106.8854 | -6.2323 | 50 | 90/210/330 |  |  |  | EID | JAW-JK-CKG-0710 | CIPINANG MUARA RELOCATION | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | Jakarta Timur | 6614469 | 2020-02-10 |  | 808 | > 150 days | 2020-03-11 | W11-2020 | Mar-2020 | 2020-06-15 | W25-2020 | Jun-2020 | 2020-03-10 | W11-2020 | Mar-2020 | 2020-08-14 | W33-2020 | Aug-2020 | [14 empty] | 12.CP Process | 07.SITAC PROCESS |  | 18.06.20 : IW on going yang melibatkan warga 3 RW (radius tower mencakup 3 RW) 30.04.20 : 23.04.20 : IW on going 25.03.20 : Hunting
|  | JAW-JB-SBM-2466 | 30739670031 | 1276861003 | WANGUNREJA_NYALINDUNG | BP2022 | TB | 106°53.11.43'E | 6°58.55.61'S | 70 | 60/200/320 | 2022 | Newsite 2022 - P2 | Kp. Wangunreja RT.002 RW.005 Desa Wangunreja Kec. Nyalindung Kab. Sukabumi | EID | JAW-JB-SBM-2466 | WANGUNREJA_NYALINDUNG | B2S | TBG | JABO | JABODETABEK | Jawa Barat | Kab. Sukabumi | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW |  |  | PLN NY | PLN NY | null | [7 empty] | SITAC | 16.IMB waiting survey | 08.GOVERNMENT PERMIT PROCESS | CURRENTLY NO ISSUE | 28:04:22: IMB 24:04:22: REKOM 20:04:22-17:04:22: IW OG 13:04:22-01:04:22: VALIDASI RNP TNP 30:03:22-20:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | KAL-KB-MPW-0713 | 30739890031 | 2008541003 | SUNGAI_KUNYIT_DALAM_MEMPAWAH | BP2022 | TB | 108°55.54.62'E | 0°29.46.44'N | 65 | 115/270/330 | 2022 | Newsite 2022 - B2 |  | HTI | KAL-KB-MPW-0713 | SUNGAI_KUNYIT_DALAM_MEMPAWAH | B2S | TBG | JABO | KALIMANTAN | Kalimantan Barat | Kab. Mempawah | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 13:04:22: REHUNTING 10:04:22-04:03:22: IW CLEAR 03:04:22-16:03:22: SURVEY OG 13:03:22; MITRA ASSIGNMENT 09:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JI-TRK-4270 | 30741680031 | 1655221003 | REPEATER JOHO PULE | NEW SITE 2022-REPEATER | TB | 111°31.21.72'E | 8°9.26.39'S | 50 | 48 |  | Newsite 2022 - Repeater |  | HTI | JAW-JI-TRK-4270 | REPEATER JOHO PULE | B2S | TBG | East | JATIM | Jawa Timur | Kab. Trenggalek | 6618139 | 2022-03-21 | 2022-03-22 | 38 | 31 - 60 days | 2022-08-18 | W34-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-06:04:22: IW OG 30:03:22: VALIDASI RNP TNP 27:03:22: SURVEY OG 22:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-KR-TBK-0588 | 30730140031 | 0507561003 | PARIT_BENUT | BP2022 | TB | 103°21.44.07'E | 1°2.48.43'N | 50 | 100/190/340 | 2022 | New site 2022 - P2 | Perumahan Mutiara Karimun RT.02 RW.08,Desa Parit Benut,Kec.Meral,Kab.Tanjung Balai Karimun,Prov.Kepulauan Riau. | HTI | SUM-KR-TBK-0588 | PARIT_BENUT | B2S | TBG | West | SUMBAGTENG | Kepulauan Riau | Kab. Karimun | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-07:04:22: IW OG 07:04:22: VALIDASI RNP TNP KANDIDAT D 06:04:22-20:02:22: IW OG 17:02:22: VALIDASI RNP TNP OG 16:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JI-PNG-4308 | 30730530031 | 1654831003 | BABADAN_KERTOSARI | BP2022 | TB | 111°28.8.4'E | 7°51.53.1'S | 30 | 60/280/350 | 2022 | New site 2022 - P2 |  | HTI | JAW-JI-PNG-4308 | BABADAN_KERTOSARI | B2S | TBG | East | JATIM | Jawa Timur | Kab. Ponorogo | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: IW OG 10:04:22-05:04:22: VALIDASI RNP TNP 03:04:22-20:03:22: REHUNTING 18:03:22-16:03:22: VALIDASI RNP TNP 13:03:22-06:03:22: IW OG 06:03:22-28:02:22: VALIDASI RNP TNP, REJECT WARGA 23:02:22-20:02:22: IW OG 16:02:22-03:02:22: VALIDASI RNP TNP, PRIORITY CANDIDATE B 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JT-PWT-0594 | 30742830031 | 1451241003 | PANEMBANGAN_BANYUMAS | BP2022 | TB | 109°8.28.73'E | 7°23.5.6'S | 70 | 70/190/280 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-PWT-0594 | PANEMBANGAN_BANYUMAS | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Banyumas | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-PWR-1680 | 30742700031 | 1451121003 | PLIPIR_PURWOREJO | BP2022 | TB | 110°3.5.76'E | 7°44.21.28'S | 70 | 90/230/320 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-PWR-1680 | PLIPIR_PURWOREJO | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Purworejo | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-RBG-1777 | 30742720031 | 1451141003 | REMBANG_PANCUR | BP2022 | TB | 111°29.22.3'E | 6°43.59.6'S | 60 | 90/230/330 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-RBG-1777 | REMBANG_PANCUR | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Rembang | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-TMG-2669 | 30742780031 | 1451201003 | ROWO_TEMANGGUNG | BP2022 | TB | 110°9.44.53'E | 7°14.31.88'S | 70 | 90/210/300 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-TMG-2669 | ROWO_TEMANGGUNG | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Temanggung | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-TMG-2678 | 30742800031 | 1451221003 | SANGGRAHAN_TEMANGGUNG | BP2022 | TB | 110°13.14.82'E | 7°20.2.44'S | 50 | 0/110/240 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-TMG-2678 | SANGGRAHAN_TEMANGGUNG | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Temanggung | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-WNG-2761 | 30742820031 | 1451231003 | SUKOHARJO_BULU | BP2022 | TB | 110°51.24.88'E | 7°47.16.47'S | 60 | 0/120/240 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-WNG-2761 | SUKOHARJO_BULU | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Wonogiri | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-SKH-1871 | 30742860031 | 1451271003 | WERU KARANGANYAR | BP2022 | TB | 110°46.16.93'E | 7°47.30.23'S | 60 | 40/150/320 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-SKH-1871 | WERU KARANGANYAR | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Sukoharjo | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-WNG-2763 | 30742790031 | 1451211003 | WONOGIRI_GIRIWOYO | BP2022 | TB | 110°55.23.02'E | 8°0.49.03'S | 60 | 40/180/310 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-WNG-2763 | WONOGIRI_GIRIWOYO | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Wonogiri | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-BTG-0222 | 30742770031 | 1451191003 | BATANG_TERSONO | BP2022 | TB | 109°58.57.72'E | 7°0.46.04'S | 70 | 90/230/320 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-BTG-0222 | BATANG_TERSONO | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Batang | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-KRG-2136 | 30742570031 | 1451071003 | PLESUNGAN GONDANGREJO | BP2022 | TB | 110°51.37.09'E | 7°31.55.64'S | 50 | 100/200/340 | 2022 | Newsite 2021 |  | EID | JAW-JT-KRG-2136 | PLESUNGAN GONDANGREJO | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Karanganyar | 6618174 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-BNR-0276 | 30742730031 | 1451151003 | BANJARNEGARA_PUNGGELAN | BP2022 | TB | 109°37.50.67'E | 7°20.30.07'S | 70 | 70/250/340 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-BNR-0276 | BANJARNEGARA_PUNGGELAN | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Banjarnegara | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-KLN-0921 | 30742870031 | 1451281003 | KLATEN_KARANGDOWO | BP2022 | TB | 110°45.44.1'E | 7°40.56.75'S | 70 | 30/150/270 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-KLN-0921 | KLATEN_KARANGDOWO | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Klaten | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-MJL-4134 | 30739780031 | 1276901003 | MANIIS | BP2022 | TB | 108°19.42.43'E | 7°2.11.73'S | 40 | 125/220/275 | 2022 | Newsite 2022 - B2 | Sindanghurip RT 02 RW 04 Desa Maniis Kecamatan Cingambul Kab. Majalengka Propinsi Jawa Barat. | HTI | JAW-JB-MJL-4134 | MANIIS | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Majalengka | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | [11 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-14:03:22: IW OG 13:04:22-11:04:22: VALIDASI RNP TNP 10:04:22-15:03:22: IW OG 13:03:22: VALIDASI RNP TNP 12:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-BT-PDG-0630 | 30739470031 | 1323251003 | KAMPUNG_KADUNGALAK_WIRASINGA | BP2022 | TB | 106°3.21.21'E | 6°24.28.86'S | 50 | 0/100/180/270 | 2022 | Newsite 2022 - B2 | Kp.Torus RT.03 RW.03 Desa Wirasinga Kecamatan Mekarjaya -Pandegelang | EID | JAW-BT-PDG-0630 | KAMPUNG_KADUNGALAK_WIRASINGA | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Pandeglang | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-20:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-SDK-2229 | 30730030031 | 0229051003 | BANDAR_HUTA_USANG | BP2022 | TB | 98°23.12.48'E | 2°48.55.58'N | 60 | 90/180/300 | 2022 | New site 2022 - P2 |  | HTI | SUM-SU-SDK-2229 | BANDAR_HUTA_USANG | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Dairi | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-23:03:22: IW OG 20:03:22-18:03:22: VALIDASI RNP TNP 16:03:22-13:03:22: REHUTING 09:03:22-06:03:22: VALIDASI RNP TNP 28:02:22-23:02:22: REHUNTING, IW FAILED 20:02:22-13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-MDN-2244 | 30729720031 | 0228941003 | MEDAN_DELI_MABAR | BP2022 | TB | 98°40.42.56'E | 3°39.40.31'N | 30 | 90/210/330 | 2022 | New site 2022 - P2 |  | HTI | SUM-SU-MDN-2244 | MEDAN_DELI_MABAR | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kota Medan | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 24:04:22-27:03:22: PENGURUSAN SURAT TANAH 23:03:22: IW OG 20:03:22-16:03:22: VALIDASI RNP TNP 13:03:22: IW OG 10:03:22: VALIDASI RNP TNP 09:03:22-13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JB-CMS-4299 | 30739770031 | 1276891003 | LUMBUNG_DARMARAJA | BP2022 | TB | 108°20.16.8'E | 7°9.9.5'S | 50 | 90/250/330 | 2022 | Newsite 2022 - B2 | Kp. Babakan Jati Desa Darmaraja Kec. Lumbung Kab. Ciamis | HTI | JAW-JB-CMS-4299 | LUMBUNG_DARMARAJA | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Ciamis | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 25:04:22: IW OG 24:04:22: VALIDASI RNP TNP 20:04:22: IW OG 18:04:22: VALIDASI 17:04:22-06:04:22: IW OG 05:04:22: VALIDASI RNP TNP 03:04:22-15:03:22: IW OG 13:03:22: VALIDASI RNP TNP 12:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-SLT-2133 | 30742850031 | 1451261003 | KUTOWINANGUN KIDUL TINGKIR | BP2022 | TB | 110°30.47.98'E | 7°19.7.47'S | 50 | 80/210/320 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-SLT-2133 | KUTOWINANGUN KIDUL TINGKIR | B2S | TBG | Central | JATENG | Jawa Tengah | Kota Salatiga | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR 25:04:22: IW OG 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-TGL-2620 | 30739680031 | 1450921003 | TEGAL_BALAPULANG | BP2022 | TB | 109°10.0.99'E | 7°6.34.63'S | 70 | 0/150/260 | 2022 | Newsite 2022 - P2 |  | NOKIA | JAW-JT-TGL-2620 | TEGAL_BALAPULANG | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Tegal | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR LMS CHANGE TO NOKIA 13:04:22-08:04:22: IW OG 06:04:22: VALIDASI RNP TNP 06:04:22-24:03:22: IW OG 23:03:22-20:03:22: VALIDASI RNP TNP 16:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-BDG-4085 | 30742600031 | 1277171003 | CIBIRU_CILANGKRANG | BP2022 | TB | 107°43.51.09'E | 6°53.51.78'S | 50 | 110/255/330 | 2022 | Newsite 2021 |  | HTI | JAW-JB-BDG-4085 | CIBIRU_CILANGKRANG | B2S | TBG | Central | JABAR | Jawa Barat | Kota Bandung | 6618175 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW CLEAR, SOIL TEST 24:04:22-20:04:22: IW OG NEW CANDIATE 17:04:22-12:04:22: IW OG 10:04:22-09:04:22: VALIDASI RNP TNP 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-KLN-0935 | 30742740031 | 1451161003 | KLATEN_KEBONARUM | BP2022 | TB | 110°33.48.36'E | 7°43.2.61'S | 50 | 70/160/290 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-KLN-0935 | KLATEN_KEBONARUM | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Klaten | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-KLN-0920 | 30742880031 | 1451291003 | KLATEN_NGAWEN | BP2022 | TB | 110°36.36.31'E | 7°40.4.54'S | 50 | 80/170/310 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-KLN-0920 | KLATEN_NGAWEN | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Klaten | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-PWT-0593 | 30742840031 | 1451251003 | BANYUMAS_CILONGOK | BP2022 | TB | 109°7.42.32'E | 7°25.0.25'S | 70 | 100/180/290 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-PWT-0593 | BANYUMAS_CILONGOK | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Banyumas | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-YO-WAT-0324 | 30742810031 | 1510181003 | KULON_PROGO_NANGGULAN | BP2022 | TB | 110°13.40.25'E | 7°47.39.16'S | 70 | 60/180/320 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-YO-WAT-0324 | KULON_PROGO_NANGGULAN | B2S | TBG | Central | JATENG | DI Yogyakarta | Kab. Kulon Progo | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-BT-RKB-0788 | 30743260031 | 1321272003 | IBS PASIR AWI CILELES | BP2022 | TB | 106°3.39.6'E | 6°28.34.68'S | 60 | 60/150/310 |  |  |  | EID | JAW-BT-RKB-0788 | CIPADANG_CILELES | COLO | XL | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6618138 | 2022-03-18 | 2022-03-21 | 41 | 31 - 60 days | 2022-04-17 | W17-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [5 empty] | 2022-04-20 | [7 empty] | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 21:04:22: STO DECLARED 14:04:22: prepare cme 21:03:22: SPK REECIVED |  | 401
|  | JAW-JT-MKD-1117 | 30742710031 | 1451131003 | MAGELANG_MERTOYUDAN | BP2022 | TB | 110°12.48.96'E | 7°33.15.12'S | 50 | 90/210/320 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-MKD-1117 | MAGELANG_MERTOYUDAN | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-TMG-2676 | 30742690031 | 1451111003 | TEMANGGUNG_KEDU | BP2022 | TB | 110°10.8.34'E | 7°17.7.61'S | 70 | 60/150/300 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-TMG-2676 | TEMANGGUNG_KEDU | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Temanggung | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-SKH-1873 | 30742750031 | 1451171003 | WONOSOBO_SUKOHARJO | BP2022 | TB | 109°46.58.58'E | 7°24.7.32'S | 70 | 120/230/320 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-SKH-1873 | WONOSOBO_SUKOHARJO | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Sukoharjo | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JK-KYB-0279 | 30727670031 | 110436104 | PERTANIAN LBK BULUS | COMMITMENT 2021 (pengganti site REPEATER JAKATAN PARI) | SKP |  |  | 32 | 100/210/310 | 2021 |  | Jl. Pertanian Raya No.51F, Kel. Lebak Bulus RT.04 RW.02, Kec. Cilandak, Kota Jakarta Selatan Prov. DKI Jakarta | EID | JAW-JK-KYB-0279 | PERTANIAN LEBAK BULUS | COLO | XL | JABO | JABODETABEK | DKI Jakarta | Jakarta Selatan | 6617920 | 2022-01-14 |  | 104 | 91 - 120 days | 2022-02-13 | 2022-02-13 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [5 empty] | 2022-01-28 | [7 empty] | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | EID WAIT PO | 14:04:22: prepare cme 09:03:22-03:03:22: CME NY START, EID WAIT PO 28:01:22-23:01:22: NEED REVIEW TNP ALITA 19:01:22-16:01:22: ESR REVIEW 14:01:22: NEW SPK PENGGANTI REPEATER JAKATAN PARI |  | 401
|  | JAW-BT-TGR-0122 | 30743140031 | 131405109 | JLBOULEVARDPALEMRAYA | RELOCATION | SKP | 106°35.19.68'E | 6°14.14.75'S | 40 | 40/120/220 | 2021 | RELOCATION |  | EID | JAW-BT-TGR-0122 | LIPPO KARAWACI RELOCATION | COLO | XL | JABO | JABODETABEK | Banten | Kab. Tangerang | 6617925 | 2022-01-18 |  | 100 | 91 - 120 days | 2022-02-17 | W08-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [5 empty] | 2022-01-24 | [7 empty] | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | EID WAIT PO | 14:04:22: prepare cme 03:03:22: CME NY START, EID WAIT PO 28:01:22-23:01:22: NEED REVIEW CIVIL EID 19:01:22-18:01:22: SPK RELEASED FROM LMS TO EMAIL TBG |  | 401
|  | JAW-JT-PWD-0022 | 30742560031 | 1451061003 | TERKESI KLAMBU | BP2022 | TB | 110°45.43.39'E | 6°58.42.32'S | 42 | 0/90/190 | 2022 | Newsite 2021 |  | EID | JAW-JT-PWD-0022 | TERKESI KLAMBU | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Grobogan | 6618174 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-WSB-2943 | 30742550031 | 1451051003 | SUMBING KALIKUNING | BP2022 | TB | 109°59.39.76'E | 7°24.5.86'S | 50 | 80/240/325 | 2022 | Newsite 2021 |  | EID | JAW-JT-WSB-2943 | SUMBING KALIKUNING | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Wonosobo | 6618174 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | KAL-KI-TNR-1008 | 30740400031 | 2316071003 | REPEATER MUARA LESAN KELAY | NEW SITE 2022-REPEATER | TB | 117°6.30.53'E | 1°42.32.81'N | 70 | 137 |  | Newsite 2022 - Repeater |  | HTI | KAL-KI-TNR-1008 | REPEATER MUARA LESAN KELAY | B2S | TBG | Jabodetabek | KALIMANTAN | Kalimantan Timur | Kab. Berau | 6618120 | 2022-03-08 | 2022-03-09 | 51 | 31 - 60 days | 2022-08-05 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 12.CP Process | 07.SITAC PROCESS | NO POWER, TBG PROPOSE SOLAR CELL | 28:04:22: IW OG 24:04:22-16:03:22: SURVEY OG 13:03:22; MITRA ASSIGNMENT 09:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JT-PWT-0589 | 30742950031 | 1451301003 | BANYUMAS_KALIBAGOR | BP2022 | TB | 109°17.47.22'E | 7°30.5.51'S | 50 | 30/150/300 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-PWT-0589 | BANYUMAS_KALIBAGOR | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Banyumas | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 09.Under TNP review | 06.ERM PROCESS | PROPOSE CHANGE TO COLO | 28:04:22: IW OG 24:04:22-19:04:22: VALIDASI 17:04:22-10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-MKD-1120 | 30742670031 | 1451091003 | JALAN_DESA_SUTOPATI | BP2022 | TB | 110°3.32.4'E | 7°27.0.0'S | 70 | 0/100 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-MKD-1120 | JALAN_DESA_SUTOPATI | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 09.Under TNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-19:04:22: VALIDASI 17:04:22-10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-MKD-1121 | 30742680031 | 1451101003 | MAGELANG_KALIANGKRIK | BP2022 | TB | 110°5.13.2'E | 7°25.33.06'S | 70 | 0/100/190 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-MKD-1121 | MAGELANG_KALIANGKRIK | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 09.Under TNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-19:04:22: VALIDASI 17:04:22-10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
958 |  | KAL-KU-MLN-0094 | 30723460031 | 231297109 | SEBIDAY | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 116°38.34.74'E | 3°30.38.52'N | 40 | 90/220/300 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Desa Sempayang, Desa Sempayang RT 001, Kec. Malinau Barat, Kab. Malinau Prov. Kalimantan Utara | HTI | KAL-KU-MLN-0094 | MALINAU_BARAT_SEMPAYANG | COLO | XL | JABO | KALIMANTAN | Kalimantan Utara | Kab. Malinau | 6617766 | 2021-11-05 |  | 174 | > 150 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-24 | [7 empty] | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 17:03:22: MATERIAL HOLD BY PAK LURAH, NEED PERMIT 23:02:22-16:01:22: PREPARE MATERIAL 12:01:22-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: STO DECLARE, WAIT RFI BY HTI 21:11:21-07:11:21: ESR PROCESS OG,NEED REVIEW RNP HUAWEI |  | 401
|  | JAW-JT-TGL-2624 | 30739630031 | 1450901003 | TEGAL_TALANG | BP2022 | TB | 109°7.37.2'E | 6°54.34.2'S | 40 | 60/180/310 | 2022 | Newsite 2022 - P1 |  | NOKIA | JAW-JT-TGL-2624 | TEGAL_TALANG | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Tegal | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 24:04:22-21:04:22: VALIDASI 20:04:22-17:04:22: REHUNTING, LMS CHANGE TO NOKIA 13:04:22-05:04:22: REHUNTING, RNP NOK 03:04:22-30:03:22: VALIDASI RNP TNP 27:03:22-23:03:22: REHUNTING 20:03:22: VALIDASI RNP TNP 16:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30747880031 | 0720011003 | TANJUNG_KARI XL | BP2022 | TB | 103°39.53.28'E | 4°28.40.91'S | 65 | 25/160/265 |  | Newsite 2022 - P2 |  | HTI | SUM-SS-MRD-1002 | TANJUNG_KARI | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Se | 6618211 | 2022-04-19 | 2022-04-20 | 9 | < 30 days | 2022-09-16 | W38-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG 25:04:22: VALIDASI 24:04:22: SURVEY OG 20:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-SU-SRH-2251 |  | 228521004 | KAMPUNG_PON - RELOC | X RELOC TBG | SMI | 99°9.9.79'E | 3°27.27.25'N | 45 | 90/210/330 |  | RELOCATION | Dusun IV Desa Penggalangan Kec. Sei Bamban Kab. Serdang Bedagai Provinsi Sumatera Utara | HTI | SUM-SU-SRH-2251 | PON SERDANG BEDAGAI RELOCATION | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Serdang Bedagai | 6618058 | 2022-02-24 | 2022-02-25 | 63 | 61 - 90 days | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 16:03:22-06:03:22: BATAL RELOC, CONTINUE TO RENEWAL SITE EXISTING, NEED EVIDENCE CONFIRMATION 25:02:22: SPK RELEASED RELOCBY TP
|  | JAW-JT-CLP-0560 |  | 1446552023 | IBS KALIKUDI ADIPALA | RELOCATION | TB | 109°9.39.28'E | 7°37.50.38'S | 36 | 0/120/250 | 2022 | RELOCATION RIGHT |  | EID | JAW-JT-CLP-0560 | CILACAP_ADIPALA | COLO | XL | Central | JATENG | Jawa Tengah | Kab. Cilacap | 6618118 | 2022-03-08 | 2022-03-08 | 51 | 31 - 60 days | 2022-04-07 | W15-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [13 empty] | 19.Mobilisasi dan Demobilisasi |  | CURRENTLY NO ISSUE | 14:04:22: prepare cme 08:03:22: SPK RECEIVED |  | 401
955 |  | SUM-SU-TJB-2211 | 30720740031 | 022319123 | TANJUNG BALAI SELATAN | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 99°47.1.1'E | 2°55.55.02'N | 40 | 90/210/330 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Bandar jepang / Jalan Kavling, Link. IV Kelurahan Pahang, Kecamatan Datuk bandar, Kota Tanjung balai Prov. Sumatera utara | HTI | SUM-SU-TJB-2211 | DATUK_BANDAR_PAHANG | COLO | XL | WEST | SUMBAGUT | Sumatera Utara | Kota Tanjung Balai | 6617742 | 2021-10-25 |  | 185 | > 150 days | 2021-11-24 | W48-2021 | Nov-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-02 | [7 empty] | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | PERMANENISASI | 14:04:22: PREPARE CME 17:03:22-12:01:22: WAITING PERMANENISASI GM KE SST 05:01:22-02:01:22: WAITING PERMIT 02:01:22-29:12:21: PERMANENISASI GM KE SST 26:12:21-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-03:11:21: NEED REVIEW RNP, STO DECLARE 2 NOV |  | 401
NEW SPK B2S |  | JAW-JT-KRG-2156 | 30729340031 | 1450201003 | KARANGANYAR_MOJOGEDANG | BP2022 | TB | 111°3.3.6'E | 7°34.14.16'S | 70 | 90/220/330 | 2022 | New site 2022 - P2 |  | NOKIA | JAW-JT-KRG-2156 | KARANGANYAR_MOJOGEDANG | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Karanganyar | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: IW OG LMS CHANGE TO NOKIA 13:04:22: IW OG 10:04:22-15:03:22: VALIDASI RNP TNP 13:03:22: REHUNTING 09:03:22-23:02:22: VALIDASI RNP TNP 22:02:22-20:02:22: REHUNTING REJECT WARGA 16:02:22-09:02:22: IW OG 06:02:22-04:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUL-SN-MLL-1572 | 30730250031 | 2817571003 | BAYONDO_TOMONI | BP2022 | TB | 120°48.54.31'E | 2°32.7.67'S | 60 | 0/180/270 | 2022 |  |  | HTI | SUL-SN-MLL-1572 | BAYONDO_TOMONI | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Luwu Timur | 6618149 | 2022-03-24 | 2022-03-24 | 35 | 31 - 60 days | 2022-08-21 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 12.CP Process | 07.SITAC PROCESS | RND NOK | 28:04:22: IW 27:04:22: VALIDASI 24:04:22-19:04:22: REHUNTING 17:04:22: VALIDASI RNP TNP 13:04:22-05:04:22: RNP NOK 03:04:22-27:03:22: SURVEY OG 24:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-UJT-0953 | 30729890031 | 0416571003 | LABUHAN_PAPAN | BP2022 | TB | 101°4.19.2'E | 1°40.58.98'N | 50 | 40/230/310 | 2022 | New site 2022 - P2 | Jl. Kalifah Ali RT.003 RW.003 Kepenghuluan Labuhan Papan Kecamatan Tanah Putih Tanjung Melawan Kabupaten Rokan Hilir Provinsi Riau | HTI | SUM-RI-UJT-0953 | LABUHAN_PAPAN | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Rokan Hilir | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-31 | 2022-04-01 | [10 empty] | CME | 33.ME & Grounding system process | 19.MECHANICAL & ELECTRICAL OG | CURRENTLY NO ISSUE | 28:04:22: ME OG 24:04:22-20:04:22: ERECTION 17:04:22: POURING 13:04:22-10:04:22: REBARRING 06:04:22: BOUWPLANK 03:04:22-23:03:22: RFC 20:03:22-09:03:22: REKOM OG 06:03:22-23:02:22: IW OG 20:02:22-16:02:22: VALIDASI RNP TNP OG 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
927 |  | JAW-BT-CPT-0396 |  |  |  | X RENEWAL |  |  |  | 0 |  |  |  |  | EID | JAW-BT-CPT-0396 | PONDOK CABE TERMINAL RELOCATION | COLO |  | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614690 | 2020-04-24 |  | 734 | > 150 days | 2020-05-24 | W22-2020 | May-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | [14 empty] | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION |  | 22.06.20 : 11.06.20 : 08.06.20 : 28.05.20 :
|  |  | 30749850031 |  |  |  | TB | 104°1.44.79'E | 1°3.40.7'N | 30 | 0/90/220 |  |  |  | HTI | SUM-KR-BTM-0613 | SUNGAI_BEDUK_MUKA_KUNING | B2S | TBG | West | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6618227 | 2022-04-26 | 2022-04-26 | 2 | < 30 days | 2022-09-23 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 03.Survey ny start | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 28:04:22: MITRA ASSIGNMEN 26:04:22: SPK RECEIVED |  | 401 | 388 TBG
[6 empty] | BP2022 | TB | 106°0.21.41'E | 6°30.36.26'S | 70 | 90/210/330 |  | Newsite 2022 - B2 |  | EID | JAW-BT-RKB-0786 | MEKARJAYA_CILELES | B2S | TBG | JABO | JABODETABEK | Kab. Lebak | New Build | 6618216 | 2022-04-22 | 2022-04-25 | 6 | < 30 days | 2022-09-19 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 03.Survey ny start | 03.SURVEY PROCESS | PROPOSE TO COLO | 28:04:22: MITRA ASSIGNMENT 25:04:22: SPK RECEIVED |  | 401 | 388 TBG
[6 empty] | BP2022 | TB | 106°36.3.18'E | 6°5.7.5'S | 40 | 0/120/240 |  | Newsite 2022 - P2 |  | EID | JAW-BT-TGR-0114 | RAWA_BONI_PAKUHAJI | B2S | TBG | JABO | JABODETABEK | Kab. Tangerang | New Build | 6618216 | 2022-04-22 | 2022-04-25 | 6 | < 30 days | 2022-09-19 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 03.Survey ny start | 03.SURVEY PROCESS | PROPOSE TO COLO | 28:04:22: MITRA ASSIGNMENT 25:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30749830031 |  |  |  | TB | 113°56.48.7'E | 2°15.29.9'S | 50 | 0/165/290 |  |  |  | HTI | KAL-KT-PLK-0442 | PAHANDUT_PANARUNG | B2S | TBG | Central | KALIMANTAN | Kalimantan Tengah | Kota Palangkaraya | 6618227 | 2022-04-26 | 2022-04-26 | 2 | < 30 days | 2022-09-23 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 03.Survey ny start | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 28:04:22: MITRA ASSIGNMENT 26:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30749840031 |  |  |  | TB | 115°17.56.98'E | 2°22.23.36'S | 60 | 20/190/280 |  |  |  | HTI | KAL-KS-AMT-0950 | AMUNTAI_UTARA | B2S | TBG | Central | KALIMANTAN | Kalimantan Selatan | Kab. Hulu Sungai Utara | 6618227 | 2022-04-26 | 2022-04-26 | 2 | < 30 days | 2022-09-23 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 03.Survey ny start | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 28:04:22: MITRA ASSIGNMENT 26:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-SU-TRT-2017 | 30738840031 | 0229281003 | DOLOK_MATUMBUR | BP2022 | TB | 98°57.2.52'E | 2°19.41.09'N | 50 | 70/160/310 | 2022 | New site 2022 - P2 | Jalan Propinsi, Dolok Martumbur, Kecamatan Muara Kabupaten Tapanuli Utara Prop Sumatera Utara | HTI | SUM-SU-TRT-2017 | DOLOK_MATUMBUR | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Tapanuli Utara | 6618062 | 2022-02-25 | 2022-02-25 | 62 | 61 - 90 days | 2022-07-25 | W31-2022 | Jul-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-11 | 2022-03-15 |  | 6.6 | [8 empty] | SITAC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | RFI COMBAT | 28:04:22: MOBDEMOB REPLACE PERANGKAT COMBAT 24:04:22-30:03:22: REKOM OG 27:03:22-20:03:22: PROSES DELIVERY COMBAT & PARALEL IW OG 16:03:22-10:03:22: IW OG 09:03:22-06:03:22: VALIDASI RNP TNP 28:02:22: SURVEY OG 25:02:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-KJN-1006 | 30729260031 | 1450151003 | KARANGREJO_KESESI | BP2022 | TB | 109°31.17.59'E | 7°1.3.59'S | 50 | 0/100/280 | 2022 | New site 2022 - P2 |  | NOKIA | JAW-JT-KJN-1006 | KARANGREJO_KESESI | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Pekalongan | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | WAIT PSB | 28:04:22: MOBDEMOB 20:04:22: IW OG 18:04:22: UNDER TNP LMS CHANGE TO NOKIA 13:04:22: REHUNTING 10:04:22-31:03:22: IW OG 30:03:22: VALIDASI RNP TNP KANDIDAT G 27:03:22-23:03:22: IW OG 21:03:22: VALIDASI RNP TNP KANDIDAT F 20:03:22-18:03:22: VALIDASI RNP TNP 16:03:22-15:03:22: IW OG 13:03:22-07:03:22: VALIDASI RNP TNP 06:03:22: REHUNTING, IW FAILED 28:02:22-08:02:22: IW OG 07:02:22: RNP OK, TNP OP -> VALIDASI CANDIDATE B, KANDIDAT A REJECT WARGA 06:02:22-04:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  |  | 30735460031 | 090170109 | BENGKULU2014_2G5 | BP2022 | TB | 102°21.27.95'E | 3°54.8.16'S | 50 | 20/150/310 |  | Newsite 2022 - P2 |  | HTI | SUM-BE-TAS-0214 | SUKARAJA_BABATAN | B2S | TBG | West | SUMBAGSEL | Bengkulu | Kab. Seluma | 6618217 | 2022-04-22 | 2022-04-25 | 6 | < 30 days | 2022-09-19 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 03.Survey ny start | 03.SURVEY PROCESS | PROPOSED TO COLO | 28:04:22: PLAN SURVEY 9 MAY 22 25:04:22: SPK RECEIVED |  | 401 | 388 TBG
[6 empty] | BP2022 | TB | 103°30.56.48'E | 4°29.9.38'S | 65 | 100/240/335 |  | Newsite 2022 - P2 |  | HTI | SUM-SS-MRD-1011 | SIMPANG_LUAS | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Se | 6618217 | 2022-04-22 | 2022-04-25 | 6 | < 30 days | 2022-09-19 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 03.Survey ny start | 03.SURVEY PROCESS | PROPOSED TO COLO | 28:04:22: PLAN SURVEY 9 MAY 22 25:04:22: SPK RECEIVED |  | 401 | 388 TBG
[6 empty] | BP2022 | TB | 103°36.22.18'E | 4°29.31.7'S | 50 | 120/290 |  | Newsite 2022 - P2 |  | HTI | SUM-SS-MRD-1008 | TANJUNG_BULAN_ULU | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Se | 6618217 | 2022-04-22 | 2022-04-25 | 6 | < 30 days | 2022-09-19 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 03.Survey ny start | 03.SURVEY PROCESS | PROPOSED TO COLO | 28:04:22: PLAN SURVEY 9 MAY 22 25:04:22: SPK RECEIVED |  | 401 | 388 TBG
[6 empty] | BP2022 | TB | 103°33.48.4'E | 4°26.39.25'S | 65 | 15/100/200 |  | Newsite 2022 - P2 |  | HTI | SUM-SS-MRD-1014 | PEMATANG_DANAU | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Se | 6618217 | 2022-04-22 | 2022-04-25 | 6 | < 30 days | 2022-09-19 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 03.Survey ny start | 03.SURVEY PROCESS | PROPOSED TO COLO | 28:04:22: PLAN SURVEY 9 MAY 22 25:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30749860031 |  |  |  | TB | 106°22.50.8'E | 2°28.46.5'S | 50 | 110/220/280 |  |  |  | HTI | SUM-BB-KBA-0535 | KOBA_ARUNG_DALAM | B2S | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kab. Bangka Tengah | 6618227 | 2022-04-26 | 2022-04-26 | 2 | < 30 days | 2022-09-23 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 03.Survey ny start | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 28:04:22: PLAN SURVEY 9 MAY 22 26:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30749870031 |  |  |  | TB | 104°54.14.91'E | 4°49.43.31'S | 40 | 0/95/250 |  |  |  | HTI | SUM-LA-KTB-1136 | KOTABUMI_REJOSARI | B2S | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Utara | 6618227 | 2022-04-26 | 2022-04-26 | 2 | < 30 days | 2022-09-23 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 03.Survey ny start | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 28:04:22: PLAN SURVEY 9 MAY 22 26:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30749820031 |  |  |  | TB | 98°28.0.63'E | 3°55.6.49'N | 60 | 20/110/210 |  |  |  | HTI | SUM-SU-STB-2202 | TANJUNGPURA_PANTAI_CERMIN | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Langkat | 6618227 | 2022-04-26 | 2022-04-26 | 2 | < 30 days | 2022-09-23 | W39-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 03.Survey ny start | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 28:04:22: PLAN SURVEY AFTER LEBARAN, VALIDASI 11 26:04:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SN-WNS-0985 | 30729150031 | 2817541003 | KELURAHAN_LAPAJUNG_LALABATA | BP2022 | TB | 119°52.41.39'E | 4°20.18.64'S | 50 | 50/150/250 | 2022 | New site 2022 - P2 | JL. PESANTREN, RT/RW. 000/000, KELURAHAN LAPAJUNG, KECAMATAN LALABATA, KABUPATEN SOPPENG, PROVINSI SULAWESI SELATAN. | HTI | SUL-SN-WNS-0985 | KELURAHAN_LAPAJUNG_LALABATA | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Soppeng | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-21 | 2022-03-23 | [10 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: PLN 24:04:22: CURRING 20:04:22-13:04:22: BOUWPLANK, HOLD REKOM :04:22-06:04:22: BOUWPLANK 03:04:22-23:03:22: WAITING APD 20:03:22-16:03:22: REKOM 13:03:22-04:03:22: IW OG 02:03:22: VALIDASI RNP TNP 28:02:22-13:02:22: IW OG 09:02:22: RNP TNP OG -> IW OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-BKN-1167 | 30729860031 | 0416541003 | KUSAU_MAKMUR | BP2022 | TB | 100°50.51.59'E | 0°37.52.5'N | 60 | 60/170/260 | 2022 | New site 2022 - P2 | Jl. Lintas Petapahan - Bangkinang RT 003 RW 001 Desa Kusau Makmur Kecamatan Tapung Hulu Kabupaten Kampar Provinsi Riau | HTI | SUM-RI-BKN-1167 | KUSAU_MAKMUR | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Kampar | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | 2022-03-15 | [10 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: PLN 24:04:22: ERECTION 20:04:22: ERECTION 17:04:22-14:03:22: BACKFILLING 10:04:22: CURRING TIME 06:04:22: EXCAVATION 03:04:22-27:03:22: LAND CLEARING & BOUWPLANK 23:03:22-13:03:22: RFC 09:03:22: REKOM OG 06:03:22-28:02:22: IW CLEAR 23:02:22-16:02:22: IW OG 13:02:22-11:02:22: VALIDASI RNP TNP 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SS-RPT-1105 | 30730050031 | 0719171003 | MUARA_RUPIT | BP2022 | TB | 102°54.5.61'E | 2°44.17.43'S | 50 | 50/230/330 | 2022 | New site 2022 - P2 | RT.15 RW.03 Kel.Muara Rupit Kecamatan Rupit Kabupaten Musi Rawas Utara Provinsi Sumatra Selatan | HTI | SUM-SS-RPT-1105 | MUARA_RUPIT | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas Utara | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-02 | [10 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: PLN 24:04:22-06:04:22: PREPARE ERECTION 03:04:22: EXCA 30:03:22-27:03:22: BOUWPLANK 23:03:22-06:03:22: REKOM 28:02:22-23:02:22: IW CLEAR 20:02:22-16:02:22: IW OG 15:02:22-14:02:22: VALIDASI RNP TNP 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUM-SU-STB-2231 | 30730330031 | 0229071003 | SECANGGANG_KARANG_GADING | BP2022 | TB | 98°34.35.47'E | 3°50.4.25'N | 50 | 80/160/300 |  |  | DS.DUSUN VI MERBAU RINTIS KARANG GADING, SECANGGANG, KAB. LANGKAT, SUMATERA UTARA | HTI | SUM-SU-STB-2231 | SECANGGANG_KARANG_GADING | B2S | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6618193 | 2022-04-07 | 2022-04-07 | 21 | < 30 days | 2022-09-04 | W37-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 2022-04-10 | 2022-04-11 | [10 empty] | CME | 37.Power connection process | 20.SRFI | COMMCASE | 28:04:22: PLN 24:04:22-10:04:22: ERECTION 07:04:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-SRH-2245 | 30729790031 | 0228981003 | MELATI_II | BP2022 | TB | 98°58.52.34'E | 3°31.6.86'N | 60 | 90/220/320 | 2022 | New site 2022 - P2 | Dusun Cempedak Desa Melati II Kecamatan Perbaungan Kabupaten Serdang Bedagai Provinsi Sumatera Utara | HTI | SUM-SU-SRH-2245 | MELATI_II | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Serdang Bedagai | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-21 | 2022-03-23 |  |  |  | 2022-04-21 | [6 empty] | CME | 37.Power connection process | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: PLN 24:04:22-20:04:22: CURRING 17:04:22: POURING 13:04:22-10:04:22-06:04:22: REBARRING 03:04:22-16:03:22: PERMIT OG 13:03:22: REKOM 09:03:22-06:03:22: IW CLEAR 28:02:22-13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-BB-MGR-0528 | 30730180031 | 0804351003 | KELAPA_KAMPIT_MAYANG | BP2022 | TB | 108°5.22.93'E | 2°41.12.66'S | 50 | 90/240/340 | 2022 | New site 2022 - P1 | Jl. Gg Madura,RT.010, RW. 005, Dusun Balai Selatan, Desa Mayang,Kecamatan Kelapa Kampit,Kabupaten Belitung Timur, Provinsi Kepulauan Bangka Belitung | HTI | SUM-BB-MGR-0528 | KELAPA_KAMPIT_MAYANG | B2S | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kab. Belitung Timur | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-02 | [10 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: PLN 24:04:22-20:04:22: ERECTION 17:04:22: CURRING TIME 13:04:22-10:04:22: EXCAVATION 03:04:22: BOUWPLANK 30:03:22-27:03:22: DELIVERY MATERIAL 23:03:22-06:03:22: REKOM 28:02:22-23:02:22: IW CLEAR 20:02:22-16:02:22: IW OG 14:02:22: VALIDASI RNP TNP 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JT-KDS-0862 | 30725610031 | 1449631003 | HONGGO YUDHO MEJOBO | ACTIVE - BLITZKRIEG | TB | 110°53.20.08'E | 6°49.44.04'S | 50 | 40/140/280 | 2021 | New site 2021 | Gg Kusumo RT 006 RW 001 Desa Mejobo Kecamatan Mejobo Kabupaten Kudus Provinsi Jawa Tengah. | EID | JAW-JT-KDS-0862 | HONGGO YUDHO MEJOBO | B2S | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Kudus | 6617945 | 2022-01-24 |  | 94 | 91 - 120 days | 2022-06-23 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 |  |  | 6.6 | [8 empty] | RFC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | WAIT PSB | 28:04:22: PREPARE CME 24:04:22: APD DAN PREPARE TEAM 20:04:22-13:04:22: REKOM 10:04:22-03:04:22: IW CLEAR 30:03:22-23:03:22: IW OG 22:03:22: VALIDASI RNP TNP 20:03:22-07:03:22: DIMINTA GESER MENDEKATI PEMUKIMAN, OG REHUNTING 06:03:22-01:03:22: VALIDASI RNP TNP 28:02:22-22:02:22: IW OG 21:02:22: VALIDASI RNP TNP KANDIDAT ARAHAN 20:02:22: REHUNTING ARAHAN XL 16:02:22: IW FAILED, VALIDASI RNP TNP 13:02:22-06:02:22: IW OG (25 kk kurang 13 kk) 02:02:22-30:01:22: VALIDASI KANDIDAT OG 26:01:22: SURVEY OG 24:01:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JK-GGP-0447 | 30739520031 | 1137601003 | PELITA_DAAN_MOGOT | BP2022 | TB | 106°44.8.26'E | 6°9.12.85'S | 25 | 90/210/330 | 2022 | Newsite 2022 - B2 |  | EID | JAW-JK-GGP-0447 | PELITA_DAAN_MOGOT | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: PROPOSED DROP BY XL 24:04:22-03:04:22: IW CLEAR 30:03:22-09:02:22: SURVEY OG 07:02:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SA-ARM-0427 | 30730450031 | 2405941003 | WUSA_TALAWAAN | BP2022 | TB | 124°54.59.4'E | 1°34.6.13'N | 50 | 110/190/270 | 2022 | New site 2022 - P2 | Jl. Wusa Pandu, Jaga V, Desa Wusa, RT/RW 000/000, Kacamatan Talawaan, Kabupaten Minahasa Utara, Propinsi Sulawesi Utara | HTI | SUL-SA-ARM-0427 | WUSA_TALAWAAN | B2S | TBG | East | SULAWESI | Sulawesi Utara | Kab. Minahasa Utara | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-21 | 2022-03-23 | [10 empty] | CME | 24.Rebaring | 13.REBARING OG | CURRENTLY NO ISSUE | 28:04:22: rebaring 24:04:22: EXCAVATION 23:03:22: WAITING APD & REKOM 20:03:22-09:03:22: REKOM OG 06:03:22-13:02:22: IW OG 09:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUM-RI-PRP-1113 | 30740150031 | 0416961003 | RAMBAH_PEMATANG_BERANGAN | BP2022 | TB | 100°17.43.0'E | 0°52.48.29'N | 50 | 50/250/2- | 2022 | Newsite 2022 - P2 | Rt 001 Rw 001 Dusun Tulang Gajah Desa Pematang Barangan Kecamatan Rambah Kab. Rokan Hulu Provinsi Riau | HTI | SUM-RI-PRP-1113 | RAMBAH_PEMATANG_BERANGAN | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Rokan Hulu | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-10 | 2022-04-11 | [10 empty] | CME | 24.Rebaring | 13.REBARING OG | CURRENTLY NO ISSUE | 28:04:22: REBARRING 24:04:22: EXCAVATION 20:04:22-06:04:22: BOUWPLANK 03:04:22: REKOM 30:03:22-23:03:22: IW CLEAR 22:03:22: IW OG 20:03:22-13:03:22: VALIDASI RNP TNP OG 09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | BAL-BA-TAB-1961 | 30740190031 | 1721121003 | BATURITI_PEREAN_KANGIN | BP2022 | TB | 115°12.45.22'E | 8°26.11.5'S | 60 | 0/170/270 | 2022 | Newsite 2022 - P2 | Br. Basangbe Desa Perean Kangin Kec. Baturiti Kab. Tabanan Prov. Bali | HTI | BAL-BA-TAB-1961 | BATURITI_PEREAN_KANGIN | B2S | TBG | East | BALINUSRA | Bali | Kab. Tabanan | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-11 | 2022-04-13 | [10 empty] | RFC | 24.Rebaring | 13.REBARING OG | CURRENTLY NO ISSUE | 28:04:22: REBARRING 24:04:22: RFC 10:04:22: REKOM 06:04:22-03:04:22: IW CLEAR 30:03:22-17:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SS-RPT-1101 | 30730090031 | 0719191003 | BUMI_MAKMUR | BP2022 | TB | 103°1.40.8'E | 2°28.29.32'S | 60 | 45/180/300 | 2022 | New site 2022 - P2 | Desa Bumi Makmur Kecamatan Nibung Kabupaten Musi Rawas Utara Provinsi Sumatra Selatan | HTI | SUM-SS-RPT-1101 | BUMI_MAKMUR | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas Utara | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-02 | [10 empty] | CME | 24.Rebaring | 13.REBARING OG | CURRENTLY NO ISSUE | 28:04:22: REBARRING 24:04:22-10:04:22: EXCAVATION 06:04:22-03:04:22: PREPARE CME 30:03:22-27:03:22: REKOM OG 23:03:22-06:03:22: REKOM 28:02:22: IW CLEAR 23:02:22-16:02:22: IW OG 13:02:22-11:02:22: VALIDASI RNP TNP 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-BT-RKB-0770 | 30729420031 | 1322991003 | KERSARATU_MALINGPING | BP2022 | TB | 106°2.27.52'E | 6°46.34.75'S | 70 | 60/250 | 2022 | New site 2022 - P2 | Kp. CIPEUNDEY LEBAK RT.001/001 Desa KERSARATU Kec. MALINPING KAB.LEBAK | EID | JAW-BT-RKB-0770 | KERSARATU_MALINGPING | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 3/7/2022, , resend 28 apr 22 |  |  | 6.6 | 2022-04-20 | [7 empty] | CME | 24.Rebaring | 13.REBARING OG | CURRENTLY NO ISSUE | 28:04:22: REBARRING 24:04:22-13:04:22: EXCAVATION 10:04:22-03:04:22: RFC 30:03:22-06:03:22: REKOM OG 28:02:22: IW CLEAR & PARALEL COLLECT DOC 23:02:22-16:02:22: IW OG 13:02:22-03:02:22: VALIDASI RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | BAL-BA-MGW-1570 | 30742390031 | 1721141003 | RAYA NUSA DUA RELOCATION | RELOCATION | TB | 115°11.41.58'E | 8°47.5.36'S | 30 | 80/170/320 | 2022 |  |  | CAA | BAL-BA-MGW-1570 | RAYA NUSA DUA RELOCATION | B2S | TBG | East | BALINUSRA | Bali | Kab. Badung | 6618151 | 2022-03-24 | 2022-03-24 | 35 | 31 - 60 days | 2022-08-21 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22: REHUNTING ARAHAN 24:04:22-27:03:22: SURVEY OG 24:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-NPH-4384 | 30739880031 | 1276931003 | CILILIN_PASAR_CILILIN | BP2022 | TB | 107°27.25.75'E | 6°57.3.17'S | 40 | 20/150/270 | 2022 | Newsite 2022 - P1 |  | HTI | JAW-JB-NPH-4384 | CILILIN_PASAR_CILILIN | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Bandung Barat | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: REHUNTING CAND 6 24:04:22-12:04:22: IW OG 10:04:22-06:04:22: REHUNTING, VALIDASI RNP TNP 05:04:22: RNP NOK 03:04:22-24:03:22: IW OG 23:03:22: VALIDASI RNP TNP 23:03:22-20:03:22: REHUNTING 16:03:22-11:03:22: VALIDASI RNP TNP -> RNP NOK, REHUNTING 09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-TSM-4152 | 30742630031 | 1277181003 | PURBARATU_SUKANAGARA | BP2022 | TB | 108°14.46.36'E | 7°19.59.88'S | 30 | 60/205/295 | 2022 | Newsite 2021 |  | HTI | JAW-JB-TSM-4152 | PURBARATU_SUKANAGARA | B2S | TBG | Central | JABAR | Jawa Barat | Kota Tasikmalaya | 6618175 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22: REHUNTING 12:04:22: IW OG 10:04:22-09:04:22: VALIDASI RNP TNP 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-NPH-3751 | 30739810031 | 1276911003 | PADAASIH | BP2022 | TB | 107°33.13.59'E | 6°50.49.29'S | 30 | 20/120/220 | 2022 | Newsite 2022 - B2 |  | HTI | JAW-JB-NPH-3751 | PADAASIH | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Bandung Barat | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22: REHUNTING 24:04:22: IW NEW CANDIATE 12:04:22: IW OG 10:04:22-01:04:22: VALIDASI RNP TNP 30:03:22-27:03:22: REHUNTING 23:03:22-15:03:22: IW OG 13:03:22: VALIDASI RNP TNP 12:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-BYL-0264 | 30742760031 | 1451181003 | BOYOLALI_SAWIT | BP2022 | TB | 110°40.31.85'E | 7°35.7.47'S | 50 | 20/110/260 | 2022 | Newsite 2022 - B2 |  | NOKIA | JAW-JT-BYL-0264 | BOYOLALI_SAWIT | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Boyolali | 6618156 | 2022-03-28 | 2022-04-05 | 31 | 31 - 60 days | 2022-08-25 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22: REHUNTING 24:04:22-13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JT-TGL-2622 | 30739710031 | 1450941003 | TEGAL_KRAMAT | BP2022 | TB | 109°11.1.99'E | 6°53.19.05'S | 50 | 60/180/310 | 2022 | Newsite 2022 - P2 |  | NOKIA | JAW-JT-TGL-2622 | TEGAL_KRAMAT | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Tegal | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22: REHUNTING 24:04:22-17:04:22: VALIDASI RNP TNP, LMS CHANGE TO NOKIA 13:04:22-20:03:22: VALIDASI RNP TNP 16:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-SPA-4132 | 30742590031 | 1277161003 | LEUWISARI_CIAWANG | BP2022 | TB | 108°6.51.72'E | 7°19.30.15'S | 40 | 0/205/270 | 2022 | Newsite 2021 |  | HTI | JAW-JB-SPA-4132 | LEUWISARI_CIAWANG | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Tasikmalaya | 6618175 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22: REHUNTING 24:04:22-20:04:22: IW OG 19:04:22: VALIDASI 17:04:22-12:04:22: IW OG 10:04:22-09:04:22: VALIDASI RNP TNP 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-RI-PBR-1186 | 30725600031 | 0416301003 | SRI_MERANTI | ACTIVE - BLITZKRIEG H2 | TB | 101°25.51.68'E | 0°33.29.18'N | 40 | 90/190/320 | 2021 | New site 2021 - H2 |  | HTI | SUM-RI-PBR-1186 | SRI_MERANTI | B2S | TBG | WEST | SUMBAGTENG | Riau | Kota Pekanbaru | 6617944 | 2022-01-24 |  | 94 | 91 - 120 days | 2022-06-23 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22: REHUNTING 24:04:22-30:03:22: IW OG 27:03:22-24:03:22: VALIDASI RNP TNP KANIDAT F 23:03:22-15:03:22: REHUNTING, RNP NOK KANDIDAT E 14:03:22: VALIDASI RNP TNP, IW FAILED KANDIDAT D 13:03:22-09:03:22: IW OG 09:03:22-08:02:22: VALIDASI RNP TNP 06:03:22-26:01:22: SURVEY OG 24:01:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JI-BJN-4293 | 30740050031 | 1655141003 | KALITIDU_WOTANNGARE | BP2022 | TB | 111°45.32.4'E | 7°9.18.72'S | 50 | 0/180/275 | 2022 | Newsite 2022 - P2 |  | HTI | JAW-JI-BJN-4293 | KALITIDU_WOTANNGARE | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CELL PLAN ISSUE | 28:04:22: REHUNTING 25:04:22: VALIDAIS NOK, FAR FROM NOM, CELL PLAN LOCATION RADIUS 1KM 24:04:22-07:04:22: IW OG 06:04:22-05:04:22: VALIDASI RNP TNP 03:04:22:-15:03:22: VALIDASI RNP TNP (KANDIDAT OUTCELL) 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-BGR-0234 | 30733540031 | 1276281003 | BANTARJATI RELOCATION | RELOCATION | TB | 106°49.6.37'E | 6°34.47.97'S | 35 | 10/100/200/290 | 2022 | RELOCATION - PROTELINDO |  | EID | JAW-JB-BGR-0234 | BANTARJATI RELOCATION | B2S | TBG | JABO | JABODETABEK | Jawa Barat | Kota Bogor | 6618026 | 2022-02-07 | 2022-02-07 | 80 | 61 - 90 days | 2022-07-07 | W28-2022 | Jul-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | HARDSITAC NO FREE SPACE | 28:04:22: REHUNTING, PLAN 30 APRIL 2022 03:04:22: VALIDASI RNP TNP 30:03:22-09:02:22: SURVEY OG 07:02:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JK-KYB-0467 | 30729560031 | 1136861003 | CEMPAKA_HARAPAN_MULIA | BP2022 | TB | 106°51.24.88'E | 6°9.58.21'S | 25 | 90/210/330 | 2022-2024 | New site 2022 - P1 | Jl. H. Ung RT 07 RW 04 Kelurahan Utan Panjang, Kecamatan Kemayoran, Kota Jakarta Pusat, DKI Jakarta | EID | JAW-JK-KYB-0467 | CEMPAKA_HARAPAN_MULIA | B2S | TBG | Jabodetabek | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Pusat | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: RE-IW 24:04:22-13:04:22: REKOM 10:04:22-25:03:22: PROPOSE MCP 23:03:22-28:02:22: REKOM OG 23:02:22: IW CLEAR 20:02:22-16:02:22: VALIDASI RNP TNP 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUL-ST-PSO-1137 | 30740390031 | 2605131003 | REPEATER TANGKURA POSO | NEW SITE 2022-REPEATER | TB | 120°37.51.69'E | 1°31.25.21'S | 55 | 185 |  | Newsite 2022 - Repeater | Jalan Werainu, Desa Tangkura, Kec. Peisir Poso Selatan, Kab. Poso, Prop Sulteng | HTI | SUL-ST-PSO-1137 | REPEATER TANGKURA POSO | B2S | TBG | East | SULAWESI | Sulawesi Tengah | Kab. Poso | 6618120 | 2022-03-08 | 2022-03-09 | 51 | 31 - 60 days | 2022-08-05 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 2022-04-28 | [11 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | NO POWER, TBG PROPOSE SOLAR CELL | 28:04:22: REKOM DONE 24:04:22-05:04:22: IW OG, WAIT DECISSION XL SOLAR PANEL OR CDC 04:04:22: VALIDASI RNP TNP 03:04:22-20:03:22: SURVEY OG, DAERAH TIDAK ADA JARINGAN & DAERAH RAWAN TERORIS 16:03:22-13:03:22: MITRA ASSIGNMENT 09:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | KAL-KT-SPT-0703 | 30739720031 | 2107511003 | BAAMANG_TENGAH_BAAMANG | BP2022 | TB | 112°56.1.96'E | 2°30.31.03'S | 50 | 80/190/305 | 2022 | Newsite 2022 - B2 | Area Golf Driving Komplek Perumahan Wengga Metropolitan Jl. Wengga Metropolitan Kelurahan Baamang Barat Kecamatan Baamang Kabupaten Kotawaringin Timur Provinsi Kalimantan Tengah | HTI | KAL-KT-SPT-0703 | BAAMANG_TENGAH_BAAMANG | B2S | TBG | Central | KALIMANTAN | Kalimantan Tengah | Kab. Kotawaringin Timur | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: REKOM KKOP 24:04:22-30:03:22: IW OG 27:03:22-08:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-NPH-4378 | 30740120031 | 1277011003 | BONGAS | BP2022 | TB | 107°25.55.57'E | 6°57.34.83'S | 50 | 55/160/335 | 2022 | Newsite 2022 - P2 | Kp. Datar Manggu Rt. 001 Rw. 010 Desa. Bongas Kec. Cililin Kab Bandung Barat | HTI | JAW-JB-NPH-4378 | BONGAS | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Bandung Barat | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: REKOM 24:04:22: IW OG 21:04:22: VALIDASI KANDIDAT BERGESER 20:04:22-13:04:22: IW OG 10:04:22-06:04:22: VALIDASI RNP TNP 03:04:22-13:03:22: IW OG 11:03:22: VALIDASI RNP TNP 09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | KAL-KS-TJG-1107 | 30730650031 | 2209811003 | KARANGAN_PUTIH_KELUA | BP2022 | TB | 115°16.24.44'E | 2°14.26.39'S | 60 | 55/150/330 | 2022 | New site 2022 - P2 | Jl. Ayani Km 5 RT.03 Desa Karangan Putih Kec. Kelua Kab. Tabalong Prov.Kalsel | HTI | KAL-KS-TJG-1107 | KARANGAN_PUTIH_KELUA | B2S | TBG | Central | KALIMANTAN | Kalimantan Selatan | Kab. Tabalong | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: REKOM 24:04:22-17:04:22: IW OG 14:04:22: VALIDASI RNP TNP -> IW OG 13:04:22-13:03:22: BAN/BAK 09:03:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JB-SPA-4240 | 30730210031 | 1276211003 | CIKUNTEN | BP2022 | TB | 108°5.47.6'E | 7°21.39.57'S | 30 | 90/180/320 | 2022 | New site 2022 - P1 | Kp. Cicarulang Rt 15 Rw 06 Desa Cikunten Kecamatan Singaparna Kab. Tasikmalaya Propinsi Jawa Barat | HTI | JAW-JB-SPA-4240 | CIKUNTEN | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Tasikmalaya | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-03 | [10 empty] | PRESITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: REKOM 24:04:22-18:04:22: VALIDASI 17:04:22-13:04:22: IW OG 12:04:22-27:03:22: REHUNTING 23:03:22-09:03:22: REKOM 07:03:22-28:02:22: VALIDASI RNP TNP 23:02:22-20:02:22: REKOM OG 16:02:22: IW CLEAR 13:02:22-05:02:22: IW OG 04:02:22: OK CANIDATE B 02:02:22: REHUNTING 30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | KAL-KB-SRY-0823 | 30739860031 | 2008531003 | JL.MASJID_PARIT_HARUNAH_PAL_SEMBILAN | BP2022 | TB | 109°17.3.47'E | 0°4.26.68'S | 50 | 80/180/315 | 2022 | Newsite 2022 - B2 |  | HTI | KAL-KB-SRY-0823 | JL.MASJID_PARIT_HARUNAH_PAL_SEMBILAN | B2S | TBG | JABO | KALIMANTAN | Kalimantan Barat | Kota Pontianak | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW |  |  | wait address | [9 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22: REKOM 24:04:22-22:04:22: VALIDASI -> IW 20:04:22-25:03:22: IW OG 23:03:22-08:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SA-TNN-0432 | 30730370031 | 2405931003 | KAUNERAN_SONDER | BP2022 | TB | 124°46.34.03'E | 1°15.39.51'N | 60 | 130/220/350 | 2022 | New site 2022 - P2 | Desa Tounelet 1 , Kec. Sonder Kab. Minahasa | HTI | SUL-SA-TNN-0432 | KAUNERAN_SONDER | B2S | TBG | East | SULAWESI | Sulawesi Utara | Kab. Minahasa | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: RFC 24:04:22: REKOM 20:04:22-06:04:22: IW OG 06:04:22-05:04:22: VALIDASI RNP TNP 03:04:22-27:03:22: VALIDASI RNP TNP 23:03:22-16:03:22: IW OG 13:03:22: REHUNTING 09:03:22-09:02:22: IW OG 07:02:22: REVIEW RNP TNP OG, RNP OK CANDIDATE B, IW OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
949 |  | SUL-ST-LWK-1104 | 30714630031 | 2604961003 | LUWUK_UTARA_KILONGAN | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 122°50.36.21'E | 0°55.38.08'S | 60 | 0/90/250 | 2021 | BLITZKRIEG 2021 [NEW] | Kel. Kilongan Permai, RT.1/RW.1 Kec. Luwuk, Kab. Banggai, Prov.Sulteng | HTI | SUL-ST-LWK-1104 | LUWUK_UTARA_KILONGAN | B2S | TBG | EAST | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617749 | 2021-10-25 |  | 185 | > 150 days | 2022-03-24 | W13-2022 | Mar-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: RFC 24:04:22:REKOM OG 20:04:22: IW OG 20:04:22-19:04:22: VALIDASI PERGESERAN KANDIDAT 30M 17:04:22-28:02:22: IW OG, LAHAN PEMDA 25:02:22: ANNOUNCEMENT GO UNTIL RFI 23:02:22-16:02:22: IW OG, LAHAN PEMDA 13:02:22: VALIDASI RNP TNP, KANDIDAT V REJECT WARGA 09:02:22-06:02:22: IW OG KANDIDAT V 02:02:22: RNP REVIEW OG 30:01:22-26:01:22: REHUNTING SESUAI ARAHAN XL 25:01:22: SUBMIT NEW CANDIDATE, BUT REJECTED BY XL 23:01:22-09:01:22: KANDIDAT P SLOPE LAHAN 45 DEGREES, OG REHUNTING 05:01:22: IW OG KANDIDAT P (KANDIDAT OPSI KE-2) 02:01:22-29:12:21: KANDIDAT Q GAGAL IW, OG IW KANDIDAT P 26:12:21: IW OG 22:12:21-19:12:21: SITAC PREPARATION 16:12:21: PMO XL CONFIRMED GO SITAC 15:12:21-05:12:21: REVIEW TNP OK, NEED CONFIRMATION FROM XL TO CONTINUE SITAC PROCESS 01:12:21-10:11:21: REVIEW TNP OG, ERM REJECT 08:11:21: REVIEW RNP OG 07:11:21-31:10:21: SURVEY OG, PLAN SUBMIT KANDIDAT 10 NOV |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SG-KDI-0372 | 30730240031 | 2703821003 | KELURAHAN_MOKOAU_KAMBU | BP2022 | TB | 122°32.6.87'E | 4°2.13.03'S | 50 | 70/180/260 | 2022 | New site 2022 - P2 | BTN Green Boulevard Regency RT. 14 RW. 003 Kel. Mokoau Kec. Kambu Kota Kendari Prov. Sulawesi Tenggara | HTI | SUL-SG-KDI-0372 | KELURAHAN_MOKOAU_KAMBU | B2S | TBG | East | SULAWESI | Sulawesi Tenggara | Kota Kendari | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: RFC 24:04:22-12:04:22: IW OG 10:04:22: VALIDASI RNP TNP 06:04:22-01:04:22: REHUNTING RNP NOK 31:03:22: VALIDASI RNP TNP 30:03:22: REHUNTING 27:03:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-ST-SGB-1017 | 30730440031 | 2605101003 | KALUKUBULA_SIGI_BIROMARU | BP2022 | TB | 119°53.6.0'E | 0°56.0.42'S | 50 | 10/110/270 | 2022 | New site 2022 - P2 | Jl Lahima RT 01 Dusun 02 Desa Kalukubula Kecamatan Sigi Biromaru Kabupaten Sigi Provinsi Sulawesi Tengah | HTI | SUL-ST-SGB-1017 | KALUKUBULA_SIGI_BIROMARU | B2S | TBG | East | SULAWESI | Sulawesi Tengah | Kab. Sigi | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: RFC 24:04:22-17:04:22: REKOM 13:04:22-30:03:22: IW OG 27:03:22: VALIDASI RNP TNP 23:03:22-13:03:22: IW OG 09:03:22: REHUNTING 06:03:22-09:02:22: IW OG 07:02:22: VALIDASI RNP TNP OG -> IW OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUL-ST-LWK-1101 | 30742890031 | 2605141003 | KINTOM_MONDONUN | BP2022 | TB | 122°42.9.67'E | 1°8.7.41'S | 60 | 70/160/275 | 2022 |  | Jalan Madani / Kantong Produksi Kelurahan Mondonum Kecamatan Kintom Kabupaten Banggai Provinsi Sulawesi Tengah | HTI | SUL-ST-LWK-1101 | KINTOM_MONDONUN | B2S | TBG | East | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6618189 | 2022-04-06 | 2022-04-06 | 22 | < 30 days | 2022-09-03 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 2022-04-28 | [11 empty] | SITAC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: RFC 24:04:22-20:04:22: IW OG 19:04:22: VALIDASI 17:04:22-14:04:22: IW OG 13:04:22: VALIDASI RNP TNP 10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-SRH-2247 | 30729820031 | 0229011003 | TEBING_SYAHBANDAR_PENGGALANGAN | BP2022 | TB | 99°14.45.86'E | 3°20.40.87'N | 50 | 0/90/180 | 2022 | New site 2022 - P2 | Dusun VII Desa Penggalangan Kecamatan Tebing Syahbandar Kabupaten Serdang Bedagai Provinsi Sumatera Utara | HTI | SUM-SU-SRH-2247 | TEBING_SYAHBANDAR_PENGGALANGAN | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Serdang Bedagai | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-21 | 2022-03-23 |  |  |  | 2022-04-21 | [6 empty] | CME | 37.Power connection process | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: RFI, WAIT RFIN 24:04:22-20:04:22: CURRING 17:04:22: POURING 13:04:22-10:04:22: REBARRING 06:04:22: EXCAVATION 03:04:22-23:03:22: PERMIT OG 20:03:22-13:03:22: REKOM 09:03:22-06:03:22: IW CLEAR 28:02:22-13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-BT-SRG-0062 | 30739580031 | 1323291003 | OTONOMI_CIKANDE_SERANG | BP2022 | TB | 106°21.16.15'E | 6°12.52.75'S | 40 | 90/270/350 | 2022 | Newsite 2022 - B2 | JL.Raya Patikus RT.003/RW.005 Desa Cikande, Kecamatan Cikande, Kabupaten Serang, Provinsi Banten | EID | JAW-BT-SRG-0062 | OTONOMI_CIKANDE_SERANG | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Serang | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-14 | 2022-04-14 |  | 10.6 | [8 empty] | CME | 37.Power connection process | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: RFI, WAIT RFIN 24:04:22-20:04:22: ME 17:04:22: ERECTION 14:04:22: CURRING 10:04:22-03:04:22: EXCAVATION 01:04:22-27:03:22: IW CLEAR 23:03:22-20:03:22: IW OG 16:03:22-13:03:22: VALIDASI RNP TNP OG 12:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-YO-BTL-0149 | 30739620031 | 1510151003 | BANTUL_JETIS | BP2022 | TB | 110°21.26.76'E | 7°56.34.59'S | 70 | 0/120/240 | 2022 | Newsite 2022 - B2 | GADUHAN RT 001 RW - Kel.CANDEN Kec.JETIS Kab. Bantul Prov.DIY | NOKIA | JAW-YO-BTL-0149 | BANTUL_JETIS | B2S | TBG | Central | JATENG | DI Yogyakarta | Kab. Bantul | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22: SRFI 24:04:22: ERECTION 20:04:22: EXCA 17:04:22-14:04:22: LMS CHANGE TO NOKIA 13:04:22: DESIGN OG 10:04:22-03:04:22: IW CLEAR 30:03:22-17:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SS-RPT-1106 | 30729970031 | 0719151003 | BINGIN_RUPIT | BP2022 | TB | 102°52.45.76'E | 2°45.26.5'S | 60 | 0/80/200 | 2022 | New site 2022 - P2 | Kampung 6 Desa Bingin Rupit Kecamatan Rupit Kabupaten Musi Rawas Utara Provinsi Sumatra Selatan | HTI | SUM-SS-RPT-1106 | BINGIN_RUPIT | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas Utara | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-02 | [10 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: PLN 24:04:22-20:04:22: ME 17:04:22-10:04:22: ERECTION 06:04:22-03:04:22: CURRING TIME 30:03:22-27:03:22: BOUWPLANK 23:03:22-06:03:22: REKOM 28:02:22-23:02:22: IW CLEAR 20:02:22-16:02:22: IW OG 13:02:22-11:02:22: VALIDASI RNP TNP 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr | 401 | 388 TBG
NEW SPK B2S |  | JAW-BT-PDG-0620 | 30729230031 | 1322901003 | SUKASARI_KADUHEJO | BP2022 | TB | 106°3.50.88'E | 6°20.24.66'S | 50 | 120/240/330 | 2022 | New site 2022 - P2 | Kp. Kadukanas RT 001 RW 003 Ds Sukasari Kecamatan Kaduhejo, Kabupaten Pandeglang, Provinsi Banten | EID | JAW-BT-PDG-0620 | SUKASARI_KADUHEJO | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Pandeglang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 3/7/2022, , resend 28 apr 22 |  |  | 6.6 | 2022-04-13 | [7 empty] | CME | 37.Power connection process | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22: SRFI 24:04:22-13:04:22: ME OG 10:04:22-03:04:22: REBARRING 30:03:22-20:03:22: EXCAVATION OG 16:03:22-28:02:22: REKOM OG 23:02:22: IW CLEAR & PARALEL COLLECT DOKUMEN 20:02:22: IW OG 16:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-MKD-1140 | 30729640031 | 1450281003 | JALAN_BOJONG_MAGELANG | BP2022 | TB | 110°16.12.34'E | 7°34.16.96'S | 50 | 0/140/230 | 2022 | New site 2022 - P1 | Blangkunan Utara, RT.002 RW. 021, Desa Pabelan, Kecamatan Mungkid, Kabupaten Magelang, Provinsi Jawa Tengah. | NOKIA | JAW-JT-MKD-1140 | JALAN_BOJONG_MAGELANG | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22: SRFI 24:04:22-20:04:22: REBARRING 17:04:22: DESIGN OG 14:04:22: LMS CHANGE TO NOKIA 13:04:22: DESIGN OG 10:04:22-31:03:22: APPROVED KANDIDAT C 30:03:22-23:03:22: VALIDASI RNP TNP KANDIDAT C 20:03:22-23:02:22: VALIDASI RNP TNP 22:02:22-20:02:22: REHUNTING, REJECT WARGA 16:02:22-13:02:22: IW OG 09:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-PKL-1303 | 30729390031 | 1450211003 | JALAN_KI_MANGUNSARKORO | BP2022 | TB | 109°42.18.0'E | 6°53.30.23'S | 35 | 100/200/290 | 2022 | New site 2022 - P2 | Gg. Kampung, RT 003 / RW 004, Kelurahan Gamer, Kecamatan Pekalongan Timur, Kota Pekalongan, Provinsi Jawa Tengah | NOKIA | JAW-JT-PKL-1303 | JALAN_KI_MANGUNSARKORO | B2S | TBG | Central | JATENG | Jawa Tengah | Kota Pekalongan | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22: SRFI 4:04:22: ERECTION 20:04:22-17:04:22: POURING, WAIT PSB 14:04:22: LMS CHANGE TO NOKIA 13:04:22-03:04:22: EXCAVATION 30:03:22: BOUWPLANK 27:03:22-23:03:22-20:03:22: REKOM 16:03:22-09:03:22: REALISASI IW 06:02:22: IW OG 01:03:22: VALIDASI RNP TNP 01:03:22: IW OG 28:02:22-14:02:22: VALIDASI RNP TNP, KANDIDAT A REJECT WARGA 13:02:22: IW OG 09:02:22-03:02:22: VALIDATION RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-YO-SMN-0077 | 30739610031 | 1510141003 | POTON_SLEMAN | BP2022 | TB | 110°22.55.48'E | 7°42.49.96'S | 40 | 50/180/300 | 2022 | Newsite 2022 - B2 | Poton RT 005 RW 006 Kalurahan Sariharjo Kapanewon Ngaglik Kabupaten Sleman Provinsi D.I.Yogyakarta | NOKIA | JAW-YO-SMN-0077 | POTON_SLEMAN | B2S | TBG | Central | JATENG | DI Yogyakarta | Kab. Sleman | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22: REKOM 10:04:22-05:04:22: IW OG 04:04:22: VALIDASI RNP TNP 03:04:22: IW CLEAR 30:03:22-17:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | BAL-BA-SRP-1482 | 30740160031 | 1721111003 | SAMPALAN_TENGAH_DAWAN | BP2022 | TB | 115°24.52.33'E | 8°32.30.64'S | 50 | 60/140/320 | 2022 | Newsite 2022 - P2 |  | HTI | BAL-BA-SRP-1482 | SAMPALAN_TENGAH_DAWAN | B2S | TBG | East | BALINUSRA | Bali | Kab. Klungkung | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 08.Under RNP review | 06.ERM PROCESS | COMMCASE | 28:04:22: VALIDASI 17:04:22: REHUNTING 13:04:22-28:03:22: VALIDASI RNP TNP 27:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30747870031 | 1015271003 | NEGARA_BATIN_ADI_JAYA | BP2022 | TB | 104°57.38.42'E | 4°20.17.28'S | 40 | 60/195/340 |  | Newsite 2022 - B2 |  | HTI | SUM-LA-BBU-0866 | NEGARA_BATIN_ADI_JAYA | B2S | TBG | West | SUMBAGSEL | Lampung | Kab. Way Kanan | 6618211 | 2022-04-19 | 2022-04-20 | 9 | < 30 days | 2022-09-16 | W38-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 09.Under TNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22: VALIDASI 24:04:22: SURVEY OG 20:04:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SA-BIT-0396 | 30730520031 | 2405951003 | WANGURER_UTARA_MADIDIR | BP2022 | TB | 125°8.57.2'E | 1°26.49.68'N | 50 | 20/180/270 | 2022 | New site 2022 - P2 |  | HTI | SUL-SA-BIT-0396 | WANGURER_UTARA_MADIDIR | B2S | TBG | East | SULAWESI | Sulawesi Utara | Kota Bitung | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 08.Under RNP review | 06.ERM PROCESS | PENOLAKAN WARGA | 28:04:22: VALIDASI 24:04:22-19:04:22: REHUNTIN 17:04:22-16:04:22: VALIDASI RNP TNP 13:04:22-31:03:22: IW OG 30:03:22: VALIDASI RNP TNP 27:03:22-23:03:22: IW OG 22:03:22-16:03:22: VALIDASI RNP TNP 13:03:22: REHUNTING 11:03:22: VALIDASI RNP TNP, RNP NOK, RHEUNTING 09:03:22-28:02:22: REHUNTING 28:02:22: VALIDASI RNP TNP 23:02:22-20:02:22: REHUNTING OG 16:02:22-09:02:22: IW OG 07:02:22: RNP TNP OK, IW OG 06:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-BT-RKB-0789 | 30739540031 | 1323281003 | CURUGBADAK_MAJA_LEBAK | BP2022 | TB | 106°23.7.23'E | 6°20.51.59'S | 50 | 90/210/310 | 2022 | Newsite 2022 - B2 | Kp. Cipondok RT.003 RW.004 Desa Curugbadak Kec. Maja Kab. Lebak | EID | JAW-BT-RKB-0789 | CURUGBADAK_MAJA_LEBAK | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Lebak | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW |  |  | LMS NY | LMS NY | #N/A | [7 empty] | SITAC | 20.APD & Design Process | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22: WAIT APD 24:04:22: REKOM 20:04:22-03:04:22: IW CLEAR 30:03:22-20:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-SU-AKK-2255 | 30740250031 | 0229331003 | NA_IX-X_BANGUN_REJO | BP2022 | TB | 99°42.55.84'E | 2°17.23.74'N | 50 | 0/80/260 | 2022 | Newsite 2022 - B2 | Dusun 2 Padang Nabidang Desa Bangun Rejo Kecamatan Na IX-X Kabupaten Labuhan Batu Utara Provinsi Sumatera Utara | HTI | SUM-SU-AKK-2255 | NA_IX-X_BANGUN_REJO | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu Utara | 6618109 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 16.IMB waiting survey | 08.GOVERNMENT PERMIT PROCESS | CURRENTLY NO ISSUE | 28:04:22: WAIT IMB 24:04:22-03:04:22: IW CLEAR 30:03:22-23:03:22: IW OG 20:03:22-17:03:22: VALIDASI RNP TNP 16:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-SU-AKK-2249 | 30740200031 | 0229291003 | KUALUH_HULU_SUKARAME | BP2022 | TB | 99°45.51.45'E | 2°34.50.24'N | 50 | 80/150/300 | 2022 | Newsite 2022 - B2 | DESA SUKARAME BARU KECAMATAN KUALUH HULU KABUPATEN LABUHANBATU UTARA PROVINSI SUMATERA UTARA | HTI | SUM-SU-AKK-2249 | KUALUH_HULU_SUKARAME | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu Utara | 6618109 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 16.IMB waiting survey | 08.GOVERNMENT PERMIT PROCESS | CURRENTLY NO ISSUE | 28:04:22: WAIT IMB 24:04:22-10:04:22: REKOM 06:04:22-03:04:22: IW CLEAR 30:03:22-20:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-SU-AKK-2250 | 30740230031 | 0229321003 | BULUNGIHIT | BP2022 | TB | 99°52.26.04'E | 2°16.55.06'N | 50 | 0/160/230 | 2022 | Newsite 2022 - B2 | DUSUN III BULUNGIHIT DESA BULUNGIHIT KECAMATAN MARBAU KABUPATEN LABUHAN BATU UTARA PROVINSI SUMATERA UTARA | HTI | SUM-SU-AKK-2250 | BULUNGIHIT | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu Utara | 6618109 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 16.IMB waiting survey | 08.GOVERNMENT PERMIT PROCESS | CURRENTLY NO ISSUE | 28:04:22: WAIT IMB 24:04:22-10:04:22: REKOM 06:04:22-03:04:22: IW CLEAR 30:03:22-23:03:22: IW OG 20:03:22-17:03:22: VALIDASI RNP TNP 16:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-SU-KPI-2238 | 30740220031 | 0229311003 | SIMATAHARI | BP2022 | TB | 100°1.33.56'E | 1°48.18.86'N | 50 | 80/210/330 | 2022 | Newsite 2022 - B2 | Jl. Kota Pinang-Gunung Tua, Dusun Sejahtera, Desa Simatahari, Kecamatan Kota Pinang, Kabupaten Labuhan Batu Selatan | HTI | SUM-SU-KPI-2238 | SIMATAHARI | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu Selatan | 6618109 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 16.IMB waiting survey | 08.GOVERNMENT PERMIT PROCESS | CURRENTLY NO ISSUE | 28:04:22: WAIT IMB 24:04:22-17:04:22: SOIL TEST 13:04:22-10:04:22: REKOM 06:04:22-03:04:22: IW CLEAR 30:03:22-23:03:22: IW 20:03:22-17:03:22: VALIDASI RNP TNP 16:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-KR-BTM-0591 | 30742250031 | 0507601003 | ANGGREK MAS RELOCATION | RELOCATION | TB | 104°1.44.76'null | 1°6.50.46'N | 40 | 40/150/340 |  |  |  | CAA | SUM-KR-BTM-0591 | ANGGREK MAS RELOCATION | B2S | TBG | WEST | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6618158 | 2022-03-29 | 2022-03-29 | 30 | < 30 days | 2022-08-26 | W35-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 05.Hunting OG | 04.HUNTING | CURRENTLY NO ISSUE | 28:04:22-03:04:22: HUNTING 30:03:22: MITRA ASSIGNMENT 29:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JK-GGP-0441 | 30739570031 | 1137641003 | TAMAN__PALEM_TEGALALUR | BP2022 | TB | 106°42.54.7'E | 6°7.50.65'S | 25 | 40/170/240 | 2022 | Newsite 2022 - B2 |  | EID | JAW-JK-GGP-0441 | TAMAN__PALEM_TEGALALUR | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW |  |  | wait address | LMS NY | #N/A | [7 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-03:04:22: IW CLEAR 30:03:22-09:02:22: SURVEY OG 07:02:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-LMP-2230 | 30730080031 | 0229061003 | LAUT_TADOR_LAUT_TADOR | BP2022 | TB | 99°15.43.99'E | 3°18.9.84'N | 50 | 40/220/290 | 2022 | New site 2022 - P2 |  | HTI | SUM-SU-LMP-2230 | LAUT_TADOR_LAUT_TADOR | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Batu Bara | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-03:04:22: IW CLEAR 30:03:22-27:03:22: PENGURUSAN SURAT TANAH 23:03:22: IW CLEAR 20:03:22-16:03:22: IW DONE 13:03:22: IW OG 09:03:22-06:03:22: VALIDASI RNP TNP 28:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-MDN-2245 | 30729710031 | 0228931003 | MEDAN_DELI_TITIPAPAN | BP2022 | TB | 98°40.13.03'E | 3°41.31.86'N | 30 | 90/200/340 | 2022 | New site 2022 - P2 | Lingkungan 34 Kelurahan Rengas Pulau Kecamatan Medan Marelan Kota Medan Provinsi Sumatera Utara | HTI | SUM-SU-MDN-2245 | MEDAN_DELI_TITIPAPAN | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kota Medan | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | COMMCASE | 28:04:22-06:03:22: IW CLEAR 28:02:22-13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JK-GGP-0463 | 30729430031 | 1136831003 | TANAH_SEREAL_TAMBORA | BP2022 | TB | 106°48.35.17'E | 6°9.30.68'S | 25 | 0/90/239 | 2022-2024 | New site 2022 - P1 |  | EID | JAW-JK-GGP-0463 | TANAH_SEREAL_TAMBORA | B2S | TBG | Jabodetabek | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22-06:03:22: REHUNTING 28:02:22-16:02:22: VALIDASI RNP TNP 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-LA-BBU-0868 | 30730060031 | 1014581003 | WAY_PISANG | BP2022 | TB | 104°22.23.15'E | 4°23.38.55'S | 50 | 50/110/275 | 2022 | New site 2022 - P2 | Way Pisang RT 002/RW 001 Desa Way Pisang Kecamatan Way Tuba Kab. Way Kanan Prov Lampung | HTI | SUM-LA-BBU-0868 | WAY_PISANG | B2S | TBG | West | SUMBAGSEL | Lampung | Kab. Way Kanan | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-02 | [10 empty] | CME | 21.Bouwplank | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22-06:04:22: BOUWPLANK & PARALEL PERMIT 03:04:22-27:03:22: PREPARE CME 23:03:22: DESIGN OG 20:03:22-06:03:22: REKOM 28:02:22-16:02:22: IW CLEAR 13:02:22-09:02:22: IW OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUM-BB-MGR-0532 | 30739970031 | 0804431003 | SIMPANG_RENGGIANG_SIMPANG_TIGA | BP2022 | TB | 107°54.20.46'E | 2°50.34.92'S | 50 | 100/180/260 | 2022 | Newsite 2022 - B2 | Jl. Lintas Tengah RT.001 Dusun Simpang Tiga, Desa Simpang Tiga, Kecamatan Simpang Renggiang, Kabupaten Belitung Timur, Provinsi Kepulauan Bangka Belitung | HTI | SUM-BB-MGR-0532 | SIMPANG_RENGGIANG_SIMPANG_TIGA | B2S | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kab. Belitung Timur | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-10 | 2022-04-11 | [10 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-06:04:22: IW CLEAR 03:04:22: IW OG 30:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-AC-MBO-0649 | 30739820031 | 0111281003 | TEUPIN_PERAHO | BP2022 | TB | 95°58.30.87'E | 4°18.33.4'N | 60 | 0/150/300 | 2022 | Newsite 2022 - B2 |  | HTI | SUM-AC-MBO-0649 | TEUPIN_PERAHO | B2S | TBG | West | SUMBAGUT | Aceh | Kab. Aceh Barat | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-06:04:22: IW CLEAR 03:04:22-23:03:22: IW OG 20:03:22-17:03:22: VALIDASI RNP TNP 16:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-BT-TGR-0115 | 30739700031 | 1323311003 | TANJUNG_ANOM_BONISARI | BP2022 | TB | 106°32.41.64'E | 6°1.33.41'S | 50 | 90/200/310 | 2022 | Newsite 2022 - P2 | Kp.Buaran Asem RT.004/RW.004 Desa Tanjung Anom, Kecamatan Mauk, Kabupaten Tangerang, Provinsi Banten | EID | JAW-BT-TGR-0115 | TANJUNG_ANOM_BONISARI | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Tangerang | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-07:04:22: VALIDASI RNP TNP 06:04:22-05:04:22: rehunting 03:04:22-01:04:22: VALIDASI RNP TNP 30:03:22-20:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JK-GGP-0440 |  |  |  | BP2022 | TB | 106°42.52.89'E | 6°7.13.2'S | 25 | 90/210/330 | 2022 | Newsite 2022 - B2 |  | EID | JAW-JK-GGP-0440 | PERMATA_TEGAL_ALUR | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | NY STIP | 04.Survey OG | 03.SURVEY PROCESS | PROPOSE TO COLO | 28:04:22-09:02:22: SURVEY OG, PROPOSED COLO 07:02:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-LMP-2234 | 30729920031 | 0229041003 | KELURAHAN_PERKEBUNAN_SIPARE_PARE | BP2022 | TB | 99°20.34.37'E | 3°19.21.0'N | 50 | 130/240/320 | 2022 | New site 2022 - P2 |  | HTI | SUM-SU-LMP-2234 | KELURAHAN_PERKEBUNAN_SIPARE_PARE | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Batu Bara | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 11.BAN / BAK Process | 07.SITAC PROCESS | HARDSITAC CORPORATE LONSUM | 28:04:22-09:03:22: BAN/BAK OG 06:03:22: VALIDASI RNP TNP 28:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-LMP-2235 | 30729830031 | 0229021003 | MEDANG_DERAS_LALANG | BP2022 | TB | 99°25.8.54'E | 3°21.36.36'N | 50 | 120/240/320 | 2022 | New site 2022 - P2 | Dusun Tasak Baru Desa Lalang Kec. Medang Deras Kab. Batu Bara Prov. Sumatera Utara | HTI | SUM-SU-LMP-2235 | MEDANG_DERAS_LALANG | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Batu Bara | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-09:03:22: IW CLEAR 06:03:22: VALIDASI RNP TNP, IW FAILED 28:02:22-13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUM-RI-TBH-1094 | 30740090031 | 0416931003 | KELURAHAN_SEBERANG_TEMBILAHAN | BP2022 | TB | 103°10.4.8'E | 0°20.31.52'S | 50 | 50/150/240 | 2022 | Newsite 2022 - P2 | Jl. Lintas Enok RT004 RW002, Kelurahan Seberang Tembilahan, Kecamatan Tembilahan, Kabupaten Indragiri Hilir, Provinsi Riau | HTI | SUM-RI-TBH-1094 | KELURAHAN_SEBERANG_TEMBILAHAN | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Indragiri Hilir | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-11 | 2022-04-13 | [10 empty] | RFC | 20.APD & Design Process | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22-10:04:22: DESIGN OG 06:04:22-03:04:22: REKOM 30:03:22-23:03:22: IW CLEAR 20:03:22-16:03:22: IW OG 15:03:22-15:03:22: VALIDASI RNP TNP 13:03:22: MITRA ASSIGNMENT 09:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | SUM-SU-STB-2235 | 30730340031 | 0229081003 | PERTUMBUKAN | BP2022 | TB | 98°23.44.16'E | 3°42.49.0'N | 60 | 0/80/270 |  |  | Dusun I, Desa Pertumbukan, Kec. Wampu, Kab. Langkat, Provinsi Sumatera Utara | HTI | SUM-SU-STB-2235 | PERTUMBUKAN | B2S | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6618193 | 2022-04-07 | 2022-04-07 | 21 | < 30 days | 2022-09-04 | W37-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 2022-04-10 | 2022-04-11 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | COMMCASE | 28:04:22-10:04:22: ERECTION 07:04:22: SPK RELEASED |  | 401 | 388 TBG
|  | BAL-BA-KRA-1486 | 30740130031 | 1721101003 | KARANGASEM_SERAYA_BARAT | BP2022 | TB | 115°39.6.6'E | 8°26.35.12'S | 60 | 30/180/270 | 2022 | Newsite 2022 - P2 | Banjar Dinas Tenggang, Desa Seraya Kecamatan Karangasem Kabupaten Karangasem Provinsi Bali. | HTI | BAL-BA-KRA-1486 | KARANGASEM_SERAYA_BARAT | B2S | TBG | East | BALINUSRA | Bali | Kab. Karangasem | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | PERGUB ISSUE | 28:04:22-10:04:22: IW CLEAR, PENGECEKAN PERUBAHAN PERDA 06:04:22-03:04:22: IW CLEAR 30:03:22-23:03:22: IW OG 21:03:22: VALIDASI RNP TNP 20:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-RI-TBH-1091 | 30740040031 | 0416901003 | KELURAHAN_TEMBILAHAN_HILIR | BP2022 | TB | 103°10.26.05'E | 0°18.47.21'S | 50 | 60/180/280 | 2022 | Newsite 2022 - P2 | Lorong H. Arahman RT 003 RW 009, Kelurahan Tembilahan Hilir, Kecamatan Tembilahan, Kabupaten Indragiri Hilir, Provinsi Riau | HTI | SUM-RI-TBH-1091 | KELURAHAN_TEMBILAHAN_HILIR | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Indragiri Hilir | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-10:04:22: REKOM 10:04:22: IW OG 07:04:22: VALIDASI RNP TNP KANDIDAT D 06:04:22-03:04:22: REKOM 30:03:22-23:03:22: IW CLEAR 20:03:22-16:03:22: IW OG 15:03:22-15:03:22: VALIDASI RNP TNP 13:03:22: MITRA ASSIGNMENT 09:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JK-KYB-0301 | 30742660031 | 1138131003 | TEBET TIMUR IV RELOCATION | RELOCATION | TB | 106°51.14.25'E | 6°14.15.9'S | 25 | 90/210/330 | 2022 |  |  | EID | JAW-JK-KYB-0301 | TEBET TIMUR IV RELOCATION | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Selatan | 6618181 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 04.Survey OG | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 28:04:22-10:04:22: SURVEY OG 06:04:22-05:04:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-KR-BTM-0623 | 30730380031 | 0507571003 | TIBAN_INDAH | BP2022 | TB | 103°59.14.23'E | 1°7.15.44'N | 30 | 0/180/280 | 2022 | New site 2022 - P2 | Pondok Pelangi 2 Blok E2 No.15 RT.04 RW.09 Kel.Tiban Indah Kec.Sekupang Kota Batam Provinsi Kepulauan Riau | HTI | SUM-KR-BTM-0623 | TIBAN_INDAH | B2S | TBG | West | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-21 | 2022-03-23 | [10 empty] | CME | 23.Bore pile Rebaring & Pouring | 11.BORE PILE OG | CURRENTLY NO ISSUE | 28:04:22-13:04:22: BOREPILE 10:04:22: BOREPILE 06:04:22-09:03:22: REKOM OG 06:03:22-20:02:22: PREPARE REKOM & PARALEL PKS DI BATAM 16:02:22-13:02:22: IW OG 09:02:22: RNP OK KANDIDAT A, TNP OG 06:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUM-SU-AKK-2253 | 30740260031 | 0229341003 | BANDAR_LAMA | BP2022 | TB | 99°35.54.53'E | 2°30.38.14'N | 60 | 30/210/300 | 2022 | Newsite 2022 - B2 | Dusun 2 Kampung Tempel Desa Bandar Lama Kecamatan Kualu Selatan Kabupaten Labuhan Batu Utara Provinsi Sumatera Utara | HTI | SUM-SU-AKK-2253 | BANDAR_LAMA | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu Utara | 6618109 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-10 | 2022-04-11 |  |  |  | 2022-04-22 | [6 empty] | CME | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22-13:04:22: EXCAVATION 10:04:22-06:04:22: BOUWPLANK 03:04:22-23:03:22: IW CLEAR 20:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-CBI-0148 | 30739660031 | 1276851003 | BOGOR_LEUWISADENG | BP2022 | TB | 106°50.25.77'E | 6°17.20.28'S | 40 | 60/180/280 | 2022 | Newsite 2022 - P1 |  | EID | JAW-JB-CBI-0148 | BOGOR_LEUWISADENG | B2S | TBG | JABO | JABODETABEK | Jawa Barat | Kab. Bogor | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-13:04:22: IW OG 10:04:22-06:04:22: VALIDASI RNP TNP 05:04:22: NEEED CONFIRM APA BISA DI KETINGGIAN 50? 03:04:22-01:04:22: VALIDASI RNP TNP 30:03:22-20:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JK-GGP-0444 | 30739510031 | 1137591003 | UTAMA_CENGKARENG_BARAT | BP2022 | TB | 106°43.24.6'E | 6°8.59.69'S | 25 | 90/210/330 | 2022 | Newsite 2022 - B2 |  | EID | JAW-JK-GGP-0444 | UTAMA_CENGKARENG_BARAT | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22-13:04:22: REHUNTING 10:04:22-03:04:22: IW OG 30:03:22-09:02:22: SURVEY OG 07:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JK-GGP-0446 | 30739530031 | 1137611003 | PETERNAKAN_KAPUK_CENGKARENG | BP2022 | TB | 106°46.0.7'E | 6°8.37.01'S | 25 | 90/210/330 | 2022 | Newsite 2022 - B2 |  | EID | JAW-JK-GGP-0446 | PETERNAKAN_KAPUK_CENGKARENG | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22-13:04:22: REHUNTING 10:04:22-03:04:22: IW OG 30:03:22-09:02:22: SURVEY OG 07:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JK-GGP-0442 | 30739550031 | 1137621003 | JELAMBAR_BARAT_GROGOL | BP2022 | TB | 106°47.5.74'E | 6°8.59.68'S | 25 | 90/210/330 | 2022 | Newsite 2022 - B2 |  | EID | JAW-JK-GGP-0442 | JELAMBAR_BARAT_GROGOL | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22-13:04:22: REHUNTING 10:04:22-03:04:22: IW OG 30:03:22-09:02:22: SURVEY OG 07:02:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JK-KYB-0468 | 30729220031 | 1136821003 | RAWASARI_BARAT | BP2022 | TB | 106°52.1.52'E | 6°10.59.0'S | 30 | 40/210/295 | 2022-2024 | New site 2022 - P1 | Jl. Cempaka Putih Barat, RT. 003 RW. 007 Cempaka Putih Barat, Cempaka Putih, Kota Jakarta Pusat, DKI Jakarta | EID | JAW-JK-KYB-0468 | RAWASARI_BARAT | B2S | TBG | Jabodetabek | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Pusat | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | NEAR EXISTING XL | 28:04:22-13:04:22: REHUNTING 10:04:22-25:03:22: PROPOSE MCP 23:03:22-28:02:22: REKOM OG 23:02:22: IW CLEAR 20:02:22-16:02:22: VALIDASI RNP TNP 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-BT-SRG-0060 | 30739480031 | 1323261003 | TAKTAKAN_CILOWONG_SERANG | BP2022 | TB | 106°4.46.94'E | 6°8.59.46'S | 70 | 50/120/250 | 2022 | Newsite 2022 - B2 | JL.Takari Lingk.Cilowong Mesjid RT.001/RW.002 Kel.Cibendung, Kec.Taktakan, Kota Serang, Provinsi Banten | EID | JAW-BT-SRG-0060 | TAKTAKAN_CILOWONG_SERANG | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Serang | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW |  |  | LMS NY | LMS NY | #N/A | [7 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-13:04:22: REKOM 10:04:22-25:03:22: IW CLEAR, PREPARE REKOM 23:03:22-20:03:22: IW OG 16:03:22-13:03:22: VALIDASI RNP TNP OG 12:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-BT-PDG-0628 | 30739440031 | 1323221003 | RANCABUGEL_MEKARJAYA | BP2022 | TB | 106°2.6.66'E | 6°23.37.19'S | 55 | 20/120/220 | 2022 | Newsite 2022 - B2 | Kp.Pasir Pogor RT.09 RW.05 Desa Bugel Kecamatan Mekarjaya -Pandegelang | EID | JAW-BT-PDG-0628 | RANCABUGEL_MEKARJAYA | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Pandeglang | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW |  |  | LMS NY | LMS NY | #N/A | [7 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-13:04:22: REKOM 10:04:22-27:03:22: IW CLEAR 23:03:22-20:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-BGR-0239 | 30743350031 | 1277231003 | HARJASARI BOGOR | Newsite 2022 - DENSI | TB | 106°50.28.1'E | 6°39.9.76'S | 30 | 100/190/335 |  | Newsite 2022 - DENSI |  | EID | JAW-JB-BGR-0239 | HARJASARI BOGOR | B2S | TBG | JABO | JABODETABEK | Jawa Barat | Kota Bogor | 6618206 | 2022-04-12 | 2022-04-12 | 16 | < 30 days | 2022-09-09 | W37-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 04.Survey OG | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 28:04:22-13:04:22: SURVEY OG 12:04:22: SPK RELEASED |  | 401 | 388 TBG
|  | NUS-NT-LBJ-0252 |  |  |  | Newsite 2020 - Additional | TB | 119°32.41.37'null | 8°35.1.72'S | 50 | 85/160/260 |  | Newsite 2020 - Additional |  | ALT | NUS-NT-LBJ-0252 | PULAU KOMODO | B2S | TBG | East | BALINUSRA | Nusa Tenggara Timur | Kab. Manggarai Barat | 6618205 | 2022-04-12 | 2022-04-12 | 16 | < 30 days | 2022-09-09 | W37-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 04.Survey OG | 03.SURVEY PROCESS | SAR ON TN KOMODO | 28:04:22-13:04:22: TBG PROPOSE DROP, SAR ON TAMAN NASIONAL KOMODO, POTENTIAL DELAY LT > 360D 12:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | NUS-NT-LBJ-0253 |  |  |  | Newsite 2020 - Additional | TB | 119°34.7.49'null | 8°39.26.34'S | 50 | 20/170/280 |  | Newsite 2020 - Additional |  | ALT | NUS-NT-LBJ-0253 | PULAU PADAR | B2S | TBG | East | BALINUSRA | Nusa Tenggara Timur | Kab. Manggarai Barat | 6618205 | 2022-04-12 | 2022-04-12 | 16 | < 30 days | 2022-09-09 | W37-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 04.Survey OG | 03.SURVEY PROCESS | SAR ON TN KOMODO | 28:04:22-13:04:22: TBG PROPOSE DROP, SAR ON TAMAN NASIONAL KOMODO, POTENTIAL DELAY LT > 360D 12:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | NUS-NT-LBJ-0251 |  |  |  | Newsite 2020 - Additional | TB | 119°43.13.94'null | 8°34.31.64'S | 50 | 10/150/265 |  | Newsite 2020 - Additional |  | ALT | NUS-NT-LBJ-0251 | PAPA GARANG | B2S | TBG | East | BALINUSRA | Nusa Tenggara Timur | Kab. Manggarai Barat | 6618205 | 2022-04-12 | 2022-04-12 | 16 | < 30 days | 2022-09-09 | W37-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 04.Survey OG | 03.SURVEY PROCESS | SAR ON TN KOMODO | 28:04:22-13:04:22: TBG PROPOSE DROP, SAR ON TAMAN NASIONAL KOMODO, POTENTIAL DELAY LT > 360D 12:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | SUM-KR-DKL-0637 | 30740410031 | 0507591003 | REPEATER BUKIT TENGKORAK | NEW SITE 2022-REPEATER | TB | 104°43.45.19'E | 0°12.15.66'S | 70 | 347 |  | Newsite 2022 - Repeater | Dusun II Kerandin RT.002 RW.004 Desa Kerandin Kec.Lingga Timur Kab.Lingga Propinsi Kepulauan Riau | HTI | SUM-KR-DKL-0637 | REPEATER BUKIT TENGKORAK | B2S | TBG | West | SUMBAGTENG | Kepulauan Riau | Kab. Lingga | 6618120 | 2022-03-08 | 2022-03-09 | 51 | 31 - 60 days | 2022-08-05 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 2022-04-11 | 2022-04-13 | [10 empty] | RFC | 20.APD & Design Process | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22-17:04:22: DESIGN OG 13:04:22-10:04:22: PRESPARE CME 06:04:22-03:04:22: REKOM 30:03:22-21:03:22: IW OG 20:03:22-15:03:22: VALIDASI RNP TNP 13:03:22: MITRA ASSIGNMENT 09:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | NUS-NB-GRG-5399 | 30739110031 | 1806911003 | REPEATER SEKOTONG | NEW SITE 2022-REPEATER | TB | 116°3.14.15'E | 8°50.28.78'S | 72 | 173/353 | 2022 | Newsite 2022 - B2 |  | HTI | NUS-NB-GRG-5399 | REPEATER SEKOTONG | B2S | TBG | East | BALINUSRA | Nusa Tenggara Barat | Kab. Lombok Barat | 6618093 | 2022-03-03 | 2022-03-04 | 56 | 31 - 60 days | 2022-07-31 | W32-2022 | Jul-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | NO POWER, TBG PROPOSE SOLAR CELL | 28:04:22-17:04:22: REHUNTING TITIK ARAHAN 13:04:22-06:04:22: VALIDASI TNP 03:04:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | NUS-NB-MTR-5406 | 30735730031 | 1806901003 | MATARAM RELOCATION | RELOCATION | TB | 116°7.24.25'E | 8°35.23.46'S | 30 | 80/210/300 | 2022 | RELOCATION |  | CAA | NUS-NB-MTR-5406 | MATARAM RELOCATION | B2S | TBG | East | BALINUSRA | Nusa Tenggara Barat | Kota Mataram | 6618043 | 2022-02-15 | 2022-02-16 | 72 | 61 - 90 days | 2022-07-15 | W29-2022 | Jul-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22-17:04:22: REHUNTING, IW FAILED 13:04:22: IW OG 10:04:22-22:03:22: VALIDASI RNP TNP 20:03:22-09:03:22: PREPARE KANDIDAT ROOFTOP 06:03:22-20:02:22: SURVEY OG 16:02:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-SAK-1161 | 30729990031 | 0416601003 | PANGKALAN_PISANG | BP2022 | TB | 101°48.40.04'E | 0°43.2.85'N | 50 | 0/80/180 | 2022 | New site 2022 - P2 | Jl. Masjid RT012 RW005 Dusun Suak Tandun, Kampung Pangkalan Pisang, Kec. Koto Gasib, Kab. Siak, Prov. Riau | HTI | SUM-RI-SAK-1161 | PANGKALAN_PISANG | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Siak | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: REKOM 13:04:22-01:04:22: VALIDASI RNP TNP 30:03:22-20:03:22: REHUNTING 16:03:22-20:02:22: IW OG 17:02:22: VALIDASI RNP TNP OG, IW FAILED 16:02:22-13:02:22: IW OG 09:02:22: VALIDASI RNP TNP OG 08:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-UJT-0957 | 30729870031 | 0416551003 | KELURAHAN_BANJAR_XII | BP2022 | TB | 100°56.53.34'E | 1°36.6.56'N | 50 | 0/100/290 | 2022 | New site 2022 - P2 | Jl. Dusun Karya RT 017 RW 07 Kelurahan Banjar XII Kec.Tanah Putih Kab. Rokan Hilir Prov. Riau. | HTI | SUM-RI-UJT-0957 | KELURAHAN_BANJAR_XII | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Rokan Hilir | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | [11 empty] | RFC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22-17:04:22: RFC 13:04:22-06:04:22: REKOM 03:04:22-16:02:22: IW OG 13:02:22-11:02:22: VALIDASI RNP TNP 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-KRG-2158 | 30729240031 | 1450141003 | KARANGLO_KARANGANYAR | BP2022 | TB | 111°6.34.74'E | 7°37.45.59'S | 60 | 90/210/330 | 2022-2024 | New site 2022 - P1 |  | NOKIA | JAW-JT-KRG-2158 | KARANGLO_KARANGANYAR | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Karanganyar | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 08.RNP review nok | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: RNP NOK, REHUNTING, LMS CHANGE TO NOKIA 13:04:22-15:03:22: VALIDASI RNP TNP 13:03:22-22:02:22: VALIDASI RNP TNP 20:02:22: REHUNTING 16:02:22-13:02:22: IW OG 09:02:22-08:02:22: REHUNTING, CANDIDATE NOK 06:02:22-04:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | BAL-BA-DPR-1531 | 30731000031 | 1719151003 | SANUR BEACH VIEW RELOCATION | RELOCATION | TB | 115°15.44.16'E | 8°42.4.45'S | 30 | 10/100/210 | 2022 | RELOCATION - XL |  | CAA | BAL-BA-DPR-1531 | SANUR BEACH VIEW RELOCATION | B2S | TBG | EAST | BALINUSRA | Bali | Kota Denpasar | 6618016 | 2022-02-03 | 2022-02-04 | 84 | 61 - 90 days | 2022-07-03 | W28-2022 | Jul-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: TITIK YANG DISETUJUI HANYA BISA MCP, NEED CONFIRM PERANGKAT BTS GENDONG 13:04:22-07:04:22: VALIDASI RNP TNP 06:04:22-18:03:22: REHUNTING 16:03:22-11:03:22: VALIDASI RNP TNP 09:03:22: PREPARE KANDIDAT ROOFTOP 06:03:22-06:02:22: SURVEY OG 04:02:22: NEW SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JB-SBM-2468 | 30739640031 | 1276841003 | LANGENSARI_SUKARAJA | BP2022 | TB | 106°58.45.86'E | 6°52.55.62'S | 50 | 80/200/320 | 2022 | Newsite 2022 - P1 |  | EID | JAW-JB-SBM-2468 | LANGENSARI_SUKARAJA | B2S | TBG | JABO | JABODETABEK | Jawa Barat | Kab. Sukabumi | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-17:04:22: VALIDASI RNP TNP 13:04:22: REHUNTING 12:04:22: VALIDASI RNP TNP 10:04:22-05:04:22: REHUNTING KANDIDAT NOK 03:04:22-01:04:22: VALIDASI RNP TNP 30:03:22-20:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | KAL-KI-SMR-0994 | 30725590031 | 2315911003 | REJO_MULYO_LEMPAKE | ACTIVE - BLITZKRIEG H2 | TB | 117°11.42.51'E | 0°23.56.98'S | 50 | 40/185/235 | 2021 | New site 2021 - H2 | Jl. Rejo Mulyo RT 31 Kelurahan Lempake, Kecamatan Samarinda Utara, Kota Samarida, Provinsi Kalimantan Timur | HTI | KAL-KI-SMR-0994 | REJO_MULYO_LEMPAKE | B2S | TBG | JABO | KALIMANTAN | Kalimantan Timur | Kota Samarinda | 6617944 | 2022-01-24 |  | 94 | 91 - 120 days | 2022-06-23 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-18:04:22: REKOM 17:04:22-28:03:22: IW OG 27:03:22: VALIDASI RNP TNP 23:03:22: REHUNTING 20:03:22-13:03:22: IW OG 7 OF 8 09:03:22-28:02:22: IW OG 23:02:22: UNDER TNP REVIEW & PARALEL IW 20:02:22-13:02:22: KANDIDAT REJECT, REHUNTING 12:02:22-02:02:22: SURVEY OG 30:01:22-26:01:22: MITRA ASSIGNMENT 24:01:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JB-SBR-4123 | 30742900031 | 1277191003 | PANGERAN KEJAKSAN 2 | BP2022 | TB | 108°29.7.84'E | 6°46.2.32'S | 50 | 0/120/240 | 2022 | Newsite 2021 |  | HTI | JAW-JB-SBR-4123 | SUMBER_BABAKAN | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Cirebon | 6618203 | 2022-04-11 | 2022-04-11 | 17 | < 30 days | 2022-09-08 | W37-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-19:04:22: IW ON GOING, PROPOSE COLO CANCEL 17:04:22-13:04:22: PROPOSE COLO 11:04:22: IW OG 10:04:22: PROPOSE TO COLO 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JK-KSU-1133 | 30729600031 | 1136871003 | PULAU_HARAPAN | BP2022 | TB | 106°23.28.46'E | 5°28.42.77'S | 30 | 90/210/330 | 2022 | New site 2022 - P2 |  | EID | JAW-JK-KSU-1133 | PULAU_HARAPAN | B2S | TBG | Jabodetabek | JABODETABEK | DKI Jakarta | Kab. Adm. Kep. Seribu | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 11.BAN / BAK Process | 07.SITAC PROCESS | SITE NO POWER | 28:04:22-20:03:22: BAN/BAK ACTUAL, BUT KANDIDAT NY SUBMIT 16:03:22-30:01:22: SURVEY OG (PHE OSES) 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JK-GGP-0456 | 30729500031 | 1136841003 | SETIA_KAWAN_KALI_ANYAR | BP2022 | TB | 106°48.1.18'E | 6°9.36.64'S | 30 | 90/210/325 | 2022-2024 | New site 2022 - P1 |  | EID | JAW-JK-GGP-0456 | SETIA_KAWAN_KALI_ANYAR | B2S | TBG | Jabodetabek | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22-20:03:22: REHUNTING 16:03:22-06:03:22: REKOM OG 28:02:22: IW CLEAR & PARALEL COLLECT DOC 23:02:22-16:02:22: IW OG 13:02:22-03:02:22: VALIDASI RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
932 |  | JAW-JB-BKS-0648 | 30719690031 | 1266962010 | IBS GALAXI RAYA-JAKASAMPURNA | RELOCATION | TB | 106°58.6.46'E | 6°15.0.25'S | 32.5 | 90/210/330 | 2021 | RELOCATION | Jl. Galaxy Raya Ruko No.4, Kel. Jaka Sampurna RT.006 RW.09, Kec. Bekasi Barat, Kota Bekasi Prov. Jawa Barat | EID | JAW-JB-BKS-0648 | JAKASAMPURNA MALABAR RELOCATION 2 | COLO | XL | JABO | JABODETABEK | Jawa Barat | Kota Bekasi | 6617758 | 2021-11-01 |  | 178 | > 150 days | 2021-12-01 | W49-2021 | Dec-2021 | TBD | TBD | TBD | 2022-01-14 | W03-2022 | Jan-2022 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-22 | [7 empty] | 35.Pemasangan KWH Box dan pole | 19.MECHANICAL & ELECTRICAL OG | COMMCASE | 14:04:22: minus kwh 03:03:22-24:02:22: PREAPRE CME, NEW DESIGN 17:02:22: HOLD COMMCASE BY LL 02:02:22-16:01:22: PONDASI OG 12:01:22-12:21-15:12:21: STO DECLARE 22 NOV, EID TERIMA PO 15 DEC, PLAN RFI 14 JAN 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY EID, EID WAIT PO FROM XL 21:11:21-07:11:21: NEED REVIEW RNP EID 03:11:21: ERM PROCESS |  | 401
|  | SUM-KR-BTM-0611 | 30725620031 | 0507551003 | TANJUNG_RIAU_PERUMAHAN_RICCI2 | ACTIVE - BLITZKRIEG H2 | TB | 103°56.31.88'E | 1°3.43.31'N | 40 | 80/250/350 | 2021 | New site 2021 - H2 | RICCI 2 BLOK H1 NO.16 RT.01 RW.24 KELURAHAN TANJUNG RIAU KECAMATAN SEKUPANG KOTA BATAM | HTI | SUM-KR-BTM-0611 | TANJUNG_RIAU_PERUMAHAN_RICCI2 | B2S | TBG | WEST | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6617944 | 2022-01-24 |  | 94 | 91 - 120 days | 2022-06-23 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | 2022-03-15 | [10 empty] | CME | 23.Bore pile Rebaring & Pouring | 11.BORE PILE OG | CURRENTLY NO ISSUE | 28:04:22-20:04:22: BOREPILE 17:04:22-10:04:22: PRESPARE CME 06:04:22-06:03:22: REKOM OG 28:02:22-20:02:22: PREPARE REKOM & PARALEL PKS DI BATAM 16:02:22-09:02:22: IW OG 06:02:22: VALIDASI RNP TNP OG 02:02:22-26:01:22: SURVEY OG 24:01:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | NUS-NT-RTG-0328 | 30729170031 | 1910631003 | WAE_RII | BP2022 | TB | 120°29.56.0'E | 8°36.51.47'S | 60 | 40/130/220 | 2022 | New site 2022 - P2 | Golo Ngorok Desa Wae Rii Kecamatan Wae Rii Kabupaten Manggarai | ALT | NUS-NT-RTG-0328 | WAE_RII | B2S | TBG | East | BALINUSRA | Nusa Tenggara Timur | Kab. Manggarai | 6617947 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-31 | 2022-04-04 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-20:04:22: ERECTION 17:04:22: PREPARE ERECTION 14:04:22-10:04:22: REBARRING 06:04:22-03:04:22: EXCAVATION 30:03:22: BOUWPLANK 27:03:22-20:03:22: RFC, PREPARE CME 16:03:22-09:03:22: REKOM 06:03:22-28:02:22: IW CLEAR, PREPARE SOIL TEST 23:02:22: SOSWAR OG 20:02:22: IW CLEAR, PREPARE REKOM 16:02:22-08:02:22: IW OG 06:02:22-03:02:22: VALIDASI RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUM-RI-TBH-1088 | 30740070031 | 0416911003 | PARUNA_TEMBILAHAN_BARAT | BP2022 | TB | 103°7.36.13'E | 0°20.33.39'S | 50 | 0/70/240 | 2022 | Newsite 2022 - P2 | Gg Keluarga RT 003 RW 003 Kelurahan Tembilahan Barat, Kecamatan Tembilahan Hulu, Kabupaten Indragiri Hilir, Provinsi Riau | HTI | SUM-RI-TBH-1088 | PARUNA_TEMBILAHAN_BARAT | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Indragiri Hilir | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | [11 empty] | CME | 22.Excavation | 12.EXCAVATION OG | CURRENTLY NO ISSUE | 28:04:22-20:04:22: EXCAVATION 17:04:22: RFC 13:04:22-10:04:22: REKOM 06:04:22-30:03:22: IW CLEAR 23:03:22-16:03:22: IW OG 15:03:22-15:03:22: VALIDASI RNP TNP 13:03:22: MITRA ASSIGNMENT 09:02:22: SPK RELEASED |  | 401 | 388 TBG
|  | JAW-JI-KDR-4311 | 30743020031 | 1655251003 | MOJOROTO_DERMO | BP2022 | TB | 112°0.3.94'E | 7°46.20.73'S | 40 | 5/105/230 | 2022 | Newsite 2021 |  | HTI | JAW-JI-KDR-4311 | MOJOROTO_DERMO | B2S | TBG | East | JATIM | Jawa Timur | Kota Kediri | 6618175 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22-20:04:22: REHUNTING 18:04:22: VALIDASI 17:04:22-10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-BB-MGR-0526 | 30730510031 | 0804381003 | MANGGAR_MEKAR_JAYA | BP2022 | TB | 108°16.41.62'E | 2°52.10.83'S | 40 | 0/130/250 | 2022 | New site 2022 - P1 |  | HTI | SUM-BB-MGR-0526 | MANGGAR_MEKAR_JAYA | B2S | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kab. Belitung Timur | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-20:04:22-12:04:22: IW 10:04:22-08:04:22: VALIDASI RNP TNP 06:04:22: IW CLEAR 03:04:22-16:03:22: VALIDASI RNP TNP 13:03:22-10:03:22: VALIDASI RNP -> RNP NOK, REHUNTING 09:03:22-28:02:22: REHUNTING 23:02:22-20:02:22: IW OG 16:02:22: VALIDASI RNP TNP -> IW OG 15:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | NUS-NT-MME-0344 | 30740860031 | 1910741003 | REPEATER PARABUBU | NEW SITE 2022-REPEATER | TB | 122°2.1.92'E | 8°37.53.51'S | 45 | 116 |  | Newsite Repeater |  | ALT | NUS-NT-MME-0344 | REPEATER PARABUBU | B2S | TBG | East | BALINUSRA | Nusa Tenggara Timur | Kab. Sikka | 6618131 | 2022-03-16 | 2022-03-17 | 43 | 31 - 60 days | 2022-08-13 | W33-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | NO POWER, TBG PROPOSE SOLAR CELL | 28:04:22-21:04:22: DECISSION POWER XL, PROPOSE DROP BY XL 20:04:22-17:04:22: REHUNTING TITIK ARAHAN 13:04:22-04:04:22: VALIDASI RNP TNP 03:04:22-23:03:22: LAHAN KEHUTANNA, HUNTING 20:03:22: MITRA ASSIGNMENT 17:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | KAL-KI-TNR-1007 | 30740380031 | 2316061003 | REPEATER SAMBALIUNG BENA BARU | NEW SITE 2022-REPEATER | TB | 117°17.40.19'E | 1°54.41.78'N | 70 | 27 |  | Newsite 2022 - Repeater |  | HTI | KAL-KI-TNR-1007 | REPEATER SAMBALIUNG BENA BARU | B2S | TBG | Jabodetabek | KALIMANTAN | Kalimantan Timur | Kab. Berau | 6618120 | 2022-03-08 | 2022-03-09 | 51 | 31 - 60 days | 2022-08-05 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | NO POWER, TBG PROPOSE SOLAR CELL | 28:04:22-21:04:22: DECISSION POWER XL, PROPOSE DROP BY XL 20:04:22-19:04:22: IW OG 17:04:22: VALIDASI RNP TNP, LAHAN CORPORATE PT PAMA 13:04:22-16:03:22: SURVEY OG 13:03:22; MITRA ASSIGNMENT 09:02:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-MDN-2242 | 30729740031 | 0228951003 | MEDAN_AMPLAS_TIMBANG_DELI | BP2022 | TB | 98°43.13.77'E | 3°32.22.9'N | 30 | 80/200/310 | 2022-2024 | New site 2022 - P1 |  | HTI | SUM-SU-MDN-2242 | MEDAN_AMPLAS_TIMBANG_DELI | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kota Medan | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-21:04:22: VALIDASI 20:04:22-23:03:22: IW OG 20:03:22-16:03:22: VALIDASI TNP OG 13:03:22: REHUTING 09:03:22-06:02:22: UNDER RNP TNP 28:02:22-13:02:22: REHUNTING RNP NOK 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JI-KDR-4345 | 30740470031 | 1655211003 | GURAH_TIRU_KIDUL | BP2022 | TB | 112°8.2.4'E | 7°49.27.77'S | 50 | 45/195/290 | 2022 | Newsite 2022 - P2 |  | HTI | JAW-JI-KDR-4345 | GURAH_TIRU_KIDUL | B2S | TBG | East | JATIM | Jawa Timur | Kab. Kediri | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 08.Under RNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-22:04:22: VALIDASI 20:04:22: REHUNTING 18:04:22: VALIDASI 17:04:22-13:04:22: IW OG 10:04:22-15:03:22: VALIDASI RNP TNP 15:03:22: KANDIDAT NOK 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-MDN-2236 | 30729910031 | 0229031003 | MEDAN_JOHOR_GEDUNG_JOHOR | BP2022 | TB | 98°40.19.43'E | 3°31.23.16'N | 40 | 90/210/320 | 2022 | New site 2022 - P2 |  | HTI | SUM-SU-MDN-2236 | MEDAN_JOHOR_GEDUNG_JOHOR | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kota Medan | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-23:03:22: IW OG 20:03:22-16:03:22: REHUNTING 13:03:22-13:02:22: IW OG 09:02:22: IW OG, RNP TNP OK 07:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-KR-BTM-0622 | 30730480031 | 0507581003 | NONGSA_BATU_BESAR | BP2022 | TB | 104°7.37.65'E | 1°9.41.69'N | 40 | 0/160/280 | 2022 | New site 2022 - P2 | Pangkalan TNI AU Hang Nadim,Jln Hang Jebat Kelurahan Batu Besar Kecamatan Nongsa Kota Batam Provinsi Kepulauan Riau | HTI | SUM-KR-BTM-0622 | NONGSA_BATU_BESAR | B2S | TBG | West | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-31 | 2022-04-01 | [10 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-23:03:22: REKOM 20:03:22-16:03:22: REHUNTING 14:03:22: IW OG 13:03:22: VALIDASI RNP TNP 09:03:22: VALIDASI RNP TNP 06:03:22-07:02:22: NOK, REHUNTING ARAHAN XL 06:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SS-BTA-1088 | 30729730031 | 0719111003 | LUBUK_BATANG_BARU | BP2022 | TB | 104°11.52.8'E | 4°2.54.49'S | 60 | 150/205/285 | 2022 | New site 2022 - P2 | Jl. Raya Prabumulih - Baturaja Dusun 13 Desa Lubuk Batang Baru, Kecamatan Lubuk Batang, Kabupaten Ogan Komering Ulu, Provinsi Sumatera Selatan | HTI | SUM-SS-BTA-1088 | LUBUK_BATANG_BARU | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | 2022-03-15 | [10 empty] | RFC | 21.Bouwplank | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22-24:04:22: BOUPLANK 20:04:22-10:04:22: SOIL TEST 06:04:22-03:04:22: PREPARE CME 30:03:22-27:03:22: REKOM OG 23:03:22-06:03:22: IW CLEAR 28:02:22-16:02:22: IW OG 15:02:22-15:02:22: VALIDASI RNP TNP 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUM-RI-TBH-1093 | 30740080031 | 0416921003 | SEBERANG_PEBENAAN | BP2022 | TB | 103°1.15.6'E | 0°41.49.78'S | 50 | 50/230/330 | 2022 | Newsite 2022 - P2 | Jl. Penunjang RT001 RW004 Dusun Berkah Usaha, Kecamatan Keritang, Kabupaten Indragiri Hilir, Provinsi Riau. | HTI | SUM-RI-TBH-1093 | SEBERANG_PEBENAAN | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Indragiri Hilir | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-11 | 2022-04-13 | [10 empty] | CME | 21.Bouwplank | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22-24:04:22: BOUWPLANK 20:04:22-17:04:22: DESIGN OG 13:04:22-10:04:22: SOIL TEST 06:04:22-03:04:22: REKOM 30:03:22: IW OG 27:03:22-24:03:22: VALIDASI RNP TNP KANIDAT D 23:03:22-16:03:22: IW OG 15:03:22-15:03:22: VALIDASI RNP TNP 13:03:22: MITRA ASSIGNMENT 09:02:22: SPK RELEASED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-PBR-1203 | 30729670031 | 0416521003 | KELURAHAN_BINAWIDYA | BP2022 | TB | 101°21.58.5'E | 0°29.35.74'N | 40 | 30/160/250 | 2022-2024 | New site 2022 - P1 | Jl, Kayu Putih Gg. Akasia RT.001 RW.006 Kelurahan Binawidya,Kecamatan Binawidya Kota Pekanbaru Provinsi Riau | HTI | SUM-RI-PBR-1203 | KELURAHAN_BINAWIDYA | B2S | TBG | West | SUMBAGTENG | Riau | Kota Pekanbaru | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-11 | 2022-04-13 |  |  |  | 2022-04-25 | [6 empty] | CME | 21.Bouwplank | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22-24:04:22: BOUWPLANK 20:04:22-17:04:22: RFC 13:04:22-10:04:22: DESIGN OG 06:04:22: REKOM 03:04:22-20:03:22: IW CLEAR 16:03:22-23:02:22: IW OG 20:02:22-16:02:22: VALIDASI RNP TNP OG 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-BT-RKB-0768 | 30729570031 | 1323071003 | LEBAK_CIMARGA | BP2022 | TB | 106°12.32.61'E | 6°24.28.89'S | 70 | 60/160/250 | 2022 | New site 2022 - P2 | Kp. Ilham Jaya RT 010 RW 004 Desa Mekarjaya Kec. Cimarga Kab.Lebak | EID | JAW-BT-RKB-0768 | LEBAK_CIMARGA | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 3/7/2022, , resend 28 apr 22 |  |  | 10.6 | 2022-04-20 | [7 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERECTION 20:04:22: CURRING 17:04:22-03:04:22: REBARRING 30:03:22-20:03:22: EXCAVATION OG 16:03:22-23:02:22: REKOM OG 20:02:22-13:02:22: IW OG 09:02:22-04:02:22: PRIORITY CANDIDATE A 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-UJT-0961 | 30729950031 | 0416591003 | PUJUD_SUKA_JADI | BP2022 | TB | 100°48.56.84'E | 1°28.54.23'N | 50 | 20/200/320 | 2022 | New site 2022 - P2 | Jl. Menggala Sakti RT. 002 RW. 001 Dusun Menggala Kota Kepenghuluan Menggala Sakti Kec. Tanah Putih Kab. Rokan Hilir Prov. Riau. | HTI | SUM-RI-UJT-0961 | PUJUD_SUKA_JADI | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Rokan Hilir | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-03 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERECTION 20:04:22: CURRING 17:04:22-10:04:22: REBARRING 06:04:22: EXCAVATION 03:04:22: PREPARE CME 30:03:22-20:03:22: DESIGN PROCESS 16:03:22-09:03:22: REKOM OG 06:03:22-16:02:22: IW OG 13:02:22-11:02:22: VALIDASI RNP TNP 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-BT-PDG-0621 | 30729360031 | 1322961003 | RANCATEUREUP_LABUAN | BP2022 | TB | 105°50.47.39'E | 6°22.48.58'S | 50 | 40/120/220 | 2022 | New site 2022 - P2 | Jl. Kp. Badur, Rancateureup, Kec. Labuan, Kab. Pandeglang, Prov. Banten | EID | JAW-BT-PDG-0621 | RANCATEUREUP_LABUAN | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Pandeglang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 3/7/2022, , resend 28 apr 22 |  |  | 6.6 | 2022-04-25 | [7 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERECTION 20:04:22: CURRING 17:04:22-13:04:22: REBARRING 10:04:22-03:04:22: EXCAVATION 30:02:22-20:03:22: RFC, MOBDEMOB 16:03:22-06:03:22: REKOM OG 28:02:22: IW CLEAR & PARALEL COLLECT DOC 23:02:22-22:02:22: IW OG 20:02:22: UNDER RNP TNP 16:02:22-13:02:22: REHUNTING RNP NOK 09:02:22-06:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-UJT-0949 | 30730010031 | 0416621003 | BAGANSINEMBAH_BARAT | BP2022 | TB | 100°26.2.4'E | 1°48.8.06'N | 60 | 130/210/340 | 2022 | New site 2022 - P2 | Jl. Salean RT.0l0 RW.004 Dusun Suka Mulya Jaya Kepenghuluan Bagan Sinembah Barat Kecamatan Bagan Sinembah Raya Kabupaten Rokan Hilir Provinsi Riau | HTI | SUM-RI-UJT-0949 | BAGANSINEMBAH_BARAT | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Rokan Hilir | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-03 |  |  |  | 2022-04-25 | [6 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERECTION 20:04:22-10:04:22: POURING 06:04:22: BOUWPLANK 03:04:22-13:03:22: RFC 09:03:22: DESIGN PROCESS 06:03:22-28:02:22: IW CLEAR 23:02:22-13:02:22: IW OG 09:02:22: VALIDASI RNP TNP OG 08:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-BT-RKB-0773 | 30729440031 | 1323001003 | SUKAMANAH_RANGKASBITUNG | BP2022 | TB | 106°16.44.4'E | 6°18.59.22'S | 70 | 70/190/320 | 2022 | New site 2022 - P1 | Kp. Pasir Ranji RT. 03/05 Desa. Sukamanah Kec. Rangkasbitung Kab.Lebak | EID | JAW-BT-RKB-0773 | SUKAMANAH_RANGKASBITUNG | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 3/8/2022, , resend 28 apr 22 |  |  | 10.6 | 2022-04-20 | [7 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERECTION 20:04:22-13:04:22: CURRING 10:04:22-03:04:22: EXCAVATION 30:03:22: BOUWPLANK 27:03:22-20:03:22: LAND CLEARING 16:03:22-13:03:22: REKOM OG 09:03:22-06:03:22: IW CLEAR 28:02:22-13:02:22: VALIDASI RNP TNP, KANDIDAT BERGESER 09:02:22-04:02:22: PRIORITY CANDIDATE A 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-BT-RKB-0767 | 30729480031 | 1323031003 | PARAGE_CIKULUR | BP2022 | TB | 106°8.30.72'E | 6°20.58.6'S | 50 | 60/180/260 | 2022 | New site 2022 - P1 | Kp. Parage Lembur RT.010/002 Desa Parage Kecamatan Cikulur Kab. Lebak Banten | EID | JAW-BT-RKB-0767 | PARAGE_CIKULUR | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 3/7/2022, , resend 28 apr 22 |  |  | 10.6 | 2022-04-25 | [7 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERECTION 20:04:22-13:04:22: CURRING 10:04:22-03:04:22: REBARRING 30:03:22-27:03:22: EXCAVATION 23:03:22-20:03:22: RFC, MOBDEMOB 16:03:22-06:03:22: REKOM OG 28:02:22: IW CLEAR & PARALEL COLLECT DOC 23:02:22-20:02:22: IW OG 17:02:22: VALIDASI RNP OG, IW FAILED 16:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-BKN-1164 | 30730150031 | 0416651003 | GADING_SARI | BP2022 | TB | 101°7.36.49'E | 0°37.39.48'N | 50 | 100/230/320 | 2022 | New site 2022 - P2 | RT 01 RW 02 Dusun 1 Sukajadi Desa Indrapuri Kecamatan Tapung Kabupaten Kampar Provinsi Riau | HTI | SUM-RI-BKN-1164 | GADING_SARI | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Kampar | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-31 | 2022-04-01 | [10 empty] | CME | 29.Erection | 16.TOWER ERECTION OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ERECTION 20:04:22-17:04:22: CURRING 13:04:22-10:04:22: REBARRING 06:04:22: EXCAVATION 03:04:22-27:03:22: LAND CLEARING & BOUWPLANK 23:03:22: RFC 20:03:22-09:03:22: REHUNTING 06:03:22-01:02:22: IW OG 28:02:22: UNDER RNP TNP 23:02:22-20:02:22: REHUNTING 16:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-BT-PDG-0626 | 30739600031 | 1323301003 | SINARJAYA_MANDALAWANGI | BP2022 | TB | 105°58.18.18'E | 6°17.43.99'S | 60 | 10/100/190 | 2022 | Newsite 2022 - B2 |  | EID | JAW-BT-PDG-0626 | SINARJAYA_MANDALAWANGI | B2S | TBG | JABO | JABODETABEK | Banten | Kab. Pandeglang | 6618106 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: IW CLEAR 20:04:22-20:03:22: IW OG 16:03:22-15:03:22: VALIDASI RNP TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JB-BDG-4317 | 30739840031 | 1276921003 | TAMANSAKURA_SUKAHAJI | BP2022 | TB | 107°34.48.84'E | 6°56.0.92'S | 30 | 90/210/330 | 2022 | Newsite 2022 - B2 |  | HTI | JAW-JB-BDG-4317 | TAMANSAKURA_SUKAHAJI | B2S | TBG | Central | JABAR | Jawa Barat | Kota Bandung | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: IW OG 20:04:22: VALIDASI 25:03:22: REHUNTING KANDIDANK NOK 23:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-KDS-0844 | 30729180031 | 1450121003 | KUDUS_UNDAAN | BP2022 | TB | 110°48.37.93'E | 6°55.44.16'S | 50 | 90/210/330 | 2022-2024 | New site 2022 - P1 | Desa Glagahwaru RT 003 RW 005 Desa Glagahwaru Kecamatan Undaan Kabupaten Kudus Provinsi Jawa Tengah | NOKIA | JAW-JT-KDS-0844 | KUDUS_UNDAAN | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Kudus | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22: ME OG 20:04:22: CURRING 17:04:22-14:04:22: LMS CHANGE TO NOKIA 13:04:22-03:04:22: EXCAVATION 30:03:22: BOUWPLANK 27:03:22-23:03:22: IW OG 20:03:22-18:03:22: SUBMIT KANDIDAT D-E 16:03:22-03:03:22: VALIDASI RNP TNP, IW FAILED 01:03:22: IW OG 28:02:22-21:02:22: VALIDASI RNP TNP, IW FAILED 20:02:22-13:02:22: IW OG 09:02:22-08:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-RI-UJT-0952 | 30730040031 | 0416631003 | BAGAN_SINEMBAH_RAYA_PANCA_MUKTI | BP2022 | TB | 100°27.50.4'E | 1°49.3.14'N | 50 | 60/140/300 | 2022 | New site 2022 - P2 | RT.007 RW.003 Dusun Sumber Mukti Kepenghuluan Panca Mukti Kecamatan Bagan Sinembah Raya Kabupaten Rokan Hilir Provinsi Riau. | HTI | SUM-RI-UJT-0952 | BAGAN_SINEMBAH_RAYA_PANCA_MUKTI | B2S | TBG | West | SUMBAGTENG | Riau | Kab. Rokan Hilir | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-03 | [10 empty] | CME | 33.ME & Grounding system process | 19.MECHANICAL & ELECTRICAL OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: ME OG 20:04:22: ERECTION 17:04:22: CURRING 13:04:22: POURING 10:04:22: REBARRING 06:04:22: BOUWPLANK 03:04:22-20:03:22: MOBDEMOB 16:03:22-09:03:22: DESIGN PROCESS 06:03:22-28:02:22: IW CLEAR 23:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
951 |  | SUL-ST-LWK-1100 | 30714640031 | 2604971003 | LUWUK_BUNGIN | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 122°47.41.24'E | 0°56.37.96'S | 60 | 90/210/330 | 2021 | BLITZKRIEG 2021 [NEW] | Lapangan Persibal, Kel. Soho, Kec. Luwuk, Kab. Banggai, Prov. Sul Teng | HTI | SUL-ST-LWK-1100 | LUWUK_BUNGIN | B2S | TBG | EAST | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617749 | 2021-10-25 |  | 185 | > 150 days | 2022-03-24 | W13-2022 | Mar-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-26 | [11 empty] | RFC | 19.Mobilisasi dan Demobilisasi | 10.CME PREPARATION | CURRENTLY NO ISSUE | 28:04:22-24:04:22: MOBDEMOB 03:04:22: REKOM 30:03:22: IW OG 27:03:22-23:03:22: VALIDASI RNP TNP 23:03:22: REHUNTING 20:03:22-18:03:22: VALIDASI RNP TNP 16:03:22-13:03:22: REKOM 09:03:22: VALIDASI DONE, PLAN KETEMU LL 10 MAR 22 UNTUK BAN/BAK 06:03:22: REHUNTING, KANDIDAT NOK 28:02:22: VALIDASI RNP TNP, KANDIDAT OUTSAR KARENA REJECT WARGA --> REHUNTING 25:02:22: ANNOUNCEMENT GO UNTIL RFI 23:02:22-20:02:22: REHUNTING, LL BERUBAH PIKIRAN 16:02:22: IW OG NEW CANDIDATE 14:02:22-06:02:22: REHUNTING, IW FAILED 30:01:22-26:01:22: IW OG 25:01:22: SUBMIT NEW KANDIDAT S & R 23:01:22-19:01:22: WAIT REVIEW NEW CANDIDATE DARI XL 16:01:22: VALIDASI NEW CANDIDATE 12:01:22-02:01:22: REHUNTING NEW CANDIDATE 29:12:21: TIDAK ADA CANDIDATE (POLSEK & PRIVATE TAPI TIDAK MAU DISEWAKAN), OG SURVEY NEW CANDIDATE 26:12:21: IW OG 22:12:21-19:12:21: SITAC PREPARATION 16:12:21: PMO XL CONFIRMED GO SITAC 15:12:21-05:12:21: REVIEW TNP OK, NEED CONFIRMATION FROM XL TO CONTINUE SITAC PROCESS, REVIEW RNP NOK, PARALEL REHUNTING 01:12:21-10:11:21: REVIEW RNP NOK, OG RE-HUNTING PROCESS 07:11:21: CANDIDAT VERIFICATION OG 03:11:21-31:10:21: SURVEY OG, PLAN SUBMIT KANDIDAT W1 NOV |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-KJN-0994 | 30729300031 | 1450181003 | PEKALONGAN_KESESI | BP2022 | TB | 109°31.50.41'E | 7°2.28.82'S | 50 | 90/200/310 | 2022 | New site 2022 - P2 | KWASEN RT 004 RW 007 DESA KWASEN KECAMATAN KESESI KABUPATEN PEKALONGAN | NOKIA | JAW-JT-KJN-0994 | PEKALONGAN_KESESI | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Pekalongan | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-24 |  |  | 7.7 | [8 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22: PONDASI OG, WAIT PSB 20:04:22-17:04:22: ERECTION, WAIT PSB LMS CHANGE TO NOKIA 13:-4:22-03:04:22: ERECTION 30:03:22: REBARRING 27:03:22-16:03:22: EXCAVATION 13:03:22: SITE PREPARATION 09:03:22: DESIGN OG 06:03:22-01:03:22: IW OG 28:02:22-21:02:22: VALIDASI RNP TNP, REJECT WARGA 20:02:22-08:02:22: IW OG 07:02:22: RNP OK, TNP OP 06:02:22-04:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JT-TGL-2619 | 30739650031 | 1450911003 | TEGAL_TARUB | BP2022 | TB | 109°12.41.62'E | 6°55.35.46'S | 50 | 90/210/330 | 2022 | Newsite 2022 - P1 | Kesamiran RT 006 RW 001 Desa Kesamiran Kecamatan Tarub Kabupaten Tegal Provinsi Jawa Tengah | NOKIA | JAW-JT-TGL-2619 | TEGAL_TARUB | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Tegal | 6618110 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | CME | 24.Rebaring | 13.REBARING OG | WAIT PSB | 28:04:22-24:04:22: REBARRING 20:04:22: EXCA 17:04:22-14:04:22: LMS CHANGE TO NOKIA 13:04:22: DESIGN OG 10:04:22-20:03:22: VALIDASI RNP TNP 16:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-BB-SGL-0540 | 30730570031 | 0804401003 | PETALING_BANJAR | BP2022 | TB | 106°0.49.98'E | 2°6.52.29'S | 50 | 10/120/270 | 2022 | New site 2022 - P2 | Jl. Lengkeng RT.004 RW.003 Desa Petaling Banjar, Kecamatan Mendo Barat, Kabupaten Bangka, Provinsi Kepulauan Bangka Belitung | HTI | SUM-BB-SGL-0540 | PETALING_BANJAR | B2S | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kab. Bangka | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | 2022-03-15 | [10 empty] | CME | 24.Rebaring | 13.REBARING OG | CURRENTLY NO ISSUE | 28:04:22-24:04:22: REBARRING 20:04:22-17:04:22: EXCAVATION 13:04:22-06:04:22: BOUWPLANK 03:04:22-27:03:22: PREPARE CME 23:03:22-16:03:22: REKOM 13:03:22-09:03:22: IW CLEAR 06:03:22-03:02:22: UNDER RNP TNP, REJECT WARGA 28:02:22: IW OG 23:02:22: UNDER RNP TNP, VALIDASI KANDIDAT D 23:02:22: IW OG 22:02:22-20:02:22: UNDER RNP TNP REVIEW 16:02:22-14:02:22: REHUNTING 13:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JI-LMJ-4242 | 30742650031 | 1655241003 | LUMAJANG TOMPOKERSAN | BP2022 | TB | 113°13.25.46'E | 8°7.29.32'S | 25 | 90/240/340 | 2022 | Newsite 2021 - H2 |  | HTI | JAW-JI-LMJ-4242 | LUMAJANG TOMPOKERSAN | B2S | TBG | East | JATIM | Jawa Timur | Kab. Lumajang | 6618175 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22-24:04:22: REHUNTING ARAHAN 22:04:22: VALIDASI NOK 20:04:22-10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SS-MPR-1266 | 30730130031 | 0719211003 | BEDILAN | BP2022 | TB | 104°39.39.7'E | 4°6.3.8'S | 60 | 30/185/275 | 2022 | New site 2022 - P2 | Jl. Budiharjo RT.007 RW.002 Desa Bedilan, Kecamatan Belitang, Kabupaten Ogan Komering Ulu Timur, Provinsi Sumatera Selatan | HTI | SUM-SS-MPR-1266 | BEDILAN | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-10 | 2022-04-11 | [10 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: REKOM 20:04:22-06:04:22: IW CLEAR 03:04:22-09:03:22: IW OG 06:03:22: VALIDASI RNP TNP OG, IW FAILED 28:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | SUM-AC-SUS-0344 | 30739830031 | 0111291003 | SIMPANG_KIRI_SUBULUSSALAM_BARAT | BP2022 | TB | 97°59.20.04'E | 2°38.56.44'N | 50 | 0/170/280 | 2022 | Newsite 2022 - B2 |  | HTI | SUM-AC-SUS-0344 | SIMPANG_KIRI_SUBULUSSALAM_BARAT | B2S | TBG | West | SUMBAGUT | Aceh | Kota Subulussalam | 6618108 | 2022-03-07 | 2022-03-07 | 52 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW |  |  | wait address | [9 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: REKOM 20:04:22-06:04:22: IW CLEAR 03:04:22-23:03:22: IW OG 20:03:22-17:03:22: VALIDASI RNP TNP 16:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-LMP-2232 | 30729700031 | 0228921003 | SIMPANG_KOPI | BP2022 | TB | 99°19.44.51'E | 3°18.9.43'N | 40 | 0/180/270 | 2022 | New site 2022 - P2 |  | HTI | SUM-SU-LMP-2232 | SIMPANG_KOPI | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Batu Bara | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW |  |  | wait address | [9 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: REKOM 20:04:22-07:04:22: IW OG 06:04:22-05:04:22: VALIDASI RNP TNP 03:04:22-23:03:22: REHUNTING 20:03:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-SU-SRH-2250 | 30729810031 | 0229001003 | TANAH_BESIH | BP2022 | TB | 99°12.40.5'E | 3°19.25.86'N | 50 | 90/170/250 | 2022 | New site 2022 - P2 | Jalan Desa Tebat Monok Kampung 5 Desa Tebat Monok Kecamatan Kepahiang Kabupaten Kepahiang Provinsi Bengkulu | HTI | SUM-SU-SRH-2250 | TANAH_BESIH | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Serdang Bedagai | 6617950 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | LAHAN CORPORATE SUCOFINDO | 28:04:22-24:04:22: REKOM 20:04:22-23:03:22: BAN/BAK OG 20:03:22-16:03:22: VALIDASI RNP TNP 13:03:22-11:03:22: IW OG 10:03:22: VALIDASI RNP TNP 09:03:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-YO-BTL-0153 | 30739190031 | 1510131003 | BANGUNJIWO_KASIHAN | BP2022 | TB | 110°20.45.35'E | 7°50.31.09'S | 40 | 30/150/260 |  | Newsite 2022 - Repeater | SEMBUNGAN RT. 04, Kalurahan Bangunjiwo, Kapanewon Kasihan, Kabupaten Bantul, Provinsi D.I. Yogyakarta. | NOKIA | JAW-YO-BTL-0153 | BANGUNJIWO_KASIHAN | B2S | TBG | Central | JATENG | DI Yogyakarta | Kab. Bantul | 6618092 | 2022-03-03 | 2022-03-04 | 56 | 31 - 60 days | 2022-07-31 | W32-2022 | Jul-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: REKOM LMS CHANGE TO NOKIA 13:04:22: REKOM 10:04:22-06:04:22: VALIDASI RNP TNP 06:04:22-05:04:22: IW OG 04:04:22: VALIDASI RNP TNP 03:04:22: IW CLEAR 30:03:22-15:03:22: IW OG 13:03:22-09:03:22: VALIDASI RNP TNP OG 06:03:22: MITRA ASSIGNMENT 04:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SN-PLP-1340 | 30730580031 | 2817631003 | SEBA-SEBA_WALENRANG_TIMUR | BP2022 | TB | 120°12.54.0'E | 2°53.35.52'S | 60 | 120/200/290 | 2022 | New site 2022 - P2 | Desa Seba-Seba, Kec. Walenrang Timur , Kab. Luwu Prov. Sulawesi Selatan | HTI | SUL-SN-PLP-1340 | SEBA-SEBA_WALENRANG_TIMUR | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Luwu | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-02 | [10 empty] | CME | 36.PLN application | 20.SRFI | CURRENTLY NO ISSUE | 28:04:22-24:04:22: RFI, WAIT RFIN 20:04:22-17:04:22: PREPARE ERECTION 10:04:22: CURRING 06:04:22: BACKFILLING 03:04:22-20:03:22: REBARRING 16:03:22-06:03:22: WAIT APD, SOIL TEST DONE 28:02:22: REKOM OG 20:02:22: IW CLEAR 16:02:22-13:02:22: IW OG 09:02:22: RNP TNP OG -> IW OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-UNR-2561 | 30729530031 | 1450241003 | SEMARANG_TENGARAN | BP2022 | TB | 110°34.22.08'E | 7°25.3.81'S | 70 | 70/220/340 | 2022 | New site 2022 - P2 | Dusun Miri RT. 013 RW. 003 Desa Duren Kecamatan Tengaran Kabupaten Semarang Provinsi Jawa Tengah | NOKIA | JAW-JT-UNR-2561 | SEMARANG_TENGARAN | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Semarang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-08 | [11 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22: SRFI, WAIT PSB 17:04:22: ME OG, WAIT PSB LMS CHANGE TO NOKIA 13:04:22-06:04:22: POURING 03:04:22-30:03:22: REBARRING 27:03:22-16:03:22: MOBDEMOB 13:03:22-09:03:22: SOIL TEST 06:03:22: REKOM 28:02:22-16:02:22: IW CLEAR 13:02:22: IW OG 09:02:22-03:02:22: VALIDATION RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-KRG-2162 | 30729580031 | 1450261003 | KARANGANYAR_JUMAPOLO | BP2022 | TB | 110°58.51.85'E | 7°42.16.65'S | 60 | 90/210/330 | 2022 | New site 2022 - P1 | Geneng RT 001 Rw 007 Desa Kwangsan Kecamatan Jumapolo Kabupaten Karanganyar Provinsi Jawa Tengah | NOKIA | JAW-JT-KRG-2162 | KARANGANYAR_JUMAPOLO | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Karanganyar | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22: SRFI, WAIT PSB 20:04:22: CURRING 17:04:22-14:04:22: LMS CHANGE TO NOKIA 13:04:22: BOUWPLANK 10:04:22: EXCAVATION 06:04:22-03:04:22: BOUWPLANK 30:03:22: REKOM 27:03:22-23:03:22: IW OG 20:03:22-16:03:22: VALIDASI RNP TNP 15:03:22-15:03:22: IW OG 13:03:22-09:03:22: IW FAILED, VALIDASI RNP TNP OG 06:03:22-01:03:22: IW OG 28:02:22-18:02:22: VALIDASI RNP TNP OG, REJECT WARGA 16:02:22-13:02:22: IW OG 09:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-TMG-2674 | 30729410031 | 1450221003 | TEMANGGUNG_KANDANGAN | BP2022 | TB | 110°11.50.0'E | 7°14.36.9'S | 70 | 80/180/290 | 2022 | New site 2022 - P1 | Dusun Kejiwan RT. 001 RW. 006 Desa Kandangan Kecamatan Kandangan Kabupaten Temanggung Provinsi Jawa Tengah | NOKIA | JAW-JT-TMG-2674 | TEMANGGUNG_KANDANGAN | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Temanggung | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | [11 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22: SRFI, WAIT PSB 20:04:22: ME LMS CHANGE TO NOKIA 13:04:22-30:03:22: ERECTION 27:03:22-16:03:22: REBARRING 13:03:22-06:03:22: EXCAVATION OG 28:02:22-20:02:22: REALISASI IW 16:02:22-13:02:22: IW OG 09:02:22-04:02:22: TNP OG. RNP OK KANDIDAT B&C, PRIORITY 1 C 03:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-PWD-0050 | 30729280031 | 1450171003 | CANDISARI_GROBOGAN | BP2022 | TB | 110°51.53.06'E | 7°6.26.57'S | 60 | 90/180/300 | 2022 | New site 2022 - P2 | Krajan RT 007/RW 002 Desa Candisari Kecamatan Purwodadi Kabupaten Grobogan Provinsi Jawa Tengah | NOKIA | JAW-JT-PWD-0050 | CANDISARI_GROBOGAN | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Grobogan | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22: SRFI, WAIT PSB 20:04:22:-17:04:22: ME OG, WAIT PSB 14:04:22: LMS CHANGE TO NOKIA 13:04:22-03:04:22: ERECTION 30:03:22: REBARRING 27:03:22-01:03:22: VALIDASI RNP TNP, BERGESER 45M 01:03:22: IW OG 28:02:22-16:02:22: VALIDASI RNP TNP OG, KANDIDAT REJECT WARGA 15:02:22-08:02:22: IW OG 06:02:22-03:02:22: VALIDASI RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-PWD-0047 | 30729270031 | 1450161003 | KARANGWADER_GROBOGAN | BP2022 | TB | 110°49.43.43'E | 7°6.55.48'S | 60 | 10/150/270 | 2022 | New site 2022 - P2 | Karangwader RT.001 RW.002 Desa Karangwader Kecamatan Penawangan Kabupaten Grobogan Provinsi Jawa Tengah | NOKIA | JAW-JT-PWD-0047 | KARANGWADER_GROBOGAN | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Grobogan | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | [11 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22: SRFI, WAIT PSB 20:04:22-17:04:22: ME OG, WAIT PSB LMS CHANGE TO NOKIA 13:04:22-30:03:22: ERECTION 27:03:22-16:03:22: REBARRING 13:03:22-06:03:22: EXCAVATION OG 28:02:22-23:02:22: REKOM OG 20:02:22: REALISASI IW 16:02:22-13:02:22: IW OG KANDIDAT B 09:02:22: RNP TNP REVIEW, IW FAILED KANDIDAT A 08:02:22: IW OG 06:02:22-02:02:22: VALIDASI KANDIDAT 30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-UNR-2562 | 30729630031 | 1450271003 | SEMARANG_SURUH | BP2022 | TB | 110°37.45.29'E | 7°20.32.77'S | 50 | 10/120/240 | 2022 | New site 2022 - P2 | Dusun Krajan RT. 013 RW. 002 Desa Kedungringin Kecamatan Suruh Kabupaten Semarang Provinsi Jawa Tengah | NOKIA | JAW-JT-UNR-2562 | SEMARANG_SURUH | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Semarang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | [11 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22: SRFI, WAIT PSB 20:04:22-17:04:22: ME OG, WAIT PSB LMS CHANGE TO NOKIA 13:04:22-30:03:22: ERECTION 27:03:22-23:03:22: REBARRING 20:03:22-16:03:22: EXCAVATION 13:03:22-09:03:22: SITE PREPARATION 06:03:22: REKOM 28:02:22-23:02:22: REALISASI IW 20:02:22: IW OG 16:02:22-15:02:22: REJECT IW, VALIDASI RNP TNP 13:02:22-08:02:22: IW OG 06:02:22: TNP OG. RNP OK CANDIDATE A 04:02:22: VALIDASI RNP TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JK-TJP-0720 |  | 110965109 | ANGINGENDINGMW_HBTS | RELOCATION | SKP | 106°55.14.2'E | 6°6.41.9'S | 20 | 90/210/330 | 0 |  | Jl. Dukuh Timur No.5, Kel. Semper Barat RT.009 RW.15 Kec. Cilincing, Kota Jakarta Utara Prov. DKI Jakarta | EID | JAW-JK-TJP-0720 | CACING CILINCING RELOCATION | COLO | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Utara | 6618157 | 2022-03-29 | 2022-03-29 | 30 | < 30 days | 2022-04-28 | W18-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 10.Under CIVIL review | 06.ERM PROCESS | NEED STRENGTENING PARALEL | 28:04:22-30:03:22: ESR PREPARATION 29:03:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30747890031 | 1451961003 | JALAN_DR_WAHIDIN | BP2022 | TB | 110°10.33.31'E | 7°18.47.88'S | 30 | 30/120/240 |  | Newsite 2022 - B2 |  | NOKIA | JAW-JT-TMG-2679 | JALAN_DR_WAHIDIN | B2S | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Temanggung | 6618212 | 2022-04-19 | 2022-04-20 | 9 | < 30 days | 2022-09-16 | W38-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 04.Survey OG | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: SURVEY OG 20:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30747860031 | 1806951003 | BUWUN_MAS_SEKOTONG | BP2022 | TB | 116°4.52.85'E | 8°51.21.86'S | 50 | 40/200/310 |  | Newsite 2022 - B2 |  | HTI | NUS-NB-GRG-5398 | BUWUN_MAS_SEKOTONG | B2S | TBG | East | BALINUSRA | Nusa Tenggara Barat | Kab. Lombok Barat | 6618211 | 2022-04-19 | 2022-04-20 | 9 | < 30 days | 2022-09-16 | W38-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 09.Under TNP review | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-24:04:22: VALIDASI 20:04:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-RBG-1775 | 30729550031 | 1450251003 | REMBANG_KALIORI | BP2022 | TB | 111°17.33.01'E | 6°44.29.08'S | 60 | 0/120/210 | 2022 | New site 2022 - P2 | Pengkol RT 001 RW 002 Desa Pengkol Kecamatan Kaliori Kabupaten Rembang Provinsi Jawa Tengah | NOKIA | JAW-JT-RBG-1775 | REMBANG_KALIORI | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Rembang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-24 |  |  | 7.7 | [8 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22-17:04:22: PLN, WAIT PSB 17:04:22: SRFI, PLN, LMS CHANGE TO NOKIA 13:04:22-03:04:22: PLN 30:03:22: ERECTION 27:03:22-16:03:22: EXCAVATION 13:03:22-09:03:22: SITE PREPARATION 06:02:22-01:03:22: IW OG 28:02:22-20:02:22: VALIDASI RNP TNP, REJECT WARGA 16:02:22: IW CLEAR 13:02:22: IW OG 09:02:22-03:02:22: VALIDATION RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-RBG-1776 | 30729460031 | 1450231003 | REMBANG_LASEM | BP2022 | TB | 111°26.7.41'E | 6°42.29.96'S | 60 | 30/110/210 | 2022 | New site 2022 - P2 | Desa Karasgede RT 08 RW 03, Kecamatan Lasem, Kabupaten Rembang Provinsi Jawa Tengah | NOKIA | JAW-JT-RBG-1776 | REMBANG_LASEM | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Rembang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-24 |  |  | 7.7 | [8 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22-17:04:22: PLN, WAIT PSB LMS CHANGE TO NOKIA 13:04:22-30:03:22: ERECTION 27:03:22-16:03:22: REBARRING 13:03:22-09:03:22: SITE PREPARATION 06:03:22-01:03:22: IW OG 28:02:22-22:02:22: VALIDASI RNP TNP, PERGESERAN 45M 20:02:22: REALISASI IW 16:02:22: IW CLEAR 13:02:22: IW OG 09:02:22-03:02:22: VALIDATION RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-BLA-0127 | 30729320031 | 1450191003 | BLORA_KRADENAN | BP2022 | TB | 111°26.25.2'E | 7°14.10.27'S | 60 | 0/120/270 | 2022 | New site 2022 - P2 | Dusun Goito RT. 005 RW. 001 Desa Mendenrejo, Kecamatan Kradenan Kabupaten Blora Prov Jawa Tengah | NOKIA | JAW-JT-BLA-0127 | BLORA_KRADENAN | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Blora | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | [11 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22-17:04:22: SRFI, WAIT PSB LMS CHANGE TO NOKIA 13:04:22-03:04:22: PLN 30:03:22: ERECTION 27:03:22-16:03:22: REBARRING 13:03:22-06:03:22: CME PREPARATION 28:02:22-20:02:22: SITE PREPARATION 16:02:22-16:02:22: REKOM OG 13:02:22-08:02:22: IW OG 06:02:22-02:02:22: VALIDASI KANDIDAT 30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JT-MKD-1126 | 30729200031 | 1450131003 | MAGELANG_TEMPURAN | BP2022 | TB | 110°9.19.48'E | 7°33.28.73'S | 50 | 90/210/330 | 2022 | New site 2022 - P1 | Dsn Bowan RT.004 RW.012, Desa Tanggulrejo, Kecamatan Tempuran, Kabupaten Magelang, Provinsi Jawa Tengah. | NOKIA | JAW-JT-MKD-1126 | MAGELANG_TEMPURAN | B2S | TBG | Central | JATENG | Jawa Tengah | Kab. Magelang | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-07 | [11 empty] | CME | 37.Power connection process | 20.SRFI | WAIT PSB | 28:04:22-24:04:22-17:04:22: SRFI, WAIT PSB LMS CHANGE TO NOKIA 13:04:22-30:03:22: PLN 27:03:22-16:03:22: CURING TIME 13:03:22-06:03:22: PONDASI OG 28:02:22-23:02:22: REKOM OG 20:02:22: IW OG 16:02:22-15:02:22: REJECT IW, VALIDASI RNP TNP 13:02:22: IW OG 09:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JK-TNA-0441 |  | JK-JKP-0003 |  | NEW COLO | TB | 106°50.0.02'E | 6°11.41.3'S | 20 | 80/190/310 | 2022 |  |  | EID | JAW-JK-TNA-0441 | LEMBANG MENTENG RELOCATION BARU | COLO | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Pusat | 6618179 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-05-05 | W19-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | NY STIP | 07.ESR preparation | 06.ERM PROCESS | CURRENTLY NO ISSUE | 28:04:22-13:04:22: ERM PROCESS 10:04:22-05:04:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | SUM-BB-MGR-0529 | 30730550031 | 0804391003 | DAMAR_SUKAMANDI | BP2022 | TB | 108°14.11.85'E | 2°48.47.7'S | 50 | 50/190/330 | 2022 | New site 2022 - P2 | Jl. Kuweni,RT.002, RW. 001, Dusun Sukamandi, Desa Sukamandi,Kecamatan Damar,Kabupaten Belitung Timur, Provinsi Kepulauan Bangka Belitung | HTI | SUM-BB-MGR-0529 | DAMAR_SUKAMANDI | B2S | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kab. Belitung Timur | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22-25:04:22: REHUNTING 24:04:22: VALIDASI RNP TNP KANDIDAT KE-9 20:04:22-05:04:22: VALIDASI RNP TNP 05:04:22: REHUNTING, KANDIDAT NOK 03:04:22-20:03:22: VALIDASI RNP TNP NEW CANDIDTAE 16:03:22: UNDER RNP TNP 13:03:22: REHUNTING 09:03:22: IW OG 06:03:22-23:02:22; REHUNTING 20:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SN-SGM-1609 | 30730500031 | 2817611003 | MONCONGLOE_MANUJU | BP2022 | TB | 119°35.3.25'E | 5°17.29.4'S | 60 | 90/190/280 | 2022 | New site 2022 - P2 |  | HTI | SUL-SN-SGM-1609 | MONCONGLOE_MANUJU | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Gowa | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 08.Under RNP review | 06.ERM PROCESS | ISSUE PERUNTUKAN LAHAN UNTUK BENDUNGAN | 28:04:22-25:04:22: VALIDASI 24:04:22-22:03:22: IW OG 20:03:22-18:03:22: VALIDASI RNP TNP, SITE BERADA DI GOWA 16:03:22-06:03:22: REHUNTING 28:02:22-22:02:22: VALIDASI RNP TNP 20:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
|  | JAW-JI-SDA-4319 | 30742610031 | 1655231003 | TAMAN_SEPANJANG | BP2022 | TB | 112°42.33.31'E | 7°20.22.83'S | 20 | 20/105/225 | 2022 | Newsite 2021 |  | HTI | JAW-JI-SDA-4319 | TAMAN_SEPANJANG | B2S | TBG | East | JATIM | Jawa Timur | Kab. Sidoarjo | 6618175 | 2022-04-05 | 2022-04-05 | 23 | < 30 days | 2022-09-02 | W36-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | SITAC | 12.CP Process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-26:04:22: IW OG MCP +2M 24:04:22-22:04:22: VALIDASI 20:04:22-10:04:22: SURVEY OG 06:04:22: MITRA ASSIGNMENT 05:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  |  | 30747840031 | 1015261003 | SUKADANA_BUMI_AYU | BP2022 | TB | 105°28.56.52'E | 5°1.15.58'S | 60 | 0/125/220 |  | Newsite 2022 - B2 |  | HTI | SUM-LA-SDN-1146 | SUKADANA_BUMI_AYU | B2S | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Timur | 6618211 | 2022-04-19 | 2022-04-20 | 9 | < 30 days | 2022-09-16 | W38-2022 | Sep-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | [13 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | CURRENTLY NO ISSUE | 28:04:22-26:04:22: REHUNTING 25:04:22: VALIDASI 24:04:22: SURVEY OG 20:04:22: SPK RECEIVED |  | 401 | 388 TBG
|  | JAW-JK-GGP-0435 | 30741690031 | 1137891003 | JAW-JK-GGP-0435 | RELOCATION | TB | 106°45.33.84'E | 6°8.20.04'S | 25 | 90/210/330 |  |  |  | EID | JAW-JK-GGP-0435 | PETERNAKAN KAPUK RAYA RELOCATION | B2S | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618147 | 2022-03-22 | 2022-03-22 | 37 | 31 - 60 days | 2022-08-19 | W34-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 04.Survey OG | 03.SURVEY PROCESS | CURRENTLY NO ISSUE | 28:04:22-27:03:22: SURVEY OG 23:03:22-22:03:22: SPK RECEIVED |  | 401 | 388 TBG
NEW SPK B2S |  | JAW-JK-GGP-0458 | 30729520031 | 1136851003 | ANGKE_JAYA_TAMBORA | BP2022 | TB | 106°47.49.78'E | 6°8.39.81'S | 20 | 150/260/340 | 2022-2024 | New site 2022 - P1 |  | EID | JAW-JK-GGP-0458 | ANGKE_JAYA_TAMBORA | B2S | TBG | Jabodetabek | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6617948 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [12 empty] | PRESITAC | 06.Rehunting OG | 05.REHUNTING | HARDSITAC LACK OF FREE SPACE | 28:04:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
NEW SPK B2S |  | SUL-SA-ARM-0429 | 30730300031 | 2405921003 | PAPUTUNGAN_LIKUPANG_BARAT | BP2022 | TB | 124°58.1.2'E | 1°43.34.0'N | 60 | 0/140/270 | 2022 | New site 2022 - P2 | Lorong Jiko, Jaga III, RT/RW 000/000, Desa Paputungan, Kecamatan Likupang Barat, Kabupaten Minahasa Utara, Propinsi Sulawesi Utara. | HTI | SUL-SA-ARM-0429 | PAPUTUNGAN_LIKUPANG_BARAT | B2S | TBG | East | SULAWESI | Sulawesi Utara | Kab. Minahasa Utara | 6617949 | 2022-01-25 | 2022-01-28 | 93 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-28 | [11 empty] | SITAC | 13.Rekom L/C process | 07.SITAC PROCESS | CURRENTLY NO ISSUE | 28:04:22-30:03:22: REKOM 27:03:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS |  | 401 | 388 TBG
960 |  | SUL-ST-LWK-1084 | 30742410031 | 260091104 | Toili3 | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 122°22.35.9'E | 1°27.44.24'S | 60 | 50/180/300 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | SUL-ST-LWK-1084 | MOILONG_MINAHAKI | COLO | XL | EAST | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617766 | 2021-11-05 |  | 174 | > 150 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2022-02-25 | [7 empty] | 37.Power connection process | 20.SRFI | GO SRFI | 14:03:22: SRFI 17:03:22: PONDASI OG 28:02:22-25:02:22: ANNOUNCEMENT GO UNTIL SRFI 24:02:22-16:12:21: TNP OK, NEED CONFIRM PMO GO CME 15:12:21-09:12:21: STO RECALL 08:12:21: STO DECLARED, WAIT RFI BY HTI 05:12:21-28:11:21: ERM REJECTION, SITE ISSOLATED 21:11:21-07:11:21: ESR PROCESS OG, NEED REVIEW TNP ALITA |  | 401
957 |  | KAL-KT-KSN-0432 | 30723440031 | 210596107 | KATINGAN HILIR-3 | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 113°19.4.55'E | 1°52.48.72'S | 45 | 120/205/310 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Pinggir Sei Katingan Rt 02/- Desa Telangkah Kec Katingan Hilir | HTI | KAL-KT-KSN-0432 | KATINGAN_HILIR_TELANGKAH | COLO | XL | CENTRAL | KALIMANTAN | Kalimantan Tengah | Kab. Katingan | 6617766 | 2021-11-05 |  | 147 | 121 - 150 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW |  |  | 224200238022 |  |  | 2021-11-22 |  |  | 2022-04-01 |  |  |  |  | 37.Power connection process | 20.SRFI | CURRENTLY NO ISSUE | 27:04:22: 1 APR RFI, BUT RFIN TO TBG 27 APR 17:03:22: SRFI, WAIT MATERIAL PLN 24:02:22: FOUNDATION DONE 17:02:22-16:01:22: PREPARE MATERIAL 12:01:22-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-07:11:21: ESR PROCESS OG, NEED REVIEW TNP ALITA |  | 401
968 |  | SUM-SU-PSP-2163 | 30720800031 | 021417109 | DESA SISOMA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 99°25.57.9'E | 1°2.3.37'N | 60 | 90/180/340 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Tano Tombangan, Desa Haren, Kec. Tano Tombangan Angkola, Kab. Tapanuli Selatan, Prov. Sumatera Utara | HTI | SUM-SU-PSP-2163 | INGUL_JAE | COLO | XL | WEST | SUMBAGUT | Sumatera Utara | Kab. Tapanuli Selatan | 6617768 | 2021-11-05 |  | 174 | > 150 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-19 | [7 empty] | 37.Power connection process | 20.SRFI | CURRENTLY NO ISSUE | 14:04:22-16:01:22: SRFI, PLN CONNECTION 12:01:22: FOUNDATION DONE, PLAN PLN NEXT WEEK & WAITING SK PLN FROM XL 02:01:22-29:12:21: RBS DONE, START ME OG 26:12:21-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-07:11:21: ESR PREPARATION OG,NEED REVIEW RNP HUAWEI |  | 401
959 |  | JAW-JB-SPA-4115 | 30720750031 | 125059109 | RNC_KARANGPAWITAN1_P2_SITE PLANNING 1_NEWSITE_407 | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 108°6.23.62'E | 7°36.53.93'S | 50 | 0/120/240 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Hegarwangi Kp. Rancabugis RT.002 RW.004, Kec. Bantarkalong, Kab. Tasikmalaya Prov. Jawa Barat | HTI | JAW-JB-SPA-4115 | BANTARKALONG_HEGARWANGI | COLO | XL | CENTRAL | JABAR | Jawa Barat | Kab. Tasikmalaya | 6617766 | 2021-11-05 |  | 174 | > 150 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-15 | [7 empty] | 37.Power connection process | 20.SRFI | CURRENTLY NO ISSUE | 14:04:22-17:03:22: SRFI, WAIT PLN SURVEY 24:02:22: FOUNDATION OG 17:02:22: PROSES EXTEND PERMIT 02:02:22: RBS FOUNDATION 26:01:22-16:01:22: PREPARE MATERIAL 12:01:22: PROCESS PR PO TO INTISEL 05:01:22-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-07:11:21: ESR PROCESS OG,NEED REVIEW RNP HUAWEI |  | 401
|  | SUL-SN-RTP-1398 |  | 2816241001 | TAGARI - RELOC | X RELOC TBG | TRB | 119°54.6.37'E | 2°57.47.23'S | 42 | 90/210/330 |  | RELOCATION | Jalan Limbong, RT/RW 002/001, Kelurahan Tampo Tallunglipu, Kecamatan Tallunglipu, Kabupaten Toraja Utara, Propinsi Sulawesi Selatan | CAA | SUL-SN-RTP-1398 | RANTEPAO RELOCATION II | COLO | TBG | EAST | SULAWESI | Sulawesi Selatan | Kab. Toraja Utara | 6618000 | 2022-01-31 | 2022-01-31 | 87 | 61 - 90 days | 2022-03-02 | W10-2022 | Mar-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-03 | [12 empty] | 37.Power connection process | 20.SRFI | CURRENTLY NO ISSUE | 13:03:22-28:02:22: PERKUATAN 16:02:22-06:01:22: SRFI, POWER CONNECTION 02:02:22: ERM PROCESS 31:01:22: SPK RELEASED
520 |  | SUM-KR-RAN-0601 | 30692120031 | 0506581003 | TANJUNG_KUMBIK_UTARA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 108°5.9.21'E | 3°38.43.54'N | 60 | 65/115/180 | 2021 | BLITZKRIEG 2021 [NEW] | Karang Labak RT.004 RW.001 Desa Tanjung Kumbik Utara Kec. Pulau Tiga Barat Kab. Natuna Provinsi Kepulauan Riau | HTI | SUM-KR-RAN-0601 | TANJUNG_KUMBIK_UTARA | B2S | TBG | West | SUMBAGTENG | Kepulauan Riau | Kab. Natuna | 6617438 | 2021-08-06 |  | 170 | > 150 days | 2022-01-03 | W02-2022 | Jan-2022 | 2021-12-13 | W51-2021 | Dec-2021 | 2021-11-27 | W48-2021 | Nov-2021 | 2022-01-21 | W04-2022 | Jan-2022 | MW | 2021-10-03 |  | 183082846970 | 6.6 |  | sto |  |  | 2022-01-23 | W05-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23:01:22: RFIN 19:01:22: RFI, WAIT RFIN 16:01:22: SRFI, PLAN PLN CONNECT 17 JAN 12:01:22-29:12:21: ERECTION OG, BACKFILL & PONDASI RBS OG 26:12:21: BACKFILL OG 22:12:21: POURING OG, PLAN ERECTION 25 DEC, PLAN RFI 30 DEC 19:12:21: START POURING 15:12:21: PREPARE POURING PLAN ERECTION 15 DEC, PLAN RFI 26 DEC 12:12:21: REBARING OG 08:12:21: EXCAVATION DONE, LEAN CONCRETE PLAN 7 DEC, PLAN REBARING 8 DEC, PLAN COR 11 DEC, ETA TOWER 12 DEC, ON SITE 14 DEC KARENA LANGSIR, PLAN ERECTION 15 DEC, PLAN RFI 25 DEC 05:12:21: EXCAVATION MANUAL OG 70%, TERKENDALA CUACA, PARALEL LANGSIR MATERIAL COR, DELIVERY MATERIAL ETA 10 DEC 01:11:21-28:11:21: EXCAVATION MANUAL OG, PARALEL BARBERNDING, DELIVERY MATERIAL PLAN 27 NOV, ETA 12 DEC 24:11:21-21:11:21: EXCAVATION MANUAL OG, DELIVERY MATERIAL PLAN 27 NOV, ETA 12 DEC 17:11:21: EXCAVATION OG DILAKUKAN OLEH WARGA KARNE MINTA FULL DIKERJAIN WARGA, LAGI NEGOSIASI DGN WARGA PLAN DEAL 17 NOV, WAITING DEAL PPO LANGSIR MATERIAL, PLAN DEAL PPO 17 NOV, JIKA LANGSIR MATERIAL UDAH CONFIRM PPO, PLAN START BESOK & DELIVERY TOWER VIA KAPAL H+1 (BESOK) 14:11:21-10:11:21: EXCAVATION OG 07:11:21: OG EXCAVATION MANUAL 8 NOV, Plan Tower naik kapal tgl 15 Nov, Tower Onsite 25 Nov via kapal 03:11:21: MATERIAL ON DELIVERY, PLAN ON SITE 10 NOV, TOWER SORTIR OG, PLAN EXCAVATION 5 NOV, ANCHOR&TEMPLATE PLAN ON SITE 12 NOV, PLAN POURING 14 NOV, PLAN RFI 27 NOV 31:10:21 - 23:10:21: SITE KEPULAUAN NEED ADD TRANSPORT OG 20:10:21-17:10:21: NEED APPROVAL OPSIC, PENGAJUAN ADD TRANSPORT PLAN CME START W3 OCT 13:10:21: NY START CME NEED PENGAJUAN ADD TRANSPORT KARENA SITE BERADA DIKEPULAUAN, KEPULAUAN RIAU 10:10:21-06:10:21: REKOM DONE, MENUNGGU JADWAL SOILTEST, PLAN SOILTEST 10 OCT, ESTIMASI START GALIAN 10 OCT 2021 04:10:21-26:09:21: REKOM DONE, TIM SOILTEST MASIH MENUNGGU JADWAL KAPAL KE KEP NATUNA, KARENA JADWAL KAPAL MASIH BELUM MENENTU UNTUK SAAT INI 22:09:21: REKOM LURAH CAMAT DONE, SOILTEST OG 19:09:21: KANDIDAT D APPROVE BY TNP VALIDASI UNDER RNP 15:09:21: 13:09:21: UNDER REVIEW REPEATER BY PAK SUKRI 08:09:21: 01:09:21: 25:08:21:22:08:21 : 18:08:21: 16:08:21: UNDER REVIEW TIM TNP, NEED REVIEW REPEATER 10:08:21 : REVIEW RNP DONE CANDIDAT A PRIORITY 1 CANDIDAT C PRIORITY 2, REVIEW TNP CANDIDAT A NOK, WAITING REVIEW CANDIDAT C 09:08:21 : SPK NEW BUILD RELEASED, HUNTING PROSES
89 COLO |  | JAW-BT-PDG-0614 | 30742140031 | 130203104 | TANJUNG_JAYA | BP2022 | SMI | 105°40.59.2'E | 6°31.25.1'S | 50 | 100/190/330 | 2022 | Newsite 2022 - B2 | Desa Tanjung Jaya Kp. Cikadu Indah RT.01 RW.01 Kec. Panimbang, Kab. Pandeglang Prov. Banten | EID | JAW-BT-PDG-0614 | TANJUNG_LESUNG_PANDEGLANG | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Pandeglang | 6618085 | 2022-03-11 | 2022-03-11 | 45 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-05-13 | W20-2022 | May-2022 | 2022-05-13 | W20-2022 | May-2022 | MW | 2022-04-10 |  | 562400513574 | 10.6 |  | 2022-04-13 |  |  | 2022-04-25 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22-20:04:22: SRFI 17:04:22-14:04:22: ME OG 13:04:22: STO 13 APR 10:04:22-07:04:22: PARALEL STR 06:04:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED
|  | JAW-BT-TGR-0110 | 30735200031 | 1317921023 | PEMATANG TIGARAKSA | BP2022 | TB | 106°27.15.01'E | 6°14.26.7'S | 45 | 90/210/330 | 2022 | New site 2022 - P1 | Desa Pematang Kp. Sikluk RT.02 RW.01 Kec. Tigaraksa, Kab. Tangerang Prov. Banten | EID | JAW-BT-TGR-0110 | PETE_TEGAL_SARI | COLO | TBG | JABO | JABODETABEK | Banten | Kab. Tangerang | 6618023 | 2022-02-04 | 2022-02-04 | 80 | 61 - 90 days | 2022-03-06 | W11-2022 | Mar-2022 | TBD | TBD | TBD | 2022-04-22 | W17-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-07 | 2022-03-14 | 566402075773 | 6.6 |  | 2022-03-08 |  |  | 2022-04-25 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22-20:04:22: ME (str done 19 apr) 17:04:22-03:04:22: PONDASI OG & PERKUATAN (PLAN START 7 APR) 30:03:22-09:03:22: PERKUATAN OG 06:03:22-16:02:22: READY TO STO 13:02:22-09:02:22: NEED REVIEW CIVIL EID 07:02:22-06:02:22: NEED REVIEW RNP EID 04:02:22: NEW SPK RELEASED | apr
|  | JAW-BT-TGR-0109 | 30735190031 | 1317961023 | SOLEAR BANTEN | BP2022 | TB | 106°25.58.19'E | 6°17.8.0'S | 45 | 90/210/330 | 2022 | New site 2022 - P2 | Desa Pasanggrahan Kp. Bojong RT.01 RW.06 Kec. Solear, Kab. Tangerang Prov. Banten | EID | JAW-BT-TGR-0109 | JEUNGJING_CISOKA | COLO | TBG | JABO | JABODETABEK | Banten | Kab. Tangerang | 6618023 | 2022-02-04 | 2022-02-04 | 80 | 61 - 90 days | 2022-03-06 | W11-2022 | Mar-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-07 | 2022-03-14 | 566402074692 | 6.6 |  | 2022-03-09 |  |  | 2022-04-25 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22: ME OG 20:04:22:STR DONE, PREPARE CME 17:04:22-14:04:22: FINISHING STRENGTENING 13:04:22-03:04:22: PONDASI OG & PERKUATAN (PLAN START 7 APR) 30:03:22-09:03:22: PERKUATAN OG 06:03:22-16:02:22: READY TO STO 13:02:22-09:02:22: NEED REVIEW CIVIL EID 07:02:22-06:02:22: NEED REVIEW RNP EID 04:02:22: NEW SPK RELEASED | apr
NEW SPK B2S |  | JAW-JI-BKL-4326 | 30730390031 | 1654781003 | BURNEH_SOBIH | BP2022 | TB | 112°48.9.97'E | 7°1.17.65'S | 50 | 60/160/270 | 2022 | New site 2022 - P2 | Dsn Sapen RT- RW – Desa Sobih Kec Burneh Kab Bangkalan | HTI | JAW-JI-BKL-4326 | BURNEH_SOBIH | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617949 | 2022-01-25 | 2022-01-28 | 90 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | MG |  |  | 2022-04-05 |  |  | 2022-04-25 |  |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 25:04:22: RFIN 24:04:22: RFI, WAIT RFIN 17:04:22: SRFI 13:04:22-10:04:22: ERECTION 06:04:22: CURRING 03:04:22-30:03:22: REBARRING 27:03:22: BOREPILE 23:03:22: REKOM, SOIL TEST DONE WATIT APD 20:03:22: REALISASI IW, SOIL TEST DONE WAIT APD 16:03:22-09:03:22: IW CLEAR 06:03:22: IW OG 06:03:22-03:03:22: VAALIDASI RNP TNP, IW FAILED 02:03:22-20:02:22: IW CLEAR 16:02:22: IW OG 13:02:22-03:02:22: VALIDASI RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
953 |  | SUL-ST-LWK-1103 | 30714660031 | 2604991003 | TOILI_SENTRAL_TIMUR | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 122°21.14.77'E | 1°28.15.57'S | 60 | 20/90/320 | 2021 | BLITZKRIEG 2021 [NEW] | DUSUN 1 RT002 DESA SENTRAL SARI, KEC TOILI, KAB BANGGAI | HTI | SUL-ST-LWK-1103 | TOILI_SENTRAL_TIMUR | B2S | TBG | EAST | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617749 | 2021-10-25 |  | 182 | > 150 days | 2022-03-24 | W13-2022 | Mar-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-21 | 2022-02-23 |  |  |  | 2022-03-01 |  |  | 2022-04-25 |  |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 25:04:22: RFIN 24:04:22-30:03:22: PLN 27:03:22-20:03:22: ERECTION 17:03:22: GO RFI, KEJAR DI MARET 16:03:22-13:03:22: CURRING 09:03:22: POURING 06:03:22-28:02:22: REBARRING 25:02:22: ANNOUNCEMENT GO UNTIL SRFI 23:02:22-20:02:22: EXCAVATION 16:02:22-02:02:22: DELIVERY MATERIAL & PARALEL ON CHECK PERIZINAN 30:01:22: RFL 26:01:22-19:01:22: APD DONE, RFC 16:01:22-09:01:22: REKOM DONE, REQ SOIL TEST DONE, APD DONE 05:01:22-26:12:21: IW CLEAR, REKOM OG 22:12:21-19:12:21: SITAC PREPARATION 16:12:21: PMO XL CONFIRMED GO SITAC 15:12:21-05:12:21: REVIEW TNP OK, NEED CONFIRMATION FROM XL TO CONTINUE SITAC PROCESS 01:12:21-10:11:21-08:11:21: RNP OK, OG VALIDASI TNP, HOLD HUWAWEI 07:11:21: CANDIDAT VERIFICATION OG 03:11:21-31:10:21: SURVEY OG, PLAN SUBMIT KANDIDAT W1 NOV | apr
NEW SPK |  | SUL-SN-PKJ-1595 | 30734380031 | 2815882010 | IBS IBS_BULUCINDEA | BP2022 | TB | 119°29.53.92'E | 4°48.45.54'S | 50 | 80/160/250 | 2022 | New site 2022 - P2 | Jl Biringkassi Dalam RT 08 Desa Bulucindea Kec Bungoro Kab Pangkep | HTI | SUL-SN-PKJ-1595 | BULU_TELLUE_TONDONG_TALLASA | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Pangkajene Kepulauan | 6617991 | 2022-01-28 | 2022-01-28 | 87 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 320400193178 |  |  | 2022-03-21 |  |  | 2022-04-25 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22-30:03:22: PLN & PERKUATAN 27:03:22-13:03:22: PARALEL STRENGTENING 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK B2S |  | JAW-BT-PDG-0622 | 30729250031 | 1322911003 | MAKUI_BANYUMEKAR | BP2022 | TB | 105°50.32.08'E | 6°22.3.67'S | 50 | 100/210/345 | 2022 | New site 2022 - P2 | Kp. Sepen RT002/001 Desa Banyumekar Kecamatan Labuan Kabupaten Pandeglang Provinsi Banten | EID | JAW-BT-PDG-0622 | MAKUI_BANYUMEKAR | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Pandeglang | 6617948 | 2022-01-25 | 2022-01-28 | 87 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-10 | W20-2022 | May-2022 | 2022-05-10 | W20-2022 | May-2022 | MW | 2022-03-07 | 2022-04-05 | 562400512324 | 6.6 |  | 2022-04-06 |  |  | 2022-04-22 |  |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:04:22: RFIN 20:04:22: RFI, WAIT RFIN 17:04:22-14:04:22: ME 10:04:22-30:03:22: REBARRING 27:03:22-20:03:22: EXCAVATION OG 16:03:22-13:03:22: LAND CLEARING 12:03:22-23:02:22: REKOM OG 20:02:22: IW OG 16:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
948 |  | SUL-ST-LWK-1073 | 30714620031 | 2604951003 | MOILONG XL | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 122°23.39.87'E | 1°26.23.68'S | 60 | 100/220/320 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun III, RT.001,Desa Sumber Harjo, Kecamatan Moilong, Kabupaten Banggai, Provinsi Sulawesi Tengah | HTI | SUL-ST-LWK-1073 | MOILONG | B2S | TBG | EAST | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617749 | 2021-10-25 |  | 182 | > 150 days | 2022-03-24 | W13-2022 | Mar-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-21 | 2022-02-23 | 319100339182 |  |  | 2022-03-01 |  |  | 2022-04-25 |  |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22-13:04:22: RFI, WAIT RFIN 10:04:22: PLN 06:04:22-30:03:22: ERECTION 27:03:22-20:03:22: CURING 16:03:22: POURING 13:03:22-28:02:22: REBARRING 23:02:22-20:02:22: EXCAVATION 16:02:22-02:02:22: DELIVERY MATERIAL & PARALEL ON CHECK PERIZINAN 30:01:22-23:01:22: APD & REKOM DONE 19:01:22-12:01:22: REKOM OG, PARALEL REQ SOIL TEST 09:01:22: IW CLEAR, PREPARE REKOM 05:01:22: BAN BAK OG 02:01:22: TNP OK, IW OG 29:12:21-26:12:21: RNP OK, UNDER TNP REVIEW 22:12:21: WAIT REVIEW RNP TNP 19:12:21: SITAC PREPARATION, NEED FU VALIDASI TNP RNP 16:12:21: PMO XL CONFIRMED GO SITAC, NEED FU VALIDASI TNP RNP 15:12:21-09:11:21: VALIDASI RNP OG, HOLD BY XL 07:11:21-31:10:21: SURVEY OG, PLAN SUBMIT KANDIDAT 10 NOV | apr
NEW SPK |  | SUM-RI-TBH-1089 | 30734520031 | 040082109 | SC_TH5093C (TEMBILAHAN KOTA) | BP2022 | SKP | 103°9.16.96'E | 0°19.44.54'S | 40 | 30/230/290 | 2022 | New site 2022 - P2 | Jl. Jendral Sudirman RT.06/RW.07, Kel. Tembilahan Kota, Kec. Tembilahan, Kab. Indragiri Hilir, Prov. Riau | HTI | SUM-RI-TBH-1089 | TEMBILAHAN_HULU | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Indragiri Hilir | 6617986 | 2022-01-28 | 2022-01-28 | 64 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-16 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-02 | W14-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 184409852561 | 6.6 |  | 2022-03-22 |  | 2022-03-16 | 2022-04-02 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02:04:22: RFIN 30:03:22-23:03:22: PLN CPNNECTION 20:03:22-16:03:22: SRFI, WAITING STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: READY TO DECLARE STO 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | JAW-JT-WNG-2766 | 30735800031 | 1443162010 | IBS JARANMATI BULUSARI | BP2022 | TB | 111°9.55.22'E | 7°50.4.52'S | 49 | 40/160/300 | 2022-2024 | New site 2022 - P1 | Desa Bulusari-Jaranmati RT.02 RW.09 Kec. Slogohimo, Kab.Wonogiri Prov. Jawa Tengah | NOKIA | JAW-JT-WNG-2766 | JARANMATI_BULUSARI | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Wonogiri | 6617993 | 2022-01-28 | 2022-01-28 | 68 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-07 | W15-2022 | Apr-2022 | 2022-04-07 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 |  | 11 |  | 2022-03-09 |  |  | 2022-04-06 | W15-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | LMS CHANGED TO NOKIA | 06:04:22: RFIN 23:03:22: PLN CONNECTION & STR NY PARALEL 20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB, PARALEL STRENGTENING 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
|  | JAW-BT-TGR-0099 | 30734620031 | 1321462010 | IBS KRAGILAN | BP2022 | TB | 106°27.49.27'E | 6°9.32.74'S | 60 | 50/220/300 | 2022 | New site 2022 - P1 | Jl. Raya Kresek, Desa Bunar Kp. Bunar RT.008 RW.001 Kec. Sukamulya, Kab. Tangerang Prov. Banten | EID | JAW-BT-TGR-0099 | KRAGILAN_TANGERANG | COLO | TBG | JABO | JABODETABEK | Banten | Kab. Tangerang | 6618018 | 2022-02-03 | 2022-02-04 | 58 | 31 - 60 days | 2022-03-05 | W10-2022 | Mar-2022 | TBD | TBD | TBD | 2022-04-07 | W15-2022 | Apr-2022 | 2022-04-07 | W15-2022 | Apr-2022 | MW | 2022-02-07 | 2022-03-17 | 566402027048 | 10.6 |  | 2022-02-09 |  |  | 2022-04-02 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02:04:22: RFIN 30:03:22-27:03:22: SRFI 23:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI BTS DONE 06:03:22-13:02:22: PONDASI BTS OG, HOLD XL 09:02:22: CME PREPARATION 08:02:22: NEED REVIEW TNP ALITA 06:02:22: NEED REVIEW RNP EID 04:02:22: NEW SPK RELEASED | apr
NEW SPK |  | JAW-BT-TGR-0119 | 30734000031 | 131404109 | CIKUYASOLEAR | BP2022 | SKP | 106°25.47.71'E | 6°19.29.53'S | 50 | 70/150/230 | 2022 | New site 2022 - P2 | Desa Cileles Kp. Gardu RT.01 RW.01 Kec. Tigaraksa, Kab. Tangerang Prov. Banten | EID | JAW-BT-TGR-0119 | RAYA_PINANG_CILELES | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Tangerang | 6617984 | 2022-01-28 | 2022-01-28 | 64 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-07 | W15-2022 | Apr-2022 | 2022-04-07 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-17 |  | 6.6 |  | 2022-02-08 |  |  | 2022-04-02 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02:04:22: RFIN 30:03:22-27:03:22: SRFI 23:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI BTS DONE 06:03:22-13:02:22: PONDASI BTS OG, HOLD XL 09:02:22: CME PREPARATION 07:02:22: NEED REVIEW POWER EID 06:02:22: NEED REVIEW TNP ALITA 02:02:22-30:01:22: ESR REVIEW, NEED REVIEW RNP EID 28:01:22: SPK RELEASED | apr
|  | SUM-SU-STB-2233 | 30734850031 | 22026109 | STUNGKIT -3 | BP2022 | TB | 98°21.57.96'E | 3°40.41.99'N | 40 | 20/210/300 | 2022 |  | Jl. Stungkit, Dusun III, Desa Stungkit, Kec. Wampu, Kab. Langkat, Prov. Sumatera Utara | HTI | SUM-SU-STB-2233 | WAMPU_STUNGKIT | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Langkat | 6618183 | 2022-04-06 | 2022-04-06 | -15 | < 30 days | 2022-05-06 | W19-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-10 | 2022-04-11 |  |  |  | 2022-04-12 |  |  | 2022-03-22 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | RFI DONE 22 MAR, STO 12 APR ON NEW SITE ID 10:04:22: ERM PROCESS 06:04:22: SPK RECEIVED
|  | SUM-SU-STB-2230 | 30734560031 | 22016109 | LADA HULU | BP2022 | TB | 98°25.41.16'E | 3°48.46.98'N | 50 | 30/160/240 | 2022 |  | Jl. Penggabungan, Dusun VI, Desa Baru Pasar 8, Kec. Hinai, Kab. Langkat, Prov. Sumatera Utara | HTI | SUM-SU-STB-2230 | BARU_PASAR_VIII | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Langkat | 6618183 | 2022-04-06 | 2022-04-06 | -7 | < 30 days | 2022-05-06 | W19-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-10 | 2022-04-11 | 122150561096 |  |  | 2022-04-12 |  |  | 2022-03-30 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | RFI DONE 30 MAR, STO 12 APR ON NEW SITE ID 10:04:22: ERM PROCESS 06:04:22: SPK RECEIVED
|  | SUM-SU-STB-2239 | 30734660031 | TBG05_NSM178 | KUALA MADU | BP2022 | BT | 98°30.11.88'E | 3°42.49.0'N | 50 | 0/130/230 | 2022 |  | Jl. Amarta Karang Rejo Langkat Sumatera Utara Sumatera Utara | HTI | SUM-SU-STB-2239 | STABAT_KARANG_REJO | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Langkat | 6618184 | 2022-04-06 | 2022-04-06 | -7 | < 30 days | 2022-05-06 | W19-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-10 | 2022-04-11 | 122140915415 |  |  | 2022-04-12 |  |  | 2022-03-30 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | RFI DONE 30 MAR, STO 12 APR ON NEW SITE ID 10:04:22: ERM PROCESS 06:04:22: SPK RECEIVED
736 |  | JAW-JI-SPG-4231 | 30701550031 | 160198104 | TEROSAN | RORO JONGRANG 2021 [NEW] | SKP | 113°6.58.36'E | 6°56.41.82'S | 50 | 0/150/245 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Terosan Ban-Ban kec.Banyuates kab.Sampang | HTI | JAW-JI-SPG-4231 | BANYUATES TEROSAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Sampang | 6617454 | 2021-08-09 |  | 77 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-26 | W44-2021 | Oct-2021 | 2021-10-26 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 517500847210 | 6.6 |  | 2021-10-04 |  | 2021-09-24 | 2021-10-25 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:10:21-15:09:21: SRFI 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
NEW SPK B2S |  | JAW-JI-BKL-4329 | 30730280031 | 1654751003 | BLEGA_BATES | BP2022 | TB | 113°5.16.24'E | 7°5.23.71'S | 50 | 85/230/350 | 2022 | New site 2022 - P2 | DSN.MANGKA AN RT.00 RW.00 DESA.BATES KECAMATAN BLEGA KABUPATEN BANGKALAN PROVENSI JAWA TIMUR | HTI | JAW-JI-BKL-4329 | BLEGA_BATES | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617949 | 2022-01-25 | 2022-01-28 | 70 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-15 | W16-2022 | Apr-2022 | 2022-04-15 | W16-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-01 | 517600665934 | 6.6 |  | 2022-04-08 |  |  | 2022-04-05 | W15-2022 |  |  | PRESITAC | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22: RFI, WAIT RFIN 30:03:22-27:03:22: SRFI 23:03:22-20:03:22: ERECTION 16:03:22: CURRING 13:03:22-09:03:22: REBARRING 06:03:22-23:02:22: REKOM OG 20:02:22: REALISASI IW 16:02:22: IW CLEAR 13:02:22-06:02:22: VALIDASI TNP OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
|  | JAW-JI-KRS-4363 | 30740010031 | 1655111003 | SUMBERASIH_MUNENG_KIDUL | BP2022 | TB | 113°10.17.87'E | 7°48.30.06'S | 40 | 85/250/340 | 2022 | Newsite 2022 - P1 | Dusun Timur ll Rt 19 Rw 04 Desa Muneng Kidul Kec. Sumberasih Kab. Probolinggo, Prov. Jawa Timur | HTI | JAW-JI-KRS-4363 | SUMBERASIH_MUNENG_KIDUL | B2S | TBG | East | JATIM | Jawa Timur | Kab. Probolinggo | 6618108 | 2022-03-07 | 2022-03-07 | 49 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | MG |  |  | 2022-04-12 |  |  | 2022-04-25 |  |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 25:04:22: RFIN 24:04:22: RFI, WAIT RFIN 10:04:22: SRFI 06:04:22: CURRING 03:04:22-30:03:22: REBARRING 27:03:22: EXCAVATION 23:03:22-20:03:22: REKOM DONE, SOIL TEST DONE, WAIT APD 16:03:22-11:03:22: VALIDASI RNP TNP -> IW OG 09:03:22: SURVEY OG 07:03:22: SPK RECEIVED | apr
NEW SPK |  | JAW-JT-PTI-1430 | 30735960031 | 141618109 | KEBEN TAMBAKROMO | BP2022 | SKP | 111°3.31.72'E | 6°53.9.17'S | 60 | 110/270/350 | 2022 | New site 2022 - P1 | Desa Keben Ds. Keben RT.004 RW.02 Kec. Tambakromo, Kab. Pati Prov. Jawa Tengah | NOKIA | JAW-JT-PTI-1430 | KEBEN_TAMBAKROMO | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Pati | 6617987 | 2022-01-28 | 2022-01-28 | 68 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | MG | 11 |  | 2022-03-09 |  |  | 2022-04-06 | W15-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | LMS CHANGED TO NOKIA | 06:04:22: RFIN 27:03:22: SRFI, PLN CONENCTION 23:03:22: ME 20:03:22: PONDASI OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUL-SN-SDR-1282 | 30734350031 | 2815462007 | IBS IBS_PHASE 4C_2262_SSL/MARITENGNGAE_SIDRAP | BP2022 | TB | 119°47.56.76'E | 3°56.20.15'S | 60 | 40/160/320 | 2022 | New site 2022 - P2 | Jl. Amparita - Soppeng, Kelurahan Rijang Pittu, Kecamatan Maritengngae, Kabupaten Sidenreng Rappang, Provinsi Sulawesi Selatan | HTI | SUL-SN-SDR-1282 | KELURAHAN_RIJANG_PITU_MARITENGNGAE | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Sidenreng Rappang | 6617991 | 2022-01-28 | 2022-01-28 | 87 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-08 | W11-2022 | Mar-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 325500312145 |  |  | 2022-03-21 |  | 2022-03-08 | 2022-04-25 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22-09:03:22: SRFI, PLN CONNECTION, PARALEL STRENGTENING 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | JAW-JB-KWG-1101 | 30735430031 | 125279126 | ANGGADITA KLARI | BP2022 | TB | 107°20.19.14'E | 6°20.41.39'S | 40 | 90/210/330 | 2022-2024 | New site 2022 - P1 | Desa Anggadita Dusun Sukamakmur RT.011 RW.004, Kec. Klari, Kab. Karawang Prov. Jawa Barat | EID | JAW-JB-KWG-1101 | ANGGADITA_KLARI | COLO | TBG | Jabodetabek | JABODETABEK | Jawa Barat | Kab. Karawang | 6617993 | 2022-01-28 | 2022-01-28 | 66 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-17 | 534686103244 | 10.6 |  | 2022-03-09 |  |  | 2022-04-04 | W15-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:04:22: RFIN 03:04:22: PLN CONNECTION 30:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22-13:02:22: NEED REVIEW POWER EID 09:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
|  | SUM-SU-TRT-2016 | 30738830031 | 0229271003 | LOBU_SIREGAR_II | BP2022 | TB | 98°59.43.8'E | 2°12.47.56'N | 50 | 90/170/280 | 2022 | New site 2022 - P2 | PARHASIORAN, DESA LOBU SIREGAR II Kecamatan Siborong borong Kabupaten Tapanuli Utara Prop Sumatera Utara | HTI | SUM-SU-TRT-2016 | LOBU_SIREGAR_II | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Tapanuli Utara | 6618062 | 2022-02-25 | 2022-02-25 | 33 | 31 - 60 days | 2022-07-25 | W31-2022 | Jul-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-03-11 | 2022-03-15 | MG | 6.6 |  | 2022-04-08 |  |  | 2022-03-30 | W14-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30:03:22: RFIN COMBAT 27:03:22: REKOM, COMBAT ERECTION DONE 23:03:22-20:03:22: PROSES DELIVERY COMBAT & PARALEL IW OG 16:03:22: IW CLEAR 13:03:22-10:03:22: IW OG 09:03:22-06:03:22: VALIDASI RNP TNP 28:02:22: SURVEY OG 25:02:22: SPK RELEASED
NEW SPK |  | JAW-JB-CKR-0104 | 30735500031 | 123234109 | BABELAN KOTA 2 | BP2022 | SKP | 107°2.16.4'E | 6°9.45.43'S | 42 | 0/90/180/270 | 2022 | New site 2022 - P1 | Desa Babelan Kota Kp. Pintu RT.001 RW.004, Kec. Babelan, Kab. Bekasi Prov. Jawa Barat | EID | JAW-JB-CKR-0104 | BABELAN_KOTA | COLO | TBG | Jabodetabek | JABODETABEK | Jawa Barat | Kab. Bekasi | 6617984 | 2022-01-28 | 2022-01-28 | 69 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-17 | 537321818352 | 10.6 |  | 2022-03-09 |  |  | 2022-04-07 | W15-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 07:04:22: RFIN 06:04:22-03:04:22: PLN CONNECTION 30:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22-13:02:22: NEED REVIEW POWER EID 09:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | BAL-BA-MGW-1569 | 30739120031 | 171348126 | CANGGU AVENUE | BP2022 | TB | 115°8.31.85'E | 8°38.32.75'S | 30 | 30/200/290 | 2022 | New site 2022 - P2 | Kab Badung - Bali | HTI | BAL-BA-MGW-1569 | CANGGU_KUTA_UTARA | COLO | TBG | East | BALINUSRA | Bali | Kab. Badung | 6617991 | 2022-01-28 | 2022-01-28 | 56 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-05 | W19-2022 | May-2022 | 2022-05-05 | W19-2022 | May-2022 | MW | 2022-02-02 | 2022-02-03 | 551104016938 |  |  | 2022-03-21 |  |  | 2022-03-25 |  |  |  |  | 38.RFI | 21.RFI | NEED STRENGTENING PARALEL | 25:04:22: RFIN 24:04:22: STR ON GOING NY PARALEL 20:04:22-09:03:22: PABRIKASI MATERIAL PERKUATAN 06:03:22: READY TO STO 23:02:22: RND NOK NEED 20M 20:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JT-JPA-0714 | 30735920031 | 1442792010 | IBS ZSMG_1578 | BP2022 | TB | 110°45.18.0'E | 6°39.3.71'S | 39 | 90/210/330 | 2022-2024 | New site 2022 - P1 | Desa Mindahan Kidul RT.3 RW.5 Kec.Batealit, Kab.Jepara Prov. Jawa Tengah | NOKIA | JAW-JT-JPA-0714 | MINDAHAN_KIDUL_JEPARA | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Jepara | 6617993 | 2022-01-28 | 2022-01-28 | 68 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 520022109564 | 11 |  | 2022-03-09 |  |  | 2022-04-06 | W15-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | LMS CHANGED TO NOKIA | 06:04:22: RFIN 03:04:22-27:03:22: SRFI, PLN CONENCTION 23:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
|  | SUM-SU-TRT-2014 | 30738820031 | 0229261003 | SITABOTABO | BP2022 | TB | 98°57.57.96'E | 2°11.30.77'N | 50 | 30/170/260 | 2022 | New site 2022 - P2 | Jalan Lintas Sumatera Dusun Sipiuan Desa Sitabotabo Kecamatan Siborongborong Kabupaten Tapanuli Utara Prov Sumatera Utara | HTI | SUM-SU-TRT-2014 | SITABOTABO | B2S | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Tapanuli Utara | 6618062 | 2022-02-25 | 2022-02-25 | 35 | 31 - 60 days | 2022-07-25 | W31-2022 | Jul-2022 | TBD | TBD | TBD | 2022-04-10 | W16-2022 | Apr-2022 | 2022-04-10 | W16-2022 | Apr-2022 | MW | 2022-03-11 | 2022-03-15 |  | 6.6 |  | 2022-04-07 |  |  | 2022-04-01 | W14-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01:04:22: RFIN COMBAT 30:03:22-20:03:22: PROSES DELIVERY COMBAT & PARALEL IW OG 16:03:22: IW CLEAR 13:03:22-10:03:22: IW OG 09:03:22-06:03:22: VALIDASI RNP TNP 28:02:22: SURVEY OG 25:02:22: SPK RELEASED | apr
|  | JAW-JB-DPK-0496 | 30730850031 | T000916 | HJ SYUKUR LENTENG AGUNG | RELOCATION | SKP | 106°50.21.95'E | 6°20.40.2'S | 35 | 10/90/180 | 2022 | RELOCATION - XL | Kel. Srengseng Sawah Gg. Gardu RT.12 RW.02 Kec. Jagakarsa, Kota Jakarta Selatan Prov. DKI Jakarta | EID | JAW-JB-DPK-0496 | KELAPA DUA RELOCATION | COLO | TBG | JABO | JABODETABEK | Kota Depok | Jawa Barat | 6617928 | 2022-01-19 |  | 55 | 31 - 60 days | 2022-02-18 | W08-2022 | Feb-2022 | TBD | TBD | TBD | 2022-03-17 | W12-2022 | Mar-2022 | 2022-03-17 | W12-2022 | Mar-2022 | MW | 2022-01-30 |  | 547401893080 | 6.6 |  | 2022-04-04 |  | 2022-02-16 | 2022-03-15 | W12-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:03:22: RFIN 13:03:22: RFI, WAIT RFIN 09:03:22: CONTINUE TO RFI 06:03:22-23:02:22: SRFI 16 FEB, PMO MEMINTA UNTUK DI HOLD HINGGA SRFI DULU 20:02:22-16:02:22: ME OG, PMO MEMINTA UNTUK DI HOLD HINGGA SRFI DULU 13:02:22-09:02:22: PONDASI OG 06:02:22: READY TO DECLARE STO 02:02:22-23:01:22: NEED REVIEW TNP ALITA 19:01:22: SPK RELEASED FROM LMS TO EMAIL TBG
NEW SPK B2S |  | JAW-JI-PNG-4307 | 30730560031 | 1654841003 | SUKOREJO_SIDOREJO | BP2022 | TB | 111°24.21.6'E | 7°48.58.79'S | 70 | 90/190/290 | 2022 | New site 2022 - P2 | Jl. Waringin, Buayanan Desa Sidorejo Kecamatan Sukorejo Kab. Ponorogo | HTI | JAW-JI-PNG-4307 | SUKOREJO_SIDOREJO | B2S | TBG | East | JATIM | Jawa Timur | Kab. Ponorogo | 6617949 | 2022-01-25 | 2022-01-28 | 71 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-15 | W16-2022 | Apr-2022 | 2022-04-15 | W16-2022 | Apr-2022 | MW | 2022-03-02 | 2022-03-18 | 515402573105 | 6.6 |  | 2022-04-04 |  |  | 2022-04-06 | W15-2022 |  |  | PRESITAC | 38.RFI | 21.RFI | 38.RFI | 06:04:22: RFIN 03:04:22: RFI, WAIT RFIN 30:03:22: POWER CONNECTION 27:03:22: SRFI 23:03:22: CURRING TIME 20:03:22: POURING 16:03:22: REBARRING 13:03:22: EXCAVATION 09:03:22: REKOM 06:03:22-28:02:22: IW CLEAR 23:02:22-20:02:22: IW OG 16:02:22-13:02:22: VALIDASI RNP TNP, IWFAILED CANDIATE A&B 09:02:22-03:02:22: VALIDASI RNP TNP, PRIORITY CANDIDATE B 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
691 |  | SUM-RI-PKK-1150 | 30700310031 | 040164109 | ESTATE 2 MUSIM MAS | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 102° 1' 42.74" E | 0° 4' 40.66" N | 60 | 60/150/250 | 2021 | BLITZKRIEG 2021 [NEW] | Perkebunan Sawit PT. Musim Mas, Desa Batang Kulim, Kec. Pangkalan Kuras, Kab. Pelalawan, Prov. Riau | HTI | SUM-RI-PKK-1150 | PANGKALAN_KURAS_TANJUNGBERINGIN | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Pelalawan | 6617506 | 2021-08-16 |  | 246 | > 150 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2022-01-26 | W05-2022 | Jan-2022 | 2022-04-15 | W16-2022 | Apr-2022 | MW | 2021-08-28 |  |  |  |  | 2021-08-25 |  | 2021-09-28 | 2022-04-19 | W17-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:04:22: RFIN 17:04:22-30:03:22: RFI, WAIT RFIN 30:03:22-23:03:22: PLN CONNECTION 20:03:22-16:03:22: PROCESS PENGRIMAN MATERIAL PLN DARI JAKARTA, PLAN ARRIVED W3 MAR 13:03:22-06:02:22: PROCESS COLLECT DOC PKS 02:02:22-19:01:22: NEED CONFIRM XL SETUJU DENGAN COST PLN AGAR BISA LANJUT PKS DENGAN BM 16:01:22-20:12:21: ON PROCESS CONFIRM PLN CORPORATE DENGAN XL 19:12:21-05:12:21: WAITING CONFIRM PLN CORPORATE HARGA PER KWH, PLAN 19 DEC RELEASED DARI CORPORATE 01:12:21 - 23:10:21: WAITING CONFIRM PLN CORPORATE (PABRIK SAWIT PT. MUSIM MAS), NY CONFIRMED BY CORPORATE UNTUK SURAT KERJASAMANYA 20:10:21-08:09:21: SRFI, PLN BY CORPORATE PROSES PEMBUATAN SURAT KERJASAMA ANTARA CORPORATE DENGAN PENGAJUAN PKS PLN 01:09:21:30:08:21: CME PREPARATION 30:08:21:25:08:21:STO DECLARE 25 AUG 22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21 : SPK COLO RELEASED, ERM PROSESS | apr
NEW SPK B2S |  | JAW-BT-TGR-0108 | 30729470031 | 1323021003 | ABAS_KEMIRI | BP2022 | TB | 106°28.0.66'E | 6°6.44.88'S | 50 | 100/260/350 | 2022 | New site 2022 - P1 | Kp. Santri RT014 RW004 Desa Kemiri Kecamatan Kemiri Kab. Tangerang Prov. Banten | EID | JAW-BT-TGR-0108 | ABAS_KEMIRI | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Tangerang | 6617948 | 2022-01-25 | 2022-01-28 | 78 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-15 | W16-2022 | Apr-2022 | 2022-04-15 | W16-2022 | Apr-2022 | MW | 2022-03-07 | 2022-04-05 | 566602157918 | 6.6 |  | 2022-04-13 |  |  | 2022-04-13 | W16-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:04:22: RFIN 10:04:22-30:03:22: ERECTION 27:03:22: CURRING TIME 23:03:22-20:03:22: REBARRING 16:03:22-13:03:22: EXCAVATION 09:03:22-28:02:22: REKOM OG 23:02:22: IW CLEAR & PARALEL COLLECT DOKUMEN 20:02:22-13:02:22: IW OG 09:02:22-04:02:22: PRIORITY CANDIDATE B 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
NEW SPK B2S |  | JAW-JI-BKL-4324 | 30730630031 | 1654871003 | BLEGA_KAMPAO | BP2022 | TB | 113°1.32.23'E | 7°9.3.13'S | 50 | 90/190/340 | 2022 | New site 2022 - P2 | DSN.DAJAH LORONG RT.- RW.- DESA.KAMPAO KECAMATAN BLEGA KABUPATEN BANGKALAN PROVENSI JAWA TIMUR | HTI | JAW-JI-BKL-4324 | BLEGA_KAMPAO | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617949 | 2022-01-25 | 2022-01-28 | 76 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-01 | 517600665900 | 6.6 |  | 2022-03-21 |  |  | 2022-04-11 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11:04:22: RFIN 10:04:22-03:04:22: RFI, WAIT RFIN 30:03:2022: SRFI 27:03:22-24:03:22: ERECTION 20:03:22: CURRING TIME 16:03:22: REBARRING 13:03:22: LANTAI KERJA OG 09:03:22: BOUWPLANK OG 06:03:22-23:02:22: REKOM OG 20:02:22: REALISASI IW 16:02:22: IW CLEAR 13:02:22-03:02:22: VALIDASI RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
NEW SPK |  | JAW-YO-SMN-0076 | 30735910031 | 1509422007 | IBS PRAMBANAN | BP2022 | TB | 110°28.55.16'E | 7°45.30.38'S | 50 | 30/150/270 | 2022-2024 | New site 2022 - P1 | Kel.Tamanmartani Dukuh Kepatihan Kec.Kalasan, Kab.Sleman Prov. DI Yogyakarta | NOKIA | JAW-YO-SMN-0076 | PRAMBANAN_SLEMAN | COLO | TBG | Central | JATENG | DI Yogyakarta | Kab. Sleman | 6617993 | 2022-01-28 | 2022-01-28 | 76 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-20 | W17-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 521013005670 | 11 |  | 2022-03-09 |  |  | 2022-04-14 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 14:04:22: RFIN LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI, PLN CONENCTION 23:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
|  | SUM-SS-KAG-1250 | 30735120031 | 0717762001 | IBS TUGU MULYO | BP2022 | TB | 104°57.21.6'E | 3°48.3.2'S | 60 | 105/175/290 | 2022 | New site 2022 - P2 | Dusun I RT. 002, Desa Muktisari, Kecamatan Lempuing Jaya, Kabupaten Ogan Komering Ilir, Provinsi Sumatera Selatan | HTI | SUM-SS-KAG-1250 | MUKTISARI | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ilir | 6618017 | 2022-02-03 | 2022-02-04 | 77 | 61 - 90 days | 2022-03-05 | W10-2022 | Mar-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-07 | 2022-02-08 | 149300221239 |  |  | 2022-03-22 |  |  | 2022-04-21 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21:04:22: RFIN 20:04:22-03:04:22: PLN, CAN BE ACCELERATE TO APR 03:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW RNP HUAWEI 04:02:22: NEW SPK RELEASED | apr
NEW SPK |  | JAW-JT-BYL-0261 | 30735940031 | 140599104 | MANGGUNG | BP2022 | SMI | 110°46.43.93'E | 7°29.22.88'S | 28 | 90/230/340 | 2022 | New site 2022 - p1 | Desa Manggung, Ds Manggun RT 3/1 Kec. Ngemplak, Kab. Boyolali Prov. Jawa Tengah | NOKIA | JAW-JT-BYL-0261 | MANGGUNG_BOYOLALI | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Boyolali | 6617989 | 2022-01-28 | 2022-01-28 | 73 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-07 | W15-2022 | Apr-2022 | 2022-04-20 | W17-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 520551342430 | 11 |  | 2022-03-09 |  |  | 2022-04-11 | W16-2022 |  |  |  | 38.RFI | 21.RFI | LMS CHANGED TO NOKIA | 11:04:22: RFIN 10:04:22-23:03:22: PLN CONNECTION 20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-20:02:22: NEED REVIEW CIVIL 16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK B2S |  | SUM-LA-TWG-1029 | 30730670031 | 1014601003 | PAGAR_DEWA_SUKA_MULYA | BP2022 | TB | 105°11.32.01'E | 4°20.20.92'S | 60 | 20/90/265 | 2022 | New site 2022 - P2 | PAGAR DEWA SUKA MULYA RT.002 RW.001 DESA PAGAR DEWA SUKA MULYA KECAMATAN PAGAR DEWA KABUPATEN TULANG BAWANG BARAT PROVINSI LAMPUNG | HTI | SUM-LA-TWG-1029 | PAGAR_DEWA_SUKA_MULYA | B2S | TBG | West | SUMBAGSEL | Lampung | Kab. Tulang Bawang Barat | 6617950 | 2022-01-25 | 2022-01-28 | 84 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-20 | W17-2022 | Apr-2022 | 2022-04-20 | W17-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-02 | 173400203925 |  |  | 2022-04-25 |  |  | 2022-04-19 | W17-2022 |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 19:04:22: RFIN 17:04:22-30:03:22: ERECTION 27:03:22: REBARRING 23:03:22: DESIGN OG 20:03:22-06:03:22: REKOM 28:02:22-16:02:22: IW CLEAR 13:02:22-09:02:22: IW OG 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
954 |  | SUL-ST-LWK-1102 | 30714670031 | 2605001003 | KINTOM_MANYULA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 122°38.6.67'E | 1°10.22.12'S | 60 | 0/60/180 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun satu, Desa Manyula, Kecamatan Kintom, Kabupaten Banggai, Provinsi Sulawesi Tengah | HTI | SUL-ST-LWK-1102 | KINTOM_MANYULA | B2S | TBG | EAST | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617749 | 2021-10-25 |  | 171 | > 150 days | 2022-03-24 | W13-2022 | Mar-2022 | TBD | TBD | TBD | 2022-04-20 | W17-2022 | Apr-2022 | 2022-04-20 | W17-2022 | Apr-2022 | MW | 2022-02-21 | 2022-02-23 | 319500346268 | 6.6 |  |  |  |  | 2022-04-14 | W16-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14:04:22: RFIN 13:04:22: RFI, WAIT RFIN 10:04:22: PLN 06:04:22-30:03:22: ERECTION 27:03:22-20:03:22: CURING OG 17:03:22: GO RFI, KEJAR DI MARET 16:03:22-13:03:22: REBARING 09:03:22-28:02:22: EXCAVATION 25:02:22: ANNOUNCEMENT GO UNTIL SRFI 23:02:22: EXCAVATION 20:02:22-02:02:22: DELIVERY MATERIAL & PARALEL ON CHECK PERIZINAN 30:01:22-26:01:22: WAITING APD 23:01:22: REKOM DONE & PROSES SOIL TEST 19:01:22: IW OG KANDIDAT S 18:01:22: IW FAILED, VALIDASI TNP RNP KANDIDAT S 16:01:22-09:01:22: BAN BAK & IW OG (MINUS 4 KK) 06:01:22: TNP REVIEW OK, PREPARE IW OG 05:01:22-26:12:21-22:12:21: WAIT TNP REVIEW 19:12:21: SITAC PREPARATION, NEED FU VALIDASI TNP RNP 16:12:21: PMO XL CONFIRMED GO SITAC, NEED FU VALIDASI TNP RNP 15:12:21-10:11:21: TNP REVIEW OG, HOLD HUWAWEI 07:11:21: CANDIDAT VERIFICATION OG 03:11:21-31:10:21: SURVEY OG, PLAN SUBMIT KANDIDAT W1 NOV | apr
NEW SPK |  | JAW-JT-SMG-0626 | 30735890031 | 141888109 | GONDANG TEMBALANG | BP2022 | TB | 110°26.33.36'E | 7°4.3.18'S | 30 | 20/140/250 | 2022 | New site 2022 - P2 | Kel. Kramas RT.02 RW.03 Kec. Tembalang, Kota Semarang Prov. Jawa Tengah | NOKIA | JAW-JT-SMG-0626 | GONDANG_TEMBALANG | COLO | TBG | Central | JATENG | Jawa Tengah | Kota Semarang | 6617993 | 2022-01-28 | 2022-01-28 | 67 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-22 | W17-2022 | Apr-2022 | 2022-04-22 | W17-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 523041113381 | 11 |  | 2022-03-08 |  |  | 2022-04-05 | W15-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | LMS CHANGED TO NOKIA | 05:04:22: RFIN 03:04:22-27:03:22: SRFI 23:03:22-20:03:22: ME OG 16:03:22-09:03:22: PONDASI OG & PERKUATAN 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | JAW-JT-CLP-0563 | 30735900031 | 1440862003 | IBS TRITIH KULON | BP2022 | TB | 109°1.47.1'E | 7°40.59.95'S | 30 | 30/150/270 | 2022 | New site 2022 - P2 | Jl. Jati, RT 006/ 009, Desa Tritih Kulon, Kec. Cilacap Utara, Kab. Cilacap | NOKIA | JAW-JT-CLP-0563 | JALAN_JATI_CILACAP | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Cilacap | 6617993 | 2022-01-28 | 2022-01-28 | 70 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-22 | W17-2022 | Apr-2022 | 2022-04-22 | W17-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 525011421993 | 11 |  | 2022-03-08 |  |  | 2022-04-08 | W15-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | LMS CHANGED TO NOKIA | 08:04:22: RFIN 06:04:22-27:03:22: SRFI & STR NY PARALEL 23:03:22-20:03:22: ME OG 16:03:22-09:03:22: PONDASI OG & PERKUATAN 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | JAW-YO-BTL-0140 | 30735930031 | 150092104 | TRIMULYO | BP2022 | SMI | 110°23.5.24'E | 7°53.40.92'S | 50 | 60/190/300 | 2022 | New site 2022 - p1 | Kel.Trimulyo Dsn.Bendogorok Rt.3 Kec.Jetis, Kab.Bantul Prov. DI Yogyakarta | NOKIA | JAW-YO-BTL-0140 | TRIMULYO_BANTUL | COLO | TBG | Central | JATENG | DI Yogyakarta | Kab. Bantul | 6617989 | 2022-01-28 | 2022-01-28 | 70 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-23 | W17-2022 | Apr-2022 | 2022-04-23 | W17-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 521032604426 | 11 |  | 2022-03-09 |  |  | 2022-04-08 | W15-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | LMS CHANGED TO NOKIA | 08:04:22: RFIN 06:04:22-27:03:22: SRFI & STR NY PARALEL 23:03:22-20:03:22: ME OG 16:03:22-09:03:22: PONDASI OG & PERKUATAN 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
|  | SUM-SU-STB-2232 | 30734530031 | 22236109 | API_SELOTONG SECANGGANG | BP2022 | TB | 98°33.33.12'E | 3°52.9.98'N | 50 | 100/210/300 | 2022 |  | Jl. Besat Selotong / Jl. Tambak, Dusun I, Desa Selotong, Kec. Secanggang, Kab. Langkat, Prov. Sumatera Utara | HTI | SUM-SU-STB-2232 | SELOTONG | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Langkat | 6618183 | 2022-04-06 | 2022-04-06 | 6 | < 30 days | 2022-05-06 | W19-2022 | May-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-04-10 | 2022-04-11 |  |  |  | 2022-04-12 |  |  | 2022-04-12 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12:04:22: RFIN, STO 12 APR 10:04:22: ERM PROCESS 06:04:22: SPK RECEIVED | apr
89 COLO |  | SUM-SU-PYB-2172 | 30741380031 | 20298104 | V_BATANG_NATAL | BP2022 | SMI | 99°22.8.47'E | 0°41.23.1'N | 60 | 0/130/260 | 2022 | Newsite 2022 - B2 | Jl. Lintas Pantai Barat, Kel. Muara Soma, Kec. Batang Natal, Kab. Mandailing Natal, Prov. Sumatera Utara | HTI | SUM-SU-PYB-2172 | KELURAHAN_MUARA_SOMA | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Mandailing Natal | 6618086 | 2022-03-11 | 2022-03-11 | 34 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 124150469123 | 6.6 |  | 2022-03-22 |  |  | 2022-04-14 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14:04:22: RFIN 17:04:22-10:04:22: PLN 06:04:22: ME OG 03:04:22: PLN OG 30:03:22: PONDASI OG 27:03:22-23:03:22: CME PREPARATION 20:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
|  | KAL-KB-SKW-0773 | 30715470031 | 2008251003 | SINGKAWANG_UTARA_NARAM | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 108°59.46.21'E | 0°56.28.97'N | 45 | 20/110/200 | 2021 | BLITZKRIEG 2021 [NEW] | Jalan Semai, Gang Harmoni, Kelurahan Naram, Kecamatan Singkawang Utara, Kota Singkawang, Propinsi Kalimantan Barat | HTI | KAL-KB-SKW-0773 | SINGKAWANG_UTARA_NARAM | COLO | TBG | JABO | KALIMANTAN | Kalimantan Barat | Kota Singkawang | 6617778 | 2021-11-09 |  | 164 | > 150 days | 2021-12-09 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2022-02-25 | W09-2022 | Feb-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2021-12-16 |  | MG |  |  | 2021-11-29 |  |  | 2022-04-22 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:04:22: RFIN 20:04:22-17:04:22: ME 14:04:22-10:04:22: FINISHING ERECTION 06:04:22-03:04:22: ERECTION BUT STOPPED BY LL (COMMCASE) 27:03:22-23:03:22: CURRING TIME 20:03:22: POURING 17:03:22-13:03:22: REBAARRING,PLAN POURING 19 MAR 09:03:22: EXCAVATION PERAPIHAN GALIAN LONGSOR 06:03:22: EXCAVATION 28:02:22-24:02:22: RE-MOBILISASI TEAM CME & START CME 1 MAR 20:02:22-13:02:22: PROSES SCHEDULED KOMINFO 09:02:21-30:01:22: DESIGNPACK OG & PARALEL PERIZINAN 26:01:22-23:01:22: REKOM OG 19:01:22: CME HOLD PARALEL REKOM OG, PLAN RFI FEB 16:01:22: PROSES REALISASI KOMPENSASI WARGA 12:01:22-15:12:21: HOLD COMCASE KOMPENSASI WARGA, PROSES NEGO 08:12:21-01:12:21: CME PREPARATION 28:11:21: APD RELEASED, PLAN KOM CME 29 NOV 24:11:21-21:11:21: BAK PROCESS 17:11:21: SURVEY OG 14:11:21-10:11:21: ESR PROCESS OG | apr
|  | JAW-JB-SOR-4420 | 30739910031 | 1276951003 | NEGLAS_SARI_PINGGIRSARI | BP2022 | TB | 107°39.45.44'E | 7°3.57.09'S | 50 | 110/230/300 | 2022 | Newsite 2022 - B2 | Kp. Mekarsari RT.003 RW.019 Desa Pinggirsari Kecamatan Arjasari Kabupaten Bandung Provinsi Jawa Barat | HTI | JAW-JB-SOR-4420 | NEGLAS_SARI_PINGGIRSARI | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Bandung | 6618108 | 2022-03-07 | 2022-03-07 | 50 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-04-10 | 2022-04-11 | 535342252845 |  |  | 2022-04-21 |  |  | 2022-04-26 |  |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:04:22-20:04:22: ERECTION 17:04:22: REBARRING 14:04:22-10:04:22: BOUWPLANK 06:04:22: REKOM 03:04:22-25:03:22: VALIDASI RNP TNP 23:03:22-15:03:22: IW OG 13:03:22: VALIDASI RNP TNP 12:03:22-09:03:22: SURVEY OG 07:03:22: SPK RECEIVED
89 COLO |  | SUM-LA-BBU-0878 | 30741790031 | 100178104 | BALIREJO | BP2022 | SMI | 104°29.24.0'E | 4°39.30.49'S | 60 | 0/205 | 2022 | Newsite 2022 - B2 | Desa Balirejo Kec. Banjit Kab. Way Kanan | HTI | SUM-LA-BBU-0878 | BLAMBANGAN_UMPU_GISTANG | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Way Kanan | 6618086 | 2022-03-11 | 2022-03-11 | 42 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-03-24 | 2022-03-25 | 173700729262 |  |  | 2022-03-23 |  |  | 2022-04-22 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:04:22: RFIN 20:04:22-17:04:22: PLN 13:04:22-10:04:22: SRFI 06:04:22-03:04:22: PONDASI OG 30:03:22-23:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED
NEW SPK B2S |  | SUL-SN-SDR-1284 | 30730270031 | 2817591003 | KELURAHAN_BILOKKA_PANCA_LAUTAN | BP2022 | TB | 119°49.52.49'E | 4°4.0.85'S | 60 | 0/160/260 | 2022 | New site 2022 - P2 | Lingkungan Maroangin, RT003/RW002, Kelurahan Billokka, Kecamatan Panca Lautang, Kabupaten Sidenreng Rappang, Propinsi Sulawesi Selatan | HTI | SUL-SN-SDR-1284 | KELURAHAN_BILOKKA_PANCA_LAUTAN | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Sidenreng Rappang | 6617949 | 2022-01-25 | 2022-01-28 | 90 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-02 | 325500312812 |  |  | 2022-03-28 |  |  | 2022-04-25 |  |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22: RFI, WAIT RFIN 20:04:22-10:04:22: ERECTION 06:04:22-03:04:22: CURRING 30:03:22-20:03:22: REBARRING 16:03:22-06:03:22: WAIT APD, SOIL TEST DONE 28:02:22-23:02:22: REKOM DONE 20:02:22-16:02:22: REKOM OG 13:02:22-09:02:22: IW OG 07:02:22: RNP TNP REVIEW OK, IW OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
NEW SPK B2S |  | SUL-SN-SDR-1283 | 30730260031 | 2817581003 | WANIO_TIMORENG_PANCA_LAUTAN | BP2022 | TB | 119°52.10.82'E | 4°3.55.14'S | 60 | 0/90/250 | 2022 | New site 2022 - P2 | Dusun Labempa, RT002/RW002, Desa Wanio Timoreng, Kecamatan Panca Lautang, Kabupaten Sidenreng Rappang, Propinsi Sulawesi Selatan | HTI | SUL-SN-SDR-1283 | WANIO_TIMORENG_PANCA_LAUTAN | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Sidenreng Rappang | 6617949 | 2022-01-25 | 2022-01-28 | 90 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-02 | 325500312463 |  |  | 2022-03-28 |  |  | 2022-04-25 |  |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22: RFI WAIT RFIN 20:04:22-10:04:22: ERECTION 06:04:22-03:04:22: CURRING 30:03:22-20:03:22: REBARRING 16:03:22-06:03:22: WAIT APD, SOIL TEST DONE 28:02:22-23:02:22: REKOM DONE 20:02:22-16:02:22: REKOM OG 13:02:22-09:02:22: IW OG 07:02:22: RNP TNP OG, IW OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
89 COLO |  | JAW-JB-CJR-4330 | 30741350031 | 125415126 | CIBADAK-CIBEBER | BP2022 | TB | 107°9.3.6'E | 6°56.34.76'S | 40 | 20/120/290 | 2022 | Newsite 2022 - B2 | Desa Cimanggu Kp. Cogreg RT.001 RW.007, Kec. Cibeber, Kab. Cianjur Prov. Jawa Barat | HTI | JAW-JB-CJR-4330 | CIBEBER_CIBADAK | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Cianjur | 6618079 | 2022-03-11 | 2022-03-11 | 20 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 536612821953 |  |  | 2022-03-22 |  | 2022-03-29 | 2022-03-31 | W14-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:03:22: RFIN 30:03:22-29:03:22: SRFIN 27:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED
89 COLO |  | SUM-LA-BBU-0869 | 30741730031 | 100029109 | BUAY BAHUGA-1 | BP2022 | SKP | 104°38.54.64'E | 4°15.8.21'S | 50 | 0/215/320 | 2022 | Newsite 2022 - B2 | Kampung Sapto Reggo, Kec.Bahuga, Kab.Way Kanan Prop.Lampung | HTI | SUM-LA-BBU-0869 | SAPTO_RENGGO | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Way Kanan | 6618082 | 2022-03-11 | 2022-03-11 | 46 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-05-08 | W20-2022 | May-2022 | 2022-05-08 | W20-2022 | May-2022 | MW | 2022-03-24 | 2022-03-25 | 173700729213 |  |  | 2022-03-24 |  |  | 2022-04-26 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26:04:22: RFIN 24:04:22-17:04:22: PLN 13:04:22: ME OG 10:04:22-03:04:22: PONDASI OG 30:03:22-27:03:22: PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED
|  | SUM-SU-SRH-2249 | 30736210031 | 0228611001 | PABATU III | BP2022 | TB | 99°1.10.24'E | 3°19.5.81'N | 50 | 0/90/260 | 2022 | New site 2022 - P2 | Dusun II, Desa Kerapuh, Kecamatan Dolok Masihul, Kabupaten Serdang Bedagai, Provinsi Sumatera Utara | HTI | SUM-SU-SRH-2249 | KERAPUH | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Serdang Bedagai | 6618017 | 2022-02-03 | 2022-02-04 | 61 | 61 - 90 days | 2022-03-05 | W10-2022 | Mar-2022 | 2022-04-10 | W16-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-07 | 2022-02-08 | 126180006928 | 6.6 |  | 2022-03-22 |  |  | 2022-04-05 | W15-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL 13:02:22-06:02:22: NEED REVIEW RNP HUAWEI 04:02:22: NEW SPK RELEASED | apr
NEW SPK |  | SUM-SU-SRH-2239 | 30734740031 | 022029109 | SEI BAMBAN | BP2022 | TB | 99°7.59.16'E | 3°24.15.01'N | 50 | 40/140/220 | 2022 | New site 2022 - P2 | Dusun X Kelapa Tinggi, Desa Sei Belutu, Kec. Sei Bamban, Kab. Serdang Bedagai, Prov. Sumatera Utara | HTI | SUM-SU-SRH-2239 | SEI_BELUTU | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Serdang Bedagai | 6617992 | 2022-01-28 | 2022-01-28 | 67 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-04-10 | W16-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 126160731940 | 6.6 |  | 2022-03-22 |  |  | 2022-04-05 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22-07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-LA-KTB-1142 | 30735480031 | 101031109 | SEMULI JAYA 2 | BP2022 | TB | 104°59.59.6'E | 4°46.27.77'S | 50 | 0/90/180 | 2022 | New site 2022 - P2 | Dusun V Semuli Jaya RT.001 Desa Semuli Jaya, Kec. Abung Semuli, Kab. Lampung Utara, Prov. Lampung | HTI | SUM-LA-KTB-1142 | SEMULI_JAYA | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Utara | 6617991 | 2022-01-28 | 2022-01-28 | 62 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-02 | 2022-02-03 | 173001525920 |  |  | 2022-03-22 |  | 2022-03-28 | 2022-03-31 | W14-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:03:22: RFIN 30:03:22-28:03:22: SRFIN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22-06:02:22: RND NOK NEED 50 METER 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-LA-BBU-0865 | 30734130031 | 100563109 | SEMARANG | BP2022 | TB | 104°33.9.04'E | 4°42.56.52'S | 40 | 60/165/300 | 2022 | New site 2022 - P2 | Jl. Veteran No.196, Desa Bhakti Negara RT.1, Kel. Baradatu, Kab. Way Kanan Timur Prov. Lampung | HTI | SUM-LA-BBU-0865 | BHAKTI_NEGARA | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Way Kanan | 6617991 | 2022-01-28 | 2022-01-28 | 62 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 173700727609 |  |  | 2022-03-22 |  |  | 2022-03-31 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:03:22: RFIN 30:03:22-27:03:22: ME OG 23:03:22-13:03:22: STRENGTENING PARALEL CME 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-KR-TPG-0598 | 30734880031 | 0506091001 | PINANG KENCANA TBG | BP2022 | TB | 104°31.29.86'E | 0°55.59.41'N | 30 | 20/120/300 | 2022 | New site 2022 - P2 | Kampung Karangrejo RT 001 RW 008 Kelurahan Pinang Kencana, Kecamatan Tanjung Pinang Timur Kota Tanjung Pinang Provinsi Kepulauan Riau | HTI | SUM-KR-TPG-0598 | PINANG_KENCANA_GANET | COLO | TBG | West | SUMBAGTENG | Kepulauan Riau | Kota Tanjung Pinang | 6617991 | 2022-01-28 | 2022-01-28 | 62 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 183010544807 |  |  | 2022-03-22 |  |  | 2022-03-31 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:03:22: RFIN 30:03:22: PLN 27:03:22-16:03:22: ME OG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-SB-PNN-0804 | 30734570031 | 030798109 | API_SC_PNN168W | BP2022 | TB | 100°27.27.36'E | 1°15.41.47'S | 40 | 50/130/340 | 2022 | New site 2022 - P1 | Jl. Kambeh, Karang Tangah, Desa Pulau Karam, Kec. Koto XI Tarusam, Kab. Pesisir Selatan, Prov. Sumatera Barat | HTI | SUM-SB-PNN-0804 | PULAU_KARAM_AMPANG_PULAI | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Pesisir Selatan | 6617992 | 2022-01-28 | 2022-01-28 | 62 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 131074276788 |  |  | 2022-03-22 |  |  | 2022-03-31 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:03:22: RFIN 30:03:22: PLN 27:03:22: ME OG 23:03:22-13:03:22: PARALEL STRENGTENING 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-RI-PRP-1110 | 30734510031 | 040223104 | RAMBAH_SAMO | BP2022 | SMI | 100°21.9.65'E | 0°50.11.8'N | 50 | 60/120/300 | 2022 | New site 2022 - P2 | Lubuk Limau Kota Lama RT.01 RW.02 Darussalam, Kel. Kota Lama, Kec. Kunto, Kab. Rokan Hulu, Prov. Riau | HTI | SUM-RI-PRP-1110 | RAMBAH_SUKA_MAJU | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Rokan Hulu | 6617988 | 2022-01-28 | 2022-01-28 | 61 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-16 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 181140133073 |  |  | 2022-03-22 |  | 2022-03-16 | 2022-03-30 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30:03:22: RFIN 27:03:22-23:03:22: PLN CPNNECTION 20:03:22-16:03:22: SRFI, WAITING STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK B2S |  | JAW-JI-BKL-4322 | 30730430031 | 1654811003 | BLEGA_KARANG_GAYAM | BP2022 | TB | 113°4.59.92'E | 7°6.25.17'S | 50 | 100/170/290 | 2022 | New site 2022 - P2 | KMP. Pombulan RT.00 / RW. 00 Desa Karang Gayam Kecamatan Blega Kabupaten Bangkalan | HTI | JAW-JI-BKL-4322 | BLEGA_KARANG_GAYAM | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617949 | 2022-01-25 | 2022-01-28 | 70 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-01 | 517600665862 | 6.6 |  | 2022-03-21 |  |  | 2022-04-05 | W15-2022 |  |  | PRESITAC | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22: RFI, WAIT RFIN 30:03:22-23:03:22: SRFI 20:03:22: ERECTION 16:03:22: CURRING TIME 13:03:22: LANTAI KERJA OG 09:03:22: BOUWPLANK OG 06:03:22-23:02:22: REKOM OG 20:02:22: REALISASI IW 16:02:22: IW CLEAR 13:02:22-03:02:22: VALIDASI RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
NEW SPK |  | SUM-SS-MRE-1236 | 30735030031 | 070149109 | GELUMBANG 2 | BP2022 | SKP | 104°28.12.04'E | 3°13.20.93'S | 60 | 85/240/250 | 2022 | New site 2022 - P2 | Jl. Raya Palembang - Prabumulih Kel. Sukamenang , Kec. Gelumbang, Kota Prabumulih, Prov. Sumatera Selatan | HTI | SUM-SS-MRE-1236 | GELUMBANG_SUKA_MENANG | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Muara Enim | 6617983 | 2022-01-28 | 2022-01-28 | 59 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-01 | 2022-02-02 | 149000163699 | 6.6 |  | 2022-03-22 |  |  | 2022-03-28 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28:03:22: RFIN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22-07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
89 COLO |  | KAL-KT-PPS-0703 | 30740630031 | 210146104 | SIMPANG TIGA PERTAMINA | BP2022 | SMI | 114°16.33.6'E | 2°40.52.1'S | 65 | 75/160/355 | 2022 | Newsite 2022 - B2 | Jl. Bahaur Palangkaraya (Trans Kalimantan), Desa Gohong RT.01,Kec. Kahayan Hilir, Kab. Pulang Pisau Prov. Kalimantan Tengah | HTI | KAL-KT-PPS-0703 | GOHONG_KAHAYAN_HILIR | COLO | TBG | Central | KALIMANTAN | Kalimantan Tengah | Kab. Pulang Pisau | 6618086 | 2022-03-11 | 2022-03-11 | 34 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 225100195277 | 6.6 |  | 2022-03-21 |  | 2022-04-05 | 2022-04-14 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14:04:22: RFIN 05:04:22: SRFIN 03:04:22-20:03:22: PONDASI OG 16:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
NEW SPK |  | SUM-LA-KLA-1135 | 30734170031 | 100180104 | AIRPORT_LAMPUNG | BP2022 | SMI | 105°11.11.47'E | 5°16.3.54'S | 40 | 0/80/270 | 2022 | New site 2022 - P2 | Jl. Raya candi mas gg panahan komp bandara branti ds candi mas | HTI | SUM-LA-KLA-1135 | NATAR_CANDI_MAS | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Selatan | 6617988 | 2022-01-28 | 2022-01-28 | 58 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-02 | 2022-02-03 | 171101119651 | 6.6 |  | 2022-03-22 |  | 2022-03-27 | 2022-03-27 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:03:22: RFIN 27:03:22-23:03:22: SRFI 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
746 |  | JAW-JI-TLG-4243 | 30701020031 | 1651702004 | IBS TANJUNGUNUT | RORO JONGRANG 2021 [NEW] | TB | 111°58.30.5'E | 8°8.54.24'S | 50 | 5/75/280 | 2021 | RORO JONGRANG 2021 [NEW] | Dsn. Banjaran RT 01 RW 01 Desa Domasan, Kecamatan Kalidawir, Kabupaten Tulungagung | HTI | JAW-JI-TLG-4243 | KALIDAWIR DOMASAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Tulungagung | 6617471 | 2021-08-12 |  | 116 | 91 - 120 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-12-10 | W50-2021 | Dec-2021 | MW | 2021-09-04 |  | 514041725472 | 6.6 |  | 2021-10-04 |  | 2021-09-30 | 2021-12-06 | W50-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:12:21: RFIN 05:12:21: RFI, WAIT FOR RFIN 01:12:21-28:11:21: COMCASE, LL MEMINTA KOMPENSASI 50JT, OG PROCESS PENDEKATAN KE LL 24:11:21: EXTEND TOWER STOP KARENA COMCASE, 30 NOV ESCORT BY ARCOM AGAR DAPAT DILANJUT EXTEND NYA 21:11:21-27:10:21: OG CONNECT PLN, STOCK KWH NOT YET READY, PLAN RFI 30 NOV 24:10:21: SRFI PROSES CONNECT PLN, PEKERJAAN EXTEND TOWER DONE 20:10:21-29:09:21: SRFI, MINUS EXTEND TOWER 26:09:21-08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
NEW SPK |  | SUM-LA-KLA-1133 | 30734110031 | 100911109 | PURWODADI DALAM | BP2022 | TB | 105°25.13.08'E | 5°22.39.04'S | 60 | 55/235/280 | 2022 | New site 2022 - P2 | Dusun III, RT.006 RW.003, Desa Purwodadi dalam, Kec. Tanjung sari, Kab.Lampung, Propinsi Lampung | HTI | SUM-LA-KLA-1133 | PURWODADI_DALAM | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Selatan | 6617991 | 2022-01-28 | 2022-01-28 | 58 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-02 | 2022-02-03 | 171502546135 | 6.6 |  | 2022-03-22 |  | 2022-03-27 | 2022-03-27 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:03:22: RFIN 27:03:22: SRFIN 23:03:22: SRFI 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-LA-KLA-1147 | 30734890031 | 1013631001 | INSTITUT TEKNOLOGI SUMATERA | BP2022 | TB | 105°18.24.2'E | 5°21.37.13'S | 40 | 85/170/290 | 2022 | New site 2022 - P2 | Jl Terusan Ryacudu Desa Way Huwi Kecamatan Jati Agung Kabupaten Lampung Selatan Provinsi Lampung | HTI | SUM-LA-KLA-1147 | WAY_HUI | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Selatan | 6617991 | 2022-01-28 | 2022-01-28 | 58 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 171202975694 | 6.6 |  | 2022-03-22 |  |  | 2022-03-27 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:03:22: RFIN 23:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW POWER HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-LA-KLA-1145 | 30734870031 | 100089109 | DESA SABAH BALAU | BP2022 | TB | 105°20.18.56'E | 5°22.7.07'S | 60 | 15/100/270 | 2022 | New site 2022 - P2 | Jl. Perjuangan Dusun 3A RT.02/01, Desa Sabah Balau, Kec. Tanjung Bintang, Kab. Lampung Selatan, Lampung. | HTI | SUM-LA-KLA-1145 | TANJUNG_BINTANG_SABAH_BALAU | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Selatan | 6617991 | 2022-01-28 | 2022-01-28 | 58 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 171502546006 | 6.6 |  | 2022-03-22 |  |  | 2022-03-27 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:03:22: RFIN 23:03:22: SRFI 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-LA-KLA-1139 | 30734150031 | 100928109 | DESARUANG TENGAH | BP2022 | TB | 105°41.32.96'E | 5°46.17.33'S | 50 | 60/115/330 | 2022 | New site 2022 - P1 | Desa Gedong Harta RT.002 RW.001, Kec. Penengahan, Kab. Lampung Selatan Prov. Lampung | HTI | SUM-LA-KLA-1139 | GEDUNG_HARTA | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Selatan | 6617991 | 2022-01-28 | 2022-01-28 | 58 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 171300690223 |  |  | 2022-03-22 |  |  | 2022-03-27 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:03:22: RFIN 23:03:22: SRFI 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-RI-BLS-1141 | 30734590031 | 040521109 | DESA BATANG TENGAH | BP2022 | TB | 102°4.37.6'E | 1°29.54.82'N | 55 | 50/140/290 | 2022 | New site 2022 - P2 | Jl. Utama Gang Abdullah RT 05 RW 03 Desa Pangkalan Batang, Kec. Bengkalis, Kab. Bengkalis, Prov. Riau | HTI | SUM-RI-BLS-1141 | PANGKALAN_BATANG | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Bengkalis | 6617992 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 182302227330 | 6.6 |  | 2022-03-22 |  |  | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: SRFI 20:03:22-16:03:22-13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-RI-BKN-1169 | 30734550031 | 041089109 | BUKIT KEMUNING | BP2022 | TB | 100°54.18.0'E | 0°38.41.1'N | 40 | 40/120/320 | 2022 | New site 2022 - P2 | Jl. Poros RT 08 RW 03 Dusun 2, Desa Bukit Kemuning, Kec. Tapung Hulu, Kab. Kampar, Prov. Riau | HTI | SUM-RI-BKN-1169 | BUKIT_KEMUNING | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Kampar | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 181901210103 | 6.6 |  | 2022-03-22 |  |  | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: SRFI 20:03:22-16:03:22: ME OG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-RI-PBR-1201 | 30736170031 | 040535109 | JL. PEMUDI | BP2022 | TB | 101°24.35.42'E | 0°32.43.8'N | 35 | 0/100/270 | 2022 | New site 2022 - P2 | Jl. Pemudi Gang Aman RT 05 RW 09 Kel Tampan Kec Payung Sekaki Kota Pekanbaru | HTI | SUM-RI-PBR-1201 | KELURAHAN_TIRTASIAK | COLO | TBG | West | SUMBAGTENG | Riau | Kota Pekanbaru | 6617992 | 2022-01-28 | 2022-01-28 | 54 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-16 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 181111045658 | 6.6 |  | 2022-03-22 |  | 2022-03-16 | 2022-03-23 | W13-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23:03:22: RFIN 20:03:22-16:03:22: SRFI, WAITING STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL HUAWEI 13:02:22: NEED REVIEW TNP ALITA 09:02:22: RND NOK NEED 25 METER 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-LA-KLA-1128 | 30734360031 | 100100109 | DESA UMBUL JERUK | BP2022 | TB | 105°36.56.81'E | 5°30.1.44'S | 60 | 120/205/335 | 2022 | New site 2022 - P2 | Dusun 4 Jl. Andalas RT.01/04, Kel. Beringin Kencana, Kec. Candipuro, Kab. Lampung Selatan, Lampung. | HTI | SUM-LA-KLA-1128 | SINAR_PASEMAH | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Selatan | 6617991 | 2022-01-28 | 2022-01-28 | 53 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 171310603829 | 6.6 |  | 2022-03-22 |  |  | 2022-03-22 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:03:22: RFIN 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-SU-KIS-2227 | 30734580031 | 022007109 | PERUMAHAN WARGA | BP2022 | TB | 99°40.30.47'E | 2°55.37.88'N | 40 | 90/180/260 | 2022 | New site 2022 - P2 | Jl. Kebun Kelapa Dusun IV, Desa Hessa Air Genting, Kec. Air Batu , Kab. Asahan, Prov. Sumatera Utara | HTI | SUM-SU-KIS-2227 | HESSA_AIR_GENTING | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Asahan | 6617992 | 2022-01-28 | 2022-01-28 | 53 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-01 | 2022-02-02 | 125160052531 |  |  | 2022-03-22 |  |  | 2022-03-22 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:03:22: RFIN 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: KWH INSTALATION OG 11:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-LA-KTB-1143 | 30734330031 | 1013422003 | IBS LA00421 | BP2022 | TB | 104°53.41.7'E | 4°45.42.6'S | 55 | 10/125/215 | 2022 | New site 2022 - P2 | Wono Mulyo RT 001/ 001, Desa Margorejo, Kec. Kotabumi Utara, Kab. Lampung Utara | HTI | SUM-LA-KTB-1143 | KOTABUMI_UTARA_MARGO_REJO | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Utara | 6617991 | 2022-01-28 | 2022-01-28 | 53 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-25 | W13-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 173001522318 | 6.6 |  | 2022-03-22 |  |  | 2022-03-22 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:03:22: RFIN 20:03:22-16:03:22: ME OG, WAIT STO 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-RI-UJT-0948 | 30734300031 | 041133109 | UJT PANIPAHAN 2 | BP2022 | TB | 100°19.37.42'E | 2°28.45.48'N | 50 | 70/220/350 | 2022 | New site 2022 - P2 | Jl. Teluk Pulai, RT 002 RW 009, Kepenghuluan Teluk Pulai, Kec. Pasir Limau Kapas, Kab. Rokan Hilir, Prov. Riau | HTI | SUM-RI-UJT-0948 | TELUKPULAI | COLO | TBG | West | SUMBAGUT | Riau | Kab. Rokan Hilir | 6617992 | 2022-01-28 | 2022-01-28 | 53 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-01 | 2022-02-02 | 182204461537 |  |  | 2022-03-22 |  |  | 2022-03-22 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:03:22: RFIN 20:03:22: ME OG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-SU-MDN-2237 | 30734770031 | 0224962003 | IBS BAJAK II | BP2022 | TB | 98°41.58.03'E | 3°32.6.88'N | 40 | 120/240/340 | 2022 | New site 2022 - P2 | Gg. Coklat, Jl. Bajak II, Kelurahan Harjosari II, Kecamatan Medan Amplas, Kota Medan, Provinsi Sumatera Utara | HTI | SUM-SU-MDN-2237 | MEDAN_AMPLAS_HARJOSARI_II | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kota Medan | 6617992 | 2022-01-28 | 2022-01-28 | 67 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 120031125824 | 6.6 |  | 2022-03-22 |  |  | 2022-04-05 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22-30:03:22: PLN 27:03:22-23:03:22: ME OG 20:03:22-09:03:22: BTS PONDASI OG, PARALEL STRENGTENING 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-SB-LBB-0836 | 30734610031 | 0309991023 | AGAM AMPEK ANGKEK | BP2022 | TB | 100°25.42.74'E | 0°18.47.04'S | 50 | 80/170/250 | 2022 | New site 2022 - P1 | Jorong Sitapuang, Nagari Balai Gurah, Kecamatan Ampek Angkek Kabupaten Agam, Propinsi Sumatera Barat. | HTI | SUM-SB-LBB-0836 | AMPEK_ANGKEK_PASIA | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Agam | 6617992 | 2022-01-28 | 2022-01-28 | 73 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 132260127223 | 6.6 |  | 2022-03-22 |  |  | 2022-04-11 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11:04:22: RFIN 10:04:22-30:03:22: PLN 27:03:22: ME OG 23:03:22-13:03:22: PARALEL STRENGTENING 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-SU-TBT-2220 | 30735140031 | 0225242003 | IBS KOMPLEKS SATRIA | BP2022 | TB | 99°10.37.06'E | 3°20.11.11'N | 50 | 70/190/310 | 2022 | New site 2022 - P2 | Jl. Baja Gg Perak Lingkungan 004, Kelurahan Pertambangan Hulu, Kecamatan Padang Hilir, Kota Tebing Tinggi, Provinsi Sumatera Utara | HTI | SUM-SU-TBT-2220 | TAMBANGAN_HULU | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kota Tebing Tinggi | 6617992 | 2022-01-28 | 2022-01-28 | 70 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-04-10 | W16-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 121101069934 |  |  | 2022-03-22 |  |  | 2022-04-08 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 06:04:22-30:03:22: PLN 27:03:22-16:03:22: ME PARALEL STRENGTENING 13:03:22-09:03:22: BTS PONDASI OG, PARALEL STRENGTENING 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-SS-MBL-1210 | 30735070031 | 070070104 | SP 1 DAN 2 TRANS SUBUR | BP2022 | SKP | 103°10.15.6'E | 2°48.22.5'S | 60 | 90/190/270 | 2022 | New site 2022 - P2 | Jl. Nakula, Dusun Sidomulyo,Desa SidomulyoKec. Muara Lakitan, Kab. Musi Rawas | HTI | SUM-SS-MBL-1210 | MI_ALMUHAJIRIN_SIDOMULYO | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas | 6617983 | 2022-01-28 | 2022-01-28 | 80 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 147800877441 | 6.6 |  | 2022-03-22 |  | 2022-03-29 | 2022-04-18 | W17-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18:04:22: RFIN 17:04:22-29:03:22: SRFI 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22-07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-BE-CRP-0189 | 30734140031 | 090208109 | DESA TELADAN | BP2022 | TB | 102°31.51.6'E | 3°29.25.48'S | 40 | 0/90/270 | 2022 | New site 2022 - P2 | Jl. Pembangunan, Desa Teladan Kec. Curup Selatan, Kab. Rejang Lebong Prov. Bengkulu | HTI | SUM-BE-CRP-0189 | CURUP_SELATAN_TELADAN | COLO | TBG | West | SUMBAGSEL | Bengkulu | Kab. Rejang Lebong | 6617991 | 2022-01-28 | 2022-01-28 | 80 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 146102458010 | 6.6 |  | 2022-03-22 |  |  | 2022-04-18 | W17-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18:04:22: RFIN 17:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-KR-BSB-0576 | 30735180031 | 050038109 | BATU LICIN | BP2022 | SKP | 104°32.27.6'E | 0°51.16.13'N | 60 | 0/130/230 | 2022 | New site 2022 - P2 | Kp. Wacopek, RT.01/04, Desa Gunung Lengkuas, Kec. Bintan Timur, Kab. Bintan, Prov. Kepulauan Riau | HTI | SUM-KR-BSB-0576 | BINTAN_TIMUR_GUNUNG_LENGKUAS | COLO | TBG | West | SUMBAGTENG | Kepulauan Riau | Kab. Bintan | 6617983 | 2022-01-28 | 2022-01-28 | 75 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 183021818286 | 6.6 |  | 2022-03-22 |  |  | 2022-04-13 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:04:22: RFIN 10:04:22-30:03:22: PLN 27:03:22-16:03:22: ME OG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUL-SN-WNS-0980 | 30734390031 | 2815952010 | IBS IBS_PANINCONG | BP2022 | TB | 119°53.19.18'E | 4°12.27.94'S | 45 | 0/180/270 | 2022 | New site 2022 - P2 | Jl. Panincong, RT.02, RW.08, Desa Panincong, Kec. Marioriawa, Kab. Soppeng, Sul-Sel | HTI | SUL-SN-WNS-0980 | PANINCONG_MARIORIAWA | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Soppeng | 6617991 | 2022-01-28 | 2022-01-28 | 76 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-08 | W11-2022 | Mar-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 325600253534 | 6.6 |  | 2022-03-21 |  | 2022-03-08 | 2022-04-14 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14:04:22: RFIN 09:03:22: SRFI, PLN CONNECTION, PARALEL STRENGTENING 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUL-SN-SDR-1279 | 30734180031 | 280007109 | DATAE DCS | BP2022 | TRB | 119°42.51.8'E | 3°54.46.19'S | 70 | 50/240 | 2022 | New site 2022 - P2 | Jl. Poros Sidrap - Pare, Kampung Datae Kel. Lawowoi Kec. Wattang Puluh Kab. Sidrap, Sulawesi Selatan | HTI | SUL-SN-SDR-1279 | KELURAHAN_LAWAWOI_WATANG_PULU | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Sidenreng Rappang | 6617994 | 2022-01-28 | 2022-01-28 | 69 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 325500309827 | 6.6 |  | 2022-03-21 |  |  | 2022-04-07 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07:04:22: RFIN 06:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUL-SA-BIT-0393 | 30730880031 | 310084109 | BISUI | BP2022 | SKP | 125°5.51.11'E | 1°26.48.88'N | 60 | 60/170/320 | 2022 | New site 2022 - P2 | Lingkungan II RT/RW 006/002 Kel. Tendeki, Kec. Matuari, Kota Bitung, Prov. Sulawesi Utara | HTI | SUL-SA-BIT-0393 | TENDEKI_MATUARI | COLO | TBG | East | SULAWESI | Sulawesi Utara | Kota Bitung | 6617983 | 2022-01-28 | 2022-01-28 | 69 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 311100512513 | 6.6 |  | 2022-03-21 |  |  | 2022-04-07 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07:04:22: RFIN 06:04:22-03:04:22: PLN & PERKUATAN 30:03:22-13:03:22: PARALEL STRENGTENING 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: CME PREPARATION -> STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 02:02:22: NEED REVIEW TNP ALITA 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
89 COLO |  | JAW-JB-SPA-4229 | 30741220031 | 125046109 | TONJONGSARI-BARENGKOK | BP2022 | SKP | 108°10.39.5'E | 7°43.43.0'S | 50 | 20/145/280 | 2022 | Newsite 2022 - B2 | Desa Singkir Kp. Singkir RT.001 RW.002, Kec. Cikalong, Kab. Tasikmalaya Prov. Jawa Barat | HTI | JAW-JB-SPA-4229 | SINGKIR | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Tasikmalaya | 6618082 | 2022-03-11 | 2022-03-11 | 26 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 532652455645 |  |  | 2022-03-21 |  |  | 2022-04-06 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:04:22: RFIN 06:04:22: SRFI 03:04:22: ME OG 30:03:22-27:03:22: PONDASI OG 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
NEW SPK B2S |  | JAW-JI-BKL-4323 | 30730310031 | 1654761003 | KARANG_GAYAM_BLEGA | BP2022 | TB | 113°4.36.86'E | 7°7.8.48'S | 50 | 100/250/340 | 2022 | New site 2022 - P2 | Jalan Raya Blega Rt.00 Rw.00 Desa.Karangayam Kecamatan Blega Kabupaten Bangkalan Provinsi Jawa Timur | HTI | JAW-JI-BKL-4323 | KARANG_GAYAM_BLEGA | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617949 | 2022-01-25 | 2022-01-28 | 70 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-01 | 517600665854 | 6.6 |  | 2022-03-21 |  |  | 2022-04-05 | W15-2022 |  |  | PRESITAC | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22: RFI, WAIT RFIN 30:03:22-27:03:22: SRFI 23:03:22; ERECTION 20:03:22: CURRING TIME 16:03:22: REBARRING 13:03:22-09:03:22: EXCAVATION 06:03:22-23:02:22: REKOM OG 20:02:22: REALISASI IW 16:02:22: IW CLEAR 13:02:22-03:02:22: VALIDASI RNP TNP 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
740 |  | JAW-JI-SPG-4232 | 30701680031 | 160197104 | LAR LAR | RORO JONGRANG 2021 [NEW] | SKP | 113°14.6.83'E | 6°57.33.26'S | 50 | 10/90/250 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Toguran Desa Tlagah kec.Banyuates kab.Sampang | HTI | JAW-JI-SPG-4232 | KETAPANG PAOPALELAOK | COLO | TBG | East | JATIM | Jawa Timur | Kab. Sampang | 6617454 | 2021-08-09 |  | 77 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-26 | W44-2021 | Oct-2021 | 2021-10-26 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 517500852034 | 6.6 |  | 2021-10-04 |  | 2021-09-24 | 2021-10-25 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:10:21: RFIN 20:10:21-15:09:21: SRFI 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
NEW SPK |  | SUM-LA-SDN-1151 | 30736200031 | 101002126 | WONOKARTO_SEKAMPUNG | BP2022 | TB | 105°30.0.0'E | 5°7.48.0'S | 50 | 40/240/310 | 2022 | New site 2022 - P2 | Dusun IV RT.008 RW.004, Desa Mekar Sari, Kec. Sekampung, Kab. Lampung Timur, Prov. Lampung | HTI | SUM-LA-SDN-1151 | MEKAR_SARI | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Timur | 6617991 | 2022-01-28 | 2022-01-28 | 58 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-31 | W23-2022 | May-2022 | 2022-05-31 | W23-2022 | May-2022 | MW | 2022-02-02 | 2022-02-03 | 172000881967 | 6.6 |  | 2022-03-22 |  |  | 2022-03-27 | W14-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:03:22: RFIN 27:03:22: STRENGTENING 23:03:22-16:03:22: ME OG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL 13:02:22: NEED REVIEW TNP ALITA 09:02:22: RND NOK NEED 50 METER 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
89 COLO |  | JAW-JB-CJR-4322 | 30740800031 | 120914104 | NAGASARI | BP2022 | SMI | 106°57.36.0'E | 7°22.20.39'S | 50 | 30/130/290 | 2022 | Newsite 2022 - B2 | Jl. Nagasari, Desa Nagasari RT.01 RW.01, Kec. Leles, Kab. Cianjur Prov. Jawa Barat | HTI | JAW-JB-CJR-4322 | NAGASARI | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Cianjur | 6618086 | 2022-03-11 | 2022-03-11 | 28 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-29 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 536911879805 |  |  | 2022-03-21 |  | 2022-03-29 | 2022-04-08 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 06:04:22-04:04:22: NO NEED STR 03:04:22-29:03:22: SRFIN & STR NY PARALEL 27:03:22: STRENGTENING OG 23:03:22-20:03:22: PONDASI OG 16:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-GRT-4265 | 30741270031 | 125488126 | CARINGIN GARUT | BP2022 | TB | 107°30.46.8'E | 7°27.15.23'S | 40 | 30/170/285 | 2022 | Newsite 2022 - B2 | Desa Caringin Kp. Caringin RT.02 RW.01, Kec. Caringin, Kab. Garut Prov. Jawa Barat | HTI | JAW-JB-GRT-4265 | PASAR_DESA_CARINGIN | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Garut | 6618079 | 2022-03-11 | 2022-03-11 | 35 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 532770754426 | 6.6 |  | 2022-03-21 |  |  | 2022-04-15 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:04:22: RFIN 13:04:22-06:04:22: SRFI 03:04:22: ME OG 30:03:22-27:03:22: PONDASI OG 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-CJR-4337 | 30741240031 | 122384109 | GNGGEDEH-CIBULAKAN | BP2022 | SKP | 107°4.22.19'E | 6°49.3.0'S | 40 | 0/135/295 | 2022 | Newsite 2022 - B2 | Desa Talaga RT.01 RW.04, Kec. Cugenang, Kab. Cianjur Prov. Jawa Barat | HTI | JAW-JB-CJR-4337 | CUGENANGTALAGA | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Cianjur | 6618082 | 2022-03-11 | 2022-03-11 | 24 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 536712719563 | 6.6 |  | 2022-03-21 |  | 2022-03-31 | 2022-04-04 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:04:22: RFIN 03:04:22-31:03:22: SRFIN, BUT STRENGENING 30:03:22: PONDASI OG 27:03:22: MOBDEMOB, STRENGTENING 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-SOR-4422 | 30741310031 | 1264551023 | IBUN BANDUNG | BP2022 | TB | 107°44.50.03'E | 7°6.36.0'S | 50 | 170/240/340 | 2022 | Newsite 2022 - B2 | Desa Neglasari Kp. Mincrik RT.003 RW.010, Kec. Ibun, Kab. Bandung Prov. Jawa Barat | HTI | JAW-JB-SOR-4422 | PANGGUH | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Bandung | 6618079 | 2022-03-11 | 2022-03-11 | 25 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 535312341803 | 6.6 |  | 2022-03-21 |  | 2022-03-31 | 2022-04-05 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22-31:03:22: SRFIN, PLN 30:03:22-27:03:22: PONDASI OG 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-SPA-4242 | 30740770031 | 125261126 | JL RAYA SALOPA | BP2022 | TB | 108°16.15.6'E | 7°31.30.58'S | 50 | 5/140/275 | 2022 | Newsite 2022 - B2 | Desa Mandalahayu Dusun Cilegi RT.02 RW.02, Kec. Salopa, Kab. Tasikmalaya Prov. Jawa Barat | HTI | JAW-JB-SPA-4242 | MANDALAHAYU | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Tasikmalaya | 6618079 | 2022-03-11 | 2022-03-11 | 25 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-29 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 532652455652 | 6.6 |  | 2022-03-21 |  | 2022-03-25 | 2022-04-05 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22-25:03:22: SRFI, PLN CONNECTION 23:03:22-20:03:22: PONDASI OG 16:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-CJR-4320 | 30740820031 | 120901104 | SUKARAMA | BP2022 | SMI | 106°59.9.96'E | 7°21.40.5'S | 70 | 200/250/290 | 2022 | Newsite 2022 - B2 | Desa Sukamulya Kp. Cibangsa RT.04 RW.02, Kec. Leles, Kab. Cianjur Prov. Jawa Barat | HTI | JAW-JB-CJR-4320 | LELES_SUKAMULYA | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Cianjur | 6618086 | 2022-03-11 | 2022-03-11 | 25 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-29 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 536911879480 | 6.6 |  | 2022-03-21 |  | 2022-03-29 | 2022-04-05 | W15-2022 |  |  |  | 38.RFI | 21.RFI | PARALEL STRENGTENING | 05:04:22: RFIN, PARALEL STR 03:04:22-29:03:22: SRFIN 27:03:22: STRENGTENING OG 23:03:22-20:03:22: PONDASI OG 16:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-SPA-4233 | 30740740031 | 120271109 | LANDEUH-PAGERAGEUNG | BP2022 | TB | 108°11.34.44'E | 7°6.1.55'S | 50 | 20/115/260 | 2022 | Newsite 2022 - B2 | Kp. Guranteng RT.01 RW.01 Desa Guranteng, Kec. Pageuregeung, Kab. Tasikmalaya Prov. Jawa Barat | HTI | JAW-JB-SPA-4233 | PAGERAGEUNG_PUTERAN_GURANTENG | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Tasikmalaya | 6618079 | 2022-03-11 | 2022-03-11 | 25 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-29 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 532513708385 | 6.6 |  | 2022-03-21 |  | 2022-03-25 | 2022-04-05 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 05:04:22: RFIN, NO NEED STR 03:04:22--25:03:22: SRFI & STR NY PARALEL 23:03:22-20:03:22: PONDASI OG 16:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-CMS-4292 | 30740750031 | 121765109 | PROTEL-CIAMIS | BP2022 | TB | 108°20.34.8'E | 7°5.31.7'S | 60 | 75/170/250 | 2022 | Newsite 2022 - B2 | Desa Mekarwangi Dusun Pajagan RT.15 RW.05, Kec. Sukamantri, Kab. Ciamis Prov. Jawa Barat | HTI | JAW-JB-CMS-4292 | SUKAMANTRI_MEKARWANGI | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Ciamis | 6618079 | 2022-03-11 | 2022-03-11 | 25 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-29 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 532513708377 | 6.6 |  | 2022-03-21 |  | 2022-03-25 | 2022-04-05 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 05:04:22: RFIN, NO NEED STR 03:04:22-25:03:22: SRFI & STR NY PARALEL 23:03:22-20:03:22: PONDASI OG 16:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-SPA-4224 | 30740780031 | 121425104 | BURUJULJAYA | BP2022 | SMI | 108°7.51.6'E | 7°28.16.79'S | 70 | 120/230/290 | 2022 | Newsite 2022 - B2 | Desa Burujuljaya RT.02 RW.02, Kec. Parungponteng, Kab. Tasikmalaya Prov. Jawa Barat | HTI | JAW-JB-SPA-4224 | BURUJULJAYA | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Tasikmalaya | 6618086 | 2022-03-11 | 2022-03-11 | 25 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-29 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 532652455660 | 6.6 |  | 2022-03-21 |  | 2022-03-25 | 2022-04-05 | W15-2022 |  |  |  | 38.RFI | 21.RFI | PARALEL STRENGTENING | 05:04:22: RFIN, PARALEL STR 03:04:22-25:03:22: SRFI & STR NY PARALEL 23:03:22-20:03:22: PONDASI OG 16:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-CMS-4286 | 30741250031 | 122423109 | SADANANYA (DS CITULANG, DESA TANJUNGSARI) | BP2022 | SKP | 108°18.54.0'E | 7°15.3.74'S | 60 | 135/260/340 | 2022 | Newsite 2022 - B2 | Desa Tanjungsari Dusun Cukanguncal RT.04 RW.07, Kec. Sadananya, Kab. Ciamis Prov. Jawa Barat | HTI | JAW-JB-CMS-4286 | SADANANYA_TANJUNGSARI | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Ciamis | 6618082 | 2022-03-11 | 2022-03-11 | 25 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 532314758311 | 6.6 |  | 2022-03-21 |  |  | 2022-04-05 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 05:04:22: RFIN (NO NEED STR) 03:04:22: ME OG & PERKUATAN 30:03:22: PONDASI OG 27:03:22: MOBDEMOB, STRENGTENING 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-MJL-4127 | 30741340031 | 120128109 | BANTARUJEG-MEKARRAHARJA | BP2022 | TB | 108°15.36.14'E | 6°57.46.22'S | 50 | 115/210/295 | 2022 | Newsite 2022 - B2 | Jl. Dusun Cikidang, Blok Cikidang RT.01 RW.01, Kec. Bantarujeg, Kab. Majalengka Prov. Jawa Barat | HTI | JAW-JB-MJL-4127 | BANTARUJEG_CIKIDANG | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Majalengka | 6618079 | 2022-03-11 | 2022-03-11 | 24 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 535212688199 | 6.6 |  | 2022-03-21 |  |  | 2022-04-04 | W15-2022 |  |  |  | 38.RFI | 21.RFI | PARALEL STRENGTENING | 04:04:22: RFIN, PARALEL STR 03:04:22: ME OG 30:03:22: PONDASI OG 27:03:22: MOBDEMOB, STRENGTENING 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-GRT-4258 | 30740790031 | 121245104 | RD_WADO_MLGBNG | BP2022 | SMI | 108°5.27.6'E | 7°0.55.44'S | 60 | 70/140/275 | 2022 | Newsite 2022 - B2 | Jl. RD Wado to Malangbong (Depan Argo), Desa Cilampuyang RT.07 RW.03 Kec. Malangbong, Kab. Garut Prov. Jawa Barat | HTI | JAW-JB-GRT-4258 | CILAMPUYANG | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Garut | 6618086 | 2022-03-11 | 2022-03-11 | 27 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-29 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 532861296523 | 6.6 |  | 2022-03-21 |  | 2022-03-25 | 2022-04-07 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07:04:22: RFIN 06:04:22-25:03:22: SRFI, PLN CONNECTION 23:03:22-20:03:22: PONDASI OG 16:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-SMD-4365 | 30741330031 | 125697109 | BO-MARGAMEKAR-SUMEDANGSELATAN | BP2022 | TB | 107°54.54.0'E | 6°53.50.21'S | 40 | 25/95/310 | 2022 | Newsite 2022 - B2 | Desa Margamekar Dusun Cipicung RT.002 RW.006, Kec. Sumedang Selatan, Kab. Sumedang Prov. Jawa Barat | HTI | JAW-JB-SMD-4365 | MARGAMEKAR | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Sumedang | 6618079 | 2022-03-11 | 2022-03-11 | 28 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 535113442381 | 6.6 |  | 2022-03-21 |  |  | 2022-04-08 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 06:04:22-03:04:22: ME OG 30:03:22-27:03:22: PONDASI OG 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-CJR-4318 | 30740810031 | 120916104 | GN_ BATU_CNJR | BP2022 | SMI | 107°17.10.39'E | 7°25.13.58'S | 50 | 0/120/195 | 2022 | Newsite 2022 - B2 | Desa Cinerang Kp. Cikacang RT.01 RW.02, Kec. Naringgul, Kab. Cianjur Prov. Jawa Barat | HTI | JAW-JB-CJR-4318 | CINERANG | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Cianjur | 6618086 | 2022-03-11 | 2022-03-11 | 28 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-29 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 536911879870 |  |  | 2022-03-21 |  | 2022-04-01 | 2022-04-08 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 07:04:22: NO NEED STR 06:04:22-01:04:22: SRFIN & STR NY PARALEL 30:03:22: PONDASI OG 27:03:22: STRENGTENING OG 23:03:22-20:03:22: PONDASI OG 16:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-CJR-4319 | 30741360031 | 120899104 | JAYAGIRI_CJR | BP2022 | SMI | 107°10.41.2'E | 7°27.58.58'S | 70 | 0/100/275 | 2022 | Newsite 2022 - B2 | Jl. Raya Sindang Barang-Sukapura, Desa Jaya Giri Kp. Babakan Tanjung RT.11 RW.03, Kec. Sindangbarang, Kab. Cianjur Prov. Jawa Barat | HTI | JAW-JB-CJR-4319 | MEKARLAKSANA | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Cianjur | 6618086 | 2022-03-11 | 2022-03-11 | 28 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 536911880015 |  |  | 2022-03-21 |  | 2022-03-31 | 2022-04-08 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 06:04:22-31:03:22: SRFIN, PLN 30:03:22-27:03:22: PONDASI OG 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
NEW SPK B2S |  | JAW-BT-RKB-0774 | 30729610031 | 1323091003 | BANJARSARI_WARUNGGUNUNG | BP2022 | TB | 106°10.37.2'E | 6°19.20.32'S | 50 | 100/190/280 | 2022 | New site 2022 - P1 | Kp. Citundun Lor RT 008 RW 002 Desa Banjarsari Kec.Warunggung | EID | JAW-BT-RKB-0774 | BANJARSARI_WARUNGGUNUNG | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6617948 | 2022-01-25 | 2022-01-28 | 83 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-07 | 2022-04-05 | 562101020031 | 6.6 |  | 2022-04-13 |  |  | 2022-04-18 | W17-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18:04:22: RFIN 17:04:22-13:04:22: SRFI, WAIT RFIN 10:04:22-03:04:22: ME 30:03:22-27:03:22: ERECTION 23:03:22-20:03:22: CURRING 16:03:22-13:03:22: EXCAVATION 09:03:22-23:02:22: REKOM OG 20:02:22-13:02:22: IW OG 09:02:22-04:02:22: PRIORITY CANDIDATE A 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
|  | JAW-JB-CKR-0118 | 30735530031 | 1267522007 | IBS KP BABAKAN BEKASI | BP2022 | TB | 107°4.48.58'E | 6°19.19.06'S | 30 | 30/170/310 | 2022 | New site 2022 - P1 | Desa Jatiwangi Kp. Babakan RT.003 RW.001 Kec. Cikarang Barat, Kab. Bekasi Prov. Jawa Barat | EID | JAW-JB-CKR-0118 | BABAKAN_BEKASI | COLO | TBG | JABO | JABODETABEK | Jawa Barat | Kab. Bekasi | 6618018 | 2022-02-03 | 2022-02-04 | 74 | 61 - 90 days | 2022-03-05 | W10-2022 | Mar-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-07 | 2022-04-05 | 537422013604 | 10.6 |  | 2022-04-05 |  |  | 2022-04-18 | W17-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18:04:22: RFIN 17:04:22: RFI, WAIT RFIN 13:04:22-06:04:22: PLN 03:04:22 ME OG 30:03:22-13:03:22: WAIT PSB & STO 09:03:22: PONDASI OG 06:03:22-13:02:22: NEED REVIEW POWER EID 09:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW RNP EID 04:02:22: NEW SPK RELEASED | apr
|  | JAW-JB-NPH-4379 | 30739990031 | 1276991003 | JATIMEKAR | BP2022 | TB | 107°22.20.3'E | 6°44.44.68'S | 50 | 100/200/290 | 2022 | Newsite 2022 - P1 | Kp. Ciburial Rt. 004 Rw. 003 Desa. Jatimekar Kec. Cipendeuy Kab Bandung Barat Provinsi Jawa Barat | HTI | JAW-JB-NPH-4379 | JATIMEKAR | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Bandung Barat | 6618108 | 2022-03-07 | 2022-03-07 | 38 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 535852226270 | 6.6 |  | 2022-03-31 |  |  | 2022-04-14 | W16-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14:04:22: RFIN 13:04:22-06:04:22: ERECTION 03:04:22: POURING 30:03:22-27:03:22: OG FABRIKASI BESI 23:03:22: EXCAVATION 20:03:22: REKOM 16:03:22-13:03:22: IW OG 11:03:22: VALIDASI RNP TNP 09:03:22: SURVEY OG 07:03:22: SPK RECEIVED | apr
|  | JAW-JB-NPH-4380 | 30739920031 | 1276961003 | NYENANG | BP2022 | TB | 107°21.13.54'E | 6°44.47.21'S | 50 | 15/190/270 | 2022 | Newsite 2022 - P1 | Kp. Nyenang Rt. 002 Rw. 003 Desa. Nyenang Kec. Cipendeuy Kab Bandung Barat Provinsi Jawa Barat. | HTI | JAW-JB-NPH-4380 | NYENANG | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Bandung Barat | 6618108 | 2022-03-07 | 2022-03-07 | 36 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 535852226558 | 6.6 |  | 2022-03-31 |  |  | 2022-04-12 | W16-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12:04:22: RFIN 10:04:22-06:04:22: ERECTION 03:04:22: POURING 30:03:22-27:03:22: OG FABRIKASI BESI 23:03:22: EXCAVATION 20:03:22: REKOM 16:03:22-13:03:22: IW OG 11:03:22: VALIDASI RNP TNP 09:03:22: SURVEY OG 07:03:22: SPK RECEIVED | apr
NEW SPK B2S |  | SUM-SS-BTA-1081 | 30729900031 | 0719131003 | SINAR_PENINJAUAN_SRI_MULYA | BP2022 | TB | 104°24.28.3'E | 3°54.17.94'S | 60 | 60/215/330 | 2022 | New site 2022 - P2 | Blok H Dusun III RT 003 RW 003 Desa Sri Mulya, Kecamatan Sinar Peninjauan Kabupaten Ogan Komering Ulu, Provinsi Sumatera Selatan | HTI | SUM-SS-BTA-1081 | SINAR_PENINJAUAN_SRI_MULYA | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu | 6617950 | 2022-01-25 | 2022-01-28 | 90 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-02 | 147500959272 |  |  | 2022-04-25 |  |  | 2022-04-25 |  |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22-20:04:22: PLN CONNECTION 30:03:22: ERECTION 27:03:22: REBARRING 23:03:22-06:03:22: REKOM 28:02:22-23:02:22: IW CLEAR 20:02:22-13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
89 COLO |  | JAW-JB-SOR-4417 | 0030740760031 | 1271102010 | IBS PANYINDANGAN PANGALENGAN | BP2022 | TB | 107°33.41.76'E | 7°9.20.74'S | 35 | 55/140/335 | 2022 | Newsite 2022 - B2 | Desa Margamulya Kp. Panyindangan RT.004 RW.005, Kec. Pangalengan, Kab. Bandung Prov. Jawa Barat | HTI | JAW-JB-SOR-4417 | MARGAMULYA_RAYA_PANGALENGAN | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Bandung | 6618079 | 2022-03-11 | 2022-03-11 | 20 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | 2022-03-29 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 535342247503 |  |  | 2022-03-21 |  |  | 2022-03-31 | W14-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:03:22: RFIN 30:03:22-27:03:22: ME OG 23:03:22-20:03:22: PONDASI OG 16:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED
89 COLO |  | SUM-SU-AKK-2239 | 30741390031 | 225382007 | IBS AEK NABARA | BP2022 | TB | 99°56.31.27'E | 2°4.6.24'N | 55 | 30/110/260 | 2022 | Newsite 2022 - B2 | Jl. Mangga Besar Dusun V, Desa Sidorukun, Kecamatan Pangkatan, Kabupaten Labuhanbatu, Provinsi Sumatera Utara | HTI | SUM-SU-AKK-2239 | PERKEBUNAN_PANGKATAN | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu | 6618079 | 2022-03-11 | 2022-03-11 | 28 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 125150244399 |  |  | 2022-03-24 |  |  | 2022-04-08 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 06:04:22: PLN & PARALEL STR 03:04:22: ME OG & PERKUATAN PARALEL 30:03:22: PONDASI OG 27:03:22: PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | SUM-SS-SKY-1242 | 30741280031 | 71056109 | SUMSEL2G02 | BP2022 | TB | 103°25.26.15'E | 2°45.0.36'S | 60 | 60/200/355 | 2022 | Newsite 2022 - B2 | Jl. Provinsi Desa Ngulak 2, Kec. Sanggadesa, Kab. Musi Banyuasin Prov. Sumatera Selatan | HTI | SUM-SS-SKY-1242 | NGULAK_I | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Banyuasin | 6618079 | 2022-03-11 | 2022-03-11 | 40 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 142200517499 |  |  | 2022-03-24 |  | 2022-04-14 | 2022-04-20 | W17-2022 |  |  |  | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 20:04:22: RFIN 14:04:22: SRFIN 13:04:22-06:04:22: ME OG 03:04:22: PONDASI OG 30:03:22-27:03:22: PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | SUM-SU-PMS-2248 | 30741750031 | 226882007 | IBS NMDN_0991 | BP2022 | TB | 99°2.27.31'E | 2°50.51.86'N | 50 | 50/210/300 | 2022 | Newsite 2022 - B2 | JL Parapat Pasar Baru Gamot 2 Kel Dolok Pariasan Kec Jorlang hataran Kab Simalungun | HTI | SUM-SU-PMS-2248 | DOLOK_PARRIASAN | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Simalungun | 6618079 | 2022-03-11 | 2022-03-11 | 40 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-24 | 2022-03-25 | 121130193690 |  |  | 2022-03-23 |  |  | 2022-04-20 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:04:22: RFIN 17:04:22-10:04:22: ME, PARALEL STR 07:04:22: PARALEL STR 06:04:22: ME OG 03:04:22-30:03:22: PONDASI OG 27:03:22-23:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-SPA-4230 | 30741260031 | 120270109 | KRGNUNGGAL-TOBONGJAYA | BP2022 | TB | 108°6.57.2'E | 7°38.57.59'S | 50 | 50/220/300 | 2022 | Newsite 2022 - B2 | Kp. Datar Kadaka RT.10 RW.04 Desa Cikupa, Kec. Karang Nunggal, Kab. Tasikmalaya Prov. Jawa Barat | HTI | JAW-JB-SPA-4230 | CIKUPA | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Tasikmalaya | 6618079 | 2022-03-11 | 2022-03-11 | 26 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 532652455637 | 6.6 |  | 2022-03-23 |  |  | 2022-04-06 | W15-2022 |  |  |  | 38.RFI | 21.RFI | NEED STRENGTENING PARALEL | 06:04:22: RFIN, STR PARALEL 03:04:22: ME OG & PERKUATAN 30:03:22: PONDASI OG 27:0:22-23:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-SMD-4367 | 30741660031 | 121260104 | GUNASARI | BP2022 | SMI | 107°55.51.6'E | 6°51.40.9'S | 40 | 90/155/340 | 2022 | Newsite 2022 - B2 | Kel. Cipameumpeuk Kp. Tenjolaya, Kec. Sumedang Selatan, Kab. Sumedang Prov. Jawa Barat | HTI | JAW-JB-SMD-4367 | CIPAMEUNGPEUK | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Sumedang | 6618086 | 2022-03-11 | 2022-03-11 | 28 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-24 | 2022-03-25 | 535113442730 | 6.6 |  | 2022-03-23 |  |  | 2022-04-08 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 06:04:22-03:04:22: ME OG 30:03:22: PONDASI OG 27:0:22-23:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-CJR-4327 | 30741650031 | 120918104 | CILEPO | BP2022 | SMI | 107°9.39.06'E | 7°23.49.56'S | 70 | 175/235/305 | 2022 | Newsite 2022 - B2 | Jl. Raya Sindangbarang-Cilepo, Desa Girimukti RT.05 RW.02, Kec. Sindangbarang, Kab. Cianjur Prov. Jawa Barat | HTI | JAW-JB-CJR-4327 | SINDANGBARANG_GIRIMUKTI | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Cianjur | 6618086 | 2022-03-11 | 2022-03-11 | 28 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-24 | 2022-03-25 | 536911879792 |  |  | 2022-03-23 |  | 2022-03-31 | 2022-04-08 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 06:04:22-31:03:22: SRFIN 30:03:22: PONDASI OG 27:0:22-23:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | NUS-NB-TJN-5384 | 30741640031 | 180283109 | SELELOS | BP2022 | TB | 116°13.18.08'E | 8°20.21.16'S | 70 | 50/130/300 | 2022 | Newsite 2022 - B2 | Dusun Penjor Desa Ganggelang Kecamatan Gangga Kabupaten Lombok Utara Propinsi Nusa Tenggara Barat. | HTI | NUS-NB-TJN-5384 | GENGGELANG | COLO | TBG | East | BALINUSRA | Nusa Tenggara Barat | Kab. Lombok Utara | 6618079 | 2022-03-11 | 2022-03-11 | 25 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-24 | 2022-03-25 | 441301097678 | 6.6 |  | 2022-03-22 |  |  | 2022-04-05 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22: ME OG 30:03:22: PONDASI OG 27:03:22: PREPARE CME 23:03:22-13:03:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-CJR-4331 | 30741320031 | 125588109 | BO-CIDADAP-CAMPAKA | BP2022 | TB | 107°8.16.8'E | 7°1.12.79'S | 40 | 25/70/220 | 2022 | Newsite 2022 - B2 | Desa Cidadap Kp. Cikekep RT.006 RW.003, Kec. Campaka, Kab. Cianjur Prov. Jawa Barat | HTI | JAW-JB-CJR-4331 | CAMPAKA_CIDADAP | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Cianjur | 6618079 | 2022-03-11 | 2022-03-11 | 24 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 536950533776 | 6.6 |  | 2022-03-22 |  | 2022-03-29 | 2022-04-04 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:04:22: RFIN 03:04:22-29:03:22: SRFIN, PLN 27:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-GRT-4254 | 30741370031 | 121071104 | CISOMPET | BP2022 | SMI | 107°48.30.24'E | 7°30.39.96'S | 50 | 45/115/185 | 2022 | Newsite 2022 - B2 | Desa Neglasari RT.01 RW.11, Kec. Cisompet, Kab. Garut Prov. Jawa Barat | HTI | JAW-JB-GRT-4254 | CISOMPET_NEGLASARI | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Garut | 6618086 | 2022-03-11 | 2022-03-11 | 27 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 532770754077 | 6.6 |  | 2022-03-22 |  |  | 2022-04-07 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07:04:22: RFIN 06:04:22: SRFI & STR 03:04:22: ME OG 30:03:22: PONDASI OG 27:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
89 COLO |  | JAW-JB-CMS-4293 | 30741230031 | 122418109 | RANCAH | BP2022 | SKP | 108°18.14.4'E | 7°8.57.16'S | 50 | 45/200/300 | 2022 | Newsite 2022 - B2 | Jl. Raya Kwali - Panjalu, Kec. Rancah, Kab. Ciamis Prov. Jawa Barat | HTI | JAW-JB-CMS-4293 | CIOMAS | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Ciamis | 6618082 | 2022-03-11 | 2022-03-11 | 27 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 532513709188 | 6.6 |  | 2022-03-22 |  |  | 2022-04-07 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07:04:22: RFIN 06:04:22: SRFI & STR 03:04:22: ME OG 30:03:22: PONDASI OG 27:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
NEW SPK |  | SUM-LA-KOT-1087 | 30735000031 | 100123109 | ISLAMIC CENTER KOTA AGUNG | BP2022 | TB | 104°38.37.97'E | 5°29.14.5'S | 50 | 35/115/300 | 2022 | New site 2022 - P2 | Jl. Islamic Center, Dukuh Cunggung RT.04/02, Kel. Kedamaian, Kec. Kota Agung, Kab. Tanggamus Prov. Lampung | HTI | SUM-LA-KOT-1087 | KOTA_AGUNG_KEDAMAIAN | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Tanggamus | 6617991 | 2022-01-28 | 2022-01-28 | 68 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 172400482877 | 6.6 |  | 2022-03-22 |  |  | 2022-04-06 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:04:22: RFIN 03:04:22: PLN, CAN BE ACCELERATE TO APR 03:04:22-27:03:22: ME OG 23:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22-07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-SS-MBL-1202 | 30734100031 | 071227109 | DESA SUGI WARAS | BP2022 | TB | 103°8.56.4'E | 3°15.11.16'S | 60 | 40/230/300 | 2022 | New site 2022 - P2 | Desa Sugih Waras,Kecamatan Suka Karya Kabupaten Musi Rawas, Provinsi Sumatera Selatan | HTI | SUM-SS-MBL-1202 | SUKOWARNO | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas | 6617992 | 2022-01-28 | 2022-01-28 | 67 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 147800877458 | 6.6 |  | 2022-03-22 |  | 2022-03-28 | 2022-04-05 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22: PLN, CAN BE ACCELERATE TO APR 03:04:22-28:03:22: SRFIN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-SS-MBL-1206 | 30734730031 | 071278109 | DESA SERIANG | BP2022 | TB | 103°8.38.4'E | 3°9.53.86'S | 50 | 160/270/340 | 2022 | New site 2022 - P2 | RT.01 Dusun 4 Desa Jaya Bakti Kec. Tuah Negeri Kab. Musi Rawas Prov. Sumsel | HTI | SUM-SS-MBL-1206 | JAYA_BHAKTI | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas | 6617992 | 2022-01-28 | 2022-01-28 | 67 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 147800877466 | 6.6 |  | 2022-03-22 |  | 2022-03-28 | 2022-04-05 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22: PLN, CAN BE ACCELERATE TO APR 03:04:22-28:03:22: SRFI 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 08:02:22: NEED REVIEW TNP ALITA 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-SS-MRD-1012 | 30734080031 | 071395109 | DESA ANUGERAH | BP2022 | TB | 103°43.58.87'E | 4°30.55.08'S | 40 | 70/270 | 2022 | New site 2022 - P2 | Dusun II, Desa Anugerah, Kec. Pulau Beringin, Kab. Ogan Komering Ulu Selatan, Prov. Sumatera Selatan | HTI | SUM-SS-MRD-1012 | ANUGERAH_KEMU | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Se | 6617992 | 2022-01-28 | 2022-01-28 | 67 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 147700649244 | 6.6 |  | 2022-03-22 |  |  | 2022-04-05 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22: PLN, CAN BE ACCELERATE TO APR 03:04:22-30:03:22: PLN 27:03:22-16:03:22: ME OG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-LA-PRW-1126 | 30734460031 | 100217104 | MARGOSARI | BP2022 | SMI | 104°53.0.56'E | 5°16.14.48'S | 60 | 100/210/355 | 2022 | New site 2022 - P2 | DESA MAGOSARI KEC PAGELARAN KAB TANGGAMUS PROP LAMPUNG | HTI | SUM-LA-PRW-1126 | MARGOSARI | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Pringsewu | 6617988 | 2022-01-28 | 2022-01-28 | 68 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 172501123531 | 6.6 |  | 2022-03-22 |  |  | 2022-04-06 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:04:22: RFIN 03:04:22: PLN, CAN BE ACCELERATE TO APR 03:04:22-30:03:22: PLN 27:03:22-16:03:22: ME OG KWH KOSONG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-SS-MPR-1274 | 30734290031 | 071389109 | DESA KARANG SAMBUNG | BP2022 | TB | 104°44.16.08'E | 4°0.21.53'S | 50 | 35/190/255 | 2022 | New site 2022 - P2 | Karang Endah RT.007 RW.003 DesaKarang Endah, Kec. Semendawai Suku III, Kab. Ogan Komering Ulu Timur | HTI | SUM-SS-MPR-1274 | SEMENDAWAI_SUKU_III_KARANG_ENDAH | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617992 | 2022-01-28 | 2022-01-28 | 68 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 149300217417 | 6.6 |  | 2022-03-22 |  | 2022-04-02 | 2022-04-06 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:04:22: RFIN 03:04:22: PLN, CAN BE ACCELERATE TO APR 03:04:22-02:04:22: SRFIN 30:03:22: PLN 27:03:22-20:03:22: ME OG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-JA-KLT-0473 | 30734540031 | 100934109 | JALAN MESUJI | BP2022 | TB | 102°55.44.4'E | 1°2.36.53'S | 50 | 20/230/320 | 2022 | New site 2022 - P1 | Jl. Sedap Malam RT.009 RW.002, KEL/Desa Sri Agung, Kec. Batang Asam, Kab. Tanjung Jabung Barat. Provinsi Jambi | HTI | SUM-JA-KLT-0473 | SRI_AGUNG | COLO | TBG | West | SUMBAGSEL | Jambi | Kab. Tanjung Jabung Barat | 6617991 | 2022-01-28 | 2022-01-28 | 66 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 143600998992 | 6.6 |  | 2022-03-22 |  |  | 2022-04-04 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:04:22: RFIN 03:04:22: PLN, CAN BE ACCELERATE TO APR 30:03:22: PLN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22-09:02:22: READY TO DECLARE STO 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-LA-KTB-1146 | 30734370031 | 100502109 | LAMPUNG2G54 | BP2022 | TB | 104°46.55.92'E | 4°42.42.41'S | 50 | 20/180/290 | 2022 | New site 2022 - P2 | Desa Gedung Ketapang RT 05 RW 02, Kec. Sungkai Selatan, Kab Lampung Utara Prov. Lampung | HTI | SUM-LA-KTB-1146 | GEDUNG_KETAPANG | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Utara | 6617991 | 2022-01-28 | 2022-01-28 | 66 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 173001525124 | 6.6 |  | 2022-03-22 |  |  | 2022-04-04 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:04:22: RFIN 03:04:22: PLN, CAN BE ACCELERATE TO APR 03:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-SS-MRD-1007 | 30734090031 | 070047109 | PIUS3 | BP2022 | TB | 103°46.40.19'E | 4°28.31.69'S | 65 | 50/145/205 | 2022 | New site 2022 - P2 | Desa PengadonanKec. Kisam Hilir | HTI | SUM-SS-MRD-1007 | PULAU_KEMILING | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Se | 6617992 | 2022-01-28 | 2022-01-28 | 66 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 147700649236 | 6.6 |  | 2022-03-22 |  |  | 2022-04-04 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:04:22: RFIN 03:04:22: PLN, CAN BE ACCELERATE TO APR 03:04:22-30:03:22: PLN 27:03:22-16:03:22: ME OG KWH KOSONG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-LA-KTB-1147 | 30734320031 | 100631109 | BUNGA MAYANG 2 | BP2022 | TB | 104°50.11.47'E | 4°36.1.84'S | 50 | 95/250/315 | 2022 | New site 2022 - P2 | Desa Kota napal RT. 02 RW. 03 Kec. Bunga Mayang Kab. Lampung Utara | HTI | SUM-LA-KTB-1147 | KOTA_NAPAL | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Utara | 6617991 | 2022-01-28 | 2022-01-28 | 66 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 173001525132 | 6.6 |  | 2022-03-22 |  |  | 2022-04-04 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:04:22: RFIN 03:04:22: PLN, CAN BE ACCELERATE TO APR 03:04:22: ME OG & PERKUATAN 30:03:22-13:03:22: STRENGTENING PARALEL CME 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | SUM-LA-GDT-1132 | 30735470031 | 100087109 | KAMPUNG UMBUL KUNCI | BP2022 | TB | 105°13.38.03'E | 5°28.11.96'S | 60 | 145/200 | 2022 | New site 2022 - P2 | Jl. Kunci, Kel. Keteguhan, Kec. Teluk Betung Barat, Bandar Lampung.Kel. KeteguhanKec. Teluk Betung Selatan | HTI | SUM-LA-GDT-1132 | JL_UMBUL_KUNCI_KETEGUHAN | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Pesawaran | 6617991 | 2022-01-28 | 2022-01-28 | 70 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 171802788465 |  |  | 2022-03-22 |  |  | 2022-04-08 | W15-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 06:04:22-03:04:22: PLN, CAN BE ACCELERATE TO APR 03:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW TNP ALITA 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK B2S |  | JAW-JI-BKL-4331 | 30730460031 | 1654821003 | MODUNG_ALAS_KOKON | BP2022 | TB | 112°55.23.02'E | 7°10.45.95'S | 50 | 100/250/330 | 2022 | New site 2022 - P2 | Dusun Paser RT. - RW. - Desa Karang Anyar Kecamatan Modung Kabupaten Bangkalan | HTI | JAW-JI-BKL-4331 | MODUNG_ALAS_KOKON | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617949 | 2022-01-25 | 2022-01-28 | 70 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-01 | 517401350389 | 6.6 |  | 2022-03-21 |  |  | 2022-04-05 | W15-2022 |  |  | PRESITAC | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22: RFI, WAIT RFIN 30:03:22: POWER CONNECTION 27:03:22-20:03:22: SRFI 16:03:22: ERECTION 13:03:22-09:03:22: CURRING TIME 06:03:22-03:03:22: REBARRING OG 28:02:22-23:02:22: REKOM OG 20:02:22: REALISASI IW 16:02:22: IW CLEAR 13:02:22-04:02:22: VALIDASI RNP TNP OG, OK CANDICATE A&C, PRIORITY CANDIDATE A 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
NEW SPK |  | JAW-JB-BDG-4316 | 30739180031 | 123032109 | BDGN-101 | BP2022 | SKP | 107°33.59.11'E | 6°55.34.1'S | 30 | 90/210/330 | 2022 | New site 2022 - P2 | Jl. Bojong Raya No.48, Kel. Caringin RT.09 RW.01, Kec. Bandung Kulon, Kota Bandung Prov. Jawa Barat | HTI | JAW-JB-BDG-4316 | BANDUNG_KULON_CIBUNTU | COLO | TBG | Central | JABAR | Jawa Barat | Kota Bandung | 6617983 | 2022-01-28 | 2022-01-28 | 62 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-29 | W14-2022 | Mar-2022 | 2022-04-26 | W18-2022 | Apr-2022 | 2022-04-26 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 535556218987 |  |  | 2022-03-21 |  |  | 2022-03-31 | W14-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:03:22: RFIN 30:03:22-27:03:22: ME OG 23:03:22-13:03:22: PONDASI OG 09:02:22: MOBDEMOB 06:03:22: NEED REVIEW TNP 23:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK B2S |  | JAW-JI-BKL-4325 | 30730350031 | 1654771003 | MODUNG_SRABI_BARAT | BP2022 | TB | 113°1.52.32'E | 7°10.56.28'S | 50 | 20/190/250 | 2022 | New site 2022 - P2 | Dusun Blireng Rt. _ Rw. - Desa Srabi Timur Kecamatan Modung Kabupaten Bangkalan Provinsi Jawa Timur | HTI | JAW-JI-BKL-4325 | MODUNG_SRABI_BARAT | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617949 | 2022-01-25 | 2022-01-28 | 76 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-01 | MG |  |  | 2022-03-21 |  |  | 2022-04-11 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11:04:22: RFIN 10:04:22-03:04:22: RFI, WAIT RFIN 30:03:22-23:03:22: SRFI 20:03:22: SRFI, WAITING STO & PLN CONNECTION 13:03:22: ERECTION 09:03:22: CURRING TIME 06:03:22-03:03:22: REBARRING OG 28:02:22-23:02:22: REKOM OG 20:02:22: REALISASI IW 16:02:22: IW CLEAR 13:02:22-04:02:22: VALIDASI RNP TNP OG, OK ABC, PRIORITY B 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
NEW SPK B2S |  | JAW-JI-BKL-4327 | 30730600031 | 1654861003 | PEKADDAN_GALIS | BP2022 | TB | 112°57.10.22'E | 7°7.27.48'S | 50 | 70/170/290 | 2022 | New site 2022 - P1 | Dusun Bates RT. - RW. - Desa Pekadan Kecamatan Galis Kabupaten Bangkalan Provinsi Jawa Timur | HTI | JAW-JI-BKL-4327 | PEKADDAN_GALIS | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617949 | 2022-01-25 | 2022-01-28 | 76 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-01 | MG |  |  | 2022-03-21 |  |  | 2022-04-11 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11:04:22: RFIN 10:04:22-03:04:22: RFI, WAIT RFIN 30:03:22-27:03:22: SRFI 23:03:22-20:03:22: ERECTION 16:03:22-13:03:22: CURRING TIME 09:03:22: REBARRING 06:03:22-03:03:22: EXCAVATION OG 28:02:22-23:02:22: REKOM OG 20:02:22: REALISASI IW 16:02:22: IW CLEAR 13:02:22-04:02:22: VALIDASI RNP TNP OG, OK A&B, PRIORITY A 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
NEW SPK |  | SUM-LA-GNS-1139 | 30734470031 | 100278104 | MAJAPAHIT | BP2022 | SMI | 105°14.40.9'E | 4°59.28.2'S | 60 | 5/140/210 | 2022 | New site 2022 - P2 | Dusun V RT.03 RW.02 Kel. Mojopahit Kec. Punggur, Kab. Lampung Tengah Prov. Lampung | HTI | SUM-LA-GNS-1139 | MOJOPAHIT | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Tengah | 6617988 | 2022-01-28 | 2022-01-28 | 59 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 172801526265 | 6.6 |  | 2022-03-22 |  |  | 2022-03-28 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28:03:22: RFIN 27:03:22: PLN CONNECTION OG 23:03:22-20:03:22: ME OG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUL-SN-WNS-0977 | 30734240031 | 280173109 | TBG LOMPOE TEMPE | BP2022 | SKP | 119°53.17.16'E | 4°10.39.47'S | 60 | 10/180/250 | 2022 | New site 2022 - P2 | Dusun Lompoe RT 001 RW 004 Desa Tellulimpoe Kec. Mario Riowa Kab. Soppeng | HTI | SUL-SN-WNS-0977 | TELLULIMPOE_MARIORIAWA | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Soppeng | 6617983 | 2022-01-28 | 2022-01-28 | 61 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-17 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 325600251228 |  |  | 2022-03-21 |  | 2022-03-17 | 2022-03-30 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30:03:22: RFIN 27:03:22-17:03:22: SRFIN 16:03:22: SRFI 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUL-SN-WNS-0988 | 30734210031 | T002786 | HCPTSS-212369 | BP2022 | SKP | 119°51.21.35'E | 4°6.32.87'S | 60 | 150/240/330 | 2022 | New site 2022 - P2 | Jl. Poros Sidrap Km 28 No.3, Kampung Laulaweng Rt.02/002 Kel. Monorasalo, Kec. Marioriawa, Kab. Soppeng Prov. Sulawesi Selatan | HTI | SUL-SN-WNS-0988 | LARINGGI_MARIORIAWA | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Soppeng | 6617983 | 2022-01-28 | 2022-01-28 | 59 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-17 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 325600251244 |  |  | 2022-03-21 |  | 2022-03-17 | 2022-03-28 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28:03:22: RFIN 27:03:22-17:03:22: SRFIN 16:03:22: SRFI 13:03:22: ME OG 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUL-SN-PLP-1343 | 30734230031 | 280182109 | TBG LAMASI PANTAI | BP2022 | SKP | 120°13.15.24'E | 2°55.9.19'S | 50 | 0/150/270 | 2022 | New site 2022 - P2 | Dusun Lamasi Pantai desa Lamasi Pantai kec. Walenrang timur kab.Luwu Prop. Sulsel | HTI | SUL-SN-PLP-1343 | LAMASI_PANTAI_WALENRANG_TIMUR | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Luwu | 6617983 | 2022-01-28 | 2022-01-28 | 58 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-09 | W11-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 326101082237 | 6.6 |  | 2022-03-21 |  | 2022-03-09 | 2022-03-27 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:03:22: RFIN 27:03:22-13:03:22: PROCESS CONNECTION PLN TO PLN WILAYAH 09:03:22: SRFI, PLN CONNECTION 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
743 |  | JAW-JI-JBG-4167 | 30701590031 | 160479104 | KALIKEJAMBON | RORO JONGRANG 2021 [NEW] | SKP | 112°15.12.71'E | 7°29.39.66'S | 50 | 110/190/340 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Melati RT.01 RW.03 Ds. Kedunglosari Kec. Tembelang, Kab. Jombang Prov. Jawa Timur | HTI | JAW-JI-JBG-4167 | TEMBELANG KEDUNGLOSARI | COLO | TBG | East | JATIM | Jawa Timur | Kab. Jombang | 6617454 | 2021-08-09 |  | 77 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-26 | W44-2021 | Oct-2021 | 2021-10-26 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 514531761377 | 6.6 |  | 2021-10-04 |  | 2021-09-25 | 2021-10-25 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:10:21: RFIN 20:10:21-15:09:21: SRFI 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
NEW SPK |  | JAW-JI-BKL-4321 | 30734800031 | 160611104 | MODUNG | BP2022 | SMI | 112°56.24.72'E | 7°11.18.49'S | 70 | 0/100/300 | 2022 | New site 2022 - P2 | Desa Modung, Kampung Modung Temor Kec. Modung, Kab. Bangkalan Prov. Jawa Timur | HTI | JAW-JI-BKL-4321 | MODUNG_KWANYAR | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617988 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 515402569749 | 6.6 |  | 2022-03-21 |  | 2022-03-22 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22-22:03:22: SRFI 20:03:22-16:03:22: ME OG 13:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-KNR-4289 | 30734790031 | 160630104 | MARON | BP2022 | SMI | 112°3.25.2'E | 8°11.47.22'S | 70 | 105/215/290 | 2022 | New site 2022 - P2 | Desa Maron RT.03/RW.01, Kec. Kademangan, Kab. Blitar Prov. Jawa Timur | HTI | JAW-JI-KNR-4289 | KADEMANGAN_MARON | COLO | TBG | East | JATIM | Jawa Timur | Kab. Blitar | 6617988 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-16 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 514091940243 | 6.6 |  | 2022-03-21 |  | 2022-03-16 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22-16:03:22: SRFI 16:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUL-SN-WNS-0973 | 30730870031 | 2814422003 | IBS KAYANGAN SOPENG | BP2022 | TB | 119°53.14.35'E | 4°21.38.16'S | 60 | 40/170/280 | 2022 | New site 2022 - P1 | Jl. Kayangan, Kelurahan Lemba, Kecamatan Lalabata, Kabupaten Soppeng, Provinsi Sulawesi Selatan | HTI | SUL-SN-WNS-0973 | KELURAHAN_LEMBA_LALABATA | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Soppeng | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-08 | W11-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 325600251199 | 6.6 |  | 2022-03-21 |  | 2022-03-08 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION 20:03:22-13:03:22: PROSES CONNCET PLN & WAIT STO 09:03:22: SRFI, PLN CONNECTION 06:03:22-09:02:22: CME PREPARATION -> STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 02:02:22: NEED REVIEW TNP ALITA 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-KDR-4330 | 30737890031 | 162210109 | PONPES GONTOR 3 KEDIRI | BP2022 | SKP | 112°6.15.48'E | 7°49.8.98'S | 40 | 40/195/300 | 2022 | New site 2022 - P2 | Jl. Pondok Gg.1, Desa Besuk Rt.006 Rw.003 Kec.Gurah, Kab.Kediri Prov.Jawa Timur | HTI | JAW-JI-KDR-4330 | GURAH_BESUK | COLO | TBG | East | JATIM | Jawa Timur | Kab. Kediri | 6617983 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-16 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 514101105388 | 6.6 |  | 2022-03-21 |  | 2022-03-16 | 2022-03-24 | W13-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 16:03:22-13:03:22: PARALEL STRENGTENING 09:03:22: PONDASI OG 06:03:22: NEED REVIEW CIVIL 23:02:22-20:02:22: NEED REVIEW TNP 16:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-KDR-4332 | 30736010031 | 162172109 | BAGAWAN TABARI KEDIRI | BP2022 | SKP | 112°5.13.2'E | 7°47.24.0'S | 40 | 105/225/295 | 2022 | New site 2022 - P2 | Jl. Teratai RT.002 RW.002 Ds. Kambingan Kec. Pagu, Kab. Kediri Prov. Jawa Timur | HTI | JAW-JI-KDR-4332 | PAGU_KAMBINGAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Kediri | 6617983 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 514011188660 | 6.6 |  | 2022-03-21 |  |  | 2022-03-24 | W13-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 16:03:22-13:03:22: PARALEL STRENGTENING 09:03:22: PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-KDR-4350 | 30734960031 | 160414109 | MANISRENGGO KOTA KEDIRI | BP2022 | TB | 112°0.46.19'E | 7°51.43.09'S | 40 | 65/145/300 | 2022 | New site 2022 - P2 | Desa Banjarejo Dusun Paras RT.001 RW.001 Kec.Ngadiluwih, Kab.Kediri Prov.Jawa Timur | HTI | JAW-JI-KDR-4350 | PESANTREN_TOSAREN | COLO | TBG | East | JATIM | Jawa Timur | Kota Kediri | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 515402569557 | 6.6 |  | 2022-03-21 |  |  | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 16:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-NJK-4255 | 30735060031 | 162128109 | ARUM DALU | BP2022 | SKP | 111°52.15.6'E | 7°35.56.87'S | 40 | 90/190/260 | 2022 | New site 2022 - P2 | Desa Buduran RT.01 RW.05 Kec.Bagor, Kab.Nganjuk Prov.Jawa Timur | HTI | JAW-JI-NJK-4255 | BAGOR_BUDURAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Nganjuk | 6617983 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 514601947036 | 6.6 |  | 2022-03-21 |  |  | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 16:03:22: ME OG 13:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-KDR-4333 | 30734940031 | 163629126 | PAMONGAN MOJO | BP2022 | TB | 111°53.13.2'E | 7°53.45.96'S | 40 | 50/125/275 | 2022 | New site 2022 - P2 | Desa Pamongan Dusun Pamongan RT.010 RW.04 Kec.Mojo, Kab.Kediri Prov.Jawa Timur | HTI | JAW-JI-KDR-4333 | MOJO_PAMONGAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Kediri | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-16 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 514111266188 | 6.6 |  | 2022-03-21 |  | 2022-03-16 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 15:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-PNG-4309 | 30734910031 | 1648232007 | IBS BADEGAN | BP2022 | TB | 111°21.53.93'E | 7°52.16.18'S | 40 | 160/260/340 | 2022 | New site 2022 - P2 | Desa Bandar Alim Dusun Bandar Alim Lor RT.01 RW.01 Kec.Badegan, Kab.Ponorogo Prov.Jawa Timur | HTI | JAW-JI-PNG-4309 | BADEGAN_BANDARALIM | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ponorogo | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 514601947036 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-GSK-4339 | 30734710031 | TBG06_EJ051 | BENJENG BLANDONG | BP2022 | PMS | 112°27.25.06'E | 7°17.58.31'S | 40 | 70/235/325 | 2022 | New site 2022 - P2 | Desa Banjar Agung Dusun Banjar Melati RT.03 RW.01 Kec.Balongpanggang, Kab.Gresik Prov.Jawa Timur | HTI | JAW-JI-GSK-4339 | BALONGPANGGANG_WOTANSARI | COLO | TBG | East | JATIM | Jawa Timur | Kab. Gresik | 6617982 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 511220910328 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-LMG-4305 | 30734920031 | 164016109 | DINOYODEKET2 | BP2022 | TB | 112°26.51.36'E | 7°5.17.12'S | 40 | 0/100/200 | 2022 | New site 2022 - P2 | Desa Dinoyo, Keputran RT 11 RW 03 Kec. Deket, Kab. Lamongan Prov. Jawa Timur | HTI | JAW-JI-LMG-4305 | DEKET_DINOYO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Lamongan | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518031823113 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-LMG-4297 | 30734780031 | 161854109 | REJOSARI | BP2022 | SKP | 112°27.14.4'E | 7°6.31.03'S | 40 | 65/90/295 | 2022 | New site 2022 - P2 | Desa Sidobinangun Dusun Sidobinangun RT.01 RW.01 Kec.Deket, Kab.Lamongan Prov.Jawa Timur | HTI | JAW-JI-LMG-4297 | DEKET_SIDOBINANGUN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Lamongan | 6617985 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518031823105 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-GSK-4340 | 30734700031 | TBG06_EJ047 | BENJENG 2 | BP2022 | PMS | 112°30.36.68'E | 7°10.59.41'S | 40 | 0/120/240 | 2022 | New site 2022 - P2 | Jl. Raya Benjeng, Kec.Benjeng, Kab.Gresik Prov.Jawa Timur | HTI | JAW-JI-GSK-4340 | DUDUKSAMPEYAN_SUMENGKO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Gresik | 6617982 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 511201218562 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-BJN-4296 | 30735090031 | 162146109 | NGANTRU | BP2022 | SKP | 111°40.55.02'E | 7°11.13.24'S | 40 | 45/160/295 | 2022 | New site 2022 - P2 | Desa Mojodelik Dusun Samben RT.01 RW.01 Kec. Gayam, Kab.Bojonegoro Prov.Jawa Timur | HTI | JAW-JI-BJN-4296 | GAYAM_MOJODELIK | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6617983 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518050996344 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-LMG-4301 | 30734950031 | 163590109 | KARANGBINANGUN | BP2022 | TB | 112°28.42.89'E | 7°1.36.88'S | 40 | 15/80/200 | 2022 | New site 2022 - P2 | Jl. Pendowo Limo, Desa Sambopinggir RT.03 RW.01 Kec.Karangbinangun, Kab.Lamongan Prov.Jawa Timur | HTI | JAW-JI-LMG-4301 | KARANGBINANGUN_SAMBOPINGGIR | COLO | TBG | East | JATIM | Jawa Timur | Kab. Lamongan | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518031823121 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-BJN-4307 | 30734970031 | 160059109 | DS TAMBAK MERAH | BP2022 | TB | 111°40.0.41'E | 7°6.56.7'S | 70 | 90/230/320 | 2022 | New site 2022 - P2 | Desa Tambak Merak RT.03/RW.01 Kec. Kasiman, Kab. Bojonegoro Prov. Jawa Timur | HTI | JAW-JI-BJN-4307 | KASIMAN_TAMBAKMERAK | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518050996351 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-BJN-4302 | 30734840031 | 162618126 | POM PADANGAN/PASAR KLOTOK | BP2022 | TB | 111°38.9.38'E | 7°9.42.77'S | 50 | 20/110/285 | 2022 | New site 2022 - P2 | Desa Banjar Dowo, Kel. Banjar Rejo Rt. 08 Rw. 02 Kec. Padangan, Kab. Bojonegoro Prov. Jawa Timur | HTI | JAW-JI-BJN-4302 | PADANGAN_BANJARJO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518050996336 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-PNG-4304 | 30735050031 | 164121107 | GOLAN SUKOREJO | BP2022 | SKP | 111°24.18.94'E | 7°51.3.82'S | 40 | 0/90/250 | 2022 | New site 2022 - P2 | Desa Kauman Dukuh Kepek RT.02 RW.01 Kec.Kauman, Kab.Ponorogo Prov.Jawa Timur | HTI | JAW-JI-PNG-4304 | SAMPUNG_KAUMAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ponorogo | 6617983 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 514011188660 | 6.6 |  | 2022-03-21 |  |  | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-MJY-4144 | 30734830031 | 160827104 | MANISREJO | BP2022 | SMI | 111°35.0.38'E | 7°40.3.04'S | 40 | 10/160/265 | 2022 | New site 2022 - P2 | Jl. Raya Dungus, Desa Karangrejo RT.12 RW.02 Kec.Wungu, Kab.Madiun Prov.Jawa Timur | HTI | JAW-JI-MJY-4144 | WUNGU_KARANGREJO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Madiun | 6617988 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 514011188802 | 6.6 |  | 2022-03-21 |  |  | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-BJN-4304 | 30735100031 | 1644971004 | KEDUNGBONDO_BJO | BP2022 | SKP | 111°57.7.2'E | 7°10.12.76'S | 50 | 75/160/240 | 2022 | New site 2022 - P2 | Desa Prambatan RT 02 RW 01 Kec. Balen, Kab. Bojonegoro Prov. Jawa Timur | HTI | JAW-JI-BJN-4304 | BALEN_PRAMBATAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6617983 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518013692806 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: ME OG 13:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-JBG-5133 | 30734980031 | 164038109 | API_PLOSO JOMBANG 2 | BP2022 | TB | 112°14.12.52'E | 7°26.16.69'S | 40 | 25/200/290 | 2022 | New site 2022 - P2 | Jl. Karang Tanjung, Desa Pagertanjung Kec. Ploso, Kab. Jombang Prov. Jawa Timur | HTI | JAW-JI-JBG-5133 | PLOSO_PAGERTANJUNG | COLO | TBG | East | JATIM | Jawa Timur | Kab. Jombang | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518080353599 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: ME OG 13:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-BJN-4301 | 30735110031 | 162208109 | RSUD BARU BOJONEGORO | BP2022 | SKP | 111°53.54.17'E | 7°9.33.23'S | 40 | 20/110/215 | 2022 | New site 2022 - P2 | Jl. Veteran, Kel.Kadipaten RT.015 RW.01 Kec.Bojonegoro, Kab.Bojonegoro Prov.Jawa Timur | HTI | JAW-JI-BJN-4301 | BOJONEGORO_SUKOREJO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6617983 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518013692814 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22: ME OG, PARALEL STRENGTENING 16:03:22-09:03:22: PONDASI OG PARALEL STRENGTENING 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-TBN-4072 | 30734810031 | 160945104 | TEMANDANG | BP2022 | SMI | 111°56.49.2'E | 6°51.58.03'S | 50 | 120/190/280 | 2022 | New site 2022 - P2 | Desa Pongpongan Kec.Merakurak, Kab.Tuban Prov.Jawa Timur | HTI | JAW-JI-TBN-4072 | MERAKURAK_PONGPONGAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Tuban | 6617988 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518023374359 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22: ME OG 16:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-BJN-4298 | 30734930031 | 160418109 | NGANTRU NGASEM | BP2022 | TB | 111°45.35.35'E | 7°13.9.19'S | 70 | 10/175/270 | 2022 | New site 2022 - P2 | Desa Ngantru Dsn. Ngantru RT.21 RW.02 Kec.Ngasem, Kab.Bojonegoro Prov.Jawa Timur | HTI | JAW-JI-BJN-4298 | NGASEM_NGANTRU | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518013692822 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22: ME OG 16:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-BJN-4303 | 30734990031 | 160534109 | BULU SUGIHWARAS TBG | BP2022 | TB | 111°58.33.6'E | 7°19.55.2'S | 70 | 5/150/250 | 2022 | New site 2022 - P2 | Jl. Raya Bulu, Ds. Pamunggalan Kec. Sugihwaras, Kab. Bojonegoro Prov. Jawa Timur | HTI | JAW-JI-BJN-4303 | SUGIHWARAS_PANUNGGALAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6617991 | 2022-01-28 | 2022-01-28 | 55 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 518080353599 | 6.6 |  | 2022-03-21 |  | 2022-03-21 | 2022-03-24 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:03:22: RFIN 23:03:22: PLN CONNECTION OG 20:03:22: ME OG 16:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUL-SN-SDR-1285 | 30734120031 | 280962109 | TBG BAPANGI | BP2022 | TB | 119°50.3.7'E | 4°5.7.4'S | 50 | 0/120/260 | 2022 | New site 2022 - P2 | Dusun Bingkulu Rt. 001 Rw. 001 Desa Bapangi Kec. Panca Lautang Kab.Sidenreng Rappang Prov. Sulawesi Selatan | HTI | SUL-SN-SDR-1285 | BAPANGI_PANCA_LAUTAN | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Sidenreng Rappang | 6617991 | 2022-01-28 | 2022-01-28 | 54 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 325500309628 |  |  | 2022-03-21 |  |  | 2022-03-23 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23:03:22: RFIN 22:03:22-13:03:22: PARALEL STRENGTENING 09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JB-NPH-4377 | 30734160031 | 1271662023 | IBS IN20_WJ_0230 | BP2022 | TB | 107°21.27.68'E | 6°49.56.28'S | 40 | 10/70/115 | 2022 | New site 2022 - P1 | Kp. Warung Jambe RT00 RW015, Kel Rajamandala Kulon, Kec. Cipatat Kabupaten Bandung Barat | HTI | JAW-JB-NPH-4377 | CIPATAT_RAJAMANDALAKULON | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Bandung Barat | 6617991 | 2022-01-28 | 2022-01-28 | 54 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-25 | W13-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 535950926587 | 6.6 |  | 2022-03-21 |  | 2022-03-20 | 2022-03-23 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23:03:22: RFIN 20:03:22: SRFIN 20:03:22: ME OG, PARALEL STRENGTENING 16:03:22-13:03:22: PARALEL STRENGTENING 09:03:22: PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JB-SMD-4366 | 30734340031 | 1270562007 | IBS TRUNAMANGGALA | BP2022 | TB | 107°55.19.2'E | 6°48.26.68'S | 40 | 70/180/275 | 2022 | New site 2022 - P1 | Desa Trunamanggala Dusun Ciulur RT.01 RW.04 Kec. Cimalaka, Kab. Sumedang Prov. Jawa Barat | HTI | JAW-JB-SMD-4366 | TRUNAMANGGALA | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Sumedang | 6617991 | 2022-01-28 | 2022-01-28 | 54 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-25 | W13-2022 | Mar-2022 | 2022-03-25 | W13-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 535113438378 | 6.6 |  | 2022-03-21 |  | 2022-03-20 | 2022-03-23 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23:03:22: RFIN 20:03:22: SRFIN 20:03:22: ME OG, PARALEL STRENGTENING 16:03:22-13:03:22: PARALEL STRENGTENING 09:03:22: PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUL-SN-SDR-1280 | 30734010031 | T002263 | RAPPANG | BP2022 | SKP | 119°49.2.42'E | 3°50.54.82'S | 50 | 80/250/350 | 2022 | New site 2022 - P2 | Jl. Harapan Rappang Desa Rappang Kec. Panca Rijang Kab. Sidrap | HTI | SUL-SN-SDR-1280 | KELURAHAN_RAPPANG_PANCA_RIJANG | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Sidenreng Rappang | 6617983 | 2022-01-28 | 2022-01-28 | 53 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 325300489255 | 6.6 |  | 2022-03-21 |  |  | 2022-03-22 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:03:22: RFIN 20:03:22: ME OG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JB-SOR-4415 | 30734650031 | 120407109 | BIRU - STO MAJALAYA | BP2022 | MSI | 107°44.3.48'E | 7°3.59.9'S | 40 | 50/210/355 | 2022 | New site 2022 - P2 | JL. Waru Setanggal Kp. Sukamandi RT. 01/12 Ds. Paduluan Kec. Majalaya Kab. Bandung | HTI | JAW-JB-SOR-4415 | PADAULUN | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Bandung | 6617981 | 2022-01-28 | 2022-01-28 | 53 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-16 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 535312338572 | 6.6 |  | 2022-03-21 |  | 2022-03-16 | 2022-03-22 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:03:22: RFIN 20:02:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JB-CMH-4322 | 30734030031 | 122413104 | CISANGKAN TIMUR | BP2022 | SKP | 107°31.42.89'E | 6°52.28.34'S | 30 | 90/210/330 | 2022 | New site 2022 - P2 | Jl. Lestari RT 8 RW 019, Kel. Padasuka Kec. Cimahi Tengah, Kota Cimahi Prov. Jawa Barat | HTI | JAW-JB-CMH-4322 | VELODROME_CIMAHI_PADASUKA | COLO | TBG | Central | JABAR | Jawa Barat | Kota Cimahi | 6617983 | 2022-01-28 | 2022-01-28 | 53 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-16 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 535812260942 | 6.6 |  | 2022-03-21 |  | 2022-03-16 | 2022-03-22 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:03:22: RFIN 20:02:22-16:03:22: SRFI, PLN CONNECTION OG & WAIT STO 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JB-NPH-4385 | 30734020031 | 120320104 | CINENGAH - GIRIMUKTI | BP2022 | SKP | 107°20.2.51'E | 6°57.58.03'S | 70 | 210/280/345 | 2022 | New site 2022 - P2 | Jl. Gunung Karang, Desa Karangsari RT.03 RW.05 Kec. Cipongkor, Kab. Bandung Barat Prov. Jawa Barat | HTI | JAW-JB-NPH-4385 | CIPONGKOR_KARANGSARI | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Bandung Barat | 6617983 | 2022-01-28 | 2022-01-28 | 53 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-16 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 535950926520 | 6.6 |  | 2022-03-21 |  | 2022-03-16 | 2022-03-22 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:03:22: RFIN 20:02:22-16:03:22: SRFI, PLN CONNECTION OG & WAIT STO 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JB-SOR-4416 | 30735290031 | 125426126 | RAWABOGO-CIWIDEY | BP2022 | TB | 107°26.23.53'E | 7°4.33.06'S | 40 | 145/240/310 | 2022 | New site 2022 - P2 | Desa Rawabogo Kp. Cimapag RT.02 RW.02, Kec. Ciwidey, Kab. Bandung Prov. Jawa Barat | HTI | JAW-JB-SOR-4416 | CIWIDEY_RAWABOGO | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Bandung | 6617991 | 2022-01-28 | 2022-01-28 | 53 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-16 | W12-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 535322209600 | 6.6 |  | 2022-03-21 |  | 2022-03-16 | 2022-03-22 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:03:22: RFIN 20:02:22-16:03:22: SRFI, PLN CONNECTION OG & WAIT STO 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO DECLARE STO 13:02:22: NEED REVIEW POWER 09:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JB-CMS-4298 | 30734420031 | 125601109 | BO-CILEUNGSIR-RANCAH | BP2022 | TB | 108°29.9.6'E | 7°12.37.08'S | 40 | 30/130/265 | 2022 | New site 2022 - P1 | Desa Cileungsir, Pangrumasan RT.11 RW.11, Kec. Rancah, Kab. Ciamis Prov. Jawa Barat | HTI | JAW-JB-CMS-4298 | CILEUNGSIR | COLO | TBG | Central | JABAR | Jawa Barat | Kab. Ciamis | 6617991 | 2022-01-28 | 2022-01-28 | 45 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-02 | 2022-02-03 | 532217825759 | 6.6 |  | 2022-03-21 |  |  | 2022-03-14 | W12-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14:03:22: RFIN 13:03:22: ME OG 09:03:22: PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK B2S |  | JAW-JI-BKL-4334 | 30730400031 | 1654791003 | TRAGAH_ALANG-ALANG | BP2022 | TB | 112°50.25.87'E | 7°7.42.74'S | 50 | 30/120/220 | 2022 | New site 2022 - P1 | Dsn Masjid RT - RW - Desa Bajeman Kec Tragah Kab Bangkalan | HTI | JAW-JI-BKL-4334 | TRAGAH_ALANG-ALANG | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617949 | 2022-01-25 | 2022-01-28 | 71 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-01 | MG |  |  | 2022-03-21 |  |  | 2022-04-06 | W15-2022 |  |  | SITAC | 38.RFI | 21.RFI | 38.RFI | 06:04:22: RFIN 03:04:22: RFI, WAIT RFIN 30:03:22: POWER CONNECTION 27:03:22-23:03:22: ERECTION 20:03:22: CURRING TIME 16:03:22-13:03:22: REBARRING 09:03:22: EXCAVATION 06:03:22: IW OG 06:03:22-28:02:22: VALIDASI RNP TNP, REJECT WARGA 23:02:22-20:02:22: IW OG 18:02:22: VALIDASI RNP TNP, IW FAILED 16:02:22-07:02:22: VALIDASI RNP TNP OG 06:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
753 |  | JAW-JI-TLG-4245 | 30700990031 | 1649832007 | IBS WILIS TULUNGAGUNG | RORO JONGRANG 2021 [NEW] | TB | 111°51.42.52'E | 8°2.54.02'S | 30 | 130/230/340 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Willis Gang 3, RT. 02 RW. 03, Kelurahan Kalangbret, Kecamatan Kauman, Kabupaten Tulungagung, Provinsi Jawa Timur | HTI | JAW-JI-TLG-4245 | KAUMAN KALANGBRET | COLO | TBG | East | JATIM | Jawa Timur | Kab. Tulungagung | 6617471 | 2021-08-12 |  | 69 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 514032193553 | 6.6 |  | 2021-10-04 |  |  | 2021-10-20 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-29:09:21: SRFI 22:09:21: ME OG 19:09:21:15:09:21: 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
NEW SPK B2S |  | JAW-JB-GRT-4257 | 30730220031 | 1276221003 | CINTARASA | BP2022 | TB | 107°51.43.56'E | 7°13.20.75'S | 40 | 125/250/310 | 2022 | New site 2022 - P1 | kp. Babakan jati Rt 002 Rw 001 Desa Cintarayat kecamatan Samarang Kabupaten Garut Provinsi Jawa Barat | HTI | JAW-JB-GRT-4257 | CINTARASA | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Garut | 6617949 | 2022-01-25 | 2022-01-28 | 66 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | 2022-04-03 | W15-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-02 | 2022-03-18 | 532931866603 | 6.6 |  | 2022-03-21 |  |  | 2022-04-01 | W14-2022 |  |  | SITAC | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01:04:22: RFIN 30:03:22-27:03:22: ME OG 23:03:22-20:03:22: BACKFILL 16:03:22: POURING 13:03:22-09:03:22: EXCAVATION 06:03:22: PREPARE CME 28:02:22: REKOM OG 23:02:22-20:02:22: VALIDASI RNP TNP OG 16:02:22: REHUNTING 13:02:22-05:02:22: IW OG 02:02:22: UNDER TNP REVIEW 30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
NEW SPK B2S |  | JAW-JI-BKL-4328 | 30730590031 | 1654851003 | GALIS_SADAH | BP2022 | TB | 112°54.57.56'E | 7°3.38.17'S | 50 | 70/180/300 | 2022 | New site 2022 - P2 | Dusun Alas Durin RT_ / Rw_ Desa Banjar Kecamatan Galis | HTI | JAW-JI-BKL-4328 | GALIS_SADAH | B2S | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617949 | 2022-01-25 | 2022-01-28 | 85 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-25 | 2022-03-01 | MG |  |  | 2022-03-21 |  |  | 2022-04-20 | W17-2022 |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 20:04:22: RFIN 17:04:22-17:04:22-10:04:22: RFI, WAIT RFIN 06:04:22-30:03:22: ERECTION 27:03:22: CURRING TIME 23:03:22: REBARRING 20:03:22-09:03:22: EXCAVATION 06:03:22: REKOM OG 28:02:22-04:02:22: VALIDASI RNP TNP OG, PRIORITY CANDIDATE A 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | apr
89 COLO |  | NUS-NB-TJN-5377 | 30741300031 | 180423109 | PEMENANG BARAT PEMENANG 2 | BP2022 | TB | 116°5.3.48'E | 8°24.11.88'S | 60 | 60/200/300 | 2022 | Newsite 2022 - B2 | Dusun Teluk Kombal RT 02/03 Ds. Pemenang Barat Kec. Pemenang Kab. Lombok Utara | HTI | NUS-NB-TJN-5377 | SENGGIGI_PEMENANG_BARAT | COLO | TBG | East | BALINUSRA | Nusa Tenggara Barat | Kab. Lombok Utara | 6618079 | 2022-03-11 | 2022-03-11 | 24 | < 30 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 441301097844 | 6.6 |  | 2022-03-21 |  |  | 2022-04-04 | W15-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:04:22: RFIN 03:04:22: ME OG 30:03:22: PONDASI OG 27:03:22-23:03:22: CME PREPARATION 20:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
700 |  | SUM-SU-LBP-2249 | 30701440031 | 020255104 | PS_7_BTG_KUIS | RORO JONGRANG 2021 [NEW] | SMI | 98°47.9.82'E | 3°36.32.83'N | 40 | 80/240/340 | 2021 | RORO JONGRANG 2021 [NEW] | Gang Sejahtera Utama Desa Sei Rotan Kecamatan Percut Sei Tuan, Kab. Deli Serdang, Prov. Sumatera Utara | HTI | SUM-SU-LBP-2249 | SAMBIREJO_TIMUR_MEDAN_BATANGKUIS | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617453 | 2021-08-09 |  | 83 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-19 | W43-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 128050013157 | 6.6 |  | 2021-10-04 |  |  | 2021-10-31 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:10:21: RFI, NEED RFIN 26:10:21 - 24:10:21-22:10:21: WAITING KWH, PLAN CONNECT TGL 27 20:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: PONDASI OG 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
NEW SPK |  | JAW-JI-BKL-4330 | 30728110031 | 1654741003 | PATENGTENG_MODUNG | BP2022 | TB | 112°58.4.01'E | 7°9.48.92'S | 50 | 85/200/310 | 2022 | New site 2022 - P2 | Dsn.Balet Rt. Rw. Desa Patengteng Kec.Modung Kab.Bangkalan Provinsi Jawa Timur | HTI | JAW-JI-BKL-4330 | PATENGTENG_MODUNG | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bangkalan | 6617996 | 2022-01-31 | 2022-01-31 | 65 | 61 - 90 days | 2022-03-02 | W10-2022 | Mar-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-02 | 2022-03-18 | MG |  |  | 2022-03-21 |  |  | 2022-04-06 | W15-2022 |  |  | STIP RELEASED, COLO RASA B2S | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:04:22: RFIN 06:04:22-30:03:22: POWER CONNECTION 27:03:22-20:03:22: ERECTION OG 16:03:22: REBARRING 13:03:22-09:03:22: EXCAVATION 23:02:22-06:02:22: REKOM OG 31:01:22: SPK RELEASED | apr
NEW SPK |  | JAW-JI-TLG-4251 | 30735020031 | 162226109 | PP. AL KAMAL | BP2022 | SKP | 112°5.29.62'E | 8°7.57.36'S | 40 | 180/270/320 | 2022 | New site 2022 - P2 | Desa Blimbing Dusun Blimbing, Rt.002 Rw.006 Kec.Rejotangan, Kab.Tulungagung Prov.Jawa Timur | HTI | JAW-JI-TLG-4251 | REJOTANGAN_BLIMBING | COLO | TBG | East | JATIM | Jawa Timur | Kab. Tulungagung | 6617983 | 2022-01-28 | 2022-01-28 | 67 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-16 | W12-2022 | Mar-2022 | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | 514041726864 | 6.6 |  | 2022-03-21 |  | 2022-03-16 | 2022-04-05 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05:04:22: RFIN 03:04:22-16:03:22: SRFI 16:03:22-13:03:22: PARALEL STRENGTENING 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK B2S |  | JAW-JB-GRT-4268 | 30730410031 | 1276231003 | SITUGEDE | BP2022 | TB | 107°58.16.47'E | 7°12.35.93'S | 50 | 30/145/290 | 2022 | New site 2022 - P2 | Kp. Nangewer RT 001 RW 005 Desa Situgede Kecamatan Karangpawitan Kabupaten Garut Provinsi Jawa Barat | HTI | JAW-JB-GRT-4268 | SITUGEDE | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Garut | 6617949 | 2022-01-25 | 2022-01-28 | 51 | 31 - 60 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-03-17 | W12-2022 | Mar-2022 | 2022-03-17 | W12-2022 | Mar-2022 | MW | 2022-02-25 | 2022-03-10 | 532861294529 | 6.6 |  | 2022-03-21 |  |  | 2022-03-17 | W12-2022 |  |  | SITAC | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:03:22: RFIN 16:03:22-09:03:22: ERECTION 06:03:22: PREPARE ERECTION 01:03:22: CURRING TIME 23:02:22-20:02:22: EXCAVATION OG 16:02:22: RFC, MOB DEMOB 13:02:22: REKOM OG 09:02:22: IW OG 07:02:22: TNP REVOEW OG CANDIDATE BARU, CANDIATE SEBELUMNYA REJECT WARGA 06:02:22-05:02:22: IW OG 02:02:22: UNDER TNP REVIEW 30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK B2S |  | JAW-JB-CJR-4341 | 30730640031 | 1276251003 | SUKABAKTI | BP2022 | TB | 107°21.22.04'E | 7°17.23.16'S | 50 | 55/225/340 | 2022 | New site 2022 - P1 | Kp. Situ Randu RT.01 RW.06 Desa Sukabakti Kec. Naringgul Kab. Cianjur | HTI | JAW-JB-CJR-4341 | SUKABAKTI | B2S | TBG | Central | JABAR | Jawa Barat | Kab. Cianjur | 6617949 | 2022-01-25 | 2022-01-28 | 48 | 31 - 60 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-03-15 | W12-2022 | Mar-2022 | 2022-03-15 | W12-2022 | Mar-2022 | MW | 2022-02-25 | 2022-03-10 | 536911877238 | 6.6 |  | 2022-03-21 |  |  | 2022-03-14 | W12-2022 |  |  | SITAC | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14:03:22: RFIN 13:03:22-09:03:22: ERECTION 06:03:22: ERECTION OG 01:03:22: POURING OG 23:02:22-20:02:22: EXCAVATION OG 16:02:22: RFC, MOB DEMOB 13:02:22: REKOM OG 09:02:22-07:02:22: IW CLEAR, PARALALE REQ SOIL TEST 06:02:22-05:02:22: IW OG 02:02:22: UNDER TNP REVIEW 30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
|  | SUM-SU-TRT-2222 | 30738940031 | 020076109 | POHAN EX SC-TR5213A | BP2022 | TB | 98°58.57.07'E | 2°13.25.79'N | 42 | 40/190/300 | 2022 | New site 2022 - P1 | Jl. SMA Negeri 2 Siborong Borong, Dus. Lumban, Silintong I, Des. Pohan Tonga, Kec. Siborong, Borong, | HTI | SUM-SU-TRT-2222 | SIBORONGBORONG_TAPUT | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Tapanuli Utara | 6618055 | 2022-02-23 | 2022-03-01 | 20 | < 30 days | 2022-03-25 | W13-2022 | Mar-2022 | TBD | TBD | TBD | 2022-03-18 | W12-2022 | Mar-2022 | 2022-03-18 | W12-2022 | Mar-2022 | MW | 2022-03-01 | 2022-03-02 | 123120572500 |  |  | 2022-03-11 |  |  | 2022-03-15 | W12-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:03:22: RFIN 13:03:22-08:03:22: SRFI 06:03:22: PONDASI OG 02:03:22: PREPARE CME 01:03:22: SPK RECEIVED
|  | SUM-SU-PRR-2221 | 30738950031 | 022303123 | PANGURURAN SAMOSIR | BP2022 | TB | 98°43.11.71'E | 2°36.42.77'N | 50 | 50/160/310 | 2022 | New site 2022 - P1 | Jl. Onan Tungkup Dusun II, Kab. Samosir, Prov. Sumatera Utara | HTI | SUM-SU-PRR-2221 | PANGURURAN_SAMOSIR | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Samosir | 6618055 | 2022-02-23 | 2022-03-01 | 20 | < 30 days | 2022-03-25 | W13-2022 | Mar-2022 | TBD | TBD | TBD | 2022-03-18 | W12-2022 | Mar-2022 | 2022-03-18 | W12-2022 | Mar-2022 | MW | 2022-03-01 | 2022-03-02 |  |  |  | 2022-03-11 |  |  | 2022-03-15 | W12-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:03:22: RFIN 13:03:22: SRFI, PLN CONNECTION 09:03:22: PONDASI OG 06:03:22: MOBILIZATION TO SAMOSIR ISLAND, PLAN START CME 7 MAR 02:03:22: PREPARE CME 01:03:22: SPK RECEIVED
|  | JAW-JK-KYB-0297 | 30739170031 | 110488109 | KOMPLEKKAVILINGPOLRIMW | NEW COLO | SKP | 106°49.3.45'E | 6°18.56.03'S | 30 | 90/210/330 |  |  | Jl. Paso No.40, Kel. Ragunan RT.011 RW.07, Kec. Pasar Minggu, Kota Jakarta Selatan Prov. DKI Jakarta | EID | JAW-JK-KYB-0297 | JALAN PASO BARU | COLO | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Selatan | 6618059 | 2022-02-25 | 2022-02-25 | 26 | < 30 days | TBD | TBD | TBD | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-03-09 | 2022-03-14 |  | 6.6 |  | 2022-03-09 |  |  | 2022-03-23 | W13-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23:03:22: RFIN 20:03:22: PONDASI OG 20:03:22-13:03:22: WAIT PSB 09:03:22: STO DECLARE 06:03:22: NEED REVIEW CIVIL 28:02:22: ESR REVIEW 25:02:22: SPK RELEASED
NEW SPK |  | JAW-JB-SBM-2450 | 30735510031 | 120651104 | GUNUNG PADANG | BP2022 | SKP | 107°1.26.26'E | 6°56.58.63'S | 72 | 135/280/350 | 2022 | New site 2022 - P1 | Desa Cireunghas Kp. Nagrok , Kec. Cireunghas, Kab. Sukabumi Prov. Jawa Barat | EID | JAW-JB-SBM-2450 | GUNUNG_PADANG | COLO | TBG | Jabodetabek | JABODETABEK | Jawa Barat | Kab. Sukabumi | 6617984 | 2022-01-28 | 2022-01-28 | 61 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-17 | 536511200036 | 10.6 |  | 2022-03-09 |  |  | 2022-03-30 | W14-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30:03:22: RFIN 27:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22-13:02:22: NEED REVIEW POWER EID 09:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JB-SBM-2452 | 30735490031 | 122282109 | JALAN KERAMAT SUKALARANG | BP2022 | SKP | 107°0.24.98'E | 6°52.2.1'S | 60 | 60/150/240 | 2022 | New site 2022 - P2 | Desa Sukalarang Kp. Karamat RT.003 RW.002, Kec. Sukalarang, Kab. Sukabumi Prov. Jawa Barat | EID | JAW-JB-SBM-2452 | JALAN_KERAMAT_SUKALARANG | COLO | TBG | Jabodetabek | JABODETABEK | Jawa Barat | Kab. Sukabumi | 6617984 | 2022-01-28 | 2022-01-28 | 61 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-17 | 536511200028 | 10.6 |  | 2022-03-09 |  |  | 2022-03-30 | W14-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30:03:22: RFIN 27:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22-13:02:22: NEED REVIEW POWER EID 09:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-BT-RKB-0591 | 30734680031 | 130219104 | CILEBANG | BP2022 | SMI | 106°17.15.07'E | 6°39.29.45'S | 72 | 110/210/330 | 2022 | New site 2022 - P2 | Jl. Gunung Bongkok Cilebang, Desa Cilebang RT.02 RW.02 Kec. Sobang, Kab. Lebak Prov. Banten | EID | JAW-BT-RKB-0591 | SUKAJAYA_SOBANG | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6617989 | 2022-01-28 | 2022-01-28 | 59 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 562101014497 | 6.6 |  | 2022-03-09 |  |  | 2022-03-28 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28:03:22: RFIN 27:03:22-20:03:22: PONDASI OG 20:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22-09:02:22: NEED REVIEW CIVIL EID 08:02:22: NEED REVIEW TNP ALITA 06:02:22-30:01:22: ESR REVIEW, NEED REVIEW RNP EID 28:01:22: SPK RELEASED
NEW SPK |  | JAW-BT-PDG-0617 | 30735150031 | 131497126 | JALANPATIADMT | BP2022 | TB | 105°52.44.44'E | 6°26.8.02'S | 42 | 70/180/290 | 2022 | New site 2022 - P2 | Desa Bulagor Kp. Pematang RT.03 RW.01 Kec. Pagelaran, Kab. Pandeglang Prov. Banten | EID | JAW-BT-PDG-0617 | BULAGOR_PAGELARAN | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Pandeglang | 6617993 | 2022-01-28 | 2022-01-28 | 59 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 562400509275 | 6.6 |  | 2022-03-09 |  |  | 2022-03-28 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28:03:22: RFIN 27:03:22: SRFI 23:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-09:02:22: NEED REVIEW CIVIL EID 08:02:22: NEED REVIEW TNP ALITA 06:02:22-30:01:22: ESR REVIEW, NEED REVIEW RNP EID 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JB-CKR-0125 | 30735440031 | 1261782001 | PT. DIAMOND GOLDSTORAGE | BP2022 | TB | 107°6.22.97'E | 6°18.11.34'S | 40 | 20/140/270 | 2022-2024 | New site 2022 - P1 | Desa DanauIndah Kp. Jarakosta RT.003 RW.001, Kec. Cikarang Barat, Kab. Bekasi Prov. Jawa Barat | EID | JAW-JB-CKR-0125 | JARAKOSTA_DANAUINDAH | COLO | TBG | Jabodetabek | JABODETABEK | Jawa Barat | Kab. Bekasi | 6617993 | 2022-01-28 | 2022-01-28 | 56 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-17 | 537030546015 | 6.6 |  | 2022-03-09 |  |  | 2022-03-25 | W13-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:03:22: RFIN 23:03:22-20:03:22: PONDASI OG 16:03:22-13:03:22: WAIT PSB 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: NEED REVIEW POWER EID 09:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | JAW-BT-SRG-0058 | 30734690031 | 120836104 | CURUG AGUNG | BP2022 | SMI | 106°6.47.09'E | 6°12.56.77'S | 50 | 60/160/260 | 2022 | New site 2022 - P2 | Desa Curug Agung Kp. Masigit RT.02 RW.02 Kec. Baros, Kab. Serang Prov. Banten | EID | JAW-BT-SRG-0058 | CURUG_AGUNG | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Serang | 6617989 | 2022-01-28 | 2022-01-28 | 56 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 561100867919 | 10.6 |  | 2022-03-09 |  |  | 2022-03-25 | W13-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:03:22: RFIN 23:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22-09:02:22: NEED REVIEW CIVIL EID 06:02:22-30:01:22: ESR REVIEW, NEED REVIEW RNP EID 28:01:22: SPK RELEASED
NEW SPK |  | JAW-BT-SRG-0051 | 30735370031 | 130238104 | BATUKUDA | BP2022 | SMI | 106°0.26.24'E | 6°3.12.24'S | 46 | 20/210/290 | 2022 | New site 2022 - P2 | Desa Batu Kuda Kp. Sambi Landak RT.08 RW.02 Kec. Mancak, Kab. Serang Prov. Banten | EID | JAW-BT-SRG-0051 | BATUKUDA_SERANG | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Serang | 6617989 | 2022-01-28 | 2022-01-28 | 53 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-08 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 561200506958 | 6.6 |  | 2022-03-09 |  | 2022-02-15 | 2022-03-22 | W13-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:03:22: RFIN 20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22-09:02:22: NEED REVIEW CIVIL EID 08:02:22: NEED REVIEW TNP ALITA 06:02:22-30:01:22: ESR REVIEW, NEED REVIEW RNP EID 28:01:22: SPK RELEASED
NEW SPK |  | JAW-JI-BJN-4292 | 30735010031 | 160417109 | SEDENG KANOR | BP2022 | TB | 112°1.8.76'E | 7°8.24.61'S | 70 | 100/210/325 | 2022 | New site 2022 - P2 | Desa Sedeng Dusun Sedeng RT.01 RW.II Kec.Kanor, Kab.Bojonegoro Prov.Jawa Timur | HTI | JAW-JI-BJN-4292 | KANOR_SEDENG | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6617991 | 2022-01-28 | 2022-01-28 | 70 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | MG |  |  | 2022-03-21 |  | 2022-03-22 | 2022-04-08 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 06:04:22-22:03:22: SRFI 20:03:22-16:03:22: ME OG 13:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22: NEED REVIEW POWER 09:02:22: NEED REVIEW POWER HUAWEI 08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
NEW SPK |  | JAW-JI-KDR-4349 | 30735970031 | 1654381004 | BANGSONGAN | BP2022 | TB | 112°4.1.85'E | 7°44.20.26'S | 40 | 100/220/305 | 2022 | New site 2022 - P2 | DUSUN BANGSONGAN RT.001/RW.001 Desa Bangsongan Kecamatan Kayen Kidul Kabupaten Kediri Provinsi Jawa Timur | HTI | JAW-JI-KDR-4349 | KAYEN_KIDUL_SENDEN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Kediri | 6617991 | 2022-01-28 | 2022-01-28 | 70 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-03-30 | W14-2022 | Mar-2022 | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-02-03 | MG |  |  | 2022-03-21 |  | 2022-03-16 | 2022-04-08 | W15-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 06:04:22-23:03:22: PLN CONNECTION OG 20:03:22-16:03:22: SRFI, WAIT STO & PLN CONNECTION 16:03:22-09:03:22: PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
|  | JAW-JK-GGP-0459 | 30735630031 | 1134321023 | JAKARTA BARAT CENGKARENG-1 | BP2022 | TB | 106°44.53.48'E | 6°8.13.92'S | 25 | 90/210/330 | 2022 | New site 2022 - P1 | Kapuk RT.010 RW.012 Kelurahan Kapuk Kecamatan Cengkareng, Kota Jakarta Barat, Daerah Khusus Ibukota Jakarta | EID | JAW-JK-GGP-0459 | KEBON_JAHE_KAPUK | COLO | TBG | JABO | JABODETABEK | DKI Jakarta | Kota Adm. Jakarta Barat | 6618023 | 2022-02-04 | 2022-02-04 | 73 | 61 - 90 days | 2022-03-06 | W11-2022 | Mar-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-07 | 2022-03-14 | 542103991826 | 10.6 |  | 2022-03-08 |  |  | 2022-04-18 | W17-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18:04:22: RFIN 17:04:22: SRFI 13:04:22-13:03:22: PERKUATAN OG 09:03:22-08:03:22: STO DECLARE 06:03:22-16:02:22: READY TO DECLARE STO 13:02:22: NEED REVIEW POWER EID 09:02:22-06:02:22: NEED REVIEW RNP EID 04:02:22: NEW SPK RELEASED | apr
|  | SUL-ST-LWK-1068 | 30735360031 | 260297109 | ZTE NEW188_NORTH | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 122°20.24.4'E | 1°27.1.76'S | 50 | 0/160/260 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Poros Luwuk - Toili, Desa Rusa Kencana, Kec. Toili, Kab. Banggai Prov. Sulawesi Tengah | HTI | SUL-ST-LWK-1068 | TOILI | COLO | TBG | EAST | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617806 | 2021-11-23 |  | 135 | 121 - 150 days | 2021-12-23 | W52-2021 | Dec-2021 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-07 | 2022-03-15 | 319100338633 | 6.6 |  | 2022-02-25 |  | 2022-03-16 | 2022-04-07 | W15-2022 |  |  | HOLD | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07:04:22: RFIN 06:04:22-17:03:22: GO RFI, KEJAR RFI DI MID APR 16:03:22-13:03:22: SRFI 09:03:22: ME OG 06:03:22-28:02:22: PONDASI OG 25:02:22: ANNOUNCEMENT GO UNTIL SRFI 23:02:22-16:12:21: TNP OK, NEED CONFIRM PMO GO CME 15:12:21-09:12:21: STO RECALL 08:12:21: STO DECLARE 05:12:21: NEED REVIEW TNP ALITA 01:12:21-24:11:21: ERM PROCESS | apr
|  | SUL-ST-LWK-1085 | 30735350031 | 260092104 | TOLISU | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 122�16.58.4'E | 1�26.10.61'S | 60 | 30/120/220 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Poros Trans Unit XIV,Desa Tolisu Kec. Toili, Kab. Banggai SULAWESI TENGAH | HTI | SUL-ST-LWK-1085 | TOILI_TOLISU | COLO | TBG | East | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617793 | 2021-11-18 |  | 148 | 121 - 150 days | 2021-12-18 | TBD | TBD | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-07 | 2022-03-15 | 319100338625 | 6.6 |  | 2022-02-25 |  | 2022-03-15 | 2022-04-15 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:04:22: RFIN 13:04:22-17:03:22: GO RFI 16:03:22-13:03:22: SRFI 09:03:22: ME OG 06:03:22-28:02:22: PONDASI OG 25:02:22: ANNOUNCEMENT GO UNTIL SRFI 23:02:22-16:12:21: TNP OK, NEED CONFIRM PMO GO CME 15:12:21-09:12:21: STO RECALL 08:12:21: STO DECALARE 05:12:21-24:11:21: ERM REJECTION, SITE ISSOLATED 21:11:21: ESR PROCESS | apr
|  | SUL-ST-LWK-1090 | 30735330031 | 260387126 | BO MEKAR JAYA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 122°11.43.04'E | 1°34.25.18'S | 50 | 50/170/340 | 2021 | BLITZKRIEG 2021 [NEW] | RT 04/03, Desa Mentawa, Kec. Toili Barat, Kab. Banggai, Prov. Sulawesi Tengah | HTI | SUL-ST-LWK-1090 | TOILIBARAT_MEKAR_JAYA | COLO | TBG | East | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617794 | 2021-11-18 |  | 140 | 121 - 150 days | 2021-12-18 | TBD | TBD | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-07 | 2022-03-15 | 319100338658 | 6.6 |  | 2022-02-25 |  | 2022-03-15 | 2022-04-07 | W15-2022 |  |  | HOLD | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07:04:22: RFIN 06:04:22-13:03:22: SRFI, W3 APR DI RFI KAN 09:03:22: ME OG 06:03:22-28:02:22: PONDASI OG 25:02:22: ANNOUNCEMENT GO UNTIL SRFI 23:02:22-16:12:21: TNP OK, NEED CONFIRM PMO GO CME 15:12:21-09:12:21: STO RECALL 08:12:21: STO DECLARE 7 DEC 05:12:21: REVIEW TNP ALITA 01:12:21-24:11:21: NEED REVIEW RNP HUWAWEI 21:11:21: ESR PROCESS | apr
|  | SUL-ST-LWK-1091 | 30735340031 | 260054109 | SKP KAMIWANGI EX NEW MAKAPA 1 | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 122�15.33.08'E | 1�33.21.24'S | 60 | 20/150/300 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun I Desa Kamiwangi RT.002 Kec. Toili Barat, Kab. Banggai Prov. Sulawesi Tengah | HTI | SUL-ST-LWK-1091 | TOILIBARAT_KAMI_WANGI | COLO | TBG | East | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617794 | 2021-11-18 |  | 142 | 121 - 150 days | 2021-12-18 | TBD | TBD | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-07 | 2022-03-15 | 319100338641 |  |  | 2022-02-25 |  | 2022-03-15 | 2022-04-09 | W15-2022 |  |  | HOLD | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:04:22: RFIN 06:04:22-13:03:22: SRFI, MID APR DI RFI KAN 09:03:22: ME OG 06:03:22-28:02:22: PONDASI OG 25:02:22: ANNOUNCEMENT GO UNTIL SRFI 23:02:22-16:12:21: TNP OK, NEED CONFIRM PMO GO CME 15:12:21-09:12:21: STO RECALL 08:12:21: STO DECLARE 7 DEC 05:12:21-24:11:21: ERM REJECTION, SITE ISSOLATED 21:11:21: ESR PROCESS | apr
89 COLO |  | SUM-SU-AKK-2248 | 30742100031 | 20139105 | TANJUNG PASIR | BP2022 | MSI | 99°43.19.27'E | 2°30.54.65'N | 50 | 50/110/300 | 2022 | Newsite 2022 - B2 | Desa Tanjung Pasir Kec. Kualuh Selatan Kab. Labuhan Batu Utara | HTI | SUM-SU-AKK-2248 | KUALUH_SELATAN_TANJUNG_PASIR | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu Utara | 6618081 | 2022-03-11 | 2022-03-11 | 34 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-05-04 | W19-2022 | May-2022 | 2022-05-04 | W19-2022 | May-2022 | MW | 2022-03-24 | 2022-03-25 | 125120754054 | 6.6 |  | 2022-03-25 |  |  | 2022-04-14 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14:04:22: RFIN 30:03:22: PONDASI OG 27:03:22: PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | buffer apr
|  | JAW-JK-CKG-0723 |  | 1262101003 | CIJANTUNG - RELOC | X RELOC TBG | SKP | 106°50.50.86'null | 6°20.33.97'S | 31 | 90/210/330 | 2022 | RELOCATION - SKP | Kp. Rumbut RT 007 RW 09 Kelurahan Pasir Gunung Selatan Kec Cimanggis Kota Depok Prov Jawa Barat | EID | JAW-JK-CKG-0723 | GARUDA KALISARI RELOCATION | COLO | TBG | JABO | JABODETABEK | DKI Jakarta | Jakarta Timur | 6617923 | 2022-01-18 |  | 100 | 91 - 120 days | 2022-02-17 | W08-2022 | Feb-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-01-28 |  |  |  |  | 2022-03-09 | [7 empty] | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 16:02:21-26:01:22: SRFI PLN CONNECTION 23:01:22: RNP REVIEW 19:01:22-18:01:22: SPK RELEASED FROM LMS TO EMAIL TBG
89 COLO |  | SUM-SU-AKK-2254 | 30741760031 | 223521023 | KUALUH HULU | BP2022 | TB | 99°36.31.68'E | 2°34.24.53'N | 40 | 180/280/340 | 2022 | Newsite 2022 - B2 | Dusun III Banyuwangi Desa Perk. Kanopan Ulu Kec. Kualuh ulu Kab. Labuhanbatu utara Prop. Sumatera utara | HTI | SUM-SU-AKK-2254 | PERKEBUNAN_KANOPAN_ULU_SELATAN | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu Utara | 6618079 | 2022-03-11 | 2022-03-11 | 34 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-05-04 | W19-2022 | May-2022 | 2022-05-04 | W19-2022 | May-2022 | MW | 2022-03-24 | 2022-03-25 | 125120754062 | 6.6 |  | 2022-03-24 |  |  | 2022-04-14 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14:04:22: RFIN 06:04:22: PLN CONNECTION 03:04:22: ME OG 30:03:22: PONDASI OG 27:03:22: PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | buffer apr
NEW SPK |  | JAW-JT-KRG-2152 | 30735770031 | 142770126 | KARANGPANDAN-MATESIH | BP2022 | TB | 111°3.40.43'E | 7°37.55.34'S | 39 | 10/110/250 | 2022-2024 | New site 2022 - P1 | Desa Pablengan Dukuh Karangtengah Kec. Matesih, Kab. Karanganyar Prov. Jawa Tengah | NOKIA | JAW-JT-KRG-2152 | PABLENGAN_KARANGANYAR | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Karanganyar | 6617993 | 2022-01-28 | 2022-01-28 | 54 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-07 | W15-2022 | Apr-2022 | 2022-04-07 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 526550154448 | 11 |  | 2022-03-08 |  |  | 2022-03-23 | W13-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | LMS CHANGED TO NOKIA | 23:03:22: RFIN 20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK B2S |  | JAW-BT-RKB-0775 | 30729310031 | 1322931003 | CIGOONG_UTARA_CIKULUR | BP2022 | TB | 106°10.0.38'E | 6°23.18.8'S | 50 | 40/130/280 | 2022 | New site 2022 - P2 | Kp. Kayu Dampit RT.01/03 Desa Cigoong Utara Kec. Cikulur Kab. Lebak | EID | JAW-BT-RKB-0775 | CIGOONG_UTARA_CIKULUR | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6617948 | 2022-01-25 | 2022-01-28 | 83 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-05 | W19-2022 | May-2022 | 2022-05-05 | W19-2022 | May-2022 | MW | 2022-03-07 | 2022-04-05 | 562101019303 | 6.6 |  | 2022-04-13 |  |  | 2022-04-18 | W17-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18:04:22: RFIN 7:04:22-06:03:22: ME OG 03:04:22-27:03:22: ERECTION 23:03:22: POURING 20:03:22: REBARRING 16:03:22-13:03:22: EXCAVATION 09:03:22-23:02:22: REKOM OG 20:02:22-16:02:22: IW OG 13:02:22-12:02:22: VALIDASI RNP TNP 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | buffer apr
NEW SPK B2S |  | JAW-BT-SRG-0057 | 30729450031 | 1323011003 | CIKANDE_CEMPLANG | BP2022 | TB | 106°20.7.81'E | 6°19.44.51'S | 50 | 50/130/230 | 2022 | New site 2022 - P2 | Kamp Tegal RT 007 RW 002 Desa Cemplang Kecamatan Jawilan Kabupaten Serang Provinsi Banten | EID | JAW-BT-SRG-0057 | CIKANDE_CEMPLANG | B2S | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Serang | 6617948 | 2022-01-25 | 2022-01-28 | 83 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-05 | W19-2022 | May-2022 | 2022-05-05 | W19-2022 | May-2022 | MW | 2022-03-07 | 2022-04-05 | 561400951596 | 6.6 |  | 2022-04-13 |  |  | 2022-04-18 | W17-2022 |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 18:04:22: RFIN 17:04:22-06:03:22: ME OG 03:04:22-27:03:22: ERECTION 23:03:22-20:03:22: CURRING 16:03:22-13:03:22: LANTAI KERJA 09:03:22-06:03:22: EXCAVATION 28:02:22: REKOM OG 23:02:22: IW CLEAR & PARALEL COLLECT DOKUMEN 20:02:22: IW OG 16:02:22: VALIDASI RNP TNP, IW FAILED 13:02:22: IW OG 09:02:22-04:02:22: CANDIDATE OK 02:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | buffer apr
89 COLO |  | SUM-SB-PLJ-0771 | 30742080031 | 30663109 | KINARI | BP2022 | TB | 101°38.41.28'E | 1°3.27.29'S | 50 | 120/240/300 | 2022 | Newsite 2022 - B2 | Jorong Pinang Gadang Nagari Koto Padang, Kec. Koto Baru, Kab. Dharmasraya, Prov. Sumatera Barat | HTI | SUM-SB-PLJ-0771 | LINTAS_TENGAH_SUMATERA | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Dharmasraya | 6618079 | 2022-03-11 | 2022-03-11 | 35 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-05-09 | W20-2022 | May-2022 | 2022-05-09 | W20-2022 | May-2022 | MW | 2022-03-24 | 2022-03-25 | 133360240962 |  |  | 2022-03-25 |  |  | 2022-04-15 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:04:22: RFIN 13:04:22-03:04:22: PONDASI OG 30:03:22-27:03:22: MOBDEMOB 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | buffer apr
NEW SPK |  | SUM-SS-MPR-1262 | 30734440031 | 070287104 | TAWANG REJO | BP2022 | SMI | 104°38.3.01'E | 4°11.37.79'S | 65 | 110/245/335 | 2022 | New site 2022 - P2 | Dusun Tri Tunggal, Desa Tawang Rejo RT 01, kec. Bilatang, Kab. OKU Timur Prov. Sumatera Selatan | HTI | SUM-SS-MPR-1262 | JL_KALANG_TAWANGREJO | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617988 | 2022-01-28 | 2022-01-28 | 70 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-01 | 2022-02-02 | 149300218199 |  |  | 2022-03-22 |  |  | 2022-04-08 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:04:22: RFIN 06:04:22-30:03:22: PLN 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | buffer apr
934 |  | SUM-SU-LBP-2291 | 30713320031 | 0224932007 | IBS KAMPUNG ANGGAS | RORO JONGRANG 2021 [NEW] | TB | 98°41.45.64'E | 3°38.31.38'N | 45 | 30/120/190 | 2021 |  | Komplek Anugrah Jl. Anugrah 7 Desa Sampali, Kecamatan Percut Sei Tuan, Kabupaten Deli Serdang, Provinsi Sumatera Utara | HTI | SUM-SU-LBP-2291 | BATANG_KUIS_BAKARAN_BATU | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617678 | 2021-10-06 |  | 29 | < 30 days | 2021-11-05 | W45-2021 | Nov-2021 | TBD | TBD | TBD | 2021-11-10 | W46-2021 | Nov-2021 | 2021-11-10 | W46-2021 | Nov-2021 | MW | 2021-10-15 |  | 128010141005 | 6.6 |  | 2021-10-14 |  |  | 2021-11-04 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:11:21: RFIN 03:11:21: PLN CONNECTION OG, SRFI, PLAN RFI 6 NOV 31:10:21-26:10:21: ME OG, PLAN SFRI 31 OCT, RFI 6 NOV 24:10:21: ME OG, PLAN RFI 6 NOV 20:10:21: RBS BTS PONDASI OG, PLAN ME GROUNDING 25 OCT 17:10:21: STO DECLARE 14 OCT CME PREPARATION 13:10:21: NEED REVIEW RNP HUAWEI 04:10:21: ERM PROSES
NEW SPK B2S |  | SUL-SN-PLP-1341 | 30730540031 | 2817621003 | MARIO_PONRANG | BP2022 | TB | 120°15.21.14'E | 3°10.16.77'S | 60 | 70/180/330 | 2022 | New site 2022 - P2 | Dusun Lare-Lare RT 01 Desa Lare-Lare Kec. Bua Kab. Luwu Prov. Sulawesi Selatan | HTI | SUL-SN-PLP-1341 | MARIO_PONRANG | B2S | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Luwu | 6617949 | 2022-01-25 | 2022-01-28 | 85 | 61 - 90 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | 2022-05-20 | W21-2022 | May-2022 | 2022-05-20 | W21-2022 | May-2022 | MW | 2022-02-25 | 2022-03-02 | MG |  |  | 2022-03-25 |  |  | 2022-04-20 | W17-2022 |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 20:04:22: RFIN 17:04:22: PREPARE ERECTION 13:04:22-10:04:22: CURRING 06:04:22-03:04:22: CURRING 30:03:22: CURRING 27:03:22-20:03:22: REBARRING 16:03:22-06:03:22: WAIT APD, SOIL TEST DONE 28:02:22: REKOM DONE 23:02:22-20:02:22: REKOM OG 16:02:22: IW CLEAR 13:02:22: IW OG 09:02:22: VALIDASI RNP TNP OG 08:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS | buffer apr
NEW SPK |  | JAW-BT-RKB-0587 | 30734640031 | 130214104 | CILAYANG | BP2022 | SMI | 106°25.5.34'E | 6°24.36.54'S | 52 | 50/190/320 | 2022 | New site 2022 - P2 | Desa Cilayang Kp. Cilayang RT.04 RW.01 kec. Curugbitung, Kab. Lebak Prov. Banten | EID | JAW-BT-RKB-0587 | CILAYANG_LEBAK | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kab. Lebak | 6617989 | 2022-01-28 | 2022-01-28 | 59 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-07 | W15-2022 | Apr-2022 | 2022-04-07 | W15-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-17 | 562101014501 | 6.6 |  | 2022-02-09 |  |  | 2022-03-28 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28:03:22: RFIN 27:03:22: SRFI 23:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI BTS DONE 06:03:22-13:02:22: PONDASI BTS DONE, HOLD XL 09:02:22: CME PREPARATION 07:02:22: NEED REVIEW POWER EID 06:02:22: NEED REVIEW TNP ALITA 02:02:22-30:01:22: ESR REVIEW, NEED REVIEW RNP EID 28:01:22: SPK RELEASED
NEW SPK |  | SUM-LA-KLA-1134 | 30736190031 | 101036109 | DESA SINAR PALEMBANG | BP2022 | TB | 105°32.33.47'E | 5°32.4.67'S | 60 | 65/155/350 | 2022 | New site 2022 - P2 | Desa Sinar Palembang RT.002 RW.001, Kec. Candipuro, Kab. Lampung Selatan Prov. Lampung | HTI | SUM-LA-KLA-1134 | SINAR_PALEMBANG | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Selatan | 6617991 | 2022-01-28 | 2022-01-28 | 81 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-31 | W23-2022 | May-2022 | 2022-05-31 | W23-2022 | May-2022 | MW | 2022-02-02 | 2022-02-03 | 171310604209 |  |  | 2022-03-22 |  |  | 2022-04-19 | W17-2022 |  |  |  | 38.RFI | 21.RFI | STR DONE | 19:04:22: RFIN 17:04:22-06:04:22: PLN & STR 03:04:22: ME OG & STRENGTENING 30:03:22-27:03:22: STRENGTENING 23:03:22-16:03:22: ME OG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-20:02:22: READY TO STO 16:02:22: NEED REVIEW CIVIL 13:02:22: NEED REVIEW TNP ALITA 09:02:22: RND NOK NEED 50 METER 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | buffer apr
NEW SPK |  | SUM-SS-MPR-1279 | 30734450031 | 070290104 | SUKANEGERI | BP2022 | SMI | 104°36.54.36'E | 3°48.48.6'S | 65 | 40/190/330 | 2022 | New site 2022 - P2 | Desa Sukanegeri, Kel. Sukanegeri RT 2, Kec. Semendawai Barat, Kab. OKU Timur Prov. Sumatera Selatan | HTI | SUM-SS-MPR-1279 | SEMENDAWAI_BARAT_SUKA_NEGERI | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617988 | 2022-01-28 | 2022-01-28 | 74 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-03 | W23-2022 | Jun-2022 | 2022-06-03 | W23-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 | 149100152593 | 6.6 |  | 2022-03-22 |  |  | 2022-04-12 | W16-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:04:22: RFIN 10:04:22:COMMCASE, PONDASI OG HOLD 06:04:22-03:04:22: PONDASI OG 30:03:22-27:03:22: COMMCASE 23:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | buffer apr
|  | SUM-RI-BLS-1133 | 30730860031 | 41295109 | PT. ADEI PLANTATION 2 | ACTIVE - BLITZKRIEG | TB | 101°19.42.47'E | 1°4.53.25'N | 50 | 80/190/315 | 2021 | New site 2021 | Komplek Perumahan PT. Adei Plantation & Industry KM 5 Kebun Km 4 Divisi 15 RT 04 RW05 Desa Tengganau Kecamatan Pinggir Kab. Bengkalis | HTI | SUM-RI-BLS-1133 | PINGGIR_TENGGANAU | COLO | TBG | WEST | SUMBAGTENG | Riau | Kab. Bengkalis | 6617946 | 2022-01-25 |  | 30 | < 30 days | 2022-02-24 | W09-2022 | Feb-2022 | TBD | TBD | TBD | 2022-02-20 | W09-2022 | Feb-2022 | 2022-02-24 | W09-2022 | Feb-2022 | MW | 2022-02-09 |  | 182103613019 | 6.6 |  | 2022-02-04 |  |  | 2022-02-24 | W09-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:02:22: RFIN 23:02:22: RFI, WAIT RFIN 20:02:22-14:02:22: ME OG 09:02:22: TEAM MOBILIZATION 06:02:22: CME PREPARATION & WAIT PSB 02:02:22-30:01:22: NEED REVIEW TNP ALITA 26:01:22: ERM PROCESS 25:01:22: SPK RELEASED
|  | JAW-JB-BKS-0640 | 30727560031 | 123282109 | KLAYAN JATIMAKMUR | RELOCATION | SKP | 106°55.36.37'E | 6°16.20.42'S | 30 | 90/210/330 | 2022 | RELOCATION - PROTELINDO | Jl. Klayan 1, Perum Jatiwaringin Asri Blok F7 No.1, Kec. Pondok Gede, Kota Bekasi Prov. Jawa Barat | EID | JAW-JB-BKS-0640 | KUALA SIMPANG RELOCATION | COLO | TBG | JABO | JABODETABEK | Jawa Barat | Kota Bekasi | 6617931 | 2022-01-20 | 2022-01-24 | 32 | 31 - 60 days | 2022-02-19 | W08-2022 | Feb-2022 | TBD | TBD | TBD | 2022-02-25 | W09-2022 | Feb-2022 | 2022-02-25 | W09-2022 | Feb-2022 | MW | 2022-01-30 |  | 547303354183 | 10.6 |  | 2022-01-26 |  | 2022-02-16 | 2022-02-21 | W09-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | RETURN XL BUT DONE RFIN, SPK NY RETURN 21:02:22: RFIN 16:02:22-13:02:22: SRFI 09:02:22-06:02:22: PONDASI STACKING 02:02:22: PABRIKASI OG 30:01:22: CME PREPARATION 26:01:22: ESR REVIEW 24:01:22: SPK RELEASED
|  | JAW-JB-BDG-4313 | 30725540031 | 121832109 | SIMPANGLIMA-STEMBI | RELOCATION | TB | 107°37.11.78'E | 6°55.32.92'S | 40 | 70/160/265 | 2021 |  | Jl. Burangrang No.28 (Radio Dahlia), kel. Burangrang Kec. Lengkong, Kota Bandung Prov. Jawa Barat | CAA | JAW-JB-BDG-4313 | TALAGA BODAS RELOCATION | COLO | TBG | Central | JABAR | Jawa Barat | Kota Bandung | 6617899 | 2021-12-27 |  | 58 | 31 - 60 days | 2022-05-26 | W22-2022 | May-2022 | TBD | TBD | TBD | 2022-02-14 | W08-2022 | Feb-2022 | 2022-02-28 | W10-2022 | Feb-2022 | MW | 2022-01-26 |  | 535515962915 | 6.6 |  | 2022-01-21 |  |  | 2022-02-23 | W09-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23:02:22: RFIN 21:02:22: ME OG 16:02:22: PONDASI OG 13:02:22-06:02:22: COMMCASE DENGAN LL, MATERIAL BELUM MOS 02:02:22: PABRIKASI 30:01:22-23:01:22: CME PREPARATION 19:01:22-12:01:22: TNP REVIEW 09:01:22-29:12:21: REVIEW DAN APPROVAL RND, RF MAX DI 28M KARENA TOWER MILIK RADIO 27:12:21: NEW SPK
|  | BAL-BA-GIN-1489 | 30721640031 | 171190126 | THE EYE VILLAS | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 115°18.29.74'E | 8°28.34.36'S | 40 | 0/140/270 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Sumita Br.Sema Kec.Gianyar, Kab.Gianyar Prov.Bali | HTI | BAL-BA-GIN-1489 | GIANYAR_SUMITA | COLO | TBG | East | BALINUSRA | Bali | Kab. Gianyar | 6617836 | 2021-11-29 |  | 42 | 31 - 60 days | 2021-12-29 | W53-2021 | Dec-2021 | 2021-10-08 | W41-2021 | Oct-2021 | 2022-01-20 | W04-2022 | Jan-2022 | 2022-01-20 | W04-2022 | Jan-2022 | MW | 2021-12-21 |  | 552001743730 | 6.6 |  | 2021-12-15 |  | 2021-12-24 | 2022-01-10 | W03-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:01:22: RFIN 09:01:22-07:12:22: RFI, WAIT RFIN 05:01:22-26:12:21: SRFI, KWH KOSONG, WAIT STOCK KWH 22:12:21: SRFI, OG PLN CONNECTION 19:12:21: CME OG, PLAN SRFI 20 DEC 15:12:21: NEED REVIEW POWER HUAWEI 12:12:21-08:12:21: NEED REVIEW TNP ALITA 05:12:21-30:11:21: ESR PROCESS
|  | BAL-BA-DPR-8075 | 30720860031 | 170330109 | CITRALAND DENPASAR | RELOCATION | SKP | 115°11.23.6'E | 8°37.51.56'S | 20 | 5/180/275 | 2021 | RELOCATION | Jl. Karang Sari V No. 25, dusun Robokan, Desa Padangsambian Kaja, kecamatan Denpasar Barat Kota denpasar | CAA | BAL-BA-DPR-8075 | UBUNG TIMUR RELOCATION | COLO | TBG | East | BALINUSRA | Bali | Kota Denpasar | 6617869 | 2021-12-07 |  | 99 | 91 - 120 days | 2022-01-06 | W02-2022 | Jan-2022 | TBD | TBD | TBD | 2022-03-20 | W13-2022 | Mar-2022 | 2022-03-20 | W13-2022 | Mar-2022 | MW | 2021-12-21 |  | 551005019757 | 6.6 |  | 2021-12-14 |  | 2021-12-24 | 2022-03-16 | W12-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16:03:22: RFIN 13:03:22: POWER CONNECTION 09:03:22: CONFIRM LANJUT KONEKSI PLN 06:03:22-19:12:21: SRFI, PLN CONNECTION OG, NY READY RFS KARENA BELUM TERIMA PO 15:12:21: STO DECLARED 14 DEC, CME PREPARATION 12:12:21-07:12:21: NEW SPK, NEED REVIEW RNP
938.6 |  | SUM-KR-BTM-0595 | 30714530031 | 0506871003 | TEMBESI TB | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 104°1.44.32'E | 0°59.0.61'N | 50 | 100/200/300 | 2021 | BLITZKRIEG 2021 [NEW] | Kampung Tua Tiang Wangkang RT 03 RW 01 KELURAHAN TEMBESI KEC SAGULUNG KOTA BATAM | HTI | SUM-KR-BTM-0595 | TEMBESI | B2S | TBG | WEST | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6617734 | 2021-10-21 |  | 106 | 91 - 120 days | 2022-03-20 | W13-2022 | Mar-2022 | TBD | TBD | TBD | 2022-01-31 | W06-2022 | Jan-2022 | 2022-02-28 | W10-2022 | Feb-2022 | MW | 2021-12-16 |  | 153000398174 | 6.6 |  | 2021-12-14 |  |  | 2022-02-04 | W06-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:02:22: RFIN 02:02:22: PEMASANAN KWH, PLAN PLN CONNECT 03/02/22 30:01:22-23:01:22: ME OG 19:01:22-12:01:22: ERECTION OG 09:01:22-19:12:21: POURING BOREPILE OG, PLAN 10 JAN BACKFILL 15:12:21: BOREPILE OG, PLAN POURING 18 DEC 12:12:21-08:12:21: EXCAVATION OG, PLAN POURING 18 DEC 05:12:21-01:12:21: BOREPILE OG, KONDISI DI BAWAH PASIR SEHINGGA LONGSOR TERUS, NEED PROPOSE REVISED DESIGN 28:11:21-21:11:21: RFC, PLAN START CME 25 NOV 17:11:21-14:11:21: PROCESS REKOM OG 10:11:21: RNP & TNP REVIEW OK, OG SITAC PROCESS 07:11:21-31:10:21: SITE BERADA DI KAMPUNG KUA (TIDAK BISA MENYEWA LAHAN ATAUPUN DIJUAL BELIKAN), PROSES PENDEKATAN KE PEMERINTAHAN BATAM UNTUK PROVIDE LAHAN PEMERINTAHAN BATAM, MENUNGGU JAWABAN DARI PIHAK PEMERINTAHAN BATAM 24:10:21: NEW SPK NEW BUILT, HUNTING PROSES, PLAN SUBMIT KANDIDAT 4 NOV 2021
|  | SUL-SG-RAH-0472 | 30720660031 | 270153109 | TBG Kasimpa Jaya Muna | NEW SITE 2022-REPEATER | TB | 122°23.21.05'E | 4°52.29.53'S | 43 | 30/235 | 2021 | NEW SITE 2022-REPEATER | Jl. KUBIS Rt 004 / Rw 002Desa Kasimpa JayaKecamatan Tiworo Selatan, Kabupaten Muna | HTI | SUL-SG-RAH-0472 | REPEATER KASIMPA JAYA | COLO | TBG | East | SULAWESI | Sulawesi Tenggara | Kab. Muna | 6617860 | 2021-12-02 |  | 42 | 31 - 60 days | 2022-01-01 | W01-2022 | Jan-2022 | TBD | TBD | TBD | 2022-01-12 | W03-2022 | Jan-2022 | 2022-01-14 | W03-2022 | Jan-2022 | MW | 2021-12-16 |  | 328200582331 | 6.6 |  | 2021-12-13 |  |  | 2022-01-13 | W03-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:01:22: RFIN 12:01:22: SRFI, PLN CONNECTION OG 05:01:22-22:12:21: PONDASI RBS OG 19:12:21-15:12:21: STO DECLARED, CME PREPARATION 12:12:21: NEED REVIEW TNP ALITA 08:05:21-05:12:21: ERM PROCESS, NEED REVIEW RNP
|  | SUL-ST-LWK-1082 | 30720440031 | 260093104 | LUWUK KM 1 | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 122�49.30.5'E | 0�55.54.66'S | 50 | 70/160/250 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Batu Ceper KM 3, Kel. Bungin Timur Rt.05/Rw.02 Kec. Luwuk Banggai, Kab. Banggai Prov. Sulawesi Tengah | HTI | SUL-ST-LWK-1082 | LUWUK_KILONGAN_PERMAI | COLO | TBG | East | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617793 | 2021-11-18 |  | 47 | 31 - 60 days | 2021-12-18 | TBD | TBD | TBD | TBD | TBD | 2021-12-29 | W53-2021 | Dec-2021 | 2022-01-07 | W02-2022 | Jan-2022 | MW | 2021-12-08 |  | 319500337732 | 6.6 |  | 2021-12-07 |  |  | 2022-01-04 | W02-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:01:22: RFIN 02:01:22: RFI, WAIT RFIN 29:12:21: ME OG, PLAN INSTALL 27 DEC, PLN REGIST OG 26:12:21-19:12:21: PONDASI BTS OG, PARALEL DELIVERY MATERIAL 15:12:21-12:12:21: CME PREPARATION, WAIT PSB RELEASED 08:12:21: STO DECLARE 05:12:21-24:11:21: ERM REJECTION, SITE ISSOLATED 21:11:21: ESR PROCESS
685 |  | SUM-KR-BTM-0605 | 30720400031 |  | PULAU KARAS 2 | RORO JONGRANG 2021 [NEW] |  | 104°20.24.65'E | 0°45.11.74'N | 65 | 15/115/270 | 2021 | RORO JONGRANG 2021 [NEW] | Kampung Padang, RT.04/03, Kel. Karas, Kec. Galang, Kota Batam, Prov. Kepulauan Riau | HTI | SUM-KR-BTM-0605 | KARAS | COLO | TBG | West | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6617454 | 2021-08-09 |  | 147 | 121 - 150 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-12-22 | W52-2021 | Dec-2021 | 2022-01-03 | W02-2022 | Jan-2022 | MW | 2021-10-04 |  | 183090454902 | 6.6 |  | 2021-12-06 |  |  | 2022-01-03 | W02-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03:01:22: RFIN 02:01:22: RFI, WAIT RFIN 29:12:21: SRFI, PLN CONNECTION OG, GANTI JARINGAN 800M DENGAN KABEL 35 26:12:21: ME OG 22:12:21: PONDASI BTS OG, PLAN RFI 24 DEC 19:12:21: DELIVERY MATERIAL, SITE KEPULAUAN, PLAN MATERIAL ON SITE 19 DES 15:12:21: PONDASI RBS OG, PLAN RFI 22 DEC 12:12:21-08:12:21: STO DECLARE 6 DEC, OG PROCESS ASSIGN MITRA & WAIT CONFIRM PROCUREMENT, PLAN RFI 22 DEC 05:12:21-30:11:21: XL CONFIRM GO dengan PLN 12 Hrs + additional solusi power back up, Utk timing PLN connection agar d bahas dengan team PIC PMO XL & PMO Technology Partner. STO NY DECLARE 28:11:21-03:11:21: WAIT KONFIRM TIM POWER XL, PLN HANYA TERSEDIA 12 JAM, NEED REVIEW POWER HUWAWEI 31:10:21 - 20:10:21-22:08:21: NEED REVIEW POWER HUAWEI 18:08:21: 16:08:21:09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES NEED REVIEW TNP ALITA
651 |  | SUM-KR-BTM-0617 | 30692090031 | 050044109 | PULAU PEMPING | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 103°47.34.8'E | 1°6.5.15'N | 50 | 0/160/255 | 2021 | BLITZKRIEG 2021 [NEW] | Kampung Tengah RT 003 RW01 Kel. Pemping, Kec. Belakang Padang, Kota Batam, Prov. Kepulauan Riau | HTI | SUM-KR-BTM-0617 | PEMPING | COLO | TBG | West | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6617413 | 2021-08-04 |  | 121 | 121 - 150 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-28 | W40-2021 | Sep-2021 | 2021-12-04 | W49-2021 | Dec-2021 | 2021-12-03 | W49-2021 | Dec-2021 | MW | 2021-08-13 |  | 183041635485 | 6.6 |  | 2021-12-06 |  | 2021-11-18 | 2021-12-03 | W49-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03:12:21: RFIN 01:12:21-28:11:21: SRFI, PLN CONNECTION OG PLAN RFI 3 DEC 25:11:21: CONFIRM GO FROM XL PLN 14 JAM, NEED SUPPORT ADDITIONAL TIME BY HTI 24:11:21-03:11:21: POWER ISSUE HANYA TERSEDIA 14 JAM, WAITING REVIEW SOLUSI POWER&PRICE CAPEX DARI XL, WAITING APPROVAL GO/NOT GO UNTUK SITE INI. PROPOSE HOLD ACCRUE 31:10:21-20:10:21-13:09:21: POWER ISSUE, STO RECALL POWER HANYA TERSEDIA 14 JAM 08:09:21: PLAN CONNECT MULTIGUNA DAYA 5.5, NEED APPROVAL XL 06:09:21: SRFI, REPLAN RFI 28 SEP NEED SURAT JAWABAN PLN TERKAIT POWER 12 JAM 01:09:21:30:08:21:25:08:21: PONDASI RBS BTS OG 22:08:21: 18:08:21: CME PREPARATION 10:08:21: 09:08:21: STO DECLARE 9 AUG, CME PREPARATION 04:08:21 : SPK COLO RELEASED, ERM PROSES
|  | JAW-JB-SBM-2134 | 30719970031 | 123549109 | NEGLASARI | ACTIVE - BLITZKRIEG | TB | 106°46.40.01'E | 6°47.41.64'S | 40 | 70/200/270 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Nyangkowek Kp. Caringin RT.003 RW.006, Kec. Cicurug, Kab. Sukabumi Prov. Jawa Barat | EID | JAW-JB-SBM-2134 | RAYA CIDAHU MEKARSARI | COLO | TBG | JABO | JABODETABEK | Jawa Barat | Kab. Sukabumi | 6617812 | 2021-11-23 |  | 21 | < 30 days | 2021-12-23 | W52-2021 | Dec-2021 | 2021-10-08 | W41-2021 | Oct-2021 | 2021-12-25 | W52-2021 | Dec-2021 | 2021-12-25 | W52-2021 | Dec-2021 | MW | 2021-12-01 | 2021-12-08 | 536590596124 | 6.6 |  | 2021-11-30 |  | 2021-12-10 | 2021-12-14 | W51-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14:12:21: RFIN 12:12:21: SRFI, OG PLN CONNECTION 08:12:21-05:12:21: PONDASI OG 01:12:21-01:12:21: CME PREPARATION, WAIT PSB PLN RELEASED 28:11:21: NEED REVIEW POWER EID 24:11:21: ERM PROCESS
NEW SPK |  | SUM-LA-GDT-1131 | 30734820031 | 100200104 | PASAR_WIYONO | BP2022 | SMI | 105°8.30.34'E | 5°22.54.37'S | 50 | 140/255/300 | 2022 | New site 2022 - P2 | Jl. Proklamasi RT/RW. 02/07 Pasar Wiyono,Gedong Tataan ,kab.Pesawaran | HTI | SUM-LA-GDT-1131 | GEDONG_TATAAN_WIYONO | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Pesawaran | 6617988 | 2022-01-28 | 2022-01-28 | 87 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-02 | 2022-02-03 | 172501123469 | 6.6 |  | 2022-03-22 |  |  | 2022-04-25 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22-06:04:22: SRFI & STR 03:04:22: ME OG & PERKUATAN 30:03:22-13:03:22: STRENGTENING PARALEL CME 09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 07:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
967 |  | KAL-KS-TJG-0954 | 30720640031 | 220757109 | TBG GM DESA SIMPUNG LAYUNG | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 115°34.9.44'E | 1°54.46.22'S | 45 | 10/105/295 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | KAL-KS-TJG-0954 | MUARA_UYA_UWIE | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | Kab. Tabalong | 6617768 | 2021-11-05 |  | 67 | 61 - 90 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-01-10 | W03-2022 | Jan-2022 | MW | 2021-12-14 |  | 222400317590 | 6.6 |  | 2021-11-29 |  |  | 2022-01-11 | W03-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11:01:22: RFIN 09:01:22: SRFI 05:01:22-02:01:22: ME OG, REGIST PLN 29:12:21: PONDASI RBS OG, PREPARE ME 26:12:21: PONDASI RBS OG 22:12:21-15:12:21: CME PREPARATION 13:12:21: Ada perubahan komitmen dari reloc right 1200 ER menjadi komitmen New order 2021 12:12:21: STO DECLARE 29 NOV, WAIT RFI BY HTI 05:12:21-28:11:21: NEED REVIEW POWER HUWAWEI 21:11:21-07:11:21: ESR PROCESS OG,NEED REVIEW RNP HUAWEI
|  | JAW-JB-BGR-0235 | 30719840031 | 120165102 | BARANANGSIANG BOGOR | RELOCATION | PMS | 106�49.18.16'E | 6�36.16.13'S | 36 | 50/140/260 | 2021 | RELOCATION | Kel. Cimahpar Kp. Sawah RT.02 RW.11, Kec. Bogor Utara, Kota Bogor Prov. Jawa Barat | EID | JAW-JB-BGR-0235 | JAGORAWI CIMAHPAR RELOCATION | COLO | TBG | JABO | JABODETABEK | Jawa Barat | Kota Bogor | 6617795 | 2021-11-19 |  | 27 | < 30 days | 2021-12-19 | TBD | TBD | TBD | TBD | TBD | 2021-12-19 | W52-2021 | Dec-2021 | 2021-12-19 | W52-2021 | Dec-2021 | MW | 2021-11-29 | 2021-12-08 | 538216433530 | 7.7 |  | 2021-11-26 |  |  | 2021-12-16 | W51-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16:12:21: RFIN 15:12:21: RFI, WAIT RFIN 12:12:21: PONDASI DONE, OG PEMASANGAN TRAY 08:12:21-05:12:21: PONDASI OG 01:12:21-01:12:21: CME PREPARATION, WAIT PSB PLN RELEASED 28:11:21: STO DECLARE 24:11:21-21:11:21: ESR PROCESS, NEED REVIEW TNP ALITA
962 |  | JAW-JI-KNR-4196 | 30720630031 | 160632104 | MARON_SRENGAT | ACTIVE - BLITZKRIEG 2021 [NEW] | SMI | 112°4.54.59'E | 8°5.50.03'S | 50 | 150/220/340 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | JAW-JI-KNR-4196 | SRENGAT_MARON | COLO | TBG | EAST | JATIM | Jawa Timur | Kab. Blitar | 6617767 | 2021-11-05 |  | 49 | 31 - 60 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-17 | W51-2021 | Dec-2021 | 2021-12-31 | W53-2021 | Dec-2021 | MW | 2021-12-14 | 2021-12-14 | 514051659104 | 10.6 |  | 2021-11-22 |  | 2021-12-17 | 2021-12-24 | W52-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24:12:21: RFIN 22:12:12-19:12:21: SRFI TGL 17 DEC, OG PROCESS PLN CONNECTION 15:12:21: PONDASI BTS OG, WAIT PSB RELEASED 13:12:21: Ada perubahan komitmen dari reloc right 1200 ER menjadi komitmen New order 2021 12:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-07:11:21: ESR PROCESS OG,NEED REVIEW RNP HUAWEI
964 |  | BAL-BA-KRA-1477 | 30720780031 | 171248126 | DUKUH KUBU | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 115°33.26.68'E | 8°17.8.99'S | 50 | 80/200/300 | 2021 | BLITZKRIEG 2021 [NEW] | Banjar Dinas Bhuana Kusuma, Desa Dukuh, Kecamatan Kubu, Kabupaten Karangasem Propinsi Bali | HTI | BAL-BA-KRA-1477 | KUBU_DUKUH | COLO | XL | EAST | BALINUSRA | Bali | Kab. Karangasem | 6617768 | 2021-11-05 |  | 141 | 121 - 150 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-22 |  |  | 2022-03-26 | W13-2022 |  |  |  | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 26:03:22: RFIN 24:02:22-17:02:22: SRFI 02:02:22: RBS FOUNDATION 26:01:22-16:01:22: PREPARE MATERIAL 12:01:22: PREPARE MATERIAL & WAITING PERMIT 05:01:22-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-07:11:21: ESR PROCESS OG,NEED REVIEW RNP HUAWEI
89 COLO |  | SUM-LA-BBU-0876 | 30741290031 | 100958109 | TALANG MANGGA | BP2022 | TB | 104°24.11.45'E | 4°45.1.08'S | 60 | 55/155/315 | 2022 | Newsite 2022 - B2 | Desa talang mangga RT001 RW004 Kecamatan Kasui, Kab way kanan , Prov Lampung | HTI | SUM-LA-BBU-0876 | TALANG_MANGGA | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Way Kanan | 6618079 | 2022-03-11 | 2022-03-11 | 46 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-03-21 | 2022-03-23 | 173700729205 |  |  | 2022-03-24 |  |  | 2022-04-26 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26:04:22: RFIN 24:04:22-17:04:22: PLN 13:04:22: ME OG 10:04:22-03:04:22: PONDASI OG 30:03:22-27:03:22: PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | apr
937 |  | KAL-KS-BLN-0964 | 30709170031 | 2209061003 | MANTEWE | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 115°52.51.88'E | 3°15.57.14'S | 50 | 0/130/280 | 2021 | BLITZKRIEG 2021 [NEW] | Jalan Transmigrasi RT. 10, Desa Sari Mulya, Kecamatan Mentewe, Kabupaten Tanah Bumbu, Propinsi Kalimantan Selatan | HTI | KAL-KS-BLN-0964 | MANTEWE | COLO | TBG | Central | KALIMANTAN | Kalimantan Selatan | Kab. Tanah Bumbu | 6617643 | 2021-09-23 |  | 95 | 91 - 120 days | 2022-02-20 | W09-2022 | Feb-2022 | TBD | TBD | TBD | 2021-11-22 | W48-2021 | Nov-2021 | 2021-12-31 | W53-2021 | Dec-2021 | MW | 2021-11-10 |  | 223200582873 | 6.6 |  | 2021-11-22 |  |  | 2021-12-27 | W53-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:12:21: RFIN 26:12:21-19:12:21: RFI, WAIT RFIN 15:12:21-05:12:21: ERECTION OG 01:12:21: CURING TIME OG 28:11:21: POURING DONE 24:11:21: REBARING OG 21:11:21: EXCAVATION OG 17:11:21-10:11:21: OG DELIVERY MATERIAL JADWAL KAPAL 12 NOV, ETA 22/11. 07:11:21: TEAM PREPARATION & BOREPILE PREPARATION OG 03:11:21: DESIGNPACK DONE, REKOM DONE, PLAN START CME 9 NOV 31:10:21-27:10:21: IW CLEAR, PARALEL SOIL TEST DONE 24:10:21-26:09:21: SPK RELEASED COLO, PEKERJAAN B2S NEEW REVIEW IMB
965 |  | SUM-RI-RGT-0967 | 30720790031 | 40119109 | SC_RG5083A | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 102°34.24.6'E | 0°23.22.09'S | 60 | 50/130/290 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | SUM-RI-RGT-0967 | SUNGAI_BERINGIN | COLO | XL | WEST | SUMBAGTENG | Riau | Kab. Indragiri Hulu | 6617768 | 2021-11-05 |  | 105 | 91 - 120 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-19 |  |  | 2022-02-18 | W08-2022 |  |  |  | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 02:02:22-16:01:22: SRFI, PLN CONNECTION 12:01:22: PONDASI DONE, WAITING SK PLN FROM XL 05:01:22-29:12:21: WAIT PERMIT 26:12:21-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-07:11:21: ESR PREPARATION OG, NEED REVIEW RNP HUAWEI
|  | JAW-JK-TJP-0707 | 30716000031 | 110984109 | VILA GADING INDAH | RORO JONGRANG 2021 [NEW] | SKP | 106°53'52.39''E | 6°10'1.3''S |  |  | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Perintis Kemerdekaan, Kel. Kelapa Gading Barat RT.01 RW.05, Kec. Kelapa Gading, Kota Jakarta Utara Prov. DKI Jakarta | EID | JAW-JK-TJP-0707 | PELEPAH RAYA RELOCATION | COLO | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | Kota Adm. Jakarta Utara | 6617777 | 2021-11-08 |  | 21 | < 30 days | 2021-12-08 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-11-30 | W49-2021 | Nov-2021 | 2021-11-28 | W49-2021 | Nov-2021 | MW | 2021-11-18 | 2021-11-22 | 545103628446 | 6.6 |  | 2021-11-16 |  |  | 2021-11-29 | W49-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29:11:21: RFIN 24:11:21: OG FABRIKASI MATERIAL BASEFRAME, START CME 25 NOV, PLAN RFI 28 NOV 21:11:21: WAIT PSB PLN RELEASE 17:11:21: STO DECLARE 16 NOV 14:11:21-10:11:21: ESR PROCESS OG
966 |  | SUM-SS-PKB-1247 | 30723450031 | 71410109 | SIDANG MAS BANYUASIN | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 104°19.55.02'E | 2°58.12.43'S | 45 | 30/190/290 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | SUM-SS-PKB-1247 | SIDANG_MAS | COLO | XL | WEST | SUMBAGSEL | Sumatera Selatan | Kab. Banyuasin | 6617768 | 2021-11-05 |  | 111 | 91 - 120 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-15 |  |  | 2022-02-24 | W09-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02:02:22: RFI, WAIT RFIN 26:01:22: SRFI, PROCESS SURVEY PLN 19:01:22-16:01:22: WAITING PANEL KWH 12:01:22-29:12:21: WAIT PERMIT 26:12:21-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-07:11:21: ESR PROCESS OG,NEED REVIEW TNP ALITA
963 |  | SUM-RI-BKN-1158 | 30720770031 | 41320109 | SUNGAI PUTIH | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 101°10.43.97'E | 0°28.35.44'N | 40 | 70/90/240 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | SUM-RI-BKN-1158 | SEIPUTIH_KAMPAR_TIMUR | COLO | XL | WEST | SUMBAGTENG | Riau | Kab. Kampar | 6617768 | 2021-11-05 |  | 121 | 121 - 150 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-12 |  |  | 2022-03-06 | W11-2022 |  |  |  | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 24:02:22: RFI, NEED RFIN TO INJECT 17:02:22-16:01:22: SRFI,PLN CONNECTION 12:01:22: PONDASI OG 05:01:22-29:12:21: WAIT PERMIT 26:12:21-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-17:11:21: STO RELEASED 12 NOV, WAIT RFI BY HTI 17:11:21-07:11:21: ESR PREPARATION OG,NEED REVIEW TNP ALITA
961 |  | SUM-SS-LLG-1236 | 30720760031 | 70217104 | PETANANG | ACTIVE - BLITZKRIEG 2021 [NEW] | SMI | 102°50.34.04'E | 3°13.11.75'S | 50 | 80/160/340 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | SUM-SS-LLG-1236 | PETANANG_ULU | COLO | XL | WEST | SUMBAGSEL | Sumatera Selatan | Kota Lubuk Linggau | 6617767 | 2021-11-05 |  | 111 | 91 - 120 days | 2021-12-05 | W50-2021 | Dec-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-12 |  |  | 2022-02-24 | W09-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02:02:22-26:01:22: SRFI, PROSES SURVEY PLN 19:01:22-16:01:22: PREPARE MATERIAL 12:01:22-29:12:21: WAIT PERMIT 26:12:21-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-17:11:21: STO RELEASED, WAIT RFI BY HTI 14:11:21-07:11:21: ESR PROCESS OG,NEED REVIEW TNP ALITA
943 |  | JAW-JT-SKT-2142 | 30715640031 | 141870109 | KADIPIRO SURAKARTA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°49.19.85'E | 7°32.23.53'S | 25 | 60/210/330 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Sumpah Pemuda No.1, Kel. Kadipiro RT.001 RW.IX Sambirejo Kec. Banjarsari, Kota Surakarta Prov. Jawa Tengah | NOKIA | JAW-JT-SKT-2142 | KALINGGA KADIPIRO | COLO | TBG | Central | JATENG | Jawa Tengah | Kota Surakarta | 6617651 | 2021-09-27 |  | 156 | > 150 days | 2021-10-27 | W44-2021 | Oct-2021 | 2021-10-27 | W44-2021 | Oct-2021 | 2022-03-02 | W10-2022 | Mar-2022 | TBD | TBD | TBD | MW | 2021-10-04 |  | 520521518979 | 7.7 |  | 2021-11-11 |  |  | 2022-03-02 | W10-2022 |  |  | CME | 38.RFI | 21.RFI | LMS CHANGED TO NOKIA | 02:03:22: RFIN 28:02:22: RFI, WAIT RFIN 24:02:22: MOBILISASI & PROSES INSTALASI COMBAT 23:02:22-02:02:22: PROSES REALISASI TUNTUTAN 30:01:22-19:01:22: APPROVAL PENGAJUAN SEWA LAHAN 16:01:22-22:12:21: RESCHEDULE PERTEMUAN DGN PIHAK TNI 19:12:21: PLAN PERTEMUAN DGN PIHAK TNI PADA 22 DEC 15:12:21-05:12:21: OG PROCESS IZIN UNTUK LAHAN COMBAT, PROPOSE AKAN DICOMBATKAN 01:12:21-03:11:21: MENUNGGU KEPUTUSAN DARI KABABINKUM, STATUS TANAH MILIK NEGARA DAN DIMANFAATKAN TNI AD (KODAM 4 DIPONEGORO), DIGUNAKAN OLEH ODITUR MILITER SURAKARTA, PLAN EOM NOV. Desain perkuatan dari mono pole steel angle dirubah menjadi SST-32 meter MLTBI, TAMBAH OPSI DI PROPOSAL PASANG COMBAT TEMPORARY 31:10:21-27:10:21: REVIEW CIVIL EID SITE STEEL ANGLE, WAITING APPROVAL JENDRAL KODAM 20:10:21:-04:10:21: ESR PROSES NEED REVIEW RNP EID
934 |  | SUM-RI-PBR-1162 | 30720730031 | 040925109 | TELAUK SAMAK | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 101°23.41.6'E | 0°38.12.95'N | 40 | 0/100/270 | 2021 | BLITZKRIEG 2021 [NEW] |  | HTI | SUM-RI-PBR-1162 | RUMBAI_MUARA_FAJAR | COLO | XL | West | SUMBAGTENG | Riau | Kota Pekanbaru | 6617715 | 2021-10-18 |  | 134 | 121 - 150 days | 2021-11-17 | W47-2021 | Nov-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-03 |  |  | 2022-03-01 | W10-2022 |  |  |  | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 24:02:22-16:01:22: SRFI, PLN CONNECTION 12:01:22: FOUNDATION DONE, PLAN PLN NEXT WEEK & WAITING SK PLN FROM XL 02:01:22-29:12:21: PONDASI OG 26:12:21-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-17:11:21: STO RELEASE, WAIT RFI BY HTI 14:11:21-03:11:21: WAIT APPROVAL TNP 31:10:21-20:10:21: NEED REVIEW RNP HUAWEI
|  | SUL-SN-MKS-1581 | 30720810031 | 2815332004 | IBS PAI_MAKASSAR | RORO JONGRANG 2021 [NEW] | TB | 119°30.47.63'E | 5°4.56.42'S | 30 | 30/155/335 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. KH.Jabbar Ashyri RT.003 RW.002, Kelurahan Pai, Kecamatan Biringkanaya, Kota Makassar, Provinsi Sulawesi Selatan | HTI | SUL-SN-MKS-1581 | CITRA_MART_PAI | COLO | XL | EAST | SULAWESI | Sulawesi Selatan | Kota Makassar | 6617724 | 2021-10-18 |  | 192 | > 150 days | 2021-11-17 | TBD | TBD | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-11-01 | [7 empty] | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | WAIT RFIN 24:02:22-17:02:22: STRENGTENING BY TBG 02:02:22: Issue Proposed Foundation in area Strengthening Tower, Need Check with TBG 26:01:22: PEMASANGAN KWH & CABLE TRAY 19:01:22-16:01:22: PONDASI BTS OG 12:01:22: WAITING PERMIT 02:01:22-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT 15:12:21-28:11:21: STO DECLARED, WAIT RFI BY HTI 21:11:21-18:11:21: UNDER ESR REVIEW
932 |  | BAL-BA-TAB-1496 | 30720720031 | 170863109 | 2016_DENBANTAS 1 | RORO JONGRANG 2021 [NEW] |  | 115°8.9.24'E | 8°31.28.31'S | 25 | 90/210/330 | 2021 | RORO JONGRANG 2021 [NEW] | Perumahan Griya Wahana Asri Banjar Denbantas Desa Denbantas Kec.Tabanan, Kab.Tabanan Prov.Bali | HTI | BAL-BA-TAB-1496 | TABANAN DENBANTAS | COLO | XL | East | BALINUSRA | Bali | Kab. Tabanan | 6617706 | 2021-10-15 |  | 195 | > 150 days | 2021-11-14 | W47-2021 | Nov-2021 | TBD | TBD | TBD | 2021-12-24 | W52-2021 | Dec-2021 | 2022-02-28 | W10-2022 | Feb-2022 | MW | [5 empty] | 2021-10-29 | [7 empty] | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | WAIT RFIN 24:02:22-16:01:22: PREPARE MATERIAL 12:01:22: PROCESS PR PO TO POCA 05:01:22-16:12:21: PROSES FINALISASI SUBCON ASSIGNMENT, WAIT RFIN BY HTI 15:12:21-28:11:21: MOBDEMOB OG, WAIT RFI BY HTI 24:11:21-17:11:21: MCP 26, OG PROCESS PERKUATAN, APPROVED REVISI DESIGN DI KONSULTAN, FABRIKASI MATERIAL PERKUATAN ESTIMASI 2 MINGGU SETELAH HASIL DESIGN APPROVED, PENGIRIMAN PERKUATAN MATERIAL 4 HARI, PEKERJAAN PERKUATAN 5 HARI, ESTIMASI START CME COLO 3 MINGGU 14:11:21: OG PROCESS PERKUATAN, ADA REVISI DESIGN DI KONSULTAN, FABRIKASI MATERIAL PERKUATAN ESTIMASI 2 MINGGU SETELAH HASIL DESIGN APPROVED, PENGIRIMAN PERKUATAN MATERIAL 4 HARI, PEKERJAAN PERKUATAN 5 HARI, ESTIMASI START CME COLO 3 MINGGU 10:11:21-07:11:21: ESR PREPARATION OG 03:11:21: STO DECLARE 29 OKTOBER 2021 31:10:21-27:10:21: REVIEW TNP OG 20:10:21: NEED REVIEW RNP HTI
932 |  | KAL-KU-TAR-0109 | 30715180031 | 230185104 | KAMPUNG 4 (RRI TARAKAN) | RELOCATION |  | 117°37.22.08'E | 3°17.57.3'N | 50 | 10/130/240 | 2021 |  | Jl. Manburungan, Kel. Kampung 4 RT.09, Kec. Tarakan Timur, Kota Tarakan Prov. Kalimantan Utara | CAA | KAL-KU-TAR-0109 | KAMPUNG4(RRITARAKAN) RELOCATION | COLO | TBG | JABO | KALIMANTAN | Kalimantan Utara | Kota Tarakan | 6617683 | 2021-10-06 |  | 50 | 31 - 60 days | 2021-11-05 | W45-2021 | Nov-2021 | TBD | TBD | TBD | TBD | TBD | TBD | 2021-11-28 | W49-2021 | Nov-2021 | MW | 2021-10-15 |  | 235200030349 | 6.6 |  | 2021-10-28 |  |  | 2021-11-25 | W48-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:11:21: RFIN 24:11:21-21:11:21: WAIT FOR CONNECT PLN & KWH METER, PLAN RFI 28 NOV 17:11:21: WAIT MATERIAL ONSITE 19 NOV, PLAN RFI 25 NOV 14:11:21: ME OG, PLAN FU PLN 15 NOV, PLAN CONNECT PLN 25 NOV 10:11:21: PONDASI BTS DONE, PARALEL WAIT PSB & CONNECT PLN 07:11:21: BOUWPLANK OG 03:11:21: START PONDASI 4 NOV,OG DELIVERY MATERIAL ME & MOUNTING 31:10:21: STO DECLARE 28 OCT, TEAM CME PREPARATION, PLAN PONDASI 5 NOV 20:10:21-17:10:21: NEED REVIEW RNP HTI 13:10:21: ERM PROSES
935 |  | SUM-SU-AKK-2205 | 30714850031 | 0226602010 | IBS IBS_MED0010_NORTH SUMATERA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 99°57.59.11'E | 2°7.6.67'N | 50 | 60/170/260 | 2021 |  | Dusun Sidodadi A, Kelurahan Kampung Padang, Kecamatan Pangkatan, Kabupaten Labuhanbatu, Propinsi Sumatera Utara | HTI | SUM-SU-AKK-2205 | PERK._PANGKATAN | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu | 6617716 | 2021-10-18 |  | 31 | 31 - 60 days | 2021-11-17 | W47-2021 | Nov-2021 | TBD | TBD | TBD | 2021-11-18 | W47-2021 | Nov-2021 | 2021-11-18 | W47-2021 | Nov-2021 | MW | 2021-10-28 | 2021-10-29 |  |  |  | 2021-10-26 |  |  | 2021-11-18 | W47-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:11:21: RFIN 17:11:21-14:11:21: INSTALASI PANEL OG, PLAN RFI 18 NOV 10:11:21-07:11:21: ME OG 03:11:21: PONDASI RBS OG 31:10:21: CME PREPARATION, STO DECLARE 26 OCT, PLAN PONDASI 4 NOV 27:10:21-20:10:21: NEED REVIEW RNP HTI
933 |  | KAL-KB-PTK-0809 | 30714840031 | #N/A | UJUNGPANDANG | RORO JONGRANG 2021 [NEW] |  | 109°17.57.37'E | 0°2.23.03'S | 30 | 80/160/320 | 2021 |  | Jl. Petani Rt 04 / 38 Kelurahan sungai jawiKec. Pontianak Kota. Pontianak kotaKalaimantan Barat | HTI | KAL-KB-PTK-0809 | ABDULLAH_SAIGON | COLO | TBG | Jabodetabek | KALIMANTAN | Kalimantan Barat | Kota Pontianak | 6617678 | 2021-10-06 |  | 43 | 31 - 60 days | 2021-11-05 | W45-2021 | Nov-2021 | TBD | TBD | TBD | 2021-11-19 | W47-2021 | Nov-2021 | 2021-11-22 | W48-2021 | Nov-2021 | MW | 2021-10-15 |  | 211002617744 |  |  | 2021-10-26 |  | 2021-11-12 | 2021-11-18 | W47-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18:11:21: RFIN 17:11:21: OG PROCESS PENCARIAN PENYAMBUNGAN SEMENTARA 5.5 KVA, PLAN PERMANEN 22 NOV 14:11:21: SRFI 12 NOV, PLAN FU PLN 15 NOV, PLAN CONNECT PLN 25 NOV 10:11:21: CME DONE, WAIT PSB & CONNECT PLN 07:11:21-03:11:21: EXCAVATION OG, PONDASI OG 31:10:21: BOUWPLANK OG, PLAN START EXCAVATION 1 NOV 27:10:21-20:10:21: NEED REVIEW TNP ALITA 17:10:21-13:10:21: NEED REVIEW RNP HUAWEI
935.4 |  | JAW-YO-BTL-0132 | 30714890031 | 150615126 | TUNDAN NGRAME | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°19.23.52'E | 7°49.10.47'S | 30 | 50/140/260/335 | 2021 |  | Kel.Tamantirto RT.04 Kec.Kasihan, Kab.Bantul Prov. DI Yogyakarta | EID | JAW-YO-BTL-0132 | TUNDAN NGRAME | COLO | XL | Central | JATENG | DI Yogyakarta | Kab. Bantul | 6617725 | 2021-10-18 |  | 39 | 31 - 60 days | 2021-11-17 | W47-2021 | Nov-2021 | TBD | TBD | TBD | 2021-11-30 | W49-2021 | Nov-2021 | 2021-11-26 | W48-2021 | Nov-2021 | MW | [5 empty] | 2021-10-25 |  |  | 2021-11-26 | W48-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26:11:21: RFIN 24:11:21-03:11:21: WAITING RFI BY EID, STIP RELEASED 25 OCT, PLAN RFI 30 NOV 31:10:21-27:10:21: WAITING CAF REALESED SITE PAIRING XL 20:10:21: NEED REVIEW RNP HTI
940 |  | JAW-YO-SMN-0064 | 30714580031 | 150701123 | GODEAN SIDOREJO | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 110°16.30.9'E | 7°45.46.22'S | 40 | 90/210/330 | 2021 | BLITZKRIEG 2021 [NEW] | Kel.Sidoluhur-Berjo Wetan RT.002 RW.007 Kec.Godean, Kab.Sleman Prov. DI Yogyakarta | EID | JAW-YO-SMN-0064 | SIDOREJO GODEAN | COLO | TBG | Central | JATENG | DI Yogyakarta | Kab. Sleman | 6617674 | 2021-10-05 |  | 97 | 91 - 120 days | 2021-11-04 | W45-2021 | Nov-2021 | 2021-11-05 | W45-2021 | Nov-2021 | 2021-11-25 | W48-2021 | Nov-2021 | 2022-01-08 | W02-2022 | Jan-2022 | MW | 2021-12-06 | 2021-12-08 | 521041710933 | 7.7 |  | 2021-10-25 |  |  | 2022-01-10 | W03-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:01:22: RFIN 09:01:22-08:01:22: RFI, WAIT RFIN 05:01:22-26:12:21: SRFI, PLN PROSES REGISTER, PLAN RFI W1 JAN 22 22:12:21: SRFI, OG PLN CONNECTION 19:12:21-15:12:21: ME OG 12:12:21-08:12:21: ERECTION ON TOP SECTION 05:12:21: CURRING TIME OG, PLAN ERECTION 7 DEC 01:12:21: POURING OG, PLAN RFI 20 DEC 28:11:21: PLAN POURING 30 NOV, PLAN RFI 20 DEC 24:11:21-21:11:21: REBARING OG, PLAN RFI 20 DEC 17:11:21: EXCAVATION OG 14:11:21-27:10:21: OPSIC OG, PLAN RELEASED END OF NOV, PLAN RFI EOM DECEMBER 28 DEC, COLO PADA SITE PERMANENISASI, 20:10:21-17:10:21-06:10:21: NEED REVIEW RNP EID
936 |  | KAL-KS-MRH-0948 | 30709160031 | 2209051003 | ALALAK KALIMANTAN | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 114°35.58.05'E | 3°15.5.97'S | 40 | 10/230/290 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Tatah Mesjid Rt. 15 Desa Tatah Mesjid, Kecamatan Alalak ,Kabupaten Barito Kuala Provinsi. Kalimantan Selatan | HTI | KAL-KS-MRH-0948 | ALALAK | COLO | TBG | Central | KALIMANTAN | Kalimantan Selatan | Kab. Barito Kuala | 6617643 | 2021-09-23 |  | 132 | 121 - 150 days | 2022-02-20 | W09-2022 | Feb-2022 | TBD | TBD | TBD | 2021-11-22 | W48-2021 | Nov-2021 | 2022-02-04 | W06-2022 | Feb-2022 | MW | 2021-11-10 |  | 221500582244 | 6.6 |  | 2021-10-25 |  |  | 2022-02-02 | W06-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02:02:22: RFIN 30:01:22: RFI, WAIT RFIN 26:01:22: SRFI, PLN CONNECTION 23:01:22: ERECTION OG 19:01:22: POURING OG, PLAN RFI 28 JAN 16:01:22-12:01:22: REBARING OG, PLAN COR PONDASI 19 JAN (LANGSIR MATERIAL) 09:02:22-02:01:22: BOREPILE OG, PARALEL PROSES BENDUNG BANJIR ROB, PLAN COR BOREPILE 11 JAN 29:12:21-12:12:21: HOLD KARENA TERGENANG BANJIR, PARALEL APPROVAL ADD LANGSIRAN 08:12:21-01:12:21: BOREPILE OG, GALIAN TERGENANG BANJIR 28:11:21: PREPARE BOREPILE, PLAN 29 NOV BOR 24:11:21-21:11:21: PREPARE BOREPILE, TERKENDALA PERIZINAN (NOT RECOMENDED PARALEL) 17:11:21-10:11:21: PROCESS SPH LANGSIR MATERIAL (JEMBATAN KAYU TIDAK BISA DILEWATI). ANKUR&TOWER DENGN JADWAL KAPAL 12, ETA 22/11. 07:11:21: TEAM PREPARATION & BOREPILE PREPARATION OG 03:11:21: DESIGNPACK DONE, REKOM DONE, PLAN START CME 9 NOV 31:10:21-27:10:21: IW CLEAR, PARALEL SOIL TEST DONE 24:10:21-26:09:21: SPK RELEASED COLO, PEKERJAAN B2S NEEW REVIEW IMB
594 |  | JAW-JB-CBI-0134 | 30705670031 | 1267022010 | IBS PARUNG PANJANG | ACTIVE - BLITZKRIEG 2021 [NEW]-H2 | TB | 106°34.0.9'E | 6°20.31.68'S | 40 | 50/150/305 | 2021 |  | Desa Parung Panjang Kp. Kaum RT.001 RW.001, Kec. Parung Panjang, Kab. Bogor Prov. Jawa Barat | EID | JAW-JB-CBI-0134 | MOH_TOHA_PARUNG_PANJANG | COLO | TBG | CENTRAL | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6617462 | 2021-08-10 |  | 101 | 91 - 120 days | 2021-09-09 | W37-2021 | Sep-2021 | 2021-09-08 | W37-2021 | Sep-2021 | 2021-11-22 | W48-2021 | Nov-2021 | 2021-11-22 | W48-2021 | Nov-2021 | MW | 2021-11-09 |  | 538531213966 | 10.6 |  | 2021-10-25 |  |  | 2021-11-19 | W47-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:11:21: RFIN 17:11:21: WAIT CONNECT PLN, PLAN RFI 22 NOV 14:11:21-10:11:21: CME DONE, WAIT CONNECT PLN & PSB PLN RELEASED 07:11:21: CME OG, PONDASI 03:11:21: OG CAF REVISED, TIDAK PERLU STACKING 31:10:21-27:10:21: FABRIKASI STACKING BASEFRAME OG, PLAN RFI W3 NOV 19:09:21: STO RECALL HOLD PEKERJAAN 08:30:2021:08:22:2021: NEED REVIEW POWER HUAWEI (HOLD, SAMPAI DENGAN PEMBERITAHUAN DARI XL, PROJECT H2) 08:18:2021: ERM PROSES, NEED REVIEW RNP EID 08:16:2021 : 08:10:2021 : SPK COLO RELEASED, ERM PROSES
941 |  | JAW-JT-SGN-1825 | 30714410031 | 140825104 | KALIJAMBESLO | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 110°48.29.52'E | 7°26.24.54'S | 40 | 90/210/330 | 2021 |  | Jl. Solo - Purwodadi KM. 15, RT. 08 / RW. 4, Ds. Pilangsari, Kel. Banaran, Kec. Kalijambe, Kab. Sragen Prov. Jawa Tengah | EID | JAW-JT-SGN-1825 | KEBAYANAN BANARAN KALIJAMBE | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Sragen | 6617673 | 2021-10-05 |  | 43 | 31 - 60 days | 2021-11-04 | W45-2021 | Nov-2021 | 2021-11-05 | W45-2021 | Nov-2021 | 2021-11-22 | W48-2021 | Nov-2021 | 2021-11-22 | W48-2021 | Nov-2021 | MW | 2021-10-25 |  | 520592269559 | 7.7 |  | 2021-10-21 |  |  | 2021-11-17 | W47-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:11:21: RFIN 14:11:21-14:11:21: RFI, WAIT FOR RFIN, WAIT DOC RFIN MITRA 10:11:21: SRFI, WAITING CONNECT PLN, PLAN RFI 16 NOV 07:11:21: SHELATER INSTALLATION OG 03:11:21-31:10:21: ME OG, PLAN SRFI 3 NOV 27:10:21: CME PREPARATION 20:10:21: READY TO DECLARE STO 17:10:21-06:10:21: NEED REVIEW RNP EID
939 |  | JAW-JT-KDS-0853 | 30714000031 | 1445481004 | LAU | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 110°52.36.77'E | 6°43.18.91'S | 39 | 90/210/330 | 2021 |  | Jl. Raya Jurang, Desa Lau RT.002 RW.003 Kec. Dawe, Kab. Kudus Prov. Jawa Tengah | EID | JAW-JT-KDS-0853 | LAU DAWE KUDUS | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Kudus | 6617674 | 2021-10-05 |  | 44 | 31 - 60 days | 2021-11-04 | W45-2021 | Nov-2021 | 2021-11-05 | W45-2021 | Nov-2021 | 2021-11-18 | W47-2021 | Nov-2021 | 2021-11-18 | W47-2021 | Nov-2021 | MW | 2021-10-25 |  | 520013357867 | 7.7 |  | 2021-10-19 |  |  | 2021-11-18 | W47-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18:11:21: RFIN 17:11:21: RFI, PLN DONE CONNECT, WAIT FOR RFIN 14:11:21-10:11:21: SRFI, PLAN CONNECT PLN, PLAN RFI 16 NOV 07:11:21: SHELTER INSTALATION OG 03:11:21-31:10:21: ME OG 27:10:21: PONDASI BTS OG 24:10:21: CME PREPARATION 20:10:21: STO DECLARE 19 OCT 2021, PREPARE TIM CME 17:10:21-06:10:21: NEED REVIEW RNP EID
945 |  | SUM-SU-MDN-2213 | 30709910031 | 225732007 | IBS PLAZA MILLENIUM | RELOCATION | TB | 98°38.40.27'E | 3°35.58.27'N | 38 | 90/210/330 | 2021 |  | Plaza Millenium, Jl. Kapten Muslim, Kelurahan Dwikora, Kecamatan Medan Helvetia, Kota Medan, Provinsi Sumatera Utara | CAA | SUM-SU-MDN-2213 | MILLENIUM PLAZA RELOCATION | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | Kota Medan | 6617705 | 2021-10-15 |  | 36 | 31 - 60 days | 2021-11-14 | W47-2021 | Nov-2021 | TBD | TBD | TBD | 2021-11-21 | W48-2021 | Nov-2021 | 2021-11-25 | W48-2021 | Nov-2021 |  | 2021-10-19 |  |  |  |  | 2021-10-18 |  |  | 2021-11-20 | W47-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:11:21: RFIN 17:11:21-07:11:21: ME OG, KWH KOSONG PLAN CONNECT PLN 25 NOV 03:11:21: FABRIKASI BASEFRAME, PARALEL ONSITE ME OG, PLAN RFI 21 NOV 31:10:21-26:10:21: FABRIKASI BASEFRAME, PLAN DONE 31 OCT 24:10:21: CME PREPARATION 20:10:21: STO DECLARE 18 OCT PREPARE TEAM CME
937 |  | SUM-SU-LBP-2256 | 30713250031 | 021221109 | SUMBER_REJO | RORO JONGRANG 2021 [NEW] | TB | 98°45.45.65'E | 3°36.47.95'N | 40 | 45/180/255 | 2021 |  | Jl. Pasar Belakang Pasar XI, Dusun XVI, Desa Bandar Klippa, Kec. Percut Sei Tuan, Kab. Deli Serdang, Prov. Sumatera Utara | HTI | SUM-SU-LBP-2256 | PERCUT_SEI_TUAN_SAMBIREJO_TIMUR | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617678 | 2021-10-06 |  | 38 | 31 - 60 days | 2021-11-05 | W45-2021 | Nov-2021 | TBD | TBD | TBD | 2021-11-10 | W46-2021 | Nov-2021 | 2021-11-23 | W48-2021 | Nov-2021 | MW | 2021-10-15 |  | 128050016992 | 6.6 |  | 2021-10-14 |  |  | 2021-11-13 | W46-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:11:21: RFIN 10:11:21-07:11:21: OG POWER CONNECTION, KWH KOSONG, PLAN CONNECT 23 NOV 03:11:21-26:10:21: ME OG 24:10:21: ME OG, PLAN RFI 6 NOV 20:10:21: RBS BTS PONDASI OG, PLAN ME GROUNDING 25 OCT 17:10:21: STO DECLARE 14 OCT CME PREPARATION 13:10:21: NEED REVIEW RNP HUAWEI 04:10:21: ERM PROSES
938 |  | SUM-SU-LBP-2252 | 30713240031 | 021215109 | SYAHMAD | RORO JONGRANG 2021 [NEW] | TB | 98°51.46.37'E | 3°34.15.06'N | 40 | 70/155/270 | 2021 |  | Jl. Purwo, Gg. Mangga, Desa Bakaran Batu, Kecamatan Lubuk PakamKabupaten Deli Serdang, Provinsi Sumatera Utara | HTI | SUM-SU-LBP-2252 | PERDAMEAN_PURWO | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617678 | 2021-10-06 |  | 38 | 31 - 60 days | 2021-11-05 | W45-2021 | Nov-2021 | TBD | TBD | TBD | 2021-11-10 | W46-2021 | Nov-2021 | 2021-11-23 | W48-2021 | Nov-2021 | MW | 2021-10-15 |  | 126120950900 | 6.6 |  | 2021-10-14 |  |  | 2021-11-13 | W46-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:11:21: RFIN 10:11:21-07:11:21: OG POWER CONNECTION, KWH KOSONG, PLAN CONNECT 23 NOV 24:10:21: ME OG, PLAN RFI 6 NOV 20:10:21: RBS BTS PONDASI OG, PLAN ME GROUNDING 25 OCT 17:10:21: STO DECLARE 14 OCT CME PREPARATION 13:10:21: NEED REVIEW RNP HUAWEI 04:10:21: ERM PROSES
936 |  | SUM-RI-RGT-0973 | 30713340031 | 040157109 | KAMPUNG SEBERANG | RORO JONGRANG 2021 [NEW] | TB | 102°32.29.38'E | 0°21.27.05'S | 40 | 25/150/220 | 2021 |  | Jl. Tengku Alim No.153 Rt.06 Kel. Kampung Pulau, Kec. Rengat, Kab. Indragiri Hulu, Prov. Riau | HTI | SUM-RI-RGT-0973 | KAMPUNG_BESAR_SEBERANG | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Indragiri Hulu | 6617678 | 2021-10-06 |  | 36 | 31 - 60 days | 2021-11-05 | W45-2021 | Nov-2021 | TBD | TBD | TBD | 2021-11-10 | W46-2021 | Nov-2021 | 2021-11-14 | W47-2021 | Nov-2021 | MW | 2021-10-15 |  | 184103616402 | 6.6 |  | 2021-10-14 |  | 2021-11-08 | 2021-11-11 | W46-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11:11:21: RFIN 10:11:21: PLN DONE CONNECT, WAIT RFIN 08:11:21: SRFI NOTIF, OG CONNECT PLN 07:11:21: PONDASI RBS & TRAY DONE, PLAN PLN CONNECT 8 Nov, PLAN RFI 9 Nov 03:11:21: OG CME, NO REGISTER DONE RELEASED, PLAN BAYAR BPUJL 4 NOV 31:10:21: WAIT PLN CONNECT 27:10:21: RBS BTS PONDASI OG, PLAN RFI W1 NOV 20:10:21: RBS BTS PONDASI OG, PLAN ME GROUNDING 25 OCT 17:10:21: STO DECLARE 14 OCT CME PREPARATION 13:10:21: NEED REVIEW RNP HUAWEI 04:10:21: ERM PROSES
702 |  | SUM-SU-STB-2215 | 30700880031 | 021291109 | SC-BJ1507G | RORO JONGRANG 2021 [NEW] | TB | 98°24.23.62'E | 3°37.23.09'N | 50 | 45/230/330 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Selayang, Lingk. XI Rambung Putih, Desa Pekan Selesai, Kec. Selesai, Kab. Langkat | HTI | SUM-SU-STB-2215 | SELESAI_PEKAN_SELESAI | COLO | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6617470 | 2021-08-12 |  | 109 | 91 - 120 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-11-30 | W49-2021 | Nov-2021 | 2021-11-30 | W49-2021 | Nov-2021 | MW | 2021-09-04 |  | 122030625513 | 6.6 |  | 2021-10-04 |  |  | 2021-11-29 | W49-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28:11:21: RFIN 28:11:21: PLN CONNECTION OG, PLAN RFI 29 NOV 24:11:21-03:11:21: OG PROCESSEXTEND TOWER, PLAN EXTEND SELESAI 26 NOV, PLAN RFI 30 NOV 31:10:21-13:09:21: NEED PENAMBAHAN KETINGGIAN TOWER, PROSES REVISI IMB, DAN PERLUASAN IW 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
932 |  | SUM-SS-PLG-1275 | 30713170031 | 0716752004 | IBS TANJUNG BAKIA | RORO JONGRANG 2021 [NEW] | TB | 104°41.55.9'E | 2°58.0.37'S | 50 | 90/190/290 | 2021 | RORO JONGRANG 2021 [NEW] | Jl.Tanjung Bakia RT.06/RW.03 Kel.Bukit Baru Kec.Ilir Barat I, Kota.Palembang | HTI | SUM-SS-PLG-1275 | TALANG_KELAPA_SUKOSARI | COLO | TBG | West | SUMBGSEL | Sumatera Selatan | Kota Palembang | 6617657 | 2021-09-26 |  | 35 | 31 - 60 days | 2021-10-26 | W44-2021 | Oct-2021 | TBD | TBD | TBD | 2021-11-14 | W47-2021 | Nov-2021 | 2021-11-14 | W47-2021 | Nov-2021 | MW | 2021-10-04 |  | 141203544150 | 6.6 |  | 2021-10-14 |  |  | 2021-10-31 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:10:21: RFIN 27:10:21-24:10:21: ME OG PLAN SRFI END OF OCT 20:10:21: RBS BTS PONDASI OG, PLAN ME GROUNDING 25 OCT 17:10:21: STO DECLARE 14 OCT CME PREPARATION 13:10:21: NEED REVIEW RNP HUAWEI 04:10:21: ERM PROSES
935 |  | SUM-SB-SRK-0940 | 30713160031 | 030780126 | BALAI PANJANG_LAREH SAGO HALABAN | RORO JONGRANG 2021 [NEW] | TB | 100°42.49.93'E | 0°17.17.41'S | 40 | 55/240/310 | 2021 |  | Jorong Kayu Tanam, Nagari Labuah Gunuang, Kec. Lareh Sago Halaban, Kab. Lima Puluh Kota, Prov. Sumatera Barat | HTI | SUM-SB-SRK-0940 | LABUAH_GUNUANG | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Lima Puluh Kota | 6617678 | 2021-10-06 |  | 34 | 31 - 60 days | 2021-11-05 | W45-2021 | Nov-2021 | TBD | TBD | TBD | 2021-11-15 | W47-2021 | Nov-2021 | 2021-11-15 | W47-2021 | Nov-2021 | MW | 2021-10-15 |  | 134520326445 | 6.6 |  | 2021-10-13 |  |  | 2021-11-09 | W46-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:11:21: RFIN 07:11:21-31:10:21: SRFI, WAIT CONNECT PLN, KWH KOSONG, PLAN CONNECT PLN 10 NOV, PLAN RFI 15 NOV 27:10:21: PEMASANGAN TRAY, PLAN TRAY DONE 29 OCT 23:10:21 - 20:10:21: PONDASI BTS OG, PLAN ME GROUNDING 25 OCT 17:10:21-13:10:21: STO DECLARE, CME PREPARARTION 10:10:21: NEED REVIEW TNP ALITA
932 |  | SUM-LA-GNS-1137 | 30713150031 | 1011121023 | PUJODADI TRIMURJO | RORO JONGRANG 2021 [NEW] |  | 105°15.58.36'E | 5°5.3.44'S | 40 | 150/280/350 | 2021 |  | Dusun IV RT.015/008, Desa Pujodadi, Kec. Trimurjo, Kab. Lampung Tengah, Prov. Lampung. | HTI | SUM-LA-GNS-1137 | BUMI_NABUNG_UTARA | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Tengah | 6617678 | 2021-10-06 |  | 23 | < 30 days | 2021-11-05 | W45-2021 | Nov-2021 | TBD | TBD | TBD | 2021-11-15 | W47-2021 | Nov-2021 | 2021-11-15 | W47-2021 | Nov-2021 | MW | 2021-10-15 |  | 172801510119 | 6.6 |  | 2021-10-13 |  |  | 2021-10-29 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29:10:21: RFIN 27:10:21: SRFI, PLAN RFI 29 OCT 24:10:21-20:10:21: ME GROUNDING OG 17:10:21: RBS/BTS FONDATION, NEED SK PLN 13:10:21: STO DECLARE, CME PREPARATION 10:10:21: NEED REVIEW RNP HUAWEI
944 |  | JAW-JT-KLN-0919 | 30712620031 | 1440572003 | IBS TELOYO | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°45.16.02'E | 7°37.22.48'S | 40 | 30/120/295 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Teloyo - Banjaran Teloyo RT.01 RW.03 Kec. Wonosari, Kab. Klaten Prov. Jawa Tengah | EID | JAW-JT-KLN-0919 | TELOYO | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Klaten | 6617651 | 2021-09-27 |  | 35 | 31 - 60 days | 2021-10-27 | W44-2021 | Oct-2021 | TBD | TBD | TBD | 2021-10-30 | W44-2021 | Oct-2021 | 2021-11-05 | W45-2021 | Nov-2021 | MW | 2021-10-04 |  | 524020698374 | 7.7 |  | 2021-10-07 | 2021-10-07 |  | 2021-11-01 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01:11:21:RFIN 31:10:21-27:10:21: SRFI 24:10:21-20:10:21: ME GROUNDING OG 17:10:21: PONDASI RBS BTS OG 13:10:21: CME PREPARATION, NEED SK PLN 06:10:21-04:10:21: ESR PROSES NEED REVIEW RNP EID
942 |  | JAW-JT-SMG-0624 | 30712610031 | 1441002007 | IBS DEMETA BAMBAN KEREP | RELOCATION | TB | 110°21.22.61'E | 7°1.1.34'S | 30 | 90/210/330 | 2021 | RELOCATION | Jl. Pucung, Kel. Bamban Kerep RT.04 RW.01 Kec. Ngaliyan, Kota Semarang Prov. Jawa Tengah | EID | JAW-JT-SMG-0624 | PUCUNG RAYA INDUSTRI RELOCATION | COLO | TBG | Central | JATENG | Jawa Tengah | Kota Semarang | 6617648 | 2021-09-24 |  | 33 | 31 - 60 days | 2021-10-24 | W44-2021 | Oct-2021 | TBD | TBD | TBD | 2021-10-24 | W44-2021 | Oct-2021 | 2021-10-28 | W44-2021 | Oct-2021 | MW | 2021-10-04 |  | 523024864892 | 7.7 |  | 2021-10-07 |  |  | 2021-10-27 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:10:21: RFIN 24:10:21-20:10:21: SRFI PROSES CONNECT PLN 13:10:21: PONDASI RBS OG 10:10:21: CME PREPARATION 04:10:2021-26:09:21: NEED REVIEW RNP EID
563 |  | KAL-KT-KSN-0435 | 30704160031 | 210138104 | MENDAWAI_KATINGAN | ACTIVE - BLITZKRIEG 2021 [NEW] | SMI | 113°16.18.37'E | 2°59.35.81'S | 60 | 0/180/300 | 2021 | BLITZKRIEG 2021 [NEW] | JL.Dahlia Ds.Mendawai Kec.Mendawai, Kab. Katingan Kalimantan Tengah | HTI | KAL-KT-KSN-0435 | MENDAWAI_MENDAWAI | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Tengah | Kab. Katingan | 6617415 | 2021-08-04 |  | 62 | 61 - 90 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2021-10-08 | W41-2021 | Oct-2021 | MW | 2021-09-07 |  | 224400773973 | 6.6 |  | 2021-10-07 |  |  | 2021-10-05 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:10:21-29:09:21: SRFI, PLAN CONNECT PLN 30 SEP, COLLECTING DOC RFIN 26:09:21: ME OG, MATERIAL TRAY ON DELIVERY KARENA AKSES MENUJU SITE HANYA BISA MENGGUNAKAN KAPAL KELOTOK, IMBAS BANJIR JALANAN MASIH BELUM BISA DILEWATI 19:09:21: PONDASI BTS OG 15:09:21: 13:09:21: 08:09:21: 06:09:21: STO DECLARE 2 SEPT 2021, PREPARE TIM CME, REPLAN RFI W4 SEPT 30:08:21:22:08:21: NEED REVIEW TNP ALITA 22:09:21: PONDASI BTS OG 22:08:21: 18:08:21: 16:08:21:09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES NEED REVIEW TNP ALITA
694 |  | SUM-SU-LBP-2290 | 30703910031 | 0226992001 | IBS MULIOREJO | RORO JONGRANG 2021 [NEW] | TB | 98°33.59.51'E | 3°36.3.74'N | 30 | 90/220/300 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Setia, Dusun VII, Desa Muliorejo, Kecamatan Sunggal, Kabupaten Deli Serdang, Propinsi Sumatera Utara | HTI | SUM-SU-LBP-2290 | LUBUK_PAKAM_TANJUNG_GARBUS_I | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617547 | 2021-08-26 |  | 49 | 31 - 60 days | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-10-22 | W43-2021 | Oct-2021 | 2021-10-22 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 122021125525 | 6.6 |  | 2021-10-04 |  |  | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: PONDASI OG 08:09:21: 06:09:21: CME PREPARATION
785 |  | SUM-SU-KIS-1901 | 30705630031 | 021918109 | PELITA 2 GG SAUDARA | RORO JONGRANG 2021 [NEW] | TB | 99°38.1.1'E | 2°58.53.18'N | 30 | 30/150/220 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. SM. Raja Gang Rahmad I Lingkungan VII Kelurahan Kisaran Timur Kecamatan Kota Kisaran Timur | HTI | SUM-SU-KIS-1901 | TELADAN_PELITA | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Asahan | 6617547 | 2021-08-26 |  | 44 | 31 - 60 days | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-10-28 | W44-2021 | Oct-2021 | 2021-10-28 | W44-2021 | Oct-2021 | MW | 2021-10-04 |  | 121111105973 | 6.6 |  | 2021-10-04 |  |  | 2021-10-09 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:10:21-19:09:21: SRFI 15:09:21: RBS/BTS PONDASI 13:09:21: CME PREPARATION
763 |  | SUM-LA-BDL-1130 | 30701710031 | T000821 | SUKAMAJU | RORO JONGRANG 2021 [NEW] | SKP | 105°14.41.21'E | 5°28.16.46'S | 51 | 15/170/275 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Laksamana RE. Martadinata Kel. Sukamaju Teluk Betung Barat | HTI | SUM-LA-BDL-1130 | TIMUR_SUKAMAJU_REMARTADINATA | COLO | TBG | West | LAMPUNG | Lampung | Kota Bandar Lampung | 6617490 | 2021-08-13 |  | 63 | 61 - 90 days | 2021-09-12 | W38-2021 | Sep-2021 | 2021-09-11 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 171802765325 | 6.6 |  | 2021-10-04 |  |  | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-13:09:21: SRFI 08:09:21: POWER CONNECTION PROSES 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: ERM PROSES, NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
703 |  | SUM-SU-STB-2218 | 30700890031 | 022011109 | KEBUN LADA -2 | RORO JONGRANG 2021 [NEW] | TB | 98°25.54.25'E | 3°50.26.25'N | 50 | 30/150/260 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Pendidikan, Dusun II, Desa Tanjung Mulia, Kec. Hinai, Kab. Langkat, Prov. Sumatera Utara | HTI | SUM-SU-STB-2218 | PERK_TANJUNG__BERINGIN | COLO | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6617470 | 2021-08-12 |  | 63 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 122150553680 | 6.6 |  | 2021-10-04 |  |  | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: PONDASI OG 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
742 |  | JAW-JI-KPN-4398 | 30700960031 | 1647592001 | IBS GN JIDOR/KALIGADUNG | RORO JONGRANG 2021 [NEW] | TB | 112°48.44.96'E | 8°13.38.93'S | 50 | 165/260/340 | 2021 | RORO JONGRANG 2021 [NEW] | Gunung Jidor RT. 04 RW. 01 Desa Gadungsari, Kecamatan Tirtoyudo, Kabupaten Malang, Provinsi Jawa Timur | HTI | JAW-JI-KPN-4398 | TIRTOYUDO GADUNGSARI | COLO | TBG | East | JATIM | Jawa Timur | Kab. Malang | 6617471 | 2021-08-12 |  | 64 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-09-04 |  | 513080337178 | 6.6 |  | 2021-10-04 |  |  | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-29:09:21: POWER CONNECTION PROSES 22:09:21: ME OG 19:09:21:15:09:21: 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
NEW SPK |  | SUM-SS-KAG-1256 | 30734050031 | 071420109 | BENAWA | BP2022 | TB | 104°44.45.6'E | 3°35.52.4'S | 40 | 40/210/355 | 2022 | New site 2022 - P2 | Dusun V Desa Benawa, Kec. Teluk Gelam, Kab. OKI, Prov. Sumatera SelatanKec. Teluk GelamKab. OKI, Provinsi Sumatera Selatan | HTI | SUM-SS-KAG-1256 | BENAWA | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ilir | 6617992 | 2022-01-28 | 2022-01-28 | 58 | 31 - 60 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | 2022-02-01 | 2022-02-02 | 149100150095 | 6.6 |  | 2022-03-22 |  |  | 2022-03-27 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:03:22: RFIN 23:03:22: ME OG 20:03:22-16:03:22: ME OG, WAIT STO 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
754 |  | JAW-JI-KDR-4322 | 30701010031 | 1647422004 | IBS PLEMAHAN PAGU | RORO JONGRANG 2021 [NEW] | TB | 112°9.17.86'E | 7°44.32.93'S | 40 | 20/240/295 | 2021 | RORO JONGRANG 2021 [NEW] | Tegowangi RT.03 RW.03, Desa Tegowangi, Kecamatan Plemahan, Kabupaten Kediri, Provinsi Jawa Timur | HTI | JAW-JI-KDR-4322 | PLEMAHAN TEGOWANGI | COLO | TBG | East | JATIM | Jawa Timur | Kab. Kediri | 6617471 | 2021-08-12 |  | 68 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  | 2021-09-25 | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
723 |  | JAW-JI-TBN-4070 | 30700970031 | 1648622004 | IBS BANCAR | RORO JONGRANG 2021 [NEW] | TB | 111°47.1.53'E | 6°47.0.78'S | 50 | 0/120/280 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Bancar RT. 06 RW. 02, Kelurahan Bancar, Kecamatan Bancar, Kabupaten Tuban, Provinsi Jawa Timur | HTI | JAW-JI-TBN-4070 | BANCAR BANCAR | COLO | TBG | East | JATIM | Jawa Timur | Kab. Tuban | 6617471 | 2021-08-12 |  | 67 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  | 2021-09-25 | 2021-10-18 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: ERM PROSES, NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
719 |  | JAW-JI-JBG-4175 | 30700920031 | 1649472001 | IBS PULO GEDANG | RORO JONGRANG 2021 [NEW] | TB | 112°14.54.31'E | 7°27.22.5'S | 50 | 100/180/250 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Delima RT. 08 RW. 05 Dukuhan Kedung Bajul, Kelurahan Pulo Gedang, Kecamatan Tembelang, Kabupaten Jombang, Provinsi Jawa Timur | HTI | JAW-JI-JBG-4175 | TEMBELANG PULO GEDANG | COLO | TBG | East | JATIM | Jawa Timur | Kab. Jombang | 6617471 | 2021-08-12 |  | 67 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  |  | 2021-10-18 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21: 08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: READY TO DECLARE STO 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
758 |  | SUM-SS-PKB-1260 | 30700940031 | 0717522007 | IBS PERUM HANDAYANI | RORO JONGRANG 2021 [NEW] | TB | 104°39.51.69'E | 2°53.26.58'S | 30 | 30/220/290 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Kelompok Tani Dusun, Desa Pangkalan Benteng, Kecamatan Talang Kelapa, Kabupaten Banyuasin, Provinsi Sumatera Selatan | HTI | SUM-SS-PKB-1260 | SUKOMORO_PANGKALAN_BENTENG | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Banyuasin | 6617471 | 2021-08-12 |  | 60 | 31 - 60 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 141203536711 | 6.6 |  | 2021-10-04 |  |  | 2021-10-11 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-19:09:21: SRFI 15:09:21: 13:09:21: ME OG 08:09:21: PONDASI RBS/BTS OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
718 |  | JAW-JI-JBG-4179 | 30700870031 | 164235104 | JOMBATAN_JMB | RORO JONGRANG 2021 [NEW] | SKP | 112°13.33.64'E | 7°32.56.15'S | 30 | 105/155/330 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Dewi Sartika, Desa Sengon RT.007 RW.01B kec.Jombang, Kab.Jombang Prov.Jawa Timur | HTI | JAW-JI-JBG-4179 | JOMBANG SENGON | COLO | TBG | East | JATIM | Jawa Timur | Kab. Jombang | 6617466 | 2021-08-12 |  | 69 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-19 | W43-2021 | Oct-2021 | 2021-10-19 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 514531761385 | 6.6 |  | 2021-10-04 |  | 2021-09-25 | 2021-10-20 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-29:09:21: POWER CONNECTION PROSES 22:09:21:19:09:21: 15:09:21: SRFI 13:09:21: 08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: READY TO DECLARE STO 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
671 |  | JAW-JI-SDA-4316 | 30700980031 | 1650362001 | IBS KALITENGAH_SDA_SDA | RORO JONGRANG 2021 [NEW] | TB | 112°43.5.2'E | 7°30.22.79'S | 35 | 160/265/350 | 2021 | RORO JONGRANG 2021 [NEW] | Putat RT. 2 RW 1, Desa Putat, Kecamatan Tanggulangin, Kabupaten Sidoarjo, Provinsi Jawa Timur | HTI | JAW-JI-SDA-4316 | TANGGULANGIN KALITENGAH | COLO | TBG | East | JATIM | Jawa Timur | Kab. Sidoarjo | 6617471 | 2021-08-12 |  | 74 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 511821724552 | 6.6 |  | 2021-10-04 |  | 2021-09-25 | 2021-10-25 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:10:21: RFIN 20:10:21-15:09:21: SRFI 13:09:21:06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: ERM PROSES, NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
752 |  | JAW-JI-NGW-3676 | 30700930031 | 1650712001 | IBS SC_EJ_INFILL48 | RORO JONGRANG 2021 [NEW] | TB | 111°26.19.85'E | 7°24.45.86'S | 30 | 0/100/245 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Padas RT. 003 RW. 014, Kelurahan Jururejo, Kecamatan Ngawi, Kabupaten Ngawi, Provinsi Jawa Timur | HTI | JAW-JI-NGW-3676 | JURUREJO NGAWI | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ngawi | 6617471 | 2021-08-12 |  | 68 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 515042230448 | 6.6 |  | 2021-10-04 |  |  | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-29:09:21: COMMCASE OPPEN, SRFI OG 29:09:21-22:09:21: ME OG, COMMCASE PROSES NEGOSIASI DENGAN LL TERKAIT EXPAND LAHAN OLEH TIM ARCOM 19:09:21:15:09:21: 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
697 |  | SUM-AC-JTH-0741 | 30700900031 | 010362109 | PRADA / TBG_NAD117-PINEUNG | RORO JONGRANG 2021 [NEW] | TB | 95°20.21.66'E | 5°30.6.46'N | 40 | 40/160/260 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Lamkawe, Kec. Darul Imarah, Kab. Aceh Besar, Prov. Nanggro Aceh Darusalam | HTI | SUM-AC-JTH-0741 | LAM_KAWE | COLO | TBG | West | SUMBAGUT | Aceh | Kab. Aceh Besar | 6617470 | 2021-08-12 |  | 64 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 111120269512 | 6.6 |  | 2021-10-04 |  |  | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21:PONDASI OG 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW TNP ALITA 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
768 |  | SUM-LA-MET-1131 | 30701700031 | 1012982003 | IBS YOSODADI | RORO JONGRANG 2021 [NEW] | TB | 105°19.29.43'E | 5°6.53.1'S | 30 | 70/160/350 | 2021 | RORO JONGRANG 2021 [NEW] | Yosodadi RT. 8 RW. 3 Desa Yosodadi, Kecamatan Metro Timur, Kota Metro, Provinsi Lampung | HTI | SUM-LA-MET-1131 | METRO_TIMUR_YOSODADI | COLO | TBG | West | LAMPUNG | Lampung | Kota Metro | 6617471 | 2021-08-12 |  | 63 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 172000864111 | 6.6 |  | 2021-10-04 |  |  | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-26:09:21: SRFI 22:09:21: 19:09:21:15:09:21: 13:09:21: ME OG 08:09:21: RBS BTS PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW TNP ALITA 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
770 |  | SUM-SU-LBP-2271 | 30700910031 | 021211109 | BANGUN_REJO_2 | RORO JONGRANG 2021 [NEW] | TB | 98°46.42.7'E | 3°30.1.72'N | 50 | 0/170/270 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Bandar Labuhan No. 83, Dusun V, Desa Bandar Labuhan, Kec. Tanjung Morawa, Kab. Deli Serdang, Prov. Sumatera Utara | HTI | SUM-SU-LBP-2271 | LIMAU_MANIS | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617470 | 2021-08-12 |  | 60 | 31 - 60 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 126131201701 | 6.6 |  | 2021-10-04 |  |  | 2021-10-11 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: 08:09:21: RBS/BTS PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW TNP ALITA 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
696 |  | SUM-SU-LBP-2269 | 30700950031 | 0226822007 | IBS MED0117 | RORO JONGRANG 2021 [NEW] | TB | 98°44.42.5'E | 3°37.9.95'N | 30 | 0/160/270 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Pembinaan, Dusun III, Kelurahan Bandar Setia, Kecamatan Percut Sei Tuan, Kabupaten Deli Serdang, Propinsi Sumatera Utara | HTI | SUM-SU-LBP-2269 | TEMBUNG_PEMBANGUNAN | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617471 | 2021-08-12 |  | 80 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-22 | W43-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 128050014438 | 6.6 |  | 2021-10-04 |  |  | 2021-10-31 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:10:21: RFI, NEED RFIN 26:10:21: PENGADAAN KWH, PLAN CONNECT 29 OCT 24:10:21-19:09:21 SRFI 15:09:21: ME OG 13:09:21: PONDASI OG 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: ERM PROSES, NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
776 |  | SUM-SS-PKB-1262 | 30705590031 | 0717512007 | IBS TALANG BETUTU SUKARAMI | RORO JONGRANG 2021 [NEW] | TB | 104°40.23.56'E | 2°53.53.05'S | 30 | 90/180/350 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. H.M. Yusuf Senen, RT. 005 RW. 002, Kelurahan Talang Betutu, Kecamatan Sukarami, Kota Palembang, Provinsi Sumatera Selatan | HTI | SUM-SS-PKB-1262 | SUKOMORO_BOM_BARLAN | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Banyuasin | 6617471 | 2021-08-12 |  | 60 | 31 - 60 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-25 | W44-2021 | Oct-2021 | 2021-10-25 | W44-2021 | Oct-2021 | MW | 2021-10-04 |  | 141203538574 | 6.6 |  | 2021-10-04 |  |  | 2021-10-11 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-06:10:21: SRFI 04:10:21-19:09:21: ME OG 15:09:21: PONDASI OG 13:09:21: CME PREPARATION 08:09:21: READY TO DECLARE STO 30:08:21: 22:08:21: NEED REVIEW RNP HUAWEI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
781 |  | SUM-SS-PLG-1274 | 30711860031 | 0717922023 | IBS SAKO | RORO JONGRANG 2021 [NEW] | TB | 104°48.23.53'E | 2°54.47.04'S | 40 | 70/150/260 | 2021 | RORO JONGRANG 2021 [NEW] | JLN. SEMATANG BORANG RT.006 RW. 010 KEL.SAKO KEC.SAKO KOTA PALEMBANG | HTI | SUM-SS-PLG-1274 | SAKO_SAKO | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kota Palembang | 6617470 | 2021-08-12 |  | 64 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-26 | W44-2021 | Oct-2021 | 2021-10-26 | W44-2021 | Oct-2021 | MW | 2021-10-04 |  | 141103467801 | 6.6 |  | 2021-10-04 |  |  | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21: RBS BTS PONDASI OG 06:10:21: STO DECLARE 4 OCT, CME PREPARATION 04:10:21-26:09:21: READY TO DECLARE STO 22:09:21: 19:09:21: 13:09:21: NEED REVIEW POWER HTI 08:09:21: RND NOK 22:08:21: 18:08:21: NEED REVIEW RNP HUWAWEI, ERM PROSES 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
706 |  | SUM-RI-BKN-1159 | 30701000031 | 0415232001 | IBS BANGKINANG | RORO JONGRANG 2021 [NEW] | TB | 101°1.2.52'E | 0°19.40.25'N | 40 | 40/110/280 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Subrantas Siswanto Lingkungan Candika, Kelurahan Langgining, Kecamatan Bangkinang, Kabupaten Kampar, Provinsi Riau | HTI | SUM-RI-BKN-1159 | BANGKINANG_KOTA_LANGGINI | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Kampar | 6617471 | 2021-08-12 |  | 67 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-28 | W44-2021 | Oct-2021 | 2021-10-28 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 181901192343 | 6.6 |  | 2021-10-04 |  |  | 2021-10-18 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-29:09:21: SRFI, ISSUE PERKUATAN 22:09:21:19:09:21: ME OG 15:09:21: 13:09:21: PONDASI BTS RBS NEED PERKUATA, PROSES FABRIKASI PERKUATAN 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: ERM PROSES, NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
|  | SUM-SU-STB-2225 | 30734900031 | 22021109 | HINAI KIRI HULU | BP2022 | TB | 98°27.46.15'E | 3°49.35.15'N | 50 | 10/140/280 | 2022 |  | JL. Caraka , Dusun II , Desa Hinai Kanan, Kec. Hinai, Kab. Langkat, Prov. Sumatera Utara. | HTI | SUM-SU-STB-2225 | HINAI_KANAN | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Langkat | 6618183 | 2022-04-06 | 2022-04-06 | -6 | < 30 days | 2022-05-06 | W19-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-10 | 2022-04-11 | 122150561374 | 6.6 |  | 2022-04-12 |  |  | 2022-03-31 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | RFI DONE 31 MAR, STO 12 APR ON NEW SITE ID 10:04:22: ERM PROCESS 06:04:22: SPK RECEIVED
782 |  | SUM-JA-JMB-0503 | 30711850031 | 060083104 | KUMPEH | RORO JONGRANG 2021 [NEW] | SMI | 103°38.56.51'E | 1°33.53.86'S | 50 | 120/250/320 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Raden Patah, Kel. Sijinjing RT 05 RW 02, Kec. Jambi Timur, Kota Jambi, Prov. Jambi | HTI | SUM-JA-JMB-0503 | SIJENJANG | COLO | TBG | West | SUMBAGSEL | Jambi | Kota Jambi | 6617467 | 2021-08-12 |  | 68 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-10-04 |  | 143005622990 | 6.6 |  | 2021-10-04 |  |  | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21: RBS BTS PONDASI OG 06:10:21: STO DECLARE, CME PREPARATION 04:10:21-26:09:21: READY TO DECLARE STO 22:09:21: 19:09:21:13:09:21: NEED REVIEW POWER HTI 08:09:21: RND NOK 08:24:2021:22:08:21: 18:08:21: NEED REVIEW RNP HUWAWEI, ERM PROSES 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
682 |  | KAL-KS-BJB-1113 | 30705610031 | 220246109 | PLAN MACRO CLUSTER (WBB BANJARMASIN) 30 | RORO JONGRANG 2021 [NEW] | SKP | 114°43.5.38'E | 3°27.36.2'S | 50 | 90/260/340 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Ahmad Yani KM 21 Gg.Kenanga 1 Rt.06/02, Kel. Landasan Ulin Barat Kec. Liang Anggang, Kalimantan Selatan | HTI | KAL-KS-BJB-1113 | LANDASAN_ULIN_SELATAN | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | Kota Banjarbaru | 6617469 | 2021-08-12 |  | 75 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-24 | W44-2021 | Oct-2021 | 2021-10-27 | W44-2021 | Oct-2021 | MW | 2021-10-04 |  | 221600433107 | 6.6 |  | 2021-10-04 |  | 2021-10-10 | 2021-10-26 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26:10:21: RFIN, MINUS DOC PLN PSB 24:10:21: SRFI, WAITING KONFIRMASI KETERSEDIAAN PERANGKAT DARI PIHAK HTI (PLN PLAN MULTIGUNA) 20:10:21-10:10:21: SRFI, PROSES CONNECT PLN, PLAN PLN CONNECT 26 OCT 06:10:21: STO DECLARE 4 OCT, PROSES PLN CONNECTION 04:10:21-29:09:21: ME OG 26:09:21-19:09:21: PONDASI BTS OG 15:09:21: PREPARE CME, MATERIAL ON DELIVERY 13:09:21: 06:09:21: READY TO DECLARE STO 30:08:21: 22:08:21: NEED REVIEW TNP ALITA 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
775 |  | SUL-ST-PAL-1123 | 30705680031 | 260135109 | TAIPA | RORO JONGRANG 2021 [NEW] | SKP | 119°52.9.31'E | 0°46.28.05'S | 50 | 150/250/350 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Taluadea, Kel Taipa Kec. Palu Utara Kota Palu | HTI | SUL-ST-PAL-1123 | PALU_UTARA_TAIPA | COLO | TBG | East | SULAWESI | Sulawesi Tengah | Kota Palu | 6617469 | 2021-08-12 |  | 64 | 61 - 90 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-10-28 | W44-2021 | Oct-2021 | 2021-10-28 | W44-2021 | Oct-2021 | MW | 2021-10-04 |  | 312300275192 | 6.6 |  | 2021-10-04 |  |  | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-29:09:21: SRFI,BP PAID 26:09:21-22:09:21: ME OG 13:09:21: CME PREPARATION 08:09:21: READY DECLARE STO 30:08:21:22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
|  | SUM-SU-STB-2229 | 30735160031 | 22012109 | SICANGGANG HINAI | BP2022 | TB | 98°29.25.08'E | 3°51.36.0'N | 50 | 100/210/280 | 2022 |  | Lingkungan VII, Kel. Hinai Kiri, Kec. Secanggang, Kab. Langkat, Prov. Sumatera Utara | HTI | SUM-SU-STB-2229 | HINAI_KIRI | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Langkat | 6618183 | 2022-04-06 | 2022-04-06 | -6 | < 30 days | 2022-05-06 | W19-2022 | May-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-10 | 2022-04-11 | 122140915926 | 6.6 |  | 2022-04-12 |  |  | 2022-03-31 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | RFI DONE 31 MAR, STO 12 APR ON NEW SITE ID 10:04:22: ERM PROCESS 06:04:22: SPK RECEIVED
699 |  | SUM-SU-STB-2219 | 30701240031 | 022014109 | SMA 1 SELESAI | RORO JONGRANG 2021 [NEW] | TB | 98°24.2.05'E | 3°36.11.05'N | 40 | 25/120/230 | 2021 | RORO JONGRANG 2021 [NEW] | Lingkungan VIII Pasar II, Kel. Pekan Selesai, Kec. Selesai, Kab. Langkat, Prov. Sumatera Utara | HTI | SUM-SU-STB-2219 | PEKAN_SELESAI | COLO | TBG | West | SUMBAGUT | Aceh | Kab. Langkat | 6617456 | 2021-08-09 |  | 66 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-21 | W43-2021 | Oct-2021 | 2021-10-21 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 122030622843 | 6.6 |  | 2021-10-04 |  |  | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: PONDASI OG 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
760 |  | SUM-SU-AKK-2215 | 30701090031 | 021276109 | PERDAMAIAN2 | RORO JONGRANG 2021 [NEW] | TB | 99°52.15.1'E | 2°3.2.63'N | 40 | 20/100/200 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Kancil No 5, Kel. Perdamaian, Kec. Rantau Selatan, Kab. Labuhanbatu, Prov. Sumatera Utara | HTI | SUM-SU-AKK-2215 | RANTAU_SELATAN_SIGAMBAL | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu | 6617456 | 2021-08-09 |  | 56 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-08 | W41-2021 | Oct-2021 | 2021-10-11 | W42-2021 | Oct-2021 | MW | 2021-08-18 |  | 125010773394 | 6.6 |  | 2021-10-04 |  |  | 2021-10-04 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:10:21-15:09:21: SRFI 13:09:21: 08:09:21: Power Connection Proses 06:09:21: 30:08:21:25:08:21: CME PREPARATION 22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
774 |  | SUM-SB-PAD-0879 | 30701300031 | 030433109 | PAD MC 58 / LUBUK GADING PERMAI | RORO JONGRANG 2021 [NEW] | TB | 100°19.26.65'E | 0°50.5.86'S | 40 | 90/165/300 | 2021 | RORO JONGRANG 2021 [NEW] | Lubuk Buaya RT. 004 / RW. 002, Kel. Lubuk Buaya, Kec. Koto Tengah, Kota Padang, Prov. Sumatera Barat | HTI | SUM-SB-PAD-0879 | KOTO_TANGAH_LUBUK_BUAYA | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kota Padang | 6617456 | 2021-08-09 |  | 58 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-08 | W41-2021 | Oct-2021 | 2021-10-08 | W41-2021 | Oct-2021 | MW | 2021-08-18 |  | 131023834095 | 6.6 |  | 2021-10-04 |  |  | 2021-10-06 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: 08:09:21: RBS/BTS PONDASI 06:09:21: PREPARE TIM, CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
772 |  | SUM-RI-BLS-1135 | 30701280031 | 040851109 | SITE MANDAU | RORO JONGRANG 2021 [NEW] | TB | 101°11.30.16'E | 1°16.16.36'N | 40 | 50/120/310 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Dewi Sartika Gg. Al- Hidayah No.27 Kel Duri Barat, Kec. Mandau, Kab. Bengkalis, Prov. Riau | HTI | SUM-RI-BLS-1135 | DURI_BARAT | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Bengkalis | 6617456 | 2021-08-09 |  | 63 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-14 | W42-2021 | Oct-2021 | 2021-10-14 | W42-2021 | Oct-2021 | MW | 2021-09-04 |  | 182103587972 | 6.6 |  | 2021-10-04 |  |  | 2021-10-11 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-29:09:21: SRFI 22:09:21:19:09:21: SRFI 15:09:21: ME OG 13:09:21: 08:09:21: RBS/BTS PONDASI OG 06:09:21: PREPARE TIM, CME PREPARATION 30:08:21:25:08:21:22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
662 |  | JAW-JB-GRT-4251 | 30696180031 | 122372109 | WANGUNJAYA-BANJARWANGI | RORO JONGRANG 2021 [NEW] | SKP | 107°54.1.4'E | 7°25.2.78'S | 50 | 90/140/320 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Kadongdong Kp. Bukit Dipa RT.04 RW.01, Kec. Banjarwangi, Kab. Garut Prov. Jawa Barat | HTI | JAW-JB-GRT-4251 | BANJARWANGI_KADONGDONG | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Garut | 6617454 | 2021-08-09 |  | 67 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-08-18 |  | 532762045566 | 6.6 |  | 2021-10-04 |  | 2021-08-27 | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: POWER CONNECTION PROSES 13:09:21: 01:09:21: 30:08:21: 25:08:21: SRFI 22:08:21: Pondasi Done, ME OG 18:08:21: CME PREPARATION 16:08:21: REAY TO DECLARE 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
690 |  | SUM-LA-BDL-1128 | 30696340031 | 100343104 | JL_SAMRATULANGI | RORO JONGRANG 2021 [NEW] | SMI | 105°19.4.69'E | 5°24.27.04'S | 50 | 45/165/300 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Pangeran Ryacudu, Kel. Campang Rayas RT.01/02 , Kec. Tanjung Karang Timur, Kota Bandar Lampung Prov. Lampung | HTI | SUM-LA-BDL-1128 | CAMPANG_RAYA_SOETTA | COLO | TBG | West | LAMPUNG | Lampung | Kota Bandar Lampung | 6617453 | 2021-08-09 |  | 67 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-08-18 |  | 171202936753 | 6.6 |  | 2021-10-04 |  | 2021-08-31 | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-25:08:21:SRFI 22:08:21:RBS BTS FOUNDATION 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
757 |  | JAW-JB-GRT-4250 | 30701450031 | 121098104 | NODAL BANJARWANGI | RORO JONGRANG 2021 [NEW] | SMI | 107°53.2.8'E | 7°28.34.14'S | 50 | 5/65/135 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Girimukti Kp. Gunung Kec. Singajaya, Kab. Garut Prov. Jawa Barat | HTI | JAW-JB-GRT-4250 | SINGAJAYA_GIRIMUKTI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Garut | 6617453 | 2021-08-09 |  | 67 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-08-18 |  | MULTIGUNA |  |  | 2021-10-04 |  |  | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26:10:21: RFIN 13:10:21-04:10:21: SRFI 19:09:21: ME OG 13:09:21: 08:09:21: PONDASI RBS/BTS OG 01:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
734 |  | JAW-JI-TRK-4263 | 30701360031 | 163717126 | DAWUHANTRENGGALEK | RORO JONGRANG 2021 [NEW] | TB | 111°44.30.01'E | 7°59.52.51'S | 40 | 65/200/320 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Cari RT 013 RW RW 004 Desa Dawuhan Kec. Trenggalek, Kab. Trenggalek Prov. Jawa Timur | HTI | JAW-JI-TRK-4263 | TRENGGALEK DAWUHAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Trenggalek | 6617456 | 2021-08-09 |  | 67 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  |  | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-29:09:21: SRFI 19:09:21:15:09:21: ME OG 12:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
733 |  | JAW-JI-JMR-5127 | 30701210031 | 163958109 | SUKORENOUMBULSARI | RORO JONGRANG 2021 [NEW] | TB | 113°23.52.58'E | 8°15.5.62'S | 40 | 10/200/290 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Kandangrejo, RT01/RW17, Desa Sukoreno, Kec. Umbulsari, Kab. Jember Prov. Jawa Timur | HTI | JAW-JI-JMR-5127 | UMBULSARI SUKORENO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Jember | 6617456 | 2021-08-09 |  | 67 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  |  | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-29:09:21: SRFI 19:09:21:15:09:21: ME OG 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
749 |  | JAW-JI-SDA-4315 | 30701340031 | 163610126 | KEDUNGREJO JABON | RORO JONGRANG 2021 [NEW] | TB | 112°45.8.42'E | 7°34.21.61'S | 37 | 25/110/270 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Kluthuk RT. 014 RW. 005 Desa Kedungrejo Kec. Jabon Kab. Sidoarjo | HTI | JAW-JI-SDA-4315 | JABON KEDUNGREJO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Sidoarjo | 6617456 | 2021-08-09 |  | 66 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-09-04 |  | 511821708283 | 6.6 |  | 2021-10-04 |  |  | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-29:09:21: SRFI 22:09:21: ME OG 19:09:21:15:09:21: 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
717 |  | JAW-JB-SBR-4246 | 30701430031 | 121027104 | KARANGMULYA | RORO JONGRANG 2021 [NEW] | SMI | 108°27.20.7'E | 6°45.33.66'S | 30 | 90/180/355 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Ageng Serang, Desa Kenangan RT.06 RW.01, Kec. Sumber, Kab. Cirebon Prov. Jawa Barat | HTI | JAW-JB-SBR-4246 | SUMBER_KENANGA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Cirebon | 6617453 | 2021-08-09 |  | 66 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-09-04 |  | 533313478129 | 6.6 |  | 2021-10-04 |  |  | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: POWER CONNECTION PROSES 13:09:21: 08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: READY TO DECLARE STO 18:08:21: 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
759 |  | JAW-JB-NPH-4233 | 30696200031 | 122406109 | KOTABARU - BALEPARE ( BTS HOTEL ) | RORO JONGRANG 2021 [NEW] | SKP | 107°29.29.76'E | 6°51.33.84'S | 30 | 0/160/270 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Cipeundey Kp. Pajagalan RT.005 RW.02 Kec. Padalarang, Kab. Bandung Barat Prov. Jawa Barat | HTI | JAW-JB-NPH-4233 | PADALARANG_CIPEUNDEUY | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung Barat | 6617454 | 2021-08-09 |  | 65 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-08-18 |  | 535852190263 | 6.6 |  | 2021-10-04 |  | 2021-08-31 | 2021-10-13 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-01:09:21: SRFI 30:08:21: PONDASI BTS/RBS DONE 25:08:21: Pondasi RBS/BTS OG 22:08:21: CME PREPARATION 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
711 |  | JAW-JB-CMS-4235 | 30701420031 | 121435104 | JATINEGARA | RORO JONGRANG 2021 [NEW] | SMI | 108°25.29.35'E | 7°10.21.11'S | 50 | 30/170/255 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Wetan Desa Bayasari Blok Pondok Cibadun, Kec. Jatinagara, Kab. Ciamis Prov. Jawa Barat | HTI | JAW-JB-CMS-4235 | JATINAGARA_BAYASARI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Ciamis | 6617453 | 2021-08-09 |  | 64 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-08-18 |  | 532314731868 | 6.6 |  | 2021-10-04 |  |  | 2021-10-12 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-19:09:21: POWER CONNECTION PROSES 13:09:21: 08:09:21: 06:09:21: RBS/BTS FOUNDATION 30:08:21:25:08:21:22:08:21: READY TO DECLARE STO 18:08:21: 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
747 |  | JAW-JI-NGW-3677 | 30701130031 | 163433109 | TRUNOJOYO 2 | RORO JONGRANG 2021 [NEW] | TB | 111°25.27.55'E | 7°24.11.23'S | 30 | 10/95/225 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Garuda RT 03 RW 01 Desa Grudo Kec. Ngawi, Kab. Ngawi Prov. Jawa Timur | HTI | JAW-JI-NGW-3677 | NGAWI GRUDO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ngawi | 6617456 | 2021-08-09 |  | 64 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  |  | 2021-10-12 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-15:09:21: SRFI 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
761 |  | JAW-JB-SNG-4264 | 30701470031 | 121343104 | KAWUNGANTEN | RORO JONGRANG 2021 [NEW] | SMI | 107°43.52.18'E | 6°29.1.72'S | 50 | 110/245/340 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Kawunganten Kp. Kawunganten, Kec. Cikaum, Kab. Subang Prov. Jawa Barat | HTI | JAW-JB-SNG-4264 | CIKAUM_KAWUNGANTEN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Subang | 6617453 | 2021-08-09 |  | 60 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-09-04 |  | 534254181689 | 6.6 |  | 2021-10-04 |  |  | 2021-10-08 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-08:09:21: SRFI 06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: READY TO DECLARE STO 18:08:21: 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
764 |  | JAW-JI-JBG-4177 | 30701760031 | TBG06_EJ065 | SUMBEREJO | RORO JONGRANG 2021 [NEW] | PMS | 112°11.28.75'E | 7°31.11.53'S | 50 | 30/105/310 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Desa Sumberejo RT.06 RW.01 Kel. Sumberejo Kec. Jombang, Kab. Jombang Prov. Jawa Timur | HTI | JAW-JI-JBG-4177 | JOMBANG SUMBERJO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Jombang | 6617452 | 2021-08-09 |  | 68 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-17 | W43-2021 | Oct-2021 | 2021-10-17 | W43-2021 | Oct-2021 | MW | 2021-08-18 |  | 514531761654 | 6.6 |  | 2021-10-04 |  |  | 2021-10-16 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-15:09:21: SRFI 13:09:21: 08:09:21: POWER CONNECTION PROSES 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
751 |  | JAW-JI-KPN-4411 | 30701720031 | TBG05_EJ216 | ARJOWILANGUN | RORO JONGRANG 2021 [NEW] | BK | 112°25.40.55'E | 8°11.6.32'S | 50 | 10/110/265 | 2021 | RORO JONGRANG 2021 [NEW] | Dukuh Barisan RT 13 / RW 02, Kel. Arjowilangun, Kec. Kalipare, Kab. Malang Prov. Jawa Timur | HTI | JAW-JI-KPN-4411 | KALIPARE ARJOWILANGUN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Malang | 6617449 | 2021-08-09 |  | 67 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-17 | W43-2021 | Oct-2021 | 2021-10-17 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 513100329904 | 6.6 |  | 2021-10-04 |  |  | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-15:09:21: SRFI 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
762 |  | JAW-JI-KPN-4401 | 30701250031 | 162699109 | PERTIGAANTUMPANGTBG | RORO JONGRANG 2021 [NEW] | TB | 112°45.55.87'E | 8°1.13.15'S | 50 | 10/225/300 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Prapatan Tulusayu RT.39 RW.05 Ds. Tulusayu Kec. Tumpang, Kab. Malang Prov. Jawa Timur | HTI | JAW-JI-KPN-4401 | TULUSBESAR TUMPANG | COLO | TBG | East | JATIM | Jawa Timur | Kab. Malang | 6617456 | 2021-08-09 |  | 71 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  | 2021-09-25 | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21: 08:09:21: POWER CONNECTION PROSES 06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: STO READY TO DECLARE 18:08:21: NEED REVIEW POWER HTI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
705 |  | SUM-JA-JMB-0502 | 30701220031 | 060347109 | AGUS SALIM JBI | RORO JONGRANG 2021 [NEW] | TB | 103°37.3.58'E | 1°38.17.59'S | 30 | 15/140/270 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. H.A. Roni Sani RT 2 Kel. Paal Lima, Kec. Kota Baru, Kota Jambi, Prov. Jambi | HTI | SUM-JA-JMB-0502 | PAAL_LIMA | COLO | TBG | West | SUMBAGSEL | Jambi | Kota Jambi | 6617456 | 2021-08-09 |  | 70 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 143105973982 | 6.6 |  | 2021-10-04 |  | 2021-09-16 | 2021-10-18 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21: ME OG 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
676 |  | SUM-SS-SKY-1238 | 30701120031 | 071030109 | JAMBI2G59 | RORO JONGRANG 2021 [NEW] | TB | 103°40.41.38'E | 2°4.29.35'S | 40 | 10/100/190 | 2021 | RORO JONGRANG 2021 [NEW] | Lingkungan I RT 12 RW 01Kel. Bayung Lencir, Kec. Bayung Lencir. Kab. Muba Provinsi SUMSEL | HTI | SUM-SS-SKY-1238 | SIMPANG_BAYAT | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Banyuasin | 6617456 | 2021-08-09 |  | 70 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 143509478756 | 6.6 |  | 2021-10-04 |  |  | 2021-10-18 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
756 |  | SUM-SS-KAG-1243 | 30701260031 | 070743109 | OKI14 | RORO JONGRANG 2021 [NEW] | TB | 104°51.10.22'E | 3°23.38.62'S | 40 | 130/200/270 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Sepucuk, Kel. Kota Raya, Kec. Kota Kayuagung, Kab. OKI, Prop. Sumsel | HTI | SUM-SS-KAG-1243 | KUTARAYA | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ilir | 6617456 | 2021-08-09 |  | 67 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 149100127229 | 6.6 |  | 2021-10-04 |  |  | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-15:09:21: SRFI 13:09:21: ME OG 08:09:21: PONDASI RBS BTS OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
707 |  | SUM-JA-JMB-0507 | 30701290031 | 060239109 | JAMBI10 | RORO JONGRANG 2021 [NEW] | TB | 103°35.32.82'E | 1°35.50.57'S | 30 | 70/165/265 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Danau Sipin,RT 024, kel. Legok, Kec. Telanai Pura, Kota Jambi, Prop. Jambi | HTI | SUM-JA-JMB-0507 | LEGOK | COLO | TBG | West | SUMBAGSEL | Jambi | Kota Jambi | 6617456 | 2021-08-09 |  | 67 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 143005622696 | 6.6 |  | 2021-10-04 |  |  | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-15:09:21: SRFI 13:09:21: RBS BTS PONDASI 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
701 |  | SUM-SS-PLG-1271 | 30701310031 | 070710109 | KELAPA RAYA 2 | RORO JONGRANG 2021 [NEW] | TB | 104°41.16.26'E | 2°57.13.46'S | 30 | 70/150/310 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Kelapa RT 013 RW 005, Kel. Talang kelapa, Kec. Alang Alang Lebar, Kota Palembang, Prop. Sumsel | HTI | SUM-SS-PLG-1271 | ALANGLEBAR_TALANG_KELAPA | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kota Palembang | 6617456 | 2021-08-09 |  | 65 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 141203537053 | 6.6 |  | 2021-10-04 |  |  | 2021-10-13 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-26:09:21: SRFI, ISSUE PERKUATAN TOWER 22:09:21: 19:09:21: 15:09:21: ME OG 13:09:2021: 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
665 |  | SUM-SS-MRE-1229 | 30701110031 | 071065109 | SUMSEL2G179 | RORO JONGRANG 2021 [NEW] | TB | 103°46.4.22'E | 3°37.29.39'S | 40 | 10/125/240 | 2021 | RORO JONGRANG 2021 [NEW] | Dsn.1 Ds kebun no.63 Kec Muara Enim Kab.Muara Enim Prov. Sumatera Selatan | HTI | SUM-SS-MRE-1229 | KEPUR | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Muara Enim | 6617456 | 2021-08-09 |  | 65 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 147100685541 | 6.6 |  | 2021-10-04 |  |  | 2021-10-13 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
783 |  | SUM-SS-PKB-1258 | 30701060031 | 070773109 | BETUTU LAMA | RORO JONGRANG 2021 [NEW] | TB | 104°39.37.26'E | 2°54.22.25'S | 30 | 20/110/190 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Pangkalan Benteng, Kel. Sukajad RT 46 RW 17, Kec. Talang Kelapa, Kab. Banyuasin Prov. Sumatera Selatan | HTI | SUM-SS-PKB-1258 | SUKOMORO_ALHIDAYAH | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Banyuasin | 6617456 | 2021-08-09 |  | 65 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 141203537046 | 6.6 |  | 2021-10-04 |  |  | 2021-10-13 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-26:09:21: SRFI 22:09:21: 19:09:21: ME OG 15:09:21: PONDSI OG 13:09:21: ME OG 08:09:21:06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
674 |  | SUM-SS-PKB-1256 | 30701040031 | 070734109 | SUKOMORO 3 | RORO JONGRANG 2021 [NEW] | TB | 104°38.47.47'E | 2°54.44.17'S | 35 | 150/220/340 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Simpang Pasir Putih KM17, Kel. Sukajadi RT/RW 54/20, Kec. Talang Kelapa, Kab. Banyuasin Prov. Sumatera Selatan | HTI | SUM-SS-PKB-1256 | SUKOMORO_PALEMBANG_BETUNG | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Banyuasin | 6617456 | 2021-08-09 |  | 65 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 141203537020 | 6.6 |  | 2021-10-04 |  |  | 2021-10-13 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: SRFI 15:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HTI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
729 |  | JAW-JI-MJY-4142 | 30701330031 | 163438109 | BABADAN 4 | RORO JONGRANG 2021 [NEW] | TB | 111°31.57.25'E | 7°47.41.32'S | 40 | 0/180/270 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Gunting RT. 25 RW.06 desa Kradinan Kec Dolopo Kab Madiun | HTI | JAW-JI-MJY-4142 | DOLOPO KRADINAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Madiun | 6617456 | 2021-08-09 |  | 64 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  |  | 2021-10-12 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-15:09:21: SRFI 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW POWER HUAWEI 18:08:21: 16:08:21:09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES NEED REVIEW TNP ALITA
670 |  | SUM-SS-PKB-1261 | 30701270031 | 071048109 | SUMSEL2G08 | RORO JONGRANG 2021 [NEW] | TB | 104°24.9.14'E | 2°52.44.69'S | 40 | 30/230/320 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Bom Berlian, RT.025 RW.010, Kel. Pangkalan Balai, Kec. Banyuasin III, Kab. Banyuasin, Prov. Sumatera Selatan | HTI | SUM-SS-PKB-1261 | BANYUASINIII_PANGKALAN_BALAI | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Banyuasin | 6617456 | 2021-08-09 |  | 60 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 142300883781 | 6.6 |  | 2021-10-04 |  |  | 2021-10-08 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
675 |  | SUM-SS-PKB-1257 | 30701050031 | 070977109 | KENTEN KERAMAT | RORO JONGRANG 2021 [NEW] | TB | 104°46.13.94'E | 2°54.29.48'S | 30 | 130/220/350 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Pangeran Ayin Simpang Talang Keramat Kel. Kenten Kec. Talang Kelapa Kab. Banyuasin Prop. Sumsl | HTI | SUM-SS-PKB-1257 | TALANG_BULUH | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Banyuasin | 6617456 | 2021-08-09 |  | 58 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 141103466674 | 6.6 |  | 2021-10-04 |  |  | 2021-10-06 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:10:21-26:09:21: SRFI 22:09:21: 19:09:21: 15:09:21: 13:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
692 |  | SUM-JA-SNT-0710 | 30696150031 | 060415109 | JAMBI2G37 | RORO JONGRANG 2021 [NEW] | TB | 103°51.54.11'E | 1°42.55.51'S | 60 | 120/205/340 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Nusantara Rt 001 Rw.001 Desa Sumber Agung, Kec. Sungai Gelam Kab. Muaro Jambi Jambi | HTI | SUM-JA-SNT-0710 | SUNGAI_GELAM_SUMBER_AGUNG | COLO | TBG | West | SUMBAGSEL | Jambi | Kab. Muaro Jambi | 6617456 | 2021-08-09 |  | 57 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-08-18 |  | 143105959365 | 6.6 |  | 2021-10-04 |  | 2021-09-03 | 2021-10-05 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:10:21-01:09:21: SRFI 30:08:21: ME OG 25:08:21: RBS BTS FOUNDATION 22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
NEW SPK |  | SUM-SU-SDK-2227 | 30734600031 | 0226622007 | IBS IBS_MED0053_NORTH SUMATERA | BP2022 | TB | 98°22.42.17'E | 2°43.57.94'N | 50 | 60/170/280 | 2022 | New site 2022 - P2 | Jl. Taman Wisata Iman, Dusun II, Desa Sitinjo, Kecamatan Sitinjo, Kabupaten Dairi, Propinsi Sumatera Utara | HTI | SUM-SU-SDK-2227 | SITINJO_I | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Dairi | 6617992 | 2022-01-28 | 2022-01-28 | 62 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 129010129372 | 6.6 |  | 2022-03-22 |  |  | 2022-03-31 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:03:22: RFIN 30:03:22: PLN 27:03:22-16:03:22: ME PARALEL STRENGTENING 13:03:22-09:03:22: BTS PONDASI OG, PARALEL STRENGTENING 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
732 |  | JAW-JI-SPG-4233 | 30701560031 | 160218104 | TOBAI TIMUR | RORO JONGRANG 2021 [NEW] | SKP | 113°23.31.31'E | 6°56.57.88'S | 50 | 0/130/260 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Derbing Desa Pancor, Kec.Ketapang Kab.Sampang, Prov.Jawa Timur | HTI | JAW-JI-SPG-4233 | SOKOBANAH BIRA TIMUR | COLO | TBG | East | JATIM | Jawa Timur | Kab. Sampang | 6617454 | 2021-08-09 |  | 72 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-19 | W43-2021 | Oct-2021 | 2021-10-19 | W43-2021 | Oct-2021 | MW | 2021-08-18 |  | 517800690857 | 6.6 |  | 2021-10-04 |  | 2021-09-24 | 2021-10-20 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
672 |  | JAW-JI-BDW-3619 | 30701780031 | 164067104 | JAMBESARI - RELOC | RORO JONGRANG 2021 [NEW] | SMI | 113°50.28.03'E | 7°58.49.87'S | 50 | 25/125/205 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Krajan RT.01 RW.01 Desa Jambesari Kec. Jambesari, Kab. Bondowoso Prov. Jawa Timur | HTI | JAW-JI-BDW-3619 | JAMBESARI DARUS SHOLAH JAMBESARI | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bondowoso | 6617453 | 2021-08-09 |  | 71 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-19 | W43-2021 | Oct-2021 | 2021-10-19 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  |  | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-29:09:21: POWER CONNECTION PROSES 19:09:21: 15:09:21: ME OG 13:09:21:06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HTI 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
730 |  | JAW-JI-PNG-4298 | 30701610031 | 162143109 | TAMANSARI PONOROGO | RORO JONGRANG 2021 [NEW] | SKP | 111°29.22.63'E | 7°57.50.58'S | 50 | 40/95/320 | 2021 | RORO JONGRANG 2021 [NEW] | Dukuh Ngelo rt.02 rw.01 Ds. Bacangan Kec. Sambit, Kab. Ponorogo Prov. Jawa Timur | HTI | JAW-JI-PNG-4298 | SAMBIT BANCANGAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ponorogo | 6617454 | 2021-08-09 |  | 71 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-19 | W43-2021 | Oct-2021 | 2021-10-19 | W43-2021 | Oct-2021 | MW | 2021-08-18 |  | MULTIGUNA |  |  | 2021-10-04 |  | 2021-09-24 | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
673 |  | JAW-JI-BYW-4148 | 30701800031 | 160693104 | SUMBERBULU | RORO JONGRANG 2021 [NEW] | SMI | 114°10.51.42'E | 8°13.38.68'S | 50 | 135/250/325 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Sumberagung RT/RW 1/1, Desa Sumberbulu Kec. Songgon, Kab. Banyuwangi Prov. Jawa Timur | HTI | JAW-JI-BYW-4148 | SONGGON SUMBERBULU KOESNO REJO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Banyuwangi | 6617453 | 2021-08-09 |  | 71 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-19 | W43-2021 | Oct-2021 | 2021-10-19 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 516711495042 | 6.6 |  | 2021-10-04 |  |  | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-29:09:21: POWER CONNECTION PROSES 19:09:21:15:09:21: ME OG 13:09:21:06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HTI 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
667 |  | JAW-JI-BDW-3622 | 30701500031 | 162198109 | TAMANAN3 | RORO JONGRANG 2021 [NEW] | SKP | 113°48.47.84'E | 7°59.54.82'S | 50 | 90/250/350 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Krajan Barat RT 06 RW 02 Kel. Wonosuko Kec. Tamanan Kab. BondowosoKec. Tamanan | HTI | JAW-JI-BDW-3622 | TAMANAN WONOSUKO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bondowoso | 6617454 | 2021-08-09 |  | 71 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-19 | W43-2021 | Oct-2021 | 2021-10-19 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  |  | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-29:09:21: POWER CONNECTION PROSES 19:09:21: 15:09:21: ME OG 13:09:21:06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: STO READY TO DECLARE 18:08:21: NEED REVIEW POWER HTI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
688 |  | SUM-SU-PMS-2239 | 30701490031 | 020268104 | KARANG_SARI | RORO JONGRANG 2021 [NEW] | SMI | 99°7.24.6'E | 3°0.16.09'N | 50 | 60/180/310 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Kuncara, Dusun 8 No. 73, Kel. Karang Anyar, Kec. Gunung Maligas, Kab. Simalungun, Prov. Sumatera Utara | HTI | SUM-SU-PMS-2239 | GUNUNG_MALIGAS_KARANG_ANYAR | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Simalungun | 6617453 | 2021-08-09 |  | 70 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-19 | W43-2021 | Oct-2021 | 2021-10-19 | W43-2021 | Oct-2021 | MW | 2021-08-18 |  | 121011230546 | 6.6 |  | 2021-10-04 |  |  | 2021-10-18 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21: PONDASI OG 08:09:21: 06:09:21: 30:08:21:25:08:21: CME PREPARATION 22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
683 |  | SUM-SU-PMS-2236 | 30701480031 | 020277104 | RTANAHJAWA | RORO JONGRANG 2021 [NEW] | SMI | 99°6.43.52'E | 2°53.19.25'N | 50 | 100/175/320 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Lintas Sumatera RT I Hataran Jawa, Desa Marubun Jaya, Kec. Tanah Jawa, Kab. Simalungun, Prov. Sumatera Utara | HTI | SUM-SU-PMS-2236 | TANAH_JAWA_PARBALOGAN | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Simalungun | 6617453 | 2021-08-09 |  | 70 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-19 | W43-2021 | Oct-2021 | 2021-10-19 | W43-2021 | Oct-2021 | MW | 2021-08-18 |  | 121170471564 | 6.6 |  | 2021-10-04 |  |  | 2021-10-18 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21: PONDASI OG 08:09:21: 08:06:2021: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
767 |  | JAW-JI-JMR-5123 | 30701200031 | 162648109 | KARANGDUREN2TBG | RORO JONGRANG 2021 [NEW] | TB | 113°30.41.44'E | 8°15.43.38'S | 50 | 65/205/335 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Kedungnilo RT 010 RW 07 Desa Karangsemanding Kec. Balung, Kab. Jember Prov. Jawa Timur | HTI | JAW-JI-JMR-5123 | BALUNG KARANG SEMANDING | COLO | TBG | East | JATIM | Jawa Timur | Kab. Jember | 6617456 | 2021-08-09 |  | 77 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-08-18 |  | 516041138833 | 6.6 |  | 2021-10-04 |  | 2021-09-30 | 2021-10-25 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:10:21-15:09:21: SRFI 13:09:21: ME OG 08:09:21: RBS BTS PONDASI OG 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
739 |  | JAW-JI-TRK-4264 | 30701660031 | 162223109 | GEMBLEB TRENGGALEK | RORO JONGRANG 2021 [NEW] | SKP | 111°45.33.01'E | 8°4.52.14'S | 40 | 185/250/345 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Kayu Jaran RT.09/RW.03, Ds. Gembleb, Kec. Pogalan, Kab. Trenggalek Prov. Jawa Timur | HTI | JAW-JI-TRK-4264 | POGALAN GEMBLEB | COLO | TBG | East | JATIM | Jawa Timur | Kab. Trenggalek | 6617454 | 2021-08-09 |  | 77 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  |  | 2021-10-25 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:10:21: RFIN 20:10:21-29:09:21: SRFI 15:09:21: ME OG 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
677 |  | SUM-LA-PRW-1123 | 30701460031 | 100213104 | PSR_PRINGSEWU | RORO JONGRANG 2021 [NEW] | SMI | 104°58.28.81'E | 5°20.56.72'S | 40 | 80/220/320 | 2021 | RORO JONGRANG 2021 [NEW] | KEL PRINGSEWU BARAT KEC PRINGSEWU KEC. TANJUNG SENANG KODYA BANDAR LAMPUNG,LAMPUNG | HTI | SUM-LA-PRW-1123 | PRINGSEWU_UTARA | COLO | TBG | West | LAMPUNG | Lampung | Kab. Pringsewu | 6617453 | 2021-08-09 |  | 74 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-08-18 |  | 172501081176 | 6.6 |  | 2021-10-04 | 2021-10-08 | 2021-09-22 | 2021-10-22 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:10:21: RFIN SENT 20:10:21-13:09:21: SRFI 08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
748 |  | JAW-JI-MJY-4141 | 30701320031 | TBG03_EJ127 | CARUBAN | RORO JONGRANG 2021 [NEW] | TB | 111°39.27.25'E | 7°32.28.07'S | 30 | 15/185/310 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Bangunsari Kec. Mejayan Kab. Madiun Prov Jawa Timur | HTI | JAW-JI-MJY-4141 | MEJAYAN BANGUNSARI | COLO | TBG | East | JATIM | Jawa Timur | Kab. Madiun | 6617456 | 2021-08-09 |  | 73 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 515071136343 | 6.6 |  | 2021-10-04 |  | 2021-09-24 | 2021-10-21 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:10:21-15:09:21: SRFI 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
773 |  | SUM-KR-BTM-0606 | 30701750031 | 050486103 | MEKAR TAMAN SARI - RELOC | RORO JONGRANG 2021 [NEW] | TI | 103°58.11.75'E | 1°6.13.14'N | 30 | 20/190/290 | 2021 | RORO JONGRANG 2021 [NEW] | Perum Tiban Koperasi Blok K No. 85 Kel. Tiban Baru Kec. Sekupang - Kota Batam | HTI | SUM-KR-BTM-0606 | TIBAN_BARU | COLO | TBG | West | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6617455 | 2021-08-09 |  | 73 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 152002074451 | 6.6 |  | 2021-10-04 |  | 2021-09-21 | 2021-10-21 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:10:21-19:09:21: SRFI, ISSUE PERKUATAN 15:09:21: ME OG 13:09:21: 08:09:21: RBS/BTS PONDASI 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
769 |  | JAW-JB-CMS-4284 | 30701380031 | 125398126 | SITUMANDALA-RANCAH | RORO JONGRANG 2021 [NEW] | TB | 108°31.57.54'E | 7°12.9.14'S | 50 | 0/120/240 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Sukasari Dusun Nangela RT.001 RW.001, Kec. Tambaksari, Kab. Ciamis Prov. Jawa Barat | HTI | JAW-JB-CMS-4284 | TAMBAKSARI_SUKASARI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Ciamis | 6617456 | 2021-08-09 |  | 72 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 532217794155 | 6.6 |  | 2021-10-04 |  |  | 2021-10-20 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-04:10:21: SRFI MINUS EXTEND TOWER 26:09:21-08:09:21: RBS BTS PONDASI, NEED EXTEND TOWER 3 M 06:09:21: CME PREPARATION 30:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW TNP ALITA 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
728 |  | JAW-JI-LMG-4294 | 30701100031 | 164015109 | LOPANGKEMBANGBAHU | RORO JONGRANG 2021 [NEW] | TB | 112°22.11.96'E | 7°10.25.25'S | 40 | 75/205/275 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Lopang, Mojomanis RT001 RW001 Kec. Kembangbahu, Kab. Lamongan Prov. Jawa Timur | HTI | JAW-JI-LMG-4294 | LOPANG KEMBANGBAHU | COLO | TBG | East | JATIM | Jawa Timur | Kab. Lamongan | 6617456 | 2021-08-09 |  | 71 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 518031807284 | 6.6 |  | 2021-10-04 |  |  | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW POWER HUAWEI 18:08:21: 16:08:21:09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES NEED REVIEW TNP ALITA
737 |  | JAW-JI-KPN-4406 | 30701570031 | 161862109 | TURIREJO | RORO JONGRANG 2021 [NEW] | SKP | 112°40.42.35'E | 7°49.53.9'S | 40 | 90/290/350 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Ketindan RT. 04/ RW. 04 Ds. Ketindan Kec Lawang Kab Malang | HTI | JAW-JI-KPN-4406 | NGANTANG MULYOREJO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Malang | 6617454 | 2021-08-09 |  | 71 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  | 2021-09-25 | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-29:09:21: SRFI 22:09:21: 19:09:21:15:09:21: ME OG 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
724 |  | JAW-JI-PNG-4295 | 30701230031 | 163977109 | BANGUNREJO SUKOREJO | RORO JONGRANG 2021 [NEW] | TB | 111°23.39.77'E | 7°50.39.41'S | 40 | 105/220/310 | 2021 | RORO JONGRANG 2021 [NEW] | Dukuh Ngambakan RT01 RW01, Desa Bangunrejo, Kecamatan Sukorejo, Kabupaten Ponorogo | HTI | JAW-JI-PNG-4295 | SUKOREJO BANGUNREJO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ponorogo | 6617456 | 2021-08-09 |  | 71 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 515402549206 |  |  | 2021-10-04 |  | 2021-09-24 | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HTI 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
766 |  | JAW-JI-KPN-4414 | 30701740031 | 160009102 | NGAWONGGO | RORO JONGRANG 2021 [NEW] | TI | 112°42.22.93'E | 8°4.2.35'S | 50 | 80/190/275 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Purwosekar, Kamp. Purboyo Kec. Tajinan, Kab. Malang Prov. Jawa Timur | HTI | JAW-JI-KPN-4414 | TAJINAN PURWOSEKAR | COLO | TBG | East | JATIM | Jawa Timur | Kab. Malang | 6617455 | 2021-08-09 |  | 71 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-08-18 |  | MULTIGUNA |  |  | 2021-10-04 |  | 2021-09-25 | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-29:09:21: SRFI 15:09:21: ME OG 13:09:21: 08:09:21: RBS BTS PONDASI IG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
664 |  | SUM-JA-JMB-0504 | 30701400031 | 060165109 | SELARAS PINANG JBI | RORO JONGRANG 2021 [NEW] | TB | 103°36.49.93'E | 1°34.58.55'S | 30 | 15/75/255 | 2021 | RORO JONGRANG 2021 [NEW] | JL.KH Somat Kelurahan Arab Melayu Kecamatan Pelayang Kotamadya Jambi Provinsi Jambi | HTI | SUM-JA-JMB-0504 | TENGAH_ULU_GEDONG | COLO | TBG | West | SUMBAGSEL | Jambi | Kota Jambi | 6617456 | 2021-08-09 |  | 67 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-08-18 |  | 143205451254 | 6.6 |  | 2021-10-04 |  | 2021-10-13 | 2021-10-15 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-06:10:21: SRFI 04:10:21-29:09:21: ME OG 26:09:21-13:09:21: RBS BTS PONDASI OG 06:09:21: CME PREPARARTION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
716 |  | JAW-JB-SBR-4245 | 30701580031 | 120642104 | GETASAN | RORO JONGRANG 2021 [NEW] | SKP | 108°27.48.64'E | 6°44.24.11'S | 30 | 40/180/315 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Pangeran Antasari, Desa Kejuden Kp. Kejuden RT.03 RW.05, Kec. Depok, Kab. Cirebon Prov. Jawa Barat | HTI | JAW-JB-SBR-4245 | DEPOK_KEJUDEN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Cirebon | 6617454 | 2021-08-09 |  | 66 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 533313478137 | 6.6 |  | 2021-10-04 |  |  | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: POWER CONNECTION PROSES 13:09:21: 08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: READY TO DECLARE STO 18:08:21: 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
659 |  | JAW-JB-CJR-4244 | 30701070031 | 1270682004 | IBS SUKARAHARJA / CIANJUR | RORO JONGRANG 2021 [NEW] | TB | 106°59.53.23'E | 7°13.55.96'S | 50 | 75/220/320 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Desa Sukawangi, Desa Sukaraharja RT.03 RW.07, Kec. Kadupandak, Kab. Cianjur Prov. Jawa Barat | HTI | JAW-JB-CJR-4244 | KADUPANDAK_SUKARAHARJA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Cianjur | 6617456 | 2021-08-09 |  | 66 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 536911857056 | 6.6 |  | 2021-10-04 |  | 2021-09-10 | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-13:09:21: POWER CONNECTION PROSES 08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21: 25:08:21:22:08:21: READY TO DECLARE STO 18:08:21: 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
755 |  | SUM-LA-KLA-1121 | 30701410031 | 100184104 | KALIANDA_KOTA | RORO JONGRANG 2021 [NEW] | SMI | 105°35.27.13'E | 5°44.4.88'S | 40 | 70/185/335 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Kusuma Bangsa No.28, Kel. Kalianda RT.07/01, Kec. Kalianda, Kab. Lampung Selatan Prov. Lampung | HTI | SUM-LA-KLA-1121 | KALIANDA_KALIANDA | COLO | TBG | West | LAMPUNG | Lampung | Kab. Lampung Selatan | 6617453 | 2021-08-09 |  | 65 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 171300676079 | 6.6 |  | 2021-10-04 |  |  | 2021-10-13 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-19:09:21: SRFI 15:09:21: 13:09:21: ME OG 08:09:21: PONDASI RBS BTS OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: STO READY TO DECLARE 18:08:21: NEED REVIEW POWER HTI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
720 |  | JAW-JI-NGW-3672 | 30701520031 | 160151104 | KENDAL | RORO JONGRANG 2021 [NEW] | SKP | 111°18.43.45'E | 7°32.37.03'S | 50 | 205/255/355 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Jatirejo desa patalan Rt 03 Rw 03 kec Kendal kab ngawi | HTI | JAW-JI-NGW-3672 | KENDAL PATALAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ngawi | 6617454 | 2021-08-09 |  | 64 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  |  | 2021-10-12 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-15:09:21: SRFI 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: STO READY TO DECLARE 18:08:21: NEED REVIEW POWER HTI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
669 |  | SUM-LA-MET-1128 | 30701810031 | 100060110 | KALIBENING | RORO JONGRANG 2021 [NEW] | MSI | 105°19.13.04'E | 5°5.12.8'S | 50 | 25/140/275 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. WR. Supratman RT. 14/07 Lingkungan IV Kel. Karang Rejo Kec. Metro Utara Kota Metro | HTI | SUM-LA-MET-1128 | METRO_UTARA_BANJAR_SARI | COLO | TBG | West | LAMPUNG | Lampung | Kota Metro | 6617450 | 2021-08-09 |  | 63 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 172801507598 | 6.6 |  | 2021-10-04 |  |  | 2021-10-11 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-15:09:21: SRFI 13:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: STO READY TO DECLARE 18:08:21: NEED REVIEW POWER HTI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
704 |  | SUM-RI-SAK-1157 | 30703920031 | 041316109 | API_SC_SSI132W | RORO JONGRANG 2021 [NEW] | TB | 102°2.46.43'E | 0°48.32.69'N | 40 | 60/180/290 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Syarif Ali, RT 06 RW 01, Kel. Rempak, Kec. Siak, Kab. Siak, Prov. Riau | HTI | SUM-RI-SAK-1157 | SIAK_KAMPUNG_REMPAK | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Siak | 6617456 | 2021-08-09 |  | 63 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 181700530296 | 6.6 |  | 2021-10-04 |  | 2021-09-22 | 2021-10-11 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
710 |  | JAW-JB-SOR-4227 | 30701030031 | 125419126 | MEKARSARI-CIMAUNG | RORO JONGRANG 2021 [NEW] | TB | 107°34.22.98'E | 7°7.8.36'S | 50 | 175/250/305 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Mekarsari Kp. Cigoong RT.02 RW.05, Kec. Cimaung, Kab. Bandung Prov. Jawa Barat | HTI | JAW-JB-SOR-4227 | CIMAUNG_MEKARSARI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung | 6617456 | 2021-08-09 |  | 61 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 535342211870 | 6.6 |  | 2021-10-04 |  |  | 2021-10-09 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:10:21-04:10:21: SRFI, MINUS EXTEND TOWER 26:09:21-06:09:21: PONDASI RBS/BTS, ISSUE NEED EXTEND TOWER, PROSES REVISI PERMIT UNTUK PENAMBAHAN TOWER 30:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW TNP ALITA 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
709 |  | JAW-JB-CMS-4280 | 30701370031 | 1263631023 | CISAGA CIAMIS | RORO JONGRANG 2021 [NEW] | TB | 108°29.52.15'E | 7°20.42.29'S | 50 | 50/115/295 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Mekarmukti Dusun Batununggul RT.008 RW.003, Kec. Cisaga, Kab. Ciamis Prov. Jawa Barat | HTI | JAW-JB-CMS-4280 | CISAGA_MEKARMUKTI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Ciamis | 6617456 | 2021-08-09 |  | 60 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-20 | W43-2021 | Oct-2021 | 2021-10-20 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 532217794148 | 6.6 |  | 2021-10-04 |  |  | 2021-10-08 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-19:09:21: POWER CONNECTION PROSES 13:09:21: ME OG 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: READY TO DECLARE STO 18:08:21: 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
726 |  | JAW-JI-PNG-4290 | 30701640031 | 164120107 | BANYUDONO PONOROGO | RORO JONGRANG 2021 [NEW] | SKP | 111°29.10.25'E | 7°48.23.11'S | 40 | 50/130/280 | 2021 | RORO JONGRANG 2021 [NEW] | Dukuh Malang RT01 RW01 Desa Lembah Kecamatan Babadan Kabupaten Ponorogo | HTI | JAW-JI-PNG-4290 | BABADAN LEMBAH | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ponorogo | 6617454 | 2021-08-09 |  | 74 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-22 | W43-2021 | Oct-2021 | 2021-10-28 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 515402558166 |  |  | 2021-10-04 |  | 2021-09-24 | 2021-10-22 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21:10:21-15:09:21: SRFI 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HTI 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
727 |  | JAW-JI-PNG-4293 | 30701670031 | 162124109 | KADIPATEN PONOROGO | RORO JONGRANG 2021 [NEW] | SKP | 111°30.17.32'E | 7°50.49.7'S | 40 | 70/245/340 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Margomulyo, RT04/RW01. Kel. Setono. Kec. Jenangan, Kab. Ponorogo Prov. Jawa Timur | HTI | JAW-JI-PNG-4293 | JENANGAN SETONO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ponorogo | 6617454 | 2021-08-09 |  | 73 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-22 | W43-2021 | Oct-2021 | 2021-10-22 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 515402549214 | 6.6 |  | 2021-10-04 |  | 2021-09-24 | 2021-10-21 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21:10:21: RFI 24:10:21-15:09:21: SRFI 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HTI 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
722 |  | JAW-JI-KDR-4324 | 30701600031 | 164108107 | BESOWO KEPUNG | RORO JONGRANG 2021 [NEW] | SKP | 112°16.24.67'E | 7°45.51.98'S | 40 | 50/155/330 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Jatirejo RT 09 RW 03 Desa Damarwulan Kec. Kepung, Kab. Kediri Prov. Jawa Timur | HTI | JAW-JI-KDR-4324 | KEPUNG DAMARWULAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Kediri | 6617454 | 2021-08-09 |  | 73 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-22 | W43-2021 | Oct-2021 | 2021-10-22 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 514541403592 | 6.6 |  | 2021-10-04 |  | 2021-09-24 | 2021-10-21 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:10:21-15:09:21: SRFI 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: STO READY TO DECLARE 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
725 |  | JAW-JI-NJK-4250 | 30701530031 | 161779109 | MLANDANGAN | RORO JONGRANG 2021 [NEW] | SKP | 111°55.2.89'E | 7°39.48.89'S | 40 | 100/200/275 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Babadan, RT. 001. RW. 004, Desa Babadan, Kec. Pace, Kab. Nganjuk - Jawa Timur | HTI | JAW-JI-NJK-4250 | PACE BABADAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Nganjuk | 6617454 | 2021-08-09 |  | 73 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-22 | W43-2021 | Oct-2021 | 2021-10-22 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 514601929137 | 6.6 |  | 2021-10-04 |  | 2021-09-24 | 2021-10-21 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:10:21-15:09:21: SRFI 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HTI 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
721 |  | JAW-JI-NGW-3667 | 30701790031 | 160862104 | BANYUBIRU_NWI | RORO JONGRANG 2021 [NEW] | SMI | 111°12.23.58'E | 7°26.35.52'S | 50 | 85/160/285 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Kedunggudel RT/RW 04/02 Kedunggudel, Kab. Ngawi Prov. Jawa Timur | HTI | JAW-JI-NGW-3667 | WIDODAREN KEDUNGGUDEL | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ngawi | 6617453 | 2021-08-09 |  | 71 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-22 | W43-2021 | Oct-2021 | 2021-10-22 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  | 2021-09-24 | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: STO READY TO DECLARE 18:08:21: NEED REVIEW POWER HTI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
663 |  | SUM-SU-LBP-2296 | 30701140031 | 022061109 | TAMBAK CEKUR | RORO JONGRANG 2021 [NEW] | TB | 98°54.50.54'E | 3°26.0.78'N | 40 | 110/230/310 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Timbang Deli,kecamatan galang, kabupaten deli serdang. | HTI | SUM-SU-LBP-2296 | SUNGGAL_MEDAN_KRIO | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617456 | 2021-08-09 |  | 68 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-22 | W43-2021 | Oct-2021 | 2021-10-22 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 126170618607 | 6.6 |  | 2021-10-04 |  |  | 2021-10-16 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: PONDASI OG 06:09:21: CME PREAPRATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
735 |  | JAW-JI-PSN-4127 | 30701510031 | 161903109 | POHJENTREK | RORO JONGRANG 2021 [NEW] | SKP | 112°53.41.32'E | 7°40.12.65'S | 40 | 40/110/310 | 2021 | RORO JONGRANG 2021 [NEW] | Jl Sastro Surotoko Desa Kel Wirogunan kec Purworejo Kab Pasuruan Jawa Timur | HTI | JAW-JI-PSN-4127 | PURWOREJO WIROGUNAN | COLO | TBG | East | JATIM | Jawa Timur | Kota Pasuruan | 6617454 | 2021-08-09 |  | 66 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-22 | W43-2021 | Oct-2021 | 2021-10-22 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 513500998222 | 6.6 |  | 2021-10-04 |  |  | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-29:09:21: SRFI 22:09:21: ME OG 19:09:21:15:09:21: 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
784 |  | SUM-SS-PLG-1273 | 30701730031 | TBG05_SSM132 | PERUM TLG. KELAPA | RORO JONGRANG 2021 [NEW] | BK | 104°41.38.08'E | 2°56.15.07'S | 40 | 0/180/250 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Perumas Talang Kelapa Kel. Talang Kelapa Kec. Alang-Alang Lebar, Kota Palembang, Prov. Sumatera Selatan | HTI | SUM-SS-PLG-1273 | TALANG_KELAPA_JALAN_BYPASS | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kota Palembang | 6617449 | 2021-08-09 |  | 65 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-22 | W43-2021 | Oct-2021 | 2021-10-22 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 141203537038 | 6.6 |  | 2021-10-04 |  |  | 2021-10-13 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-26:09:21: SRFI 22:09:21: 19:09:21:15:09:21: 13:09:21: ME OG 08:09:21:06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
689 |  | SUM-SU-LBP-2259 | 30701160031 | 021411109 | TERATAI PATUMBAK | RORO JONGRANG 2021 [NEW] | TB | 98°41.48.7'E | 3°30.36.61'N | 40 | 50/170/310 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Sari Dusun VI Pasar V Teratai B Marindal I Desa Marindal I Kec. patumbak Kab. deli Serdang | HTI | SUM-SU-LBP-2259 | DELI_TUA_MEKAR_SARI | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617456 | 2021-08-09 |  | 64 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-22 | W43-2021 | Oct-2021 | 2021-10-22 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 120150006031 | 6.6 |  | 2021-10-04 |  |  | 2021-10-12 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-15:09:21: SRFI 13:09:21: 08:09:21: 06:09:21: 30:08:21:25:08:21: RBS BTS FOUNDATION 22:08:21: STO READY TO DECLARE 18:08:21: NEED REVIEW POWER HTI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
698 |  | SUM-SU-LBP-2278 | 30701170031 | 022231109 | API_DUSUN VIIA KARANG ANYAR | RORO JONGRANG 2021 [NEW] | TB | 98°53.52.12'E | 3°36.48.92'N | 40 | 80/240/330 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Karang Anyar, Kec. Beringin, Kab. Deli Serdang, Prov. Sumatera Utara | HTI | SUM-SU-LBP-2278 | BERINGIN_SIDODADI_RAMUNIA | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617456 | 2021-08-09 |  | 68 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-23 | W43-2021 | Oct-2021 | 2021-10-23 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 126120948671 | 6.6 |  | 2021-10-04 |  |  | 2021-10-16 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: PONDASI OG 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
771 |  | SUM-SU-LBP-2257 | 30701150031 | 021236109 | SAWIT_REJO | RORO JONGRANG 2021 [NEW] | TB | 98°32.16.48'E | 3°33.22.03'N | 45 | 0/150/260 | 2021 | RORO JONGRANG 2021 [NEW] | Gang Perkutut Desa Sei Mencirim Kecamatan Sunggal Kabupaten Deli Serdang Provinsi Sumatera Utara | HTI | SUM-SU-LBP-2257 | KUTALIMBARU_SAWIT_REJO | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617456 | 2021-08-09 |  | 66 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-23 | W43-2021 | Oct-2021 | 2021-10-23 | W43-2021 | Oct-2021 | MW | 2021-09-04 |  | 122021125694 | 6.6 |  | 2021-10-04 |  |  | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: 08:09:21: RBS/BTS PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW CIVIL HUAWEI 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
695 |  | SUM-SU-PMS-2238 | 30701350031 | 021739109 | JLN HULAKMA SINAGA | RORO JONGRANG 2021 [NEW] | TB | 99°5.49.6'E | 2°58.36.48'N | 40 | 90/180/320 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Lorong Cempaka Bawah No. 0, Kel. Rambung Merah, Kec. Siantar, Kab. Simalungun, Prov. Sumatera Utara | HTI | SUM-SU-PMS-2238 | SIANTAR_PAMATANG_SIMALUNGUN | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Simalungun | 6617456 | 2021-08-09 |  | 66 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-24 | W44-2021 | Oct-2021 | 2021-10-24 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 121011230561 | 6.6 |  | 2021-10-04 |  |  | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-19:09:21: SRFI 15:09:21: ME OG 13:09:21: PONDASI OG 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21: STO READY TO DECLARE 22:08:21: 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
NEW SPK |  | SUM-SU-SDK-2228 | 30734670031 | T000677 | REP. SIDIKALANG-TONGGING | BP2022 | SKP | 98°26.27.56'E | 2°45.19.3'N | 50 | 80/130/330 | 2022 | New site 2022 - P2 | Desa Tanjung Beringin, Dusun I Sumbul | HTI | SUM-SU-SDK-2228 | PAGAGAN_JULU_II | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Dairi | 6617983 | 2022-01-28 | 2022-01-28 | 62 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 129010129364 | 6.6 |  | 2022-03-22 |  |  | 2022-03-31 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:03:22: RFIN 30:03:22: PLN 27:03:22-16:03:22: ME OG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-16:02:22: READY TO STO 13:02:22-09:02:22: READY TO DECLARE STO 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-SU-MDN-2231 | 30735130031 | 020600109 | GRIYA MARTUBUNG | BP2022 | TB | 98°41.9.17'E | 3°41.40.91'N | 35 | 20/100/160 | 2022 | New site 2022 - P1 | Jl. Pancing I/Gg. Rela Lingkungan III Kel. Besar (Kampung Besar), Kecamatan Medan Labuhan | HTI | SUM-SU-MDN-2231 | MEDAN_LABUHAN_BESAR | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kota Medan | 6617992 | 2022-01-28 | 2022-01-28 | 62 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | 2022-04-10 | W16-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-01 | 2022-02-02 | 128040132677 | 6.6 |  | 2022-03-22 |  |  | 2022-03-31 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:03:22: RFIN 30:03:22: PLN 27:03:22-16:03:22: ME OG 13:03:22-09:03:22: BTS PONDASI OG 06:03:22-13:02:22: READY TO STO 09:02:22: NEED REVIEW CIVIL HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED
NEW SPK |  | SUM-SS-MPR-1271 | 30734270031 | 0716762004 | IBS GUMAWANG_OGT | BP2022 | TB | 104°44.37.97'E | 4°1.30.4'S | 60 | 80/185/300 | 2022 | New site 2022 - P2 | Purwodadi Rt.003 Dusun IV Desa Purwodadi Kecamatan Belitang Mulya Kabupaten Ogan Komering Ulu Timur Provinsi Sumatra Selatan | HTI | SUM-SS-MPR-1271 | BELITANG_MULYA_SRI_MULYO | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617992 | 2022-01-28 | 2022-01-28 | 64 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-05-15 | W21-2022 | May-2022 | 2022-05-15 | W21-2022 | May-2022 | MW | 2022-02-01 | 2022-02-02 | 149300217425 | 6.6 |  | 2022-03-22 |  |  | 2022-04-02 | W14-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02:04:22: RFIN 30:03:22: PLN 27:03:22-20:03:22: ME OG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | buffer apr
738 |  | JAW-JI-KPN-4397 | 30701650031 | 161819109 | ADIMULYA | RORO JONGRANG 2021 [NEW] | SKP | 112°35.0.82'E | 8°7.59.2'S | 40 | 45/110/285 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Adikurnia RT 04 RW 03 Kel. Ardirejo Kec. Kepanjen, Kab. Malang Prov. Jawa Timur | HTI | JAW-JI-KPN-4397 | KEPANJEN ARDIREJO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Malang | 6617454 | 2021-08-09 |  | 70 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-26 | W44-2021 | Oct-2021 | 2021-10-26 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 513051713510 | 6.6. |  | 2021-10-04 |  | 2021-09-25 | 2021-10-18 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
741 |  | JAW-JI-KPN-4403 | 30701690031 | 161818109 | NGASEM MALANG | RORO JONGRANG 2021 [NEW] | SKP | 112°33.30.92'E | 8°6.9.04'S | 40 | 95/255/350 | 2021 | RORO JONGRANG 2021 [NEW] | Dukuh Sanan RT. 002 RW. 02 Desa NgasemKecamatan Ngajum | HTI | JAW-JI-KPN-4403 | NGAJUM NGASEM | COLO | TBG | East | JATIM | Jawa Timur | Kab. Malang | 6617454 | 2021-08-09 |  | 70 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-26 | W44-2021 | Oct-2021 | 2021-10-26 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 513051713528 | 6.6 |  | 2021-10-04 |  | 2021-09-25 | 2021-10-18 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-15:09:21: SRFI 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
708 |  | SUM-RI-RGT-0976 | 30701190031 | 040932109 | SIMPANG EMPAT BELILAS | RORO JONGRANG 2021 [NEW] | TB | 102°24.34.38'E | 0°33.41.62'S | 50 | 10/100/240 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Lintas Timur Sumatera Rt.04 Rw.06Kel. Pangkalan Kasai | HTI | SUM-RI-RGT-0976 | PANGKALANKASAI_LINTAS_SUMATERA | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Indragiri Hulu | 6617456 | 2021-08-09 |  | 94 | 91 - 120 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-28 | W44-2021 | Oct-2021 | 2021-11-14 | W47-2021 | Nov-2021 | MW | 2021-09-04 |  | 184103616399 | 6.6 |  | 2021-10-04 |  | 2021-11-08 | 2021-11-11 | W46-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11:11:21: RFIN 10:11:21-08:11:21: PLN CONNECT DONE 9 NOV, WAIT FOR RFIN 07:11:21-03:11:21: OG CME, NO REGISTER DONE RELEASED, PLAN BAYAR BPUJL 4 NOV 31:10:21: PERKUATAN TOWER DONE, PLAN CONNECT PLN 10 NOV 2021 27:10:21: PEMASANGAN TRAY OG, PLAN RFI 29 OCT 23:10:21: PERKUATAN OG, PLAN PERKUATAN DONE 28 OCT 20:10:21-29:09:21: SRFI ISSUE EXTEND TOWER 22:09:21:19:09:21: ME OG 14:09:21: PONDASI OG 13:09:21: CME PREPARATION, NEED EXTEND TOWER PROSES REVISI IMB, DAN PERLUASAN IW 08:09:21: 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: NEED REVIEW TNP ALITA 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
668 |  | JAW-JI-PMK-4237 | 30701540031 | 160462104 | TAMBERULAOK | RORO JONGRANG 2021 [NEW] | SKP | 113°26.22.99'E | 6°57.31.28'S | 50 | 5/85/260 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Raya Karang Penang Dusun Gua Timur Desa Pangereman Kecamatan Batu marmar Kabupaten Pamekasan | HTI | JAW-JI-PMK-4237 | BATUMARMAR PANGERREMAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Pamekasan | 6617454 | 2021-08-09 |  | 77 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-28 | W44-2021 | Oct-2021 | 2021-10-28 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  | 2021-09-25 | 2021-10-25 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:10:21: RFIN 20:10:21-15:09:21: SRFI 13:09:21:06:09:21: CME PREPARATION 30:08:21:25:08:21: 22:08:21: STO READY TO DECLARE 18:08:21: NEED REVIEW POWER HTI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
750 |  | JAW-JI-SPG-4230 | 30701620031 | 160219104 | BIRA BARAT | RORO JONGRANG 2021 [NEW] | SKP | 113°19.57.11'E | 6°56.23.86'S | 50 | 45/200/300 | 2021 | RORO JONGRANG 2021 [NEW] | Dsn.Langslebar Laok Ds.Bira Timur, Kec.Sukobanah Kab.Sampang, Prov.Jawa Timur | HTI | JAW-JI-SPG-4230 | KETAPANG PANCOR | COLO | TBG | East | JATIM | Jawa Timur | Kab. Sampang | 6617454 | 2021-08-09 |  | 77 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-28 | W44-2021 | Oct-2021 | 2021-10-28 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 517500856033 | 6.6 |  | 2021-10-04 |  |  | 2021-10-25 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:10:21: RFIN 20:10:21-15:09:21: SRFI 13:09:21: 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
745 |  | JAW-JI-KNR-4282 | 30701770031 | 160633104 | SELOPURO_KOTA | RORO JONGRANG 2021 [NEW] | SMI | 112°18.12.38'E | 8°9.14.51'S | 40 | 10/185/295 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Gading, RT 4 RW 8 Desa Selopuro Kec. Selopuro, Kab. Blitar Prov. Jawa Timur | HTI | JAW-JI-KNR-4282 | SELOPURO SELOPURO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Blitar | 6617453 | 2021-08-09 |  | 73 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-28 | W44-2021 | Oct-2021 | 2021-10-28 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 514080992478 |  |  | 2021-10-04 |  | 2021-09-25 | 2021-10-21 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:10:21-15:09:21: SRFI 13:09:21: ME OG 08:09:21: PONDASI OG 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
714 |  | JAW-JI-JBG-4178 | 30701080031 | 163728126 | SUMBERKEPUHLENGKONG | RORO JONGRANG 2021 [NEW] | TB | 112°20.44.55'E | 7°40.37.13'S | 50 | 135/255/330 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Raya Pulosari RT 04 RW 04 Desa Pulosari Kecamatan Bareng Kabupaten Jombang | HTI | JAW-JI-JBG-4178 | BARENG NGRIMBI | COLO | TBG | East | JATIM | Jawa Timur | Kab. Jombang | 6617456 | 2021-08-09 |  | 101 | 91 - 120 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-11-23 | W48-2021 | Nov-2021 | MW | 2021-09-04 |  | 514541411739 | 6.6 |  | 2021-10-04 |  | 2021-09-30 | 2021-11-18 | W47-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18:11:21: RFIN 17:11:21: RFI, WAIT FOR RFIN 14:11:21-27:10:21: OVERBLAST, OG PROSES MANAJEMEN TRAFO, PLAN RFI 23 NOV 24:10:21-29:09:21: SRFI, MINUS EXTEND TOWER 26:09:21: ME OG, PARALEL REVISI IMB, DAN PERLUASAN IW EXTEND TOWER 3M 19:09:21:15:09:21: 13:09:21: 08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW TNP ALITA 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
777 |  | SUM-SS-MRE-1233 | 30705650031 | 071041109 | ENIM2014_3G1 | RORO JONGRANG 2021 [NEW] | TB | 103°47.48.84'E | 3°45.52.02'S | 35 | 35/155/210 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Ling. Buluran Atas RT 01 RW 04 NO. 947, Ds. Tanjung Enim, Kec. Lawang Kidul, Kab. Muara Enim, Prov. Sumatera Selatan | HTI | SUM-SS-MRE-1233 | TANJUNG_ENIM_LINTAS_TENGAH | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Muara Enim | 6617456 | 2021-08-09 |  | 95 | 91 - 120 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-11-12 | W46-2021 | Nov-2021 | MW | 2021-10-04 |  | 147100688003 | 6.6 |  | 2021-10-04 |  | 2021-11-09 | 2021-11-12 | W46-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12:11:21: RFIN 10:11:21: SRFI ANNOUNCE 9 NOV, POWER CONNECT WAIT CONFIRM XL, PLAN RFI 11 NOV 07:11:21: STACKING DONE, PLN OVERLOAD, OG FU PLN, PLAN SRFI 10NOV 03:11:21: PLN OVERLOAD, OG FU PLN, PLAN SRFI 10NOV 31:10:21: WAIT FOR LOADING MATERIAL 27:20:21: DELIVERY MATERIAL & STACKING BASEFRAME ETA 28 OCT, PLAN RFI 31 OCT 24:10:21-26:09:21: SRFI 22:09:21: 19:09:21 15:09:21: RBS BTS FONDASI 13:09:21: CME PREPARATION 08:09:21: READY TO DECLARE STO 30:08:21:22:08:21: 18:08:21: NEED REVIEW TNP ALITA 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
666 |  | JAW-JI-BDW-3623 | 30701390031 | 163526126 | TANAHWULAN MAESAN | RORO JONGRANG 2021 [NEW] | TB | 113°45.14.47'E | 8°1.44.69'S | 50 | 40/105/235 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Krajan RT08/RW01, Desa Tanah Wulan, Kecamatan Maesan, Kabupaten Bondowoso | HTI | JAW-JI-BDW-3623 | MAESAN TANAH WULAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bondowoso | 6617456 | 2021-08-09 |  | 77 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | MULTIGUNA |  |  | 2021-10-04 |  | 2021-09-30 | 2021-10-25 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:10:21-29:09:21: SRFI, MINUS EXTEND TOWER 26:09:21-13:09:21: CME NY START, PROSES PENAMBAHAN KETINGGIAN TOWER, NEED REVISI IMB 06:09:21: CME PREPARATION 30:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW TNP ALITA 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
744 |  | JAW-JI-KPN-4407 | 30701630031 | 161790109 | JAMBESARI | RORO JONGRANG 2021 [NEW] | SKP | 112°43.36.52'E | 8°4.26.83'S | 50 | 60/130/320 | 2021 | RORO JONGRANG 2021 [NEW] | Dusun Ngembal RT 015 RW 04 Desa Ngembal Kec. Wajak Kab. Malang Jawa TimurKec. Wajak | HTI | JAW-JI-KPN-4407 | NGEMBAL WAJAK | COLO | TBG | East | JATIM | Jawa Timur | Kab. Malang | 6617454 | 2021-08-09 |  | 71 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 513020736952 | 6.6 |  | 2021-10-04 |  |  | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-29:09:21: SRFI, MINUS EXTEND TOWER 26-09:21-08:09:21: PONDASI OG, PARALEL PROSES PERLUASAN IW DAN REVISI IMB 06:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: 18:08:21: READY TO DECLARE STO 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
715 |  | JAW-JI-GSK-4332 | 30701180031 | 161342102 | PULO | RORO JONGRANG 2021 [NEW] | TB | 112°30.15.48'E | 7°18.1.37'S | 50 | 80/235/295 | 2021 | RORO JONGRANG 2021 [NEW] | Jl Desa Tulung, RT 02 RW 01, Desa Tulung, Kecamatan Kedamean | HTI | JAW-JI-GSK-4332 | KEDAMEAN TULUNG | COLO | TBG | East | JATIM | Jawa Timur | Kab. Gresik | 6617456 | 2021-08-09 |  | 70 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-09-04 |  | 511812349935 | 6.6 |  | 2021-10-04 |  | 2021-10-19 | 2021-10-18 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17:10:21-29:09:21: SRFI, MINUS EXTEND TOWER 26:09:21: ME OG, PARALEL REVISI IMB, DAN PERLUASAN IW EXTEND TOWER 3M 19:09:21:15:09:21: 13:09:21:08:09:21: ME OG 06:09:21: CME PREPARATION 30:08:21: STO READY TO DECLARE 22:08:21: NEED REVIEW TNP ALITA 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
680 |  | KAL-KS-MRH-1116 | 30705640031 | 220009109 | ANTAR JAYA | RORO JONGRANG 2021 [NEW] | TB | 114°41.39.05'E | 2°52.46.67'S | 62 | 135/185/320 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Anjir Telaran, RT/RW 02, Ds. Antarjaya, Kec. Marabahan, Kab. Barito Kuala, Kalimantan Selatan | HTI | KAL-KS-MRH-1116 | ANTAR_JAYA | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | Kab. Barito Kuala | 6617456 | 2021-08-09 |  | 83 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-24 | W44-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-10-04 |  | 221500569291 | 6.6 |  | 2021-10-04 |  | 2021-10-01 | 2021-10-31 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:10:21: RFI, WAIT FOR RFIN 27:10:21: NEED APPROVAL XL KONEKSI MULTIGUNA 24:10:21: MENUNGGU KONFIRMASI DARI PIHAK HTI TERKAIT KETERSEDIAAN PERANGKT (PLAN PLN MULTIGUNA) 20:10:21-10:10:21: SRFI, PROSES CONNECT PLN, PLAN PLN CONNECT 26 OCT 06:10:21: STO DECLARE 4 OCT, PROSES PLN CONNECTION 04:10:21-29:09:21: ME OG 26:09:21-19:09:21: PONDASI BTS OG 15:09:21: PREPARE CME, MATERIAL ON DELIVERY 13:09:21: 06:09:21: READY TO DECLARE STO 30:08:21: 22:08:21: NEED REVIEW TNP ALITA 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
778 |  | SUL-ST-PAL-1124 | 30705660031 | 260008109 | SKP UNISMUH EX PLE2 | RORO JONGRANG 2021 [NEW] | SKP | 119°52.56.78'E | 0°52.22.12'S | 40 | 60/150/250 | 2021 | RORO JONGRANG 2021 [NEW] | Kampus Unismuh, Jl. Hangtuah Kec.Palu Timur Kota Palu | HTI | SUL-ST-PAL-1124 | MANTIKULORE_TALISE | COLO | TBG | East | SULAWESI | Sulawesi Tengah | Kota Palu | 6617454 | 2021-08-09 |  | 66 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-10-28 | W44-2021 | Oct-2021 | 2021-10-28 | W44-2021 | Oct-2021 | MW | 2021-10-04 |  | 312101265485 | 6.6 |  | 2021-10-04 |  |  | 2021-10-14 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:10:21-29:09:21: SRFI, BP PAID 26:09:21-22:09:21: ME OG 13:09:21: CME PREPARATION 08:09:21: READY TO DECLARE STO 30:08:21:22:08:21: NEED REVIEW TNP ALITA 18:08:21: NEED REVIEW RNP HUWAWEI 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
523 |  | BAL-BA-DPR-1519 | 30692150031 | 1718991003 | DENPASARTIMUR_SUMERTAKAJA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 115°13.54.94'E | 8°38.33.39'S | 30 | 60/170/290 | 2021 | BLITZKRIEG 2021 [NEW] | JL. Turi Gg Umasari No.2 Br Tegalkuwalon Desa Sumerta Kaja Kec Denpasar Timur Kota Denpasar | HTI | BAL-BA-DPR-1519 | DENPASARTIMUR_SUMERTAKAJA | B2S | TBG | East | BALINUSRA | Bali | Kota Denpasar | 6617429 | 2021-08-05 |  | 85 | 61 - 90 days | 2022-01-02 | W02-2022 | Jan-2022 | 2021-12-12 | W51-2021 | Dec-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW |  |  | 551004998418 | 6.6 |  | 2021-10-02 |  |  | 2021-10-29 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:10:21: SRFI, PROSES ISDP OG 23:10:21: ERECTION OG -2 SECTION, PLAN RFI 29 OCT 21 20:10:21-17:10:21: ERECTION OG, NEED SK PLN 13:10:21: CURRING TIME OG, PLAN ERECTION 23 OCT NEED SK PLN 10:10:21: EXCAVATION DONE, REBARRING OG, PLAN PENGECORAN W3 OCT NEED SK PLN 06:10:21:STO DECLARE, EXCAVATION OG PLAN REBARRING 15 OCT 2021 04:10:21: NY CME WAITING PERMIT 26:09:21: APD PROSES, PLAN CME START 30 SEP 22:09:21: 19:09:21: REKOM CLEAR PLAN 21 SEP 15:09:21: REALISASI REKOM LURAH CAMAT, PARALEL PROSES APD PERCEPATAN 13:09:13: SOILTEST DONE REQUEST, FU UNTUK JADWAL SOILTEST 08:09:21: IW CLEAR, PLAN SOILTEST 11 SEPT 01:09:21: 30:08:21: VALIDASI DONE, IW CLEAR, PROSES SOUNDING PERIJINAN TERKAIT TIPE TOWER YANG DIPERBOLEHKAN DIBANGUN DIDAERAH TERSEBUT 25:08:21: SUBMIT KANDIDAT C HUNTING SESUAI ARAHAN PAK RAHMAT, VALIDASI RNP OK, VALIDASI TNP OG 22:08:21: 18:08:21: KANDIDAT B NOK HASIL VALIDASI RNP, REHUNTING SESUAI ARAHAN KORDINAT PAK RAHMAT 16:08:21 : SUBMIT KANDIDAT B VALIDASI RNP & TNP, KANDIDAT A GAGAL IW 10:08:21 : VALIDASI RNP & TNP DONE, CANDIDAT A GO, PROSES BAN/BAK 09:08:21 : SPK NEW BUILD RELEASED, HUNTING PROSES
941 |  | JAW-BT-TNG-1524 | 30711810031 | 1320422001 | IBS NEGLASARI | RELOCATION | TB | 106°38.21.16'E | 6°9.47.77'S | 40 | 0/90/180/270 | 2021 | RELOCATION | Jl. Pembangunan VI, Kel. Karang Sari Kp. Karang Sari RT.1 RW.12 Kec. Neglasari, Kota Tangerang Prov. Banten | EID | JAW-BT-TNG-1524 | KARANGSARI PEMBANGUNAN RELIOCATION | COLO | TBG | Central | Jabodetabek | Banten | Kota Tangerang | 6617648 | 2021-09-24 |  | 33 | 31 - 60 days | 2021-10-24 | W44-2021 | Oct-2021 | TBD | TBD | TBD | 2021-11-15 | W47-2021 | Nov-2021 | 2021-11-15 | W47-2021 | Nov-2021 | MW | 2021-10-04 |  | 566101065949 | 6.6 |  | 2021-10-01 |  |  | 2021-10-27 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:10:21: RFIN 24:10:21-17:10:21: ME OG 13:10:21: PONDASI RBS BTS OG 13:10:21-06:10:21: CME PREPARATION, PLAN INFOR DARI PAK HAKIM HANYA SAMPAI SRFI 26:09:21: SPK NEW RELEASED, ERM PROSES
934 |  | KAL-KT-KLK-0426 | 30711770031 | 210529109 | TBG_DSANJIRKALAMPAN | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 114°18.31.46'E | 2°47.35.41'S | 50 | 130/230/320 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Pangkalima Kapang, RT/RW 08/- Desa Anjir Kalampan Kec. Kapuas Barat, Kab. Kapuas Prov. Kalimantan Tengah | HTI | KAL-KT-KLK-0426 | KAPUAS_BARAT | COLO | TBG | Central | KALIMANTAN | Kalimantan Tengah | Kab. Kapuas | 6617642 | 2021-09-23 |  | 48 | 31 - 60 days | 2021-10-23 | W43-2021 | Oct-2021 | TBD | TBD | TBD | 2021-11-02 | W45-2021 | Nov-2021 | 2021-11-08 | W46-2021 | Nov-2021 | MW | 2021-10-04 |  | 225100184795 | 6.6 |  | 2021-10-01 |  |  | 2021-11-10 | W46-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:11:21: RFIN 07:11:21-31:10:21: RFI, WAIT FOR RFIN, PLAN RFIN 8 NOV 27:10:21: SRFI, PLAN RFI 29 OCT 24:10:21: SRFI, PLAN CONNECT 26 OCT 20:10:21-17:10:21: RBS BTS FOUNDATION PLAN ME GROUNDING 25 OCT 13:10:21-06:10:21: CME PREPARATION 04:10:21-26:09:21: SPK NEW RELEASED, ERM PROSES
940 |  | KAL-KS-KBR-0981 | 30711800031 | 220139104 | MEKAR JAYA | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 116°3.23.26'E | 2°55.40.22'S | 50 | 20/180/315 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Ratu Intan I Batu Gantang, Desa Bangkalaan Plelayu Rt 02 RW 01 Kec. Kelumpang Hulu, Kab. Kotabaru Prov. Kalimantan Selatan | HTI | KAL-KS-KBR-0981 | KELUMPANG_HULU | COLO | TBG | Central | KALIMANTAN | Kalimantan Selatan | Kab. Kotabaru | 6617641 | 2021-09-23 |  | 42 | 31 - 60 days | 2021-10-23 | W43-2021 | Oct-2021 | TBD | TBD | TBD | 2021-11-02 | W45-2021 | Nov-2021 | 2021-11-04 | W45-2021 | Nov-2021 | MW | 2021-10-07 |  | 223200578803 | 6.6 |  | 2021-10-01 |  |  | 2021-11-04 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:11:21: RFIN 03:11:21-31:10:21: RFI, NEED RFIN, PLAN RFIN 4 NOV 27:10:21: SRFI, ISSUE KWH KOSONG PLAN RFI W1 NOV 24:10:21: CME DONE, SRFI, ISSUE KWH KOSONG PLAN MULTIGUNA 2 NOV 20:10:21-17:10:21: RBS BTS FOUNDATION PLAN ME GROUNDING 23 OCT 13:10:21-06:10:21: CME PREPARATION 04:10:21-26:09:21: SPK NEW RELEASED, ERM PROSES
935 |  | KAL-KS-KGN-0944 | 30711780031 | 220747109 | TBG GM DESA BANGKALANMELAYU | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 115°17.2.65'E | 2°51.33.05'S | 60 | 25/90/225 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. H. Busra, Desa Malutu Rt.02 Rw.I Kec. Padang Batung, Kab. Hulu Sungai Selatan Prov. Kalimantan Selatan | HTI | KAL-KS-KGN-0944 | PADANG_BATUNG | COLO | TBG | Central | KALIMANTAN | Kalimantan Selatan | Kab. Hulu Sungai Selatan | 6617642 | 2021-09-23 |  | 39 | 31 - 60 days | 2021-10-23 | W43-2021 | Oct-2021 | TBD | TBD | TBD | 2021-11-02 | W45-2021 | Nov-2021 | 2021-11-02 | W45-2021 | Nov-2021 | MW | 2021-10-07 |  | 222200235589 | 6.6 |  | 2021-10-01 |  | 2021-11-01 | 2021-11-01 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01:11:21: RFIN 31:10:21: RFI, WAIT FOR RFIN 27:10:21: SRFI, ISSUE KWH KOSONG PLAN RFI W1 NOV 24:10:21: SRFI, ISSUE KWH KOSONG PLAN MULTIGUNA 2 NOV 20:10:21-17:10:21: RBS BTS FOUNDATION PLAN ME GROUNDING 25 OCT 13:10:21-06:10:21: CME PREPARATION 04:10:21-26:09:21: SPK NEW RELEASED, ERM PROSES
938 |  | KAL-KT-KSN-0434 | 30711790031 | 210605107 | GUNUNG MAS KATINGAN | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 113°6.0.36'E | 1°26.2.69'S | 40 | 0/200/280 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Dibun Isar RT.006 RW.002 Desa Samba Katung Kec.Katingan Tengah Kab.Katingan Prov.Kalsel | HTI | KAL-KT-KSN-0434 | KATINGAN_TENGAH | COLO | TBG | Central | KALIMANTAN | Kalimantan Tengah | Kab. Katingan | 6617641 | 2021-09-23 |  | 37 | 31 - 60 days | 2021-10-23 | W43-2021 | Oct-2021 | TBD | TBD | TBD | 2021-11-02 | W45-2021 | Nov-2021 | 2021-11-02 | W45-2021 | Nov-2021 | MW | 2021-10-04 |  | 224200225871 | 6.6 |  | 2021-10-01 |  |  | 2021-10-30 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:10:21: SRFI, KWH KOSONG PLAN RFI W1 NOV 24:10:21: SRFI, KWH KOSONG PLAN MULTIGUNA 2 NOV 20:10:21-17:10:21: RBS BTS FOUNDATION PLAN ME GROUNDING 25 OCT 13:10:21-06:10:21: CME PREPARATION 04:10:21-26:09:21: SPK NEW RELEASED, ERM PROSES
933 |  | KAL-KT-KLK-0425 | 30711760031 | 210539109 | TBG DESA SIDOREJO | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 114°24.17.68'E | 3°11.51.32'S | 40 | 60/200/270 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Siderejo RT 006/002 Kec. Tamban Catur, Kab. Kapuas Prov. Kalimantan Tengah | HTI | KAL-KT-KLK-0425 | TAMBAN_CATUR | COLO | TBG | Central | KALIMANTAN | Kalimantan Tengah | Kab. Kapuas | 6617642 | 2021-09-23 |  | 37 | 31 - 60 days | 2021-10-23 | W43-2021 | Oct-2021 | TBD | TBD | TBD | 2021-11-02 | W45-2021 | Nov-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-10-04 |  | 225000369738 | 6.6 |  | 2021-10-01 |  |  | 2021-10-30 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:10:21-24:10:21: SRFI, PLAN CONNECT 28 OCT 20:10:21-17:10:21: RBS BTS FOUNDATION PLAN ME GROUNDING 24 OCT 13:10:21-06:10:21: CME PREPARATION 04:10:21-26:09:21: SPK NEW RELEASED, ERM PROSES
933 |  | JAW-JI-PNG-4300 | 30711750031 | 160899104 | TULUNG_PON | ACTIVE - BLITZKRIEG 2021 [NEW] | SMI | 111°22.27.48'E | 7°49.19.74'S | 50 | 60/135/225 | 2021 |  | Desa Tulung Kec.Sampung, Kab.Ponorogo Prov.Jawa Timur | HTI | JAW-JI-PNG-4300 | SAMPUNG_TULUNG | COLO | TBG | EAST | JAWA TIMUR | Jawa Timur | Kab. Ponorogo | 6617627 | 2021-09-17 |  | 30 | < 30 days | 2021-10-17 | W43-2021 | Oct-2021 | TBD | TBD | TBD | 2021-10-17 | W43-2021 | Oct-2021 | 2021-10-17 | W43-2021 | Oct-2021 | MW | 2021-10-04 |  | 515402547522 |  |  | 2021-10-01 |  |  | 2021-10-17 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:10:21-13:10:21: SRFI 13:10:21-04:10:21: CME PREPARATION
939 |  | KAL-KS-PLI-0982 | 30711400031 | 220630109 | PAMALONGAN | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 114°52.40.48'E | 3°49.49.94'S | 39 | 45/240/320 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Pemalongan RT. 04 RW. 02 Kec. Bajuin, Kab. Tanah Laut Prov. Kalimantan Selatan | HTI | KAL-KS-PLI-0982 | BATUAMPAR_DAMAR_LIMA | COLO | TBG | Central | KALIMANTAN | Kalimantan Selatan | Kab. Tanah Laut | 6617641 | 2021-09-23 |  | 38 | 31 - 60 days | 2021-10-23 | W43-2021 | Oct-2021 | TBD | TBD | TBD | 2021-11-02 | W45-2021 | Nov-2021 | 2021-11-02 | W45-2021 | Nov-2021 | MW | 2021-10-07 |  |  |  |  | 2021-09-30 |  |  | 2021-10-31 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31:10:21: RFI, WAIT FOR RFIN 27:10:21: SRFI, ISSUE KWH KOSONG PLAN RFI W1 NOV 24:10:21: SRFI, ISSUE KWH KOSONG PLAN MULTIGUNA 2 NOV 20:10:21-17:10:21: RBS BTS FOUNDATION PLAN ME GROUNDING 25 OCT 13:10:21-06:10:21: CME PREPARATION 04:10:21-26:09:21: SPK NEW RELEASED, ERM PROSES
655 |  | SUM-KR-BTM-0618 | 30711390031 | T000926 | HOTEL VISTA | RELOCATION |  | 103°59.40.2'E | 1°6.40.32'N | 50 | 100/260/340 | 2021 | RELOCATION | Jl. Gajah Mada Km.9 Skp Southlinks Country Club & Golf Resort Sei Ladi Sekupang Batam | CAA | SUM-KR-BTM-0618 | TIBAN KAMPUNG RELOCATION 2 | COLO | TBG | West | SUMBAGTENG | Kepulauan Riau | Kota Batam | 6617608 | 2021-09-08 |  | 188 | > 150 days | 2021-10-08 | W41-2021 | Oct-2021 | TBD | TBD | TBD | 2022-03-31 | W14-2022 | Mar-2022 | 2022-03-31 | W14-2022 | Mar-2022 | MW | DONE |  |  |  |  | 2021-09-30 |  | 2021-11-18 | 2022-03-15 | W12-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:03:22: RFIN 13:03:22-10:03:22: OG CONNECT PLN, XL CONFIRM TANPA PKS 09:03:22-11:02:22: XL MEMINTA CONTOH INVOICE, OG COLLECT CONTOH INVOICE & SURAT PERNYATAAN DARI BM 09:02:22-06:02:22: ON PROCESS PKS DENGAN BM, NAMUN BM MENOLAK ADANYA PKS & BA, HANYA MEMBUTUHKAN INFO UNTUK INVOICING SAJA TETAPI XL TIDAK MAU JIKA HANYA INVOICE SAJA, PAK IMAM NY CONFIRM SINCE 02 FEB 22 02:02:22-16:01:22: ON PROCESS PKS DENGAN BM PIHAK HOTEL 12:01:22-27:12:21: PAK ROY CONFIRM CONNECT PLN 15 JAN 2022 & PARALEL BAK CORPORATE UNTUK PLN BY CORPORATE 26:12:21-08:12:21: WAIT ARAHAN DARI PAK ROY UNTUK PROCESS CONNECTION PLN KARENA MENUNGGU MATERIAL SIAP 08:12:21: XL GO CONFIRM HARGA PLN CORPORATE, OG PLN CONNECTION 07:12:21-31:10:21: SRFI, WAIT CONFIRM XL HARGA PLN CORPORATE 27:10:21 - 24:10:21: SRFI, NEGOSIASI DENGAN PIHAK HOTEL TERKAIT HARGA PER KWH UNTUK CONNECT PLN 20:10:21-13:10:21: ME GROUNDING OG, PLAN SRFI 15 OCT PEKERJAAN SAMAPAI SRFI DAHULU 06:10:21: CME PREPARATION 04:10:21: STO DECLARE 30 SEP 2021 22:09:21:19:09:21:15:09:21: 13:09:21: ERM PROSES
932 |  | BAL-BA-DPR-1511 | 30709150031 | 170615109 | 2016_TKD BILOK 11 | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 115°11.28.21'E | 8°42.37.69'S | 20 | 0/140/260 | 2021 |  | Jl. Taman Pancing, Kota Denpasar Prov. Bali | HTI | BAL-BA-DPR-1511 | SOUTH_GLOGOR_CARIK_RELOCATION | COLO | TBG | EAST | BALINUSRA | Bali | Kota Denpasar | 6617594 | 2021-09-07 |  | 56 | 31 - 60 days | 2021-10-07 | W41-2021 | Oct-2021 | TBD | TBD | TBD | 2021-10-14 | W42-2021 | Oct-2021 | 2021-11-10 | W46-2021 | Nov-2021 | MW |  |  | 551400481716 | 6.6 |  | 2021-09-22 |  |  | 2021-11-02 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02:11:21: RFIN 30:10:21: RFI, WAIT FOR RFIN 27:10:21: PEMASANGAN PANEL KWH & CONNECT PLN OG 26:10:21: ME OG 24:10:21-20:10:21: PROSES FABRIKASI PERKUATAN TOWER, PLAN DONE W3 OCT, PLAN RFI END OF OCT 17:10:21-06:10:21: PROSES PERKUATAN POLE 04:10:21: CME PREPARATION
541 |  | JAW-JT-SMG-0621 | 30707530031 | 142409126 | LAMPER KIDUL 1 | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°26.19.28'E | 7°0.13.82'S | 18 | 10/120/220 | 2021 |  | Jl. Jeruk Raya No.7, Kec. Semarang Selatan, Kota Semarang Prov. Jawa Tengah | EID | JAW-JT-SMG-0621 | RAMBUTAN RAYA LAMPERLOR | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kota Semarang | 6617535 | 2021-08-24 |  | 49 | 31 - 60 days | 2021-09-23 | W39-2021 | Sep-2021 | 2021-09-24 | W39-2021 | Sep-2021 | 2021-09-24 | W39-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-09-08 |  | 523013628582 | 7.7 |  | 2021-09-14 |  |  | 2021-10-12 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21-10:10:21: SRFI, BPUJL PAID 26:09:21-30:08:21: NEED REVIEW RND EID 25:08:21: SPK COLO RELEASED, SUBMIT ERM PROSES
540 |  | JAW-JT-SMG-0619 | 30706810031 | 140418109 | JANGLI 2 | ACTIVE - BLITZKRIEG 2021 [NEW] | MSI | 110°25.39.22'E | 7°2.24.11'S | 20 | 80/225/350 | 2021 |  | Jl. Bukit Khayangan No.2 Kel. Ngesrep Kec. Banyumanik, Kota Semarang Prov. Jawa Tengah | EID | JAW-JT-SMG-0619 | NGESREP BANYUMANIK | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kota Semarang | 6617478 | 2021-08-12 |  | 57 | 31 - 60 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2021-10-08 | W41-2021 | Oct-2021 | MW | 2021-09-08 |  | 523041096366 | 7.7 |  | 2021-09-13 |  |  | 2021-10-08 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:10:21: SRFI, PROSES REGISTRASI PLN, PLAN CONNECT 8 OCT 2021 26:09:21: ME OG 19:09:21: PONDASI BTS OG 15:09:21: 13:09:21: STO DECLARE 13 SEP, CME PREPARATION 06:09:21: 30:08:21: 22:08:21: 18:08:21: ERM PROSES, NEED REVIEW RNP EID 16:08:21: 08:12:2021 : SPK COLO RELEASED, SUBMIT ERM PROSES
590 |  | JAW-JI-GSK-4326 | 30706040031 | 1647262003 | IBS SEMBAYAT | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 112°34.26.22'E | 7°4.12.86'S | 53 | 0/170/180 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Pendopo, Desa Sembayat RT.19 RW.04 Kec.Manyar, Kab.Gresik Prov.Jawa Timur | HTI | JAW-JI-GSK-4326 | MANYAR_GRESIK | COLO | TBG | East | JATIM | Jawa Timur | Kab. Gresik | 6617584 | 2021-09-02 |  | 34 | 31 - 60 days | 2021-10-02 | W40-2021 | Oct-2021 | 2021-10-02 | W40-2021 | Oct-2021 | 2021-10-08 | W41-2021 | Oct-2021 | 2021-10-10 | W42-2021 | Oct-2021 | MW | 2021-09-21 |  | 511201194981 | 6.6 |  | 2021-09-09 |  |  | 2021-10-06 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:10:21-29:09:21: POWER CONNECTION PROSES 22:09:21: 19:09:21: ME OG 13:09:21: STO DECLARE 9 SEP, CME PREPARATION 09:08:2021: NEED REVIEW TNP ALITA 09:01:2021: ERM PROSES
526 |  | JAW-JB-MJL-4124 | 30692010031 | 1272501003 | MALAUSMA_BANYUSARI | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 108°15.10.51'E | 7°2.37.55'S | 50 | 0/120/50 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun Malausma Kidul RT. 001/ 001 Desa Malausma Kec. Malausma Kabupaten Majalengka Provinsi Jawa Barat | HTI | JAW-JB-MJL-4124 | MALAUSMA_BANYUSARI | B2S | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Majalengka | 6617420 | 2021-08-03 |  | 87 | 61 - 90 days | 2021-12-31 | W53-2021 | Dec-2021 | 2021-12-30 | W53-2021 | Dec-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-09-07 |  | 535212664637 | 5.5 |  | 2021-09-07 |  |  | 2021-10-29 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29:10:21: RFIN 27:10:21: ME OG, PLAN 29 OCT PLN CONNECT 23:10:21: ERECTION OG, PLAN RFI 31 OCT, CURRENTLY FU PLN KE ULP MAJALENGKA 20:10:21: CURRING TIME OG, PLAN ERECTION 25 OCT 17:10:21-13:10:21: REBARRING OG, PLAN PENGECORAN W3 OCT 06:10:21: EXCAVATION OG, PLAN REBARRING 10 OCT 2021 04:10:21: BOWPLANK OG, PLAN MULAI START GALIAN 6 OCT 2021 26:09:21: APD&DESIGN RELEASED, PREPARE TIM CME, CME START 29 SEP 2021 22:09:21: PERGESERAN KANDIDAT DISEBABKAN PENOLAKAN WARGA, KANDIDAT SUBMIT SOILTEST OG 19:09:21: 15:09:21: 13:09:21: 08:09:21: POURING OG (PROSES STOP MENUNGGU KUNJUNGAN KEMENINFO) 06:09:21: PEMBESIAN OG 01:09:21: EXCAVATION OG 30:08:21: RFC 08:24:2021:22:08:21: PROSES REALISASI REKOM dan IW, PARALEL SOILTEST 18:08:21: PENGAJUAN KANDIDAT B, KANDIDAT A FAIL KARENA PERLUASAN DAERAH PERLUASAN BANGUNAN SEKOLAH 16:08:21: 10:08:21 : RNP TNP REVIEW DONE CANDIDAT A GO, PROSES NEGO IW OG 09:08:21 : SPK NEW BUILD RELEASED, UNDER RNP REVIEW
556 |  | JAW-JT-BLA-0138 | 30705620031 | 1441082003 | IBS KIDANGAN JEPON | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 111°28.16.0'E | 6°55.58.62'S | 55 | 100/175/280 | 2021 |  | Jl. Ngrenak RT.001 RW.03, Kelurahan Sonokulon, Kecamatan Todanan, Kabupaten Blora, Provinsi Jawa Tengah | EID | JAW-JT-BLA-0138 | SAMBONG_KAWENGAN | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Blora | 6617535 | 2021-08-24 |  | 81 | 61 - 90 days | 2021-09-23 | W39-2021 | Sep-2021 | TBD | TBD | TBD | 2021-10-25 | W44-2021 | Oct-2021 | 2021-11-12 | W46-2021 | Nov-2021 | MW | 2021-11-22 |  | 520071607803 | 7.7 |  | 2021-09-06 | 2021-09-21 |  | 2021-11-13 | W46-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:11:21: RFIN 10:11:21: RFI, WAIT RFIN PLAN 11 NOV 07:11:21: BPUJL PAID, PLAN CONNECT PLN 10-11 NOV 03:11:21: PLAN CONNECT PLN 5 NOV 31:10:21-27:10:21: SRFI, PLAN W1 NOV, PROSES TANAM TIANG BY PLN OG, WAITING STAOR REGIST 3DAYS 24:10:21-13:10:21: SRFI, PROSES CONNECT PLN BY LL 06:09:21: STO DECLARE 30:08:21: 25:08:21: SPK COLO RELEASED, SUBMIT ERM PROSES
579 |  | BAL-BA-DPR-1517 | 30704680031 | 170363109 | SANUR KAJA 10 | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 115°15.4.03'E | 8°40.8.26'S | 20 | 145/260/350 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Sedap Malam No.16 Kec. Denpasar Selatan, Kota Denpasar Prov. Bali | HTI | BAL-BA-DPR-1517 | DENPASAR SELATAN_SANUR KAJA | COLO | TBG | East | BALINUSRA | Bali | Kota Denpasar | 6617564 | 2021-08-27 |  | 40 | 31 - 60 days | 2021-09-26 | W40-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | 2021-10-07 | W41-2021 | Oct-2021 | MW | 2021-09-07 |  | 551400476186 | 6.6 |  | 2021-09-03 |  |  | 2021-10-06 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04:10:21-29:09:21: PROSES GALVANIS MOUNTING STAR, PLAN DONE 1 OCT, LANJUT INSTALASI MOUNTING 2 HARI 26:09:21: SRFI 22:09:21: 19:09:21: ME OG 15:09:21: 13:09:21: CME PREPARATION, FABRIKASI MOUNTING STAR 06:09:21: STO DECLARE 3 SEPT 2021, PREPARE TIM CME
581 |  | BAL-BA-MGW-1549 | 30704780031 | 171600126 | MAMBAL_7 | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 115°14.6.0'E | 8°32.57.12'S | 20 | 90/190/280 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Kenanga, Desa Mekar Bhuwana, Abiansemal, Kab Badung | HTI | BAL-BA-MGW-1549 | ABIANSEMAL_MEKAR BHUANA | COLO | TBG | East | BALINUSRA | Bali | Kab. Badung | 6617564 | 2021-08-27 |  | 32 | 31 - 60 days | 2021-09-26 | W40-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | MW | 2021-09-07 |  | 551103984464 | 6.6 |  | 2021-09-03 |  |  | 2021-09-28 | W40-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26:09:21: SRFI 22:09:21:19:09:21: 15:09:21: ME DONE, MINUS MOUNTING & PLN 13:09:21: PONDASO OG, PARALEL FABRIKASI MOUNTING STAR 06:09:21: STO DECLARE 3 SEPT 2021, PREPARE TIM CME
600 |  | SUM-SU-BLG-2136 | 30704800031 | 022216109 | SEI SEMBILANG / DESA SIGAOL BARAT | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 99°3.2.27'E | 2°23.51.4'N | 40 | 40/200/310 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun Silima Kuta, Desa Sigaol Barat, Kec. Uluan, Kab. Toba Samosir, Prov. Sumatera Utara | HTI | SUM-SU-BLG-2136 | SIGAOL_BARAT | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Toba Samosir | 6617547 | 2021-08-26 |  | 37 | 31 - 60 days | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | MW | 2021-09-07 |  | 123100306398 | 6.6 |  | 2021-09-03 |  |  | 2021-10-02 | W40-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29:09:21: SRFI 22:09:21: 19:09:21: ME OG 13:09:21: 06:09:21: STO DECLARE 3 SEPT 2021, PREPARE TIM CME
544 |  | JAW-JI-LMJ-4235 | 30704210031 | 161258109 | TUNJUNGREJO TBG | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 113°12.3.71'E | 8°14.26.09'S | 40 | 30/190/290 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Wegalih Dusun Meleman RT.02 RW.04 Kec.Yosowilangun, Kab.Lumajang Prov.Jawa Timur | HTI | JAW-JI-LMJ-4235 | YOSOWILANGUN_WOTGALIH | COLO | TBG | East | JATIM | Jawa Timur | Kab. Lumajang | 6617406 | 2021-08-26 |  | 35 | 31 - 60 days | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | 2021-09-26 | W40-2021 | Sep-2021 | MW | 2021-09-07 |  | MULTIGUNA |  |  | 2021-09-03 |  |  | 2021-09-30 | W40-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29:09:21-19:09:21: SRFI 19:09:21:15:09:21: 13:09:21: ME OG 08:09:21: PONDASI OG 06:09:21: STO DECLARE 3 SEPT 2021, PREPARE TIM CME REPLAN RFI W4 SEPT 30:08:21: 22:08:21: 16:08:21: 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
564 |  | JAW-JT-TMG-2665 | 30704190031 | 1436521023 | KEDU TEMANGGUNG | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°8.32.46'E | 7°15.57.85'S | 60 | 55/150/255 | 2021 |  | Desa Karangtejo Dusun Krajan Barat RT.002 RW.002 Kec. Kedu, Kab. Temanggung Prov. Jawa Tengah | EID | JAW-JT-TMG-2665 | KUNDISARI KEDU TEMANGGUNG | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Temanggung | 6617531 | 2021-08-23 |  | 45 | 31 - 60 days | 2021-09-22 | W39-2021 | Sep-2021 | 2021-09-24 | W39-2021 | Sep-2021 | 2021-09-24 | W39-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-09-08 |  | 521561278616 | 7.7 |  | 2021-09-03 |  |  | 2021-10-07 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:10:21-15:09:21: SRFI, PLN OVB, PROSES PENGADAAN TRAFO DARI PLN 13:09:21: PONDASI DONE, ME OG 08:09:21: CME PREPARATION 30:08:21: ERM PROSES NEED REVIEW RND EID
577 |  | JAW-JI-BTU-4120 | 30704790031 | 162120109 | TULUNGREJO BATU | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 112°32.19.32'E | 7°51.12.64'S | 40 | 150/245/305 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Bumiaji Dusun Banaran RT.04 RW.05 Kec. Bumiaji, Kota Batu Prov.Jawa Timur | HTI | JAW-JI-BTU-4120 | BUMIAJI_BUMIAJI | COLO | TBG | East | JATIM | Jawa Timur | Kota Batu | 6617492 | 2021-08-13 |  | 48 | 31 - 60 days | 2021-09-12 | W38-2021 | Sep-2021 | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-28 | W40-2021 | Sep-2021 | 2021-09-28 | W40-2021 | Sep-2021 | MW | 2021-09-13 |  | 513031057963 | 6.6 |  | 2021-09-03 |  |  | 2021-09-30 | W40-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29:09:21-15:09:21: SRFI 13:09:21: ME OG 08:09:21: RBS BTS PONDASI OG 06:09:21: STO DECLARE 3 SEP 2021, PREPARE TIM CME 30:08:21: 22:08:21: 18:08:21: ERM PROSES, NEED REVIEW ALITA 16:08:21: 08:12:2021 : SPK COLO RELEASED, SUBMIT ERM PROSES
576 |  | JAW-JI-GSK-4324 | 30704170031 | 163081109 | PHYRUSBIRUDRIYOREJO | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 112°34.26.54'E | 7°18.9.68'S | 40 | 20/210/275 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Mojotengah Dusun Ngemplak Wonoayu Ceper RT.04 RW.02 Kec.Menganti, Kab.Gresik Prov.Jawa Timur | HTI | JAW-JI-GSK-4324 | MENGANTI_BOTENG | COLO | TBG | East | JATIM | Jawa Timur | Kab. Gresik | 6617493 | 2021-08-13 |  | 42 | 31 - 60 days | 2021-09-12 | W38-2021 | Sep-2021 | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-28 | W40-2021 | Sep-2021 | 2021-09-28 | W40-2021 | Sep-2021 | MW | 2021-09-07 |  | 511812345050 | 6.6 |  | 2021-09-03 |  |  | 2021-09-24 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:09:21: 19:09:21: 15:09:21: SRFI 13:09:21: PONDASI RBS BTS OG 08:09:21: PREPARE TIM AND MATERIAL CME 06:09:21: STO DECLARE 3 SEPTEMBER, PREPARE TIM CME REPLAN CONNECT W4 SEPT 30:08:21:22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
578 |  | JAW-JI-PNG-4282 | 30704180031 | 1646021023 | SAMBIT PONOROGO | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 111°32.4.2'E | 7°58.37.56'S | 50 | 0/120/240 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Grogol Dukuh Klanan RT.01 RW.01 Kec.Sawoo, Kab.Ponorogo Prov.Jawa Timur | HTI | JAW-JI-PNG-4282 | SAWOO_GROGOL | COLO | TBG | East | JATIM | Jawa Timur | Kab. Ponorogo | 6617493 | 2021-08-13 |  | 47 | 31 - 60 days | 2021-09-12 | W38-2021 | Sep-2021 | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | MW | 2021-09-07 |  | 515413779249 | 6.6 |  | 2021-09-03 |  |  | 2021-09-29 | W40-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26:09:21-15:09:21: SRFI 08:09:21: RBS BTS PONDASI OG 06:09:21: STO DECLARE 3 SEPT 2021, PREPARE TIM CME, REPLAN RFI W4 SEPT 30:08:21:22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
582 |  | BAL-BA-MGW-1551 | 30704810031 | 170921126 | KEROBOKAN KAJA_04 | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 115°10.20.03'E | 8°37.44.04'S | 20 | 40/200/290 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. raya dalung permai, dalung, kec. kuta utara, kab. badung | HTI | BAL-BA-MGW-1551 | KUTAUTARA_DALUNG | COLO | TBG | East | BALINUSRA | Bali | Kab. Badung | 6617482 | 2021-08-12 |  | 56 | 31 - 60 days | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-09-28 | W40-2021 | Sep-2021 | 2021-10-07 | W41-2021 | Oct-2021 | MW | 2021-09-07 |  | 551103986435 | 6.6 |  | 2021-09-03 |  |  | 2021-10-07 | W41-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:10:21-29:09:21: PROSES GALVANIS MOUNTING STAR, PLAN DONE 1 OCT, LANJUT INSTALASI MOUNTING 2 HARI 26:09:21: SRFI 22:09:21: 19:09:21: ME OG 15:09:21: 13:09:21: CME PREPARATION, FABRIKASI MOUNTING STAR 06:09:21: STO DECLARE 3 SEPT 2021, PREPARE TIM CME
599 |  | SUM-BE-AGM-0209 | 30704200031 | 0902961001 | PASARBEMBAH | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 102°12.18.45'E | 3°38.24.75'S | 40 | 50/120/300 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Lintas Bengkulu Utara, Dusun I, Desa Pasar Bembah, Kec. Air Napal, Kab. Bengkulu Utara Prov. Bengkulu | HTI | SUM-BE-AGM-0209 | PASAR_BEMBAH | COLO | TBG | West | LAMPUNG | Bengkulu | Kab. Bengkulu Utara | 6617547 | 2021-08-26 |  | 34 | 31 - 60 days | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | MW | 2021-09-07 |  | 146606891915 | 6.6 |  | 2021-09-02 |  |  | 2021-09-29 | W40-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26:09:21: SRFI 22:09:21: 19:09:21: ME OG 15:09:21: BOWPLANK 13:09:21: 06:09:21: STO DECLARE 3 SEPT 2021, PREPARE TIM CME
597 |  | SUM-BE-AGM-0205 | 30703900031 | 090241126 | PASAR BARU KOTA BANI | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 101°40.19.96'E | 3°13.42.92'S | 40 | 60/200/260 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun Jaya RT.09, Desa Air Muring, Kec. Putri Hijau, Kab. Bengkulu Utara Prov. Bengkulu | HTI | SUM-BE-AGM-0205 | KOTA_BANI | COLO | TBG | West | LAMPUNG | Bengkulu | Kab. Bengkulu Utara | 6617547 | 2021-08-26 |  | 34 | 31 - 60 days | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | MW | 2021-09-07 |  | 146802513523 | 6.6 |  | 2021-08-31 |  |  | 2021-09-29 | W40-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26:09:21: SRFI 22:09:21: 19:09:21: 15:09:21: PLN CONNECTION 13:09:21: RBS/BTS FOUNDATION 06:09:21: CME PREPARATION 06:09:21: STO DECLARE 2 SEPT 2021, PREPARE TIM CME
693 |  | SUM-RI-PBR-1163 | 30700700031 | 041142109 | LINTAS OKURA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 101° 30' 14" E | 0° 35' 31.02" N | 40 | 30/100/270 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Raja Panjang RT003/RW002, Kel. Tebing Tinggi Okura, Kec. Rumbai Pesisir, Kota Pekanbaru, Prov. Riau | HTI | SUM-RI-PBR-1163 | TEBING_TINGGI_OKURA | COLO | TBG | West | SUMBAGTENG | Riau | Kota Pekanbaru | 6617506 | 2021-08-16 |  | 39 | 31 - 60 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | MW | 2021-09-07 |  | 181300639577 | 6.6 |  | 2021-08-27 |  |  | 2021-09-24 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:09:21: 19:09:21:15:09:21: 13:09:21: 08:09:21: RBS/BTS PONDASI 06:09:21: 01:09:21: CME PREPARATION 30:08:21:25:08:21:22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21 : SPK COLO RELEASED, ERM PROSESS
89 COLO |  | SUM-LA-KTB-1148 | 30741740031 | 100132109 | HANDUYANG RATU-1 | BP2022 | TB | 104°55.59.84'E | 4°34.5.02'S | 65 | 85/155/270 | 2022 | Newsite 2022 - B2 | Desa Sumber Agung, Kec. Muara Sungkai, Kab Lampung Utara Prov. Lampung | HTI | SUM-LA-KTB-1148 | MUARA_SUNGKAI_SUMBER_AGUNG | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Utara | 6618079 | 2022-03-11 | 2022-03-11 | 40 | 31 - 60 days | 2022-04-10 | W16-2022 | Apr-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-03-24 | 2022-03-25 | 173001529010 |  |  | 2022-03-23 |  |  | 2022-04-20 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:04:22: RFIN 17:04:22-03:04:22: PONDASI OG 30:03:22-23:03:22: MOBDEMOB PREPARE CME 23:03:22-13:02:22: ESR PROCESS 11:02:22: SPK RECEIVED | buffer apr
585 |  | SUM-SS-IDL-1239 | 30700330031 | 0716832001 | IBS BAKUNG | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 104° 34' 23.27" E | 3° 11' 37.97" S | 60 | 60/120/270 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Palembang - Prabumulih, Desa Lorok, Kecamatan Inderalaya Utara, Kabupaten Ogan Ilir, Provinsi Sumatera Selatan | HTI | SUM-SS-IDL-1239 | PARIT | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Ilir | 6617506 | 2021-08-16 |  | 24 | < 30 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-15 | W38-2021 | Sep-2021 | MW | 2021-08-28 |  | 149000137996 | 6.6 |  | 2021-08-25 |  |  | 2021-09-09 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:09:21: ME OG 06:09:21: RBS/BTS FOUNDATION 01:09:21: 30:08:21:25:08:21: STO DECLARE 25 AUG 22:08:21: 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21 : SPK COLO RELEASED, ERM PROSESS
686 |  | SUM-JA-JMB-0487 | 30700300031 | 060352109 | EKA JAYA 2 | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 103° 39' 37.19" E | 1° 37' 6.02" S | 40 | 190/280/350 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Sersan Darpin RT 01 Kel. Ekajaya Kec. Jambi Selatan Kota Jambi Prop. Jambi | HTI | SUM-JA-JMB-0487 | PAAL_MERAH_EKAJAYA | COLO | TBG | West | SUMBAGSEL | Jambi | Kota Jambi | 6617506 | 2021-08-16 |  | 35 | 31 - 60 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-20 | W39-2021 | Sep-2021 | 2021-09-20 | W39-2021 | Sep-2021 | MW | 2021-08-28 |  | 143105959962 | 6.6 |  | 2021-08-25 |  |  | 2021-09-20 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:09:21: 15:09:21: PLN CONNECTION, KWH KOSONG, PLAN CONNECT 17 SEPT 13:09:21: 08:09:21: POWER CONNECTION PROSES 06:09:21: RBS/BTS FOUNDATION 01:09:21: CME PREPARATION 30:08:21:25:08:21: STO DECLARE 25 AUG 25:08:21:22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21 : SPK COLO RELEASED, ERM PROSESS
603 |  | SUM-SB-BSK-0856 | 30700320031 | 030687109 | SAWAH KAREH | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 100° 35' 28.43" E | 0° 32' 59.68" S | 60 | 80/150/300 | 2021 | BLITZKRIEG 2021 [NEW] | Jorong Sawah Kareh, Kenagarian Balimbing, Kec. Rambatan, Kab. Tanah Datar, Prov. Sumatera Barat | HTI | SUM-SB-BSK-0856 | SIMAWANG | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Tanah Datar | 6617506 | 2021-08-16 |  | 76 | 61 - 90 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-10-06 | W41-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-08-28 |  | 134510175465 | 6.6 |  | 2021-08-25 |  |  | 2021-10-31 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:10:21: PLAN CONNECT PLAN 28 OCT 24:10:21-29:09:21: SRFI TRAY AND MOUNTING HOLD ISSUE PERKUATAN, PLAN CONNECT PLN 25 OCT 22:09:21: 19:09:21: ME OG 15:09:21: 13:09:21: ME OG 08:09:21: 06:09:21: PONDASI RBS/BTS OG 01:09:21:30:08:21:CME PREPARATION 25:08:21: STO DECLARE 25 AUG 2021 22:08:21: NEED REVIEW TNP ALITA 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21 : SPK COLO RELEASED, ERM PROSESS
584 |  | SUL-SR-PLW-0179 | 30700410031 | 290013109 | SAPPOANG GSM | ACTIVE - BLITZKRIEG 2021 [NEW] | TRB | 119°17.24.54'E | 3°23.47.83'S | 50 | 120/180/320 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Family, Dusun SappoangDesa Patampanua Kec. Matakali | HTI | SUL-SR-PLW-0179 | MATAKALI_PATAMPANUA | COLO | TBG | East | SULAWESI | Sulawesi Barat | Kab. Polewali Mandar | 6617443 | 2021-08-06 |  | 74 | 61 - 90 days | 2021-09-05 | W37-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-08-28 |  | 329500381474 | 6.6 |  | 2021-08-25 |  |  | 2021-10-19 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:10:21-29:09:21: SRFI MINUS EXTEND TOWER 26:09:21:-22:09:21: ME OG, ISSUE EXTEND TOWER PROSES PERLUAWASAN IW DAN REVISI IMB 13:09:21: 08:09:21: ISSUE PROPOSE KETINGGIAN DI 44 SEDANGKAN TOWER EXISTING HANYA 42, PROSES EXTEND TOWER 45 HARI 06:09:21: 01:09:21: CME PREPARATION PROPOSE PENAMBAHAN KETINGGIAN TOWER, PROSES DELIVERY MATERIAL 30:08:21:25:08:21: STO DECLARE 25 AUG 22:08:21: 18:08:21: 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
604 |  | SUM-SB-SRK-0856 | 30700130031 | 030240109 | DMT BANJA LAWEH | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 100° 28' 15.74" E | 0° 3' 4.25" S | 60 | 0/130/280 | 2021 | BLITZKRIEG 2021 [NEW] | Jorong Banja LAweh Godang Nagari Banja Laweh Kecamatan Bukit Barisan Kabupaten Lima Puluh Kota Prop Sumbar | HTI | SUM-SB-SRK-0856 | BANJA_LOWEH | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kab. Lima Puluh Kota | 6617506 | 2021-08-16 |  | 39 | 31 - 60 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | MW | 2021-08-28 |  | 134530260068 | 6.6 |  | 2021-08-24 |  |  | 2021-09-24 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:09:21: SRFI 19:09:21: ME OG 15:09:21: 13:09:21: ME OG 08:09:21: 06:09:21: RBS/BTS FOUNDATION 01:09:21:30:08:21: CME PREPARATION 25:08:21: STO DECLARE 24 AUG 22:08:21: ERM PROSES, NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
588 |  | JAW-JI-TRK-4258 | 30700110031 | 160122104 | WATUAGUNG2 | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 111°42.59.62'E | 8°11.46.93'S | 50 | 70/140/320 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Raya Bandung, Desa Watuagung RT.19 Rw.05 Kec.Watulimo, Kab.Trenggalek Prov.Jawa Timur | HTI | JAW-JI-TRK-4258 | WATULIMO_WATUAGUNG | COLO | TBG | East | JATIM | Jawa Timur | Kab. Trenggalek | 6617492 | 2021-08-13 |  | 98 | 91 - 120 days | 2021-09-12 | W38-2021 | Sep-2021 | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-28 | W40-2021 | Sep-2021 | 2021-12-10 | W50-2021 | Dec-2021 | MW | 2021-08-28 |  | 515432223593 | 6.6 |  | 2021-08-24 |  | 2021-09-25 | 2021-11-19 | W47-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:11:21: RFIN 17:11:21: BP PAID, PLAN DONE DARI PLN 23 NOV 07:10:21-27:10:21: OG PEMINDAHAN JALUR PLN KRN COMCASE, PLAN DONE W2 NOV 24:10:21-29:09:21: SRFI, ISSUE COMMCASE DAN UP DAYA SESUAI SURAT KEPUTUSAN DARI PLN ESTIMASI PENGERJAAN 3 MINGGU 06:09:21: POWER CONNECTION PROSES 06:09:21: CME PREPARATION 01:09:21: PONDASI OG 30:08:21: CME PREPARATION 25:08:21: STO DECLARE 24 AUG 22:08:21: ERM PROSES, NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
605 |  | SUM-SB-PYH-0842 | 30700120031 | 0308971001 | KAPALO KOTO TBG | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 100° 38' 25.87" E | 0° 15' 39.04" S | 40 | 0/80/150 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Ki hajar dewantara RT.003 RW.002,Desa Kapalo Koto Ampangan,Kec.Payakumbuh Selatan,Kota Payakumbuh Provinsi Sumatera Barat | HTI | SUM-SB-PYH-0842 | KAPALO_KOTO | COLO | TBG | West | SUMBAGTENG | Sumatera Barat | Kota Payakumbuh | 6617506 | 2021-08-16 |  | 37 | 31 - 60 days | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | MW | 2021-08-28 |  | 134520321399 | 6.6 |  | 2021-08-23 |  |  | 2021-09-22 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:09:21: ME OG 15:09:21: 13:09:21: 08:09:21: ME OG 06:09:21: PONDASI RBS/BTS OG 01:09:21:30:08:21: CME PREPARATION 25:08:21: STO DECLARE 23 AUG 22:08:21: ERM PROSES, NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21 : SPK COLO RELEASED, ERM PROSESS
545 |  | JAW-JB-NPH-4133 | 30696800031 | 125067109 | JALANPLERET | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 107°34.5.3'E | 6°48.5.44'S | 40 | 0/135/295 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Kertawangi Kp. Keboncau RT.02 RW.05 Kec. Cisarua, Kab. Bandung Barat Prov. Jawa Barat | HTI | JAW-JB-NPH-4133 | CISARUA_KERTAWANGI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung Barat | 6617492 | 2021-08-13 |  | 85 | 61 - 90 days | 2021-09-12 | W38-2021 | Sep-2021 | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2021-11-13 | W46-2021 | Nov-2021 | MW | 2021-08-25 |  | 535891340762 | 6.6 |  | 2021-08-23 |  |  | 2021-11-06 | W45-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:11:21: RFIN 03:11:21: PROCESS COLO OG, PONDASI OG, PLAN RFI 16 NOV 31:10:21: HARDCOMCASE, PLAN 29 REALISASI COMCASE, PLAN START CME 30 OCT 26:10:21 - 24:10:21-06:10:21:Adanya permintaan kompensasi Colo sebesar 20 jt. Sudah dilakukan negosiasi sebesar 3 jt. Akan dilakukan pertemuan kembali tanggal 9 Oktober 2021. Kalo warga tidak bisa menerima plan akan dikawal oleh Polsek. Target close 25 Oktober 2021 04:10:21-06:09:21: HARD COMMCASE PENYETOPAN BY WARGA, BELUM ADA ANGKA KEPUTUSAN UNTUK KOMPENSASI, FU BY ARCOM, PLAN CLOSED W1 OCT 08:01:2021:30:08:21: COMMCASE, ISSUE PENYETOPAN BY LL, PROSES NEGOSIASI BY TIM ARCOM (HARD COMECASE) PLAN OPEN W3 SEPT 25:08:21: STO DECLARE 23 AUG, CME PREPARATION 22:08:21: ERM PROSES, NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
558 |  | JAW-JB-CMS-4142 | 30696790031 | 125285109 | RANCAH-KAWALI | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 108°21.8.32'E | 7°11.45.24'S | 30 | 70/260/355 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Dusun Desa Kulon, Desa Ciakar RT.03 RW.06, Kec. Cipaku, Kab. Ciamis Prov. Jawa Barat | HTI | JAW-JB-CMS-4142 | CIPAKU_CIAKAR | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Ciamis | 6617493 | 2021-08-13 |  | 68 | 61 - 90 days | 2021-09-12 | W38-2021 | Sep-2021 | 2021-09-11 | W37-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2021-10-25 | W44-2021 | Oct-2021 | MW | 2021-08-25 |  | 532314733498 | 6.6 |  | 2021-08-23 |  |  | 2021-10-20 | W43-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:10:21: RFIN 17:10:21-06:10:21:Case terkait dengan permintaan kompensasi Colo oleh warga sebesar 25 jt dilakukan negosiasi sampai turun diangka 15 jt. Hari ini sudah dilakukan negosiasi kembali ke warga sesuai dengan arahan management yaitu 10 jt tetapi warga tetap meminta 15 jt. Plan koordinasi dengan RM. Target Close 9 Oktober 2021. 04:10:21-01:09:21: COMECASE, PENYETOPAN BY LL, PROSES NEGOSIASI BY TIM ARCOM SEDANG MENUJU KE CIAMIS UNTUK MELANJUTKAN PROSES NEGOSIASI, PLAN CLEAR 30 SEP 30:08:21: 25:08:21: STO DECLARE 23 AUG CME PREPARATION 22:08:21: ERM PROSES, NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
580 |  | SUM-SS-MPR-1249 | 30700100031 | 0716682004 | IBS TULUNG_HARAPAN_OGT | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 104°51.0.22'E | 3°54.35.6'S | 50 | 0/100/200 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Desa Karang Mulya Rt.003/002, Desa Karang Mulya, Kec. Semendawai Timur, Kab. Ogan Komering Ulu Timur, Sumatera Selatan | HTI | SUM-SS-MPR-1249 | SEMENDAWAI_TIMUR_TULUNGHARAPAN | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617459 | 2021-08-10 |  | 34 | 31 - 60 days | 2021-09-09 | W37-2021 | Sep-2021 | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | MW | 2021-08-28 |  | 149300178407 | 6.6 |  | 2021-08-23 |  |  | 2021-09-13 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:09:21: 06:09:21: SRFI 01:09:21: ME OG 30:08:21: RBS/BTS FOUNDATION 25:08:21: STO DECLARE 23 AUG 22:08:21: ERM PROSES, NEED REVIEW CIVIL HTI 18:08:21: ERM PROSES, NEED REVIEW RNP HTI 16:08:21:10:08:21 : SPK COLO RELEASED, ERM PROSES
596 |  | KAL-KB-SRY-0813 | 30700090031 | T002857 | KALIMAS - 140190 | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 109°13.30.25'E | 0°5.14.78'S | 50 | 60/260/340 | 2021 | BLITZKRIEG 2021 [NEW] | Jl.Kalimas Tengah Rt.005 Rw.002 Desa Kalimas Kec.Sungai Kakap Kab.Kubu Raya | HTI | KAL-KB-SRY-0813 | SUNGAIKAKAP_PUNGGUR_KECIL | COLO | TBG | JABO | KALIMANTAN | Kalimantan Barat | Kab. Kubu Raya | 6617413 | 2021-08-04 |  | 36 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | MW | 2021-08-28 |  | 211211726985 | 6.6 |  | 2021-08-23 |  |  | 2021-09-09 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:08:2021: POWER CONNECTION PROSES 09:06:2021: 09:01:2021: PONDASI RBS/BTS OG REPLAN 13 SEP 08:30:2021: CME PREPARATION 08:25:2021: STO DECLARE 23 AUG 08:22:2021: NEED REVIEW POWER HUAWEI 08:18:2021: 08:16:2021:08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES NEED REVIEW TNP ALITA
567 |  | KAL-KT-KSN-0433 | 30696780031 | 210074109 | PANGKOH | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 113°25.48.68'E | 1°58.45.91'S | 60 | 0/200/300 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. PLN Desa Luwuk Kanan RT. 05/02 Kec. Tasik Payawan, Kab. Katingan, Kalimantan Tengah | HTI | KAL-KT-KSN-0433 | LUWUK_KANAN | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Tengah | Kab. Katingan | 6617413 | 2021-08-04 |  | 55 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | MW | 2021-08-25 |  | MULTIGUNA |  |  | 2021-08-23 |  |  | 2021-09-28 | W40-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26:09:21: SRFI, CONNECT PLAN MULTIGUNA 22:09:21: 19:09:21: PONDASI BTS OG 15:09:21: 13:09:21: 08:09:21: NY START KARENA SITE MASIH BANJIR 06:09:21: 01:09:21: 30:08:21: NY START CME KARENA AREA SITE BANJIR REPLAN W3 SEP 25:08:21:STO DECLARE 25 AUG 22:08:21: NEED REVIEW POWER HUAWEI 18:08:21: 16:08:21:09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES NEED REVIEW TNP ALITA
550 |  | JAW-YO-SMN-0060 | 30696760031 | 150631109 | API_SRIMULYO PIYUNGAN | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°28.7.03'E | 7°49.20.35'S | 38.00.00 | 10/105/180/275 | 2021 |  | JL. Krasaan Desa Jogotirto Kec Berbah Kab. Sleman DI Yogyakarta | EID | JAW-YO-SMN-0060 | BERBAH PIYUNGAN JOGOTIRTO | COLO | TBG | CENTRAL | JATENG | DI Yogyakarta | Kab. Sleman | 6617408 | 2021-08-03 |  | 37 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-15 | W38-2021 | Sep-2021 | MW | 2021-08-10 |  | 521012969733 | 7.7 |  | 2021-08-23 |  |  | 2021-09-09 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:09:21: SRFI POWER CONNECTION PROSES REPLAN RFI 15 SEP 2021 30:08:21: RBS/BTS PONDASI OG 25:08:21: STO DECLARE 23 AUG, MAPPING MITRA CME, CME PREPARATION 22:08:21: STO READY TO DECLARE 18:08:21: ESR PROSES, NEED REVIEW TNP ALITA 16:08:21: 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
542 |  | JAW-JT-BYL-0242 | 30696820031 | 1436551023 | BOYOLALI NOGOSARI | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°46.22.73'E | 7°28.24.2'S | 50.00.00 | 20/110/200/280 | 2021 |  | Desa Sembungan - Karang joho RT.014 RT.003 Kec.Nogosari, Kab.Boyolali Prov. Jawa Tengah | EID | JAW-JT-BYL-0242 | KETITANG NOGOSARI | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Boyolali | 6617408 | 2021-08-03 |  | 44 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | MW | 2021-08-10 |  | 520551311502 | 7.7 |  | 2021-08-20 |  |  | 2021-09-16 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:09:21: 13:09:21: SRFI 06:09:21: 01:09:21: 30:08:21: RBS/BTS PONDASI OG 25:08:21:09:08:21: SPK COLO ACTUAL PENGERJAAN B2S NEED OPSIC, PLAN RFI W3 OCT 04:08:21 : SPK COLO RELEASED, ERM PROSES ADA POTENSI KETERLAMBATAN DI PROSES KARENA MASIH MENUNGGU IMB RELEASED
546 |  | JAW-JB-MJL-4125 | 30696770031 | 120131109 | DSMRGAMUKTI-BANYUSARI | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 108°15.57.19'E | 7°1.49.66'S | 50.00.00 | 90/210/330 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Lebakwangi Blok Cikadu Kec. Malausma, Kab. Majalengka Prov. Jawa Barat | HTI | JAW-JB-MJL-4125 | MALAUSMA_LEBAKWANGI_GELORA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Majalengka | 6617406 | 2021-08-03 |  | 34 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | MW | 2021-08-25 |  | 535212645919 | 6.6 |  | 2021-08-18 |  |  | 2021-09-06 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:06:2021: POWER CONNECTION PROSES 09:01:2021: ME OG 08:30:2021: PONDASI OG 08:25:2021: CME PREPARATION 08:22:2021: STO DECLARE 18 AUG 08:16:2021: NEED REVIEW CIVIL HTI 08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES
543 |  | JAW-JB-NPH-4176 | 30696710031 | 124935126 | SETRA DUTA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 107°34.9.62'E | 6°52.24.96'S | 20 | 0/120/240 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Sariwangi Kp. Babakan Lembur Tengah No.1 RT.01 RW.07 Kec. Parongpong, Kab. Bandung Barat Prov. Jawa Barat | HTI | JAW-JB-NPH-4176 | PARONGPONG_SARIWANGI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung Barat | 6617406 | 2021-08-03 |  | 88 | 61 - 90 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-10-10 | W42-2021 | Oct-2021 | 2021-10-30 | W44-2021 | Oct-2021 | MW | 2021-08-25 |  | 535812240425 | 6.6 |  | 2021-08-18 |  |  | 2021-10-30 | W44-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30:10:21: RFIN 27:10:21: BLOCKING BY LL, PLAN 28 OCT OPEN, PLAN RFI 30 OCT 25:10:21: FABRIKASI MATERIAL OG, PLAN DONE 29 OCT 24:10:21-06:10:21:Sudah dilakukan kunjungan ke LL terkait dengan adanya penambahan colo XL. LL meminta untuk penambahan perangkat dilakukan dibawah dengan expand lahan sebesar 50 jt / tahun. karena ditakutkan tidak kuat untuk ditempat di tower. Plan kunjungan kembali tanggal 8 Oktober 2021. Target Close 25 Oktober 2021. 04:10:21: PERKUATAN TOWER DONE, SITE COMMCASE LL MINTA PERLUASAN EXPAND LAHAN 26:09:21-01:09:21: NEED PERKUATAN TOWER, PROSES PERKUATAN BASEFRAME TOWER 30:08:21: 25:08:21:CME PREPARATION 22:08:21: STO DECLARE 18 AUG 16:08:21: NEED REVIEW CIVIL HTI 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
681 |  | JAW-JB-SMD-4268 | 30696190031 | 122232109 | CIJAMBU-DSGENTENG | RORO JONGRANG 2021 [NEW] | SKP | 107°47.50.6'E | 6°51.4.82'S | 50 | 150/220/320 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Kadakajaya Dusun Cijambu RT.04 RW.03 Kec. Tanjungsari, Kab. Indramayu Prov. Jawa Barat | HTI | JAW-JB-SMD-4268 | TANJUNGSARI_KADAKAJAYA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Sumedang | 6617454 | 2021-08-09 |  | 32 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | MW | 2021-08-18 |  | 535172077424 | 6.6 |  | 2021-08-16 |  |  | 2021-09-10 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:09:21: 01:09:21:SRFI 30:08:21: PONDASI DONE 25:08:21: PONDASI RBS/BTS OG 22:08:21: CME PREPARATION 18:08:21: STO DECLARE 16 AUG 16:08:21: 09:08:21 : SPK COLO RELEASED, ERM PROSES
598 |  | SUL-SN-MSB-1435 | 30696400031 | 280119109 | LARA BAEBUNTA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 120°17.35.38'E | 2°41.28.25'S | 60 | 0/160/220 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun Lara Desa Lara Kec. Baebunta Kab. Luwu Utara Sulawesi Selatan | HTI | SUL-SN-MSB-1435 | BAEBUNTA_LARA | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Luwu Utara | 6617435 | 2021-08-06 |  | 35 | 31 - 60 days | 2021-09-05 | W37-2021 | Sep-2021 | 2021-09-06 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | MW | 2021-08-18 |  | 326600638615 | 6.6 |  | 2021-08-16 |  |  | 2021-09-10 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:09:21: PROSES CONNECT PLN, MENUNGGU JADWAL PLN 06:09:21: 01:09:21: 30:08:21: Power Connection Proses 25:08:21:PONDASI BTS RBS OG 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 16 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
571 |  | JAW-JT-WNG-2771 | 30706710031 | 140863104 | KEBUNAGUNG | ACTIVE - BLITZKRIEG 2021 [NEW] | SMI | 110°57.17.17'E | 7°45.20.23'S | 50 | 0/115/180/250 | 2021 |  | Talunombo Rt. 01/02, Kel. Bulusulur, Kec. Wonoharjo Kab.Wonogiri. | EID | JAW-JT-WNG-2771 | MENTO WONOHARJO | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Wonogiri | 6617416 | 2021-08-04 |  | 111 | 91 - 120 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-11-22 | W48-2021 | Nov-2021 | MW | 2021-08-10 |  | 526530134532 | 7.7 |  | 2021-08-16 |  |  | 2021-11-23 | W48-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23:11:21: RFIN 21:11:21-17:11:21: CONNECT PLN 16 NOV, NAMUN METERAN RUSAK (LAMPU INDIKATOR TDK NYALA, METERAN TIDAK BERPUTAR), OG PROCESS CONNECT PLN, PLAN CONNECT 22 NOV 16:11:21: CONNECT PLN DONE 14:11:21: SRFI, PLAN CONNECT 16 NOV 10:11:21: BPUJL PAID, PLAN CONNECT 13 NOV 10:11:21-15:09:21: SRFI, PLN OVB PROSES PENGAJUAN PENGADAAN TRAFO DARI PLN, PLAN RFI W2 NOV 13:09:21: ME OG 08:09:21: RBS BTS PONDASI 30:08:21: CME PREPARATION 30:08:21:25:08:21: MAPPING MITRA CME, CME PREPARATION 18:08:21:STO DECLARE 16 AUG 09:08:21: NEED REVIEW CIVIL EID 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
551 |  | JAW-JT-PBG-1234 | 30696670031 | 141621109 | KARANG GAMBAS | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 109°18.50.0'E | 7°21.41.47'S | 50 | 65/180/245/315 | 2021 |  | Jl. Raya Karang Lesem, Ds. Karang Lesem, Kec. Kutasari, Kab. Purbalingga | EID | JAW-JT-PBG-1234 | KARANGKLESEM KUTASARI | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purbalingga | 6617414 | 2021-08-04 |  | 108 | 91 - 120 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-11-20 | W47-2021 | Nov-2021 | MW | 2021-08-10 |  | 522032706779 | 7.7 |  | 2021-08-16 |  |  | 2021-11-20 | W47-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:11:21: RFIN 17:11:21: BPUJL paid, PLN OB trafo, sudah berupaya mencara trafo dari PLN area lain blm berhasil, eskalasi ke management level PLN dan akan diupayakan menggunakan trafo rekondisi, PLAN RFI 20 NOV 14:11:21: PENAMBAHAN JTR 4 TIANG & NEW TRAFO, INSTALASI MEMERLUKAN PEMADAMAN & SOP PLN 6 HARI, PLAN CONNECT 16 NOV 21 10:11:21: OG WAIT KWH 07:11:21: REGIST RELEASED, PLAN CONNECT PLN 10-11 NOV 21 03:11:21-26:10:21: MENUNGGU MATERIAL TRAFO DARI PLN, PLAN W2 NOV 24:10:21-15:09:21: SRFI PLN OVB, PROSES PEMBAGIAN BEBAN POWER 13:09:21: SRFI 06:09:21: POWER CONNECTION PROSES 01:09:21: ME OG, REPLAN 6 SEPT 30:08:21: RBS/BTS PONDASI OG 25:08:21: MAPPING MITRA PREPARE CME 22:08:21:18:08:21: STO DECLARE 16 AUG 09:08:21: NEED REVIEW CIVIL EID 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
552 |  | JAW-JT-PBG-1224 | 30696090031 | 141662109 | KEDUNGMENJANGAN | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 109°22.27.59'E | 7°24.30.74'S | 50 | 25/200/275 | 2021 |  | Desa Kedung Menjangan RT.02 RW.01, Kec. Purbalingga, Kab. Purbalingga Prov. Jawa Tengah | EID | JAW-JT-PBG-1224 | KEDUNGMENJANGAN PURBALINGGA | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purbalingga | 6617414 | 2021-08-04 |  | 68 | 61 - 90 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-10-18 | W43-2021 | Oct-2021 | 2021-10-18 | W43-2021 | Oct-2021 | MW | 2021-08-10 |  | 522032690027 | 7.7 |  | 2021-08-16 |  |  | 2021-10-11 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10:10:21: SRFI, MINUS PONDASI STACKING, GDL READY 6 OCT, PLAN CONNECT 8 OCT 26:09:21-19:09:21: ME OG 15:09:21: PONDASI STACKING OG, MATERIAL & GDL ON PROSES 13:09:21: 06:09:21: PROSES GDL STACKING 01:09:21: FABRIKASI MATERIAL STACKING PLAN DONE W3 SEPT, REPLAN W2 OCT 30:08:21: RBS/BTS PONDASI OG 08:24:2021: CME PREPARATION 22:08:21:18:08:21: STO DECLARE 16 AUG 09:08:21: NEED REVIEW CIVIL EID 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
534 |  | SUM-SS-MPR-1254 | 30696380031 | 070987109 | SUMSEL2014_2G55 | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 104°36.3.24'E | 4°12.40.46'S | 60.00.00 | 60/250/350 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Sumber Mulyo / Berasan Mulyo RT. 02 Rw. 07 Kec. Buay Madang Timur Kab. OKU Timur Prop. Sumsel | HTI | SUM-SS-MPR-1254 | CUTNYAKDIEN_SUMBER_MULYO | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ulu Ti | 6617407 | 2021-08-03 |  | 31 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | MW | 2021-08-18 |  | 147600643560 | 6.6 |  | 2021-08-16 |  |  | 2021-09-03 | W36-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:06:2021: 09:01:2021: 08:30:2021: 08:25:2021:08:22:2021: SRFI, POWER CONNECTION PROSES 08:22:2021:RBS/BTS FOUNDATION 08:18:2021: CME PREPARATION 08:16:2021: STO DECLARE 16 AUG 08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES
535 |  | SUL-SN-PKJ-1402 | 30696390031 | 2815612010 | IBS IBS_MAK0055_SULTAN | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 119°35.57.84'E | 4°40.42.64'S | 50.00.00 | 120/220/300 | 2021 | BLITZKRIEG 2021 [NEW] | Jl desa Punranga RT 003 RW 001 Desa Punranga Kec Marang Kab Pangkep | HTI | SUL-SN-PKJ-1402 | MARANG_PUNRANGA | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Pangkajene Kepulauan | 6617407 | 2021-08-03 |  | 34 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | MW | 2021-08-18 |  | 320400177241 | 6.6 |  | 2021-08-16 |  |  | 2021-09-06 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:06:2021: 09:01:2021: 08:30:2021: Power Connection Proses 08:25:2021: CME PREPARATION 08:22:2021: 08:16:2021: 08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES
679 |  | JAW-JB-CMS-4236 | 30696160031 | 120230104 | BANTARDAWA | RORO JONGRANG 2021 [NEW] | SKP | 108°36.53.82'E | 7°25.5.84'S | 50 | 0/95/205 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Padaringan Dusun Rata Harta RT.11 RW.03, Kec. Purwadadi, Kab. Ciamis Prov. Jawa Barat | HTI | JAW-JB-CMS-4236 | PURWADADI_PADARINGAN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Ciamis | 6617454 | 2021-08-09 |  | 32 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | MW | 2021-08-18 |  | 532217786318 | 6.6 |  | 2021-08-13 |  |  | 2021-09-10 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:09:21: 01:09:21:30:08:21: 25:08:21: SRFI 22:08:21: Pondasi Done, ME OG 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
678 |  | JAW-JB-SBR-4248 | 30696130031 | 125477126 | WATUWELAH-PERBUTULAN | RORO JONGRANG 2021 [NEW] | TB | 108°29.20.51'E | 6°44.19.1'S | 30 | 15/95/190 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. I Gede Mayaguna, Kel. Pasalakan RT.01 RW.05, Kec. Sumber, Kab. Cirebon Prov. Jawa Barat | HTI | JAW-JB-SBR-4248 | SUMBER_PASALAKAN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Cirebon | 6617456 | 2021-08-09 |  | 32 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | MW | 2021-08-18 |  | 533313465243 | 6.6 |  | 2021-08-13 |  |  | 2021-09-10 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:09:21: 01:09:21:30:08:21: 25:08:21: SRFI 22:08:21: Pondasi Done, ME OG 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
712 |  | SUM-SU-LBP-2286 | 30696320031 | 020252104 | GALANG2 | RORO JONGRANG 2021 [NEW] | SMI | 98°54.7.99'E | 3°29.28.72'N | 55 | 30/110/180 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Galang, Dusun SATU, Desa Tanah Aabng, Kec. Galang, Kab. Deli Serdang, Prov. Sumatera Utara | HTI | SUM-SU-LBP-2286 | KOTASAN | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Deli Serdang | 6617453 | 2021-08-09 |  | 37 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-16 | W38-2021 | Sep-2021 | 2021-09-16 | W38-2021 | Sep-2021 | MW | 2021-08-18 |  | 126170617328 | 6.6 |  | 2021-08-13 |  |  | 2021-09-15 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:09:21: 13:09:21: 08:09:21: 01:09:21:30:08:21: SRFI 25:08:21:PONDASI RBS/BTS OG 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
731 |  | SUM-RI-PKK-1154 | 30696310031 | 040875109 | WBB PANGKALAN KERINCI 2 | RORO JONGRANG 2021 [NEW] | TB | 101°50.48.23'E | 0°24.15.62'N | 50 | 130/240/340 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Kilometer 2 Langgam RT 06 RW 10 Pangkalan Kerinci Kota, Pangkalan Kerinci, Pelalawan, Riau | HTI | SUM-RI-PKK-1154 | PANGKALAN_KERINCI_BARAT | COLO | TBG | West | SUMBAGTENG | Riau | Kab. Pelalawan | 6617456 | 2021-08-09 |  | 38 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | MW | 2021-08-18 |  | 5898 | 6.6 |  | 2021-08-13 |  |  | 2021-09-16 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:09:21: PLN OG, BY CORPORATE 08:09:21: 06:09:21: 01:09:21:POWER CONNECTION PROSES 30:08:21:ME OG 25:08:21: PONDASI RBS BTS OG 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
575 |  | JAW-JB-SOR-4230 | 30696140031 | 125274126 | JL GANDASOLI KIDUL | RORO JONGRANG 2021 [NEW] | TB | 107°32.43.84'E | 7°2.1.07'S | 30 | 50/220/315 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Gandasari Kp. Patrol RT.004 RW.009, Kec. Katapang, Kab. Bandung Prov. Jawa Barat | HTI | JAW-JB-SOR-4230 | SOREANG_CINGCIN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung | 6617456 | 2021-08-09 |  | 36 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | MW | 2021-08-18 |  | 535322166314 | 6.6 |  | 2021-08-13 |  |  | 2021-09-14 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:09:21: 08:09:21: POWER CONNECTION PROSES 06:09:21: RBS/BTS PONDASI 01:09:21:30:08:21: 25:08:21:22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
765 |  | SUM-BB-TDN-0531 | 30696330031 | 080126104 | GUNUNG TAJAM | RORO JONGRANG 2021 [NEW] | SMI | 107°50.48.34'E | 2°45.44.53'S | 50 | 50/170/320 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Gunung Tajam, Rt.10/03 Dusun Air Begantung Kel. Kacang Butor, Kec. Badau, Kab. Belitung | HTI | SUM-BB-TDN-0531 | KACANG_BOTOR_BANDARA | COLO | TBG | West | SUMBAGSEL | Kepulauan Bangka Belitung | Kab. Belitung | 6617453 | 2021-08-09 |  | 49 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-28 | W40-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | MW | 2021-08-18 |  | MULTIGUNA |  |  | 2021-08-13 |  |  | 2021-09-27 | W40-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:09:21: 19:09:21:13:09:21: 08:09:21: 06:09:21: SRFI 01:09:21:30:08:21: 25:08:21: PONDASI RBS BTS OG 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
574 |  | JAW-JB-CMS-4237 | 30696170031 | 120251104 | KERTAHARJA | RORO JONGRANG 2021 [NEW] | SKP | 108°24.35.75'E | 7°18.14.54'S | 50 | 105/250/325 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Kertaharja Dusun Kolot RT.02 RW.15, Kec. Cijeungjing, Kab. Ciamis Prov. Jawa Barat | HTI | JAW-JB-CMS-4237 | CIJEUNGJING_KERTAHARJA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Ciamis | 6617454 | 2021-08-09 |  | 64 | 61 - 90 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | MW | 2021-08-18 |  | 532314731884 | 6.6 |  | 2021-08-13 |  |  | 2021-10-12 | W42-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06:10:21: ISSUE CLOSED, ME OG PLAN SRFI 13 OCT 2021 04:10:21-13:09:21: COMMCASE, PROSES MEDIASI KE PIHAK KEPALA DESA, WARGA MEMINTA HIGH KOMPENSASI PLAN CLOSED W1 OCT 08:09:21: 06:09:21: 01:09:21: 30:08:21:25:08:21: COMMCASE, PENYETOPAN PEKERJAAN OLEH LL, PROSES NEGOSIASI BY TIM ARCOM PLAN OPEN 11 SEP 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
566 |  | JAW-JT-WNG-2776 | 30689640031 | 141137109 | SENDANGMULYO TIRTOMOYO | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 111°1.24.24'E | 7°56.26.88'S | 50 | 50/120/260 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Sendang Mulyo Dusun Kerjo RT.001 RW.01 Kec. Tirtomoyo, Kab.Wonogiri Prov. Jawa Tengah | EID | JAW-JT-WNG-2776 | SENDANGMULYO TIRTOMOYO | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Wonogiri | 6617432 | 2021-08-06 |  | 41 | 31 - 60 days | 2021-09-05 | W37-2021 | Sep-2021 | 2021-09-05 | W37-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | MW |  |  | 526530126806 | 7.7 |  | 2021-08-13 |  |  | 2021-09-16 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:09:21: POWER CONNECTION PROSES 13:09:21:08:09:21: ME OG 06:09:21: RBS/BTS PONDASI REPLAN RFI W4 SEPT 2021
572 |  | JAW-JT-PBG-1231 | 30696100031 | 141700109 | KARANGANYAR | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 109°23.38.4'E | 7°17.17.38'S | 50 | 75/265/320 | 2021 |  | Jl. Selipan RT 01/ RW 02 Kel. Bugkanel Kec. Karang Anyar, Kab. Purbalingga Prov. Jawa Tengah | EID | JAW-JT-PBG-1231 | BUNGKANEL KARANGANYAR | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purbalingga | 6617414 | 2021-08-04 |  | 37 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | MW | 2021-08-10 |  | 522032690035 | 7.7 |  | 2021-08-13 |  |  | 2021-09-10 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:09:21: 06:09:21: POWER CONNECTION PROSES 01:09:21: ME OG REPLAN CONNECT PLN 10 SEPT 30:08:21: RBS/BTS PONDASI OG 25:08:21: MAPPING MITRA CME 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
586 |  | JAW-JI-KNR-4184 | 30696080031 | 160170104 | PAGERWOJO | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 112°22.47.42'E | 8°8.0.2'S | 50 | 10/120/270 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Wahidin Sudirohusodo, Desa Pagerwojo Rt.20 RW.05 Kec.Kesamben, Kab.Blitar Prov.Jawa Timur | HTI | JAW-JI-KNR-4184 | KESAMBEN_PAGERGUNUNG | COLO | TBG | East | JATIM | Jawa Timur | Kab. Blitar | 6617411 | 2021-08-04 |  | 40 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-15 | W38-2021 | Sep-2021 | 2021-09-15 | W38-2021 | Sep-2021 | MW | 2021-08-18 |  | 514080989069 | 6.6 |  | 2021-08-13 |  |  | 2021-09-13 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:09:21: 06:09:21: 01:09:21:30:08:21:Power Connection Proses 25:08:21: 22:08:21: 18:08:21: ME OG 16:08:21: PONDASI BTS OG 09:08:21: STO DECLARE 10 AUG 04:08:21 : SPK COLO RELEASED, ERM PROSES
561 |  | JAW-JT-PWR-1670 | 30696110031 | 140756104 | KALIGESING | ACTIVE - BLITZKRIEG 2021 [NEW] | SMI | 110°7.13.8'E | 7°43.9.01'S | 50 | 0/100/170/270 | 2021 |  | Ds. Pandan Rejo RT 03/01 Kec. Kaligesing Kab. Purworejo 54175 | EID | JAW-JT-PWR-1670 | PANDANREJO KALIGESING | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purworejo | 6617416 | 2021-08-04 |  | 47 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | MW | 2021-08-10 |  | 521521373838 | 7.7 |  | 2021-08-13 |  |  | 2021-09-20 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:09:21: 15:09:21: 13:09:21: 08:09:21: 06:09:21: POWER CONNECTION PROCESS BP PAID 01:09:21: ME OG REPLAN CONNECT PLN 10 SEPT 30:08:21: RBS/BTS PONDASI OG 25:08:21: MAPPING MITRA CME 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
559 |  | JAW-JT-KRG-2132 | 30696060031 | 142768126 | MOJOGEDANG TOHKUNING | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 111°2.13.6'E | 7°35.35.34'S | 40.00.00 | 20/90/290 | 2021 |  | Sentul RT 03 RW 01Kel. Sewurejo, Kec. Mojogedang, Kab. Karanganyar | EID | JAW-JT-KRG-2132 | MOJOGEDANG SEWUREJO | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Karanganyar | 6617408 | 2021-08-03 |  | 44 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | MW | 2021-08-10 |  | 526550131833 | 7.7 |  | 2021-08-13 |  |  | 2021-09-16 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:09:21: SRFI 13:09:21: 08:09:21: 06:09:21: 01:09:21: ME OG REPLAN CONNECT PLN W3 SEP 30:08:21: RBS/BTS PONDASI OG 25:08:21: MAPPING MITRA CME 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
565 |  | JAW-JT-KRG-2147 | 30696040031 | 141129109 | REJOSARI KARANGANYAR | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°50.8.23'E | 7°29.3.12'S | 55.00.00 | 55/190/310 | 2021 |  | Dsn Kricikan RT.03 RW.03 Ds. Rejosari, Kec. Gondangrejo, Kab Karanganyar | EID | JAW-JT-KRG-2147 | PEMERINTAH REJOSARI | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Karanganyar | 6617408 | 2021-08-03 |  | 51 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | MW | 2021-08-10 |  | 520521495640 | 7.7 |  | 2021-08-13 |  |  | 2021-09-23 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:09:21:15:09:21: POWER CONNECTION PROSES 13:09:21: 08:09:21: ME OG 01:09:21: 30:08:21: RBS/BTS PONDASI OG REPLAN W2 SEPT 25:08:21: MAPPING MITRA CME 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
562 |  | JAW-JT-PBG-1233 | 30696070031 | 142643109 | CANDIWULAN | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 109°18.1.01'E | 7°20.6.22'S | 50 | 70/150/230 | 2021 | ACTIVE - BLITZKRIEG 2021 [NEW] | Jl. Raya Tobong RT.013 RW.06 Desa Candiwulan Kec. Putatsari, Kab. Purbalingga Prov. Jawa Tengah | EID | JAW-JT-PBG-1233 | CANDIWULAN KUTASARI | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purbalingga | 6617408 | 2021-08-03 |  | 122 | 121 - 150 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-12-07 | W50-2021 | Dec-2021 | MW | 2021-08-10 |  | 522032711320 | 7.7 |  | 2021-08-13 |  |  | 2021-12-03 | W49-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03:12:21: RFIN 01:12:21: RFI, WAIT FOR RFIN 28:11:21: REGISTER RELEASED, PLAN CONNECT 7 NOV, STILL WAIT FOR TRAVO, SUDAH ESKALASI KE MANAGER UP PLN NAMUN STOK TRAVO MASIH KOSONG 24:11:21-21:11:21: REGISTER RELEASED, PLAN CONNECT 30 NOV (HASIL ESKALASI KE MANAGER PLN UP3) -> PLAN PERCEPATAN RFI 27 NOV 17:11:21-14:11:21: SRFI, PLAN CONNECT EOM NOV (HASIL ESKALASI KE MANAGER PLN UP3) 10:11:21: WAIT FOR TRAVO 07:11:21-06:09:21: SRFI, PLN OVERBLAST PROSES PENGADAAN TRAFO, ESTIMASI DARI PLN UNTUK PENGADAAN TRAFO KURANG LEBIH 2 MINGGU, PLAN RFI W2 NOV 01:09:21: ME OG REPLAN CONNECT PLN 10 SEPT 30:08:21: RBS/BTS PONDASI OG 25:08:21: MAPPING MITRA CME 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
560 |  | JAW-JT-PWD-0034 | 30696050031 | 141074109 | BANGSRI GROBOGAN | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°59.21.3'E | 7°14.26.7'S | 50 | 20/150/210 | 2021 |  | Desa Bangsri RT. 05 / 02, Kec. Geyer, Kab. Grobokan Prov. Jawa Tengah | EID | JAW-JT-PWD-0034 | BANGSRI GEYER GROBOGAN | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Grobogan | 6617408 | 2021-08-03 |  | 107 | 91 - 120 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-10-15 | W42-2021 | Oct-2021 | 2021-11-18 | W47-2021 | Nov-2021 | MW | 2021-08-10 |  | 525540196895 | 7.7 |  | 2021-08-13 |  |  | 2021-11-18 | W47-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18:11:21: RFIN 17:11:21-10:11:21: BPUJL PAID, PLAN CONNECT 18 NOV 07:11:21-10:10:21: OVERBLAST, PROSES PENGADAAN TRAFO PLAN CONNECT W2 NOV 26:09:21-15:09:21: POWER CONNECTION PROSES, OVB TRAFO, PROSES PEMBAGIAN BEBAN POWER 13:09:21: 08:09:21: 06:09:21: ME OG REPLAN RFI W3 SEPT 01:09:21:30:08:21: RBS/BTS PONDASI OG REPLAN 13 SEPT 25:08:21: MAPPING MITRA CME 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
657 |  | SUM-SS-SKY-1237 | 30696010031 | 070534109 | KAYUARA SEKAYU | RORO JONGRANG 2021 [NEW] | SKP | 103°51.21.92'E | 2°53.38.0'S | 40 | 10/80/220 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Merdeka LK 1, RT 001, RW 001, Kel. Kayuara, Kec. Sekayu, Kab. Muba, Prop. Sumsel | HTI | SUM-SS-SKY-1237 | SEKAYU_KAYUARA | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Banyuasin | 6617454 | 2021-08-09 |  | 30 | < 30 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-08 | W37-2021 | Sep-2021 | MW | 2021-08-18 |  | 1422011034653 | 6.6 |  | 2021-08-12 |  |  | 2021-09-08 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:06:2021: 09:01:2021: 08:30:2021: SRFI 08:25:2021: ME OG 08:22:2021: RBS/BTS FOUNDATION 08:18:2021: CME PREPARATION 08:16:2021: STO DECLARE 08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES
658 |  | SUM-RI-DUM-1145 | 30696000031 | 040205104 | KELAKAP_TUJUH | RORO JONGRANG 2021 [NEW] | SMI | 101°24.58.61'E | 1°39.53.96'N | 45 | 60/210/310 | 2021 | RORO JONGRANG 2021 [NEW] | Jl. Dock Gg. Pinang Merah Kel.Ratu Sima Kec. Dumao Barat Kota Dumai | HTI | SUM-RI-DUM-1145 | RATU_SIMA | COLO | TBG | West | SUMBAGTENG | Riau | Kota Dumai | 6617453 | 2021-08-09 |  | 28 | < 30 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-08 | W37-2021 | Sep-2021 | MW | 2021-08-18 |  | 182501156609 | 6.6 |  | 2021-08-12 |  |  | 2021-09-06 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:06:2021: 09:06:2021: 09:01:2021:POWER CONNECTION PROSES 08:30:2021:ME OG 08:25:2021: PONDASI RBS BTS OG 08:22:2021: 08:18:2021: CME PREPARATION 08:16:2021: STO DECLARE 12 AUG 08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES
687 |  | JAW-JB-SOR-4228 | 30695990031 | 122409109 | SERELA-DIVRE3 / BIRU-STOMAJALAYA2 | RORO JONGRANG 2021 [NEW] | SKP | 107°44.13.6'E | 7°3.11.16'S | 30 | 20/120/295 | 2021 | RORO JONGRANG 2021 [NEW] | Desa Padaulun Kp. Cihareuyheuy RT.01 RT.06 Kec. Majalaya, Kab. Bandung Prov. Jawa Barat | HTI | JAW-JB-SOR-4228 | MAJALAYA_PADAULUN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung | 6617454 | 2021-08-09 |  | 35 | 31 - 60 days | 2021-09-08 | W37-2021 | Sep-2021 | 2021-09-07 | W37-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | 2021-09-13 | W38-2021 | Sep-2021 | MW | 2021-08-18 |  | 535312300377 | 6.6 |  | 2021-08-12 |  |  | 2021-09-13 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:09:21: PLN OG 08:09:21: 09:06: 2021 POWER CONNECTION PROSES 01:09:21: 30:08:21: 25:08:21:22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 12 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
593 |  | JAW-JT-BNR-0267 | 30695980031 | 140558104 | GUMIWANG | ACTIVE - BLITZKRIEG 2021 [NEW] | SMI | 109°36.17.32'E | 7°24.24.12'S | 50 | 60/150/240/330 | 2021 |  | RT02/01 Kel. Binorong, Kec. Bawang, Kab. Banjarnegara | EID | JAW-JT-BNR-0267 | AJIBARANG SECANG BINORONG | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Banjarnegara | 6617416 | 2021-08-04 |  | 37 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | MW | 2021-08-10 |  | 522042906872 | 7.7 |  | 2021-08-12 |  |  | 2021-09-10 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:09:21: POWER CONNECTION PROSES 01:09:21: ME OG REPLAN CONNECT PLN 10 SEPT 30:08:21: RBS/BTS PONDASI OG 25:08:21: MAPPING MITRA CME 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
592 |  | JAW-JT-JPA-0705 | 30695950031 | 141046109 | BANDUNGHARJO | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°52.12.25'E | 6°25.32.3'S | 70.00.00 | 55/175/335 | 2021 |  | Jl. Bandungharjo Kelet, RT003 RW006 Desa Bandungharjo Kec. Donorojo, Kab. Jepara Prov. Jawa Tengah | EID | JAW-JT-JPA-0705 | BENTENG PORTUGIS BANDUNGHARJO | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Jepara | 6617408 | 2021-08-03 |  | 37 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | MW | 2021-08-10 |  | 520031344866 | 7.7 |  | 2021-08-12 |  |  | 2021-09-09 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:09:21: POWER CONNECTION PROSES 01:09:21: ME OG REPLAN CONNECT PLN 10 SEPT 30:08:21: RBS/BTS PONDASI OG 25:08:21: MAPPING MITRA CME 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
583 |  | JAW-JI-KNR-4191 | 30695960031 | 160518109 | SUKORAME TBG | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 112°21.59.04'E | 8°13.16.61'S | 50.00.00 | 0/120/230 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Melati RT.03 RW.04 Ds/ Kelurahan Birowo Kec Binangun Kab Blitar | HTI | JAW-JI-KNR-4191 | BINANGUN_BIROWO | COLO | TBG | East | JATIM | Jawa Timur | Kab. Blitar | 6617406 | 2021-08-03 |  | 41 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | MW | 2021-08-18 |  | MULTIGUNA |  |  | 2021-08-12 |  |  | 2021-09-13 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:09:21: 06:09:21: 01:09:21:30:08:21:Power Connection Proses 25:08:21: 22:08:21: 18:08:21: ME OG 16:08:21: PONDASI BTS OG 09:08:21: STO DECLARE 10 AUG 04:08:21 : SPK COLO RELEASED, ERM PROSES
570 |  | JAW-JT-PBG-1232 | 30695940031 | 142444109 | PEKALONGAN | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 109°19.10.78'E | 7°17.59.32'S | 50.00.00 | 70/230/315 | 2021 |  | Desa Pengalusan RT.002/RW.001 Kec. Mrebet, Kab. Purbalingga Prov. Jawa Tengah | EID | JAW-JT-PBG-1232 | PAGERANDONG MREBET | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purbalingga | 6617408 | 2021-08-03 |  | 41 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | 2021-09-14 | W38-2021 | Sep-2021 | MW | 2021-08-10 |  | 522032686844 | 7.7 |  | 2021-08-12 |  |  | 2021-09-13 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13:09:21: 08:09:21: POWER CONNECTION PROSES 01:09:21: ME OG REPLAN CONNECT PLN 10 SEPT 30:08:21: RBS/BTS PONDASI OG 25:08:21: MAPPING MITRA CME 22:08:21: 18:08:21: CME PREPARATION 16:08:21: STO DECLARE 13 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
591 |  | KAL-KU-TJS-0088 | 30695740031 | 231345109 | TB_ADANIGBL EX BUNYU_TIMUR_MG_C - RELOC | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 117°51.0.97'E | 3°31.16.9'N | 50 | 30/150/240 | 2021 | BLITZKRIEG 2021 [NEW] | (PT Adani Global) Ds Bunyu Timur, Kec Bunyu, Kota Tarakan, Prov Kalimantan Timur | HTI | KAL-KU-TJS-0088 | BUNYU | COLO | TBG | JABO | KALIMANTAN | Kalimantan Utara | Kab. Bulungan | 6617407 | 2021-08-03 |  | 114 | 91 - 120 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-11-22 | W48-2021 | Nov-2021 | 2021-11-25 | W48-2021 | Nov-2021 | MW | 2021-08-13 |  |  |  |  | 2021-08-12 |  |  | 2021-11-25 | W48-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:11:21: RFIN 24:11:21: XL CONFIRMED PLN 15MIO/MONTH, OG PROSES BAK & PKS DENGAN PT ADANI 21:11:21-24:10:21: PLN BY CORPORATE, MENUNGGU HASIL KEPUTUSAN DARI XL TERKAIT HARGA YANG DIBERIKAN OLEH PIHAK CORPORATE DGN HARGA 15JT/BLN 20:10:21-29:09:21: PLN BY CORPORATE, PROSES PENGAJUAN BA KEPADA PIHAK POWER XL, UNTUK DIAJUKAN KE CORPORATE PT ANDANI, TERKAIT KERJASAMA PENYAMBUNGAN PLN 26:09:21: SRFI, PLAN CONNECT MULTIGUNA 22:09:21:19:09:21: ME OG 15:09:21: PROSES PENGIRIMAN TRAY DAN PANEL ME DAN MOUNTING 13:09:21: 08:09:21: ME OG 06:09:21: PONDASI RBS/BTS OG 01:09:21: 30:08:21: 22:08:21: CME PREPARATION, NEED ADD TRANSPORT REPLAN 17 SEP 18:08:21: STO DECLARE 12 AUG 09:08:21: 04:08:21 : SPK COLO RELEASED, ERM PROSES
548 |  | JAW-JB-SBR-4158 | 30695780031 | 124102109 | PERTAMINA-KESENDEN | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 108°33.16.09'E | 6°41.14.46'S | 30 | 0/120/240 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Raya Sunan Gunungjati Gg. Mushola, Desa Jadimulya RT.004 RW.003, Kec. Gunungjati, Kab. Cirebon Prov. Jawa Barat | HTI | JAW-JB-SBR-4158 | GUNUNGJATI_JADIMULYA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Cirebon | 6617413 | 2021-08-04 |  | 33 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | MW | 2021-08-13 |  | 533113543152 | 6.6 |  | 2021-08-10 |  |  | 2021-09-06 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:06:2021: RFI 09:01:2021: 08:30:2021: SRFI 08:25:2021: Power Connection Proses, revisi SK PLN NY Released 08:22:2021:08:18:2021: ME OG 08:16:2021: PONDASI BTS DONE, TRAY MOUNTING DONE, WAITING PANEL ONSITE 08:09:2021: STO DECLARE 10 AUG, CME PREPARATION 08:04:2021 : SPK COLO RELEASED, ERM PROSES
532 |  | SUM-SU-PSP-2161 | 30692050031 | 022031109 | MUARA MANOMPAS | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 98°57.3.24'E | 1°25.54.98'N | 50.00.00 | 0/80/255 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Poros, Desa Muara Manompas, Kec. Muara Batang Toru , Kab. Tapanuli SelatanKab. Tapanuli Selatan, Prov. Sumatera Utara. | HTI | SUM-SU-PSP-2161 | HUTARAJA_MUARA_BATANG | COLO | TBG | West | SUMBAGUT | Sumatera Utara | Kab. Tapanuli Selatan | 6617407 | 2021-08-03 |  | 37 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | MW | 2021-08-13 |  | 124011355349 | 6.6 |  | 2021-08-10 |  |  | 2021-09-09 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:09:21: 01:09:21:30:08:21: SRFI POWER CONNECTION PROSES 25:08:21: 22:08:21: 18:08:21: ME OG 16:08:21: PONDASI BTS OG 09:08:21: STO DECLARE 10 AUG 04:08:21 : SPK COLO RELEASED, ERM PROSES
533 |  | JAW-JB-SOR-4411 | 30695760031 | 125137126 | CIGURUWIK | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 107°44.12.66'E | 6°56.2.8'S | 30.00.00 | 50/150/270 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Cinunuk Kp. Cijambe Wetan RT.004 RW.018, Kec. Cileunyi, Kab. Bandung Prov. Jawa Barat | HTI | JAW-JB-SOR-4411 | CIMEKAR_MARGAMULYA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung | 6617407 | 2021-08-03 |  | 29 | < 30 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | MW | 2021-08-13 |  | 535716494163 | 6.6 |  | 2021-08-10 |  |  | 2021-09-01 | W36-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:01:2021:08:30:2021: SRFI 08:25:2021: Power Connection Prosess waiting revisi SK PLN NY RELEASED 08:22:2021: Pondasi RBS done, ME OG 08:18:2021: MOBILISASI DAN DEMOBILISASI, CME PREPARATION 08:09:2021: STO DECLARE 10 AUG 08:04:2021 : SPK COLO RELEASED, ERM PROSES
589 |  | JAW-JI-SMP-4293 | 30695770031 | 161326109 | KETAWANG LAOK GULUK GULUK TBG | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 113°39.35.17'E | 7°1.54.98'S | 50.00.00 | 105/180/255 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Larangan, Kec. Gending, Kab. Sumenep Prov. Jawa Timur | HTI | JAW-JI-SMP-4293 | GULUKGULUK_KETAWANGLAOK | COLO | TBG | East | JATIM | Jawa Timur | Kab. Sumenep | 6617407 | 2021-08-03 |  | 48 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | MW | 2021-08-13 |  | MULTIGUNA |  |  | 2021-08-10 |  |  | 2021-09-20 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:09:21:15:09:21: 13:09:21:06:09:21:01:09:21:30:08:21:Power Connection Proses,KWH N/A 25:08:21: 22:08:21: 18:08:21: ME OG 16:08:21: PONDASI BTS OG 09:08:21: STO DECLARE 10 AUG 04:08:21 : SPK COLO RELEASED, ERM PROSES
587 |  | JAW-JI-BJN-4290 | 30695730031 | 160535109 | PANCUR TEMAYANG TBG | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 111°55.18.41'E | 7°17.56.94'S | 50.00.00 | 100/190/320 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Glagahan (Belakang Masjid Desa Glagahan) Kec. Sugihwaras, Kab. Bojonegoro Prov. Jawa Timur | HTI | JAW-JI-BJN-4290 | SUGIHWARAS_GLAGAHAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Bojonegoro | 6617407 | 2021-08-03 |  | 48 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | MW | 2021-08-13 |  |  |  |  | 2021-08-10 |  |  | 2021-09-20 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:09:21: 15:09:21: 13:09:21: 06:09:21: 01:09:21: 30:08:21:Power Connection Proses, KWH N/A 25:08:21: 22:08:21: 18:08:21: ME OG 16:08:21: PONDASI BTS OG 09:08:21: STO DECLARE 10 AUG 04:08:21 : SPK COLO RELEASED, ERM PROSES
549 |  | JAW-JB-IDM-4118 | 30692100031 | 125201109 | BLOKPILANG-BBKNREDOWETAN | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 108°0.31.1'E | 6°22.49.26'S | 40 | 90/210/330 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Bongas Pentil, Desa Bongas RT.06 RW.02, Kec. Bongas, Kab. Indramayu Prov. Jawa Barat | HTI | JAW-JB-IDM-4118 | BONGAS_BONGAS | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Indramayu | 6617413 | 2021-08-04 |  | 33 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | MW | 2021-08-13 |  | 534020127495 | 6.6 |  | 2021-08-09 |  |  | 2021-09-06 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:06:2021: RFI 09:01:2021:08:30:2021: SRFI 08:25:2021: Power Connection Proses, revisi SK PLN NY Released 08:22:2021:08:18:2021: ME OG 08:16:2021: PONDASI BTS DONE, TRAY MOUNTING DONE, WAITING PANEL ONSITE 08:09:2021: STO DECLARE 9 AUG, CME PREPARATION 08:04:2021 : SPK COLO RELEASED, ERM PROSES
547 |  | JAW-JB-CMS-4109 | 30692000031 | 121000104 | CINTAJAYA_CMS | ACTIVE - BLITZKRIEG 2021 [NEW] | SMI | 108°40.31.44'E | 7°23.36.49'S | 50 | 0/120/240 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Cintajaya Kp. Nambo RT.026 RW.05, Kec. Lakbok, Kab. Ciamis Prov. Jawa Barat | HTI | JAW-JB-CMS-4109 | LAKBOK_CINTAJAYA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Ciamis | 6617415 | 2021-08-04 |  | 33 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | MW | 2021-08-13 |  | 532217785722 | 6.6 |  | 2021-08-09 |  |  | 2021-09-06 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:06:2021: RFI 09:01:2021: 08:30:2021: 08:25:2021: Power Connection Proses, revisi SK PLN NY Released 08:22:2021:08:18:2021: ME OG 08:16:2021: PONDASI BTS DONE, TRAY MOUNTING DONE, WAITING PANEL ONSITE 08:09:2021: STO DECLARE 9 AUG, CME PREPARATION 08:04:2021 : SPK COLO RELEASED, ERM PROSES
602 |  | SUM-KR-RAN-0612 | 30692080031 | 050033109 | ROAD TO SP1 | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 108°21.22.97'E | 3°51.55.51'N | 60 | 50/120/285 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Raya Sebakung Rt.01 RW.01, Kel. Batu Gajah, Kec. Bunguran Timur, Kab. Natuna, Prov. Kepulauan Riau | HTI | SUM-KR-RAN-0612 | BATU_GAJAH | COLO | TBG | West | SUMBAGTENG | Kepulauan Riau | Kab. Natuna | 6617413 | 2021-08-04 |  | 44 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | 2021-09-17 | W38-2021 | Sep-2021 | MW | 2021-08-13 |  | 183082843350 | 6.6 |  | 2021-08-09 |  |  | 2021-09-17 | W38-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15:09:21: SRFI 13:09:21: 08:09:21: 06:09:21: ME OG, REPLAN RFI 17 SEP 01:09:21:30:08:21:25:08:21: PONDASI RBS BTS OG 22:08:21: 18:08:21: CME PREPARATION 10:08:21: 09:08:21: STO DECLARE 9 AUG, CME PREPARATION 04:08:21 : SPK COLO RELEASED, ERM PROSES
601 |  | SUM-KR-RAN-0613 | 30692070031 | 050035109 | CEMAGA (BUNGURAN SELATAN) | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 108°21.45.04'E | 3°47.0.1'N | 60 | 60/200/300 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Lada Hitam, Rt.03/01, Desa Cemaga, Kec. Bunguran Selatan, Kab. Natuna, Prov. Kepulauan Riau | HTI | SUM-KR-RAN-0613 | BUNGURAN_SELATAN_CEMAGA | COLO | TBG | West | SUMBAGTENG | Kepulauan Riau | Kab. Natuna | 6617413 | 2021-08-04 |  | 49 | 31 - 60 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | 2021-09-21 | W39-2021 | Sep-2021 | MW | 2021-08-13 |  | 183082843368 | 6.6 |  | 2021-08-09 |  |  | 2021-09-22 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:09:21:15:09:21: SRFI 15:09:21: SRFI 13:09:21: 08:09:21: 06:09:21: ME OG, RE PLAN RFI W2 SEPT 17 SEPT 2021 01:09:21:30:08:21:25:08:21: PONDASI RBS/BTS OG 22:08:21: 18:08:21: CME PREPARATION 10:08:21: 09:08:21: STO DECLARE 9 AUG, CME PREPARATION 04:08:21 : SPK COLO RELEASED, ERM PROSES
573 |  | JAW-JB-SPA-4181 | 30692060031 | 125480126 | SURYALAYA-PAGERAGUNG | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 108°11.43.62'E | 7°7.8.66'S | 50.00.00 | 25/90/260 | 2021 | BLITZKRIEG 2021 [NEW] | Kp. Puteran Kaler RT.04 RW.02 Desa Puteran Kec. Pagerageung, Kab. Tasikmalaya Prov. Jawa Barat | HTI | JAW-JB-SPA-4181 | PAGERAGEUNG_PUTERAN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Tasikmalaya | 6617406 | 2021-08-03 |  | 52 | 31 - 60 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2021-09-30 | W40-2021 | Sep-2021 | MW | 2021-08-13 |  | 532513684626 | 6.6 |  | 2021-08-09 |  |  | 2021-09-24 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19:09:21: 13:09:21: 08:09:21: SPECIAL DESIGN STACING, FLEXIBLE STACKING READY 15 SEP, REPLAN RFI 30 SEPT 06:09:21: 01:09:21: PONDASI OG REPLAN RFI 13 SEP 30:08:21: 08:24:2021: 22:08:21: 18:08:21: MOBILISASI DAN DEMOBILISASI, CME PREPARATION 09:08:21: STO DECLARE 9 AUG 04:08:21 : SPK COLO RELEASED, ERM PROSES
501 |  | JAW-JI-PSR-4262 | 30690060031 | 1650972007 | IBS LEBAK REJO | ACTIVE - BLITZKRIEG | TB | E°45.55.69'E | S°49.35.33'S | 50 | 90/155/310 | 2021 | BLITZKRIEG 2021 [NEW] | Desa Lebak Rejo Dusun Cari RT.003 RW.002 Kec.Purwodadi, Kab.Pasuruan Prov.Jawa Timur | HTI | JAW-JI-PSR-4262 | PURWODADI_LEBAKREJO | COLO | TBG | East |  | Jawa Timur | Kab. Pasuruan | 6616738 | 2021-07-12 |  | 32 | 31 - 60 days | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-12 | W33-2021 | Aug-2021 | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-11 | W33-2021 | Aug-2021 |  |  |  | 513580994612 | 6.6 |  | 2021-07-21 |  |  | 2021-08-13 | W33-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:10:21: 08:09:21: 08:04:21: Power Connection Proses 08:02:21: 07:29:21: SRFI,SK RELEASED 2 Aug 07.26.21 : Pondasi RBS/BTS OG, SK PLN NY Released 07.22.21: 07:19:21 SPK REACTIVE, CME PREPARATION 03.05.21 : SPK return by XL
514 |  | JAW-JT-PWD-0026 | 30690050031 | 1442452001 | IBS SEBOTO AMPEL | ACTIVE - BLITZKRIEG | TB | E°8.10.1'E | S°11.25.76'S | 50 | 90/240/335 | 2021 |  | Desa Rejosari Majan Kec. Kradenan, Kab. Grobogan Prov. Jawa Tengah | EID | JAW-JT-PWD-0026 | HIKMAH REJOSARI | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Grobogan | 6616739 | 2021-07-12 |  | 138 | 121 - 150 days | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-12 | W33-2021 | Aug-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2021-11-26 | W48-2021 | Nov-2021 | MW | 2021-11-24 |  | 525540201381 | 7.7 |  | 2021-07-19 |  |  | 2021-11-27 | W48-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27:11:21: RFIN 24:11:21-22:11:21: RFI, WAIT FOR RFIN 21:11:21: REGISTER EXPIRED, PLAN BAYAR 22 NOV, PLAN CONNECT 26 NOV 17:11:21-10:11:21: REVISI REGISTER OG, PLAN CONNECT 18 NOV 07:11:21-26:10:21: MENUNGGU MATERIAL TRAFO DARI PLN, PLAN W2 NOV 20:10:21-26:09:21: MENUNGGU PENGADAAN TRAFO DENGAN POWER NORMAL, UNTUK POWER 4.4 TIDAK DI APPROVED, MENUNGGU PROSES CONNECT DENGAN POWER NORMAL, ESTIMASI DARI PLN 1 BULAN 22:09:21: 19:09:21 UNDER REVIEW EID TERKAIT KELAYAKAN MG DENGAN POWER 4.4 15:09:21: OVERBLAST, NEED PENGADAAN TRAFO 7.7 Kva, MENUNGGU PENGADAAN TRAFO DARI PLN 13:09:21: 09:08:2021: PENGAJUAN MULTIGUNA 4.4 DITOLAK OLEH PAK IMAM, PROSES NEGOSIASI DENGAN PLN UNTUK PENAMBAHAN POWER 5.5 09:06:2021: 08:01:2021: PENGAJUAN PLN MULTIGUNA DENGAN POWER 4.4 KE PIHAK PLN REPLAN CONNECT 13 SEPT 08:30:2021:08:25:2021: POWER CONNECTION PROSES, OVB DISETUJUI PLN DENGAN POWER 4.4 08:18:2021: 08:16:2021: ME & GROUNDING SYSTEM, PLN OVERBLAST PROSES PEMBAGIAN BEBAN, REPLAN 30 AUG 08:10:2021: FABRIKASI MATERIAL, PONDASI OG REPLAN 27 AUG 08:04:2021: FABRIKASI MATERIAL COLO DI GUYEDMAST 08:02:2021: 07:29:2021 : Proses Perkuatan Tower, Paralel Pengerjaan CME 07.26.21 : 07.22.21 : 07:19:21 SPK REACTIVE, CME PREPARATION NEED PERKUATAN TOWER 03.05.21 : SPK return by XL
513 |  | JAW-JT-RBG-1787 | 30689760031 | 1441712004 | IBS WORO KRANGGAN | ACTIVE - BLITZKRIEG | TB | E°33.42.01'E | S°40.14.52'S | 50 | 20/95/165/290 | 2021 |  | Jl. Telon, Desa Woro Kec. Kragan, Kab. Rembang Prov. Jawa Tengah | EID | JAW-JT-RBG-1787 | TELON WORO | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Rembang | 6616739 | 2021-07-12 |  | 60 | 31 - 60 days | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-12 | W33-2021 | Aug-2021 | 2021-09-10 | W37-2021 | Sep-2021 | 2021-09-10 | W37-2021 | Sep-2021 | MW |  |  | 520062016878 | 7.7 |  | 2021-07-14 |  |  | 2021-09-10 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:08:2021: 09:06:2021: PLAN CONNECT 10 SEPT 09:01:2021:08:30:2021:08:25:2021: REGISTER RELEASED 27 AUG, PLAN CONNECT 7 SEPT 2021 WAITING JADWAL PLN 08:22:2021: 08:18:2021: XL APPROVE CONNECT DENGAN 5,5, WAITING KONFIRMASI DENGAN PMO EID CENTRAL PAK TEGUH PLAN 23 AUG 2021 08:16:2021: 08:10:2021 : MENUNGGU PERSETUJUAN XL TERKAIT PENYAMBUNGAN PLN DENGAN POWER 5.5Kva 08:09:2021 : 08:04:2021: 08:02:2021: SRFI 2 Aug SK PLN RELEASED, PLN PROSES REGISTER 07.29.2021 : Pondasi BTS Done, ME OG, PSB PLN NY Released 07.26.21 : 07.22.21 : 07:19:21 SPK REACTIVE, CME PREPARATION 03.05.21 : SPK return by XL
512 |  | JAW-JT-PWD-0024 | 30689790031 | 1441672004 | IBS GEDONG | ACTIVE - BLITZKRIEG | TB | E°51.53.35'E | S°59.30.55'S | 50 | 65/140/225/340 | 2021 |  | Desa Tegalsumur Dusun Gedong RT.001 RW.006 Kec. Brati, Kab. Grobogan Prov. Jawa Tengah | EID | JAW-JT-PWD-0024 | SENTRAL GENTENG TEGALSUMUR | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Grobogan | 6616739 | 2021-07-12 |  | 59 | 31 - 60 days | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-12 | W33-2021 | Aug-2021 | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-11 | W33-2021 | Aug-2021 | MW |  |  | 525530256376 | 7.7 |  | 2021-07-13 |  |  | 2021-09-09 | W37-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:08:2021: 09:06:2021: PLAN CONNECT 10 SEPT 08:01:2021: 08:30:2021:08:25:2021:08:22:2021: 08:18:2021: REGISTER RELEASED, BPUJL PAID, PROSES CONNECT PLN PLAN CONNECT REPLAN 6 SEPT, WAITING JADWAL PLN 08:16:2021: 08:10:2021 : 08:09:2021 : 08:04:2021: 08:02:2021: SRFI 2 Aug SK PLN RELEASED, PLN PROSES REGISTER 07.29.2021 : Pondasi BTS Done, ME OG, PSB PLN NY Released 07.26.21 : 07.22.21 : 07:19:21 SPK REACTIVE, CME PREPARATION 03.05.21 : SPK return by XL
502 |  | SUM-SS-KAG-1238 | 30689800031 | 0717782001 | IBS PADAMARAN TIMUR | ACTIVE - BLITZKRIEG | TB | E°4.42.34'E | S°33.48.93'S | 60 | 20/110/220 | 2021 | BLITZKRIEG 2021 [NEW] | RT. 001 RW. 004, Desa Sumber Hidup, Kecamatan Padamaran Timur, Kabupaten Ogan Komering Ilir, Provinsi Sumatera Selatan | HTI | SUM-SS-KAG-1238 | SUMBER_HIDUP | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ilir | 6616738 | 2021-07-12 |  | 31 | 31 - 60 days | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-12 | W33-2021 | Aug-2021 | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-11 | W33-2021 | Aug-2021 | MW |  |  | 149300173782 | 6.6 |  | 2021-07-13 |  |  | 2021-08-12 | W33-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:12:2021: RFI 08:10:21:08:09:21: 08:04:21: Power Connection Proses 08:02:21 : 07:29:21: SRFI, SK RELEASED 2 AUG, 07:26:21: Pondasi RBS dan BTS OG, SK PLN NY Released 07.22.21: 07:19:21 SPK REACTIVE, CME PREPARATION 03.05.21 : SPK return by XL
475 |  | JAW-JI-JBG-4163 | 30681600031 | 1649462001 | IBS SUKODADI | ACTIVE - BLITZKRIEG | TB | E°12.47.69'E | S°22.5.36'S | 50 | 90/180/260 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun Klubuk Timur RT. 002 RW. 006, Desa Sukodadi, Kecamatan Kabuh, Kabupaten Jombang, Provinsi Jawa Timur | HTI | JAW-JI-JBG-4163 | KABUH_SUKODADI | COLO | TBG | East | JATIM | Jawa Timur | Kab. Jombang | 6616738 | 2021-03-18 |  | 60 | 31 - 60 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 514550982308 | 6.6 Kva |  | 2021-05-21 |  |  | 2021-05-17 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.10.2021 Power Connection Process 05.06.2021 RBS/BTS FOUNDATION OG 05.03.2021 CME PREPARATION
498 |  | JAW-JB-SBR-4114 | 30681580031 | 1268502003 | IBS KLAYAN | ACTIVE - BLITZKRIEG | TB | E°32.34.48'E | S°40.31.26'S | 30 | 0/120/240 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Sunan Gunung Jati Blok Astana RT. 01 RW. 01 Desa Astana, Kecamatan Gunungjati, Kabupaten Cirebon, Provinsi Jawa Barat | HTI | JAW-JB-SBR-4114 | GUNUNGJATI_ASTANA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Cirebon | 6616738 | 2021-03-18 |  | 91 | 91 - 120 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 533113526981 | 6.6 |  | 2021-05-06 |  |  | 2021-06-17 | W25-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.17.2021 : 06.14.2021 : Power Connection Prosess 06.10.2021 : RBS/BTS Foundation 06.07.2021 : Comecase solve 4 Jun, CME OG, RBS & BTS Foundation 06.02.2021 : 05.31.2021 :05.26.2021 : 05.23.2021 : 05.19.2021 : Comecase Issue, nego biaya kompensasi dengan tim Arcom 05.17.2021 : 05.10.2021 CME HOLD, ISSUE COMMCASE, MASIH PROSES NEGOSIASI DENGA WARGA PLAN SOLVE 19 MAY 05.05.2021 CME PREPARATION, COMMCASE ISSUE, PROSES NEGOSIASI DENGAN WARGA 05.03.2021 CME PREPARATION
477 |  | JAW-JI-GSK-4327 | 30681550031 | 1649402001 | IBS PANCENG | ACTIVE - BLITZKRIEG | TB | E°26.18.91'E | S°55.8.29'S | 50 | 20/90/170 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Raya Deandles Panceng RT. 001 RW. 001, Kelurahan Prupuh, Kecamatan Panceng, Kabupaten Gresik, Provinsi Jawa Timur | HTI | JAW-JI-GSK-4327 | PANCENG_PANTENAN | COLO | TBG | East | JATIM | Jawa Timur | Kab. Gresik | 6616738 | 2021-03-18 |  | 60 | 31 - 60 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 511211859728 | 6.6 Kva |  | 2021-05-06 |  |  | 2021-05-17 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.11.2021 RFI 05.10.2021 Power Connection Process 05.06.2021 RBS/BTS FOUNDATION OG 05.03.2021 CME PREPARATION
478 |  | BAL-BA-SGR-1499 | 30681560031 | 1718612003 | IBS MUSI | ACTIVE - BLITZKRIEG | TB | E°44.24.72'E | S°10.10.45'S | 50 | 30/120/300 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Musi, Kelurahan Musi, Kecamatan Gerokgak, Kabupaten Buleleng, Provinsi Bali | HTI | BAL-BA-SGR-1499 | GEROKGAK_PENYABANGAN | COLO | TBG | East | BALINUSRA | Bali | Kab. Buleleng | 6616738 | 2021-03-18 |  | 54 | 31 - 60 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 553400347596 | 6.6 Kva |  | 2021-05-06 |  |  | 2021-05-11 | W20-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.11.2021 RFI 05.10.2021 SRFI Power Connection Process 05.06.2021 RBS/BTS FOUNDATION OG 05.03.2021 CME PREPARATION
485 |  | SUL-SN-PKJ-1436 | 30681980031 | 2815892010 | IBS IBS_PUNDATA BAJI | ACTIVE - BLITZKRIEG | TB | E°29.33.72'E | S°46.24.71'S | 50 | 0/90/170 | 2021 | BLITZKRIEG 2021 [NEW] | Maccini Baji RT001 RW 004 Kel Pundata Baji Kec Labakkang Kab Pangkep | HTI | SUL-SN-PKJ-1436 | LABAKKANG_PUNDATABAJI | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Pangkajene Kepulauan | 6616795 | 2021-03-18 |  | 73 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 320400169070 | 6.6 |  | 2021-05-06 |  |  | 2021-05-30 | W23-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.26.2021 : 05.23.2021 : Power Connection Process, Plan RFI end of May 05.19.2021 : 05.17.2021 : BTS Foundation Done ME & Grounding OG, Waiting instruksi bayar BP oleh PLN 05.10.2021 : Pondasi RBS OG, Material on site Plan 15 May 05.06.2021 : 05.03.2021 CME PREPARATION
487 |  | SUL-SN-BAR-1424 | 30681590031 | 2815062001 | IBS MANGKOSO | ACTIVE - BLITZKRIEG | TB | E°37.49.8'E | S°15.49.28'S | 50 | 40/140/280 | 2021 | BLITZKRIEG 2021 [NEW] | Lingkungan Polewali, Kelurahan Kiru Kiru, Kecamatan Soppeng Riaja, Kabupaten Barru, Provinsi Sulawesi Selatan | HTI | SUL-SN-BAR-1424 | SOPPENG_RIAJA | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Barru | 6616738 | 2021-03-18 |  | 67 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 325200404764 | 6.6 |  | 2021-05-06 |  |  | 2021-05-24 | W22-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.26.2021 : RFI 05.19.2021 : 05.17.2021 : 05.10.2021 : Pondasi RBS OG, Material on site Plan 15 May 05.06.2021 : 05.03.2021 CME PREPARATION
483 |  | SUL-SN-SNJ-1465 | 30681610031 | 2815192001 | IBS SAOTENGNGA | ACTIVE - BLITZKRIEG | TB | E°7.34.07'E | S°10.31.04'S | 50 | 50/200/270 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun Kaleleng, Desa Saotengnga, Kecamatan Sinjai Tengah, Kabupaten Sinjai, Provinsi Sulawesi Selatan | HTI | SUL-SN-SNJ-1465 | SINJAI_TENGAH_SAOTENGNGA | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Sinjai | 6616829 | 2021-03-18 |  | 65 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 327600444269 | 6.6 |  | 2021-05-06 |  |  | 2021-05-22 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.23.2021 : RFI 05.19.2021 : Power Connection Process, BP Paid, FU connection PLN 05.17.2021 : BTS Foundation Done ME & Grounding OG 05.10.2021 : Pondasi RBS OG, Material on site Plan 15 May 05.06.2021 : 05.03.2021 CME PREPARATION
515 |  | JAW-JT-SKH-1900 | 30681470031 | 1440662003 | IBS CEMANI | ACTIVE - BLITZKRIEG | TB | E°47.59.21'E | S°34.19.09'S | 30 | 40/170/280 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Sidomukti1, Desa Banaran RT.07 RW.0 Kec. Grogol, Kab. Sukoharjo Prov. Jawa Tengah | NOKIA | JAW-JT-SKH-1900 | CEMANI SUKOHARJO | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Sukoharjo | 6616739 | 2021-03-18 |  | 343 | > 150 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-09-30 | W40-2021 | Sep-2021 | 2022-02-25 | W09-2022 | Feb-2022 | MW | 2021-11-01 |  | 520512082411 | 7.7 |  | 2021-04-30 |  |  | 2022-02-24 | W09-2022 |  |  | CME | 38.RFI | 21.RFI | LMS CHANGED TO NOKIA | 24:02:22: RFIN 23:02:22-16:02:22: PREPARE CONTINUE CME PLAN START 20 FEB 13:02:22-02:02:22: COMMCASE LL TERKAIT DESIGN TOWER 30:01:22-19:01:22: PERKUATAN DONE, KAMUFLASE OG, BLOCKING LL, OG MEDIASI DGN LL 16:01:22-09:01:22: PERKUATAN OG (PEMASANGAN RANGKA KAMUFLASE, NAMUN STOPED BY LL), PLAN CLEAR PERKUATAN 15 JAN 22 05:01:22-26:12:21: PERKUATAN OG, PLAN CLEAR PERKUATAN 15 JAN 22 (PERKUATAN & MINITOWER RANGKA KAMUFLASE) 19:12:21-15:12:21: PENJADWALAN PERKUATAN 20 DEC, PLAN RFI 28 DEC 12:12:21: PONDASI BTS DONE, PAGAR OG, PARALEL LANGSIR MATERIAL PERKUATAN 13 DEC 08:12:21-05:12:21: PONDASI BTS OG 01:12:21-28:11:21: COR PLAT, PLAN RFI 8 DEC 24:11:21: ERECTION STACKING, PLAN RFI W1 DEC 21:11:21: PONDASI STACKING COR OG, PLAN RFI (ISSUE SOLVED) 30 NOV 17:11:21: PARALEL STACKING & PERKUATAN OG 14:11:21: PROCESS HILTI PONDASI STACKING 10:11:21-20:10:21: REVIEW SPH BASEFRAME BY TIM PROCURMENT, PLAN START W2 NOV 17:10:21-06:10:21: PROSES PERKUATAN GEDUNG, DIKAWAL DENGAN TIM AFO DAN ARCOM 04:10:21-22:09:21: NEGOSIASI ULANG DEGAN PIHAK LL DONE, DARI PIHAK LL MEMINTA UNTUK STACKING MENGGUNAKAN BESI, PROSES DESIGN SEDANG DIAJUKAN KE KONSULTAN 19:09:21: 15:09:21: DARI PIHAK LL INGIN MEMBATALKAN EXPAND LAHAN, PROSES NEGOSIASI DENGAN LL DARI TIM ARCOM DI TANGGAL 17 SEP 13:09:21: 09:08:2021: PIHAK PONPES MEMINTA PERUBAHAN DESIGN CAMUFLAGE MINARET, SEDANG DI RUNDINGKAN DENGAN PENGURUS PONPES LAINNYA 09:06:2021: 08:01:2021: HAMMER TEST DONE, TERDAPAT BAGIAN STRUKTUR KOLOM DIBAWAH STANDAR, MASIH MENUNGGU PEROSES DESIGN DARI KONSULTAN UNTUK DISAMOAIKAN KE LL, PLAN DESIGN DONE W2 SEPT 08:30:2021:08:25:2021: 08:16:2021: 08:16:2021 : PERMINTAAN HAMMER TEST MENYELURUH DIBANGUNAN MESJID DARI PONPES, DAN PENYESUAIAN PERKUATAN 3 LANTAI 08:10:21 : 08:04:21: Comecase Proses Re Negosiasi dengan LL, Plan Close Comecase 20 Aug, Re Plan RFI W1 Sep 07.29 2021 : 07.26.2021 : Design Released, Prepare CME dengan proses Stacking Plan 15 Aug 07.22.2021 : Revisi Gambar design ke konsultan karena design tidak match antara analys dan detail plan done revisi 22 Jul 07:19:2021: 07:15:2021 : Design and analis by konsultan Plan done 19 Jul, proses terhambat karena LL masih terkena covid 19 sehingga konsultan kesulitan untuk mengunjungi site 07:12:2021: Proses Join Survey konsultan, Plan Design done, 14 Jul 07.05.2021 : Propose area done, desain detail ny karena tim konsultan tidak bisa mengunjungi site dikarenakan LL dan keluarganya terkena Covid 19 07.01.2021 : Design Release, proses kordinasi dengan ARCOM untuk memulai pekerjaan, Plan start 6 Jul Revisi Plan RFI 20 Jul (need perkuatan dan posisi odc akurat terhadap perkuatan), after perkuatan harus menemui LO untuk kordinasi plan pengerjaannya agar tidak muncul case di lokasi tersebut 06.28.2021 : Proses penempatan baseframe, Desain og 06.24.2021 : Proses Re Desain Stacking by Team Asset, plan design done W1 JUL 06.21.2021 : 06.17.2021 : Prepare CME, need revisi design 25 jun 06.14.2021 : 06.07.2021 : 06.02.2021 : 05.26.2021 : 05.23.2021 : 05.23.2021 : 05.19.2021 : 05.17.2021 : 05.10.21 : 05.06.2021 : CME Hold karena Issue Access Block by LO 05.03.2021 CME PREPARATION
482 |  | JAW-JB-BDG-4086 | 30681640031 | 1270752004 | IBS IBS_PHASE 4C_1243_WJA | ACTIVE - BLITZKRIEG | TB | E°34.31.12'E | S°54.32.08'S | 30 | 0/120/240 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Maleber Utara No.105, Kelurahan Garuda, Kecamatan Andir, Kota Bandung, Provinsi Jawa Barat | HTI | JAW-JB-BDG-4086 | ANDIR_GARUDA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kota Bandung | 6616738 | 2021-03-18 |  | 62 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 535556192713 | 6.6 |  | 2021-04-28 |  |  | 2021-05-19 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.19.2021 : RFI 05.17.2021 : BPUJL Paid, Plan Connect 27 May 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG PLAN MATERIAL ON SITE 11 MAY 05.03.2021 CME PREPARATION
476 |  | SUM-SS-TLU-1001 | 30681630031 | 0717742001 | IBS PENDOPO | ACTIVE - BLITZKRIEG | TB | E°50.38.54'E | S°17.40.92'S | 50 | 40/115/330 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Golf Permai Dusun I, Desa Talang Ubi Selatan, Kecamatan Talang Ubi, Kabupaten Penukal Abab Lematang Ilir, Provinsi Sumatera Selatan | HTI | SUM-SS-TLU-1001 | HANDAYANI_MULYA | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Penukal Abab Lematan | 6617038 | 2021-03-18 |  | 55 | 31 - 60 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 147900579083 | 6.6 |  | 2021-04-23 |  |  | 2021-05-12 | W20-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.10.2021 Power Connection Process 05.06.2021 RBS/BTS FOUNDATION OG 05.03.2021 CME PREPARATION
484 |  | SUL-SN-BLK-1534 | 30681620031 | 2815592010 | IBS IBS_PHASE 4C_2592_SSL | ACTIVE - BLITZKRIEG | TB | E°8.42.78'E | S°29.4.62'S | 50 | 60/140/340 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun Bonto Ulu RT. 001 RW. 001, Kelurahan Dampang, Kecamatan Gantarang, Kabupaten Bulukumba, Provinsi Sulawesi Selatan | HTI | SUL-SN-BLK-1534 | GANTARANG_DAMPANG | COLO | TBG | East | SULAWESI | Sulawesi Selatan | Kab. Bulukumba | 6616829 | 2021-03-18 |  | 65 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 327100643379 | 6.6 |  | 2021-04-23 |  |  | 2021-05-22 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.23.2021 : RFI 05.19.2021 : Power Connection Process, BP Paid, FU connection PLN 05.17.2021 : BTS Foundation Done ME & Grounding OG 05.10.2021 : Pondasi RBS OG, Material on site Plan 15 May 05.06.2021 : 05.03.2021 CME PREPARATION
479 |  | JAW-JB-NPH-4096 | 30681570031 | 1271052010 | IBS IBS_PHASE 4C_1252_WJA | ACTIVE - BLITZKRIEG | TB | E°29.52.98'E | S°55.4.73'S | 30 | 0/120/240 | 2021 | BLITZKRIEG 2021 [NEW] | Kp Resmi Galih rt 1 rw 1 Desa Batujajar Timur | HTI | JAW-JB-NPH-4096 | BATUJAJAR_RESMI_GALIH | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung Barat | 6616738 | 2021-03-18 |  | 60 | 31 - 60 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 535852155825 | 6.6 Kva |  | 2021-04-20 |  |  | 2021-05-17 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.17.2021 RFI 05.10.2021 MECHANICAL AND ELECTRICAL PROCESS PLAN SRFI 10 MAY 05.06.2021 RBS/BTS FOUNDATION OG 05.03.2021 CME PREPARATION
214 |  | KAL-KI-BPP-0757 | 30599930031 | 2314771003 | SEPINGGAN BARU | ACTIVE | TB | 116°54.29.89'E | 1°13.53.32'S | 40 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl.Sepinggan Baru Kel.Sepinggan Baru Kec. Balikpapan Selatan Kota Balikpapan | HTI | KAL-KI-BPP-0757 | SEPINGGAN BARU | B2S | TBG | JABO | KALIMANTAN | Kalimantan Timur | Kota Balikpapan | 6616173 | 2020-09-03 |  | 176 | > 150 days | 2021-01-31 | W06-2021 | Jan-2021 | 2021-01-31 | W06-2021 | Jan-2021 | 2020-12-25 | W52-2020 | Dec-2020 | 2021-02-15 | W08-2021 | Feb-2021 | MW | 2021-01-15 |  | 232002366637 | 6.6 |  | 2021-03-12 |  |  | 2021-02-26 | W09-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.02.21 : RFI power by Multiguna 08.02.21 : PLN connection 01.02.21 : erection OG, prepare PLN connection 18.01.21 : pouring OG 14.01.21 : galian done, pembesian on going, plan pouring start 17 Jan 04.01.21: Rekom Camat Done 31 Dec 20, Proses submit dokumen ke Diskominfo plan 05 Jan 2021 28.12.20 : IW ongoing 21.12.20 : kand F failed, submit kandidat G -> RF TX OK, IW ongoing 17.12.20 : TNP OK, IW ongoing 14.12.20 : kand F gagal IW, propose kandidat baru -> kand G RF OK, under TNP review 10.12.20 : kandidat F RF OK, under TNP review 03.12.20 : kandidat sesuai arahan dekat sutet dengan jarak 170m, mobilisasi sulit karena tidak ada akses jalan (dekat jurang). proses joint survey dengan PT. Her untuk kandidat F jarak dari NOM 480m 30.11.20 : rehunting kandidat F 19.11.20 : arahan rehunting berada di lahan terjal dan dekat sutet, proses survey kondisi aktual terkait possibility pembangunan di area tsb 12.11.20 : kand E NOK by RND XL, proses rehunting (need arahan sesuai JR submitted) 09.11.20 : 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : submit justfication report kand E, under RNP review 22.10.20 : kand D failed, submit kandidat E under RNP review (isu penolakan warga, paralel penyusunan JR) 19.10.20 : kand C failed, proses IW ongoing kand D (RF dan TX OK) 15.10.20 : kand C RF TX OK, proses negosiasi BAN 12.10.20 : kand B gagal IW, submit kandidat C proses review RNP 08.10.20 : under review TNP kand B 05.10.20 : kand A fail, submit kand B RF OK 40m, under TNP review 01.10.20 : negosiasi BAN di kand A, paralel rehunting kandidat baru 28.09.20 : IW on going, paralel proses negosiasi BAN/BAK, plan rabu joint survey untuk renego dg LL 21.09.20 : kand A RF 40m, MW 40m/0.6, IW ongoing 14.09.20 : hunting, sekitar NOM lahan developer HER 2 dan tidak mau di sewakan krn akan dibangun
5 |  | SUM-SU-LBP-2171 | 30595710031 | 0223841003 | LAHAN/TUBUH AIR | ACTIVE | TB | 98.7357 | 3.575153 | 30 | 50/210/300 | 2020 | JEDI 2020 [NEW] | Jl. Jermal VII sudut Gg. Murni Kel. Denai, Kecamatan Medan Denai | HTI | SUM-SU-LBP-2171 | LAHAN/TUBUH AIR | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KAB. DELI SERDANG | 6614816 | 2020-07-01 |  | 284 | > 150 days | 2020-11-28 | W48-2020 | Nov-2020 | 2021-03-10 | W11-2021 | Mar-2021 | 2021-04-18 | W17-2021 | Apr-2021 | 2021-04-18 | W17-2021 | Apr-2021 | FO | [5 empty] | 2021-03-03 |  |  | 2021-04-11 | W16-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.04.21 : RFIN sent 08.04.21 : OG PLN Connection 15.03.21 : SRFI 08.03.21 : 04.03.21 : erection OG 01.03.21 : pouring OG 25.02.21 : rebaring OG 18.02.21 : 11.02.21 : 08.02.21 : galian OG 04.02.21 : plan hari ini start galian 28.01.21 : bouwplank, plan CME start 2Feb 18.01.21 : plan IMB release 25 Jan 11.01.21 : 04.01.21 : permit ongoing, start CME setelah IMB release, plan release W3 Jan 28.12.20 : rekom done, waiting resi IMB release -> plan 29 Dec 21.12.20 : 17.12.20 : Soiltest done, REKOM OG, plan CME start 28 Dec 14.12.20 : REKOM & SOIL TEST OG, PLAN CME START 28 DES 07.12.20 : 03.12.20 : target RFC W3 Dec, paralel pengurusan KKOP dan soiltest 30.11.20 : 19.11.20 : proses realisasi IW, issue KKOP kota medan (estimasi 1 s.d 2 minggu) 16.11.20 : 12.11.20 : IW clear, proses realisasi IW, target RFC W5 Nov 09.11.20 : plan IW clear 10 Nov 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : 22.10.20 : IW minus 12KK, estimasi IW clear 26 Oct 19.10.20 : kand G TNP OK, IW ongoing target clear 26 Oct 15.10.20 : kand F failed, submit kandidat baru -> cand G RNP OK 26.5m, proses review TNP paralel IW 12.10.20 : TNP OK, MW 30m/0.3, negosiasi harga paralel IW ongoing 08.10.20 : IW on going, paralel review TNP kandidat F 05.10.20 : TNP review, paralel IW on going 4kk/30kk 02.10.20 : submit kand F, RND OK 30m, wait TNP review 01.10.20 : kand E RF OK 30m, MW 30m/0.3, IW ongoing 25.09.20 : submit kand E 3.57619 98°44'4.24''E, SST 32, review RND 21.09.20 : kand D IW failed karena jarak 100m terdapat tower yang comcase, proses rehunting 17.09.20 : kand D TNP OK -> MW 30m/0.3, IW ongoing 14.09.20 : 10.09.20 : kand D RF OK 30m, proses review TNP 07.09.20 : 03.09.20 : propose RENOM RNP NOK, need arahan planning XL 31.08.20 : 27.08.20 : 24.08.20 : propose re-NOM karena radius 500m dari nom adalah area comcase existing tower (ada existing tower yg hardcomcase dkt NOM) 17.08.20 : hard kandidat issue penolakan warga dan banyak lahan sengketa ex PTPN, masih proses rehunting 13.08.20 : 10.08.20 : kand C & E NOK, kand A & B IW failed , rehunting kand E, plan submit kand 14 Aug 06.08.20 : kandidat C NOK karena dekat dengan existing, proses rehunting dgn arahan 98.735309, 3.573964 03.08.20 : rehunting C 03.08.20 : 29 Jul submit kandidat B namun NOK by RNP karena dekat dgn existing, proses rehunting kand C 30.07.20 : rehunting, plan submit kandidat baru senin 2 Agustus 27.07.20 : kandidat A NOK, RND request ketinggian min 30m, namun terkendala penolakan warga (hanya provide MT 25m) 20.07.20 : submit kandidat A propose MT 25, menunggu review RNP 16.07.20 : plan besok submit kandidat 13.07.20 : hunting 09.07.20 : on going survey, kandidat di pemukiman padat 01.07.20 : SPK release
474 |  | SUM-SU-MDN-2182 | 30595720031 | 0223851003 | MEDAN TENGGARADENAI | ACTIVE | TB | 98.7266 | 3.557791 | 40 | 70/140/270 | 2020 | JEDI 2020 [NEW] | Jl. Keramat Indah Lingkungan IX, Kelurahan Medan Tenggara, Kecamatan Medan Denai, Kota Medan | HTI | SUM-SU-MDN-2182 | MEDAN TENGGARADENAI | B2S | TBG | WEST | SUMBAGUT | Kota Medan | KOTA MEDAN | 6614816 | 2020-07-01 |  | 449 | > 150 days | 2020-11-28 | W48-2020 | Nov-2020 | 2021-03-06 | W10-2021 | Mar-2021 | 2021-09-25 | W39-2021 | Sep-2021 | 2021-09-25 | W39-2021 | Sep-2021 | FO |  |  | 120031093960 | 6.6 |  | 2021-03-03 |  |  | 2021-09-23 | W39-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22:09:21: 19:09:21:15:09:21: 13:09:21: 09:08:2021: POWER CONNECTION PROSES 09:06:2021: POURING OG 09:01:2021: REBARING OG, PLAN COR 5 SEPT 08:30:2021: 08:18:21: 08:09:21: 08.09.21 : Proses Review BOQ dan SPH, Rectivasi site Plan W1 Sep 08:04:21: 07.29.21: design perkuatan akibat stolen material released, proses review untuk pelaksanaan perkuatan, paralel proses penunjukan mitra 07:.26:21: 07:19:21 : Tower Issue, Proses Pembangunan ulang tower, perlu dilakukan analisa terkait pembongkaran angkur, dan pembongkaran Cor Plan Done 31 Jul Plan start CME W1 Aug 29.04.21 : RFIN Sent, MMP FO NY RFS 19.04.21 : SPK FO issue, PLN connection hold 08.03.21 : SRFIN sent 04.03.21 : finishing pagar, SRFI 01.03.21 : erection done, ME OG 25.02.21 : erection OG 22.02.21 : pouring done, prepare start erection 18.02.21 : pembesian OG 11.02.21 : 08.02.21 : galian OG 04.02.21 : plan hari ini start galian 28.01.21 : bouwplank, plan CME start 2 Feb 18.01.21 : plan IMB release 25 Jan 11.01.21 : 04.01.21 : permit ongoing, start CME setelah IMB release, plan release W3 Jan 28.12.20 : rekom done, waiting resi IMB release -> plan 29 Dec 21.12.20 : 17.12.20 : soiltest done, REKOM OG, plan CME start 28 Dec 14.12.20 : REKOM & SOIL TEST OG, PLAN CME START 28 DES 07.12.20 : 03.12.20 : target RFC W3,p paralel pengurusan KKOP dan soiltest 30.11.20 : soitest ongoing, paralel proses rekom KKOP estimasi 1 s.d 2 minggu 19.11.20 : issue KKOP kota medan 16.11.20 : 12.11.20 : IW clear, proses realisasi IW, target RFC 29 Nov 09.11.20 : IW clear, proses realisasi IW ongoing 05.11.20 : submit kandidat baru, kandidat D RF TX OK, IW ongoing 02.11.20 : 29.10.20 : 26.10.20 : propose re-validasi penurunan ketinggian tower menjadi 36m untuk menghindari penolakan 1KK (warga tidak berada di lokasi) 22.10.20 : IW minus 1KK dari 20KK lokasi di kandidat B bergeser sekitar 30m, target clear 24 Oct 19.10.20 : kembali ke kand A, IW ongoing target clear 26 Oct 15.10.20 : 12.10.20 : 08.10.20 : proses rehunting 05.10.20 : IW on going 7kk/15kk 01.10.20 : kand C gagal IW proses rehunting 24.09.20 : iw ongoing 21.09.20 : TNP OK MW 40m/0.6, IW ongoing, kurang 12 kk lagi 17.09.20 : 16.09.20 : kand C RND OK RF 40m, proses review TNP 14.09.20 : proses pengurusan legalitas lahan (kand B), paralel submit kandidat baru (cand C) under review TNP 10.09.20 : proses pengurusan legalitas lahan 03.09.20 : iw clear proses nego dengan warga terkait kompensasi 31.08.20 : proses eskalasi sitac 27.08.20 : iw clear isu kompensasi clear 24.08.20 : masih IW on going kurang 11 kk, plan IW clear 28 Aug 17.08.20 : TNP OK, IW ongoing target IW Clear 20 Aug 20 13.08.20 : TNP review, paralel IW on going 23 kk, yg sdh done 9 kk target 20 agustus 20 10.08.20 : TNP review, IW on going 4kk/23kk, plan IW clear 15 Aug 06.08.20 : submit kandidat baru (cand B) approved dgn RF 40m, proses review TNP 03.08.20 : 30.07.20 : 27.07.20 : IW on going, plan CME Start 14/8 23.07.20 : kandidat A TX OK dgn MW height 40m/0.6, proses IW on going 20.07.20 : kandidat A RNP OK dengan RF 40m, menunggu review TX 16.07.20 : Ok candidate A, tower 42 16.07.20 : 13 jul submit kandidat A koordinat 98.72653, 3.55915 propose SST 42, menunggu review RNP 13.07.20 : hunting 09.07.20 : on going survey, kandidat di pemukiman padat 01.07.20 : SPK release
206 |  | SUM-SU-PMS-2198 | 30595730031 | 0223861003 | TOBA | ACTIVE | TB | 99.0658 | 2.9475 | 35 | 20/130/250 | 2020 | JEDI 2020 [NEW] | JL. MELANTON SIREGAR NO.12 kELURAHAN TOBA, KECAMATAN SIANTAR SELATAN KOTA PEMATANGSIANTAR | HTI | SUM-SU-PMS-2198 | TOBA | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KOTA PEMATANG SIANTA | 6614816 | 2020-07-01 |  | 257 | > 150 days | 2020-11-28 | W48-2020 | Nov-2020 | 2021-02-16 | W08-2021 | Feb-2021 | 2020-11-27 | W48-2020 | Nov-2020 | 2021-03-10 | W11-2021 | Mar-2021 | MW | 2021-02-04 |  | 121011206385 | 6.6 |  | 2021-03-02 |  |  | 2021-03-15 | W12-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.03.21 : erection OG 08.03.21 : HILTI baseframe OG 04.03.21 : material on site, CME start, plan HILTI start hari ini 01.03.21 : material baseframe on delivery 25.02. 21 : survey PLN done, material tower ETA 27 Feb 22.02.21 : estimasi MOS 24 Feb 11.02.21 : 04.02.21 : 28.01.21 : pabrikasi material baseframe OG, plan MOS 15 Feb 18.01.21 : plan IMB release 25 Jan 11.01.21 : 04.01.21 : permit ongoing, start CME setelah IMB release, plan release W3 Jan 28.12.20 : rekom done, waiting resi IMB release -> plan 29 Dec 21.12.20 : 17.12.20 : soiltest done, REKOM L/C OG, plan CME start 28 Dec 14.12.20 : REKOM & SOIL TEST OG, PLAN CME START 28 DES 07.12.20 : 03.12.20 : realisasi IW, paralel rekom ongoing, target RFC W2 Dec 30.11.20 : IW clear cand E, proses realisasi IW 23.11.20 : kembali ke kandidat E, target RCF W1 Dec realisasi19.11.20 : IW Clear, proses rekom lurah/camat 16.11.20 : plan IW clear 18 Nov 12.11.20 : IW ongoing 09.11.20 : kand J RF OK, under TNP review 05.11.20 : kand I NOK, submit kand J under RNP review 02.11.20 : kand H NOK, submit kand I under RNP review 29.10.20 : 26.10.20 : kand G NOK, rehunting 22.10.20 : gagal IW kand E, submit kandidat baru -> kand G under RNP review 19.10.20 : kembali ke kand E, IW ongoing 33KK , plan IW clear 25 Oct 15.10.20 : kand E failed, proses rehunting (kand F NOK karena dekat exisiting dan jauh dari NOM) 12.10.20 : TNP OK, IW ongoing di radius 32m 08.10.20 : re-validasi penaikan tinggi tower RT 12m + MT 20m -> RF OK 30.5m, proses review TNP paralel IW ongoing 05.10.20 : submit kand E, RF NOK karena antena terlalu rendah, RND propose RT 12 + MT20m 01.10.20 : 24.09.20 : kand D gagal IW, proses rehunting 21.09.20 : TNP OK MW 35m/0.3, IW ongoing 17.09.20 : 14.09.20 : kembali ke kandidat D, proses review TNP, 10.09.20 : proses rehunting karena kandidat awal terdapat isu sengketa waris 07.09.20 : kandidat D RF OK 31.5m, proses review TNP 03.09.20 : ada pergeseran kandidat karena issue penolakan LL, cand D under RNP review 31.08.20 : 27.08.20 : eskalasi sitac approved, proses pembayaran ijin warga 27.08.20 : eskalasi sitac approved, proses pembayaran ijin warga 24.08.20 : proses eskalasi biaya sitac, paralel rekom on going 17.08.20 : 13.08.20 : IW Clear, proses rekom on going, plan rekom done 18 Aug 10.08.20 :kandidat C TX OK, MW height 35m/0.3, IW on going kurang 1 kk, plan IW clear 11 Aug 06.08.20 : 03.08.20 : kandidat C OK RF 34.5m, under TNP review 30.07.20 : kandidat B IW failed, submit kandidat baru (cand C koordinat 99.06763, 2.947627) under RNP review 27.07.20 : kandidat B RF 34.5m OK, menunggu review TNP, paralel IW on going 20.07.20 : kandidat A NOK karena dekat dengan existing dan terlalu jauh dari NOM, proses rehunting 16.07.20 : Not ok candidate A, too far from nom, near existing, rehunting kand B 13.07.20 : 13 jul submit kandidat A koordinat 99.06718, 2.94504 propose SST 36 menunggu review RNP 13.07.20 : hunting 09.07.20 : on going survey, kandidat di pemukiman padat 01.07.20 : SPK release
48 |  | SUM-SU-KPI-2220 | 30600040031 | 0223981003 | TORGAMBA AEKBATU | ACTIVE | TB | 100°10.40.75'E | 1°42.15.93'N | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | DUSUN TERATAI, DESA AEK RASO, KECAMATAN TORGAMBA, KABUPATEN LABUHANBATU SELATAN, PROVINSI SUMATERA UTARA | HTI | SUM-SU-KPI-2220 | TORGAMBA AEKBATU | B2S | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Labuhanbatu Selatan | 6616173 | 2020-09-03 |  | 181 | > 150 days | 2021-01-31 | W06-2021 | Jan-2021 | 2021-02-22 | W09-2021 | Feb-2021 | 2020-12-25 | W52-2020 | Dec-2020 | 2021-02-26 | W09-2021 | Feb-2021 | MW | 2021-01-29 |  | 125100671476 | 6.6 |  | 2021-02-02 |  |  | 2021-03-03 | W10-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.03.21 : RFI power by PLN Multiguna 25.02.21 : erection done, ME OG, plan PLN connect 28 Feb 22.02.21 : 18.02.21 : erection ongoing 11.02.21 : pouring done 08.02.21 : rebaring OG, plan pouring 10 Feb 04.02.21 : galian done, pembersihan area galian OG 28.01.21 : CME preparation, plan start 2 Feb 18.01.21 :14.01.21 : soiltest done, proses pengurusan surat kuasa SIOP estimasi penyelesaian 20 Jan (Ijin start CME by PTPN III confirm OK), plan CME start 27 Jan 11.01.21 : soiltest ongoing, plan CME start 27 Jan 04.01.21 : PKS signed 28.12.20 : proses PKS dan kelengkapan dok legalitas, plan cme start 5 Jan 21.12.20 : 17.12.20 : proses pembuatan PKS dengan PTPN III 07.12.20 : 30.11.20 : survey KJPP (Kantor Jasa Penilaian Publik) done, proses jawaban resmi PTPN estimasi release W1 Dec 19.11.20 : 16.11.20 : 12.11.20 : 09.11.20 : proses PKS dengan PTPN 3 05.11.20 : 02.11.20 : 29.10.20 :26.10.20 : 22.10.20 : 19.10.20 : menunggu surat jawaban dari PTPN 3 terkait hasil joint survey 15.10.20 : proses joint survey dengan mitra di lahan PTPN 3 12.10.20 : proses disposisi di kepala bagian PTPN 3 08.10.20 : 05.10.20 : menunggu feedback dari PTPN 3 01.10.20 : 24.09.20 : proses BAN/BAK dengan pihak PTPN 21.09.20 : TNP OK 50m/0.6, IW ongoing, lokasi berada di LAHAN PTPN III dan sudah di ajukan proposa kerjasama dengan PTPN III 17.09.20 : kand A RF OK 50m, proses review TNP 14.09.20 : hunting, lokasi di PTPN III
41 |  | SUM-AC-LSM-0715 | 30598970031 | 0110021003 | ULEE BLANG MANE | ACTIVE | TB | 97°10.28.27'null | 5°6.59.08'N | 50 | 80/240/350 | 2020 | JEDI 2020 [NEW] | Dusun Rambong Desa Langa Kec. Syamtalira Bayu Kab. Aceh Utara Prov. Aceh | HTI | SUM-AC-LSM-0715 | ULEE BLANG MANE | B2S | TBG | WEST | SUMBAGUT | Aceh | Kota Lhokseumawe | 6616150 | 2020-08-31 |  | 151 | > 150 days | 2021-01-28 | W05-2021 | Jan-2021 | 2020-11-30 | W49-2020 | Nov-2020 | 2020-11-30 | W49-2020 | Nov-2020 | 2021-01-31 | W06-2021 | Jan-2021 | MW | 2020-10-27 |  | 112220336986 | 6.6 |  | 2021-02-02 |  |  | 2021-01-29 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : OG penarikan kabel (penambahan 10 tiang) 14.01.21 : ME OG 11.01.21 : erection ongoing section 2 04.01.21 : pouring done, plan erection start 5 Jan 28.12.20 : galian ongoing 21.12.20 : pembersihan galian site pasca banjir 17.12.20 : 14.12.20 : material on site, plan pouring 20 Dec 10.12.20 : per 3 desember galian done, namun site berada di lokasi terdampak banjir (aceh utara) 07.12.20 : 03.12.20 : start galian 30.11.20 : plan start CME W1 Dec 26.11.20 : finalisasi design tower (APD ongoing) 23.11.20 : geser kandidat (cand F), soiltest done 9.11.20 : 16.11.20 : excavation hold karena issue site berada di lahan perbatasan Kab. Aceh Utara dan Lhoksuwemawe (material on site), proses penyelesaian dengan Muspika 09.11.20 : site clearing ongoing 05.11.20 : 02.11.20 : RFC, PREPARE CME, plan CME start 5 Nov, Plan RFI 29 Nov 29.10.20 : prepare start CME 26.10.20 : menunggu resi release 22.10.20 : rekon done, dok teknis done, menunggu resi release Jumat 23 Oct 19.10.20 : dok teknis done, target resi release 22 Oct 12.10.20 : plan rekom done selasa 13 Oct 08.10.20 : camat sedang tugas luar kota dan plan kembali besok, plan rekom camat done jumat 9 oct 05.10.20 : estimasi rekom camat done tgl 6 Oct 01.10.20 : rekom camat on going 24.09.20 : rekom lurah done, proses rekom camat 21.09.20 : IW clear, proses eskalasi sitac, prepare rekom 17.09.20 : kand D TNP OK -> MW 48m/1.2, proses IW ongoing 14.09.20 : kand D RF OK 50m, proses review TNP 10.09.20 : proses rehunting reloc NOM dengan arahan titik 97.174516,5.116412 07.09.20 : rehunting, NOM berada di area kawasan hutan
126 |  | SUM-RI-DUM-1109 | 30581950031 | 0413851003 | BUKIT TIMAH_DUMAI | ACTIVE | TB | 101.4316 | 1.6129 | 50 | 10/140/230 | 2020 | JEDI 2020 [NEW] | Jalan Soekarno Hatta Kelurahan Bukit Timah Kecamatan Dumai selatan Kotamadya Dumai, Provinsi Riau. | HTI | SUM-RI-DUM-1109 | BUKIT TIMAH_DUMAI | B2S | TBG | WEST | SUMBAGTENG | Kep. Bangka Belitung | KOTA DUMAI | 6614493 | 2020-02-17 |  | 350 | > 150 days | 2020-07-16 | W29-2020 | Jul-2020 | 2021-01-20 | W04-2021 | Jan-2021 | 2020-07-31 | W31-2020 | Jul-2020 | 2021-01-31 | W06-2021 | Jan-2021 | MW | 2020-12-18 |  | 182501119476 | 6.6 |  | 2021-02-02 |  |  | 2021-02-01 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.01.21 : CME done, ME OG, proses PLN connection 11.01.21 : erection ongoing 04.01.21 : bekisting ongoing 28.12.20 : borepile ongoing, plan pengecoran 30 Dec 21.12.20 : 17.12.20 : galian ongoing 14.12.20 : REKOM DAN SOIL TEST OG, PLAN REKOM DAN SOIL TEST DONE 16 DES 10.12.20 : kepastian start cme, weekly minggu depan (note Pak Budi) 07.12.20 : issue PLH PEMDA, target RFC 14 Dec 30.11.20 : proses ttd PKS dan MoU dengan PEMDA, plan CME start W1 Desember setelah release perijinan dari PEMDA 23.11.20 : REKOM KKOP OTBAN done, proses rekom RKT (ketinggian tower) 19.11.20 : proses release jawaban hasil survey KKOP, plan minggu ini 16.11.20 : 12.1.20 : jadwal survey KKOP jumat 13 Nov, setelah survey dilanjutkan rekom L/C, plan RFC W5 Nov 09.11.20 : rekom KKOP ongoing, plan start CME 15 Nov, target RFI 18 Dec 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : target RFC W2 Nov 22.10.20 : proses pengurusan kembali KKOP 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : plan besok target revisi laporan konsultan selesai 01.10.20 : proses revisi laporan kelengkapan KKOP dari konsultan, Plan proses rekom clear minggu ini, start CME menunggu surat ijin release dari corporate 28.09.20 : 21.09.20 : Proses rekom KKOP, plan start CME 29 sept, plan RFI 30 oct 14.09.20 : 10.09.20 : 07.09.20 : proses KKOP, percepatan dengan combat 32 not approved by RND XL 03.09.20 : proses KKOP, paralel nego percepatan dengan combat 32 02.09.20 : Propose COMBAT NOT OK by RND XL (P'Dody) karena blm ada kebutuhan untuk percepatan area tersebut 31.08.20 : 27.08.20 : 25.08.20 : waiting approval pengajuan percepatan RFI dengan COMBAT32m (tinggi sama dengan propose tower Permanent 32m yang sudah approved). Propose percepatan karena proses rekom KKOP yang lama dan Combat dapat di implementasikan paralel dengan rekom KKOP ini. 24.08.20 : proses rekom KKOP 17.08.20 : 13.08.20 : 10.08.20 : menunggu jadwal KKOP/tim otban turun 06.08.20 : 30.07.20 : IW clear, proses pengurusan KKOP 27.07.20 : Bukit timah Proses KKOP, setelah itu lanjut PKS. IW Clear 09.07.20 : proses pembicaraan dengan Kadishub 02.07.20 : 29.06.20 : 25.06.20 : proses BAN 22.06.20 : 18.06.20 : plan minggu depan rekom clear, negosiasi harga lahan, plan 22/06/2020 ke DISHUB untuk fu harga lahan 15.06.20 : 11.06.20 : 08.06.20 : 04.06.20 : 28.05.20 : 25.05.20 : BAN OG_LAHAN DISHUB DEKAT BANDARA 14.05.20 : BAK, IW Clear 23.04.20 : 16.04.20 : IW on going, Proses Persetujuan resmi dr Pemda 09.04.20 : IW on going 02.04.20 : proses BAN, Lokasi site lahan Pemda, Proses Persetujuan resmi dr Pemda 25.03.20 : RND review 19.03.20 : validasi RND 12.03.20 : 05.03.20 : Lahan Konsesi PT Chevron Pacific Indonesia, Masa kontrak Karya berakhir di 2021, sekaligus Masuk masuk dalam Kawasan Hutan KSA. propose kand dilahan Bandara Pinang Kampai belum disetujui XL(Satu2 nya opsi kandidat) 26.02.20 : ReNOM RND XL, titik merupakan kantor Dinas Perhubungan dan juga bisa digunakan sebagai terminal barang oleh pihak Pertamina/Cevron --> belum memungkinkan di akuisisi. 26.02.20 : submit kand terminal di RT+pole 6m dengan tinggi total 14 m not OK by RND 20.02.20 : hunting, on going survey 17.02.20 : SPK released
91 |  | JAW-JI-BLT-1917 | 30597200031 | 1644511003 | KEPANJEN_KIDUL_SENTUL | ACTIVE | TB | 112.1952 | -8.0684 | 50 | 110/185/285 | 2020 | JEDI 2020 [NEW] | JL. CUT NYAK DIEN RT.002 RW.008, KELURAHAN SENTUL, KEC. KEPANJENKIDUL, KOTA BLITAR, PROP. JAWA TIMUR | HTI | JAW-JI-BLT-1917 | KEPANJEN_KIDUL_SENTUL | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA BLITAR | 6614889 | 2020-07-14 |  | 245 | > 150 days | 2020-12-11 | W50-2020 | Dec-2020 | 2021-02-20 | W08-2021 | Feb-2021 | 2020-12-11 | W50-2020 | Dec-2020 | TBD | TBD | TBD | FO | 2021-02-15 |  | 514021937046 | 6.6 |  | 2021-01-26 |  |  | 2021-03-16 | W12-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.03.21 : SRFI 22.02.21 : plan erection start 23-Feb 18.02.21 : curring time 15.02.21 : pouring OG 11.02.21 : 08.01.21 : plan cor borpile 8 Jan 04.02.21 : borepile OG 01.02.21 : CME stop penolakan warga, penyelesaian melalui soswar plan hari ini 28.01.21 : galian OG 21.01.21 : 18.01.21 : CME belum bisa start, IMB NY release -> plan W5 Jan 11.01.21 : 07.01.21 : estimasi ijin prinsip release 15 Jan, plan CME start 16 Jan 28.12.20 : menunggu ijin prinsip(IMB) release 21.12.20 : 17.12.20 : 14.12.20 : issue CME hold, warga meminta kompensasi. CME bisa start kembali setelah Ijin prinsip (produk perijinan) release estimasi minggu ini 18 Dec 07.12.20 : 03.12.20 : start CME 26.11.20 : soiltest done, plan RFC 27 Nov 19.11.20 : 12.11.20 : realisasi IW done, rekom done, proses soiltest plan RFC W5 Nov 09.11.20 : 05.11.20 : TNP OK, proses realisasi IW 02.11.20 : kand C RF OK 50m, under TNP review, status IW CLEAR 29.10.20 : submit kand C propose tower kamuflase 52m (isu perwali kota blitar), under RNP review 26.10.20 : 22.10.20 : 19.10.20 : IW failed berdasarkan hasil soswar pada 17 Oct, proses rehunting paralel dilakukan IW, plan dapat kandiddat 20 Oct 15.10.20 : proses negosiasi nilai sewa lahan di kandidat baru, prepare submit kandidat setelah mediasi dengan warga 12.10.20 : 08.10.20 : prepare submit kandidat, plan submit 8 Oct 05.10.20 : 01.10.20 : kandidat B gagal IW, proses rehunting 28.09.20 : IW on going 24.09.20 : review TNP OK kand B H: 50 0.6 233.53 per 23 sep 23.09.20 : submit review TNP kand B Tower 52m, kand A rejected, proses IW ongoing di kandidat baru (cand B RF OK 50m) paralel review TNP 22.09.20 : submit kand B 52m review RND Ok candidate B, tower 52 (112.19139 -8.070778 / 112° 11' 29.00" E 08° 04' 14.80" S) RF 50m 10/140/210 21.09.20 : pengajuan validasi, paralel IW on going 17.09.20 : proses soiltest, plan rekom PUPR done 18 Sept 14.09.20 : 10.09.20 : IW CLEAR, masih menunggu feedback rekom PUPR 07.09.20 : proses soswar mediasi dengan warga yang belum bertanda tangan (minus 3KK dari total 9KK) target IW CLEAR 9 Sep, paralel follow up rekom PUPR 03.09.20 : 31.08.20 : menunggu rekom PUPR, paralel masih IW ongoing 27.08.20 : kand A RF 50m OK, TNP OK -> MW 50m/0.6, IW ongoing 24.08.20 : submit kandidat A (112.190669, -8.070917) outSAR issue perwali Kota Blitar, under RNP review 17.08.20 : 13.08.20 : need eskalasi RND terkait isu perwali (jarak antar menara), PU belum setuju dengan NOM, koordinasi permintaan arahan dari PU minggu ini. 10.08.20 : 10.08.20 : 06.08.20 : need approval perluasaan SAR karena titik NOM berada di kawasan padat penduduk (tidak mendapat izin PUPR Blitar) dan dekat tower existing dgn jarak 55m dr NOM (ISSUE PERWALI BLITAR - Jarak antar Menara memiliki kecukupan jarak udara minimal 500m dari menara eksisting ) 03.08.20 : 30.07.20 : 27.07.20 : 23.07.20 : hunting 20.07.20 : hunting
625 |  | JAW-JB-BDG-4000 | 30619550031 | 120082109 | PURIASIHMD-NUANSAINDAHMG | ACTIVE - RELOCATION | TRB | 107°40'12.2''E | 6°56'40.7''S | 25 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Mercuri Timur No.1, Kel. Manjahlega Kec. Rancasari, Kota Bandung Prov. Jawa Barat | HTI | JAW-JB-BDG-4000 | MERKURIMARGAHAYURAYA RELOCATION | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Bandung | 6616405 | 2020-11-19 |  | 223 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | 2021-03-06 | W10-2021 | Mar-2021 | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-19 | W51-2020 | Dec-2020 | MW |  |  | 535679800473 | 6.6 |  | 2021-01-20 |  |  | 2021-06-30 | W27-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.28.21 : 06.24.21 : Power Connection Proses, proses perluasan jaringan kabel, karena kabel existing kecil 06.21.21 : PSB PLN Released 06.19.21 : PSB PLN on Request 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 01.03.21 : SRFI 25.02.21 : pondasi OG 18.02.21 : CME start 11.02.21 : estimasi MOS 20 Jan 08.01.21 : fabrikasi baseframe OG 28.01.21 : perubahan APD propose pondasi stacking karena terdapat isu lahan 20.01.21 : STO announced (email Pak Yanse) 19.11.21 : SPK colo release
472 |  | JAW-JB-SOR-3662 | 30619400031 | 1261511023 | CILAMPENI KATAPANG | ACTIVE | TB | 107°32.58.88'null | 6°59.31.7'S | 30 | 90/210/300 | 2020 | JEDI 2020 [NEW] | Desa Cilampeni Kp. Baraja No.04 RT.02 RW.20, Kec. Katapang, Kab. Bandung Prov. Jawa Barat | HTI | JAW-JB-SOR-3662 | CILAMPENI_KATAPANG | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6616670 | 2021-01-13 |  | 131 | 121 - 150 days | 2021-02-12 | W07-2021 | Feb-2021 | 2021-03-06 | W10-2021 | Mar-2021 | 2021-05-10 | W20-2021 | May-2021 | 2021-05-08 | W19-2021 | May-2021 | FO (Change to MW as temp solution) |  |  | 535322143774 | 6.6 |  | 2021-01-15 |  |  | 2021-05-24 | W22-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.23.21 : RFI 05.19.21 : Power Connection Proses No register Released, Proses pembayaran BPUJL 05.17.21 : Power Connection Proses No register Released, Plan Connect 27 May 05.03.21 : Power Connection Proses 26.04.21 : FO change to MW, waiting PSB release 19.04.21 : SPK FO issue, PLN connection hold 01.03.21 : SRFI 22.02.21 : CME start, pondasi OG 01.02.21 : CME hold, site disegel satpol PP 28.01.21 : pondasi BTS OG 21.01.21 : CME preparation 14.01.21 : ESR preparation 13.01.21 : SPK colo release
471 |  | SUM-RI-BLS-1113 | 30618760031 | 040523109 | BUKIT KRIKIL | ACTIVE | TB | 101°29.40.2'null | 1°26.44.16'N | 60 | 60/210/310 | 2020 | JEDI 2020 [NEW] | Jl. Sukamaju RT 04 RW 01 desa Bukit krikil Kec Bukit Batu Kab Bengkalis | HTI | SUM-RI-BLS-1113 | BUKITKERIKIL | COLO | TBG | WEST | SUMBAGTENG | Riau | KAB. BENGKALIS | 6616609 | 2021-01-05 |  | 28 | < 30 days | 2021-02-04 | W06-2021 | Feb-2021 | 2021-01-27 | W05-2021 | Jan-2021 | 2021-02-03 | W06-2021 | Feb-2021 | 2021-01-31 | W06-2021 | Jan-2021 | MW | 2021-01-15 |  | 182501116740 | 6.6 |  | 2021-01-13 |  |  | 2021-02-02 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.02.21 : PLN connected, proses collect doc RFIN 28.01.21 : BP Paid 21.01.21 : pondasi OG 18.01.21 : CME preparation 14.01.21 : ESR done, proses input STIP eparation 05.01.21 : SPK release
469 |  | JAW-JB-IDM-3816 | 30618730031 | 125169109 | BUGELIND-STOPATROL | ACTIVE | SKP | 108°0.31.0'E | 6°19.34.18'S | 40 | 0/185/280 | 2020 | JEDI 2020 [NEW] | Desa Bugel Blok Sukawera RT.02 RW.06, Kec. Patrol, Kab. Indramayu Prov. Jawa Barat | HTI | JAW-JB-IDM-3816 | BUGEL_PATROL_INDRAMAYU | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. INDRAMAYU | 6616594 | 2020-12-30 |  | 28 | < 30 days | 2021-01-29 | W05-2021 | Jan-2021 | 2021-01-28 | W05-2021 | Jan-2021 | 2021-01-28 | W05-2021 | Jan-2021 | 2021-01-28 | W05-2021 | Jan-2021 | MW | 2021-01-15 |  | 534020106142 | 6.6 |  | 2021-01-07 |  |  | 2021-01-27 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.01.21 : RFIN sent 18.01.21 : pondasi BTS OG 14.01.21 : cme preparation 07.01.21 : ESR preparation 30.12.20 : SPK release
470 |  | JAW-JI-BYW-4121 | 30618740031 | 162123109 | TEGALARUM | ACTIVE | SKP | 114°9.14.47'E | 8°20.52.91'S | 40 | 140/275/350 | 2020 | JEDI 2020 [NEW] | Dusun Jenisari RT. 01 RW.01 Desa Genteng Kulon Kec Genteng Kab Banyuwangi-Jawa Timur | HTI | JAW-JI-BYW-4121 | GENTENG_GENTENG_KULON | COLO | TBG | EAST | JATIM | Jawa Timur | Kab. Banyuwangi | 6616594 | 2020-12-30 |  | 72 | 61 - 90 days | 2021-01-29 | W05-2021 | Jan-2021 | 2021-01-28 | W05-2021 | Jan-2021 | 2021-01-29 | W05-2021 | Jan-2021 | TBD | TBD | TBD | FO | 2021-02-15 |  | 516731204445 | 6.6 |  | 2021-01-07 |  |  | 2021-03-12 | W11-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : pondasi done, ME OG 18.01.21 : pondasi OG 14.01.21 : cme preparation 07.01.21 : ESR preparation 30.12.20 : SPK release
171 |  | JAW-JI-BLT-1912 | 30597190031 | 1644501003 | SUKOREJO_TLUMPU | ACTIVE | TB | 112.1503 | -8.1122 | 40 | 0/150/240 | 2020 | JEDI 2020 [NEW] | Jl. Durian RT04 RW04 Kelurahan Tlumpu Kecamatan Sukorejo Kota Blitar Jawa Timur | HTI | JAW-JI-BLT-1912 | SUKOREJO_TLUMPU | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA BLITAR | 6614889 | 2020-07-14 |  | 225 | > 150 days | 2020-12-11 | W50-2020 | Dec-2020 | 2021-01-31 | W06-2021 | Jan-2021 | 2020-12-10 | W50-2020 | Dec-2020 | 2021-02-26 | W09-2021 | Feb-2021 | MW | 2021-01-08 |  | MULTIGUNA |  |  | 2021-01-07 |  |  | 2021-02-24 | W09-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.02.21 : RFIN sent 15.02.21 : Perluasan jaringan material PLN NY ready 04.01.21 : PLN connection process 28.01.21 : SRFI, waiting PSB PLN (request 8 Jan), potensi perluasan jaringan 21.01.21 : pouring OG 18.01.21 : 14.01.21 : borepile OG 07.01.21 : galian ongoing 04.01.21 : 28.12.20 : 21.12.20 : 14.12.10 : realisasi IW dan soiltest ongoing, rekom lurah camat done 10.12.20 : realisasi IW ongoing 07.12.20 : 03.12.20 : 30.11.20 : kandidat F approved by RND XL, proses penyelesaian sosialisasi dan IW 26.11.20 : propose return (weekly meeting 26 Nov) 26.11.20 : prepare submit kandidat, proses finalisasi soswar kandidat baru (IW clear) 19.11.20 : rehunting kandidat F 12.11.20 : rehunting 09.11.20 : 05.11.20 : kand E NOK, rehunting dengan arahan 112.147988°, -8.108774 29.10.20 : 26.10.20 : IW ongoing di kandidat E, proses door to door karena isu penolakan warga 22.10.20 : 19.10.20 : berdasarkan soswar pada 16 Oct -> IW failed, proses rehunting kandidat 15.10.20 : koordinat arahan XL dan sekitarnya ada isu penolakan warga, sedang proses soswar di kandidat E jarak 200m ke arah selatan dari arahan XL , prepare submit kandidat setelah IW secure 12.10.20 : 08.10.20 : prepare submit kandidat, plan 8 Oct 05.10.20 : 01.10.20 : kand D reject karena dekat existing XL, proses rehunting 28.09.20 : 25.09.20 : submit review RND kand D 112.14265 -8.11535 SST 42m 24.09.20 : sudah terdapat 2 existing site dekat titik arahan RND sehingga terkendala Perwali Blitar mengenai minmal jarak antar Menara 500m 23.09.20 : arahan RND rehunting ke tikor berikut : 112.148664, -8.112365. 22.09.20 : submit kand C SST 42m review RND Not ok candidate C, too far from nom, near existing 21.09.20 : 17.09.20 : kand B NOK by RND, near existing XL (validasi 14 sep), proses rehunting kand C, plan submit besok 14.09.20 : kandidat B under RNP review 10.09.20 : 07.09.20 : kandidat A IW fail, proses rehunting 03.09.20 : 31.08.20 : rekom PUPR approved, IW ongoing 27.08.20 : kand A RF 40m OK, TNP OK -> MW 40m/0.6, IW ongoing 24.08.20 : submit kandidat A (112.147139, -8.118639) outSAR karena issue Perwali Kota Blitar, under RNP review 17.08.20 : 13.08.20 : need eskalasi RND terkait isu perwali (jarak antar menara), PU belum setuju dengan NOM, koordinasi permintaan arahan dari PU minggu ini. 13.08.20 : 10.08.20 : 06.08.20 : need approval perluasaan SAR karena titik NOM berada di kawasan padat penduduk (tidak mendapat izin PUPR Blitar) dan dekat tower existing dgn jarak 400m dr NOM (ISSUE PERWALI BLITAR - Jarak antar Menara memiliki kecukupan jarak udara minimal 500m dari menara eksisting ) 03.08.20 : 30.07.20 : 27.07.20 : 23.07.20 : hunting
219 |  | JAW-JI-KNR-4253 | 30606160031 | 164105107 | SATREYAN KANIGORO | ACTIVE | SKP | 112°13.20.03' | 8°8.48.08'S | 41 | 0/60/300 | 2020 | JEDI 2020 [NEW] | Lingkungan Sawahan RT 01 RW 05 Kel, Satreyan Kec. Kanigoro Kab. Blitar Prov Jawa TimurDESA SATREYAN KEC KANIGORO KAB BLITARPROV JAWA TIMUR | HTI | JAW-JI-KNR-4253 | KANIGORO_SATREYAN | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. BLITAR | 6616350 | 2020-10-20 |  | 143 | 121 - 150 days | 2021-03-19 | W12-2021 | Mar-2021 | 2020-12-10 | W50-2020 | Dec-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-03-29 | W14-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2020-10-27 |  | 514021907297 | 33 |  | 2020-12-28 |  |  | 2021-03-12 | W11-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.03.21 : MoM 04/3, OG perluasan jaringan, revise RFI plan 29/3 18.02.21 : PLN connection daya 33 kVA, setelah pemakaian 1 bulan downgrade 6.6/13.2 kVA, HO PLN bisa dilakukan setelah downgrade 6.6 atau 13.2 kVA 26.01.21 : survey done, proses eskalasi approval daya PLN 33kVA, Revise RFI Plan W2 Mar 21.01.21 : PSB released, PLN connection OG 26.11.20 : SRFIN announce 23.11.20 : 19.11.20 : aktual SRFI 16.11.20 : 12.11.20 : ME ongoing 09.11.20 : 05.11.20 : curring time, proses permanenisasi 02.11.20 : 29.10.20 : prepare STO & CME 20.10.20 : SPK release
624 |  | JAW-JI-SBY-4373 | 30618710031 | T000512 | MARHOREJO | ACTIVE - RELOCATION | SKP | 112°44.37.07'E | 7°19.6.82'S | 34 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Raya Margorejo Indah Kav.A 131 - 132, Kel.Margorejo Kec.Wonocolo, Kota Surabaya Prov.Jawa Timur | HTI | JAW-JI-SBY-4373 | JEMURWONOSARI_RELOCATION | COLO | TBG | EAST | JATIM | Jawa Timur | Jawa Timur | 6616574 | 2020-12-17 |  | 190 | > 150 days | 2021-01-16 | W03-2021 | Jan-2021 | 2021-02-15 | W08-2021 | Feb-2021 | 2021-01-16 | W03-2021 | Jan-2021 | 2021-01-16 | W03-2021 | Jan-2021 | MW |  |  | 511434384609 | 6.6 |  | 2020-12-23 |  |  | 2021-06-25 | W26-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.24.21 : Power Connection Prosess 06.21.21 : PSB PLN Released 06.19.21 : PSB PLN on Request 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 01.02.21 : open akses, pondasi OG 21.01.21 : plan CME start W1 Feb 18.01.21 : 14.01.21 : proses perijinan (lahan corporate) untuk start CME 11.01.21 : CME preparation 04.01.21 : 21.12.20 : ESR preparation 17.12.20 : SPK release
120 |  | SUM-RI-DUM-1106 | 30597230031 | 0413871003 | BUKIT DATUK | ACTIVE | TB | 101.4193 | 1.653956 | 40 | 90/180/270 | 2020 | JEDI 2020 [NEW] | Jalan Kaswari Perumahan Pertamina Blok D RT 25 Kelurahan Bukit Datuk Kecamatan Dumai Selatan Kota Dumai Provinsi Riau | HTI | SUM-RI-DUM-1106 | BUKIT DATUK | B2S | TBG | WEST | SUMBAGTENG | Kep. Bangka Belitung | KOTA DUMAI | 6614889 | 2020-07-14 |  | 270 | > 150 days | 2020-12-11 | W50-2020 | Dec-2020 | 2021-02-19 | W08-2021 | Feb-2021 | 2020-12-10 | W50-2020 | Dec-2020 | 2021-03-15 | W12-2021 | Mar-2021 | MW | 2020-10-27 |  | 716094 |  |  | 2020-12-23 |  |  | 2021-04-10 | W15-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.04.21 : RFIN sent 29.03.21 : tower done, ME OG, RFI Plan 31 Mar 25.03.21 : erection OG, section 7 23.03.21 : erection OG section 6, paralel pemasangan kabel PLN underground (power by Pertamina) 15.03.21 : start erection 08.03.21 : backfilling OG, plan erection start 10 Mar 04.03.21 : pouring OG, plan erection start 8 Mar 01.03.21 : plan pouring start 3 Mar 25.02.21 : pembesian OG, kontur lahan cenderung turun menimbulkan genangan air akibat curah hujan tinggi. plan pouring start 3 Mar 22.02.21 : 18.02.21 : wellpile done, prepare lantai kerja (kondisi tanah membutuhkan cerucuk) 11.02.21 : OG pengecoran borpile titik ke-2 dan 3 04.01.21 : borepile OG 25%, kendala curah hujan tinggi, galian kedalaman 1.5-2m terdapat tumpukan batang poton harus dipotong manual 01.02.21 : 28.01.21 : galian OG, plan pengecoran 10 Feb 21.01.21 : re-design pondasi karena di kedalaman 1m terdapat tumpukan batang pohon 14.01.21 : 11.01.21 : borepile ongoing, plan pouring 22 Jan 07.01.21 : 04.01.21 : borepile ongoing, plan pouring 9 Jan 28.12.20 : 21.12.20 : 17.12.20 : galian ongoing 14.12.20 : 07.12.20 : soiltest dan APD ongoing target done 16 Dec, proses sign PKS PERTAMINA target penyelesaian 12 Dec 30.11.20 : proses ijin ke PERTAMINA untuk pekerjaan soiltest 19.11.20 : 16.11.20 : 12.11.20 : proses rekom lurah camat, plan RFC W5 Nov 09.11.20 : IW clear, plan rekom done 14 Nov 05.11.20 : 02.11.20 : PSB released, proses pengajuan sambungan listrik ke PERTAMINA dengan melampirkan SK PSB PLN 29.10.20 : tarif PLN approved by XL, proses request PSB PLN 26.10.20 : need konfirmasi XL terkait tarif listrik yang diajukan oleh PERTAMINA 22.10.20 : PLN tdk bisa supply Listrik, sdh kita FU ke pertamina untuk Konfirmasi bisa ga mereka supply Listrik 19.10.20 :15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : 01.10.20 : sudah mendapat ijin dari pertamina, Hari ini akli merapat ke PLN membawa surat Persetujuan dr Pertamina, menunggu konfirmasi dari PLN terkait pemasangan 28.09.20 : Update dari pertamina plan minggu ini merelease surat resmi kesediaan/ijin penggunaan existing jaringan kabel bawah tanahnya. untuk selanjutnya meminta konfirmasi resmi dari PLN. 21.09.20 : 17.09.20 : menunggu feedback persetujuan PLN, Survey PLN dgn pertamina blm bisa dilakukan, karena perumahan pertamina Lock down karena ada yg positive covid. Komunikasi by verbal dengan pihak PLN Terkait rencana penggunakan Jaringan existing pertamina dari PLN minta surat resmi dari pertamina, ini blm di dapatkan dan baru dapat jawaban via email dr pertamina 10.09.20 : jawaban dari pertamina bersedia untuk mensuply power ke site Bukit Datuk, proses pengajuan kerjasama koneksi Power dengan Pertamina 07.09.20 : proses koordinasi dengan PLN dan Pertamina mengenai opsi connect langsung ke PLN dan teknis pembangunan/penggunaan jaringan di dalam komplek Pertamina 03.09.20 : 31.08.20 : 27.08.20 : 24.08.20 : 17.08.20 : kandidat A RF TX OK, IW CLEAR, menunggu approval XL terkait issue CDC 13.08.20 : 12.08.20 : hasil joint survey dgn pertamina submit kandidat A (101.41786, 1.65304) under RNP review, isu site Need CDC, karena Power by PERTAMINA daya terbatas (kandidat berada di Komplek Pertamina Dumai). Sama seperti existing site SUM-RI-DUM-0752 - Bukit Datuk Kota Dumai 10.08.20 : plan joint survey besok 12 Aug, target rekom KKOP18 Aug 06.08.20 : Sudah ada feedback dari Pertamina, plan joint survey dg Pertamina Selasa 11 Aug 20 05.08.20 : menunggu feedback dari Pertamina terkait perijinan sewa lahan 03.08.20 : 30.07.20 : 27.07.20 : 24.07.20 : NOM BERADA DI LAHAN PERTAMINA, PROSES PENGAJUAN SURAT KERJA SAMA KE PERTAMINA
152 |  | SUM-AC-KTN-0378 | 30595030031 | 0109971003 | PASIR NUNGGUL | ACTIVE | TB | 97.8336 | 3.4216 | 50 | 170/250/340 | 2020 | JEDI 2020 [NEW] | Desa Pasir Nunggul, Kecamatan Lawe Alas, Kabupaten Aceh Tenggara, Prov. Aceh. | HTI | SUM-AC-KTN-0378 | PASIR NUNGGUL | B2S | TBG | WEST | SUMBAGUT | Aceh | ACEH TENGGARA | 6614769 | 2020-06-23 |  | 147 | 121 - 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-25 | W48-2020 | Nov-2020 | MW | 2020-10-01 |  | 113340197819 | 6.6 |  | 2020-12-11 |  |  | 2020-11-17 | W47-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.11.20 : RFIN sent 16.11.20 : plan connect PLN W3 Nov 12.11.20 : 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : penambahan tiang dan tarikan jaringan PLN 22.10.20 : 19.10.20 : proses penyambungan PLN 15.10.20 : 12.10.20 : 08.10.20 : start erection 05.10.20 : curingtime 01.10.20 : 28.09.20 : rebaring done, prepare for pouring 21.09.20 : IMB done, excavation 14.09.20 : 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : proses perijinan 24.08.20 : 13.08.20 : rekom done , collecting legal doc 10.08.20 : rekom lurah done, on going rekom camat 06.08.20 : 03.08.20 : 30.07.20 : IW DONE, proses rekom L/C 27.07.20 : IW on going 23.07.20 : 16.07.20 : kandidat D TNP reviewed MW height 48m diameter 0.6m, IW ongoing 13.07.20 : 11.07.20 : TNP review kand D 09.07.20 : submit 6 Juli kandidat A,B, dan C propose SST 52 (waiting RNP review) 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20
623 |  | NUS-NB-MTR-5387 | 30615470031 | 180381126 | PAGESANGAN_2 | ACTIVE - RELOCATION | TB | 116°7.10.85'E | 8°35.37.68'S | 17 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Sriwijaya No.136, Cilinaya, Cakranegara, Kota Mataram Prov. Nusa Tenggara Barat | HTI | NUS-NB-MTR-5387 | SRIWIJ_RELOCATION | COLO | TBG | EAST | BALINUSRA | Nusa Tenggara Barat | Kota Mataram | 6616471 | 2020-11-19 |  | 224 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-19 | W51-2020 | Dec-2020 | MW |  |  | 441103373705 | 6.6 |  | 2020-12-04 |  |  | 2021-07-01 | W27-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.01.21 : 06.28.21 : 06.21.21 : Power Connection Proses 06.21.21 : PSB PLN Released 06.17.21 : PSB PLN on Request 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 04.01.21 : PLN connection hold, menunggu konfirmasi dari XL 28.12.20 : SRFIN sent 21.12.20 : 17.12.20 : fabrikasi material, plan MOS 22 Dec 14.12.20 : CME preparation 07.12.20 : ESR done, proses input stip 03.12.20 : RNP OK, under TNP review 19.11.20 : SPK colo release
630 |  | SUM-SS-KAG-1227 | 30615170031 | 071234109 | DESA SUNGAI MENANG | ACTIVE - RELOCATION | TB | 105°20.20.98'E | 3°43.33.1'S | 66 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Dusun I Desa Sungai Menang Kec Sungai Menang Kab OKI Prov Sumsel | HTI | SUM-SS-KAG-1227 | SUNGAITEPUK_RELOCATION | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | Kab. Ogan Komering Ilir | 6616434 | 2020-11-16 |  | 43 | 31 - 60 days | 2020-12-16 | W51-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2021-01-04 | W02-2021 | Jan-2021 | 2021-01-04 | W02-2021 | Jan-2021 | MW | 2020-12-08 |  | 149300120096 | 6.6 |  | 2020-12-03 |  |  | 2020-12-29 | W53-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.12.20 : ME installation, BPUJL paid, proses connect PLN 21.12.20 : 17.12.20 : 14.12.20 : plan CME start 19 Dec 10.12.20 : cme preparation 07.12.20 : ESR done, proses input stip 03.12.20 : TNP approved, under power-civil review 23.11.20 : ESR submitted, RNP approved, under TNP review 16.11.20 : SPK colo release
622 |  | BAL-BA-DPR-1508 | 30615700031 | T000002 | RRI PALAWA | ACTIVE - RELOCATION | SKP | 115°13.40.01'E | 8°39.19.69'S | 37 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Plawa No. 95 Br. Pagan Kelod Desa Sumerta Kauh Denpasar Timur Denpasar | HTI | BAL-BA-DPR-1508 | KECUBUNG_DENPASAR_RELOCATION | COLO | TBG | East | BALINUSRA | Bali | Kota Denpasar | 6616398 | 2020-11-19 |  | 217 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-19 | W51-2020 | Dec-2020 | MW | 2021-02-15 |  | 5510011211112 | 6.6 Kva |  | 2020-12-02 |  |  | 2021-06-24 | W26-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.24.21 : RFI 06.21.21 : 06.17.21 : Konfirmasi Lanjut untuk proses connect PLN, PSB PLN on Request 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 04.01.21 : PLN connection hold, menunggu konfirmasi dari XL 28.12.20 : SRFIN sent 21.12.20 : aktual SRFI, menunggu konfirmasi dari XL untuk connect PLN (PSB already requested) 17.12.20 : pondasi BTS & cable tray ongoing, material ME grounding on delivery -> plan MOS 21 Dec 14.12.20 : CME preparation 07.12.20 : ESR done, proses input stip 30.11.20 : RNP OK, under TNP review 19.11.20 : SPK colo release
633 |  | SUM-JA-SPN-0453 | 30615120031 | 060055109 | SEMUMU | ACTIVE - RELOCATION | SKP | 101°26.35.16'E | 2°2.15.97'S | 57 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Raya Air Panas, Dusun Sungai Abu RT 05, Desa. Sungai abu, Kec. Air Hangat Timur, Kab. Kerinci, Prov. Jambi | HTI | SUM-JA-SPN-0453 | DANAU_PADANG_REPEATER_TRANS_RELOCATION | COLO | TBG | West | SUMBAGSEL | Jambi | Kab. Kerinci | 6616398 | 2020-11-19 |  | 55 | 31 - 60 days | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2021-01-08 | W02-2021 | Jan-2021 | MW | 2020-12-08 |  | 144600050666 | 6.6 |  | 2020-12-02 |  |  | 2021-01-13 | W03-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.01.21 : RFIN sent 07.01.21 : SRFIN sent, PLN connection menunggu konfirmasi XL 28.12.20 : ME finishing, BPUJL paid, proses connect PLN 21.12.20 : 17.12.20 : 14.12.20 : plan CME start 19 Dec 10.12.20 : cme preparation 07.12.20 : ESR done, proses input stip 03.12.20 : TNP OK 30.11.20 : RNP OK, under TNP review 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
205 |  | SUM-AC-KTN-0379 | 30595040031 | 0109981003 | TENEMBAK LANG LANG | ACTIVE | TB | 97.821 | 3.4979 | 50 | 10/160/270 | 2020 | JEDI 2020 [NEW] | Desa Kuta Bantil Kecamatan Lawe Bulan Kabupaten Aceh Tenggara Provinsi Aceh | HTI | SUM-AC-KTN-0379 | TENEMBAK LANG LANG | B2S | TBG | WEST | SUMBAGUT | Aceh | ACEH TENGGARA | 6614769 | 2020-06-23 |  | 147 | 121 - 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-25 | W48-2020 | Nov-2020 | MW | 2020-10-01 |  | 113340197801 | 6.6 |  | 2020-12-02 |  |  | 2020-11-17 | W47-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.11.20 : RFIN sent 16.11.20 : issue management trafo, proses input ticket PLN123agar segera di followup terkait BPUJL yg sudah terbayar. Plan connect PLN W3 Nov 12.11.20 : 09.11.20 : 05.11.20 : 29.10.20 :26.10.20 : 22.10.20 : 19.10.20 : proses penyambungan PLN 15.10.20 : 12.10.20 : erection done 08.10.20 : start erection 05.10.20 : curingtime 01.10.20 : 28.09.20 : rebaring done, prepare for pouring 21.09.20 : IMB done, excavation 14.09.20 : 07.09.20 : 31.08.20 : proses perijinan 27.08.20 : 24.08.20 : rekom done, proses perijinan 17.08.20 : 13.08.20 : IW Clear, proses rekom on going, target rekom done 19 Aug 10.08.20 : IW on going kurang 2 kk, plan IW clear 11 Aug 06.08.20 : kembali ke kandidat A, status IW CLEAR, proses eskalasi sitac cost 03.08.20 : 30.07.20 : Kandidat A gagal IW, proses rehunting plan submit kandidat senin 3 Agustus 27.07.20 : 23.07.20 : IW Clear, proses eskalasi harga 16.07.20 : kandidat A TNP approved MW height 47m dia 0.6m, IW Clear 13.07.20 : 10.07.20 : submit TNP review 09.07.20 : submit 6 Juli kandidat A,B, dan C propose SST 52 (waiting RNP review) 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20
467 |  | SUM-SB-PAD-0783 | 30615070031 | 030428109 | PAD MC 42 / BELANTI BARAT | ACTIVE | TB | 100°21.17.42'null | 0°55.7.9'S | 30 | 30/150/270 | 2020 | JEDI 2020 [NEW] | Jl. Belanti Indah Rt 03 RW 05 Kel Lolong Belanti Kec Padang UtaraKEL. LOLONG BELATI, KEC. PADANG UTARAPADANG | HTI | SUM-SB-PAD-0783 | LOLONG BELANTI | COLO | TBG | WEST | SUMBAGTENG | Sumatera Barat | Kota Padang | 6616492 | 2020-11-20 |  | 52 | 31 - 60 days | 2020-12-20 | W52-2020 | Dec-2020 | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2021-01-15 | W03-2021 | Jan-2021 | FO (Change to MW as temp solution) | 2020-12-08 |  | 131017576509 | 6.6 |  | 2020-12-01 |  |  | 2021-01-11 | W03-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.01.21 : RFIN sent 07.01.21 : SRFI, plan hari ini connect PLN 28.12.20 : pondasi done, pabrikasi ME belting ongoing, plan SRFI 31 Dec 21.12.20 : 17.12.20 : pondasi bts done, material panel on delivery 14.12.20 : PABRIKASI & DELIVERY MATERIAL, PLAN CME START 17 DES 07.12.20 : prepare start CME 03.12.20 : ESR done, proses input stip 26.11.20 : resubmit ESR, RNP OK, under RNP review 20.11.20 : SPK colo release
641 |  | NUS-NB-PYA-5394 | 30615060031 | 180125109 | KUTA LOMBOK3 | ACTIVE - RELOCATION | TB | 116°18.37.51'E | 8°53.19.21'S | 67 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Raya Kuta Awang KM 7 Dusun Petiwong Desa Sukadana Kec. Pujut, Kab. Lombok Tengah Prov. Nusa Tenggara Barat | HTI | NUS-NB-PYA-5394 | TANJUNG_ANN_RELOCATION | COLO | TBG | EAST | BALINUSRA | Nusa Tenggara Barat | Kab. Lombok Tengah | 6616471 | 2020-11-19 |  | 41 | 31 - 60 days | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2020-12-21 | W52-2020 | Dec-2020 | 2020-12-21 | W52-2020 | Dec-2020 | MW | 2020-12-04 |  | 441405833960 | 6.6 |  | 2020-12-01 |  |  | 2020-12-30 | W53-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : aktual SRFI, menunggu konfirmasi dari XL untuk connect PLN (PSB already requested) 17.12.20 : pondasi BTS ongoing, material ME grounding on delivery -> plan MOS 22 Dec 14.12.20 : 10.12.20 : material on delivery, paralel langsir material pondasi BTS 07.12.20 : CME preparation 03.12.20 : ESR done, proses input stip 30.11.20 : RNP TNP OK, rejected by civil -> need APD 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
632 |  | JAW-JB-BDG-3985 | 30615020031 | 123028109 | KOMPUNPAD-BTNAWILIGAR | ACTIVE - RELOCATION | SKP | 107°37.42.82'E | 6°52.56.64'S | 27 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Cigadung Raya Tengah, Kel. Cigadung RT.02 RW.06, Kec. Cibeunying Kaler, Kota Bandung Prov. Jawa Barat | HTI | JAW-JB-BDG-3985 | KOMPLEK_UNPAD_CIGADUNG_RELOCATION | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kota Bandung | 6616398 | 2020-11-19 |  | 27 | < 30 days | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | MW | 2020-12-04 |  | 535596882982 | 6.6 |  | 2020-12-01 |  |  | 2020-12-16 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.12.20 : RFIN sent 14.12.20 : ME installation 07.12.20 : pondasi BTS ongoing 03.12.20 : ESR done, proses input STIP 30.11.20 : RNP OK, under TNP review 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
638 |  | JAW-JB-SNG-3994 | 30615040031 | 125577109 | CIGANGSING-RANCASUBANG | ACTIVE - RELOCATION | TB | 107°41.14.68'E | 6°43.39.29'S | 55 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Desa Cibitung, Desa Cibitung RT.04 RW.01 Kec. Ciater, Kab. Subang Prov. Jawa Barat | HTI | JAW-JB-SNG-3994 | CIBEUSI_JALAN_CAGAK_RELOCATION | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Subang | 6616401 | 2020-11-19 |  | 25 | < 30 days | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | MW | 2020-12-04 |  | 534254095303 | 6.6 |  | 2020-12-01 |  |  | 2020-12-14 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.12.20 : RFIN sent 07.12.20 : pondasi BTS ongoing 03.12.20 : ESR done, proses input STIP 30.11.20 : RNP OK, under TNP review 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
642 |  | JAW-JI-SBY-4378 | 30615030031 | 160357102 | KEDINDING TENGAH | ACTIVE - RELOCATION | MSI | 112°46.36.7'E | 7°13.44.33'S | 37 |  | 2020 | JEDI 2020 [NEW] | Jl. Kalimlor Indah Gg. Mangga, Kel.Tanahkali RT.07 RW.03 Kec.Kenjeran, Kota Surabaya Prov.Jawa Timur | HTI | JAW-JI-SBY-4378 | TANAH_KALI_RELOCATION | COLO | TBG | EAST | JATIM | Jawa Timur | Kota Surabaya | 6616404 | 2020-11-19 |  | 56 | 31 - 60 days | 2020-12-19 | W51-2020 | Dec-2020 | 2021-01-07 | W02-2021 | Jan-2021 | 2021-01-07 | W02-2021 | Jan-2021 | 2021-01-07 | W02-2021 | Jan-2021 | MW | 2020-12-08 |  | 511051054878 | 6.6 |  | 2020-11-30 |  |  | 2021-01-14 | W03-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.01.21 : SRFI 04.01.21 : 28.12.20 : CME hold, community issue 21.12.20 : 17.12.20 : CME preparation 03.12.20 : ESR done 19.11.20 : SPK colo release
631 |  | JAW-JB-SOR-3998 | 30614820031 | 121327104 | HAURPUGUR | ACTIVE - RELOCATION | SMI | 107°47.57.91'E | 6°59.20.47'S | 36 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Desa Haurpugur Kp. Bojong Gempol RT.004 RW.04 , Kec. Rancaekek, Kab. Bandung Prov. Jawa Barat | HTI | JAW-JB-SOR-3998 | RANCAEKEK_BANDUNG_RELOCATION | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Bandung | 6616431 | 2020-11-16 |  | 32 | 31 - 60 days | 2020-12-16 | W51-2020 | Dec-2020 | 2020-12-15 | W51-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | MW | 2020-12-03 |  | 535331927353 | 6.6 |  | 2020-11-27 |  |  | 2020-12-18 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 17.12.20 : pln connection process 14.12.20 : ME installation 07.12.20 : pondasi BTS ongoing 03.12.20 : CME preparation, plan cme start hari ini 30.11.20 : ESR done, proses input stip 26.11.20 : RNP, TNP approved 23.11.20 : ESR submit, under TNP review 16.11.20 : SPK colo release
217 |  | NUS-NB-GRG-4540 | 30595010031 | 1806311003 | GUNUNGSARI_JATISELA | ACTIVE | TB | 116°4.55.7'null | 8°32.49.01'S | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl. Merdeka RT 02 Dusun Montong Pace, Desa Jatisela, Kecamatan Gunungsari, Kabupaten Lombok Barat, Propinsi Nusa Tenggara Barat | HTI | NUS-NB-GRG-4540 | GUNUNGSARI_JATISELA | B2S | TBG | EAST | BALINUSRA | Nusa Tenggara Barat | Kab. Lombok Barat | 6616259 | 2020-09-21 |  | 143 | 121 - 150 days | 2021-02-18 | W08-2021 | Feb-2021 | 2020-12-15 | W51-2020 | Dec-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-08 | W07-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 441503241822 | 6.6 |  | 2020-11-19 |  |  | 2021-02-11 | W07-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.02.21 : PLN connected, prepare RFIN 21.01.21 : PSB released, PLN connection OG 14.12.20 : SRFIN sent 10.12.20 : SRFI 07.12.20 : erection done, ME installation 30.11.20 : erection ongoing 26.11.20 : prepare erection 23.11.20 : pondasi ongoing 12.09.20 : start galian 09.11.20 : 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : rekom done, 28 Oct akan dilakukan survey perijinan untuk start CME 22.10.20 : 19.10.20 : 15.10.20 : on going realisasi IW dan proses rekom, plan rekom done 19 oct. Pararel proses request GDL material tower. Estimasi w4 okt atau w1 nov start CME (material sdh on site) 12.10.20 : 08.10.20 : 05.10.20 : plan realisasi dan rekom done di W2 oct, soiltest done, proses design APD 01.10.20 : IW clear, proses eskalasi biaya sitac dan prepare proses realisasi IW 28.09.20 : IW on going 21.09.20 : SPK B2S REACTIVATION Release, Reaktivasi site dengan release new SPK B2S, use old STIP
186 |  | SUM-SU-SRH-2223 | 30595110031 | 0223801003 | SEIRAMPAH PEMATANG GANJANG | ACTIVE | TB | 99.1238 | 3.4631 | 50 | 130/240/330 | 2020 | JEDI 2020 [NEW] | DUSUN IV DESA PEMATANG GANJANG KECAMATAN SEI RAMPAH KABUPATEN SERDANG BEDAGAI | HTI | SUM-SU-SRH-2223 | SEIRAMPAH PEMATANG GANJANG | B2S | TBG | WEST | SUMBAGUT | Sumatera Utara | SERDANG BEDAGAI | 6614769 | 2020-06-23 |  | 144 | 121 - 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | MW | 2020-10-01 |  | 126160702674 | 6.6 |  | 2020-11-19 |  |  | 2020-11-14 | W46-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.11.20 : RFIN sent 12.11.20 : erection done, aktual SRFI 09.11.20 : 05.11.20 : 02.11.20 : erection ongoing 29.10.20 : 26.10.20 : 22.10.20 : 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 : rebarring 05.10.20 : 01.10.20 : cerucuk on going 21.09.20 : bouwplank, proses delivery cerucuk 1000 pcs 14.09.20 : land clearing, kondisi lahan rawa, proses delivery cerucuk 1000 pcs 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : menunggu jadwal survey dan resi IMB release, plan start CME setelah survey done 24.08.20 : 13.08.20 : proses perijinan 10.08.20 : 06.08.20 : 03.08.20 : rekom done, proses perijinan 30.07.20 : target rekom done 30 Jul 27.07.20 : proses rekom camat 23.07.20 : 16.07.20 : kandidat A TNP approved MW height 45m dia 0.6m, IW clear, proses eskalasi sitac 13.07.20 : 09.07.20 : kandidat A koordinat 99.12371, 3.46285 dengan RF 50m approved by RNP 3 Juli 2020, menunggu review TX 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20
216 |  | SUL-SN-ENR-1369 | 30601730031 | 2811141003 | BAROKOBAROKO | ACTIVE | TB | 119°48.24.09'null | 3°18.28.5'S | 50 | 10/160/280 | 2020 | JEDI 2020 [NEW] | DUSUN SITARRU, RT/RW. 000/000, DESA BAROKO, KECAMATAN BAROKO, KABUPATEN ENREKANG, PROVINSI SULAWESI SELATAN. | HTI | SUL-SN-ENR-1369 | BAROKOBAROKO | B2S | TBG | EAST | SULAWESI | Sulawesi Selatan | Kab. Enrekang | 6616252 | 2020-09-21 |  | 105 | 91 - 120 days | 2021-02-18 | W08-2021 | Feb-2021 | 2021-01-18 | W04-2021 | Jan-2021 | 2020-12-25 | W52-2020 | Dec-2020 | 2021-01-05 | W02-2021 | Jan-2021 | MW | 2020-11-12 |  | 324500289881 | 6.6 |  | 2020-11-18 |  |  | 2021-01-04 | W02-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.01.21 : RFIN sent 04.01.21 : plan hari ini announce RFI 21.12.20 : PLN permanent done, collecting doc RFIN 07.12.20 : erection done, PLN connected 03.11.20 : 30.11.20 : start erection, target erection selesai 7 Dec 26.11.20 : pouring done, persiapan erection 23.11.20 : 19.11.20 : rebaring, menunggu material angkur on site (estimasi tiba hari ini) 16.11.20 : excavation done, lantai kerja ongoing 12.09.20 : RFC, start CME 14 Nov 09.11.20 : RF OK, rekom done, APD ongoing 05.11.20 : kand C failed , submit kandidat D under RNP review 02.11.20 : 29.10.20 : 26.10.20 : IW clear, proses rekom lurah 22.10.20 : kand C RF OK 50m, status IW clear, proses review TNP 19.10.20 : kand B IW failed, submit kand C under RNP review 15.10.20 : IW ongoing 12.10.20 : kand B RF TX OK, IW ongoing 08.10.20 : submit kand B, under RNP review 05.10.20 : proses rehunting kand baru, isu high CAPEX jika menggunakan tower 72 01.10.20 : kand A RF OK 50m, dari sisi TNP terdapat issue di ketinggian 52m not loss -> TNP request tinggi tower 72m
170 |  | JAW-JI-BLT-1911 | 30597180031 | 1644491003 | SUKOREJO_TANJUNGSARI | ACTIVE | TB | 112.1396 | -8.0834 | 50 | 125/230/340 | 2020 | JEDI 2020 [NEW] | Jl. Kali Sampit RT.004 RW.005, Kel. Tanjungsari, Kec. Sukorejo, Kota Blitar , Jawa Timur | HTI | JAW-JI-BLT-1911 | SUKOREJO_TANJUNGSARI | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA BLITAR | 6614889 | 2020-07-14 |  | 245 | > 150 days | 2020-12-11 | W50-2020 | Dec-2020 | 2020-12-10 | W50-2020 | Dec-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-03-29 | W14-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 514021910138 | 6.6 |  | 2020-11-11 |  |  | 2021-03-16 | W12-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.03.21 : 08.03.21 : MoM 04/3, OG perluasan jaringan, revise RFI plan 29/3 18.02.21 : PLN connection daya 23 kVA, setelah 1 bulan di downgrade 6.6 kVA 26.01.21 : survey done, need perluasan jaringan (penambahan 2 tiang) 21.01.21 : PSB released, PLN connection OG 19.11.20 : SRFIN sent 16.12.20 : aktual SRFI 12.11.20 : ME ongoing 09.11.20 : 05.11.20 : erection ongoing 02.11.20 : pondasi ongoing 29.10.20 : 22.10.20 : bouwplank, prepare start CME 19.10.20 : rekom lurah camat done, RFC 15.10.20 : rekom dan perijinan done, proses review design kamuflase tower 52m 12.10.20 : rekom lurah done, plan rekom camat 12 Oct 08.10.20 : plan rekom camat dan rekom lurah clear hari ini 05.10.20 : menunggu terbit rekom PU, plan minggu ini 01.10.20 : 28.09.20 : plan sign Kelengkapan doc SKRK hari jumat, sekaligus IP dr PU, setelah IP release dilanjutkan proses sign lurah krn untuk Kota blitar, setingkat kelurahan dan kecamatan sign kelengkapan dokument after sign dr PU, 24.09.20 : 21.09.20 : rekom PUPR done, ongoing rekom camat 17.09.20 : plan rekom PUPR done 18 Sep 14.09.20 : 10.09.20 : IW CLEAR, masih menunggu feedback rekom PUPR 07.09.20 : 03.09.20 : 31.08.20 : IW ongoing, paralel menunggu rekom PUPR 27.08.20 : kand A RF 50m OK, TNP OK -> MW 50m/0.6, IW ongoing 24.08.20 : submit kandidat A (112.135278, -8.083089) outSAR karena issue perwali Kota Blitar, under RNP review 17.08.20 : 13.08.20 : need eskalasi RND terkait isu perwali (jarak antar menara), PU belum setuju dengan NOM, koordinasi permintaan arahan dari PU minggu ini. 13.08.20 : 10.08.20 : 06.08.20 : need approval perluasaan SAR karena titik NOM berada di kawasan padat penduduk (tidak mendapat izin PUPR Blitar) dan dekat tower existing dgn jarak 24m dr NOM (ISSUE PERWALI BLITAR - Jarak antar Menara memiliki kecukupan jarak udara minimal 500m dari menara eksisting ) 03.08.20 : 30.07.20 : 27.07.20 : 23.07.20 : hunting
192 |  | SUM-SU-PRR-2117 | 30587370031 | 0223701003 | SIALLAGAN - PINDARAYA | ACTIVE | TB | 98.8416 | 2.6661 | 40 | 150/220/320 | 2020 | JEDI 2020 [NEW] | Dusun III Desa Siallagan Pindaraya Kec. Simanindo Kab. Samosir Prov. Sumatera Utara | HTI | SUM-SU-PRR-2117 | SIALLAGAN - PINDARAYA | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KAB. SAMOSIR | 6614554 | 2020-03-13 |  | 262 | > 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-07-29 | W31-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-11-30 | W49-2020 | Nov-2020 | MW | 2020-10-27 |  | 121180346467 | 6.6 |  | 2020-11-06 |  |  | 2020-11-30 | W49-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03.12.20 : RFIN sent 30.11.20 : target connect PLN hari ini 19.11.20 : erection done, proses connect PLN dan finishing site 16.11.20 : erection ongoing 09.11.20 : rebaring, plan pouring 9 Nov 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : lantai kerja ongoing 22.10.20 : 19.10.20 : rebaring 15.10.20 : 12.10.20 : 08.10.20 : start excavation 05.10.20 : 24.09.20 : soiltes done, proses perijinan 21.09.20 : 17.09.20 : 14.09.20 : rekom camat done, proses design pack / APD 10.09.20 : proses legalitas lahan untuk lanjut realisasi IW 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : plan start CME W2 sep 27.08.20 : proses eskalasi sitac done, proses realisasi IW, paralel waiting approval TNP CAA 24.08.20 : IW clear, proses eskalasi biaya sitac 13.08.20 : IW di kandidat A yang bergeser ada 15 kk. terdapat 2 kk yg masih belum setuju dan sedang di nego habis..termasuk salah satunya ex wakapolda dan warga keturunan. target tgl 18 agustus 20 10.08.20 : kandidat L NOK, memaksimalkan IW di kandidat A (tower SST 62), follow up iw di kandidat A tinggal 4 kk. termasuk salah satunya polisi dan dokter, plan IW clear 15 Aug 06.08.20 : kandidat A dgn propose tower 62 gagal IW, submit kandidat baru (cand L 98.84141 2.67512) under RNP review 03.08.20 : 30.07.20 : 27.07.20 : IW on going 23.07.20 : kembali ke kandidat A dengan menambah tinggi tower menjadi SST 62, proses IW On Going 13.07.20 : IW on going tower 52m 09.07.20 : XL tetap prefer propose di bukit (no access dan no existing PLN) atau di kand A dengan tower 62m 02.07.20 : 29.06.20 : rehunting, hard sitac karena berada di daerah wisata dan warga menolak, cand yg diiinginkan XL berada di atas bukit, tidak ada jaringan PLN dan legalitas lahannya tidak jelas, Kand yg di ajukan TBG not OK by XL karena 1 sector terhalang bukit. Prepare JR terkait kand yg di inginkan XL (Bukit) dan propose re-NOM 25.06.20 : need konfirmasi/kirim email lagi 25.06.20 : 22.06.20 : re-validasi kandidat A NOK, need re-NOM / arahan RND XL 18.06.20 : email propose kandidat 17.06.20 : proses pengajuan ulang kandidat A (RNP Not OK), IW kondusif 15.06.20 : 11.06.20 : kandidat sudah ada, IW 50 %, ada isu ketinggian tower > 52m karena ada obstacle bukit sekitar 50m, NOM berada di area wisata + sectoral blocking, 08.06.20 : 04.06.20 : 02.06.20 : arahan rehunting XL berada di bukit dan tidak ada PLN, plan besok 3 juni join survey dengan mitra (internal TBG) 01.06.20 : proses rehunting, plan submit kand minggu ini 28.05.20 : rehunting, gagal IW 25.05.20 : IW on going 14.05.20 : 08.05.20 : proses izin warga on going 30.04.20 : gagal izin warga dan proses survey 23.04.20 : 16.04.20 : arahan dari XL di titik baru dengan tinggi tower 52m, validasi done, IW on going 09.04.20 : IW OG, plan IW clear 12 Apr 02.04.20 : rehunting, kandidat A dan B di reject dan diarahkan ke bukit..proses survey 25.03.20 : hunting
211 |  | JAW-JI-BLT-1913 | 30571110031 | 1642881003 | KEPANJEN_KIDUL_KEPANJENKIDUL | ACTIVE | TB | 112°10.3.14'null | 8°6.7.83'S | 30 | 50/140/280 | 2020 | JEDI 2020 [NEW] | Jl. Sumatra, Kel.Sananwetan RT.001 RW.013 Kec.Sananwetan, Kota Blitar Prov.Jawa Timur | HTI | JAW-JI-BLT-1913 | KEPANJEN_KIDUL_KEPANJENKIDUL | B2S | TBG | EAST | JATIM | Jawa Timur | Kota Blitar | 6616155 | 2020-08-31 |  | 99 | 91 - 120 days | 2021-01-28 | W05-2021 | Jan-2021 | 2020-10-30 | W44-2020 | Oct-2020 | 2020-10-30 | W44-2020 | Oct-2020 | 2020-12-07 | W50-2020 | Dec-2020 | MW | 2020-11-12 |  | 514021901285 | 13.2 |  | 2020-11-02 |  |  | 2020-12-08 | W50-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.12.20 : RFIN sent 07.12.20 : PLN connected, prepare RFIN 26.11.20 : proses PLN connection, menunggu no register release 23.11.20 : 19.11.20 : erection ongoing 16.11.20 : prepare start erection 12.11.20 : pondasi done, curring time 09.11.20 : 05.11.20 : lantai kerja ongoing 02.11.20 : 29.10.20 : galian 26.10.20 : start CME 22.10.20 : prepare CME , plan start 26 Oct 19.10.20 : RFC, rekom lurah camat done 15.10.20 : rekom PU dan PTSP done, soiltest done, proses review design tower kamuflase 36m 12.10.20 : plan minggu depan follow up ke instansi terkait (PU dan PTSP) 08.10.20 : 05.10.20 : proses review desain tower kamuflase dgn tinggi 36m oleh PU dan PTSP 01.10.20 : realisasi IW done, proses submit design tower kamuflase 28.09.20 : IW on going 24.09.20 : aktual proses APD, review TNP OK kand C, H: 36 0.6 266.41 per 23 sep 23.09.20 : submit review TNP Kand C propose penurunan tinggi tower (SST 42 menjadi SST 36) 21.09.20 : 17.09.20 : plan start CME minggu depan 11.09.20 : RND ok candidate C, tower 42, 10.09.20 : proses rehunting 07.09.20 : 03.09.20 : Review RND kand too far from NOM karena Perwali jarak antar menara, need submit JR & Perwali ke RND
157 |  | SUM-SU-AKK-2140 | 30595690031 | 0223821003 | PERK.PADANG HALABAN | ACTIVE | TB | 99.8732 | 2.3067 | 60 | 90/175/350 | 2020 | JEDI 2020 [NEW] | DESA AEK HITETORAS KECAMATAN MARBAU KABUPATEN LABUHANBATU UTARA PROVINSI SUMATERA UTARA | HTI | SUM-SU-AKK-2140 | PERK.PADANG HALABAN | B2S | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. LABUHAN BATU UT | 6614816 | 2020-07-01 |  | 133 | 121 - 150 days | 2020-11-28 | W48-2020 | Nov-2020 | 2020-11-27 | W48-2020 | Nov-2020 | 2020-11-27 | W48-2020 | Nov-2020 | 2020-11-27 | W48-2020 | Nov-2020 | MW | 2020-10-01 |  | 125140369472 | 6.6 |  | 2020-10-22 |  |  | 2020-11-11 | W46-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.11.20 : RFIN sent 09.11.20 : 05.11.20 : 02.11.20 :29.10.20 : 26.10.20 : isu penambahan tiang dan tarikan jaringan PLN 22.10.20 : 19.10.20 : erection ongoing 15.10.20 : 12.10.20 : 09.10.20 : cor done, curingtime 08.10.20 : on going bekisting dan prepare for pouring concrete, plan pouring paling lambat sabtu 10 oct 05.10.20 : rebarring 28.09.20 : borepile done, on going cerucuk 21.09.20 : resi IMB done, on going borepile 14.09.20 : 07.09.20 : 03.09.20 : 31.08.20 : proses perijinan 27.08.20 : rekom Camat done, proses perijinan 24.08.20 : 13.08.20 : 10.08.20 : 06.08.20 : proses negosiasi harga IMB 03.08.20 : 30.07.20 : 27.07.20 : 23.07.20 : IW Clear, proses eskalasi harga 20.07.20 : 16.07.20 : kandidat A TNP approved MW height 57m dia 1.2m, IW ongoing 16.07.20 : kandidat A TNP approved MW height 57m dia 1.2m, IW ongoing 13.07.20 : 10.07.20 : submit TNP review 09.07.20 : submit 8 Juli kandidat A koordinat 99.87314, 2.3067 propose SST 52, waiting RF Validation 01.07.20 : SPK release
143 |  | SUM-SB-BSK-0806 | 30595080031 | 0309061003 | PADANG LAWEH_TARAB | ACTIVE | TB | 100.5408 | -0.42228 | 50 | 30/120/240 | 2020 | JEDI 2020 [NEW] | Jalan Raya Padang Laweh Jorong Padang Laweh Baruah Nagari Padang Laweh Kecamatan Sungai Tarab Kabupaten Tanah Datar - Sumatera Barat | HTI | SUM-SB-BSK-0806 | PADANG LAWEH_TARAB | B2S | TBG | WEST | SUMBAGTENG | Sumatera Barat | KAB. TANAH DATAR | 6614769 | 2020-06-23 |  | 183 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-12-15 | W51-2020 | Dec-2020 | MW | 2020-10-06 |  | 134510159267 | 6.6 |  | 2020-10-22 |  |  | 2020-12-23 | W52-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.12.20 : RFIN sent 21.12.20 : plan RFIN announce 22 Dec 17.12.20 : plan connect PLN 17 Dec 14.12.20 : 10.12.20 : PLN connection process 07.12.20 : ME installation 03.12.20 : erection tower done, minus tray dan tangga plan 26.11.20 : erection section 6 (kendala curah hujan tinggi) 23.11.20 : erection ongoing 19.11.20 : prepare start erection 16.11.20 : backfill ongoing 12.11.20 : curring time 09.11.20 : pouring done 05.11.20 : curring time 02.11.20 : plan pouring start 4 Nov 29.10.20 : 26.10.20 : 22.10.20 : Galian done, lean concrete OG 19.10.20 : proses galian 15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : land clearing & bouwplank 01.10.20 : plan start CME 3 oct 20 28.09.20 : 21.09.20 : 07.09.20 : 03.09.20 : proses perijinan 31.08.20 : rekom done, submit berkas perijinan 27.08.20 : 24.08.20 : 17.08.20 : proses eskalasi sitac, on going proses rekom 13.08.20 : IW Done, proses rekom ongoing 10.08.20 : kandidat B TX OK, MW height 50m/0.6, IW ongoing 06.08.20 : kembali ke kandidat B, confirm provide tower SST 62, proses re-validasi TNP 03.08.20 : 30.07.20 : kandidat baru (B) NOK karena too far from NOM, RND request tower SST 62 , need arahan hunting 27.07.20 : IW failed, rehunting 23.07.20 : Kandidat A TNP OK dengan MW 50m/0.6m 20.07.20 : kandidat A RNP OK dengan RF 50m, waiting TNP review 16.07.20 : Ok candidate A, tower 52 13.07.20 : 13 jul submit kandidat A koordinat 100.53986, -0.4224 propose SST 52, menunggu review RNP 13.07.20 : plan submit kand hari ini 09.07.20 : on going hunting, plan submit kand minggu ini atau senin depan 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20
105 |  | SUM-SB-PYH-0835 | 30595090031 | 0309071003 | BALAI GADANG_PAYAKUMBUH | ACTIVE | TB | 100.6416 | -0.2181 | 30 | 40/200/300 | 2020 | JEDI 2020 [NEW] | Jln. Jend. Sudirman RT.002 RW.001 Kelurahan Balai Tangah Koto, Kecamatan Payakumbuh Utara, Kota Payakumbuh - Sumbar | HTI | SUM-SB-PYH-0835 | BALAI GADANG_PAYAKUMBUH | B2S | TBG | WEST | SUMBAGTENG | Sumatera Barat | KOTA PAYAKUMBUH | 6614769 | 2020-06-23 |  | 181 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-12-12 | W50-2020 | Dec-2020 | MW | 2020-10-06 |  | 134520295576 | 6.6 |  | 2020-10-22 |  |  | 2020-12-21 | W52-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : plan hari ini announce RFIN 17.12.20 : 14.12.20 : PLN connected, finishing site, proses collect doc RFIN 10.12.20 : survey PLN done, target RFI 12 Dec 03.12.20 : erection done, ME ongoing, BP PLN done 30.11.20 : 26.11.20 : erection ongoing 23.11.20 : pouring ongoing, material on site 19.11.20 : 16.11.20 : 12.11.20 : rebaring 09.11.20 : plan pouring start 10 Nov 05.11.20 : 02.11.20 : proses galian, plan pouring start 4 Nov 29.10.20 : 26.10.20 : 22.10.20 : Land clearing, penyedotan kolam ikan (masuk areal galian) 19.10.20 : prepare start CME 15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : kota payakumbuh, CME start menunggu proses perijinan 01.10.20 : expose DLH lanjut survey, plan lusa Go CME 28.09.20 : 21.09.20 : 07.09.20 : 03.09.20 : rekom camat done, prepare doc perijinan 31.08.20 : rekom ongoing 27.08.20 : 24.08.20 : 17.08.20 : IW clear, proses eskalasi biaya sitac 13.08.20 : IW ongoing minus 2kk, plan IW clear minggu ini 10.08.20 : IW clear, proses eskalasi CAPEX 06.08.20 : IW ongoing kandidat B 30.07.20 : kandidat B (koordinat 100.64189, -0.21809) reviewed by RNP OK -> RF 30m, TNP OK -> MW height 30m/0.6 27.07.20 : 24.07.20 : Kandidat A Failed, propose new kandidat in SAR, warga radius anggota kaum. target besok 27/7 validasi kandidat23.07.20 : kandidat A TNP OK dengan MW height 30m/0.6m 20.07.20 : kandidat A RNP approved dengan RF 30m, waiting TNP review 16.07.20 : Ok candidate A, tower 32 13.07.20 : 13 jul submit kandidat A koordinat 100.64235, -0.21841 propose SST 52, menunggu review RNP 13.07.20 : plan submit kand hari ini 09.07.20 : on going hunting, plan submit kand minggu ini atau senin depan 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20
97 |  | SUM-SU-KPI-2143 | 30595100031 | 0223791003 | ASAM JAWA_TORGAMBA | ACTIVE | TB | 100.1747 | 1.874 | 50 | 35/145/310 | 2020 | JEDI 2020 [NEW] | Dusun Sumberjo I Desa Persiapan Sumberjo Kecamatan Torgamba Kabupaten LabuhanBatu Selatan Prov.Sumatera Utara | HTI | SUM-SU-KPI-2143 | ASAM JAWA_TORGAMBA | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KAB. LABUHAN BATU SE | 6614769 | 2020-06-23 |  | 141 | 121 - 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-25 | W48-2020 | Nov-2020 | MW | 2020-10-06 |  | 125100663178 | 6.6 |  | 2020-10-22 |  |  | 2020-11-11 | W46-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.11.20 : RFIN sent 09.11.20 : 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : curring time, pekerjaan pagar dan ME ongoing 22.10.20 : 19.10.20 : erection ongoing 15.10.20 : 12.10.20 : 08.10.20 : on going bekisting dan prepare for pouring concrete, plan pouring paling lambat sabtu 10 oct 05.10.20 : rebarring 21.09.20 : resi IMB done, proses perijinan 14.09.20 : 07.09.20 : 03.09.20 : 31.08.20 : rekom done, proses perijinan 27.08.20 : proses eskalasi sitac approved, rekom lurah done, on going rekom camat 24.08.20 : proses eskalasi biaya sitac, paralel rekom on going 17.08.20 : IW clear, proses rekom on going 13.08.20 : TNP OK, iw kurang 1 kk lg, target 14 agustus 20 11.08.20 : TNP review, 10.08.20 : kandidat D RF OK 50m, proses review TNP, paralel IW on going kurang 2 kk, plan IW clear 14 Aug 06.08.20 : submit kandidat baru (cand D 100.1737 1.87254) under RNP review, kandidat C, D yg sebelumnya diajukan gagal IW 03.08.20 : kandidat C RF OK 50m, proses review TNP, paralel IW on going 30.07.20 : Kandidat B IW failed, submit kandidat baru (cand C koordinat 100.17412, 1.8753) under RNP review 27.07.20 : IW on going 23.07.20 : kandidat B TNP OK , MW height 48m, diameter 0.6m, proses IW on going 20.07.20 : wait TNP review 17.07.20 : kandidat B RNP approved dengan RF 50m, proses IW ongoing, wait TNP review 16.07.20 : kandidat A terkendala penolakan warga, 15 Jul submit kandidat baru (cand B koordinat 100.17535, 1.874103) masih menunggu review RNP 13.07.20 : 09.07.20 : kandidat A koordinat 100.17481, 1.87365 approved 7 Juli by RNP dengan RF 50m, waiting TX review 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20
110 |  | KAL-KB-NBA-0710 | 30587240031 | 2006851003 | MENJALIN | ACTIVE | TB | 109.3395 | 0.47282 | 40 | 30/100/300 | 2020 | JEDI 2020 [NEW] | Dusun Menjalin Hulu, RT 001/RW 001, Desa Menjalin, Kecamatan Menjalin, Kab. Landak, Prov. Kalimantan Barat | HTI | KAL-KB-NBA-0710 | MENJALIN | B2S | TBG | JABO | KALIMANTAN | Kalimantan Barat | KAB. LANDAK | 6614705 | 2020-05-12 |  | 155 | > 150 days | 2020-10-09 | W41-2020 | Oct-2020 | 2020-09-30 | W40-2020 | Sep-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-10-16 | W42-2020 | Oct-2020 | MW | 2020-07-16 |  | 211101612094 | 6.6 |  | 2020-10-22 |  | 2020-10-14 | 2020-10-14 | W42-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.10.20 : RFIN sent, site open akses 12.10.20 : RFI actual, collecting doc RFIN, masih terkendala isu block akses oleh warga luar radius (penyelesaian dg hukum adat) 08.10.20 : SRFI actual, info BMKG minggu2 ini Kalbar terjadi Intensitas Hujan Tinggi, plan RFI revisi 12 oct 20 05.10.20 : erection top, revisi plan submit RFIN 9 oct 20 01.10.20 : plan RFI 5 oct 20 28.09.20 : on going erection 24.09.20 :21.09.20 : cor done, curingtime, plan start erection 24 sep 20, plan RFI 30 sep 17.09.20 : rebarring, Plan Cor 20/09 14.09.20 : rebarring 10.09.20 : 07.09.20 : on going cerucuk 03.09.20 : 31.08.20 : rebarring on going 27.08.20 : excavation done, bar bending & preparation rebarring 24.08.20 : 17.08.20 : excavation (menggunakan pekerja lokal sesuai permintaan warga), plan RFI 15 sep 13.08.20 : open akses/isu clear, continue excavation 10.08.20 : pekerjaan galian sementra di stop warga yg ber tanda tangan IW komplain karena menurut dia tower ya terlalu dekat dng rumahya,, aktualya radius 50m,, hari ini sedang di mediasi kan dgn kepala desa 06.08.20 : excavation 03.08.20 : Galian, Cerucuk OG, Plan Cor 4 Aug. 23.07.20 : plan start galian hari ini, plan cor 31 jul 16.07.20 : start excavation menunggu setelah acara adat 18 jul 20, plan galian menggunakan excavator 13.07.20 : bouwplank 09.07.20 : proses perijinan, Plan percepatan CME : Bowplank 09/07, Galian 09/07 menggunakan Excavator, Cerucuk 10/07 - Finish 11/07, Rebaring 11/07 - Finish 14/07, Pouring 15/07, Curingtime 16/07 - Finish 18/07, Erection 19/07 - Finish 26/07, ME 26/07, GRounding 26/07, SRFI: 27/07, PLN connect: 28/07, RFI: Plan 28/07 02.07.20 : start CME wait APD, bisa paralel dg perijinan, plan APD minggu ini, plan start CME minggu depan 29.06.20 : proses perijinan 25.06.20 : plan RFC end of june, plan start CME W1 juli 22.06.20 : prepare soiltest dan realisasi IW (wait approval) 18.06.20 : plan eskalasi sitac approved 19/06/2020 15.06.20 : iw clear (confirmed Cand. C) , approval CAPEX 11.06.20 : proses review dan validasi eskalasi sitac 08.06.20 : 04.06.20 : IW clear, proses pengajuan eskalasi sitac 02.06.20 : TNP OK, IW on going 01.06.20 : 29.05.20 : waiting RND review 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : IW on going 23.04.20 : 16.04.20 : rehunting 09.04.20 : IW on going 06.04.20 : 02.04.20 : 25.03.20 : RND OK. TNP NOK. All FE Obstacle, rehunting namun masih menunggu NOM arahan dari XL 12.05.20 : SPK release (revisi dari SPK no. 6614554 karena perubahan ID dari KAL-KB-MPW-0702 menjadi KAL-KB-NBA-0710
179 |  | SUM-SU-KIS-2129 | 30581630031 | 0223601003 | SEI SILAU BARAT | ACTIVE | TB | 99.5124 | 2.9361 | 50 | 10/100/300 | 2020 | JEDI 2020 [NEW] | Madrasah Ibtidaiyah, Emplasmen PTPN III Dusun IX, Desa Sei Silau Barat, Kec. Setia Janji, Kab. Asahan, Provinsi Sumatera Utara | HTI | SUM-SU-KIS-2129 | SEI SILAU BARAT | B2S | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. ASAHAN | 6614479 | 2020-02-13 |  | 255 | > 150 days | 2020-07-12 | W29-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-10-30 | W44-2020 | Oct-2020 | MW | 2020-10-01 |  | 121111060388 | 6.6 |  | 2020-10-22 |  |  | 2020-10-25 | W44-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.10.20 : RFIN sent 22.10.20 : aktual RFI, proses penyusunan dok RFIN 19.10.20 : proses penyambungan PLN 15.10.20 : 12.10.20 : 08.10.20 : start erection 05.10.20 : curingtime 28.09.20 : rebarring done, prepare for pouring 24.09.20 : 21.09.20 : IMB done, borepile 14.09.20 : 07.09.20 : 03.09.20 : rekom camat done, proses perijinan 31.08.20 : 27.08.20 : plan RFI permanent W4 Oct, submit berkas perijinan dan PKS done, menunggu jadwal survey 27.08.20 : propose percepatan RFI dengan combat 42m (permanent 52m) Not OK by RND XL. Proses birokrasi kerjasama dg PTPN III membutuhkan waktu yang lama dikarenakan harus sampai persetujuan Direksi PTPN. Dalam prosesnya Direksi terkait dinyatakan positif Covid-19 sehingga menambah panjang proses kerjasama yang harus dilakukan. Saat ini PKS sudah disetujui oleh Direksi pengganti sehingga proses akuisisi dapat dilanjutkan kembali. Karena tidak disetujuinya penggunaan Combat sebagai solusi percepatan maka TBG mengajukan permohonan extend waktu untuk melanjutkan proses pembangunan Tower Permanennya dengan segera setelah Perijinan dari Pemda setempat release yang kami targetkan untuk Tower Permanen bisa RFI di W4 Oktober 2020. 24.08.20 : rekom done, proses perijinan 17.08.20 : 13.08.20 : proses kerjasama dengam ptpn, Iw done dan pks on going. proses rekom lurah dan camat target rekom 19 agustus 20 10.08.20 : 06.08.20 : proses ttd kontrak dengam ptpn, paralel proses prepare percepatan dengan combat 42, combat sudah di area sumbagut 03.08.20 : 30.07.20 : 27.07.20 : proses ttd kontrak dengam ptpn 23.07.20 : 20.07.20 : proses approval PKS terkendala salah satu petinggi PTPN (VP) terkena covid-19, TBG sedang berusaha mengajukan addendum agar ada PIC pengganti yang dapat tandatangan PKS 09.07.20 : capex approved, proses legalitas dengan coorporate ptpn 06.07.20 : proses submit dan review capex by TBG 02.07.20 : Perhitungan kjjp sudah selesai dan sudah diserahkan ke ptpn 3 dan saat ini sedang di review oleh ptpn 3 terkait harga dr kjjp tersebut. 29.06.20 : plan selasa clear, hasil perhitungan kppj, sudah submit ke direksi, setelah jawaban keluar akan diajukan propose percepatan dengan combat, 25.06.20 : perhitungan kppj, masih proses nego harga sewa lahan 22.06.20 : 18.06.20 : koordinat approved by PTPN, proses penilaian harga sewa lahan oleh konsultan, plan clear jawaban PTPN end of Jun 15.06.20 : 11.06.20 : plan propose combat, plan RFI Juli 08.06.20 : 04.06.20 : 28.05.20: 08.05.20 : titik sdh disetujui oleh ptpn dan saat ini sedang pengajuan direksi oleh ptpn dan akan disposisi ke konsultan utk penghitungan nilai sewa 30.04.20 : kemaren baru selesai joint survey dengan ptpn dan titik sdh disetujui oleh PTPN 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : menunggu joint survey dengan pihak PTPN yang sampai saat ini terkendala isu COVID-19, Pic PTPN WFH 25.03.20 : menunggu joint survey dengan pihak PTPN. estimasi minggu depan 19.03.20 : wait appraval permohonan perpanjangan waktu dari XL, tower permanen (1 tahun) maupun temporary (3 bulan) 18.03.20 : XL request tower temporary untuk menunggu site permanent RFI. Sedangkan untuk proses penempatan tower temporary sesuai flow proses PTPN 3 minimal harus mendapatkan persetujuan dari (Senior Executive Vice President) dimana estimasi waktu yg dibutuhkan 3 bulan. Catatan : dengan kondisi & situasi saat ini kemungkinan proses akan memakan waktu lebih lama dari 3 bulan 17.03.20 : email pengajuan perpanjangan waktu karena lokasi berada di area PTPN 3 dengan proses Kerja Sama dg PTPN 3 membutuhkan waktu yg panjang (estimasi 1 tahun) 11.03.20 : menunggu suart jawaban dari PTPN plan minggu depan W12 surat jawaban release. estimasi setelah approval PTPN (approval, survey, perhitungan konsulatan PTPN) sampai start CME sekitar 3 bulan, plan percepatan dengan GM 42m 28.02.20 : lokasi di lahan PTPN dan sdh disubmit surat permohonan sewa lahannya ke PTPN, masih menunggu surat jawaban PTPN. Status koordinat kandidat sdh approved. 20.02.20 : hunting, on going survey 13.02.20 : SPK released
213 |  | SUL-SN-SKG-1279 | 30599190031 | 2811091003 | TANCUNG_TANASITOLO | ACTIVE | TB | 120°1.37.2'E | 4°3.37.3'S | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | TANCUNG, RT/RW. 001/002, KELURAHAN TANCUNG, KECAMATAN TANASITOLO, KABUPATEN WAJO, PROVINSI SULAWESI SELATAN. | HTI | SUL-SN-SKG-1279 | TANCUNG_TANASITOLO | B2S | TBG | EAST | SULAWESI | Sulawesi Selatan | Kab. Wajo | 6616166 | 2020-09-01 |  | 167 | > 150 days | 2021-01-29 | W05-2021 | Jan-2021 | 2020-12-25 | W52-2020 | Dec-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-12 | W07-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 322400382066 | 6.6 |  | 2020-10-20 |  |  | 2021-02-15 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.02.21 : RFI power by multiguna 11.02.21 : penarikan jaringan done 08.02.21 : BP Paid, waiting jadwal connect PLN 21.01.21 : PSB released, PLN connection OG 21.01.21 : PSB released, proses connect PLN 16.11.20 : SRFIN sent 12.11.20 : 09.11.20 : 05.11.20 : aktual SRFI, proses penyusunan doc SRFIN 02.11.20 : erection done, ME ongoing 29.10.20 : 26.10.20 : 22.10.20 : start erection 19.10.20 : curring time 15.10.20 : plan pouring 17 oct, material tower dan angkur baru tiba di Makassar dan masih proses bongkar dipelabuhan 12.10.20 : galian done, on going rebarring, plan pouring 13 oct, material tower on delivery sudah sandar di Makasar dan proses bongkar 08.10.20 : RFC, start galian, material masih dalam proses pengiriman 05.10.20 : 01.10.20 : rekom done, proses collect doc perijinan 28.09.20 : on going rekom Camat 24.09.20 : IW clear, proses Rekom Lurah dan paralel proses APD, Soil Test done Hari Minggu kemarin 21.09.20 : 17.09.20 : RND dan TNP OK, IW on going 14.09.20 : hunting
31 |  | JAW-JB-CMH-3439 | 30597170031 | 1262231003 | CIPAGERAN | ACTIVE | TB | 107.5435 | -6.8483 | 30 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Karya Bakti Kp. Lebak Saat RT.001/RW.018 Kelurahan Cipageran Kecamatan Cimahi Utara Kota Cimahi | HTI | JAW-JB-CMH-3439 | CIPAGERAN | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA CIMAHI | 6614889 | 2020-07-14 |  | 216 | > 150 days | 2020-12-11 | W50-2020 | Dec-2020 | 2021-02-10 | W07-2021 | Feb-2021 | 2020-12-10 | W50-2020 | Dec-2020 | 2021-02-15 | W08-2021 | Feb-2021 | MW | 2020-10-05 |  | 535812186522 | 6.6 |  | 2020-10-20 |  |  | 2021-02-15 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.02.21 : erection tower done 28.01.21 : plan CME start W1 Feb 21.01.21 : plan IMB release 22 Jan 30.11.20 : IMB not yet release 09.11.20 : kondisi aktual sudah RFI namun ada isu perijinan sehingga tower harus dibongkar, proses erection dilakukan kembali setelah IMB terbit (plan 27 Nov 2020), plan RFI W2 Dec 05.11.20 : aktual RFI, minus finishing pagar (CME distop oleh pol PP) 02.11.20 : erection done, ME installation 29.10.20 : 26.10.20 : PLN connected, erection ongoing 22.10.20 : erection ongoing 19.10.20 : curring time 12.10.20 : rebarring 08.10.20 : on going excavation 05.10.20 : 04.10.20 : start excavation 01.10.20 : rekom done, RFC, plan start CME 2 Okt 28.09.20 : rekom on going, hari ini rekom lurah, besok rekom camat 24.09.20 : eskalasi approved, realisasi IW dan rekom target done minggu ini, proses APD 21.09.20 : proses eskalasi sitac, plan realisasi IW minggu ini, paralel proses rekom dan request soiltest 17.09.20 : IW Clear, review TNP OK RF 40m , TNP OK MW 40m/0.6, request soiltest, Plan bayar iw dan rekom Minggu dpn 14.09.20 : IW on going kand baru 75% plan IW clear besok, validasi kand akan diajukan setelah IW clear 10.09.20 : kandidat D failed, proses rehunting 07.09.20 : 03.09.20 : submit kandidat baru, cand D RF OK 30m 31.08.20 : 27.08.20 : Proses Finalisasi IW (negosiasi kompensasi) 24.08.20 : 23.08.20 : malam ini finalisasi IW, plan malam ini bisa clear 17.08.20 : 13.08.20 : 10.08.20 : IW on going kand A, IW 20% (total 24 KK), IW memerlukan pendekatan khusus karena rentan terhadap penolakan warga 06.08.20 : IW on going kand A 03.08.20 : 30.07.20 : kandidat A RF TX OK namun mengalami kendala gagal IW, plan submit kandidat baru (cand B) kamis 30 Jul 27.07.20 : kandidat A under TNP review 23.07.20 : kandidat A koordinat 107.541996, -6.849767 RND approved , RF 30m 20.07.20 : plan hari ini submit kandidat 16.07.20 : hunting
74 |  | KAL-KB-NBA-0707 | 30588040031 | 2006891003 | KARANGAN LANDAK | ACTIVE | TB | 109.38 | 0.55656 | 40 | 20/110/230 | 2020 | JEDI 2020 [NEW] | Jalan Raya karangan - Sompak, RT 002/RW 003, Desa karangan, Kecamatan Mempawah Hulu, Kab. Landak, Prov. Kalimantan Barat | HTI | KAL-KB-NBA-0707 | KARANGAN | B2S | TBG | JABO | KALIMANTAN | Kalimantan Barat | KAB. LANDAK | 6614568 | 2020-03-19 |  | 214 | > 150 days | 2020-08-16 | W34-2020 | Aug-2020 | 2020-09-30 | W40-2020 | Sep-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-10-19 | W43-2020 | Oct-2020 | MW | 2020-08-10 |  | 211101612086 | 6.6 |  | 2020-10-20 |  |  | 2020-10-19 | W43-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22.10.20 : doc RFIN sent 19.10.20 : plan hari ini RFI 15.10.20 : on going erection (kendala curah hujan tinggi), PLN sudah tarik jaringan 12.10.20 : on going erection 08.10.20 : erection tower terkendala hujan, info BMKG minggu2 ini Kalbar terjadi Intensitas Hujan Tinggi, revisi plan RFI 19 oct 05.10.20 : plan hari ini start erection 01.10.20 : 30.09.20 : on going pouring concrete 28.09.20 : rebaring plan cor 29/09 24.09.20 : plan cor 27 sep 20, plan start erection 1 oct, plan RFI tetap dikejar 5 oct 21.09.20 : 17.09.20 : rebarring, Plan Cor 22/09, revisi plan RFI 5 oct 14.09.20 : kondisi site terkena banjir, rebarring 10.09.20 : 07.09.20 : 03.09.20 : on going rebarring, terkendala hujan dan galian longsor 31.08.20 : 27.08.20 : on going rebarring 24.08.20 : rebarring, plan cor 25 Aug 20 17.08.20 : 13.08.20 : plan cor 18 Aug 10.08.20 : rebarring, plan cor 14 Aug 03.08.20 : Rebaring OG, Plan Cor 4 Aug. 23.07.20 : plan start galian hari ini, plan cor 31 jul 16.07.20 : start excavation menunggu setelah acara adat 18 jul 20, plan galian menggunakan excavator 13.07.20 : bouwplank 02.07.20 : proses perijinan, Plan percepatan CME : Bowplank 09/07, Galian 09/07 Menggunakan Excavator, Cerucuk 10/07 - Finish 11/07, Rebaring 11/07 - Finish 14/07, Pouring 15/07, Curing 16/07 - Finish 18/07, Erection 19/07 - Finish 26/07, ME 26/07, SRFI 27/07 02.07.20 : start CME wait APD, bisa paralel dg perijinan, plan APD minggu ini 29.06.20 : proses perijinan 25.06.20 : plan RFC end of june, plan start CME W1 juli 25.06.20 : 22.06.20 : proses approval realisasi IW, plan prepare soiltest 18.06.20 : plan eskalasi sitac approved 19/06/2020 15.06.20 : IW clear (confirmed Cand. B), proses review dan validasi eskalasi sitac 11.06.20 : proses review dan validasi eskalasi sitac 08.06.20 : 04.06.20 : IW clear, proses pengajuan eskalasi sitac 01.06.20 : IW on going 28.05.20 : re follow up IW kand sebelumnya 25.05.20 : 14.05.20 : 08.05.20 : IW on going 30.04.20 : 23.04.20 : 16.04.20 : 09.04.20 : IW on going 02.04.20 : under review TNP 31.03.20 : waiting TNP review 25.03.20 : hunting, belum bisa masuk wilayah landak dikarenakan masih ada acara tolak bala suku dayak
458 |  | JAW-JB-CMH-4007 | 30605940031 | T000305 | GUNUNG BATU | ACTIVE | SKP | 107°33.51.77'E | 6°53.6.04'S | 30 | 0/90/200 | 2020 | JEDI 2020 [NEW] | JL.BABAGAN LOA,RANCA BALI RT 05 RW 03 ,KEL PASIRKALIKI CIMAHI UTARA CIMAHI | HTI | JAW-JB-CMH-4007 | KALIKI_UTARA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kota Cimahi | 6616314 | 2020-10-09 |  | 112 | 91 - 120 days | 2020-11-08 | W46-2020 | Nov-2020 | 2020-11-07 | W45-2020 | Nov-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 535812201016 | 6.6 |  | 2020-10-15 |  |  | 2021-01-29 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : PSB released, PLN connection OG 09.11.20 : SRFIN sent 05.11.20 : aktual SRFI 02.11.20 : ME installation 29.10.20 : prepare STO & start CME 20.10.20 : SPK release
212 |  | JAW-JI-SBY-8279 | 30571380031 | 1643151003 | KENJERAN_TANAH_KALI_KEDINDING | ACTIVE | TB | 112°46.51.42'null | 7°13.39.92'S | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl. Kalilom Lor Indah Matahari, RT.04 RW.10, Kelurahan Tanah Kali Kedinding, Kecamatan Kenjeran, Kota Surabaya | HTI | JAW-JI-SBY-8279 | KENJERAN_TANAH_KALI_KEDINDING | B2S | TBG | EAST | JATIM | Jawa Timur | Kota Surabaya | 6616155 | 2020-08-31 |  | 67 | 61 - 90 days | 2021-01-28 | W05-2021 | Jan-2021 | 2020-10-30 | W44-2020 | Oct-2020 | 2020-10-30 | W44-2020 | Oct-2020 | 2020-11-10 | W46-2020 | Nov-2020 | MW | 2020-10-01 |  | 511051046348 | 6.6 |  | 2020-10-13 |  |  | 2020-11-06 | W45-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09.11.20 : RFIN sent 05.11.20 : aktual RFI, proses collect doc RFIN 02.11.20 : 29.10.20 : 22.10.20 : 19.10.20 : pengecoran 3x bertahap total 7m (balok 4m done) 15.10.20 : curingtime, plan start erection 20 oct 20 12.10.20 : on going cor stacking 08.10.20 : 05.10.20 : start CME rebarring stacking 7m 01.10.20 : material on site, LL mengijinkam start 2 oktober 28.09.20 : plan start CME minggu ini 24.09.20 : rekom done, plan APD minggu ini. , plan start CME minggu depan 21.09.20 : realisasi IW done, proses rekom on going, hammer test done, plan APD minggu ini. 17.09.20 : plan start CME minggu depan 11.09.20 : waiting TNP review knd B, RT 8m + stacking 6m + pole 6m (Total = 20m) 10.09.20 : proses rehunting , terkendala issue perda SURABAYA max tinggi menara 20m 07.09.20 : 03.09.20 : propose tower max 20m, RND masih not OK, lokasi hanya ada bangunan tertinggi 8m + stacking 6m + pole 6 m, total 20m. Proses eskalasi & review by RND
158 |  | SUM-AC-MRN-0522 | 30595050031 | 0109991003 | REUSEB | ACTIVE | TB | 96.1712 | 5.2406 | 50 | 20/110/230 | 2020 | JEDI 2020 [NEW] | Gampong Reuseb, Kec. Trienggadeng, Kab. Pidie Jaya, Prov. Aceh | HTI | SUM-AC-MRN-0522 | REUSEB | B2S | TBG | WEST | SUMBAGUT | Aceh | PIDIE JAYA | 6614769 | 2020-06-23 |  | 155 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-25 | W48-2020 | Nov-2020 | MW | 2020-09-07 |  | 116620110189 | 6.6 |  | 2020-10-13 |  |  | 2020-11-25 | W48-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.11.20 : RFIN sent 19.11.20 : PLN connected, proses finishing site 16.11.20 : PLN connection process 12.11.20 : erection done, aktual SRFI 09.11.20 : 05.11.20 : start erection 02.11.20 : 29.10.20 : 26.10.20 : 22.10.20 : 19.10.20 : rebaring 15.10.20 : 12.10.20 : 08.10.20 : on going bekisting dan prepare for pouring concrete, plan pouring paling lambat sabtu 10 oct 05.10.20 : rebarring 24.09.20 : rebaring foundation 21.09.20 : 14.09.20 : 10.09.20 : borepile on going 07.09.20 : bouwplank 31.08.20 : 27.08.20 : 24.08.20 : 13.08.20 : mobilisasi, plan land clearing mundur besok karena hujan petir 10.08.20 : plan land clearing besok 11 Aug 06.08.20 : 03.08.20 : RFC, proses perijinan 30.07.20 : IW DONE, rekom on going 27.07.20 : rekom on going 23.07.20 : kandidat C TNP OK MW height 50m, diameter 0.6, IW clear, proses eskalasi harga 20.07.20 : wait TNP review 17.07.20 : kandidat C RNP OK dengan RF 50m, paralel proses IW ongoing, wait TNP review 16.07.20 : Ok candidate C, tower 52 13.07.20 : 13 jul submit kandidat baru (cand C koordinat 96.16953, 5.24131) masih menunggu review RNP 09.07.20 : Kandidat A approved by RNP dengan RF 50m, namun gagal IW, paralel 7 Juli submit kandidat B dengan koordinat 96.17359, 5.23867 propose SST 52, RND not OK B karena dekat NOM, rehunting 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20
153 |  | SUM-AC-KTN-0377 | 30595020031 | 0109961003 | PEJUANG | ACTIVE | TB | 97.8876 | 3.4272 | 50 | 140/240/310 | 2020 | JEDI 2020 [NEW] | Desa Empat Lima, Kec. Bukit Tusam, Kab. Aceh Tenggara, Prov. Aceh | HTI | SUM-AC-KTN-0377 | PEJUANG | B2S | TBG | WEST | SUMBAGUT | Aceh | ACEH TENGGARA | 6614769 | 2020-06-23 |  | 150 | 121 - 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-10-19 | W43-2020 | Oct-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-25 | W48-2020 | Nov-2020 | MW | 2020-09-07 |  | 113340195209 | 6.6 |  | 2020-10-13 |  |  | 2020-11-20 | W47-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23.11.20 : RFIN sent 19.11.20 : BPUJL paid, jadwal connect PLN minggu ini 16.11.20 : issue management trafo, plan connect PLN W3 Nov 12.11.20 : 09.11.20 : 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : kondisi trafo overload, pihak PLN sedang melakukan perbaikan 22.10.20 : 19.10.20 : proses penyambungan PLN 15.10.20 : 12.10.20 : 08.10.20 : continue CME, curingtime, start erection 05.10.20 : 01.10.20 : 28.09.20 : 24.09.20 : STOP karena isu perijinan 21.09.20 : 21.09.20 : 17.09.20 : 14.09.20 : CME hold, proses penyelesaian isu perijinan 10.09.20 : proses penyelesaian isu perijinan 07.09.20 : 31.08.20 : excavation 27.08.20 : 24.08.20 : 13.08.20 : mobilisasi, plan land clearing mundur besok karena hujan petir 10.08.20 : plan land clearing besok 11 Aug 06.08.20 : 03.08.20 : RFC, proses perijinan 30.07.20 : target rekom camat done 30 Jul 27.07.20 : rekom camat done, collecting berkas perijinan 23.07.20 : rekom on going 16.07.20 : kandidat A approved by TNP MW height 45m diameter 1.2m, IW Clear, proses rekom ongoing 13.07.20 : 11.07.20 : TNP review 09.07.20 : kandidat A approved by RNP dengan RF 50m namun terkendala issue penolakan warga, paralel 6 Juli submit kandidat B koordinat 97.88766, 3.42707 SST 52 (waiting RNP review) 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20
133 |  | SUM-AC-MRN-0523 | 30595060031 | 0110001003 | GEULANGGANG | ACTIVE | TB | 96.2778 | 5.2472 | 40 | 80/140/320 | 2020 | JEDI 2020 [NEW] | Desa Tijien Daboh, Kec. Ulim, Kab. Pidie Jaya, Provinsi Aceh | HTI | SUM-AC-MRN-0523 | GEULANGGANG | B2S | TBG | WEST | SUMBAGUT | Aceh | PIDIE JAYA | 6614769 | 2020-06-23 |  | 114 | 91 - 120 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-10-19 | W43-2020 | Oct-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-10-10 | W41-2020 | Oct-2020 | MW | 2020-09-07 |  | 116620110171 | 6.6 |  | 2020-10-13 |  |  | 2020-10-15 | W42-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22.10.20 : RFIN sent 19.10.20 : aktual RFI, proses pengumpulan doc RFIN 15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : SRFI actual, proses PLN connection 01.10.20 : 28.09.20 : erection on going, ME on going 21.09.20 : cor done, curingtime 14.09.20 : lanjut pembesian kondisi cuaca hujan, plan pouring concrete mundur ke rabu 16 sept 2020 10.09.20 : borepile done, on going excavation 07.09.20 : 31.08.20 : 27.08.20 : on going borepile 24.08.20 : 13.08.20 : mobilisasi CME (plan bouwplank hari ini), paralel proses perijinan 10.08.20 : 06.08.20 : 03.08.20 : RFC, proses perijinan 30.07.20 : target rekom done 30 Jul 27.07.20 : proses rekom camat 23.07.20 : rekom on going 16.07.20 : kandidat A TNP approved MW height 40m dia 0.6m, status IW Clear, proses rekom dan realisasi IW 13.07.20 : 10.07.20 : submit TNP review 09.07.20 : kandidat A approved by RND 30 Juni 2020 dengan RF 50m, menunggu validasi TX 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20
131 |  | SUM-AC-MRN-0524 | 30595070031 | 0110011003 | DRIEN BUNGONG | ACTIVE | TB | 96.3261 | 5.1811 | 50 | 40/150/330 | 2020 | JEDI 2020 [NEW] | Desa Meugit Sagoe, Kec. Bandar Dua, Kab. Pidie Jaya, Provinsi Aceh | HTI | SUM-AC-MRN-0524 | DRIEN BUNGONG | B2S | TBG | WEST | SUMBAGUT | Aceh | PIDIE JAYA | 6614769 | 2020-06-23 |  | 98 | 91 - 120 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-10-19 | W43-2020 | Oct-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-10-02 | W40-2020 | Oct-2020 | MW | 2020-09-07 |  | 116620109833 | 6.6 |  | 2020-10-13 |  | 2020-09-23 | 2020-09-29 | W40-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.10.20 : 29.09.20 : RFIN sent 28.09.20 : RFI actual, collecting doc RFIN 23.09.20 : email SRFI-N sent 21.09.20 : plan soft RFI hari ini 14.09.20 : Erection Done, BTS OD OG, M/E Og , Pagar dan akses OG , 10.09.20 : erection on going 31.08.20 : 27.08.20 : galian dengan excavator, on going bar bending 24.08.20 : 13.08.20 : mobilisasi CME (plan bouwplank hari ini), paralel proses perijinan 10.08.20 : rekom l/c done, proses perijinan 06.08.20 : proses rekom ongoing, rekom lurah done, on going rekom camat 03.08.20 : 30.07.20 : IW DONE, target rekom done 30 Jul 27.07.20 : IW on going 23.07.20 : 16.07.20 : kandidat B TNP approved MW height 48m dia 0.6m, IW ongoing 13.07.20 : 10.07.20 : submit kand B, TNP review 09.07.20 : kandidat A NOK too far from NOM. Submit kandidat B koordinat 96.32695,5.18316 SST 52 sudah approved oleh RND 7 Juli 2020, menunggu review TX 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20
137 |  | JAW-JB-BJR-3853 | 30570960031 | 1260751003 | PURWAHARJA_TENGAH | ACTIVE | TB | 108.5397 | -7.3513 | 30 |  | 2020 | JEDI 2020 [NEW] | Link Siluman Baru, RT.37 RW.17 Desa Purwarharja, Kecamatan Purwaharja, Kota Banjar, Jawa Barat. | HTI | JAW-JB-BJR-3853 | PURWAHARJA_TENGAH | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANJAR | 6614369 | 2020-01-13 |  | 301 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-10-10 | W41-2020 | Oct-2020 | 2020-08-17 | W34-2020 | Aug-2020 | 2020-11-17 | W47-2020 | Nov-2020 | MW | 2020-09-10 |  | 532217719560 | 6.6 |  | 2020-10-09 |  |  | 2020-11-09 | W46-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.09.20 : RFIN sent 09.11.20 : 05.11.20 : aktual RFI, proses collect doc RFIN 02.11.20 : ME installation 29.10.20 : 26.10.20 : erection ongoing, paralel konek jaringan PLN 22.10.20 : curring time, plan hari ini on site untuk start CME kembali 19.10.20 : curring time, stop pol PP karena issue opsic 12.10.20 : 08.10.20 : 05.10.20 : 01.10.20 : 28.09.20 : Curingtime, urugan tanah + pondasi bts OG, start erection tower waiting perijinan release 24.09.20 : 21.09.20 : rebarring, plan cor selasa 22 sep 17.09.20 : on going excavation 14.09.20 : 11.09.20 : start galian 10.09.20 : Mob demob plan sabtu 12 sep 20 07.09.20 : 03.09.20 : berkas perijinan sudah masuk TPKRD dan sedang proses review 31.08.20 : 27.08.20 : submit berkas ke perijinan 26 Aug 20 (PTSP) dan sedang proses review 24.08.20 : 17.08.20 : CME belum dapat start karena isu perijinan kota banjar, CME ny start 13.08.20 : 10.08.20 : 06.08.20 : 03.08.20 : proses koordinasi penjadwalan survey dan rapat TKPRD 27.07.20 : 16.07.20 : CME belum dapat start karena isu perijinan kota banjar 13.07.20 : proses perijinan 09.07.20 : plan rekom done minggu ini 10 jul, plan start proses perijinan minggu depan 13 jul, start CME setelah proses perijinan plan 20 jul 06.07.20 : plan rekom minggu ini 02.07.20 : IW clear, plan Rekom minggu depan, plan RFC W2 Juli, dan jika sudah submit berkas perijinan bisa paralel start CME, Plan RFI 17 Aug 20 29.06.20 : 25.06.20 : pergeseran kandidat, IW on going 22.06.20 : IW ongoing, kembali ke kandidat yang sudah approved OK (cand B) 19.06.20 : perubahan type transport dari FO menjadi MW, need req SK PLN 18.06.20 : proses nego/pendekatan IW, paralel rehunting, need arahan dari XL 15.06.20 : kandidat B RNP TNP approved, tapi reject IW 11.06.20 : 08.06.20 : 04.06.20 : 01.06.20 : IW clear proses negosiasi eskalasi 25.05.20 : 14.05.20 : finalisasi eskalasi sitac, plan start realisasi sitac dan proses rekom 08.05.20 : 30.04.20 : negosiasi eskalasi 23.04.20 : 16.04.20 : 09.04.20 : IW on going 02.04.20 : under review TNP 25.03.20 : TNP review 19.03.20 : 12.03.20 : rehunting 20.02.20 : IW on going 13.02.20 : Kand A = Rehunting 06.02.20 : Kand A = Rehunting
208 |  | SUM-BE-KPH-0198 | 30597780031 | 0902921003 | TANGSI BARU | ACTIVE | TB | 102.5917 | -3.6045 | 60 |  | 2020 | JEDI 2020 [NEW] | Jl.Makam Tangsi Baru, RT.007 RW.002, Kel.Tangsi Baru, Kec.Kabawetan, Kab.Kepahiang, Prov.Bengkulu | HTI | SUM-BE-KPH-0198 | TANGSI BARU | B2S | TBG | WEST | LAMPUNG | Bengkulu | Kepahiang | 6615571 | 2020-08-18 |  | 92 | 91 - 120 days | 2021-01-15 | W03-2021 | Jan-2021 | 2020-09-28 | W40-2020 | Sep-2020 | 2020-10-20 | W43-2020 | Oct-2020 | 2020-11-30 | W49-2020 | Nov-2020 | MW | 2020-09-07 |  | 146205124118 | 6.6 |  | 2020-10-06 |  |  | 2020-11-18 | W47-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.11.20 : RFIN sent 23.11.20 : multiguna connected 19.11.20 : proses konek PLN multiguna, PLN permanen masih menunggu jawaban dari PLN wilayah S2JB 09.11.20 : 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : 22.10.20 : proses BPUJL 19.10.20 : ME ongoing 15.10.20 : 12.10.20 : start erection 08.10.20 : COR DONE, plan Start Erection Sabtu 10 oct, target SRFI: 16 Oct 2020, nomor register PLN NY Release, sudah disurati kembali ke PLN, semoga besok sudah release no register nya 05.10.20 : rebarring 01.10.20 : rebarring 28.09.20 : galian done, on going lantai kerja 24.09.20 : plan start CME besok 25 sep, GDL tower release 21.09.20 : 17.09.20 : plan start senin 21 sep 14.09.20 : APD done, CME preparation (mobilisasi team) 10.09.20 : 07.09.20 : proses APD 03.09.20 : proses soiltest plan 4 Sept 31.08.20 : rekom done, proses approval eskalasi Sitac 27.08.20 : kand C RF TX OK -> MW 60m/0.6, IW CLEAR, ongoing rekom 24.08.20 : kandidat C RF OK, proses review TNP 13.08.20 : submit kandidat A (koordinat 102.58966, -3.60494) RNP NOK karena sectoral blocking, arahan hunting 102.593395, -3.603029 03.08.20 : SPK release
203 |  | JAW-JB-BJR-3852 | 30597760031 | 1262261003 | REJASARI_LANGENSARI | ACTIVE | TB | 108.6275 | -7.3627 | 50 | 50/130/325 | 2020 | JEDI 2020 [NEW] | Sindanggalih RT 005 RW 006 Desa Rejasari Kec Langensari Kota Banjar | HTI | JAW-JB-BJR-3852 | REJASARI_LANGENSARI | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANJAR | 6614903 | 2020-07-21 |  | 197 | > 150 days | 2020-12-18 | W51-2020 | Dec-2020 | 2020-12-17 | W51-2020 | Dec-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 532217742902 | 6.6 |  | 2020-10-06 |  |  | 2021-02-03 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : PSB released, PLN connection OG 17.12.20 : SRFIN sent 30.11.20 : erection done, SRFI 23.11.20 : prepare start erection 19.11.20 : plan issue solved dan CME start kembali 20 Nov 16.11.20 : 12.11.20 : 09.11.20 : 05.11.20 : pondasi bts ongoing, erection belum bisa dilakukan karena CME distop oleh pol pp 02.11.20 : 29.10.20 : 26.10.20 : pondasi BTS dan pagar ongoing, erection tower menunggu survey tim perijinan (plan survey hari ini) 22.10.20 : curring time, plan hari ini on site untuk start CME kembali 19.10.20 : curring time, stop pol PP karena issue opsic 12.10.20 : 08.10.20 : 05.10.20 : 01.10.20 : 28.09.20 : Curingtime, urugan tanah + pondasi bts OG, start erection tower waiting perijinan release 24.09.20 : curingtime 21.09.20 : rebarring done, plan cor hari ini 17.09.20 : on going excavation 14.09.20 : 10.09.20 : start excavation 07.09.20 : start CME menunggu IMB released 03.09.20 : 31.08.20 : kand A RF OK propose penurunan ketinggian menjadi tower 32 karena berada di runway LANUD, proses pengurusan KKOP (syarat rekom), realisasi IW ongoing 27.08.20 : realisasi IW, Disposisi Dinas PTSP penjadwalan rapat TKPRD untuk 3-Site sudah di ttd Kadis (CIBEUREUM_BANJAR, REJASARI_LANGENSARI, NEGLASARI_BANJAR), proses rekom on going 24.08.20 : plan selasa 25 Aug realisasi IW, plan rabu 26 Aug proses rekom 17.08.20 : 13.08.20 : proses eskalasi SITAC 10.08.20 : IW clear, proses finalisasi IW 06.08.20 : 03.08.20 : 27.07.20 : hunting
99 |  | KAL-KI-SMR-0756 | 30595660031 | 2314721003 | LEMPAKE_TIMUR | ACTIVE | TB | 117.2056 | -0.43439 | 50 | 80/230/300 | 2020 | JEDI 2020 [NEW] | Jl. Purwodadi Rt.44 Kel. Lempake Kec. Samarinda Utara Kota. Samarinda Prov. Kalimantan Timur | HTI | KAL-KI-SMR-0756 | LEMPAKE_TIMUR | B2S | TBG | JABO | KALIMANTAN | Kalimantan Timur | KOTA SAMARINDA | 6614816 | 2020-07-01 |  | 232 | > 150 days | 2020-11-28 | W48-2020 | Nov-2020 | 2020-12-15 | W51-2020 | Dec-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-12 | W07-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 231571776375 | 6.6 |  | 2020-10-06 |  |  | 2021-02-18 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.21 : RFI power by multiguna 21.01.21 : PSB released, PLN connection OG 21.01.21 : PSB released, proses connect PLN 28.12.20 : SRFIN sent 21.12.20 : 17.12.20 : 14.12.20 : 10.12.20 : 07.12.20 : erection ongoing 03.12.20 : pouring done, prepare start erection 26.11.20 : 23.11.20 : pengecoran 19.11.20 : setting angkur, pengecoran start 20 Nov 12.11.20 : prepare pengecoran, proses review design oleh konsultan 09.11.20 : 05.11.20 : 02.11.20 : rebarring, plan pouring start 2 Nov (isu longsor karena curah hujan tinggi) 29.10.20 : 26.10.20 : pouring ongoing, plan RFI 15 Nov 22.10.20 : 19.10.20 : 15.10.20 : plan pouring 18 oct 12.10.20 : rebarring, plan cor 20 oct 20 08.10.20 : excavation done, lantai kerja done, prepare rebarring, material besi KS on site 05.10.20 : on going excavation 01.10.20 : plan start galian dengan excavator 28.09.20 : bouwplank, plan start CME 30 sep 20 21.09.20 : 17.09.20 : KOM , preparation, plan start CME W1 oct 14.09.20 : 10.09.20 : 07.09.20 : proses design pack 03.09.20 : soiltest on going hari ini 31.08.20 : proses perijinan dan proses soiltest 27.08.20 : rekom done, status RFC, proses perijinan 24.08.20 :17.08.20 : 13.08.20 : on going rekom 10.08.20 : IW done total 15kk, plan rekom done minggu ini 06.08.20 : IW clear, proses eskalasi sitac 03.08.20 : 30.07.20 : IW on going 23.07.20 : cand A reviewed by TNP dengan MW height 51m dan diameter 0.6m, proses IW ONGOING 20.07.20 : kandidat A RNP OK, waiting TNP review 16.07.20 : submit kandidat A koordinat 117.205639, -0.438806 (jarak dr NOM 491m -> outSAR karena posisi NOM di atas bukit tidak ada akses jalan) under RNP review 13.07.20 : 09.07.20 : hunting 01.07.20 : SPK release
70 |  | SUM-SU-AKK-8002 | 30595700031 | 0223831003 | AEK KANOPAN TIMUR_HULU | ACTIVE | TB | 99.6551 | 2.5818 | 50 | 10/80/240 | 2020 | JEDI 2020 [NEW] | DUSUN II DESA LEDONG TIMUR KECAMATAN AEK LEDONG KABUPATEN ASAHAN PROVINSI SUMATERA UTARA | HTI | SUM-SU-AKK-8002 | AEK KANOPAN TIMUR_HULU | B2S | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. LABUHAN BATU UT | 6614816 | 2020-07-01 |  | 116 | 91 - 120 days | 2020-11-28 | W48-2020 | Nov-2020 | 2020-11-10 | W46-2020 | Nov-2020 | 2020-11-27 | W48-2020 | Nov-2020 | 2020-11-10 | W46-2020 | Nov-2020 | MW | 2020-10-01 |  | 125120717949 | 6.6 |  | 2020-10-05 |  |  | 2020-10-25 | W44-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.10.20 : RFIN sent 22.10.20 : aktual RFI, proses penyusunan dok RFIN 19.10.20 : proses penyambungan PLN 12.10.20 : erection done 08.10.20 : start erection 05.10.20 : curingtime 01.10.20 : 28.09.20 : borepile done, rebarring foundation 21.09.20 : IMB done, borepile 14.09.20 : 07.09.20 : 03.09.20 : 31.08.20 : rekom camat done, proses perijinan 27.08.20 : rekom camat done 24.08.20 : IW clear, proses eskalasi biaya sitac 17.08.20 : 13.08.20 : IW on going total 24 warga dan iw clear 8 kk, target IW clear total 18 agustus 20 10.08.20 : kandidat E TX OK, MW height 50m/0.6, IW on going 5kk/24kk, plan IW clear 18 Aug 06.08.20 : kandidat sebelumnya terkendala penolakan warga, submit kandidat baru (cand E) RF OK 50m, proses review TNP, paralel IW on going 03.08.20 : kandidat D OK RF 50m, proses review TNP, parelel IW on going 30.07.20 : Kandidat C IW failed, submit kandidat baru (cand D koordinat 99.6652, 2.58345) under RNP review 27.07.20 : review by TNP, paralel IW on going 23.07.20 : kandidat B terkendala issue penolakan warga, submit kandidat baru (cand C koordinat 99.6545, 2.58169) RND OK dgn RF 50m, proses validasi TNP 20.07.20 : kandidat B RNP approved RF 50m, menunggu review TNP 16.07.20 : Ok candidate B, tower 52 16.07.20 : kandidat A kendala penolakan IW, 13 Jul submit kandidat baru (B koordinat 99.65512, 2.58207 menunggu review RNP) 13.07.20 : 09.07.20 : RND NOT OK kand A karena far from nom and near existing, rehunting SAR<100m or east area from nom, rehunting B 10.07.20 : submit kand A 09.07.20 : on going survey, kandidat di pemukiman padat 01.07.20 : SPK release
108 |  | JAW-JB-BJR-3851 | 30570950031 | 1260741003 | MEKARSARI_BANJAR | ACTIVE | TB | 108.5325 | -7.3851 | 30 | 50/200/300 | 2020 | JEDI 2020 [NEW] | DUSUN PANGASINAN RT 1 RW 7 DESA BINANGUN KECAMATAN PATARUMAN KOTA BANJAR | HTI | JAW-JB-BJR-3851 | MEKARSARI_BANJAR | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANJAR | 6614369 | 2020-01-13 |  | 387 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-10-15 | W42-2020 | Oct-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 532217742910 | 6.6 |  | 2020-10-05 |  |  | 2021-02-03 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : PSB released, PLN connection OG 19.11.20 : SRFIN sent 12.11.20 : 09.11.20 : 05.11.20 : aktual SRFI, proses collect doc SRFIN 02.11.20 : ME installation 29.10.20 : 26.10.20 : erection ongoing 22.10.20 : curring time, plan hari ini on site untuk start CME kembali 19.10.20 : curring time, stop pol PP karena issue opsic 12.10.20 : 08.10.20 : 05.10.20 : 01.10.20 : 28.09.20 : Curingtime, urugan tanah + pondasi bts OG, start erection tower waiting perijinan release 24.09.20 : curingtime 21.09.20 : pouring concrete done, curingtime 17.09.20 : on going excavation 14.09.20 : 10.09.20 : start excavation 07.09.20 : 03.09.20 : berkas perijinan sudah masuk TPKRD dan sedang proses review 31.08.20 : 27.08.20 : submit berkas ke perijinan 26 Aug 20 (PTSP) dan sedang proses review 24.08.20 : 17.08.20 : CME belum dapat start karena isu perijinan kota banjar, CME ny start 13.08.20 : 10.08.20 : 06.08.20 : 03.08.20 : 27.07.20 : : 16.07.20 : CME belum dapat start karena isu perijinan kota banjar 13.07.20 : 09.07.20 : 06.07.20 : submit berkas perijinan, Plan RFC minggu ini, plan start CME 13 juli, plan SRFI 10 Aug 20 02.07.20 : baru submit berkas perijinan karena APD baru jadi, Plan RFC minggu depan, plan start CME 13 juli, plan SRFI 10 Aug 20 29.06.20 : proses perijinan 25.06.20 : 22.06.20 : 18.06.20 : soiltest done, ongoing proses rekom & perijinan 15.06.20 : request soiltest, kandidat F aktif, collecting doc/berkas legal untuk proses perijinan 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : 04.06.20 : IW OG Plan IW clear tgl 8 Juni 01.06.20 : Rekom, plan Hari ini RFC 22.05.20 : proses pembayaran Iw dan Rekom plan RFC 29 Mei 25.05.20 : 19.05.20 : submit kand E, RND Ok candidate E, tower 42 15.05.20 : TNP review 14.05.20 : 08.05.20 : IW on going, paralel submit kandidat alternatif 8 May 30.04.20 : Hunting arahan XL plan submit kandidat senin tgl 4 Mei 23.04.20 : 16.04.20 : 09.04.20 : validasi done, IW on going 02.04.20 : under review TNP 25.03.20 : 19.03.20 : 11.03.20 : IW on going 20.02.20 : 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
149 |  | JAW-JI-BLT-1916 | 30571120031 | 1642891003 | SANANWETAN_GEDOG | ACTIVE | TB | 112.1913 | -8.0988 | 40 | 110/230/300 | 2020 | JEDI 2020 [NEW] | JL. LETDA MARKAWI RT.003 RW.002, KELURAHAN GEDOG, KECAMATAN SANANWETAN, KOTA BLITAR, PROPINSI JAWA TIMUR | HTI | JAW-JI-BLT-1916 | SANANWETAN_GEDOG | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA BLITAR | 6614369 | 2020-01-13 |  | 297 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-10-25 | W44-2020 | Oct-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-11-10 | W46-2020 | Nov-2020 | MW | 2020-10-01 |  | MULTIGUNA |  |  | 2020-10-01 |  |  | 2020-11-05 | W45-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.11.20 : RFIN sent 02.11.20 : 29.10.20 : aktual SRFI, proses konek PLN (isu perluasan jaringan) 22.10.20 : 19.10.20 : erection on going 15.10.20 : curingtime, plan start erection 20 oct 20 12.10.20 : curingtime 08.10.20 : 05.10.20 : on going excavation 01.10.20 : start excavation 28.09.20 : 24.09.20 : IW done, rekom done, RFC 21.09.20 : TNP OK MW 40m/0.6, IW clear, rekom camat done kemarin 17.09.20 : re-validasi kandidat F propose penaikan tinggi tower menjadi SST 52, RNP OK -> RF 50m, proses review TNP, RND ok candidate F, tower 52, plan minggu depan start CME 14.09.20 : 10.09.20 : proses rehunting 07.09.20 : 03.09.20 : Review RND kand too far from NOM karena Perwali jarak antar menara, need submit JR & Perwali ke RND 31.08.20 : Reaktivasi SPK, validasi kand paralel IW clear 02.07.20 : MOM propose return, hard kandidat, terkait isu regulasi ketinggian tower 02.07.20 : IW on going, proses soswar forum 29.06.20 : 25.06.20 : plan start CME minggu depan 22.06.20 : 19.06.20 : perubahan type transport dari FO menjadi MW, need req SK PLN 18.06.20 : plan start CME 2 minggu kedepan, plan RFI end of July, on going proses soswar (IW) 15.06.20 : Proses soswar 11.06.20 : 08.06.20 : IW on going, soswar forum terkendala isu covid 04.06.20 : IW on going, soswar forum terkendala isu covid 01.06.20 : 28.05.20 : 25.05.20 : 14.05.20 : IW on going, soswar forum terkendala isu covid 08.05.20 : 30.04.20 : IW on going 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : 25.03.20 : IW on going, validasi done 19.03.20 : IW on going, need approval kandidat 11.03.20 : IW on going 24.02.20 = Kand B (S : 8° 05'59.61" E : 112° 11'26.08"), rehunting Cand. C langsung Pararel IW, Cand C Kurang 5 KK dr 9 KK plan clear 27.2.20 (need approval cand) 20.02.20 : IW On going, Kand C IW 8 KK sign 5 13.02.20 : TNP review 06.02.20 : kand A = validasi done, Candidate A RF TX OK
138 |  | JAW-JI-PSR-4139 | 30597220031 | 1644531003 | PURWOSARI_BAKALAN | ACTIVE | TB | 112.7549 | -7.7557 | 50 | 50/200/275 | 2020 | JEDI 2020 [NEW] | Dusun Keputran, RT 16 RW 04, Desa Bakalan, Kec. Purwosari, Kab. Pasuruan, Prov. Jawa Timur | HTI | JAW-JI-PSR-4139 | PURWOSARI_BAKALAN | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. PASURUAN | 6614889 | 2020-07-14 |  | 118 | 91 - 120 days | 2020-12-11 | W50-2020 | Dec-2020 | 2020-12-10 | W50-2020 | Dec-2020 | 2020-12-10 | W50-2020 | Dec-2020 | 2020-11-10 | W46-2020 | Nov-2020 | MW | 2020-10-06 |  | 513580973893 | 6.6 |  | 2020-09-28 |  |  | 2020-11-09 | W46-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.11.20 : RFIN sent 09.11.20 : 05.11.20 : PLN connected, proses penyusunan doc RFIN 02.11.20 : 29.10.20 : erection done, proses penyambungan PLN 26.10.20 : 22.10.20 : 19.10.20 : prepare start erection 15.10.20 : curingtime, plan start erection 20 oct 20 12.10.20 : galian done, lantai kerja done, prepare rebarring 08.10.20 : on going excavation 05.10.20 : start galian 01.10.20 : plan start CME 5 oct 28.09.20 : 24.09.20 : IW done, rekom done, RFC 21.09.20 : TNP OK 50m/1.2, IW ongoing, rekom lurah done, on going rekom camat 17.09.20 : kand E RF OK, proses review TNP, IW clear, proses rekom, soiltest done 10.09.20 : 07.09.20 : kand D IW fail (2KK menolak), proses mediasi paralel rehunting kandidat baru 03.09.20 : plan 3 Sep IW clear 31.08.20 : kand D RF OK -> 50m, TNP OK -> MW 50m/1.2, IW ongoing 27.08.20 : kandidat C RF OK, namun ada pergeseran sejauh 35m karena issue legalitas lahan, prepare submit kandidat 24.08.20 : submit kandidat B&C outSAR karena issue penolakan warga hingga radius 380m, under RNP review 17.08.20 : IW failed, rehunting kand B 13.08.20 : IW ongoing, plan hari ini clear soswar forum 10.08.20 : IW on going 06.08.20 : kandidat A koordinat (112.75494, -7.7565) RNP OK -> RF 50m, TNP OK -> MW 50m/1.2 03.08.20 : 30.07.20 : 27.07.20 : 23.07.20 : hunting
456 |  | JAW-JB-SMD-3730 | 30602170031 | TBG03_WJ268 | RANCAEKEK | ACTIVE | TB | 107°46.49.84'E | 6°57.11.84'S | 40 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Ds.Cinta Mulya Kp.Nagrak Rt.04/02 Sumedang | HTI | JAW-JB-SMD-3730 | CINTA MULYA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Sumedang | 6616241 | 2020-09-17 |  | 31 | 31 - 60 days | 2020-10-17 | W42-2020 | Oct-2020 | 2019-10-10 | W41-2019 | Oct-2019 | 2020-10-10 | W41-2020 | Oct-2020 | 2020-10-20 | W43-2020 | Oct-2020 | MW | 2020-10-01 |  | 535172016953 | 6.6 |  | 2020-09-25 |  |  | 2020-10-18 | W43-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.10.20 : aktual RFI, doc RFIN submitted 15.10.20 : 12.10.20 : Soft RFI, on going proses PLN connection 08.10.20 : mounting installation, plan material ME Grounding on site jumat 9 oct, PLN on process 05.10.20 : RBS foundation done, on going tray mounting installation 01.10.20 : 28.09.20 : mob demob & preparation 27.09.20 : proses input STIP 1 25.09.20 : STO declare 24.09.20 : review RND, upload ESR 21.09.20 : 18.09.20 : under power review 17.09.20 : SPK colo release
454 |  | JAW-JI-KRS-4252 | 30602160031 | 1644111001 | SUMBERBENDOTONGAS | ACTIVE | TB | 113°7.55.85'E | 7°46.22.44'S | 50 | 30/160/305 | 2020 | JEDI 2020 [NEW] | Dusun Kali Delu RT.025 RW.005 Desa Sumberbendo Kecamatan Sumberasih Kabupaten Probolinggo | HTI | JAW-JI-KRS-4252 | SUMBERBENDO_SUMBERASIH | COLO | TBG | EAST | JATIM | Jawa Timur | Kab. Probolinggo | 6616230 | 2020-09-11 |  | 140 | 121 - 150 days | 2020-10-11 | W42-2020 | Oct-2020 | 2020-10-10 | W41-2020 | Oct-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 513562154235 | 6.6 |  | 2020-09-25 |  | 2020-10-06 | 2021-01-29 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP Paid 21.01.21 : PSB released, PLN connection OG 06.10.20 : email SRFI-N sent 05.10.20 : SRFI actual, collecting doc SRFIN 01.10.20 : BTS foundation on going, plan SRFI 10 oct 28.09.20 : mob demob & preparation 27.09.20 : proses input STIP 1 25.09.20 : STO declare 24.09.20 : prepare STO dan preparation CME start 21.09.20 : under review Power 17.09.20 : RND dan TNP OK, prepare for STO and preparation CME start 11.09.20 : SPK colo released
159 |  | JAW-JI-TBN-4055 | 30571670031 | 1643441003 | SINGGAHAN_SARINGEMBAT | ACTIVE | TB | 111.7854 | -7.0278 | 40 | 10/210/290 | 2020 | JEDI 2020 [NEW] | Dsn Sambikerep RT 014 RW 05 Desa Tunggulrejo Kec Singgahan Kab Tuban | HTI | JAW-JI-TBN-4055 | SINGGAHAN_SARINGEMBAT | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. TUBAN | 6614369 | 2020-01-13 |  | 387 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-09-28 | W40-2020 | Sep-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 518070771463 | 6.6 |  | 2020-09-25 |  | 2020-09-30 | 2021-02-03 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP Paid, waiting KWH stock 21.01.21 : PSB released, PLN connection OG 30.09.20 : email SRFI-N sent 28.09.20 : 24.09.20 : erection done, ME og, pondasi bts dan pagar og 21.09.20 : cor done, curingtime 17.09.20 : lantai kerja done, rebarring ongoing 14.09.20 : excavation on going 10.09.20 : start excavation 07.09.20 : start CME paling lambat minggu ini 10 sept 20 03.09.20 : plan start CME minggu depan, pergeseran OK 31.08.20 : 27.08.20 : plan minggu ini sign dinas, plan CME start minggu depan. 24.08.20 : blm dpt sign dr dinas, tekait dampak dr issue covid di lingkungan dinas, dimana bbrp dinas hbs ketemu dg PLT bupati sidoarjo yg meninggal kemarin positive covid 17.08.20 : 13.08.20 : Sudah ada jaminan IMB terbit, plan start CME 20 Aug, secara peta baru sudah masuk lahan kuning, pemaparan mundur 19 Aug karena pic meninggal 10.08.20 : 06.08.20 : 03.08.20 : 23.07.20 : minggu lalu usulan TBG di setujui agar menjadi lahan alih fungsi namun harus pergeseran 50m, saat ini menunggu approval provinsi 16.07.20 : 13.07.20 : 06.07.20 : 02.07.20 : proses perijinan pengajuan perubahan lahan alih fungsi 29.06.20 : start CME terkendala aturan LP2B (LAHAN PERTANIAN PANGAN BERKELANJUTAN --> berdasarkan KEPRES), baru diketahui saat pemaparan lintas dinas (dinas pertanian) 25.06.20 : bouwplank, CME belum dapat start, menunggu proses perijinan lahan konservasi pertanian. 22.06.20 : 18.06.20 : 11.06.20 : 08.06.20 : bouwplank, proses perijinan, masuk lahan konservasi pertanian shg butuh pemaparan, plan pemaparan dituban minggu dpn 04.06.20 : 01.06.20 : 28.05.20 : bouwplank, proses perijinan 25.05.20 : 14.05.20 : bouwplank, proses perijinan 30.04.20 : bouwplank, proses perijinan 23.04.20 : 16.04.20 : 09.04.20 : proses perijinan, CME start after perijinan 02.04.20 : RFC, proses perijinan 25.03.20 : Proses perijinan, proses disposisi di Dinas pertanian 19.03.20 : 11.03.20 : 28.02.20 : Kand C = IW clear, proses submit eskalasi sitac, collecting legal doc 27.02.20 : Kand C = (-7.02602 111.78204), IW Clear 10 KK 20.02.20 : IW clear, need re approval candidat 13.02.20 : IW on going 06.02.20 : Kand C = RF OK, TX review 05.02.20 : kand C = submit C 111.78441 -7.0267 163.95 GF SST 42 In Cellplan Tuban 28.01.20 : kand A = RND 50 15/200/300 Ok candidate A, tower 52 27.01.20 : kand A = 111.78486 -7.029611 210.8 GF SST 42 In Cellplan Tuban kand B = 111.78683 -7.025611 289.35 GF SST 42 In Cellplan Tuban
118 |  | JAW-JI-KPN-4341 | 30597210031 | 1644521003 | NGANTANG_SIDODADI | ACTIVE | TB | 112.375 | -7.9047 | 50 | 140/235/300 | 2020 | JEDI 2020 [NEW] | Dusun Sekar RT 007 RW 001, Desa Sidodadi, Kec. Ngantang, Kab. Malang, Prov. Jawa Timur | HTI | JAW-JI-KPN-4341 | NGANTANG_SIDODADI | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. MALANG | 6614889 | 2020-07-14 |  | 106 | 91 - 120 days | 2020-12-11 | W50-2020 | Dec-2020 | 2020-10-10 | W41-2020 | Oct-2020 | 2020-12-10 | W50-2020 | Dec-2020 | 2020-10-28 | W44-2020 | Oct-2020 | MW | 2020-09-10 |  | 513090217800 | 6.6 |  | 2020-09-14 |  | 2020-09-30 | 2020-10-28 | W44-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29.10.20 : RFIN sent 28 Oct 26.10.20 : aktual RFI, proses penyusunan doc RFIN 22.10.20 : PLN connected, proses penyusunan doc RFIN 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 : Surat Jawaban PLN release, status jaringan PLN Overblust trafo 87% dan perluasan jaringan, revisi plan RFI 28 oct 20 05.10.20 : 01.10.20 : 30.10.20 : SRFIN sent, ada isu selisih daya PLN dan sedang di fu Surat Jawaban PLN 28.09.20 : 24.09.20 : erection on going 21.09.20 : cor done, curingtime, plan start erection 24 sept 17.09.20 : lantai kerja done, rebarring ongoing 14.09.20 : 10.09.20 : on going excavation 07.09.20 : 03.09.20 : bouwplank, paralel perijinan 31.08.20 : rekom done, submit berkas perijinan 27.08.20 : proses penjadwalan soiltest 24.08.20 : on going review eskalasi biaya sitac, plan realisasi 27 aug 17.08.20 : TNP OK MW height 50m/1.2, IW clear, proses eskalasi sitac 13.08.20 : kandidat C IW failed, submit kandidat baru (cand E) RF OK 50m, proses review TNP 10.08.20 : IW on going 06.08.20 : kandidat C (koordinat 112.37642, -7.90486) RNP OK -> RF 50m, TNP OK -> MW 50m/1.2 03.08.20 : rehunting 30.07.20 : NOM memiliki histori hardcommcase, kandidat A& B (outSAR >500m) yg disubmit NOK by RND karena terlalu jauh dari NOM 27.07.20 : 23.07.20 : hunting
82 |  | JAW-JI-PCT-4185 | 30571320031 | 1643091003 | KEBONAGUNG_KATIPUGAL | ACTIVE | TB | 111.1635 | -8.2484 | 40 | 90/180/300 | 2020 | JEDI 2020 [NEW] | DUSUN KLEPU RT.001 RW.007, DESA KATIPUGAL, KECAMATAN KEBONAGUNG, KABUPATEN PACITAN, PROPINSI JAWA TIMUR | HTI | JAW-JI-PCT-4185 | KEBONAGUNG_KATIPUGAL | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. PACITAN | 6614369 | 2020-01-13 |  | 421 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-10-20 | W43-2020 | Oct-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-03-29 | W14-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 515421485861 | 13.2 |  | 2020-09-14 |  | 2020-09-30 | 2021-03-09 | W11-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.03.21 : PLN connected, NY RFIN -> plan 08/3 18.02.21 : PLN connection daya 13.2 kVA, material PLN NY ready, revise RFI plan W2 Mar 26.01.21 : proses register, waiting PLN survey, Revise RFI Plan W2 Mar 21.01.21 : PSB released, PLN connection OG 30.09.20 : SRFIN sent 28.09.20 : 24.09.20 : curingtime 21.09.20 : plan cor hari ini 17.09.20 : lantai kerja done, rebarring ongoing 14.09.20 : 10.09.20 : rekom done, status RFC, start excavation 07.09.20 : 03.09.20 : RND OK kand C, tower 52m, TNP OK 31.08.20 : Reaktivasi SPK, validasi kand paralel IW clear 02.07.20 : MOM propose return, hard kandidat, terkait isu regulasi ketinggian tower 02.07.20 : IW on going, proses soswar door to door 29.06.20 : 25.06.20 : XL meminta untuk segera start CME minggu depan 22.06.20 : compile IW by WAG, issue pembatasan akses dr luar daerah, plan start CME 2 minggu kedepan, plan RFI end of July 18.06.20 : plan start CME 2 minggu kedepan, plan RFI end of July 15.06.20 : pembatasan akses dari luar daerah compile IW by WAG 11.06.20 : 08.06.20 : IW on going 04.06.20 : IW on going 01.06.20 : 28.05.20 : 25.05.20 : 14.05.20 : IW on going 08.05.20 : 30.04.20 : IW OG, paralel proses revalidasi 23.04.20 : 16.04.20 : 09.04.20 : continue iw on going 02.04.20 : IW on going soswar door to door terkendala isu COVID 19 25.03.20 : IW on going soswar door to door 24.03.20 : Cand. B Prepare Soswar Tanggal 18 di Balai Desa Dibatalkan. Akan Sosialisasi Door to Door tanggal 24 Maret (Larangan untuk soswar forum ) 19.03.20 : IW on going, need approval kandidat 11.03.20 : IW on going 28.02.20 : 24.02.20 : kand A (S : 8°14'49.9" E : 111°09'49.30") 4 KK Sign 3 KK, cand B IW OG , soswar 27.2.20 20.02.20 : IW Clear, proses eskalasi sitac, recheck isu ketinggian penurunan dari 52 (failed) ke 42 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
210 |  | SUM-BE-KPH-0196 | 30597800031 | 0902941003 | TUGU REJO | ACTIVE | TB | 102.6347 | -3.5845 | 50 |  | 2020 | JEDI 2020 [NEW] | Jl.Makam Dusun I, Desa Sumber Sari, Kec. Kabawetan, Kab. Kepahiang, Prov. Bengkulu | HTI | SUM-BE-KPH-0196 | TUGU REJO | B2S | TBG | WEST | LAMPUNG | Bengkulu | Kepahiang | 6615571 | 2020-08-18 |  | 92 | 91 - 120 days | 2021-01-15 | W03-2021 | Jan-2021 | 2020-09-28 | W40-2020 | Sep-2020 | 2020-10-15 | W42-2020 | Oct-2020 | 2020-11-30 | W49-2020 | Nov-2020 | MW | 2020-09-07 |  | 146205124126 | 6.6 |  | 2020-09-11 |  |  | 2020-11-18 | W47-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.11.20 : RFIN sent 23.11.20 : PLN multiguna connected 19.11.20 : proses konek PLN multiguna, PLN permanen masih menunggu jawaban dari PLN wilayah S2JB 09.11.20 : 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : 22.10.20 : proses BPUJL 19.10.20 : 15.10.20 : 12.10.20 : SRFI actual, proses PLN Connection 08.10.20 : Erection OG, target SRFI: 12 Oct 2020, nomor register PLN NY Release, sudah disurati kembali ke PLN, plan besok sudah release no register nya 05.10.20 : curingtime 01.10.20 : pouring concrete 28.09.20 : rebarring on going 24.09.20 : plan cor mundur karena terkendala cuaca (hujan), plan besok cor 21.09.20 : rebarring, plan cor selasa 22 sep 20 17.09.20 : rebarring 14.09.20 : start excavation menggunakan excavator 10.09.20 : RFC, CME preparation 07.09.20 : proses APD 03.09.20 : rekom done 2 Sept, plan soiltest 3 Sept 31.08.20 : rekom ongoing, paralel proses soiltest 27.08.20 : IW clear kand C, proses approval eskalasi sitac 24.08.20 : pergeseran kandidat 30m paralel IW ongoing, kandidat baru (cand C) RF TX OK 13.08.20 : submit kandidat A&B, RNP OK -> RF 50m kand A, proses review TNP 03.08.20 : SPK release
209 |  | SUM-BE-KPH-0197 | 30597790031 | 0902931003 | UJAN MAS PEKALONGAN | ACTIVE | TB | 102.5213 | -3.5313 | 60 |  | 2020 | JEDI 2020 [NEW] | Jl.Lintas Curup-Kepahiang, Gg.Harjo, Dusun VI, Desa Pekalongan, Kec. Ujan Mas, Kab.Kepahiang, Prov. Bengkulu | HTI | SUM-BE-KPH-0197 | UJAN MAS PEKALONGAN | B2S | TBG | WEST | LAMPUNG | Bengkulu | Kepahiang | 6615571 | 2020-08-18 |  | 92 | 91 - 120 days | 2021-01-15 | W03-2021 | Jan-2021 | 2020-09-28 | W40-2020 | Sep-2020 | 2020-10-15 | W42-2020 | Oct-2020 | 2020-11-30 | W49-2020 | Nov-2020 | MW | 2020-09-07 |  | 146102411537 | 6.6 |  | 2020-09-11 |  |  | 2020-11-18 | W47-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03.12.20 : RFIN sent 23.11.20 : 19.11.20 : proses konek PLN multiguna, PLN permanen masih menunggu jawaban dari PLN wilayah S2JB 09.11.20 : 05.11.20 :02.11.20 : 29.10.20 : 26.10.20 : 22.10.20 : proses BPUJL 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 : SRFI, nomor register PLN NY Release, sudah disurati kembali ke PLN, plan besok sudah release no register nya 05.10.20 : ME on going 01.10.20 : erection done, ME & grounding installation 28.09.20 : erection on going 24.09.20 : curingtime 21.09.20 : plan cor hari ini 17.09.20 : rebarring 14.09.20 : start excavation menggunakan excavator 10.09.20 : RFC, CME preparation 07.09.20 : APD percepatan done 03.09.20 : plan soiltest 2 Sept 31.08.20 : rekom done, proses soiltest 27.08.20 : proses realisasi IW 24.08.20 : TNP OK MW 60m/0.6 , IW clear, proses eskalasi sitac 13.08.20 : submit kandidat A (koordinat 102.52293, -3.53069) RNP OK -> RF 60m, proses review TNP 03.08.20 : SPK release
9 |  | JAW-JB-BJR-3850 | 30570940031 | 1260731003 | BALOKANG_BANJAR | ACTIVE | TB | 108.5132 | -7.372 | 40 | 0/110/270 | 2020 | JEDI 2020 [NEW] | Dsn. Cibeureum Rt.008 / Rw 003 Desa Balokang Kec Banjar Kota Banjar,Jawa Barat. | HTI | JAW-JB-BJR-3850 | BALOKANG_BANJAR | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANJAR | 6614369 | 2020-01-13 |  | 385 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-09-25 | W39-2020 | Sep-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 532217742433 | 6.6 |  | 2020-09-11 |  | 2020-09-30 | 2021-02-01 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : PSB released, PLN connection OG 01.10.20 : 30.09.20 : SRFIN sent 28.09.20 : 28.09.20 : SRFI, finishing F&Y, paralel collecting doc RFIN plan submit 30 sep 20 24.09.20 : 21.09.20 : erection done, on going fence & yard, ME on going 17.09.20 : erection on going 14.09.20 : plan start CME (continue erection) 15 sep 20 11.09.20 : erection done 10.09.20 : Mob demob plan sabtu 12 sep 20 07.09.20 : 03.09.20 : Rapat TPKRD done, plan start CME minggu ini (paling lambat kamis dimaksimalkan sudah start CME) 31.08.20 : 27.08.20 : sudah dapat disposisi dari bu wali & kepala ptsp, koordinasi fu jadwal rapar tkprd (plan kamis depan), plan start CME kembali 7 sep (last progress on going erection) 24.08.20 : 17.08.20 : 13.08.20 : tinjauan lokasi/survey done, waiting disposisi untuk continue CME, CME cor pondasi done 10.08.20 : 06.08.20 : 03.08.20 : proses koordinasi penjadwalan survey dan rapat TKPRD 30.07.20 : 27.07.20 : 16.07.20 : CME belum dapat start karena isu perijinan kota banjar 09.07.20 : 06.07.20 : 02.07.20 : plan start cme lagi 13 jul 20, plan SRFI end of Juli 29.06.20 : 22.06.20 : 18.06.20 : CME (erection) masih STOP karena isu perijinan 11.06.20 : 08.06.20 : 04.06.20 : 01.06.20 : erection tower masih STOP by satpol PP, wait perijinan 28.05.20 : 25.05.20 : 21.05.20 : 14.05.20 : erection 1 section STOP by perijinan 08.05.20 : pouring concrete 30.04.20 : excavation 23.04.20 : 16.04.20 : proses rekom 09.04.20 : realisasi IW dan rekom 02.04.20 : pembayaran IW dan rekom on going 25.03.20 : TNP review 19.03.20 : 11.03.20 : IW on going 20.02.20 : 13.02.20 : IW on going 06.02.20 : Kand A = RF OK, TX review
178 |  | KAL-KS-MRH-0891 | 30595680031 | 2208191003 | TABUNGANEN PEMURUS | ACTIVE | TB | 114.4514 | -3.4222 | 60 | 100/180/270 | 2020 | JEDI 2020 [NEW] | JL. DESA TABUNGANEN PEMURUS, RT.011, KECAMATAN TABUNGANEN, KABUPATEN BARITO KUALA, PROPINSI KALIMANTAN SELATAN. | HTI | KAL-KS-MRH-0891 | TABUNGANEN PEMURUS | B2S | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | KAB. BARITO KUALA | 6614816 | 2020-07-01 |  | 117 | 91 - 120 days | 2020-11-28 | W48-2020 | Nov-2020 | 2020-11-27 | W48-2020 | Nov-2020 | 2020-11-27 | W48-2020 | Nov-2020 | 2020-10-26 | W44-2020 | Oct-2020 | MW | 2020-09-07 |  | 221500517292 | 6.6 |  | 2020-09-08 |  |  | 2020-10-26 | W44-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29.10.20 : RFIN sent 26 Oct 26.10.20 : 22.10.20 : aktual SRFI, proses penyambungan PLN 19.10.20 : erection done, finishing pondasi BTS 15.10.20 : Tower painting dan Pondasi BTS OG. Plan Kamis SRFI 12.10.20 : erection top tower 08.10.20 : Erection OG, PLN perluasan Jaringan dan Mgmnt Trafo 05.10.20 : prepare erection, plan start erection besok 6 oct 20 01.10.20 : curingtime, plan start erection 5 oct 30.09.20 : pouring done 28.09.20 : rebaring plan Cor 29/09 24.09.20 : 21.09.20 : 17.09.20 : on going cerucuk 14.09.20 : 10.09.20 : on going borepile 07.09.20 : plan bouwplank tanggal 10 sep 03.09.20 : plan bouwplank besok jumat dan start galian 31.08.20 : masih Issue perijinan sehingga cme blm bisa start krn jarak dari bangunan sebelah masih tidak sesuai perda 27.08.20 : plan bouwplank dan plan start CME W1 sep 20, isu perda 2x radius tower tidak boleh ada rumah, max tinggi tower yg di ijinkan 58m, need revalidasi TNP 24.08.20 : start CME menunggu menunggu jadwal survey perijinan 17.08.20 : 13.08.20 : plan start CME W34 10.08.20 : proses design pack dan collect berkas perijinan 06.08.20 : rekom done, proses soiltest 03.08.20 : proses rekom L/C ongoing 30.07.20 : realisasi IW done, proses rekom L/C ongoing 23.07.20 : proses realisasi IW, plan rekom 27 Jul 16.07.20 : 13.07.20 : IW on going 11.07.20 : TNP OK kand A 09.07.20 : submit kandidat A propose SST 62, menunggu review RNP 01.07.20 : SPK release
98 |  | JAW-JI-LMG-4275 | 30571150031 | 1642921003 | LAMONGAN_BANJARMENDALAN | ACTIVE | TB | 112.4273 | -7.1144 | 30 | 0/90/250 | 2020 | JEDI 2020 [NEW] | KADEK SUWOKO 45, RT002 RW 001, DESA SIDOREJO, KEC. DEKET, KAB. LAMONGAN | HTI | JAW-JI-LMG-4275 | LAMONGAN_BANJARMENDALAN | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. LAMONGAN | 6614369 | 2020-01-13 |  | 238 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-29 | W31-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-09-07 | W37-2020 | Sep-2020 | MW | 2020-07-21 |  | 518031744443 | 6.6 |  | 2020-09-07 |  |  | 2020-09-07 | W37-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.09.20 : RFIN sent 07.09.20 : perapihan F&Y, plan hari ini declare RFIN 03.09.20 : 31.08.20 : 27.08.20 : RFI actual 26 Aug, collecting doc RFIN 24.08.20 : 17.08.20 : SRFI 14 Aug, plan RFI 25 Aug 13.08.20 : plan SRFI 14 Aug, plan RFI 25 Aug 10.08.20 : 06.08.20 : on going erection 03.08.20 : 23.07.20 : lantai kerja dan pembesian OG 16.07.20 : galian pondasi 13.07.20 : prepare team 06.07.20 : 02.07.20 : proses perijinan, plan start CME W2 Juli 29.06.20 : plan start CME W2 Juli or drop 25.06.20 : plan start CME minggu depan 22.06.20 : plan start CME June, plan RFI end July, eskalasi sitac approved, need new design kamuflase dengan PTS 19.06.20 perubahan type transport dari FO menjadi MW, need req SK PLN 18.06.20 : plan start CME June, plan RFI end July 15.06.20 : 11.06.20 : isu cell plan, approved outcell dg tower kamuflase, proses design on going, plan RFC 24 jun 20, , plan SRFI/RFI Juli 20 08.06.20 : 04.06.20 : IW clear, proses rekom, isu regulasi 01.06.20 : 28.05.20 : 25.05.20 : 14.05.20 : IW clear, proses rekom, isu regulasi 08.05.20 : 30.04.20 : IW clear, proses rekom, isu regulasi 23.04.20 : TNP review 16.04.20 : IW clear, isu regulasi 09.04.20 : iw clear, proses pengajuan eskalasi sitac 02.04.20 : 25.03.20 : proses pengajuan design Camuflase dan Koordinasi Kominfo 19.03.20 : 11.03.20 : 28.02.20 : Kand D = IW Clear, proses eskalasi sitac, collecting legal doc 22.02.20 : Kand D = IW Clear 8 kk, propsoe camuflase ( cellplan ) 20.02.20 : IW On going 13.02.20 : TNP review 06.02.20 : kand A = validasi done, Candidate A RF TX OK 28.01.20 : kand A = RND 30 0/70/225 28Jan20 : Ok candidate A, tower 32 27.01.20 : kand A = 112.42694 -7.116028 GF SST 32 Out Cellplan. Pengajuan Permohonan pertimbangan Cellplan OG kand B = 112.42839 -7.105469 995.23 GF SST 32 Kandidat Out SAR namun dalam cellplan. Perda terlampir
450 |  | SUM-JA-MBN-0482 | 30599180031 | 060098104 | DURIAN_LUNCUK | ACTIVE | SMI | 102°59.52.73'null | 1°52.47.1'S | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | RT 08 Kel. Durian Luncuk, Kab Batanghari, kec Bathin XXIV | HTI | SUM-JA-MBN-0482 | DURIAN LUNCUK | COLO | TBG | WEST | SUMBAGSEL | Jambi | Kab. Batanghari | 6616152 | 2020-08-31 |  | 21 | < 30 days | 2020-09-30 | W40-2020 | Sep-2020 | 2020-09-28 | W40-2020 | Sep-2020 | 2020-09-28 | W40-2020 | Sep-2020 | 2020-09-28 | W40-2020 | Sep-2020 | MW | 2020-09-07 |  | 143509425468 | 6.6 |  | 2020-09-01 |  |  | 2020-09-21 | W39-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.09.20 : RFIN sent 17.09.20 : pondasi on going 14.09.20 : comcase, on going proses penyelesaian 13.09.20 : Tray, mounting OG target done 14/9/20, Pondasi OG, BP Done plan connect 17/9/20 10.09.20 : Prepare Team dan Material Panel on delivery, plan Start CME 11/9/20, ETA Material panel 11/9/20 07.09.20 : mobilisasi
176 |  | KAL-KB-MPW-0708 | 30588030031 | 2006881003 | SUNGAIPURUNKECIL | ACTIVE | TB | 109.1345 | 0.23162 | 40 | 90/180/270 | 2020 | JEDI 2020 [NEW] | RT 021/RW 010, Desa Peniraman, Kecamatan Sungai Pinyuh, Kab. Mempawah, Prov. Kalimantan Barat | HTI | KAL-KB-MPW-0708 | SUNGAIPURUNKECIL | B2S | TBG | JABO | KALIMANTAN | Kalimantan Barat | KAB. MEMPAWAH | 6614568 | 2020-03-19 |  | 168 | > 150 days | 2020-08-16 | W34-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-30 | W36-2020 | Aug-2020 | MW | 2020-06-12 |  | 211101609728 | 6.6 |  | 2020-09-01 |  | 2020-08-30 | 2020-09-03 | W36-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03.09.20 : RFIN sent 31.08.20 : 30.08.20 : RFI actual, collecting doc RFIN 27.08.20 : ME on going, F&Y on going 24.08.20 : erection on going, revisi plan RFI 30 Aug 17.08.20 : start erection 18/08 Revisi plan RFI 25/08 13.08.20 : 10.08.20 : 06.08.20 : curingtime 03.08.20 : Rebaring OG,Plan Cor 03 Aug 23.07.20 : on going borepile, plan cor pondasi 31 jul 16.07.20 : plan start galian excavator 13.07.20 : 09.07.20 : CME stop by LL, proses review legal doc & paralel nego di ijinkan continue pekerjaan CME 02.07.20 : 29.06.20 : 25.06.20 : plan isu clear dan start CME W1 jul 22.06.20 : Comcase, Borepile stop (CME Stop), proses negosiasi, plan RFI 25 juli (plan percepatan 15 jul) 18.06.20 : Comcase, Borepile stop (CME Stop), proses negosiasi, plan RFI 25 juli (plan percepatan 15 jul) 17.06.20 : Go RFI, PSB PLN release 15.06.20 : on going borepile 11.06.20 : 08.06.20 : 06.06.20 : Team Plan Onsite, preparation CME start 04.06.20 : 01.06.20 : bouwplank 28.05.20 : rekom on going, paralel tim CME plan on site 28 may untuk preparation CME 25.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : rekom og 23.04.20 : 16.04.20 : IW clear, proses eskalasi sitac 09.04.20 : 07.04.20 : submit kand C, RND OK tower 52m, wait TNP review 06.04.20 : RND review 02.04.20 : rehunting sesuai arahan 27.03.20 : Validasi Kand A dan B 25.03.20 : Hunting by Mitra NOM masuk dalam kawasan PT. Perkebunan 20.03.20 : STIP Released
451 |  | SUM-SS-PKB-1239 | 30599170031 | 071054109 | SUMSEL2014_2G33 | ACTIVE | TB | 104°53.37.64'null | 2°33.28.3'S | 60 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jalur 5 Telang Desa. Marga Rahayu, Kec.Muara Telang, Kab.Banyuasin | HTI | SUM-SS-PKB-1239 | MAKARTI JAYA | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | Kab. Banyuasin | 6616133 | 2020-08-27 |  | 40 | 31 - 60 days | 2020-09-26 | W39-2020 | Sep-2020 | 2020-09-28 | W40-2020 | Sep-2020 | 2020-09-28 | W40-2020 | Sep-2020 | 2020-10-05 | W41-2020 | Oct-2020 | MW | 2020-09-07 |  | 142401778212 | 6.6 |  | 2020-08-31 |  |  | 2020-10-06 | W41-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.10.20 : 05.10.20 : RFIN sent 01.10.20 : plan submit RFIN hari ini 30.09.20 : RFI actual, plan RFIN hari ini 28.09.20 : ME on going, plan RFI 28 Sep 20 24.09.20 : Start BTS foundation, delivery material 21.09.20 : 17.09.20 : plan start CME senin 21 Sep 14.09.20 : plan start CME, 14/9/20 10.09.20 : Prepare Team dan Material, plan start CME 13/9/20 07.09.20 : mobilisasi
449 |  | SUM-JA-MBN-0480 | 30599160031 | 060549109 | API_TEBING TINGGI PEMAYUNG | ACTIVE | TB | 103°20.7.8'null | 1°38.6.22'S | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | JALAN DESA TEBING TINGGI, KELURAHAN TEBING TINGGI, KEC.PEMAYUNG, KAB.BATANG HARI, PROPINSI JAMBI | HTI | SUM-JA-MBN-0480 | PEMAYUNG | COLO | TBG | WEST | SUMBAGSEL | Jambi | Kab. Batanghari | 6616133 | 2020-08-27 |  | 25 | < 30 days | 2020-09-26 | W39-2020 | Sep-2020 | 2020-09-28 | W40-2020 | Sep-2020 | 2020-09-28 | W40-2020 | Sep-2020 | 2020-09-28 | W40-2020 | Sep-2020 | MW | 2020-09-07 |  | 143509425450 | 6.6 |  | 2020-08-31 |  |  | 2020-09-21 | W39-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.09.20 : RFIN sent 17.09.20 : SRFI, hari ini plan PLN connect 14.09.20 : tray dan Mounting done, Pondasi on Finishing, BP done plan connect Kamis 17/9/20 10.09.20 : Prepare Team dan Material, plan start CME 13/9/20 07.09.20 : mobilisasi
166 |  | JAW-JI-MJK-4140 | 30571210031 | 1642981003 | SOOKO_JAMPIROGO | ACTIVE | TB | 112.4203 | -7.5123 | 30 | 0/90/200 | 2020 | JEDI 2020 [NEW] | Dusun Sambiroto RT 03 RW 02, Desa Sambiroto, Kec. Sooko Kab. Mojokerto, Prov. Jawa Timur | HTI | JAW-JI-MJK-4140 | SOOKO_JAMPIROGO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. MOJOKERTO | 6614369 | 2020-01-13 |  | 266 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-09-30 | W40-2020 | Sep-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-10-01 | W40-2020 | Oct-2020 | MW | 2020-08-10 |  | 514521503408 | 41.5 |  | 2020-08-31 |  | 2020-09-07 | 2020-10-05 | W41-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.10.20 : RFIN sent (MULTIGUNA) 01.10.20 : plan connect MG hari ini dan declare RFIN 28.09.20 : 24.09.20 : 21.09.20 : 17.09.20 : Proses PLN connection, survey PLN done, menunggu surat jawaban PLN terkait isu up daya karena perluasan jaringan, revisi plan RFI 30 sep 14.09.20 : 10.09.20 : ada perluasan jaringan, potensi up daya dan sedang menunggu hasil survey PLN, plan RFI 19 sept 07.09.20 : SRFIN sent, plan PLN connect 10 sept 03.09.20 : 31.08.20 : SRFI, proses PLN Connection 27.08.20 : erection on going 24.08.20 : 17.08.20 : curingtime, pouring concrete 15 aug 13.08.20 : excavation, plan cor 15 aug 10.08.20 : 06.08.20 : rekom L/C done, confirm kandidat E (112.418906, -7.511394) dijalankan, prepare CME 03.08.20 : 23.07.20 : plan sign doc legal malam ini, plan submit doc dan plan bisa di jadwalkan join survey senin depan, plan start CME 29 jul 13.07.20 : 02.07.20 : proses perijinan, plan start CME W2 Juli 29.06.20 : plan start CME W2 Juli or drop 25.06.20 : plan start CME minggu depan 19.06.20 : perubahan type transport dari FO menjadi MW, need req SK PLN 22.06.20 : 18.06.20 : proses perijinan, plan start CME awal July, plan RFI end of July 15.06.20 : IW clear, realisasi IW, request soiltest, proses perijinan 11.06.20 : 08.06.20 : IW clear, pengajuan eskalasi sitac 04.06.20 : IW on going, perlu soswar forum 01.06.20 : 28.05.20 : 25.05.20 : 14.05.20 : IW on going, perlu soswar forum 08.05.20 : 30.04.20 : IW on going, perlu soswar forum 23.04.20 : TNP review 16.04.20 : 09.04.20 : wait TNP review 06.04.20 : RND OK 02.04.20 : IW on going 25.03.20 : IW failed keponakan LL (Kades) sendiri bersama 4 KK lainnya menyatakan tdk setuju, BA proses / rehunting 19.03.20 : IW on going, need approval kandidat 11.03.20 : IW on going 26.02.20 : kand D = (7° 30'47.36"S 112°25'10.91"E) BAN proses, IW on going 25.02.20 : Kand D = done submit, Kand. A B C penolakan LL 20.02.20 : Kand A B Reject , rehunting cand C 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
85 |  | JAW-JI-PBL-2911 | 30571250031 | 1643021003 | KEDOPOK_JREBENG_WETAN | ACTIVE | TB | 113.2123 | -7.7822 | 40 | 60/180/270 | 2020 | JEDI 2020 [NEW] | RT 002 RW 002 DESA JREBENG KULON KEC. KEDOPOK KOTA PROBOLINGGO | HTI | JAW-JI-PBL-2911 | KEDOPOK_JREBENG_WETAN | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA PROBOLINGGO | 6614369 | 2020-01-13 |  | 388 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-18 | W34-2020 | Aug-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 513562155053 | 6.6 |  | 2020-08-31 |  | 2020-09-01 | 2021-02-04 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP paid, need perluasan jaringan penambahan 4 tiang 21.01.21 : PSB released, PLN connection OG 01.09.20 : email SRFI-N sent 24.08.20 : collecting doc SRFIN 18.08.20 : soft RFI, collecting doc SRFIN 10.08.20 : erection 06.08.20 : curingtime, plan start erection 8 Aug 20 03.08.20 : 23.07.20 : galian OG 16.07.20 : start galian 13.07.20 : 02.07.20 : proses perijinan, plan start CME W2 Juli 29.06.20 : plan start CME W2 Juli or drop 25.06.20 : plan start CME minggu depan 22.06.20 : 18.06.20 : proses perijinan, plan start CME awal July, plan RFI end of July 15.06.20 : request Soiltest, IW clear, proses perijinan 11.06.20 :08.06.20 : IW clear, pengajuan eskalasi sitac 04.06.20 : IW on going, soswar door to door 01.06.20 : 28.05.20 : 25.05.20 : 14.05.20 : IW on going, soswar door to door 08.05.20 : 30.04.20 : IW on going, soswar door to door 23.04.20 : RND review 09.04.20 : IW on going 02.04.20 : 25.03.20 : IW on going 19.03.20 : IW on going, need approval kandidat, validasi RND OK kand C, wait TNP review 11.03.20 : IW on going 26.02.20 : target submit BAN done, plan IW clear 29-02 ( soswar ) 20.02.20 : IW On going 13.02.20 : TNP review 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
197 |  | SUM-SU-PMS-2108 | 30587350031 | 0223681003 | TOTAP MAJAWA | ACTIVE | TB | 99.1295 | 2.8996 | 50 | 70/200/300 | 2020 | JEDI 2020 [NEW] | HUTA IV TETAP REJO NAGORI TOTAP MAJAWA, KECAMATAN TANAH JAWA, KABUPATEN SIMALUNGUN, PROVINSI SUMATERA UTARA | HTI | SUM-SU-PMS-2108 | TOTAP MAJAWA | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KAB. SIMALUNGUN | 6614554 | 2020-03-13 |  | 167 | > 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-08-09 | W33-2020 | Aug-2020 | 2020-08-31 | W36-2020 | Aug-2020 | MW | 2020-08-10 |  | 121170456604 | 6.6 |  | 2020-08-26 |  | 2020-08-13 | 2020-08-27 | W35-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.08.20 : RFIN sent 27.08.20 : plan connect PLN/RFI hari ini 24.08.20 : 13.08.20 : SRFIN sent 06.08.20 : erection on going 03.08.20 : 27.07.20 : RFC, proses perijinan 23.07.20 : proses perijinan 13.07.20 :09.07.20 : rekom done 8 jul, proses collect berkas perijinan 06.07.20 : plan rekom camat done hari ini 02.07.20 : masih on going rekom camat, ada permasalahan disurat tanah sehingga camat belum mau ttd dan sedang di follow up terkait surat tanah 29.06.20 : on going rekom camat, proses rekom terkendala camatnya sedang tidak ada ditempat dan selasa baru pulang ke simalungun dari tugas dinas ke kuar kota. 25.06.20 : Rekom dan Soiltest plan done besok 22.06.20 : 18.06.20 : eskalasi approved, proses rekom on going, plan rekom done akhir bulan ini, start CME setelahada survey perijinan 15.06.20 : 11.06.20 : izin warga done, proses review dan validasi eskalasi sitac 11.06.20 : izin warga done. plan start CME awal juli 08.06.20 : 04.06.20 : 02.06.20 : sudah dapat arahan, plan besok 3 juni join survey dengan mitra (internal TBG) 01.06.20 : renego iw, paralel rehunting kand alternatif, plan submit kand minggu ini 28.05.20 : rehunting, gagal IW 25.05.20 : 21.05.20 : 14.05.20 : TNP OK Cand E,izin warga on going dikandidat baru sisa 4 kk lgi 08.05.20 : izin warga on going dikandidat baru 30.04.20 : .iw on going, terkendala dilokasi banjir 23.04.20 : TNP review 16.04.20 : gagal IW, paralel penhajuan new kandidat 09.04.20 : IW OG kurang 8kk, plan IW clear 12 Apr 06.04.20 : 02.04.20 : IW on going 25.03.20 : TNP review, paralel IW On going
71 |  | KAL-KS-KGN-0876 | 30595000031 | 2208171003 | KANDANGAN KOTA | ACTIVE | TB | 115.2813 | -2.7916 | 50 | 25/155/225 | 2020 | JEDI 2020 [NEW] | Jalan Brigjen H Hasan Baseri, Gang Padang Baru, RT/RW.001/01, Kelurahan Kandangan Kota, Kecamatan Kandangan, Kabupaten Hulu Sungai Selatan, Propinsi Kalimantan Selatan | HTI | KAL-KS-KGN-0876 | KANDANGAN KOTA | B2S | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | KAB. HULU SUNGAI SEL | 6614769 | 2020-06-23 |  | 90 | 61 - 90 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-09-25 | W39-2020 | Sep-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-09-25 | W39-2020 | Sep-2020 | MW | 2020-09-07 |  | 222200212249 | 6.6 |  | 2020-08-25 |  |  | 2020-09-21 | W39-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.09.20 : RFIN sent 21.09.20 : RFI actual, collect RFIN doc 17.09.20 : 14.09.20 : erection tower, plan minggu ini connect PLN 10.09.20 : erection on going 07.09.20 : Cor done 05/09 dan Curing Time, plan RFI 25 sep 20 03.09.20 : material angkur on site, plan cor minggu 6 sept 31.08.20 : rebarring on going 27.08.20 : excavation & cerucuk done, on going lantai kerja, bar bending & preparation rebarring, plan RFI 20 sep 24.08.20 : 17.08.20 : on going excavation, plan cor 26 Aug 13.08.20 : on going excavation, plan cor 26 Aug 10.08.20 : proses design pack dan collect berkas perijinan 06.08.20 : rekom done, proses soiltest 03.08.20 : proses rekom L/C ongoing 30.07.20 : realisasi IW done, proses rekom L/C ongoing 23.07.20 : proses realisasi IW, plan rekom 27 Jul 16.07.20 : kandidat A RF TX OK, proses IW ongoing 13.07.20 : 11.07.20 : TNP OK kand A 09.07.20 : submit 7 Juli kandidate A koordinat 115.28131, -2.79061 propose SST 42, waiting review RNP 02.07.20 : Hunting, plan minggu depan submit kandidat 29.06.20 : Hunting 23.06.20 : SPK Release 23 jun 20
146 |  | SUM-RI-PBR-1148 | 30571740031 | 0413801003 | SAIL_TENAYAN RAYA | ACTIVE | TB | 101.5382 | 0.51624 | 50 | 70/200/280 | 2020 | JEDI 2020 [NEW] | Jl. Badak RT.004 RW.003, Kel. Tuah Negeri, Kec. Tenayan Raya, Kota Pekanbaru, Provinsi Riau | HTI | SUM-RI-PBR-1148 | SAIL_TENAYAN RAYA | B2S | TBG | WEST | SUMBAGTENG | Kep. Bangka Belitung | KOTA PEKANBARU | 6614369 | 2020-01-13 |  | 230 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-16 | W34-2020 | Aug-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-08-29 | W35-2020 | Aug-2020 | MW | 2020-07-01 |  | 181101776401 | 6.6 |  | 2020-08-25 |  |  | 2020-08-30 | W36-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31.08.20 : 30.08.20 : RFIN sent 29.08.20 : RFI actual, collecting doc RFIN 27.08.20 : 24.08.20 : 22.08.20 : revisi plan connect PLN/RFI tanggal 29 Aug setelah penambahan 8 tiang 17.08.20 : 16.08.20 : Soft RFI, wait PLN connection dengan penambahan pole PLN, plan RFI 21 Aug 13.08.20 : 10.08.20 : Kekurangan material Plat ETA hr ini , start continue erection, PLN Proses Prepare material jaringan, plan SRFI 16 Aug, plan RFI 21 Aug 06.08.20 : erection on going 03.08.20 : plan on site kekurangan plat kopel tower besok 3 jul 30.07.20 : 27.07.20 : erection stop karena terkendala minus plat kopel tower dr pabrikan, plan material dikirim besok dari pabrikator 23.07.20 : erection on going, PLN register done, menunggu laporan hasil survey PLN 20.07.20 : curingtime, Backfill done, Prepare Erection 02.07.20 : rebarring, plan cor 3 jul 30.06.20 : change transport type menjadi MW, request SK PSB PLN untuk continue PLN Connectionnya 29.06.20 : rebarring on going 25.06.20 : excavation done, on going lantai kerja, prepare rebarring 22.06.20 : on going excavation 18.06.20 : start galian, proses perijinan 15.06.20 : 11.06.20 : 08.06.20 : rekom done, proses submit berkas 04.06.20 : 28.05.20 : 14.05.20 : IW clear, proses approval eskalasi sitac 23.04.20 : 16.04.20 : revalidasi kand A NOK, propose reloc NOM 09.04.20 : 02.04.20 : revalidasi kand A 27.03.20 : validasi done kand B 25.03.20 : 19.03.20 : 05.03.20 : 01.03.20 : Lahan Pemkot Pekanbaru, masih tahap pembangunan belum bisa dilakukan sewa ke pihak lain hingga proses serah terima asset ke Pemkot. Kandidat diluar lahan Pemkot yg telah di approved XL ternyata sengketa saat ini sdg proses banding pengadilan tinggi. Dan informasi yg di dapat bahwa tanah Sekitar Perkantoran Pemkot Pekanbaru akan di akuisisi oleh pemkot untuk perluasan kawasan Perkantoran Pemkot 28.02.20 : 20.02.20 : rehunting 17.02.20 : submit kand A di lahan Pemkot Pekan Baru, RND kandidat A not approve, arahan rehunting ke tikor berikut : 101.531406, 0.515776 13.02.20 : 06.02.20 : Hunting kandidat
76 |  | JAW-JI-PCT-4182 | 30571300031 | 1643071003 | KARANGTURI_SUDIMORO | ACTIVE | TB | 111.3988 | -8.2618 | 50 | 0/120/240 | 2020 | JEDI 2020 [NEW] | DUSUN KARANGREJO RT.003 RW.011 DESA SUMBEREJO KEC. SUDIMORO KAB. PACITAN PROP. JAWA TIMUR | HTI | JAW-JI-PCT-4182 | Karangturi_Sudimoro | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. PACITAN | 6614369 | 2020-01-13 |  | 249 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-29 | W31-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-09-15 | W38-2020 | Sep-2020 | MW | 2020-06-29 |  | 515421483468 | 6.6 |  | 2020-08-21 |  | 2020-09-01 | 2020-09-18 | W38-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18.09.20 : RFIN sent (MULTIGUNA) 17.09.20 : RFI Multiguna connect, plan PLN permanen akhir bulan 14.09.20 : 10.09.20 : 07.09.20 : 03.09.20 : 03.09.20 : 01.09.20 : SRFIN sent 31.08.20 : 27.08.20 : 24.08.20 : PLN connection menunggu review add work PLN by Power eng XL (eskalasi isu besar daya PLN terkait isu BP vs Biaya Investasi PLN) 17.08.20 : 06.08.20 : eskalasi isu besar daya PLN terkait isu BP vs Biaya Investasi PLN 23.07.20 : SRFI actual, collecting doc SRFIN, on going proses PLN Connection 16.07.20 : erection on going 13.07.20 : Urugan done, team erection onsite, tower sortir, pagar onsite 06.07.20 : on going cor pondasi 02.07.20 : rebarring, plan cor 3 jul 29.06.20 : rebarring don, prepare cor, sortir material tower 25.06.20 : rebarring 19.06.20 : perubahan type transport dari FO menjadi MW, need req SK PLN 18.06.20 : prepare galian, proses perijinan 15.06.20 : 08.06.20 : Rekom on going, DESIGN PROSES ,COLLECT DOC RFL AND PKS, IW CLEAR, plan RFI 24 jun 20, plan SRFI/RFI Juli 20 11.06.20 : plan RFI 24 jun 20, plan SRFI/RFI Juli 20 08.06.20 : DESIGN PROSES ,COLLECT DOC RFL AND PKS, IW CLEAR 04.06.20 : IW clear, proses submit eskalasi sitac 01.06.20 : 28.05.20 : 21.05.20 : 14.05.20 : IW clear, proses submit eskalasi sitac 08.05.20 : TNP review 30.04.20 : IW on going 23.04.20 : 16.04.20 : 09.04.20 : IW on going 02.04.20 : 25.03.20 : 19.03.20 : resoswar warga luar ( mediasi warga ) 11.03.20 : 28.02.20 : IW Clear 13 KK, proses review eskalasi sitac dan collecting legal doc 25.02.20 : IW Clear 13 KK, proses submit eskalasi sitac 20.02.20 : 13.02.20 : Kand B = Rehunting 06.02.20 : Kand A = RF OK, TX review 31.01.20 : Kand A : TNP NOK, site isolated, arahan rehunting ke -8.25971137 ; 111.3965053
123 |  | JAW-JB-SOR-3831 | 30590110031 | 1262021003 | PANUNDAAN_CIWIDEY | ACTIVE | TB | 107.4356 | -7.1058 | 40 | 70/210/330 | 2020 | JEDI 2020 [NEW] | Kp. Babakan Lampit, RT.01/07, Desa Panundaan, Kec.Ciwidey, Kab.Bandung Jawa Barat | HTI | JAW-JB-SOR-3831 | PANUNDAAN_CIWIDEY | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614612 | 2020-04-03 |  | 109 | 91 - 120 days | 2020-08-31 | W36-2020 | Aug-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-07-20 | W30-2020 | Jul-2020 | MW | 2020-06-12 |  | 535322066954 | 6.6 |  | 2020-08-14 |  | 2020-07-15 | 2020-07-21 | W30-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.07.20 : RFIN sent 20.07.20 : actual RFI, collecting doc RFIN 16.07.20 : PLN connection masih terkendala isu stock kwh meter kosong 15.07.20 : email SRFI-N sent 13.07.20 : PLN connection masih terkendala isu stock kwh meter kosong 09.07.20 : 06.07.20 : 02.07.20 : Soft RFI, collecting doc SRFIN, proses PLN connection 29.06.20 : ME on going 22.06.20 : erection on going 18.06.20 : cor done, curingtime 17.06.20 : Go RFI, PSB PLN release 11.06.20 : on going excavation 08.06.20 : start excavation 04.06.20 : 01.06.20 : proses perijinan 29.05.20 : plan hari ini RFC dan start proses perijinan 28.05.20 : 25.05.20 : 14.05.20 : Proses Rekom plan done tgl 15 Mei 08.05.20 : Proses pembayaran IW dan Rekom 30.04.20 : IW OG kurang 2 KK dari 25 KK 23.04.20 : 16.04.20 : IW on going 09.04.20 : 06.04.20 : Hunting
201 |  | JAW-JB-SOR-3839 | 30590160031 | 1262071003 | WARGALUYU_ARJASARI | ACTIVE | TB | 107.6118 | -7.0399 | 40 | 30/120/240 | 2020 | JEDI 2020 [NEW] | Kp. Pasir Malang Rt.02 Rw.08, Desa Lebak Wangi, Kecamatan Arjasari, Kab.Bandung | HTI | JAW-JB-SOR-3839 | WARGALUYU_ARJASARI | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614612 | 2020-04-03 |  | 129 | 121 - 150 days | 2020-08-31 | W36-2020 | Aug-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-15 | W33-2020 | Aug-2020 | MW | 2020-06-12 |  | 535342135933 | 6.6 |  | 2020-08-14 |  | 2020-05-10 | 2020-08-10 | W33-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.08.20 : RFIN sent 03.08.20 : RFI actual dengan Multiguna, collecting doc RFIN 30.07.20 : erection og, pondasi bts og, me og, plan percepatan PLN multiguna 27.07.20 : start erection 23.07.20 : curing time 16.07.20 : 13.07.20 : on going galian pondasi 09.07.20 : start galian pondasi 06.07.20 : CME/galian stop by ormas, isu perijinan, plan solve dan continue CME besok 7 jul02.07.20 : comcase bloking ormas terkait perijinan. sedang proses negosiasi. pekerjaan baru mau gali, plan kerja kembali 6/7 29.06.20 : 22.06.20 : site clearing, plan gali besok 23 jun 18.06.20 : 17.06.20 : Go RFI, PSB PLN release, prepare material & team 11.06.20 : prepare material & team 08.06.20 : 04.06.20 : proses perijinan 01.06.20 : 29.05.20 : rekom on going, plan hari ini RFC dan start proses perijinan 28.05.20 : 25.05.20 : rekom on going 14.05.20 : finalisasi eskalasi sitac, plan start realisasi sitac dan proses rekom 08.05.20 : IW OG ada kendala Warga narik dukungan finalisasi Sabtu pertemuaan 30.04.20 : IW OG plan IW clear Tgl 3 mei 23.04.20 : 16.04.20 : IW on going 09.04.20 : 06.04.20 : Hunting
188 |  | SUM-KR-BTM-0584 | 30589560031 | 0506141003 | TANJUNG BANUN REMPANG | ACTIVE | TB | 104.2126 | 0.81342 | 50 | 0/100/270 | 2020 | JEDI 2020 [NEW] | Tanjung Banom RT.01 RW.05 Kel.Sembulang Kec.Galang Kota Batam Prov.Kepulauan Riau | HTI | SUM-KR-BTM-0584 | TANJUNG BANUN REMPANG | B2S | TBG | WEST | SUMBAGTENG | Kep. Riau | Kep. Riau | 6614591 | 2020-03-27 |  | 159 | > 150 days | 2020-08-24 | W35-2020 | Aug-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-09-10 | W37-2020 | Sep-2020 | MW | 2020-05-20 |  | 153000353907 | 6.6 |  | 2020-08-14 |  |  | 2020-09-02 | W36-2020 |  | 2020-09-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02.09.20 : RFIN sent 31.08.20 : 27.08.20 : 24.08.20 : waiting review & approval sharing cost addtional PLN Bright Batam by XL Power Eng, revisi plan RFI 10 sept 17.08.20 : waiting review & approval sharing cost addtional PLN Bright Batam by XL Power Eng 12.08.20 : eskalasi isu pengajuan sharing cost add work trafo 50 kvA (167 juta) PLN Bright Batam le XL (Pak Imam) 10.08.20 : PP BPRAB PLN Bright release (Rp 160jt) tetapi msh minus layout dan Detail RAB utk eskalasi ke XL, eskalasi sharing cost ke XL, plan RFI 21 Aug jika minggu ini approved by XL 06.08.20 : 03.08.20 : PLN connection terkendala isu PLN Bright 30.07.20 : SRFI actual, Proses Surat Jawaban/BPRAB Bright msh blm released karena sdg Proses RAB internal Bright 27.07.20 : ME on going, plan SRFI 28 jul, wait PLN Connection 23.07.20 : ME on going, PLN register done, menunggu laporan hasil survey PLN 20.07.20 : Tower erection done, Pondasi BTS OG 13.07.20 : erection done, on going pondasi BTS, isu PLN bright hrs ada surat hibah, sudah surevy PLN, BPRAB blm release krn belum ada hibah yg belum di tandatngani LL (Polisi), plan RFI 28 juli 02.07.20 : on going erection 6 section 29.06.20 : on going erection tower 25.06.20 : erection start 24/06 22.06.20 : cor done 20/6, curingtime 18.06.20 : rebarring, persiapan cor 15.06.20 : rebarring 11.06.20 : galian done, on going lantai kerja & bar bending 08.06.20 : 04.06.20 : start galian 01.06.20 : bar bending, plan start galian 2 jun 20, plan pick up tower 2 jun 20 28.05.20 : wait team & preparation 25.05.20 : 20.05.20 : plan start galian after lebaran, isu penambahan new trafo 14.05.20 : eskalasi sitac Approved, proses cek doc Legalitas lahan 23.04.20 : 16.04.20 : proses negosiasi/BAN karena high price, paralel IW on going 09.04.20 : 07.04.20 : TNP OK kand A tower 62m 03.04.20 : RND OK kand A tower 62m 25.03.20 : hasil assessment : 1. Titik NOM Masuk dalam kawasan Hutan Konservasi 2. Jarak 650m dari titik NOM kearah Jalan Umum base on Street View tidak ada Jaringan Listrik
154 |  | KAL-KB-SBS-0706 | 30588050031 | 2006901003 | SELAKAUTUA | ACTIVE | TB | 109.06 | 1.0247 | 40 | 20/210/270 | 2020 | JEDI 2020 [NEW] | Dusun Pangkalan Asam, RT.010 RW.002, Desa Sungai Daun, Kecamatan Selakau, Kabupaten Sambas, Provinsi Kalimantan Barat | HTI | KAL-KB-SBS-0706 | SELAKAUTUA | B2S | TBG | JABO | KALIMANTAN | Kalimantan Barat | KAB. SAMBAS | 6614568 | 2020-03-19 |  | 143 | 121 - 150 days | 2020-08-16 | W34-2020 | Aug-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-11-27 | W48-2020 | Nov-2020 | MW | 2020-06-12 |  | 212000728344 | 6.6 |  | 2020-08-14 |  |  | 2020-08-09 | W33-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.08.20 : RFIN sent 06.08.20 : 03.08.20 : Erection OG, Pondasi BTS, ME, pagar, OG, Plan PLN 3 Aug 23.07.20 : curingtime, plan start erection 25 jul 20.07.20 : pouring concrete 16.07.20 : cerucuk done, on going rebarring pondasi 13.07.20 : 09.07.20 : on going cerucuk, terkendala cuaca Hujan hampir setiap hari dan langsiran mutar sungai (jauh), plan cor 14 jul, plan erection done 23 jul, plan RFI 25 jul 02.07.20 : borepile done, on going cerucuk start 30 jun (4 hari) plan lantai kerja 4 jul, plan cor 8 jul, material tower on going langsir 29.06.20 : 22.06.20 : bouwplank, Proses langsir Material, akses sementara lewat sungai, plan cor 30 jun 18.06.20 : prepare start CME, langsir material to site, proses bangun jembatan akses sementara melintasi sungai 17.06.20 : Go RFI, PSB PLN release 15.06.20 : 11.06.20 : 08.06.20 : 06.06.20 : Team Plan Onsite, preparation CME start 04.06.20 : 01.06.20 : bouwplank 28.05.20 : rekom on going, paralel tim CME plan on site 28 may untuk preparation CME 25.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : rekom og 23.04.20 : 16.04.20 : IW on going 09.04.20 : 07.04.20 : submit kand C, RND OK tower 52m, wait TNP review 02.04.20 : 01.04.20 : TNP OK, IW on going 31.03.20 : RND OK 25.03.20 : hunting
20 |  | JAW-JB-NPH-3709 | 30587450031 | 1261831003 | BOJONGHALEUANG_SAGULING | ACTIVE | TB | 107.4588 | -6.8755 | 30 | 90/190/330 | 2020 | JEDI 2020 [NEW] | Kp.Cikonde, RT 001 RW 03, Desa Bojonghaleuang, Kec. Saguling, Kab Bandung Barat, Jawa Barat | HTI | JAW-JB-NPH-3709 | BOJONGHALEUANG_SAGULING | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614560 | 2020-03-16 |  | 150 | 121 - 150 days | 2020-08-13 | W33-2020 | Aug-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-15 | W33-2020 | Aug-2020 | MW | 2020-07-01 |  | 535852112649 | 6.6 |  | 2020-08-14 |  |  | 2020-08-13 | W33-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.08.20 : RFIN sent 10.08.20 : collecting doc RFIN, plan declare RFIN 15 Aug 03.08.20 : RFI actual 30.07.20 : erection & painting, pondasi bts done, me og, plan percepatan PLN multiguna 27.07.20 : tower erection 23.07.20 : curingtime 16.07.20 : galian done, proses perapihan galian dan lantai kerja 13.07.20 : on going galian 09.07.20 : 06.07.20 : CME/galian stop by ormas, isu perijinan, plan solve dan continue CME besok 7 jul, SK PLN release 02.07.20 : comcase bloking ormas terkait perijinan. galian stop dan sedang proses negosiasi, plan kerja kembali 6/7 30.06.20 : change transport type menjadi MW, request SK PSB PLN untuk continue PLN Connectionnya 29.06.20 : 22.06.20 : 18.06.20 : on going excavation 11.06.20 : start excavation 08.06.20 : prepartion team 04.06.20 : preparation team untuk start CME 01.06.20 : CME preparation plan start 2 jun (besok) 28.05.20 : 25.05.20 : Rekom, APD/BOQ approved 14.05.20 : 08.05.20 : Proses pembayaran IW dan Rekom 30.04.20 : IW OG plan IW clear sabtu tgl 2 Mei plan submit eskalasi minggu 30.04.20 : IW on going 23.04.20 : 16.04.20 : rehunting 09.04.20 : rehunting 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 25.03.20 : Rehunting
172 |  | KAL-KS-PLI-0916 | 30587270031 | 2208111003 | SUMBERJAYA_ | ACTIVE | TB | 115.3024 | -3.8455 | 40 | 110/180/290 | 2020 | JEDI 2020 [NEW] | Jl. A. Yani RT.008 RW.003 Desa Sungai Cuka, Kecamatan Kintap, Kabupaten Tanah Laut, Provinsi Kalimantan Selatan | HTI | KAL-KS-PLI-0916 | SUMBERJAYA | B2S | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | KAB. TANAH LAUT | 6614554 | 2020-03-13 |  | 144 | 121 - 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-08-05 | W32-2020 | Aug-2020 | MW | 2020-06-12 |  | 223300243260 | 6.6 |  | 2020-08-14 |  |  | 2020-08-04 | W32-2020 |  | 2020-08-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.08.20 : 04.08.20 : RFIN sent 03.08.20 : collecting doc RFIN, plan submit 5 aug 30.07.20 : RFI actual done dengan connect PLN Multiguna, collectong doc RFIN 23.07.20 : PLN connection process, plan connect 28 jul 22.07.20 : SRFI actual, collecting doc SRFIN 16.07.20 : on going erection section 7 13.07.20 : on going erection section 5 09.07.20 : Erection OG - Section 1, Survey PLN done 02.07.20 : cor done 28 jun, curing time, material tower delivery dr pelabuhan site, plan malam ini on site, plan start erection jumat 3 jul 29.06.20 : 22.06.20 : rebaring & angkur setting done, persiapan cor, plan cor besok 23 jun, Plan Erection 27 juni 18.06.20 : excavation on going 17.06.20 : Go RFI, PSB PLN release 15.06.20 : excavation on going 11.06.20 : 08.06.20 : excavation, prepare start CME, plan SRFI 30 jun 06.06.20 : Team onsite 06/06, Galian Menggunakan Excavator 04.06.20 : 01.06.20 : bouwplank, start CME 28.05.20 : proses perijinan on going, paralel tim CME plan on site 1 juni untuk preparation CME 25.05.20 : 14.05.20 : 08.05.20 : proses perijinan 30.04.20 : 23.04.20 : 16.04.20 : rekom done, doc completion for IMB apply 09.04.20 : IW on going 02.04.20 : 30.03.20 : IW clear 8 KK, Eskalasi capex 25.03.20 : RF & TX OK, IW on going 17.3.20 : Submit Kandidat A Lat. -3,84463 Long : 115,3031 to HO 20.3.20 : Kand A Approval Operator 23.3.20 : BAN Done 15 jt/th, IW ongoing 24.3.2020 : BAN 15Jt/th, IW Total 7 KK 1 KK belum ttd target IW clear tanggal 25.3.2020
40 |  | JAW-JI-PCT-4180 | 30571290031 | 1643061003 | DONOROJO_SENDANG | ACTIVE | TB | 110.9444 | -8.2177 | 50 | 30/180/330 | 2020 | JEDI 2020 [NEW] | Dusun Kendal, RT.01 RW.4, Desa Sendang, Kecamatan Donoroo, Kabupaten Pacitan, Propinsi Jawa Timur | HTI | JAW-JI-PCT-4180 | DONOROJO_SENDANG | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. PACITAN | 6614369 | 2020-01-13 |  | 199 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-29 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | MW | 2020-06-24 |  | 515421453239 | 6.6 |  | 2020-08-14 |  |  | 2020-07-30 | W31-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30.07.20 : RFIN sent 23.07.20 : SRFI actual, collecting doc SRFIN, on going proses PLN Connection 16.07.20 : erection on going 13.07.20 : urugan done, team erection onsite, hold dp lahan, plan start erection jumat 06.07.20 : backfilling, curing time, plan start erection 7 jul 02.07.20 : rebarring, plan cor 3 jul 29.06.20 : rebaring done, prepare for pouring, wait angkur template plan sortir tower hari ini 25.06.20 : rebaring done, prepare for pouring, wait angkur template 18.06.20 : persiapan galian dengan excavator, proses perijinan 15.06.20 : Design process, collect dok RFL & PKS, rekom process 11.06.20 :08.06.20 : IW clear, proses submit eskalasi sitac, soiltest, collect legal doc 04.06.20 : IW clear, proses submit eskalasi sitac 01.06.20 : 28.05.20 : 21.05.20 : 14.05.20 : IW clear, proses submit eskalasi sitac 08.05.20 : TNP review 30.04.20 : IW on going, paralel penyelesaian comcase 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : IW on going 25.03.20 : plan resoswar hari ini tidak dapat dilanjutkan karena isu corona 19.03.20 : resoswar warga luar ( mediasi warga ) 11.03.20 : 28.02.20 : 24.02.20 : Resoswar cand IW Clear , dampak provokasi dari warga luar 20.02.20 : IW clear, IW 11 KK , renego paralel pengajuan biaya 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
90 |  | JAW-JI-BLT-1910 | 30571100031 | 1642871003 | KEPANJEN_KIDUL_KAUMAN | ACTIVE | TB | 112.1561 | -8.0888 | 40 | 100/200/310 | 2020 | JEDI 2020 [NEW] | Jl. Kali Ngebel RT.004 RW.01 Kelurahan Tanjungsari, Kecamatan Sukorejo, Kota Blitar, Propinsi Jawa Timur | HTI | JAW-JI-BLT-1910 | KEPANJEN_KIDUL_KAUMAN | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA BLITAR | 6614369 | 2020-01-13 |  | 210 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-14 | W33-2020 | Aug-2020 | 2020-10-13 | W42-2020 | Oct-2020 | 2020-08-25 | W35-2020 | Aug-2020 | MW | 2020-07-21 |  | 514021875421 | 6.6 |  | 2020-08-14 |  |  | 2020-08-10 | W33-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.08.20 : RFIN sent 06.08.20 : SRFI, proses PLN connection 03.08.20 : 23.07.20 : erection on going 20.07.20 : curing time, plan start erection vesok 16.07.20 : rebarring 13.07.20 : mobilisasi excavator, delivery material besi pondasi, sortir tower material 06.07.20 : plan start continue galian 7 jul 02.07.20 : excavation hold 29.06.20 : 25.06.20 : 22.06.20 : 18.06.20 : excavation stop, proses penyelesaian isu dengan LL 11.06.20 : CME continue 08.06.20 : curingtime 04.06.20 : 28.05.20 : 25.05.20 : 14.05.20 : curingtime 13.05.20 ; cor done, urugan done, pond bts done,pond pagar done, tower plan 13/5 mos, tim erect os 08.05.20 : 30.04.20 : proses design/bouwplank dan apply perijinan 23.04.20 : 16.04.20 : IW done, proses rekom dan soiltest 09.04.20 : 02.04.20 : 25.03.20 : IW clear, harga BAN tetap, LL tidak mau di nego, proses validasi biaya sitac 19.03.20 : 11.03.20 : IW clear, proses renego dan validasi biaya sitac 28.02.20 : 25.02.20 : IW Clear, proses review eskalasi sitac 20.02.20 : IW Clear, proses submit eskalasi sitac 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
37 |  | JAW-JI-PBL-8117 | 30571280031 | 1643051003 | DINAS_PERTANIAN_KANIGARAN | ACTIVE | TB | 113.2007 | -7.7561 | 30 | 0/90/270 | 2020 | JEDI 2020 [NEW] | Jl. Supriyadi Rt. 002 Rw. 009 Kelurahan Kanigaran Kecamatan Kanigaran Kota Probolinggo | HTI | JAW-JI-PBL-8117 | DINAS_PERTANIAN_KANIGARAN | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA PROBOLINGGO | 6614369 | 2020-01-13 |  | 388 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-20 | W34-2020 | Aug-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 513562155046 | 6.6 |  | 2020-08-14 |  | 2020-09-01 | 2021-02-04 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP paid, perluasan jaringan 1 tiang kabel 90m OG 21.01.21 : PSB released, PLN connection OG 01.09.20 : email SRFI-N sent 24.08.20 : SRFI actual 17.08.20 : pouring concrete 10.08.20 : rebarring 06.08.20 : realisasi IW done, proses rekom done 23.07.20 : email CANCEL RETURN by XL, IW clear, proses realisasi IW, plan SRFI end of Aug 02.07.20 : MOM propose return, hard kandidat, terkait isu regulasi ketinggian tower 02.07.20 : IW on going, proses soswar forum 29.06.20 : 25.06.20 : XL meminta untuk segera start CME minggu depan 25.06.20 : ketinggian 32m NOK, RND propose 42m namun kendala di IW 22.06.20 : kandidat B approved by RND, nego propose ketinggian menara SST 32 karena kendala di proses IW dalam radius PT. Eratex, plan start CME 2 minggu kedepan, plan RFI end of July 18.06.20 : plan start CME 2 minggu kedepan, plan RFI end of July 15.06.20 : cand approved by operator, issue zona menara, IW on going 11.06.20 : 08.06.20 : IW on going 04.06.20 : IW on going 01.06.20 : 28.05.20 : 25.05.20 : 14.05.20 : IW on going 08.05.20 : 30.04.20 : rehunting 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : 25.03.20 : rehunting 19.03.20 : propose colo, need JR 20.02.20 : 13.02.20 : 06.02.20 : Hunting kandidat 28.01.20 : propose colo ke site Pilang 7°45'11.41"S 113°11'56.40"E Not OK oleh RND, continue Hunting
11 |  | KAL-KS-KGN-0875 | 30587260031 | 2208101003 | BARU_ | ACTIVE | TB | 115.2121 | -2.8387 | 50 | 40/160/240 | 2020 | JEDI 2020 [NEW] | Jl. Desa Baru RT.004 RW.002, Desa Baru, Kecamatan Sungai Raya, Kabupaten Hulu Sungai Selatan, Provinsi Kalimantan Selatan | HTI | KAL-KS-KGN-0875 | BARU | B2S | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | KAB. HULU SUNGAI SEL | 6614554 | 2020-03-13 |  | 199 | > 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-09-25 | W39-2020 | Sep-2020 | 2020-08-08 | W32-2020 | Aug-2020 | 2020-09-27 | W40-2020 | Sep-2020 | MW | 2020-06-12 |  | 222200212264 | 6.6 |  | 2020-08-12 |  |  | 2020-09-28 | W40-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.09.20 : RFIN sent 28.09.20 : RFI actual, collecting doc RFIN, plan submit 28 sep 24.09.20 : 21.09.20 : 17.09.20 : PLN Connection, PLN baru install Trafo dan Perluasan jaringan, plan RFI 25 sep 20 Blocking PLN Connection, PLN baru install Trafo dan Perluasan jaringan 14.09.20 : SRFI actual 10.09.20 : erection on going, plan RFI actual dalam minggu ini 12 sep 07.09.20 : on going erection (terkendala hujan setiap hari) 03.09.20 : erection section 3 31.08.20 : curingtime 27.08.20 : pouring concrete done 26 Aug, curing time, plan RFI 10 sep 20 24.08.20 : rebarring, plan cor 24 aug, plan RFI 5 sept 17.08.20 : plan cor mundur 22 Aug karena kondisi cuaca, plan RFI 30 Aug 13.08.20 : 10.08.20 : rebarring plan cor 18 Aug 03.08.20 : Rebaring OG,Plan Cor 03 Aug 23.07.20 : on going rebarring, plan cor 25 jul 16.07.20 :13.07.20 : borepile on going 09.07.20 : plan bouwplang 9 jul, proses perijinan Done (SKRD tinggal pembayaran), Plan CME : Borpile 09/07 - plan finish 12/07, Galian Plan Menggunakan Excavator 13/07, Cerucuk 14/07, Rebaring 15/07 - Plan Finish 18/07, Pouring 19/07. Curingtime 22/07, Erection 22/07 - Plan Finish 27/07, ME 25/07, Grounding 26/07. 02.07.20 : besok soiltest karena pergeseran 28m berdasarkan hasil survey dinas Tata Ruang Kota,. plan APD rabu depan 8 jul, plan start CME Jumat 10 jul, plan RFI W1 Jul (8 Aug 20) 29.06.20 : 22.06.20 : Bowplank done, borepile terkendala dengan Camat yang meminta perijinan tower, perijinan tower on progress, join survey dengan kominfo : done, rekom kominfo akan keluar paling lambat 2 hari kedepan 18.06.20 : bouwplank, proses perijinan, prepare start CME, plan SRFI 30 jun, KS dari Banjar 17.06.20 : Go RFI, PSB PLN release 15.06.20 : 11.06.20 : 08.06.20 : bouwplank, prepare start CME, plan SRFI 30 jun, KS dari Banjar, Delivery Material Tower Plan 12/06 (Corgo Godres), Angkur By Air 04.06.20 : 01.06.20 : bouwplank, start CME 28.05.20 : on going perijinan, paralel tim CME plan on site 1 juni untuk preparation CME 25.05.20 : 14.05.20 : 08.05.20 : proses perijinan 30.04.20 : 23.04.20 : 16.04.20 : rekom done, doc completion for IMB apply 09.04.20 : rev RND 08.04.20 : submit kand 09.04.20 : 08.04.20 : submit kand C, wait RND dan TNP review 06.04.20 : wait review TNP, plan SRFI end Juni 02.04.20 : Penolakan 1 warga luar radius dan geser 50 Meter, pararel validasi kembali 30.03.20 : eskalasi capex 25.03.20 : IW Clear 10 kk, Eskalasi SITAC 25.03.20 : RF & TX OK, IW on going 18.3.20 : Submit Kandidat A Lat. -2,83869 Long : 115,21286 to HO 20.3.20 : Kand A Approval Operator 23.3.20 : BAN 13 Juta/Tahun IW Clear dari Total 10 KK 24.3.2020 : IW Clear dari Total 10 KK
23 |  | JAW-JI-BTU-4110 | 30571130031 | 1642901003 | BUMIAJI_SUMBERBRANTAS | ACTIVE | TB | 112.5277 | -7.7622 | 50 | 0/160/270 | 2020 | JEDI 2020 [NEW] | Dusun jurang kuali, Rt.3 Rw.5 Desa. Sumberbrantas, Kec.Bumiaji, Kota Batu | HTI | JAW-JI-BTU-4110 | BUMIAJI_SUMBERBRANTAS | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA BATU | 6614369 | 2020-01-13 |  | 322 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-10-20 | W43-2020 | Oct-2020 | 2020-07-15 | W29-2020 | Jul-2020 | 2020-11-25 | W48-2020 | Nov-2020 | MW | 2020-06-12 |  | 513031035994 | 6.6 |  | 2020-08-12 |  | 2020-06-24 | 2020-11-30 | W49-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03.12.20 : RFIN sent 30.11.20 : aktual RFI (PLN connected), proses penyusunan dok RFIN 26.11.20 : proses perluasan jaringan oleh PLN target selesai 28 Nov, plan site connect PLN 30 Nov 23.11.20 : plan connect 25 Nov 12.11.20 : 09.11.20 : 05.11.20 : 02.11.20 : 29.10.20 : daya 23 kVA approved by PLN, proses konek PLN 22.10.20 : 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : 01.10.20 : isu approval up daya PLN dan perluasan jaringan yg masih menunggu review add work PLN by Power eng XL 28.09.20 : 24.09.20 : 21.09.20 : 17.09.20 : proses perluasan jaringan PLN (penambahan tiang PLN), revisi plan RFI 30 sep 14.09.20 : 10.09.20 : plan percepatan RFI Multiguna minggu ini 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : 24.08.20 : PLN connection menunggu review add work PLN by Power eng XL (eskalasi isu besar daya PLN terkait isu BP vs Biaya Investasi PLN) 17.08.20 : 06.08.20 : eskalasi isu besar daya PLN terkait isu BP vs Biaya Investasi PLN 23.07.20 : 22.07.20 : PLN meminta daya menjadi 10,6kva 13.07.20 : 09.07.20 : 29.06.20 : Proses PLN Connection 24.06.20 : email SRFI-N sent 18.06.20 : PLN Connection need perluasan jaringan 3 gawang 17.06.20 : PSB PLN release 11.06.20 : 08.06.20 : curingtime 04.06.20 : 01.06.20 : curingtime 28.05.20 : rebarring, plan cor besok 25.05.20 : 14.05.20 :13.05.20 : Lantai kerja, besi mos, angkur template plan kirim 14/5, plan cor pond 18/5 08.05.20 : bouwplank 30.04.20 : proses apply perijinan, CME start wait perijinan release 23.04.20 : 16.04.20 : collecting berkas legal untuk apply perijinan 09.04.20 : on going soiltest, collecting berkas legal untuk apply perijinan 02.04.20 : 25.03.20 : 19.03.20 : IW clear, proses renego dan validasi biaya sitac, paralel cek cellplan 11.03.20 : IW clear, proses renego dan validasi biaya sitac 28.02.20 : 26.02.20 : Kand ( -7,762681 112,53003), IW Clear 6 KK, proses review eskalasi sitac, collecting legal doc 20.02.20 : IW Clear, proses eskalasi sitac 13.02.20 : TNP review 06.02.20 : Kand A,B = Rehunting, Candidate A B RF NOK
173 |  | JAW-JB-SOR-3836 | 30590140031 | 1262051003 | SUMBERSARI_CIPARAY | ACTIVE | TB | 107.7003 | -6.9955 | 40 | 30/110/240 | 2020 | JEDI 2020 [NEW] | Kp. Sapan, RT.05 RW. 06, Desa Sumbersari, Kec. Ciparay, Kab. Bandung | HTI | JAW-JB-SOR-3836 | SUMBERSARI_CIPARAY | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614612 | 2020-04-03 |  | 139 | 121 - 150 days | 2020-08-31 | W36-2020 | Aug-2020 | 2020-08-30 | W36-2020 | Aug-2020 | 2020-08-30 | W36-2020 | Aug-2020 | 2020-08-24 | W35-2020 | Aug-2020 | MW | 2020-07-16 |  | 535312230470 | 6.6 |  | 2020-08-11 |  |  | 2020-08-20 | W34-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.08.20 : RFIN sent (MULTIGUNA) plan PLN permanent 1 sept 17.08.20 : actual RFI dengan connect PLN Multiguna, collecting doc RFIN, plan submit RFIN 19 Aug 13.08.20 : ME on going 10.08.20 : tower erection done, on going tower painting, ME on going, finishing RBS foundation, on going F&Y 06.08.20 : 03.08.20 : 30.07.20 : cor done, curingtime process 27.07.20 : rebarring 23.07.20 : borepile done, on going excavation, plan cor selasa 28 jul 20 16.07.20 : on going borepile 13.07.20 : mobilisasi tim borepile 09.07.20 : prepare team dan material 06.07.20 : APD/BoQ approved, submit berkas perijinan 02.07.20 : 29.06.20 : RFC, proses perijinan 25.06.20 : 22.06.20 : 18.06.20 : proses rekom on going 15.06.20 : 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : 05.06.20 : IW yang 1 org minta pengerasan jalan estimasi Rp 50 jt,proses pendekatan LL 04.06.20 : Finalisasi IW plan IW clear Jumat tgl 5 Juni 01.06.20 : 29.05.20 : finalisasi IW, isu 1 kk masih kurang IW 28.05.20 : 25.05.20 : 14.05.20 : finalisasi eskalasi sitac, plan start realisasi sitac dan proses rekom 08.05.20 : Iw masih kurang 4 orang karena posisi di luar kota IW nya 30.04.20 : IW OG kurang 4 KK dari 18 KK 23.04.20 : 16.04.20 : IW on going 09.04.20 : 06.04.20 : Hunting
102 |  | SUL-SN-PIN-1295 | 30587290031 | 2811011003 | MASSEWAE | ACTIVE | TB | 119.6263 | -3.7021 | 40 | 60/150/300 | 2020 | JEDI 2020 [NEW] | DUSUN LOME, DESA MASSEWAE, KECAMATAN DUAMPANUA, KABUPATEN PINRANG, PROVINSI SULAWESI SELATAN | HTI | SUL-SN-PIN-1295 | MASSEWAE | B2S | TBG | EAST | SULAWESI | Kep. Bangka Belitung | KAB. PINRANG | 6614554 | 2020-03-13 |  | 179 | > 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-09-10 | W37-2020 | Sep-2020 | MW | 2020-06-12 |  | 324300208113 | 6.6 |  | 2020-08-11 |  | 2020-09-08 | 2020-09-08 | W37-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.09.20 : RFIN sent 07.09.20 : 03.09.20 : collecting doc RFIN 31.08.20 : RFI actual 27.08.20 : ME on going, F&Y on going, revisi plan RFI 30 Aug 24.08.20 : erection done, ME on going & tower painting, proses urugan dan penyelesaian retaining wall, revisi plan RFI 28 Aug 20 17.08.20 : on going erection 13.08.20 : on going erection 2 section 10.08.20 : plan start erection Rabu 12 Aug 20 06.08.20 : curingtime, on going backfilling & retaingwall, plan start erection senin 10 Aug 20, plan RFI 25 Aug 03.08.20 : curingtime 30.07.20 : cor done 29 jul 20 27.07.20 : rebarring, plan cor 30 jul 23.07.20 : on going retaining wall 20.07.20 : galian pondasi OG, plan cor 27.07.2020 16.07.20 : 13.07.20 : on going retaining wall, plan finish 18 jul (W29), plan start galian pondasi 19 jul, terkendala lokasi site yang extreme 09.07.20 : on going retaining wall 06.07.20 : start excavation, wait SK PLN release from XL (request date 12 jun 20) 02.07.20 : MOM : plan start CME sabtu 4 jul 20 29.06.20 : Plan hari ini Terbit 2 Produk perijinan (Rekomendasi PU dan Rekomendasi Lingkungan Hidup) jika 2 Produk tersebut telah terbit maka proses perijinan di PTSP lebih mudah, on going proses IP, plan bisa Lanjut CME dengan Pengawalan setelah IMB release 25.06.20 : proses nego ke warganya lagi agar tidak perlu ganti kandidat, paralel menunggu putusan PTSP, kalau menurut PTSP perijinan nya bisa Release berarti tetap lanjut di kandidat tersebut karena sudah punya legal standing yg kuat. 22.06.20 : proses penyelesaian isu, ada kemungkinan geser 30m, plan besok 23 jun submit validasi pergeserankandidat 30m dan paralel dilakukan revalidasi data soiltest/design pondasi. 18.06.20 : site masih comcase (isu IW) dan belum dapat lanjut CME (last progress excavation), plan penyelesaian 20/6 15.06.20 : 11.06.20 : plan comcase clear & start senin 08.06.20 : Comcase, CME stop (excavation), 07/06/2020 Still COM CASE (Meeting with Community & Kades DONE, no result Yet). CME HOLD. 04.06.20 : ComCase, Community Complain & request Socialization regarding Technical Tower Foundation. (Retaining Wall Foundation HOLD) 01.06.20 : on going excavation pondasi retaining wall, kondisi lahan curam/miring, pekerjaan cut&fill besar 28.05.20 : 21.05.20 : site clearing Done, Excavation of Foundation retaining wall OG 14.05.20 : penyelesaian isu add cost unloading 14.05.20 : on going excavation 08.05.20 : Plan Pickup mate tower+Anchor on Monday 11 May 2020, Plan Delivery on 13 May 2020. 06.05.20 : Kandidat B, Rekom Done, Proses RFL, Prepare Join Survey PTSP Before RFC 30.04.20 : on going rekom camat 23.04.20 : 16.04.20 : rekom dan soiltest 09.04.20 : Kandidat B, Proses Rekom Lurah, SST 52 02.04.20 : 01.04.20 : RND OK, wait TNP 31.03.20 : submit kand 25.03.20 : RND review
141 |  | JAW-JB-BJR-3857 | 20210202501 | 1260791003 | REJASARI_Banjar | ACTIVE | TB | 108.6159 | -7.3769 | 30 | 120/240/350 | 2020 | JEDI 2020 [NEW] | DUSUN SAMPIH RT.005 RW.008 DESA REJASARI KECAMATAN LANGENSARI KOTA BANJAR | HTI | JAW-JB-BJR-3857 | REJASARI_Banjar | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANJAR | 6614369 | 2020-01-13 |  | 468 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-04-25 | W18-2021 | Apr-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 532217757641 | 6.6 |  | 2020-08-11 |  | 2020-08-21 | 2021-04-25 | W18-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.04.21 : RFIN sent 15.04.21 : material Trafo ready 20 Apr, plan RFI W18 08.04.21 : material PLN (Trafo) NY ready, revise RFI plan 15 Apr 05.04.21 : Material PLN NY ready, SJ PLN released, plan connect 10 Apr 25.03.21 : negosiasi sharing cost Overblast, revise RFI plan W1 Apr 08.02.21 : trafo overblast 21.01.21 : PSB released, PLN connection OG 21.08.20 : SRFIN sent 17.08.20 : 13.08.20 : tinjauan lokasi/survey done, CME sudah di ijinkan continue 10.08.20 : 06.08.20 : 03.08.20 : proses koordinasi penjadwalan survey dan rapat TKPRD 30.07.20 : 27.07.20 : 16.07.20 : CME belum dapat start karena isu perijinan kota banjar 09.07.20 : 06.07.20 : 02.07.20 : plan start CME 13 jul, plan RFI end of jul 29.06.20 : 22.06.20 : 18.06.20 : CME masih STOP karena isu perijinan 11.06.20 : 08.06.20 : pekerjaan di stop kembali karena isu perijinan kota Banjar 04.06.20 : mobilisasi tim kembali untuk lanjut pekerjaan CME 01.06.20 : STOP by Satpol PP, isu perijinan kota banjar 28.05.20 : 25.05.20 : 21.05.20 : 14.05.20 : erection 1 section STOP by perijinan 08.05.20 : curingtime 30.04.20 : 23.04.20 : 16.04.20 : 09.04.20 : CME start after proses perijinan 02.04.20 : RFC, proses perijinan 25.03.20 : proses soiltest 19.03.20 : 11.03.20 : Rekom on going 20.02.20 : 13.02.20 : IW on going 06.02.20 : Kand A = RF OK, TX review
115 |  | JAW-JB-BJR-3855 | 30570980031 | 1260771003 | NEGLASARI_BANJAR | ACTIVE | TB | 108.5051 | -7.3856 | 40 | 20/180/280 | 2020 | JEDI 2020 [NEW] | Dsn. Warungbuah Rt.021 / Rw 013 Desa Neglasari Kec Banjar Kota Banjar,Jawa Barat. | HTI | JAW-JB-BJR-3855 | NEGLASARI_BANJAR | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANJAR | 6614369 | 2020-01-13 |  | 411 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-10-01 | W40-2020 | Oct-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-25 | W09-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 532217748191 | 6.6 |  | 2020-08-11 |  | 2020-10-06 | 2021-02-27 | W09-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.03.21 : RFIN sent 08.02.21 : Perluasan jaringan OG 21.01.21 : PSB released, PLN connection OG 06.10.20 : 05.10.20 : SRFIN sent 01.10.20 : SRFI actual, collecting doc RFIN 28.09.20 : erection on going, paralel on going F&Y 24.09.20 : erection on going, progress terkendala hujan 2 hari 21.09.20 : erection on going 17.09.20 : sortir material tower, prepare for erection start 14.09.20 : plan start CME 15 sep 20 10.09.20 : Mob demob plan sabtu 12 sep 20, last progress curingtime 07.09.20 : 03.09.20 : Rapat TPKRD done, plan start CME minggu ini (paling lambat kamis dimaksimalkan sudah start CME) 31.08.20 : 27.08.20 : Disposisi Dinas PTSP penjadwalan rapat TKPRD untuk 3-Site sudah di ttd Kadis (CIBEUREUM_BANJAR, REJASARI_LANGENSARI, NEGLASARI_BANJAR), , plan start CME kembali 7 sep (last progress cor done) 24.08.20 : 17.08.20 : 13.08.20 : tinjauan lokasi/survey done, waiting disposisi untuk continue CME, CME cor done 10.08.20 : 06.08.20 : 03.08.20 : proses koordinasi penjadwalan survey dan rapat TKPRD 30.07.20 : 27.07.20 : 16.07.20 : CME belum dapat start karena isu perijinan kota banjar 09.07.20 : 06.07.20 : 02.07.20 : plan start CME 13 jul, plan RFI end of jul 29.06.20 : 22.06.20 : 18.06.20 : CME masih STOP karena isu perijinan 11.06.20 : 08.06.20 : pekerjaan di stop kembali karena isu perijinan kota Banjar 04.06.20 : mobilisasi tim kembali untuk lanjut pekerjaan CME 01.06.20 : 31.05.20 : erection STOP by satpol PP, isu perijinan kota Banjar 28.05.20 : 25.05.20 : erection start on going 14.05.20 : Curring Time 08.05.20 : rebarring 30.04.20 : proses perijinan 23.04.20 : 16.04.20 : proses rekom 09.04.20 : realisasi IW dan rekom 02.04.20 : pembayaran IW dan rekom on going 25.03.20 : proses verifikasi dan negosiasi eskalasi 19.03.20 : 11.03.20 : IW on going 20.02.20 : 13.02.20 : IW on going 06.02.20 : Kand A = RF OK, TX review 23.01.20 : kand A = RND 50 45/150/280 23Jan20 : Ok candidate A, tower 52 23.01.20 : kand A = submit 108°30'17.10"E -7°23'7.50"S SST42
27 |  | JAW-JB-BJR-3854 | 30570970031 | 1260761003 | CIBEUREUM_BANJAR | ACTIVE | TB | 108.4859 | -7.3688 | 40 | 10/110/270 | 2020 | JEDI 2020 [NEW] | DUSUN PASIRNAGARA RT.15 RW.003 DESA CIBEREUM KECAMATAN BANJAR KOTA BANJAR | HTI | JAW-JB-BJR-3854 | CIBEUREUM_BANJAR | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANJAR | 6614369 | 2020-01-13 |  | 402 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-09-25 | W39-2020 | Sep-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-25 | W09-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 532217745783 | 6.6 |  | 2020-08-11 |  | 2020-09-30 | 2021-02-18 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18.02.21 : RFIN sent 08.02.21 : perluasan jaringan OG 21.01.21 : PSB released, PLN connection OG 01.10.20 : 30.09.20 : SRFIN sent 28.09.20 : 28.09.20 : SRFI, finishing F&Y, paralel collecting doc RFIN plan submit 30 sep 20 24.09.20 : 21.09.20 : on going ME installation 17.09.20 : erection top section 14.09.20 : erection on going 10.09.20 : Mob demob plan sabtu 12 sep 20, last progress curingtime 07.09.20 : 03.09.20 : Rapat TPKRD done, plan start CME minggu ini (paling lambat kamis dimaksimalkan sudah start CME) 31.08.20 : 27.08.20 : Disposisi Dinas PTSP penjadwalan rapat TKPRD untuk 3-Site sudah di ttd Kadis (CIBEUREUM_BANJAR, REJASARI_LANGENSARI, NEGLASARI_BANJAR), , plan start CME kembali 7 sep (last progress cor done) 24.08.20 : 17.08.20 : 13.08.20 : 10.08.20 : 06.08.20 : 03.08.20 : proses koordinasi penjadwalan survey dan rapat TKPRD 30.07.20 : 27.07.20 : 16.07.20 : CME belum dapat start karena isu perijinan kota banjar 09.07.20 : 06.07.20 : 02.07.20 : plan start cme lagi 13 jul 20, plan RFI end of Juli 29.06.20 : 22.06.20 : 18.06.20 : CME masih stop karena isu perijinan 11.06.20 : 08.06.20 : pekerjaan di stop kembali karena isu perijinan kota Banjar 04.06.20 : mobilisasi tim kembali untuk lanjut pekerjaan CME 01.06.20 : STOP by Satpol PP, isu perijinan kota banjar 28.05.20 : 25.05.20 : 14.05.20 : curingtime 08.05.20 : rebarring 30.04.20 : excavation 23.04.20 : 16.04.20 : 09.04.20 : CME start after proses perijinan 02.04.20 : RFC, proses perijinan 25.03.20 : proses soiltest 19.03.20 : 11.03.20 : Rekom on going 20.02.20 : IW clear 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 21.01.20 : Kand A = RND 50 0/120/275 21Jan20 : Ok candidate A, tower 52 20.01.20 : Kand A = submit kand A di 108.29'13.56" -7.22'7.61
196 |  | SUL-SN-PIN-1311 | 30587300031 | 2811021003 | TONYAMANG_PATAMPANUA | ACTIVE | TB | 119.653 | -3.7424 | 50 | 0/70/180 | 2020 | JEDI 2020 [NEW] | Maccobbu RT.001 RW.002, Kel. Tonyamang, Kec. Patampanua, Kabupaten Pinrang, Propinsi Sulawesi Selatan | HTI | SUL-SN-PIN-1311 | TONYAMANG_PATAMPANUA | B2S | TBG | EAST | SULAWESI | Kep. Bangka Belitung | KAB. PINRANG | 6614554 | 2020-03-13 |  | 144 | 121 - 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-08-05 | W32-2020 | Aug-2020 | MW | 2020-06-12 |  | 324300207099 | 6.6 |  | 2020-08-04 |  |  | 2020-08-04 | W32-2020 |  | 2020-08-28 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.08.20 : RFIN sent 03.08.20 : Plan connect PLN Multiguna 3 Aug 20, plan email RFIN 5 Aug 20 30.07.20 : plan percepatan RFI 31 juli dengan Multiguna 27.07.20 : SRFI actual, collecting doc SRFIN dan proses PLN connection (add work PLN/penambahan 6 tiang PLN), plan percepatan RFI 31 juli dengan Multiguna 23.07.20 : RBS pondasi done, FY OG. Erection Done, ME OG 20.07.20 : erection OG, erection baru jalan lagi, rekom IP dari perijinan baru di dapat jumat kemarin, plan SRFI 25.07.2020 (pln add jaringan penambahan 6 tiang), plan RFI 31 jul 16.07.20 : 13.07.20 : RBS pondasi done, Fence & Yard OG. Erection waiting ijin prinsip. Plan IP release W29/18 jul 09.07.20 : erection STOP karena isu perijinan, proses negosiasi 06.07.20 : prepare start erection (baru pasang baseplatenya saja tetapi di STOP), menunggu IP release 02.07.20 : 29.06.20 : prepare start erection 25.06.20 : curing time, PLN register done, Plan BP PAID. Backfill OG. Plan erection on 27 June 2020 (7 Days). 22.06.20 : Cor done 19 jun, Curring Time. Plan erection on 29 June 2020 (10 Days). 18.06.20 : Rebaring / Setting Anchor OG, Plan Pouring on Thursday 18 June 2020. 17.06.20 : Go RFI, PSB PLN release 15.06.20 : rebarring 11.06.20 : cutting barbending, dewatering lubang galian karena banjir 08.06.20 : CME stop (rebarring) karena galian longsor dan banjir akibat hujan terus, Problem Flooding not Solve Yet, New Dewatering and Geomembrand, before continue Lean Concrete. Cutting/Bending Rebar OG. 04.06.20 : Rebaring OG. Plan SRFI XL on 29 June 2020 01.06.20 : excavation done, paralel barbending dan rebarring preparation 28.05.20 : excavation 21.05.20 : confirm Plan Start CME on 26 May 2020, Plan RFI delay to 25 June 2020 18.05.20 : plan start CME after lebaran 14.05.20 : bouwplank, blm bisa start CME, NY RFC dan waiting Perijinan Clear. 08.05.20 : 06.05.20 : Kandidat A, RFC, CME Start Waiting Approval SPH OPSIC & Join Survey PTSP (Plan W2 Mei) 30.04.20 : on going rekom camat 23.04.20 : APD 16.04.20 : 09.04.20 : Kandidat A, Proses Rekom Lurah, SST 52 02.04.20 : 25.03.20 : IW on going
610 |  | KAL-KT-KLK-0390 |  |  |  | ACTIVE - CME by XL |  | 114.3442 | -2.9692 | 30 | 120/220/320 | 2020 | JEDI 2020 [NEW] |  | HTI | KAL-KT-KLK-0390 | LUNUKRAMBA | COLO | HTI | CENTRAL | KALIMANTAN | Kalimantan Tengah | KAB. KAPUAS | 6614902 | 2020-07-21 |  | 105 | 91 - 120 days | 2020-08-20 | W34-2020 | Aug-2020 | CME BY XL |  |  | 2020-08-20 | W34-2020 | Aug-2020 | 2020-08-20 | W34-2020 | Aug-2020 | MW | [5 empty] | 2020-07-30 |  |  | 2020-11-03 | W45-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09.11.20 : SRFI 18.09.20 : CME BY XL, Lacking PO CME & PO PLN, plan RFI 29 oct 20
608 |  | KAL-KS-BJM-0928 | 30606860031 | 220380109 | SUNGAI ANDAI | ACTIVE - CME by XL | TB | 114.6084 | -3.2946 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl. Purnama Permai Rt.03 Rw.01, Kel. Sungai andai / Kec. Banjarmasin Utara Banjarmasin Kalsel | HTI | KAL-KS-BJM-0928 | SURGI MUFTI_TIMURLAUT | COLO | HTI | CENTRAL | KALIMANTAN | Kalimantan Selatan | KOTA BANJARMASIN | 6614866 | 2020-07-07 |  | 209 | > 150 days | 2020-08-06 | W32-2020 | Aug-2020 | 2020-10-29 | W44-2020 | Oct-2020 | 2021-02-01 | W06-2021 | Feb-2021 | 2021-02-01 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  |  |  |  | 2020-07-30 |  |  | 2021-02-01 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.01.21 : RFI by TechPartner 01-Feb-21 18.09.20 : CME BY XL, Lacking PO CME & PO PLN, plan RFI 29 oct 20 16.07.20 : 07.07.20 : SPK release, CME by XL
175 |  | KAL-KB-MPW-0705 | 30588020031 | 2006871003 | SUNGAINIPAHSIANTAN | ACTIVE | TB | 109.2157 | 0.091695 | 30 | 0/110/190 | 2020 | JEDI 2020 [NEW] | Jl. Parit H. Amin RT.001 RW.018, Desa Jungkat, Kecamatan Siantan, Kabupaten Mempawah, Provinsi Kalimantan Barat | HTI | KAL-KB-MPW-0705 | SUNGAINIPAHSIANTAN | B2S | TBG | JABO | KALIMANTAN | Kalimantan Barat | KAB. MEMPAWAH | 6614568 | 2020-03-19 |  | 125 | 121 - 150 days | 2020-08-16 | W34-2020 | Aug-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-07-20 | W30-2020 | Jul-2020 | MW | 2020-06-12 |  | 211012275512 | 6.6 |  | 2020-07-29 |  |  | 2020-07-22 | W30-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22.07.20 : RFIN sent 16.07.20 : proses PLN connection plan connect 16 jul 13.07.20 : SRFI actual, collecting doc SRFIN 13.07.20 : ME on going 09.07.20 : Erection OG - Closed Body 02.07.20 : plan cor besok, material tower sudah on site, plan erection 8 jul 20 29.06.20 : 22.06.20 : cerucuk on going, Cor Pondasi terkendala lokasi tergenang air, tanah ikut tersedot, porositas tinggi, issue permukaan tanah naik 40cm akibat penanaman cerucuk jadi harus di gali lagi tanah diantara cerucuk untuk mendapatkan kedalaman pondasi yg sesuai. Plan Cor Pondasi 22/06, Erection Plan tgl 24/06, ME Plan dikerjakan paralel di malam hari (utk ME bawah), Pondasi RBS paralel dikerjakan di malam hari, Proses perluasan jaringan masih di koordinasiakan dengan PLN, plan SRFI 30 juni 18.06.20 : Borepile Done, Galian Finish 13/06, plan Cerucuk 17/06, plan Rebaring 20/06, plan Setting Angkur 20/06, lokasi tergenang air, tanah ikut tersedot, porositas tinggi, Plan Cor Pondasi: 21/06, Plan Erection: 24/06, Material Tower On delivery MOS 13/06, terdapat isu perluasan jaringan PLN 17.06.20 : Go RFI, PSB PLN release 15.06.20 : excavation 11.06.20 : 08.06.20 : 06.06.20 : Borpile done, Galian OG - Permasalah Air Pasang, Cerucuk Ready dipasang, COR Pondasi 15/06, Plan SRFI 25/06, Fabrikasi Material Besi di Warehause OG, Mataerial Tower Delivery Plan 10/06-plan OS 15/06 04.06.20 : cerucuk on going 01.06.20 : bouwplank 28.05.20 : on going perijinan, paralel tim CME plan on site 28 may untuk preparation CME 25.05.20 : 14.05.20 : 08.05.20 : proses perijinan 30.04.20 : 23.04.20 : 16.04.20 : IW done, proses rekom on going 09.04.20 : 02.04.20 : Eskalasi Sitac 31.03.20 : 30.03.20 : IW Clear 7 orang, eskalasi capex 25.03.20 : RF & TX OK, IW on going 25.03.20 : Kand B approved by TNP, IW ongoing 24.03.20 : Kand B approved by Huawei 23.03.20 : Validasi Kand A dan B to HO
160 |  | SUM-SU-PMS-2103 | 30587340031 | 0223671003 | SIRINGAN RINGAN | ACTIVE | TB | 99.4464 | 3.098 | 50 | 90/200/320 | 2020 | JEDI 2020 [NEW] | Huta II Urung 05, Nagori Siringan-ringan, Kec. Ujung Padang, Kab. Simalungun, Prov. Sumatera Utara | HTI | SUM-SU-PMS-2103 | SIRINGAN RINGAN | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KAB. SIMALUNGUN | 6614554 | 2020-03-13 |  | 123 | 121 - 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-13 | W29-2020 | Jul-2020 | MW | 2020-06-12 |  | 121120844987 | 6.6 |  | 2020-07-29 |  | 2020-07-14 | 2020-07-14 | W29-2020 |  | 2020-08-25 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.07.20 : SRFIN dan RFIN sent 13.07.20 : 11.07.20 : RFI actual, collecting doc RFIN, plan submit RFIN 13 jul 06.07.20 : SRFI actual, collecting doc SRFIN 02.07.20 : 29.06.20 : M/e on going, Fence&yard Grounding instalation 25.06.20 : plan SRFI end of June, plan RFI 7 jul 25.06.20 : 22.06.20 : 18.06.20 : curing time, prepare start erection 17.06.20 : Go RFI, PSB PLN release 15.06.20 : cor done, curing time 11.06.20 : rebarring, plan RFI 30 juni, request SK PLN 08.06.20 : 04.06.20 : excavation start 01.06.20 : plan start CME hari ini 1jun, plan galian done W1 jun 28.05.20 : prepare start CME 25.05.20 : land clearing 14.05.20 : bouwplank, proses GDL tower dan angkur 08.05.20 : rekom camat done.iw done.soiltest done.apd done 30.04.20 : rekom camat done.iw done.soiltest done.apd done 23.04.20 : 16.04.20 : IW clear, proses eskalasi sitac 09.04.20 : IW OG, plan IW clear 12 Apr 06.04.20 : kand A, IW kurang 2 kk, propose geser mundur 30m, need revalidasi 02.04.20 : IW clear 1 mar 20, proses eskalasi SITAC 25.03.20 : hunting
49 |  | JAW-JB-SOR-3833 | 30590130031 | 1262041003 | GIRIMULYA_PACET | ACTIVE | TB | 107.6824 | -7.1554 | 40 | 50/130/330 | 2020 | JEDI 2020 [NEW] | kp Cihejo Rt 03 rw 11, desa Girimulya, kecamatan pacet, kabupaten Bandung | HTI | JAW-JB-SOR-3833 | GIRIMULYA_PACET | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614612 | 2020-04-03 |  | 129 | 121 - 150 days | 2020-08-31 | W36-2020 | Aug-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-08-15 | W33-2020 | Aug-2020 | MW | 2020-06-12 |  | 535312226746 | 6.6 |  | 2020-07-28 |  | 2020-07-15 | 2020-08-10 | W33-2020 |  | 2020-09-14 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.08.20 : RFIN sent 03.08.20 : 27.07.20 : 23.07.20 : 16.07.20 : 13.07.20 : PLN connection masih terkendala isu stock kwh meter kosong 09.07.20 : 06.07.20 : 02.07.20 : Soft RFI, collecting doc SRFIN, proses PLN connection 29.06.20 : erection on going 22.06.20 : curing time 18.06.20 : galian done, on going lantai kerja, prepare start rebarring 17.06.20 : Go RFI, PSB PLN release 11.06.20 : start excavation 08.06.20 : 04.06.20 : proses perijinan 01.06.20 : 29.05.20 : rekom on going, plan hari ini RFC dan start proses perijinan 28.05.20 : 25.05.20 : rekom on going 14.05.20 : Proses pembayaran IW dan Rekom plan done tgl 20 Mei 08.05.20 : IW clear, Finalisasi IW plan Jumat submit eskalasi 30.04.20 : IW OG kurang 6 KK dari 24 KK 30.04.20 : IW on going 23.04.20 : RND review 16.04.20 : IW on going 09.04.20 : 06.04.20 : Hunting
12 |  | KAL-KB-SBS-0685 | 30587250031 | 2006861003 | BATUMAKJAGE | ACTIVE | TB | 109.1578 | 1.1628 | 50 | 50/110/270 | 2020 | JEDI 2020 [NEW] | Dusun Muara Dungun, RT 008 RW 004, Desa Pangkalan Kongsi, Kecamatan Tebas, Kabupaten Sambas, Provinsi Kalimantan Barat | HTI | KAL-KB-SBS-0685 | BATUMAKJAGE | B2S | TBG | JABO | KALIMANTAN | Kalimantan Barat | KAB. SAMBAS | 6614554 | 2020-03-13 |  | 129 | 121 - 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-20 | W30-2020 | Jul-2020 | MW | 2020-06-12 |  | 212100507944 | 6.6 |  | 2020-07-28 |  |  | 2020-07-20 | W30-2020 |  | 2020-08-19 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.07.20 : RFIN sent 16.07.20 : SRFI actual, collecting doc SRFIN 13.07.20 : ME on going 09.07.20 : Erection OG - Closed Body, PSB PLN sudah register, Survey PLN done, No Register Plan 06/07, pondasi RBS done, pagar on going, plan RFI 12 juli 02.07.20 : cor done 29/6, curing done, backfilling, plan start erection 5 jul 29.06.20 : 22.06.20 : cerucuk on going, plan Cor 24 Jun, Erection Plan tgl 26/06, ME bawah paralel kerjakan di malam hari, Pondasi RBS: paralel dikerjakan di malam hari, PLN : Proses perluasan jaringan masih di koordinasikan dengan PLN, plan SRFI 30 juni 18.06.20 : Borepile Done, Galian Done, Cerucuk OG-Finish 17/06, plan Rebaring 20/06, plan Setting Angkur 20/06, Plan Erection: 24/06 (Material angkur sdh onsite, mat Tower On port pontianak, plan delivery MOS 13/06, Team Erector menggunakan 2 team utk percepatan) 17.06.20 : Go RFI, PSB PLN release 15.06.20 : 11.06.20 : 08.06.20 : Borepile OG, Plan Finish 07/06, Cerucuk Plan Start 10/06, Pembesian Plan 15/06, COR Pondasi 18/06, Angkur By Air, plan Sortir Material 05/06, Pick Up 8/06, Material Delivery Tower Plan Delivery 10/06 (Corgo MKS), Plan SRFI 25/06 04.06.20 : borepile on going, plan SRFI 30 jun 01.06.20 : bouwplank 28.05.20 : on going perijinan, paralel tim CME plan on site 28 may untuk preparation CME 25.05.20 : 14.05.20 : 08.05.20 : proses perijinan 30.04.20 : 23.04.20 : 16.04.20 : rekom on going 09.04.20 : IW on going 08.04.20 : TNP OK kand B tower 52m 06.04.20 : RND OK kand B tower 52m 02.04.20 : 01.4.2020 : Eskalasi Capex, pararel update sistem 31.03.20 : 30.03.20 : IW clear 23 KK,Eskalasi capex 25.03.20 : RF & TX OK, IW on going 17.3.20 : Submit Kandidat A Lat. 1,1628 Long : 109,1578 to HO 25.3.20 : LL masih meminta BAN 20 jt parerel rehunting 20.3.20 : Kand A Approval Operator 23.3.2020 : IW ongoing 25.3.2020: IW Ongoing
67 |  | SUM-SU-PSP-2152 | 30587380031 | 0223711003 | JORING NATOBANG | ACTIVE | TB | 99.2575 | 1.4525 | 50 | 20/120/230 | 2020 | JEDI 2020 [NEW] | DESA JORING NATOBANG, KECAMATAN PADANGSIDIMPUAN ANGKOLA JULU, KOTA PADANGSIDIMPUAN, PROVINSI SUMATERA UTARA | HTI | SUM-SU-PSP-2152 | JORING NATOBANG | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KOTA PADANGSIDIMPUAN | 6614554 | 2020-03-13 |  | 130 | 121 - 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-08-09 | W33-2020 | Aug-2020 | 2020-07-31 | W31-2020 | Jul-2020 | MW | 2020-06-24 |  | 124011307427 | 6.6 |  | 2020-07-28 |  | 2020-07-14 | 2020-07-21 | W30-2020 |  | 2020-08-24 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.07.20 : RFIN sent 20.07.20 : RFI actual/PLN connect, proses collecting doc RFIN 14.07.20 : SRFIN sent 13.07.20 : 09.07.20 : 08.07.20 : erection done, ME on going 06.07.20 : curingtime 02.07.20 : 29.06.20 : prepare pouring 25.06.20 : start rebarring 22.06.20 : 18.06.20 : prepare start CME, land clearing, proses perijinan 15.06.20 : soiltest done, percepatan APD done, proses rekom 11.06.20 : izin warga done. plan start CME awal juli 08.06.20 : 04.06.20 : 01.06.20 : 28.05.20 : IW clear, proses eskalasi sitac (high price) 25.05.20 : IW on going 21.05.20 : 14.05.20 : TNP OK Cand B, IW on going 08.05.20 : Iw clear 30.04.20 : IW on going 23.04.20 : 16.04.20 : negosiasi terkait penolakan warga, iw on going, paralel rehunting kand alternatif 13.04.20 : IW on going 09.04.20 : BAN target 9 april 02.04.20 : 01.04.20 : wait review TNP (pak Fahri) 31.03.20 : RND OK twr 52 kand A 25.03.20 : hunting
187 |  | SUM-SU-PYB-2157 | 30587390031 | 0223721003 | TAMBISKI | ACTIVE | TB | 99.4862 | 0.92765 | 50 | 80/150/350 | 2020 | JEDI 2020 [NEW] | DESA TAMBISKI NAULI, KECAMATAN NAGA JUANG, KABUPATEN MANDAILING NATAL, PROVINSI SUMATERA UTARA | HTI | SUM-SU-PYB-2157 | TAMBISKI | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KAB. MANDAILING NATA | 6614554 | 2020-03-13 |  | 130 | 121 - 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-08-09 | W33-2020 | Aug-2020 | 2020-07-31 | W31-2020 | Jul-2020 | MW | 2020-06-24 |  | 124100884966 | 6.6 |  | 2020-07-28 |  |  | 2020-07-21 | W30-2020 |  | 2020-08-19 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.07.20 : RFIN sent 13.07.20 : erection top 09.07.20 : 08.07.20 : on going erection 50% 06.07.20 : 02.07.20 : 29.06.20 : rebarring 25.06.20 : 22.06.20 : 18.06.20 : start galian, proses perijinan 15.06.20 : proses perijinan 11.06.20 : iw clear. soiltest done.rekom done 08.06.20 : rekom proses 01.06.20 : 28.05.20 : 27.05.20 : IW clear, proses eskalasi sitac 25.05.20 : IW on going 14.05.20 : 08.05.20 : Iw clear 30.04.20 : IW on going 23.04.20 : 16.04.20 : IW on going, plan IW clear 22 Apr 09.04.20 : validasi done, IW on going 09.04.20 : BAN target 9 april 02.04.20 : 01.04.20 : wait review RND 25.03.20 : hunting
66 |  | JAW-JB-NPH-3702 | 30573580031 | 1260991003 | JAYAGIRI_LEMBANG | ACTIVE | TB | 107.6178 | -6.7952 | 40 | 0/150/250 | 2020 | JEDI 2020 [NEW] | KP CISARONI, RT 06 RW 08, DESA CIKAHURIPAN, KECAMATAN LEMBANG, KABUPATEN BANDUNG BARAT | HTI | JAW-JB-NPH-3702 | JAYAGIRI_LEMBANG | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614396 | 2020-01-15 |  | 208 | > 150 days | 2020-06-13 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-15 | W33-2020 | Aug-2020 | MW | 2020-07-01 |  | 535891106070 | 6.6 |  | 2020-07-28 |  | 2020-07-15 | 2020-08-10 | W33-2020 |  | 2020-09-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.08.20 : RFIN sent 03.08.20 : 27.07.20 : 23.07.20 : 16.07.20 : email SRFI-N sent, PLN connection masih terkendala isu stock kwh meter kosong dan adanya perluasan jaringan 13.07.20 : PLN connection masih terkendala isu stock kwh meter kosong dan adanya perluasan jaringan 09.07.20 : 06.07.20 : proses PLN connection 02.07.20 : SK PLN release, plan RFI = SPK release + 14 hari 30.06.20 : change transport type menjadi MW, request SK PSB PLN untuk continue PLN Connectionnya 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : 15.06.20 : Soft RFI 11.06.20 : cat tower, pagar halaman og, pondasi bts og 08.06.20 : Erection OG 04.06.20 : prepare erection (langsir material tower) 01.06.20 : curingtime & backfilling 28.05.20 : 25.05.20 : curingtime 21.05.20 : excavation on going 15.05.20 : start excavation 14.05.20 : preparation tim dan material 08.05.20 : rekom done, bouwplank, proses perijinan 30.04.20 : rekom desa done proses rekom camat 23.04.20 : 16.04.20 : proses realisasi IW dan rekom on going 09.04.20 : 02.04.20 : 25.03.20 : proses verifikasi dan negosiasi eskalasi 19.03.20 : IW clear 11.03.20 : IW on going 20.02.20 : 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 22.01.20 : kand A = RND 50 180/245/310 22Jan20 : RND ok candidate A, tower 52 20.01.20 : Kand A = submit kand A di -6.794800° 107.618820° 17.01.20 : hasil assessment PDI done (email arief), proses input STIP 1 B2S
164 |  | JAW-JB-BJR-3856 | 30570990031 | 1260781003 | SITUBATU_BANJAR | ACTIVE | TB | 108.474 | -7.3804 | 40 | 30/110/300 | 2020 | JEDI 2020 [NEW] | Dusun SukahayuRT.01 RW.01 Desa Cimaragas Kec. Cimaragas Kab.Ciamis | HTI | JAW-JB-BJR-3856 | SITUBATU_BANJAR | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANJAR | 6614369 | 2020-01-13 |  | 378 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2021-01-20 | W04-2021 | Jan-2021 | FO (Change to MW as temp solution) | 2020-12-10 |  | 532217740611 | 6.6 |  | 2020-07-28 |  | 2020-07-15 | 2021-01-25 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : OG penambahan tiang 07.01.21 : FO access RFS plan on W4 Jan confirmed by PM FO 07.01.21 : issue perluasan jaringan, penambahan tiang dan KWH meter kosong 28.12.20 : 21.12.20 : 17.12.20 : PLN connection process 10.12.20 : FO civil preparation 03.08.20 : 27.07.20 : 15.07.20 : email SRFI-N sent, PLN Connection menunggu konfirmasi dari XL 09.07.20 : 06.07.20 : 02.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : 15.06.20 : Soft RFI 11.06.20 : ME & Grounding on going 08.06.20 : erection on going, F&Y on going 04.06.20 : erection OG, pondasi BTS og, pagar halamn OG 01.06.20 : erection on going 28.05.20 : 25.05.20 : curingtime 14.05.20 : pouring foundation 08.05.20 : excavation 30.04.20 : proses perijinan, paralel bouwplank 23.04.20 : 16.04.20 : proses realisasi IW dan rekom on going 09.04.20 : validasi done, IW on going 02.04.20 : IW on going 25.03.20 : 19.03.20 : 11.03.20 : IW on going 20.02.20 : 13.02.20 : IW on going 06.02.20 : Kand B = Candidate B Submit 23.01.20 : kand A = RND 50 30/105/315 23Jan20 : Ok candidate A, tower 52 23.01.20 : kand A = submit 108°28'23.50"E -7°22'50.90"S SST42
155 |  | JAW-JI-TBN-4058 | 30571700031 | 1643471003 | SEMANDING_BEKTIHARJO | ACTIVE | TB | 112.0418 | -6.9435 | 50 | 70/210/290 | 2020 | JEDI 2020 [NEW] | Dsn Krajan RT 01 RW 07 Desa Bektiharjo Kec Semanding Kab Tuban | HTI | JAW-JI-TBN-4058 | SEMANDING_BEKTIHARJO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. TUBAN | 6614369 | 2020-01-13 |  | 396 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-14 | W33-2020 | Aug-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-13 | W07-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 518023274654 | 6.6 |  | 2020-07-28 |  | 2020-09-01 | 2021-02-12 | W07-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP Paid, Proses PK di UP3 21.01.21 : PSB released, PLN connection OG 01.09.20 : email SRFI-N sent 23.07.20 : 16.07.20 : SRFI actual, collecting doc SRFIN, PLN connection menunggu konfirmasi dari XL 13.07.20 : on going ME dan F&Y 06.07.20 : ME on going 02.07.20 : curingtime & back filling, plan start erection 4 jul 29.06.20 : rebarring done, prepare cor 25.06.20 : rebarring 22.06.20 : 18.06.20 : excavation on going 50% 15.06.20 : CME on going / excavation 11.06.20 : proses perijinan, plan start galian 12 jun 20 08.06.20 : 04.06.20 : 01.06.20 : CME start menunggu proses perijinan 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : proses design/bouwplank dan apply perijinan 30.04.20 : proses soil test, rekom, collecting doc legal 23.04.20 : 16.04.20 : IW clear, review eskalasi sitac 09.04.20 : IW clear 02.04.20 : 25.03.20 : IW OG 8kk, ( 3 KK OK ) 19.03.20 : IW on going, need approval kandidat 11.03.20 : IW on going 20.02.20 : Cand outcell , propose opsi GM Permanet Incell Reject Kominfo , JR Cand C reject RNP 20.02.20 : 13.02.20 : 06.02.20 : Kand C = Rehunting, Candidate C RF NOK 05.02.20 : kand C = submit C 112.03717 -6.942 534.42 GF SST 52 In Cellplan Tuban sesuai arahan Pemda (terlampir), atau bisa dicek di web : https://zonasi.tubankab.go.id/ 28.01.20 : kand A = RND 50 70/160/280 28Jan20 : Ok candidate A, tower 52 27.01.20 : kand A = 112.04178 -6.943333 23.98 GF SST 52 Out Cellplan Tuban. Pengajuan Permohonan pertimbangan cellplan OG kand B = 112.04278 -6.9425 162.49 GF SST 52 Out Cellplan Tuban. Pengajuan Permohonan pertimbangan cellplan OG kand C = 112.03717 -6.942 534.42 GF SST 52 In Cellplan Tuban
78 |  | JAW-JB-CBN-3734 | 30571020031 | 1260811003 | KARYAMULYA_KESAMBI | ACTIVE | TB | 108.5237 | -6.7462 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl. Perjuangan Karya Bakti, RT 004 RW 010, Kel. Karyamulya, Kec. Kesambi Kota Cirebon | HTI | JAW-JB-CBN-3734 | KARYAMULYA_KESAMBI | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA CIREBON | 6614369 | 2020-01-13 |  | 387 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-15 | W29-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 533113500287 | 6.6 |  | 2020-07-28 |  | 2020-07-15 | 2021-02-03 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : PSB released, PLN connection OG 03.08.20 : 27.07.20 : 23.07.20 : 20.07.20 : 16.07.20 : 15.07.20 : SRFIN sent, PLN connection menunggu konfirmasi XL 09.07.20 : 06.07.20 : 02.07.20 : PLN connection menunggu konfirmasi XL 30.06.20 : PLN connection HOLD karena ada perubahan type transportnya lagi menjadi FO, SK PSB PLN ny released by XL 29.06.20 : 22.06.20 : 20.06.20 : SRFI, collecting doc SRFIN, proses PLN Connection 18.06.20 : CME continue, ME & Grounding installation 11.06.20 : 08.06.20 : erection tower (pengecatan) distop kembali by ormas , pondasi BTS OG, pagar OG 04.06.20 : erection tower (pengecatan) , pondasi BTS OG, pagar OG 01.06.20 : erection on going 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : curingtime 30.04.20 : rebarring 23.04.20 : 16.04.20 : 09.04.20 : CME start after proses perijinan 02.04.20 : RFC, proses perijinan, tower 52 25.03.20 : rekom done 24/3 19.03.20 : 11.03.20 : Rekom on going 20.02.20 : IW on going 13.02.20 : TNP review 06.02.20 : Kand B = RF OK, TX review 22.01.20 : kand A = RND 30 40/120/235 22Jan20 : RND ok candidate A, tower 32 20.01.20 : Kand A = submit kand A di 108.31'23.1" -6.44'45.8"
75 |  | JAW-JB-NPH-3706 | 30571080031 | 1260871003 | KARANGANYAR_CILILIN | ACTIVE | TB | 107.3837 | -6.9364 | 50 | 100/240/310 | 2020 | JEDI 2020 [NEW] | Kp.Cimalingping, RT 04 RW 09, Desa Karanganyar, Kecamatan Cililin, Kabupaten Bandung barat, Provinsi Jawa Barat | HTI | JAW-JB-NPH-3706 | KARANGANYAR_CILILIN | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614369 | 2020-01-13 |  | 175 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-27 | W18-2020 | Apr-2020 | 2020-07-15 | W29-2020 | Jul-2020 | 2020-07-15 | W29-2020 | Jul-2020 | MW | 2020-04-22 |  | 535950876550 | 6.6 |  | 2020-07-27 |  | 2020-05-14 | 2020-07-06 | W28-2020 |  | 2020-09-27 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.07.20 : 09.07.20 : 06.07.20 : RFIN sent 02.07.20 : actual connect PLN/RFI, collecting doc RFIN 29.06.20 : 26.06.20 : SK PLN revisi daya 10.6 kVA release, continue proses PLN connectionnya 25.06.20 : PLN belum tersambung karena terkendala SK PLN 10.6 kVA yang belum release dari XL, resiko KWH meternya di alihkan ke pelanggan lain. Need support XL untuk percepatan release SK PLN 10.6 kVA nya. 22.06.20 : PLN belum tersambung karena terkendala SK PLN 10.6 kVA yang belum release dari XL, need percepatan release SK PLN nya. 17.06.20 : request revisi SK PLN 10.6 kVA sebagai syarat dilanjutkannya proses connect oleh PLN, status KWH meter 10.6 kVA sudah ready. 08.06.20 : termasuk site yang terdapat perubahan Transport Type menjadi FO sesuai email Pak Ahenk 14 May, tetapi proses PLN confirm by XL tetap dilanjutkan karena TBG sudah bayar BPUJL. Saat ini masih proses perluasan jaringan dan terdapat info dari PLN bahwa minimum daya yang dilayani untuk site ini adalah 10.6 kva, hal ini terkait dengan investasi perluasan jaringan yang dilakukan oleh PLN REVISI PLAN RFI dri 4 juni menjadi akhir minggu ini 13 Jun 20 28.05.20 : 14.05.20 : SRFIN sent 12.05.20 : SRFIN actual 08.05.20 : 30.04.20 : erection on going 23.04.20 : 22.04.20 : pekerjaan di stop LL issue dp lahan, untuk bs konek pln perlu tambah pole sekitar 4 titik 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 20.04.20 : tower on site 16.04.20 : curingtime dan proses pengurukan, gdl tower rilis, proses delivery material tower 09.04.20 : curing time, material tower 52 ready tgl 17 apr (slow due to pabricator WFH) 02.04.20 : 01.04.20 : rebarring done, plan cor 4 apr, SST 52m 25.03.20 : on going excavation 19.03.20 : start galian pondasi 11.03.20 : Rekom done, RFC, proses perijinan 20.02.20 : peroses eskalasi sitac paralel dengan rekom 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 23.01.20 : kand A = RND 60 100/185/310 22Jan20 : RND ok candidate A, tower 62 20.01.20 : Kand A = email ESR submit 20.01.20 : Kand A = submit kand A di -6'56'10.74 107'23'01.45. XL meminta ESR/foto2 kandidat untuk cek lokasi sekitar kandidatnya, karena ada bukit.
169 |  | JAW-JB-BJR-3858 | 30571010031 | 1260801003 | SUKAMUKTI_PATARUMAN | ACTIVE | TB | 108.5468 | -7.4107 | 40 | 140/240/340 | 2020 | JEDI 2020 [NEW] | Kedung Lemah, Blok Bantar Saung, RT.05 RW.06, Desa Bangunsari, Kecamatan Pamarican, Kabupaten Ciamis | HTI | JAW-JB-BJR-3858 | SUKAMUKTI_PATARUMAN | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANJAR | 6614369 | 2020-01-13 |  | 220 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-27 | W18-2020 | Apr-2020 | 2020-07-03 | W27-2020 | Jul-2020 | 2020-08-19 | W34-2020 | Aug-2020 | MW | 15-Jun-20 18-May-20 |  | 532217709553 | 6.6 |  | 2020-07-24 |  | 2020-05-10 | 2020-08-20 | W34-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.08.20 : RFIN sent (MULTIGUNA) plan PLN permanent 1 sept 17.08.20 : actual RFI dengan connect PLN Multiguna, collecting doc RFIN, plan submit RFIN 19 Aug 10.08.20 : 03.08.20 : 27.07.20 : 23.07.20 : 16.07.20 : 13.07.20 : 09.07.20 : plan PLN connect 20 jul 20, masih terkendala isu stock kwh meter kosong 06.07.20 : 02.07.20 : 29.06.20 : 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 28.05.20 : 14.05.20 : 10.05.20 : SRFIN sent, wait plan MOS & konfirmasi permintaan PLN connection dari XL/tech part 30.04.20 : SRFI actual 23.04.20 : 16.04.20 : curingtime dan proses pengurukan, gdl tower rilis, proses delivery material tower 09.04.20 : curing time, material tower 52 ready tgl 17 apr (slow due to pabricator WFH) 02.04.20 : 01.04.20 : rebarring, angkur plan besok diambil, SST 52 19.03.20 : galian done, lantai kerja, wait GDL tower 11.03.20 : bouwplank, plan start CME besok 12 Maret, plan RFI 25 Apr 20 20.02.20 : rekom L/C 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 21.01.20 : Kand A = RND 50 10/150/290 21Jan20 : Ok candidate A, tower 52 20.01.20 : Kand A = submit kand A di 108.32'41.68" -7.24'49.82"
21 |  | JAW-JB-NPH-3716 | 30571090031 | 1260881003 | BOJONGKONENG_NGAMPRAH | ACTIVE | TB | 107.4961 | -6.8131 | 50 | 40/200/330 | 2020 | JEDI 2020 [NEW] | Kampung Pasir Haur, RT.02 RW.014 , Desa Bojong Koneng, Kecamatan Ngamprah, Kabupaten Bandung Barat | HTI | JAW-JB-NPH-3716 | BOJONGKONENG_NGAMPRAH | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614369 | 2020-01-13 |  | 194 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-07-23 | W30-2020 | Jul-2020 | MW | 2020-07-01 |  | 535852102490 | 6.6 |  | 2020-07-24 |  | 2020-07-16 | 2020-07-25 | W30-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.07.20 : RFIN sent 23.07.20 : actual RFI dengan connect PLN Multiguna, plan permanent 1 aug 16.07.20 : email SRFI-N sent 13.07.20 : PLN connection masih terkendala isu stock kwh meter kosong 09.07.20 : 06.07.20 : proses PLN Connection 02.07.20 : SK PLN release, plan RFI = SPK release + 14 hari, Soft RFI, collecting doc SRFIN, proses PLN connection 30.06.20 : change transport type menjadi MW, request SK PSB PLN untuk continue PLN Connectionnya 29.06.20 : erection done, on going pondasi RBS 22.06.20 : erection on going 19.06.20 : start erection 18.06.20 : curing time & backfilling 11.06.20 : curing time 08.06.20 : rebaring, plan cor senin 8/6 04.06.20 : rebaring, plan cor sabtu 6/6 01.06.20 : plan cor hari ini 31.05.20 : rebarring done 28.05.20 : 25.05.20 : 21.05.20 : rebarring 14.05.20 : galian done, lantai kerja 08.05.20 : excavation og 30.04.20 : 23.04.20 : 16.04.20 : proses perijinan, CME preparation 09.04.20 : proses perijinan 02.04.20 : 25.03.20 : proses rekom, tower 52 11.03.20 : IW clear, proses eskalasi SITAC, proses collect SITAC doc 20.02.20 : IW on going 13.02.20 : TNP review 06.02.20 : kand C = validasi done, Candidate C RF TX OK 17.01.20 : Kand A = not approve, karena sektoralnya bloking, mohon rehunting ke koordinat berikut : 107.497497, -6.811518. 17.01.20 : Kand A = submit kand A di 06'48'46.47 107'29'44.01
609 |  | KAL-KS-PLI-0911 | 30606800031 | 220614109 | TANAH LAUT 1 | ACTIVE - CME by XL | SKP | 114.7362 | -3.7404 | 50 | 30/220/300 | 2020 | JEDI 2020 [NEW] | Jl. Telkom Gunung Keramaian, Desa Panggung Baru RT 02 / RW.01 Kec. Pelaihari, Kab. Tanah Laut Prov. Kalimantan Selatan | HTI | KAL-KS-PLI-0911 | PANGGUNG BARU | COLO | HTI | CENTRAL | KALIMANTAN | Kalimantan Selatan | KAB. TANAH LAUT | 6614863 | 2020-07-07 |  | 123 | 121 - 150 days | 2020-08-06 | W32-2020 | Aug-2020 | CME BY XL |  |  | 2020-08-06 | W32-2020 | Aug-2020 | 2020-08-06 | W32-2020 | Aug-2020 | MW | [5 empty] | 2020-07-23 |  |  | 2020-11-07 | W45-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09.11.20 : SRFI, target RFI 26 Nov 18.09.20 : CME BY XL, Lacking PO CME & PO PLN, plan RFI 29 oct 20 30.07.20 : mobilisasi, CME by XL 16.07.20 : 07.07.20 : SPK release
148 |  | JAW-JI-BLT-1915 | 30573600031 | 1643511003 | SANAN_BENDO | ACTIVE | TB | 112.1781 | -8.0862 | 30 | 10/130/240 | 2020 | JEDI 2020 [NEW] | JL. BRAU RT.005 RW.010 KELURAHAN BENDOGERIT KEC. SANANWETAN KOTA BLITAR PROP. JAWA TIMUR | HTI | JAW-JI-BLT-1915 | SANAN_BENDO | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA BLITAR | 6614396 | 2020-01-15 |  | 426 | > 150 days | 2020-06-13 | W24-2020 | Jun-2020 | 2020-08-01 | W31-2020 | Aug-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-03-29 | W14-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 514021937038 | 6.6 |  | 2020-07-22 |  | 2020-09-01 | 2021-03-16 | W12-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.03.21 : 08.03.21 : MoM 04/3, OG perluasan jaringan, revise RFI plan 29/3 18.02.21 : PLN connection daya 33 kVA, setelah 1 bulan dilakukan downgrade ke 6.6 kVA 26.01.21 : survey done, OG perluasan jaringan 21.01.21 : PSB released, PLN connection OG 01.09.20 : email SRFI-N sent 23.07.20 : SRFI actual, collecting doc SRFIN, PLN connection menunggu konfirmasi dari XL 16.07.20 : ME on going, erection & TBS foundation done, plan SRFI 17 jul 13.07.20 : 06.07.20 : erection hold karena isu perijinan 02.07.20 : erection on going 29.06.20 : rebaring og, tower onsite 25.06.20 : rebarring 22.06.20 : 18.06.20 : persiapan start galian dengan excavator 15.06.20 : 11.06.20 : plan RFC 29 Jun, jadwal survey diskominfo minggu depan 08.06.20 : DESIGN PROSES ,COLLECT DOC RFL AND PKS, IW CLEAR 04.06.20 : 01.06.20 : 28.05.20 : 21.05.20 : 14.05.20 : iw on going 08.05.20 : TNP review 30.04.20 : rehunting 23.04.20 : 16.04.20 : IW clear, review eskalasi sitac 09.04.20 : IW clear, proses renego fasum 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : IW clear, proses renego fasum 11.03.20 : IW on going 28.02.20 : 24.02.20 : Kand A = (S : 8°05'06.46" E : 112°10'46.88") IW tinggi 32 clear, need soswar IW 52 m, resoswar 25.2.20 , paralel rehunting cand pendampig Warga Minta Soswar 52 Meter 20.02.20 : 20.02.20 : rehunting 13.02.20 : 06.02.20 : Hunting kandidat 17.01.20 : hasil assessment PDI done (email arief), proses input STIP 1 B2S
150 |  | JAW-JI-BLT-1914 | 30573590031 | 1643501003 | SANANWETAN_GERIT | ACTIVE | TB | 112.1789 | -8.0924 | 30 | 70/220/320 | 2020 | JEDI 2020 [NEW] | JL. WR Supratman RT.001 RW.004 Kel. Bendogerit, Kecamatan Sananwetan, Kota Blitar, Propinsi Jawa Timur | HTI | JAW-JI-BLT-1914 | SANANWETAN_GERIT | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA BLITAR | 6614396 | 2020-01-15 |  | 426 | > 150 days | 2020-06-13 | W24-2020 | Jun-2020 | 2020-08-01 | W31-2020 | Aug-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-03-29 | W14-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 514021910120 | 6.6 |  | 2020-07-22 |  | 2020-09-01 | 2021-03-16 | W12-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.03.21 : 08.03.21 : MoM 04/3, OG perluasan jaringan, revise RFI plan 29/3 18.02.21 : PLN connection daya 23 kVA, setelah 1 bulan dilakukan downgrade ke 6.6 kVA 26.01.21 : survey done, OG perluasan jaringan 21.01.21 : PSB released, PLN connection OG 01.09.20 : SRFIN sent 23.07.20 : 16.07.20 : SRFI actual, collecting doc SRFIN, PLN connection menunggu konfirmasi dari XL 16.07.20 : SRFI actual 13.07.20 : on going ME dan F&Y 06.07.20 : ME on going 02.07.20 : erection on going 29.06.20 : rebaring done, tower keterlambatan jadwal loading, prepare cor 25.06.20 : rebarring 22.06.20 : 18.06.20 : on going borepile 15.06.20 : CME start bouwplank 11.06.20 : proses perijinan, plan start galian 12 jun 20 08.06.20 : 04.06.20 : 01.06.20 : CME start menunggu proses perijinan 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : proses design/bouwplank dan apply perijinan 23.04.20 : 16.04.20 : collecting berkas legal untuk apply perijinan 09.04.20 : on going soiltest, collecting berkas legal untuk apply perijinan 02.04.20 : 25.03.20 : 19.03.20 : 11.03.20 : 28.02.20 : IW clear, proses review eskalasi sitac, collecting legal doc 20.02.20 : IW clear, proses eskalasi sitac 13.02.20 : 06.02.20 : Hunting kandidat 17.01.20 : hasil assessment PDI done (email arief), proses input STIP 1 B2S
397 |  | SUM-AC-MRN-0520 | 30597520031 | 010689109 | SIMPANG PARU KEUDE | ACTIVE | TB | 96.1166 | 5.2643 | 50 | 0/90/260 | 2020 | JEDI 2020 [NEW] | Gampong MNS Paru Keude, Simpang Paru Keude, Desa Meunasah Paru Keude, Kec. Bandar Baru, Kab. Pidie jaya, Prop. Aceh | HTI | SUM-AC-MRN-0520 | BANDAR BARU MEUNASAH | COLO | TBG | WEST | SUMBAGUT | Aceh | PIDIE JAYA | 6614850 | 2020-07-06 |  | 52 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-26 | W35-2020 | Aug-2020 | MW | 2020-08-10 |  | 116610141407 | 6.6 |  | 2020-07-21 |  |  | 2020-08-27 | W35-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.08.20 : RFIN sent 27.08.20 : RFI actual 26 Aug 20, collecting doc RFIN 24.08.20 : plan RFI 26 Aug 18.08.20 : proses PLN connection, plan RFI 25 aug 20 03.08.20 : 30.07.20 : SRFI actual 23.07.20 : on going RBS foundation 17.07.20 : ready to declare STO
378 |  | SUM-AC-MRN-0525 | 30597530031 | 010687109 | RAMBONG | ACTIVE | TB | 96.2174 | 5.2312 | 50 | 50/110/180 | 2020 | JEDI 2020 [NEW] | GP. GrongGrong, Kec. Meureudu, Kab. Pidie Jaya, Prop. Aceh | HTI | SUM-AC-MRN-0525 | RAMBONG | COLO | TBG | WEST | SUMBAGUT | Aceh | PIDIE JAYA | 6614850 | 2020-07-06 |  | 52 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-26 | W35-2020 | Aug-2020 | MW | 2020-08-10 |  | 116620108936 | 6.6 |  | 2020-07-21 |  |  | 2020-08-27 | W35-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.08.20 : RFIN sent 27.08.20 : plan connect PLN/RFI hari ini 24.08.20 : plan RFI 26 Aug 18.08.20 : proses PLN connection, plan RFI 25 aug 20 03.08.20 : 30.07.20 : SRFI actual 23.07.20 : on going RBS foundation 17.07.20 : ready to declare STO
434 |  | SUM-SU-STB-2194 | 30597540031 | 021405109 | TIMBANG LAWAN | ACTIVE | TB | 98.165 | 3.5115 | 50 | 140/280/350 | 2020 | JEDI 2020 [NEW] | Jalan Marjunus, Dusun II Kampung Bukit, Desa Timbang Lawan, Kecamatan Bahorok, Kabupaten Langkat, Provinsi Sumatera Utara | HTI | SUM-SU-STB-2194 | TIMBANG LAWAN | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | LANGKAT | 6614850 | 2020-07-06 |  | 56 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-31 | W36-2020 | Aug-2020 | MW | 2020-08-10 |  | 129040035521 | 6.6 |  | 2020-07-21 |  | 2020-08-10 | 2020-08-31 | W36-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31.08.20 : RFIN sent 27.08.20 : RFI actual 26 Aug 20 dengan PLN temporary, plan PLN permanent connect 9 sept, collecting doc RFIN 24.08.20 : 18.08.20 : PLN connection terkendala isu Manager PLN terkena covid, revisi plan RFI 24 Aug 10.08.20 : SRFIN sent 03.08.20 : 30.07.20 : SRFI actual, proses PLN connection 23.07.20 : on going RBS foundation 17.07.20 : ready to declare STO
448 |  | SUM-RI-BKN-1118 | 30597410031 | 041321109 | KOTO DAMAI | ACTIVE | TB | 101.2317 | 0.21975 | 40 | 10/80/130 | 2020 | JEDI 2020 [NEW] | RT004 RW002 Dusun I, Desa Koto Damai, Kec. Kampar Kiri Tengah, Kab. Kampar, Prov. Riau.Kecamatan Kampar Kiri TengahKabupaten Kampar | HTI | SUM-RI-BKN-1118 | KOTO DAMAI | COLO | TBG | WEST | SUMBAGTENG | Riau | KAB. KAMPAR | 6614850 | 2020-07-06 |  | 184 | > 150 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-05 | W32-2020 | Aug-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2021-01-08 | W02-2021 | Jan-2021 | FO (Change to MW as temp solution) | 2020-12-08 |  | 181130064289 | 6.6 |  | 2020-07-17 |  | 2020-08-04 | 2021-01-06 | W02-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.01.21 : RFIN sent 28.12.20 : 21.12.20 : 17.12.20 : PLN connection process 14.12.20 : PLN connection process 10.12.20 : FO civil work (backbone) 06.08.20 : 03.08.20 : 30.07.20 : Soft RFI, collecting doc SRFIN
432 |  | KAL-KB-PTK-0681 | 30596640031 | 200614109 | TBG_DSSIANTANHULU | ACTIVE | TB | 109.347 | 0.02208 | 44 | 10/90/290 | 2020 | JEDI 2020 [NEW] | JALAN KEBANGKITAN NASIONAL, RT/RW 005.028, KEL. SIANTAN HULU, KEC. PONTIANAK UTARA, KOTA. PONTIANAK, PROV. KALIMANTAN BARAT | HTI | KAL-KB-PTK-0681 | SIANTANHILIRTimur | COLO | TBG | JABO | KALIMANTAN | Kalimantan Barat | KOTA PONTIANAK | 6614850 | 2020-07-06 |  | 43 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-20 | W34-2020 | Aug-2020 | MW | 2020-07-16 |  | 211012282202 | 6.6 |  | 2020-07-13 |  |  | 2020-08-18 | W34-2020 |  | 2020-09-06 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18.08.20 : RFIN sent 17.08.20 : PLN connect, RFI actual, collecting doc RFIN 13.08.20 : Kwh mtr masih di tera di PLN dan belum dapat dipakai. plan connect Jumat 14 Aug 10.08.20 : plan connect PLN/RFI rabu 12 Aug 03.08.20 : SRFI actual, on going PLN process, plan RFI revisi 12 Aug 23.07.20 : RBS foundation done, delivery material 16.07.20 : mobilisasi dan preparation team 14.07.20 : proses input STIP Colo 06.07.20 : SPK release
438 |  | JAW-JI-SPG-4150 | 30596610031 | 161873109 | TOLANG | ACTIVE | SKP | 113.2076 | -6.9774 | 50 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Dusun Badauh, Desa Lar Lar, Kec Banyuates, Kab Sampang | HTI | JAW-JI-SPG-4150 | BANYUATES_TOLANG | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. SAMPANG | 6614847 | 2020-07-06 |  | 39 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-20 | W34-2020 | Aug-2020 | MW | 2020-07-16 |  | 517500713385 | 6.6 |  | 2020-07-13 |  |  | 2020-08-14 | W33-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.08.20 : RFI-N sent 13.08.20 : RFI actual, plan RFIN hr ini 06.08.20 : proses PLN Connection, revisi plan RFI 20 Aug 03.08.20 : SRFI actual 23.07.20 : ME on going 16.07.20 : preparation 14.07.20 : proses input STIP Colo 06.07.20 : SPK release
427 |  | SUL-SN-SNJ-1361 | 30596620031 | 280152109 | TBG LAMBARI | ACTIVE | SKP | 120.257 | -5.2672 | 50 | 25/115/235 | 2020 | JEDI 2020 [NEW] | Dusun Lambari, RT 001/RW 001, desa Tellu Limpoe, kec.Tellu Limpoe, kab.Sinjai, Prop Sulawesi Selatan | HTI | SUL-SN-SNJ-1361 | TELLU SINJAI | COLO | TBG | EAST | SULAWESI | Sulawesi Selatan | SINJAI | 6614847 | 2020-07-06 |  | 35 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-16 |  | 327600421145 | 6.6 |  | 2020-07-13 |  |  | 2020-08-10 | W33-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.08.20 : RFIN sent 06.08.20 : material galvanis dan ME & grounding on site, on going ME, revisi plan RFI 03.08.20 : wait material galvanis dan ME & grounding on site 30.07.20 : pondasi done, plan material on site 5 aug 20 karena jadwal kapal mundur 27.07.20 : RBS pondasi done, proses delivery material plan mos 30.07.2020 23.07.20 : RBS foundation OG. Material on delivery 20.07.20 : RBS pondasi OG, proses delivery material plan mos 30.07.2020 16.07.20 : mobilisasi team 14.07.20 : proses input STIP Colo 06.07.20 : SPK release
442 |  | JAW-JB-IDM-4041 | 30596630031 | 125410126 | WANASARI-BANGODUA | ACTIVE | TB | 108.2632 | -6.5014 | 40 | 90/210/330 | 2020 | JEDI 2020 [NEW] | BLOK DESA, RT/RW 004/002, DESA MALANGSARI, KEC. BANGODUA, INDRAMAYU, JAWA BARAT | HTI | JAW-JB-IDM-4041 | MALANGSARI BANGODUA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | INDRAMAYU | 6614850 | 2020-07-06 |  | 31 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | MW | 2020-07-16 |  | 534040044095 | 6.6 |  | 2020-07-13 |  |  | 2020-08-06 | W32-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.08.20 : RFIN sent 03.08.20 : 27.07.20 : 23.07.20 : SRFI actual, collecting doc SRFIN 16.07.20 : mobilisasi team & preparation 14.07.20 : proses input STIP Colo 06.07.20 : SPK release
321 |  | JAW-JI-LMJ-4227 | 30596590031 | 162136109 | KEPUHARJO | ACTIVE | SKP | 113.2124 | -8.1114 | 30 | 60/180/330 | 2020 | JEDI 2020 [NEW] | DUSUN SIDOMUKTI, RT 003 RW 003, DESA KARANGSARI, KEC SUKODONO, KAB. LUMAJANG, Kab. Lumajang | HTI | JAW-JI-LMJ-4227 | SUKODONO_KARANGSARI | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. LUMAJANG | 6614847 | 2020-07-06 |  | 217 | > 150 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-13 | W07-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 516021562442 | 6.6 |  | 2020-07-13 |  | 2020-08-14 | 2021-02-08 | W07-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : Proses register, waiting PLN survey 21.01.21 : PSB released, PLN connection OG 14.08.20 : email SRFI-N sent 03.08.20 : SRFI actual 23.07.20 : ME on going 14.07.20 : proses input STIP Colo 06.07.20 : SPK release
416 |  | JAW-JI-PMK-4123 | 30596600031 | 160205104 | TAGANGSER DAYA | ACTIVE | SKP | 113.5373 | -6.9269 | 36 | 0/60/170 | 2020 | JEDI 2020 [NEW] | Desa Tegangser Daya, Kecamatan Pasean, Kabupaten Pamekasan | HTI | JAW-JI-PMK-4123 | PASEAN_TAGANGSER_DAJA | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. PAMEKASAN | 6614847 | 2020-07-06 |  | 213 | > 150 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 517800628422 | 6.6 |  | 2020-07-13 |  | 2020-08-14 | 2021-02-04 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : survey done, proses pengajuan BPUJL 21.01.21 : PSB released, PLN connection OG 14.08.20 : email SRFI-N sent 03.08.20 : SRFI actual 23.07.20 : ME on going 14.07.20 : proses input STIP Colo 06.07.20 : SPK release
113 |  | SUM-RI-BLS-1127 | 30587320031 | 0413861003 | MUARA BASUNG_PINGGIR | ACTIVE | TB | 101.3112 | 1.109938 | 50 | 0/160/270 | 2020 | JEDI 2020 [NEW] | Jl.PT.Adei Div.1 (KMS) RT.04 RW.02, Desa Muara Basung, Kec. Pinggir, Kab.Bengkalis, Prov.Riau | HTI | SUM-RI-BLS-1127 | MUARA BASUNG_PINGGIR | B2S | TBG | WEST | SUMBAGTENG | Kep. Bangka Belitung | KAB. BENGKALIS | 6614554 | 2020-03-13 |  | 126 | 121 - 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-14 | W29-2020 | Jul-2020 | MW | 2020-06-12 |  | 182103499865 | 6.6 |  | 2020-07-13 |  |  | 2020-07-17 | W29-2020 |  | 2020-08-21 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.07.20 : RFIN sent 02.07.20 : connectt PLN/actual RFI, collecting doc RFIN, plan submit RFIN hari ini 2 jul 29.06.20 : erection top tower 27.06.20 : erection OG sampai leher, target connect PLN minggu depan 25.06.20 : erection OG 4 section. pondasi BTS minus finishing. BP PLN Paid 22.06.20 : 18.06.20 : curingtime, start erection 17.06.20 : PSB PLN release 15.06.20 : pouring concrete hari ini 11.06.20 : galian done, on going lantai kerja & bar bending 08.06.20 : 04.06.20 : 01.06.20 : CME start menunggu proses perijinan 28.05.20 : 25.05.20 : CME preparation, wait perijinan 14.05.20 : Rekom Done, Proses submit berkas ke perijinan 23.04.20 : 16.04.20 : Surat penawarn harga submit to PT ADEI 09.04.20 : validasi done, IW on going 02.04.20 : hunting, Lokasi site dilahan PT adei. Proses Persetujuan dr PT Adei. 25.03.20 : hunting
352 |  | SUM-SU-STB-2198 | 30596520031 | 021440109 | PALUK PAKIH | ACTIVE | TB | 98.325 | 3.7259 | 60 | 30/130/270 | 2020 | JEDI 2020 [NEW] | Dusun Bukit, Desa paluk pakih Babussalam, Kecamatan Batang Serangan, Kab. Langkat Prov. Sumatera Utara | HTI | SUM-SU-STB-2198 | BANJAR JAYA | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | LANGKAT | 6614850 | 2020-07-06 |  | 31 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-16 |  | 122140849271 | 6.6 |  | 2020-07-10 |  |  | 2020-08-06 | W32-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.08.20 : RFIN sent 27.07.20 : 25.07.20 : actual SRFI, PLN connection process 23.07.20 : on going RBS foundation 06.07.20 : SPK release
329 |  | SUM-AC-KTN-0375 | 30596420031 | 010701109 | KUTAMBARU | ACTIVE | TB | 97.8325 | 3.4822 | 55 | 30/100/280 | 2020 | JEDI 2020 [NEW] | Dusun Lawe Nderasi, Desa Kutambaru, Kecamatan Lawe Bulan, Kabupaten Aceh Tenggara, Provinsi Aceh | HTI | SUM-AC-KTN-0375 | KUTEMBARU BENCAWAN | COLO | TBG | WEST | SUMBAGUT | Aceh | ACEH TENGGARA | 6614850 | 2020-07-06 |  | 75 | 61 - 90 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-09-21 | W39-2020 | Sep-2020 | MW | 2020-07-16 |  | 113340193989 | 6.6 |  | 2020-07-10 |  | 2020-08-08 | 2020-09-19 | W38-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.09.20 : RFIN sent 17.09.20 : 14.09.20 : RFI actual, menunggu foto-foto KWH 10.09.20 : Proses pemasangan trafo PLN 07.09.20 : 31.08.20 : 27.08.20 : PLN OVB, plan RFI W2 sep 24.08.20 : 18.08.20 : proses PLN connection, plan RFI 26 aug 20 08.08.20 : email SRFI-N sent 30.07.20 : SRFI actual 23.07.20 : on going RBS foundation 20.07.20 : prepare start RBS foundation, flood area, use RBS foundation type 3 (H= + 2.0m) 06.07.20 : SPK release
304 |  | SUM-SS-PKB-1236 | 30596530031 | 070185104 | JALUR18 | ACTIVE | SMI | 105.1489 | -2.6013 | 60 | 20/190/290 | 2020 | JEDI 2020 [NEW] | Ds. Sidomulyo jalur 18, jembatan 4, kec. Muara padang, kab. Banyuasin, sumatera selatan | HTI | SUM-SS-PKB-1236 | MUARAPADANG SIDO MULYO20 | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | BANYUASIN | 6614853 | 2020-07-06 |  | 64 | 61 - 90 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-09-03 | W36-2020 | Sep-2020 | MW | 2020-07-16 |  | 142401775178 | 6.6 |  | 2020-07-10 |  |  | 2020-09-08 | W37-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.09.20 : RFIN sent 03.09.20 : 31.08.20 : RFI actual, collecting doc RFIN 27.08.20 : 26.08.20 : Panel & ME on site 24.08.20 : BP paid, plan RFI 28 Aug 13.08.20 : waiting material, plan sabtu 15 Aug on site 06.08.20 : pondasi RBS done, delivery material, additional transport karena menyusuri sungai Musi 27.07.20 : pabrikasi material 23.07.20 : Survey Lokasi & prepare material (Perairan, Plan Start 25 Jul 2020) 16.07.20 : mobilisasi team 06.07.20 : SPK release
411 |  | SUM-SS-PKB-1235 | 30596450031 | 071036109 | SUMSEL2014_2G29 | ACTIVE | TB | 105.1883 | -2.6124 | 60 | 20/190/290 | 2020 | JEDI 2020 [NEW] | Desa Margo Sugihan, RT/RW005/002, Kec. Muara Padang, Kab. Banyuasin | HTI | SUM-SS-PKB-1235 | MUARAPADANG MARGA SUGIHAN | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | BANYUASIN | 6614850 | 2020-07-06 |  | 59 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-09-03 | W36-2020 | Sep-2020 | MW | 2020-07-16 |  | 142401775186 | 6.6 |  | 2020-07-10 |  |  | 2020-09-03 | W36-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03.09.20 : RFIN sent 31.08.20 : RFI actual, collecting doc RFIN 27.08.20 : 26.08.20 : Panel & ME on site 24.08.20 : BP paid, plan RFI 28 Aug 13.08.20 : waiting material, plan sabtu 15 Aug on site 06.08.20 : pondasi RBS done, delivery material, additional transport karena menyusuri sungai Musi 03.08.20 : 27.07.20 : 23.07.20 : Survey Lokasi & prepare material (Perairan, Plan Start 25 Jul 2020) 16.07.20 : mobilisasi team 06.07.20 : SPK release
412 |  | SUM-SS-PKB-1233 | 30596440031 | 071016109 | SUMSEL2G54 | ACTIVE | TB | 104.8809 | -2.8902 | 50 | 20/120/220 | 2020 | JEDI 2020 [NEW] | Dusun II Parit Beton RT. 012 RW. 002, Kel. Pulau Borang, Kec. Banyuasin I, Kab. Banyuasin, Prop. Sumsel | HTI | SUM-SS-PKB-1233 | PEMATANG PALAS | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | BANYUASIN | 6614850 | 2020-07-06 |  | 59 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-09-03 | W36-2020 | Sep-2020 | MW | 2020-07-16 |  | 141103365219 | 7.7 |  | 2020-07-10 |  |  | 2020-09-03 | W36-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03.09.20 : RFIN sent 03.09.20 : 31.08.20 : RFI actual, collecting doc RFIN 27.08.20 : 26.08.20 : Panel & ME on site 24.08.20 : BP paid, plan RFI 28 Aug 13.08.20 : waiting material, plan sabtu 15 Aug on site 06.08.20 : pondasi RBS done, delivery material, additional transport karena menyusuri sungai Musi 03.08.20 : 27.07.20 : pabrikasi material 23.07.20 : Survey Lokasi & prepare material (Perairan, Plan Start 25 Jul 2020) 16.07.20 : mobilisasi team 06.07.20 : SPK release
282 |  | SUM-BE-KPH-0195 | 30596430031 | 090234109 | DESA TEBAT KARAI 2 | ACTIVE | TB | 102.6222 | -3.665 | 60 | 90/230/290 | 2020 | JEDI 2020 [NEW] | Dusun IV, Desa Talang Karet, Kec Tebat Karai, Kab Kepahiang, Prop Bengkulu | HTI | SUM-BE-KPH-0195 | TEBAT KARAI CURUP | COLO | TBG | WEST | LAMPUNG | Bengkulu | KEPAHIANG | 6614850 | 2020-07-06 |  | 52 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-08-27 | W35-2020 | Aug-2020 | MW | 2020-07-21 |  | 146205118159 | 6.6 |  | 2020-07-10 |  |  | 2020-08-27 | W35-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.08.20 : RFIN sent 24.08.20 : PLN connection terkendala isu stock KWH meter, plan RFI revisi 27 Aug 13.08.20 : 06.08.20 : actual sudah SRFI, PLN connection terkendala isu stock KWH meter PLN 27.07.20 : 23.07.20 : on going RBS foundation, delivery material plan on site 24 jul 20 16.07.20 : mobilisasi team 06.07.20 : SPK release
320 |  | SUM-SU-LBP-2227 | 30596470031 | 010346109 | KEMBANG JAYA | ACTIVE | TB | 97.7862 | 3.5301 | 55 | 140/250/320 | 2020 | JEDI 2020 [NEW] | Jalan Raya Blang Kejeren, Desa Kumbang Jaya, Kecamatan Badar, Kab Aceh Tenggara | HTI | SUM-SU-LBP-2227 | TUBUH AIR BADAR | COLO | TBG | EAST | SUMBAGUT | Aceh | ACEH TENGGARA | 6614850 | 2020-07-06 |  | 34 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-16 |  | 113340190909 | 6.6 |  | 2020-07-10 |  | 2020-08-08 | 2020-08-09 | W33-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.08.20 : 09.08.20 : RFIN sent 08.08.20 : email SRFI-N sent 07.08.20 : actual RFI, collecting doc RFIN 30.07.20 : SRFI actual 23.07.20 : on going RBS foundation 06.07.20 : SPK release
336 |  | SUM-SU-AKK-2200 | 30596400031 | 020115105 | MARTABAJUNGKAT | ACTIVE | MSI | 100.169 | 2.5185 | 55 | 150/280/350 | 2020 | JEDI 2020 [NEW] | Desa Kota Lapan, Kelurahan Labuhan Bilik, Kec. Panai Tengah, Kab. Labuhan Batu | HTI | SUM-SU-AKK-2200 | SEI MERDEKA | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | LABUHANBATU | 6614845 | 2020-07-06 |  | 33 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-16 |  | 125130516066 | 6.6 |  | 2020-07-10 |  |  | 2020-08-08 | W32-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.08.20 : RFIN sent 27.07.20 : 25.07.20 : actual SRFI, PLN connection process 23.07.20 : on going RBS foundation 06.07.20 : SPK release
396 |  | SUM-SU-KPI-2224 | 30596410031 | 020416109 | SIMATAHARI 2 | ACTIVE | SKP | 100.0481 | 1.805 | 50 | 10/110/270 | 2020 | JEDI 2020 [NEW] | Dusun Bakti, Desa Simatahari, Kec. Kota Pinang, Kab. Labuhan Batu Selatan, Sumatra Utara | HTI | SUM-SU-KPI-2224 | KOTAPINANG SIMATAHARI | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | LABUHANBATU SELATAN | 6614847 | 2020-07-06 |  | 32 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-16 |  | 125100659285 | 6.6 |  | 2020-07-10 |  |  | 2020-08-07 | W32-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.08.20 : RFIN sent 03.08.20 : 27.07.20 : 25.07.20 : actual SRFI, PLN connection process 23.07.20 : on going RBS foundation 06.07.20 : SPK release
362 |  | SUM-SU-STB-2195 | 30596510031 | 021284109 | PERKEBUNAN_TANJUNG_KELILING | ACTIVE | TB | 98.3247 | 3.5339 | 50 | 20/100/220 | 2020 | JEDI 2020 [NEW] | Jalan Dusun II Suka Mulia, Desa Perkebunan Tanjung Keliling, Kecamatan Salapian, Kabupaten Langkat, Provinsi Sumatera Utara | HTI | SUM-SU-STB-2195 | PERK. TJ. KELILING | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | LANGKAT | 6614850 | 2020-07-06 |  | 33 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-16 |  | 129040033023 | 6.6 |  | 2020-07-10 |  | 2020-08-06 | 2020-08-08 | W32-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.08.20 : RFIN sent 06.08.20 : email SRFI-N sent 27.07.20 : 25.07.20 : actual SRFI, PLN connection process 23.07.20 : on going RBS foundation 06.07.20 : SPK release
444 |  | SUM-SU-MDN-2195 | 30596480031 | 021903109 | YOUNG PANAH HIJAU | ACTIVE | TB | 98.6711 | 3.7241 | 30 | 90/180/260 | 2020 | JEDI 2020 [NEW] | JL Mekar Bumi Marelan(Kompleks Bumi Marelan Permai)Kelurahan Labuhan Deli Kecamatan Medan Maelan, Kota Medan(Kompleks Bumi Marelan Permai)Kelurahan Labuhan Deli Kecamatan Medan Maelan, Kota Medan | HTI | SUM-SU-MDN-2195 | LABUHAN DELI_MEDAN | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KOTA MEDAN | 6614850 | 2020-07-06 |  | 204 | > 150 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2021-01-08 | W02-2021 | Jan-2021 | 2021-01-20 | W04-2021 | Jan-2021 | FO (Change to MW as temp solution) | 2020-12-10 |  | 128020052863 | 6.6 |  | 2020-07-10 |  | 2020-08-07 | 2021-01-26 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : waiting KWH stock, OG PLN Multiguna, plan connect W5 Jan 07.01.21 : FO access RFS plan on W4 Jan confirmed by PM FO 04.01.21 : isu stock KWH kosong 28.12.20 :21.12.20 : 17.12.20 : PLN connection process 14.12.20 : PSB NY release, isu PLN overblast 10.12.20 : FO civil work (backbone) 07.08.20 : email SRFI-N sent 03.08.20 : 27.07.20 : 25.07.20 : actual SRFI, PLN connection menunggu konfirmasi XL 23.07.20 : on going RBS foundation (isu space, pondasi tidak bisa panjang 5 m) 06.07.20 : SPK release
424 |  | SUM-SU-LBP-2163 | 30596460031 | 021209109 | TANJUNG_MORAWA_A | ACTIVE | TB | 98.771 | 3.5359 | 32 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jalan Sumber Jaya, gang jaya, dusun IX,Desa Bangun Sari Baru, Kecamatan Tanjung Morawa, Kabupaten DeliserdangDusun IX, Desa Bangun SariKecamatan Tanjung Morawa | HTI | SUM-SU-LBP-2163 | BANGUN SARI_TJ.MORAWA | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. DELI SERDANG | 6614850 | 2020-07-06 |  | 199 | > 150 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2021-01-08 | W02-2021 | Jan-2021 | 2021-01-20 | W04-2021 | Jan-2021 | FO (Change to MW as temp solution) | 2020-12-10 |  | 126131168163 | 6.6 |  | 2020-07-10 |  | 2020-08-08 | 2021-01-21 | W04-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : PLN connected, prepare submit RFIN 07.01.21 : FO access RFS plan on W4 Jan confirmed by PM FO 04.01.21 : isu stock KWH kosong 28.12.20 : 21.12.20 : 17.12.20 : PLN connection process 14.12.20 : PSB NY release, isu PLN overblast 10.12.20 : FO civil work (backbone) 08.08.20 : email SRFI-N sent 03.08.20 : 30.07.20 : SRFI actual 23.07.20 : on going RBS foundation 06.07.20 : SPK release
292 |  | SUM-SU-STB-2192 | 30596500031 | 021282109 | EMPLASMEN_PASAR_IV_NAMO_TRASI | ACTIVE | TB | 98.4918 | 3.4798 | 50 | 10/90/170 | 2020 | JEDI 2020 [NEW] | Dusun II Pasar VIII, Desa Namo Terasi, Kecamatan Namo Terasi, Kecamatan Sei Bingai, Kabupaten Langkat, Provinsi Sumatera Utara | HTI | SUM-SU-STB-2192 | SEI BINGAI PASARVIII | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | LANGKAT | 6614850 | 2020-07-06 |  | 50 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-08-30 | W36-2020 | Aug-2020 | MW | 2020-07-16 |  | 129040033080 | 6.6 |  | 2020-07-10 |  |  | 2020-08-25 | W35-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.08.20 : RFIN sent 24.08.20 : 17.08.20 : CME stop, proses penyelesaian isu petir 30.07.20 : Pondasi done 27.07.20 : 23.07.20 : Comcase, proses penyelesaian issue 06.07.20 : SPK release
249 |  | SUM-SU-STB-2185 | 30596490031 | 021392109 | BEKULAP | ACTIVE | TB | 98.3992 | 3.5895 | 50 | 170/290/350 | 2020 | JEDI 2020 [NEW] | Dusun V Bekulap, Desa Bekulap, Kecamatan Selesai, Kabupaten Langkat, Provinsi Sumatera Utara | HTI | SUM-SU-STB-2185 | SELESAI KUTA PARIT | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | LANGKAT | 6614850 | 2020-07-06 |  | 31 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-16 |  | 129040032892 | 6.6 |  | 2020-07-10 |  |  | 2020-08-06 | W32-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.08.20 : RFIN sent 30.07.20 : SRFI actual 23.07.20 : on going RBS foundation 06.07.20 : SPK release
330 |  | SUM-SS-LLG-1228 | 30596390031 | 071049109 | LINGGAU10 | ACTIVE | TB | 103.0078 | -3.2442 | 50 | 20/120/230 | 2020 | JEDI 2020 [NEW] | Jl. Lintas Sumatera, Ds.Muara Beliti, Kec.Muara Beliti, Kab.Musi Rawas, SUMATERA SELATAN | HTI | SUM-SS-LLG-1228 | SIRING AGUNG_SUMSEL | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | KOTA LUBUKLINGGAU | 6614825 | 2020-07-02 |  | 45 | 31 - 60 days | 2020-08-01 | W31-2020 | Aug-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-07 | W32-2020 | Aug-2020 | 2020-08-20 | W34-2020 | Aug-2020 | MW | 2020-07-16 |  | 147800773953 | 6.6 |  | 2020-07-09 |  |  | 2020-08-16 | W34-2020 |  | 2020-09-22 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.08.20 : RFIN sent 14.08.20 : RFI actual, collecting doc RFIN 13.08.20 : proses eskalasi ke PLN, isu stock KWH meter, BP paid 06.08.20 : actual sudah SRFI, PLN connection terkendala isu stock KWH meter PLN, info PLN pengerjaan 5 hari setelah pembayaran, namun sampai sekarang masih belum di realisasikan maka laporan akan di teruskan ke rayon terkait. Sudah dilakukan complain juga melalui PLN123 27.07.20 : RBS foundation on going 23.07.20 : delivery material, plan start RBS foundation jumat 24 jul 20 16.07.20 : mobilisasi team 09.07.20 : under review RND HTI 02.07.20 : SPK release
248 |  | JAW-JB-NPH-3717 | 30596220031 | T000335 | BATUJAJAR | ACTIVE | SKP | 107.5029 | -6.8691 | 40 | 75/250/315 | 2020 | JEDI 2020 [NEW] | Jl. Raya Cimareme RT 01/07, Desa Cikandang Ngamprah, Bandung | HTI | JAW-JB-NPH-3717 | CIMAREME_NGAMPRAH | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614824 | 2020-07-02 |  | 67 | 61 - 90 days | 2020-08-01 | W31-2020 | Aug-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-10 | W33-2020 | Aug-2020 | 2020-08-31 | W36-2020 | Aug-2020 | MW | 2020-07-16 |  | 535852096634 | 6.6 |  | 2020-07-08 |  |  | 2020-09-07 | W37-2020 |  | 2020-09-27 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.09.20 : RFIN sent 07.09.20 : plan email RFIN hari ini 03.09.20 : 31.08.20 : 27.08.20 : RFI actual collecting doc RFIN 24.08.20 : 17.08.20 : SRFI actual 16 Aug 13.08.20 : proses dismantle existing shelter untuk space pondasi XL, material on site 10.08.20 : 06.08.20 : 03.08.20 : plan pembayaran kompensasi minggu ini dan lanjut start CME 30.07.20 : 27.07.20 : comcase/kompensasi colo 23.07.20 : preparation team & material, prepare dismantle existing shelter 16.07.20 : proses negosiasi dan dismantle existing shelter BTEL (XL di ijinkan colo jika menempati posisi exisying tenant, warga hanya mengijinkan ada 3 tenant di dalam site) 13.07.20 : blocking by LL - isu permintaan kompensasi colo 09.07.20 : STO, CME preparation 02.07.20 : SPK release
198 |  | JAW-JI-MJK-4141 | 30571220031 | 1642991003 | TROWULAN_BEJIJONG | ACTIVE | TB | 112.3701 | -7.5588 | 40 | 50/130/230 | 2020 | JEDI 2020 [NEW] | Dsn. Penanggalan RT.01 RW.01 Kel/Desa. Dukuh Dimoro Kec. Mojoagung Kab. Jombang | HTI | JAW-JI-MJK-4141 | TROWULAN_BEJIJONG | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. MOJOKERTO | 6614369 | 2020-01-13 |  | 248 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-07-03 | W27-2020 | Jul-2020 | 2020-09-15 | W38-2020 | Sep-2020 | MW | 2020-06-15 |  | 514500948793 | 16.5 |  | 2020-07-08 |  | 2020-06-24 | 2020-09-17 | W38-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.09.20 : RFIN sent, RFI actual dengan PLN Multiguna 14.09.20 : 10.09.20 : plan percepatan RFI Multiguna minggu ini 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : 24.08.20 : PLN connection menunggu review add work PLN by Power eng XL (eskalasi isu besar daya PLN terkait isu BP vs Biaya Investasi PLN) 17.08.20 : 06.08.20 : eskalasi isu besar daya PLN terkait isu BP vs Biaya Investasi PLN 23.07.20 : PLN meminta daya menjadi 10,6kva 09.07.20 : Proses PLN Connection, plan RFI 15 jul 20 29.06.20 : Proses PLN Connection 24.06.20 : email SRFI-N sent 22.06.20 : 18.06.20 : PLN Connection need perluasan jaringan 1 gawang 15.06.20 : SRFI actual 11.06.20 : tower erection on going 08.06.20 : 04.06.20 : 01.06.20 : erection tower 28.05.20 : prepare start erection 25.05.20 : 14.05.20 : 13.05.20 ; rebaring done, plan angkur tower mos 16/5, plan cor 18/5, mat pagar me ada di sby 08.05.20 : excavataion og 30.04.20 : bouwplank, proses perijinan 23.04.20 : 16.04.20 : 09.04.20 : proses perijinan, CME start after perijinan 02.04.20 : 25.03.20 : proses soiltest, collect legal doc 19.03.20 : IW clear, proses realisasi pembayaran IW, cek cellplan 11.03.20 : IW clear, proses realisasi pembayaran IW 28.02.20 : IW clear, proses review eskalasi sitac 26.02.20 : kand -7,559689 112,3684, IW clear 15 kk, proses submit eskalasi sitac 20.02.20 : IW Clear 10 kk, proses eskalasi sitac 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
255 |  | JAW-JB-CMS-4010 | 30596150031 | 125607109 | BO-GARDUJAYA-PANAWANGAN | ACTIVE | TB | 108.3839 | -7.0749 | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Dsn. Gardu, RT4 RW2, Desa Gardujaya, Kec Panawangan . | HTI | JAW-JB-CMS-4010 | JAYA PANAWANGAN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | CIAMIS | 6614780 | 2020-06-24 |  | 49 | 31 - 60 days | 2020-07-24 | W30-2020 | Jul-2020 | 2020-08-18 | W34-2020 | Aug-2020 | 2020-08-18 | W34-2020 | Aug-2020 | 2020-08-14 | W33-2020 | Aug-2020 | MW | 2020-07-16 |  | 532314657041 | 6.6 |  | 2020-07-07 |  |  | 2020-08-12 | W33-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.08.20 : RFIN sent 10.08.20 : collecting doc RFIN, plan declare RFIN 14 Aug 03.08.20 : RFI actual dengan Multiguna 30.07.20 : permanenisasi on going erection, install ME dan pondasi RBS XL on going, plan percepatan PLN multiguna 27.07.20 : start erection 23.07.20 : Permanenisasi : on going curingtime 16.07.20 : 13.07.20 : Permanenisasi : start galian, plan RFI colo 14 Aug 09.07.20 : STO, CME preparation 06.07.20 : 02.07.20 : under review TNP ALITA 29.06.20 : ERM on going 24.06.20 : SPK Release 24 jun 20
86 |  | JAW-JI-LMJ-4226 | 30571200031 | 1642971003 | KEDUNGJAJANG_SAWARAN_KULON | ACTIVE | TB | 113.2148 | -8.0027 | 50 | 110/180/270 | 2020 | JEDI 2020 [NEW] | Dusun Makam RT 01 RW 03, Desa Sawaran Kulon, Kecamatan Kedungjajang, Kabupaten Lumajang | HTI | JAW-JI-LMJ-4226 | KEDUNGJAJANG_SAWARAN_KULON | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. LUMAJANG | 6614369 | 2020-01-13 |  | 246 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-24 | W26-2020 | Jun-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-09-15 | W38-2020 | Sep-2020 | MW | 2020-07-16 |  | 516060548002 | 6.6 |  | 2020-07-07 |  | 2020-06-24 | 2020-09-15 | W38-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.09.20 : RFIN sent 14.09.20 : 10.09.20 : plan percepatan RFI Multiguna minggu ini 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : 24.08.20 : PLN connection menunggu review add work PLN by Power eng XL (eskalasi isu besar daya PLN terkait isu BP vs Biaya Investasi PLN) 17.08.20 : 06.08.20 : proses PLN Connection, revisi plan RFI 20 Aug 23.07.20 : proses PLN Connection 09.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL 29.06.20 : PLN connection menunggu konfirmasi dari XL 24.06.20 : email SRFI-N sent 22.06.20 : SRFI, wait confirmation XL for PLN connection 18.06.20 : 15.06.20 : SRFI actual 11.06.20 : 08.06.20 : tower erection on going 04.06.20 : 01.06.20 : tower erection on going 28.05.20 : prepare start erection 25.05.20 : 14.05.20 : 13.05.20 ; rebaring, mat angtem dan tower plan mos 14/5, plan cor 17/5, mat pagar me sdh ada di sby 08.05.20 : excavataion og 30.04.20 : bouwplank, proses perijinan 23.04.20 : 16.04.20 : 09.04.20 : proses perijinan, CME start after perijinan 02.04.20 : 25.03.20 : proses soiltest, collect legal doc 19.03.20 : IW clear, proses realisasi pembayaran IW, cek cellplan 11.03.20 : IW clear, proses realisasi pembayaran IW 28.02.20 : IW clear, proses review eskalasi sitac 26.02.20 : kand -8,0025833 113,21456, IW clear 16 kk, proses submit eskalasi sitac 20.02.20 : IW clear, proses eskalasi sitac 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
68 |  | JAW-JI-PBL-2915 | 30571270031 | 1643041003 | KADEMANGAN_KADEMANGAN | ACTIVE | TB | 113.1794 | -7.7836 | 40 | 0/100/290 | 2020 | JEDI 2020 [NEW] | Jl. Murbai Blok Sepeni RT 003 RW 005 Ds. Kademangan, Kec. Kademangan, Kota Probolingg | HTI | JAW-JI-PBL-2915 | KADEMANGAN_KADEMANGAN | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA PROBOLINGGO | 6614369 | 2020-01-13 |  | 388 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 513562155020 | 6.6 |  | 2020-07-07 |  | 2020-06-30 | 2021-02-04 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP paid, need perluasan jaringan -> penambahan 3 tiang 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : PLN Connection menunggu konfirmasi dari XL 30.06.20 : email SRFI-N sent 29.06.20 : PLN Connection menunggu konfirmasi dari XL 29.06.20 : 22.06.20 : SRFI, wait confirmation XL for PLN connection 18.06.20 : 15.06.20 : SRFI actual 11.06.20 : 08.06.20 : tower erection on going 04.06.20 : 01.06.20 : tower erection on going 28.05.20 : prepare start erection 25.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : proses design/bouwplank dan apply perijinan 23.04.20 : 16.04.20 : designpack dan bouwplank, proses perijinan 09.04.20 : on going soiltest, collecting berkas legal untuk apply perijinan 02.04.20 : 25.03.20 : renego BAN LL tetap di harga awal , resubit Capex, proses review eskalasi sitac 19.03.20 : 11.03.20 : 28.02.20 : kand A = IW clear, proses review eskalasi sitac 26.02.20 : kand A = IW Clear 14 kk/done signed 11 kk), proses submit eskalasi sitac 20.02.20 : kand A = IW On going 13.02.20 : kand A = TNP review 06.02.20 : kand A = validasi done, Candidate A RF TX OK
274 |  | SUM-KR-TBK-0585 | 30596100031 | 050507109 | DARUSSALAM MERAL | ACTIVE | TB | 103.3719 | 1.0432 | 35 | 30/100/240 | 2020 | JEDI 2020 [NEW] | Jl.Paya Sunan RT.03 RW.01 Kelurahan Darussalam Kecamatan Meral Barat Kab. Karimun Prov. Kepulauan RiauKelurahan DarussalamKecamatan Meral Barat | HTI | SUM-KR-TBK-0585 | MERAL KOTA_KARIMUN | COLO | TBG | WEST | SUMBAGTENG | Kep. Bangka Belitung | KAB. KARIMUN | 6614812 | 2020-07-01 |  | 38 | 31 - 60 days | 2020-07-31 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-08-10 | W33-2020 | Aug-2020 | MW | 2020-07-21 |  | 183051480507 | 6.6 |  | 2020-07-06 |  |  | 2020-08-08 | W32-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.08.20 : RFIN sent 06.08.20 : 04.08.20 : actual RFI, collecting doc RFIN 03.08.20 : 30.07.20 : proses SLO PLN 27.07.20 : proses PLN connection, nomor register belum release dr PLN 23.07.20 : 22.07.20 : SRFI actual, collecting doc SRFIN 20.07.20 : Pondasi BTS,Material ME on delivery 09.07.20 : STO, CME preparation 01.07.20 : SPK release
381 |  | SUM-LA-MGL-0990 | 30596090031 | 100290104 | RAWAPITU | ACTIVE | SMI | 105.571 | -4.2999 | 60 | 80/190/270 | 2020 | JEDI 2020 [NEW] | RAWAPITU SP2 RT 015/RK 006, DESA BATANG HARI, KECAMATAN RAWAPITU | HTI | SUM-LA-MGL-0990 | GUNUNG TAPA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG | 6614811 | 2020-07-01 |  | 36 | 31 - 60 days | 2020-07-31 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-21 |  | 173301814825 | 6.6 |  | 2020-07-06 |  |  | 2020-08-06 | W32-2020 |  | 2020-08-31 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.08.20 : RFI actual, RFIN sent 23.07.20 : SRFI actual, collecting doc RFIN dan on going proses PLN connection 16.07.20 : plan start CME hari ini, material ME grounding tray dan mounting on delivery 13.07.20 : delivery material, plan start CME Jumat 17 jul 09.07.20 : STO, CME preparation 01.07.20 : SPK release
370 |  | SUM-BB-SGL-0514 | 30596130031 | 080285109 | POLRES SUNGAI LIAT | ACTIVE | TB | 106.1064 | -1.8726 | 40 | 40/110/300 | 2020 | JEDI 2020 [NEW] | Jl. A. Yani, RT 003, Lingkungan Samratulangi, Kel. Sri menanti, Kec. Sungai liat, Kab. Bangka, Prov Bangka Belitung. | HTI | SUM-BB-SGL-0514 | SRI MENANTI_BANGKA | COLO | TBG | WEST | SUMBAGSEL | Kep. Bangka Belitung | KAB. BANGKA | 6614812 | 2020-07-01 |  | 216 | > 150 days | 2020-07-31 | W31-2020 | Jul-2020 | 2019-07-30 | W31-2019 | Jul-2019 | 2020-12-30 | W53-2020 | Dec-2020 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2020-12-10 |  | 161100640121 | 6.6 |  | 2020-07-06 |  | 2020-07-27 | 2021-02-02 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : eskalasi approval daya PLN 10.6 kVA, under review Power Eng XL 07.01.21 : FO access RFS plan on W4 Jan confirmed by PM FO 28.12.20 : 21.12.20 : 17.12.20 : PLN connection process 10.12.20 : MOS, FO civil preparation 03.08.20 : 27.07.20 : RFIN sent 4.07.20 : PONDASI RBS DONE, ME OG, PLAN SRFI 28 JUL 23.07.20 : RBS foundation done, delivery material ME tray grounding mounting, plan on site jumat 24 jul 20 16.07.20 : 13.07.20 : delivery material, plan start CME Jumat 17 jul 09.07.20 : STO, CME preparation 01.07.20 : SPK release
335 |  | JAW-JB-SNG-3898 | 20210300011 | 122227109 | MARSINU-Tmlsubang | ACTIVE | SKP | 107.7661 | -6.5487 | 40 | 20/140/230 | 2020 | JEDI 2020 [NEW] | Jl. Kp. Sugahegar Rt.63/17, Kel. Sukamela, Kec. Subang, Kab. Subang, Jawa Barat | HTI | JAW-JB-SNG-3898 | SUKAMELANG_SUBANG | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUBANG | 6614809 | 2020-07-01 |  | 209 | > 150 days | 2020-07-31 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 534254107148 | 6.6 |  | 2020-07-06 |  | 2020-07-16 | 2021-01-26 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : PSB released, PLN connection OG 03.08.20 : 27.07.20 : 23.07.20 : 20.07.20 : 16.07.20 : SRFI N sent, PLN Connection di proses setelah ada konfirmasi dari XL 13.07.20 : on going RBS foundation 09.07.20 : STO, CME preparation 01.07.20 : SPK release
308 |  | SUM-SU-MDN-2183 | 30596110031 | 020083109 | JL. RAHARJA EX SC-ME0073C | ACTIVE | TB | 98.6181 | 3.5464 | 35 | 30/120/250 | 2020 | JEDI 2020 [NEW] | JL.RAHARJA, KEL.TANJUNG SELAMAT, KEC.MEDAN TUNTUNGAN, KOTA MEDAN | HTI | SUM-SU-MDN-2183 | TANJUNG SELAMAT_MEDAN | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KOTA MEDAN | 6614812 | 2020-07-01 |  | 255 | > 150 days | 2020-07-31 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2021-02-20 | W08-2021 | Feb-2021 | 2021-03-12 | W11-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 129060088298 | 6.6 |  | 2020-07-06 |  | 2020-08-12 | 2021-03-13 | W11-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.02.21 : BP paid, OG penggantian trafo dan tiang, plan connect W1 Mar 18.02.21 : Trafo overblast, revise RFI plan W2 Mar 13.08.20 : SRFIN sent 30.07.20 : Pondasi done 27.07.20 : 23.07.20 : Comcase, proses penyelesaian issue 13.07.20 : 09.07.20 : STO, CME preparation 01.07.20 : SPK release
406 |  | SUM-AC-KTN-0376 | 30595980031 | 010135104 | SP_TG_JNGR | ACTIVE | SMI | 97.8262 | 3.4428 | 50 | 70/110/310 | 2020 | JEDI 2020 [NEW] | DESA BIAK MULI, KEC BAMBEL, KAB ACEH TENGGARA, NANGGRO ACEH DARUSALAM | HTI | SUM-AC-KTN-0376 | KUTA CINGKAM I | COLO | TBG | WEST | SUMBAGUT | Aceh | ACEH TENGGARA | 6614796 | 2020-06-26 |  | 62 | 61 - 90 days | 2020-07-26 | W31-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-28 | W35-2020 | Aug-2020 | MW | 2020-07-16 |  | 113340191977 | 6.6 |  | 2020-07-03 |  | 2020-08-08 | 2020-08-27 | W35-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.08.20 : RFIN sent 27.08.20 : RFI actual 26 Aug 20, collecting doc RFIN 24.08.20 : rev plan RFI 28 AUg 18.08.20 : proses PLN connection, plan RFI 20 aug 20 08.08.20 : email SRFI-N sent 03.08.20 : 30.07.20 : SRFI actual, plan submit SRFIN hari ini atau besok 27.07.20 : comcase, proses penyelesaian issue 23.07.20 : on going RBS foundation 13.07.20 : 09.07.20 : STO, CME preparation 02.07.20 : under review power 29.06.20 : ERM on going 26.06.20 : SPK Release 26 jun 20
238 |  | SUM-SU-BLG-2130 | 30595990031 | 022309123 | BALIGE 1 | ACTIVE | TB | 99.0735 | 2.3481 | 40 | 80/180/240 | 2020 | JEDI 2020 [NEW] | Desa Lumban Bulbul, Kec. Balige, Kab. Toba Samosir, Prov. Sumatera Utara | HTI | SUM-SU-BLG-2130 | BALIGE LUMBAN BULBUL | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | TOBA SAMOSIR | 6614798 | 2020-06-26 |  | 41 | 31 - 60 days | 2020-07-26 | W31-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-08 | W32-2020 | Aug-2020 | MW | 2020-07-16 |  | 123110353714 | 6.6 |  | 2020-07-03 |  |  | 2020-08-06 | W32-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.08.20 : RFIN sent 30.07.20 : SRFI actual, plan submit RFIN hari ini atau besok 23.07.20 : on going RBS foundation 13.07.20 : 09.07.20 : STO, CME preparation 02.07.20 : under review power 29.06.20 : ERM on going 26.06.20 : SPK Release 26 jun 20
315 |  | JAW-JI-BYW-4131 | 30595970031 | 160691104 | KARANGSARI | ACTIVE | SMI | 114.2153 | -8.337 | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Desa Parijatah Kulon Kecamatan Srono, Kab Banyuwangi | HTI | JAW-JI-BYW-4131 | SRONO PARIJATAH KULON | COLO | TBG | EAST | JATIM | Jawa Timur | BANYUWANGI | 6614792 | 2020-06-26 |  | 223 | > 150 days | 2020-07-26 | W31-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 516711456525 | 6.6 |  | 2020-07-03 |  | 2020-08-14 | 2021-02-04 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP paid 21.01.21 : PSB released, PLN connection OG 14.08.20 : email SRFI-N sent 23.07.20 : SRFI actual, collecting doc SRFIN, PLN connection proses menunggu konfirmasi dari XL 13.07.20 : 09.07.20 : BTS foundation on going 08.07.20 : CME preparation 02.07.20 : under review Civil Huawei 29.06.20 : ERM on going 26.06.20 : SPK Release 26 jun 20
300 |  | SUL-SN-SKG-1354 | 30595960031 | T002780 | HCPTSS-212362 | ACTIVE | TB | 119.938 | -3.9661 | 50 | 5/90/180 | 2020 | JEDI 2020 [NEW] | Jl. Poros Belawa Dusun Siduntung Desa Ongkoe Kec. Belawa Kab. Wajo | HTI | SUL-SN-SKG-1354 | ONGKOE BELAWA | COLO | TBG | EAST | SULAWESI | Sulawesi Selatan | WAJO | 6614794 | 2020-06-26 |  | 221 | > 150 days | 2020-07-26 | W31-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 322400380627 | 6.6 |  | 2020-07-03 |  | 2020-08-05 | 2021-02-02 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : PSB released, plan PLN connect W2 Feb 21.01.21 : PSB released, proses register PLN 05.08.20 : email SRFI-N sent 06.08.20 : 27.07.20 : SRFI actual, collecting doc SRFIN, PLN connection menunggu konfirmasi XL (FO readiness XL) 23.07.20 : BTS foundation done, material on delivery 20.07.20 : RBS pondasi done, plan SRFI 25.07.2020 16.07.20 : finishing BTS foundation, plan on site material ME grounding Tray Mounting minggu depan 22 jul 20 13.07.20 : BTS foundation OG, material on delivery 09.07.20 : CME preparation 06.07.20 : 02.07.20 : under review power 29.06.20 : ERM on going 26.06.20 : SPK Release 26 jun 20
405 |  | SUL-SN-WTP-1344 | 30595840031 | 280665126 | SMP NEGERI 4 SIBULUE | ACTIVE | TB | 120.395 | -4.658 | 50 | 50/130/215 | 2020 | JEDI 2020 [NEW] | Jl. Hombes, RT. 03 RW.03 Dusun Kajuara, Desa Pakkasalo, Kec. Sibulue, Kab. BoneKec. sibulue, Kab. Bone | HTI | SUL-SN-WTP-1344 | PAKKASALOSIBULUE | COLO | TBG | EAST | SULAWESI | Sulawesi Barat | BONE | 6614794 | 2020-06-26 |  | 234 | > 150 days | 2020-07-26 | W31-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-12 | W07-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | MULTIGUNA |  |  | 2020-07-02 |  | 2020-08-05 | 2021-02-15 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.02.21 : RFI (PLN Permanent), prepare RFIN 04.02.21 : PSB revisi released, PLN connection OG 26.01.21 : waiting PSB revisi daya 7.7 kVA 21.01.21 : PSB released, PLN connection OG 21.01.21 : PSB released, proses connect PLN 05.08.20 : email SRFI-N sent 06.08.20 - 29.07.20 : SRFI actual, collecting doc SRFIN, PLN connection menunggu konfirmasi XL (FO readiness XL) 27.07.20 : ME on going 23.07.20 : BTS foundation done, material on port Makasar 20.07.20 : bts pondasi done, proses delivery material. Plan MOS 30.07.2020, akan dilakukan percepatan karena target SRFI 25 jun 16.07.20 : finishing BTS foundation, plan on site material ME grounding Tray Mounting minggu depan 22 jul 20 13.07.20 : BTS foundation OG, material on delivery 09.07.20 : CME preparation 06.07.20 : 02.07.20 : under review power 29.06.20 : ERM on going 26.06.20 : SPK Release 26 jun 20
189 |  | SUM-SS-MRE-1215 | 30587330031 | 0715501003 | TANJUNG RAJA_ENIM | ACTIVE | TB | 103.7984 | -3.7044 | 50 | 190/260/340 | 2020 | JEDI 2020 [NEW] | Dusun I RT. 001/001 Desa Tanjung Raja Kec. Muara Enim Kab. Muara Enim Prov. Sumatera Selatan | HTI | SUM-SS-MRE-1215 | TANJUNG RAJA_ENIM | B2S | TBG | WEST | SUMBAGSEL | Kep. Bangka Belitung | Kab. Muara Enim | 6614554 | 2020-03-13 |  | 174 | > 150 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-09-05 | W36-2020 | Sep-2020 | MW | 2020-06-24 |  | 147100635880 | 6.6 |  | 2020-07-01 |  | 2020-07-14 | 2020-09-03 | W36-2020 |  | 2020-09-21 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03.09.20 : RFIN sent 03.09.20 : RFI actual, collecting doc RFIN 31.08.20 : issue kwh di muara enim, info manager PLN rayon KWH meter sudah ready,tapi masih menunggu antrian utk instalasi, saat ini di muara enim ada 300an pelanggan 3phase yg antri dipasang. 27.08.20 : 24.08.20 : proses perluasan jaringan PLN, rev plan RFI 30 Aug, plan percepatan di 28 Aug 13.08.20 : proses koordinasi/nego ke PLN 06.08.20 : isu perluasan jaringan (BP<Biaya investasi PLN) sehingga masuk daftar tunggu atau permohonan sambungan daya > 6.6 kVA 03.08.20 : proses PLN connection 14.07.20 : email SRFI-N sent 13.07.20 : SRFI 09.07.20 : Sk PLN release 7 jul, proses PLN connection 06.07.20 : tower erection 02.07.20 : curingtime 29.06.20 : rebarring on going 25.06.20 : excavation 22.06.20 : [MIM/Risk RFI Jun] plan RFI 10 jul 22.06.20 : 18.06.20 : Rekom done, proses perijinan, plan start CME minggu depan 15.06.20 : on going proses rekom dan realisasi IW, plan senin 15/06/2020 11.06.20 : on going proses rekom dan realisasi IW 08.06.20 : on going proses rekom 04.06.20 : 01.06.20 : rekom, team prepare rapid test 28.05.20 : proses rekom on going 25.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : 23.04.20 : 16.04.20 : plan Senin 20 Apr, eskalasi done dan start rekom 09.04.20 : IW clear, proses submit eskalasi sitac 02.04.20 : iw on going 20.03.20 : Hunting
194 |  | SUM-LA-KTB-1117 | 30581610031 | 1011171003 | SINAR OGAN_ATAS | ACTIVE | TB | 105.034 | -4.7805 | 50 | 140/230/330 | 2020 | JEDI 2020 [NEW] | Bumi Jaya RT. 002/002, Desa Bumi Jaya, Kec. Abung Timur, Kab. Lampung Utara, Prov. Lampung. | HTI | SUM-LA-KTB-1117 | SINAR OGAN_ATAS | B2S | TBG | WEST | LAMPUNG | Lampung | KAB. LAMPUNG UTARA | 6614479 | 2020-02-13 |  | 268 | > 150 days | 2020-07-12 | W29-2020 | Jul-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-21 | W30-2020 | Jul-2020 | 2020-11-17 | W47-2020 | Nov-2020 | MW | 2020-06-24 |  | 173001419781 | 6.6 |  | 2020-07-01 |  | 2020-07-01 | 2020-11-07 | W45-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.11.20 : RFIN sent 7 Nov 09.11.20 : 05.11.20 : 02.11.20 : 29.10.20 :26.10.20 : aktual RFI, proses penyusunan doc RFIN 22.10.20 : proses penyambungan PLN, target connect 23 Oct 19.10.20 : 15.10.20 : 12.10.20 : update dari PLN untuk stock KWH meter tahap selanjutnya pengiriman minggu ini dan proses tera minggu depan, plan connect PLN max 23 oct 20 05.10.20 : masih isu stock KWH meter, plan KWH meter ready minggu ini 01.10.20 : masih isu stock KWH meter dan info dari UIW PLN Lampung ketersediaan material KWH meter masih menunggu antrian uji material dan mulai pengiriman material awal oktober secara bertahap. revisi plan RFI 10 oct 28.09.20 : 24.09.20 : 21.09.20 : isu stock KWH meter, revisi plan connect PLN 30 sep 20 17.09.20 : 14.09.20 : isu stock material KWH meter rayon Kota Bumi Lampung sesuai SJ PLN 10 sep 20, re-plan RFI 18 Sep 20 07.09.20 : 03.09.20 : 31.08.20 : perluasan jaringan done, issue kwh meter, plan RFI minggu ini 27.08.20 : 24.08.20 : proses perluasan jaringan PLN, rev plan RFI 30 Aug, plan percepatan di 28 Aug 13.08.20 : proses koordinasi/nego ke PLN 06.08.20 : isu perluasan jaringan (BP<Biaya investasi PLN) sehingga masuk daftar tunggu atau permohonan sambungan daya > 6.6 kVA 13.07.20 : 09.07.20 : Sk PLN release 7 jul sehingga plan RFI revisi jadi 21 jul (SK PLN date + 14D), proses PLN connection 06.07.20 : 02.07.20 : waiting SK PLN release from XL 01.07.20 : email SRFI-N sent 29.06.20 : SRFI, collecting doc SRFIN 25.06.20 : ME on going, plan SRFI 27 jun 22.06.20 : 18.06.20 : erection on going 15.06.20 : curingtime, plan start erection 11.06.20 : pouring concrete foundation 04.06.20 : CME preparation, wait perijinan 01.06.20 : 28.05.20 : 25.05.20 : CME preparation, wait perijinan 14.05.20 : proses perijinan, start CME preparation 08.05.20 : 30.04.20 : 23.04.20 : 16.04.20 : start rekom, paralel approval eskalasi sitac 09.04.20 : IW clear, proses submit eskalasi sitac 02.04.20 : 25.03.20 : IW clear, proses nego dan review sitac 19.03.20 : IW clear, proses eskalasi sitac 11.03.20 : IW on going 20.02.20 : on going survey, hunting 13.02.20 : SPK released
151 |  | SUM-SS-KAG-1203 | 30581620031 | 0715451003 | SEDYOMULYO | ACTIVE | TB | 105.0391 | -3.6566 | 50 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Sedyo Mulyo, RT. 007 RW. 003, Desa Sedyo Mulyo, Kecamatan Mesuji Raya, Kabupaten Ogan Komering Ilir, Provinsi Sumatera Selatan. | HTI | SUM-SS-KAG-1203 | SEDYOMULYO | B2S | TBG | WEST | SUMBAGSEL | Sumatera Selatan | KAB. OGAN KOMERING I | 6614479 | 2020-02-13 |  | 201 | > 150 days | 2020-07-12 | W29-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-31 | W36-2020 | Aug-2020 | MW | 2020-06-24 |  | 149300087909 | 6.6 |  | 2020-07-01 |  | 2020-07-13 | 2020-09-01 | W36-2020 |  | 2020-09-12 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.09.20 : RFIN sent 31.08.20 : RFI actual, collecting doc RFIN 27.08.20 : 24.08.20 : proses perluasan jaringan PLN, rev plan RFI 30 Aug, plan percepatan di 28 Aug 13.08.20 : proses koordinasi/nego ke PLN 06.08.20 : isu perluasan jaringan (BP<Biaya investasi PLN) sehingga masuk daftar tunggu atau permohonan sambungan daya > 6.6 kVA 03.08.20 : proses PLN connection 13.07.20 : email SRFI-N sent 09.07.20 : Sk PLN release 7 jul, proses PLN connection 06.07.20 : tower erection, waiting SK PLN release from XL 02.07.20 : curingtime 29.06.20 : 25.06.20 : rebarring 22.06.20 : [MIM/Risk RFI Jun] start excavation,plan RFI 15 jul 22.06.20 : 18.06.20 : prepare galian, CME ny start, proses perijinan 15.06.20 : soiltest done, APD ongoing 11.06.20 : rekom done, plan besok soiltest 08.06.20 : on going proses rekom 04.06.20 : 01.06.20 : rekom, team prepare rapid test 28.05.20 : 25.05.20 : rekom on going 14.05.20 : 08.05.20 : 30.04.20 : 23.04.20 : 16.04.20 : plan Senin 20 Apr, eskalasi done dan start rekom 09.04.20 : IW clear, proses submit eskalasi sitac 02.04.20 : 25.03.20 : IW on going, plan iw clear 29/3 19.03.20 : IW on going, plan iw clear sabtu 21/3 11.03.20 : IW on going 20.02.20 : on going survey, hunting 13.02.20 : SPK released
319 |  | JAW-JI-JBG-4151 | 30595750031 | 160752104 | KEDUNGBOTO | ACTIVE | SMI | 112.1783 | -7.5143 | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | DSN. BALONG SARI RT/RW 02/01 JOMBANGDS. BALONGSARI KEC. MAGALUH, | HTI | JAW-JI-JBG-4151 | MEGALUH BALONGSARI | COLO | TBG | EAST | JATIM | Jawa Timur | JOMBANG | 6614792 | 2020-06-26 |  | 229 | > 150 days | 2020-07-26 | W31-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-13 | W07-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 514531725092 | 6.6 |  | 2020-06-30 |  | 2020-08-14 | 2021-02-10 | W07-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : survey PLN done, proses pengajuan BPUJL 21.01.21 : PSB released, PLN connection OG 14.08.20 : email SRFI-N sent 23.07.20 : SRFI actual, collecting doc SRFIN, PLN connection proses menunggu konfirmasi dari XL 13.07.20 : 09.07.20 : BTS foundation on going 06.07.20 : preparation 02.07.20 : Go CME 29.06.20 : ERM on going 26.06.20 : SPK Release 26 jun 20
288 |  | JAW-JI-BJN-4272 | 30595760031 | 160058109 | DS. DOLOK GEDE EX DS TRACAL (SPLIT BULUBRANGSI_2) | ACTIVE | TB | 111.7056 | -7.2494 | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Dsn Kuluhan RT.13/RW.04 Desa Dolok GedeKecamatan Tambak Rejo | HTI | JAW-JI-BJN-4272 | TAMBAKREJO DOLOKGEDE | COLO | TBG | EAST | JATIM | Jawa Timur | BOJONEGORO | 6614794 | 2020-06-26 |  | 227 | > 150 days | 2020-07-26 | W31-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-13 | W07-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 518050968326 | 6.6 |  | 2020-06-30 |  | 2020-08-14 | 2021-02-08 | W07-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : survey done, proses pengajuan BPUJL 21.01.21 : PSB released, PLN connection OG 14.08.20 : email SRFI-N sent 06.08.20 : 23.07.20 : SRFI actual, collecting doc SRFIN, PLN connection proses menunggu konfirmasi dari XL (FO readiness XL) 13.07.20 : 09.07.20 : BTS foundation on going 06.07.20 : preparation 02.07.20 : Go CME 29.06.20 : ERM on going 26.06.20 : SPK Release 26 jun 20
101 |  | SUL-SN-PKJ-1256 | 30587310031 | 2811031003 | MANGGALUNG | ACTIVE | TB | 119.6162 | -4.6127 | 50 | 0/120/300 | 2020 | JEDI 2020 [NEW] | Kampung Baru RT.012/RW.006, Desa Manggalung, Kec.Mandalle, Kab.Pangkep, Prop. Sul Sel | HTI | SUL-SN-PKJ-1256 | MANGGALUNG | B2S | TBG | EAST | SULAWESI | Kep. Bangka Belitung | KAB. PANGKAJENE DAN | 6614554 | 2020-03-13 |  | 116 | 91 - 120 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-06-25 | W26-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 2020-06-12 |  | 320400139759 | 6.6 |  | 2020-06-26 |  |  | 2020-07-07 | W28-2020 |  | 2020-08-05 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.07.20 : RFIN sent 06.07.20 : 02.07.20 : RFI ACTUAL, plan submit RFIN 6 jul 29.06.20 : proses PLN connection 25.06.20 : SRFI, collecting doc RFIN, proses PLN connection 22.06.20 : Install Fence & Yard OG, ME OG. Paralel fu for PLN Permanent. Plan RFI BTS for ON Air on 30 June 2020 18.06.20 : 17.06.20 : Go RFI, PSB PLN release, Painting Tower OG. Backfill OG, parael Foundation Fence OG and install Pole fence OG 15.06.20 : Painting Tower OG. Backfill OG, parael Foundation Fence OG and install Pole fence OG 11.06.20 : Erection OG (90 %). Backfill OG, paralel Foundation Fence OG and install Pole fence OG. 08.06.20 : erection on going 04.06.20 : Erector Team OS, Sortir Mat OG, Plan Start Erection on 04 june 2020. Plan SRFI XL on 22 June 2020 01.06.20 : curingtime 29.05.20 : pouring concrete tower foundation 28.05.20 : rebarring done 21.05.20 : Rebaring OG. 18.05.20 : rebarring, delivery material tower 14.05.20 : excavation done, on going lantai kerja 08.05.20 : 06.05.20 : Kandidat A, RFL, Prepare Join Survey PTSP Before RFC 30.04.20 : bouwplank, rekom camat done 23.04.20 : bouwplank 16.04.20 : 09.04.20 : Kandidat A, Proses Rekom Lurah, SST 52 02.04.20 : 25.03.20 : IW on going
190 |  | SUL-SN-PIN-1283 | 30587280031 | 2811001003 | TANRA TUO | ACTIVE | TB | 119.602 | -3.7422 | 50 | 50/180/270 | 2020 | JEDI 2020 [NEW] | Dusun Cempa Dao RT.02, Desa Tanra Tuo, Kec. Cempa, Kab. Pinrang, Propinsi Sulawesi Selatan. | HTI | SUL-SN-PIN-1283 | TANRA TUO | B2S | TBG | EAST | SULAWESI | Kep. Bangka Belitung | KAB. PINRANG | 6614554 | 2020-03-13 |  | 115 | 91 - 120 days | 2020-08-10 | W33-2020 | Aug-2020 | 2020-06-25 | W26-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 2020-06-12 |  | 324300205817 | 6.6 |  | 2020-06-26 |  | 2020-06-15 | 2020-07-06 | W28-2020 |  | 2020-07-17 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.07.20 : RFIN sent 02.07.20 : RFI ACTUAL hari ini, plan submit RFIN 4 jul 29.06.20 : PSB Register done. PLN Survey 25 jun, plan RFI BTS for ON Air on 30 June 2020. 22.06.20 : PSB Register to PLN. Plan RFI BTS for ON Air on 30 June 2020 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 15.06.20 : SRFIN sent 11.06.20 : collecting doc SRFIN 08.06.20 : plan SRFI hari ini 04.06.20 : Fence & Yard OG. PLan SRFI on 11 June 2020. 01.06.20 : 28.05.20 : erection done, on going tower painting 21.05.20 : 19.05.20 : erection 50% 14.05.20 : pouring done, curring time 08.05.20 : rebaring OG. Plan SRFI on 11 June 2020. 30.04.20 : Kandidat B, RFC Done, Submit STO Waiting Dokumentasi Bowplank 23.04.20 : bouwplank 16.04.20 : 09.04.20 : Kandidat B, Proses Rekom Lurah, SST 52 02.04.20 : 25.03.20 : IW on going
347 |  | JAW-JI-KNR-4275 | 30595510031 | 160544109 | NGARINGAN GANDUSARI TBG | ACTIVE | TB | 112.3096 | -8.019 | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | dsn. Sukosari, RT.01 RW.01, ds. ngusri, kel.gadungan, kec.gandusari, kec. blitar | HTI | JAW-JI-KNR-4275 | GANDUSARI GADUNGAN | COLO | TBG | EAST | JATIM | Jawa Timur | BLITAR | 6614780 | 2020-06-24 |  | 33 | 31 - 60 days | 2020-07-24 | W30-2020 | Jul-2020 | 2020-07-23 | W30-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | MW | 2020-07-16 |  | 514080956700 | 6.6 |  | 2020-06-25 |  |  | 2020-07-27 | W31-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.07.20 : RFIN sent 23.07.20 : SRFI actual, collecting doc SRFIN, proses PLN 16.07.20 : 13.07.20 : 09.07.20 : BTS foundation on going 06.07.20 : preparation 02.07.20 : Go CME 29.06.20 : ERM on going 24.06.20 : SPK Release 24 jun 20
327 |  | JAW-JI-KNR-4277 | 30595550031 | 160387104 | KRISIK | ACTIVE | SKP | 112.3619 | -7.9693 | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Krisik Ngantang, dsn. Wonorejo, RT/RW 02/01, Desa Krisik, Kec. Gandusari, Kab. Blitar | HTI | JAW-JI-KNR-4277 | GANDUSARI KRISIK | COLO | TBG | EAST | JATIM | Jawa Timur | BLITAR | 6614782 | 2020-06-24 |  | 30 | < 30 days | 2020-07-24 | W30-2020 | Jul-2020 | 2020-07-23 | W30-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | MW | 2020-07-16 |  | 514080956696 | 6.6 |  | 2020-06-25 |  |  | 2020-07-24 | W30-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.07.20 : RFIN sent 23.07.20 : SRFI actual, collecting doc SRFIN, proses PLN 16.07.20 : 13.07.20 : 09.07.20 : BTS foundation on going 06.07.20 : preparation 02.07.20 : Go CME 29.06.20 : ERM on going 24.06.20 : SPK Release 24 jun 20
437 |  | JAW-JI-KPN-4375 | 30595540031 | 160527109 | TLOGOREJO TBG | ACTIVE | TB | 112.4967 | -8.2076 | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jalan Puring, dusun dadapan, RT.15 RW.04, Desa Tlogorejo, Kec. Pagak, Kab. Malang | HTI | JAW-JI-KPN-4375 | PAGAK TLOGOREJO | COLO | TBG | EAST | JATIM | Jawa Timur | MALANG | 6614780 | 2020-06-24 |  | 30 | < 30 days | 2020-07-24 | W30-2020 | Jul-2020 | 2020-07-23 | W30-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | MW | 2020-07-16 |  | 513051670073 | 6.6 |  | 2020-06-25 |  |  | 2020-07-24 | W30-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.07.20 : RFIN sent 23.07.20 : SRFI actual, collecting doc SRFIN, proses PLN 16.07.20 : 13.07.20 : 09.07.20 : BTS foundation on going 06.07.20 : preparation 02.07.20 : Go CME 29.06.20 : ERM on going 24.06.20 : SPK Release 24 jun 20
348 |  | JAW-JI-KPN-4346 | 30595530031 | 161215109 | NGROTO | ACTIVE | TB | 112.4548 | -7.8583 | 50 | 20/90/280 | 2020 | JEDI 2020 [NEW] | Ds. PUJON KIDUL, Kec. PUJON, MALANG-JAWA TIMUR | HTI | JAW-JI-KPN-4346 | PUJON_PUJONKIDUL | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. MALANG | 6614780 | 2020-06-24 |  | 30 | < 30 days | 2020-07-24 | W30-2020 | Jul-2020 | 2020-07-23 | W30-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | MW | 2020-07-16 |  | 513031011212 | 6.6 |  | 2020-06-25 |  |  | 2020-07-24 | W30-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.07.20 : RFIN sent 23.07.20 : SRFI actual, collecting doc SRFIN, proses PLN 16.07.20 : 13.07.20 : 09.07.20 : BTS foundation on going 06.07.20 : preparation 02.07.20 : Go CME 29.06.20 : ERM on going 24.06.20 : SPK Release 24 jun 20
260 |  | JAW-JI-KNR-4278 | 30595520031 | 160516109 | BUMIREJO KESAMBEN TBG | ACTIVE | TB | 112.4182 | -8.0869 | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Sumberbendo RT 004 RW 03, Ds bumirejo, Kec Kesamben, Kab Blitar | HTI | JAW-JI-KNR-4278 | SELOREJO BANJARSARI | COLO | TBG | EAST | JATIM | Jawa Timur | BLITAR | 6614780 | 2020-06-24 |  | 30 | < 30 days | 2020-07-24 | W30-2020 | Jul-2020 | 2020-07-23 | W30-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | MW | 2020-07-16 |  | 513100309989 | 6.6 |  | 2020-06-25 |  |  | 2020-07-24 | W30-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.07.20 : RFIN sent 23.07.20 : SRFI actual, collecting doc SRFIN, proses PLN 16.07.20 : 13.07.20 : 09.07.20 : BTS foundation on going 06.07.20 : preparation 02.07.20 : Go CME 29.06.20 : ERM on going 24.06.20 : SPK Release 24 jun 20
3 |  | JAW-JB-CBN-3843 | 30571050031 | 1260841003 | ARGASUNYA CIREBON | ACTIVE | TB | 108.5473 | -6.7881 | 30 | 20/210/300 | 2020 | JEDI 2020 [NEW] | Benda Kebon Kelapa Lebak Ngok, RT 001 RW.011, Kelurahan Argasunya, Kec. Harjamukti, Kota Cirebon | HTI | JAW-JB-CBN-3843 | ARGASUNYA | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA CIREBON | 6614369 | 2020-01-13 |  | 220 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-07-03 | W27-2020 | Jul-2020 | 2020-08-19 | W34-2020 | Aug-2020 | MW | 2020-06-15 |  | 533113458609 | 6.6 |  | 2020-06-23 |  | 2020-07-15 | 2020-08-20 | W34-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.08.20 : RFIN sent (MULTIGUNA) plan PLN permanent 1 sept 17.08.20 : actual RFI dengan connect PLN Multiguna, collecting doc RFIN, plan submit RFIN 19 Aug 10.08.20 : 27.07.20 : 23.07.20 : PLN connection masih terkendala isu stock kwh meter kosong 16.07.20 : 15.07.20 : email SRFI-N sent 13.07.20 : PLN connection masih terkendala isu stock kwh meter kosong 09.07.20 : plan PLN connect 20 jul 20, isu stock kwh meter kosong 06.07.20 : 02.07.20 : 29.06.20 : 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 15.06.20 : Soft RFI 11.06.20 : ME & Grounding on going 08.06.20 : cat tower Og, pondsi BTS og, pagar OG 04.06.20 : cat tower Og, pondsi BTS og, pagar OG 01.06.20 : 28.05.20 : 25.05.20 : erection on going 21.05.20 : 15.05.20 : curing time 14.05.20 : rebarring 08.05.20 : 30.04.20 : galian pondasi 23.04.20 : 16.04.20 : 09.04.20 : CME start after proses perijinan 06.04.20 : isu proses rekom KKOP 02.04.20 : RFC, proses perijinan, prepare for start CME, tower 52m 25.03.20 : proses rekom untuk penurunan ketinggian 19.03.20 : area cirebon, menunggu suket camat 19 mar dan rekom BPM PTSP release untuk start CME 11.03.20 : Rekom done, RFC, proses perijinan 20.02.20 : IW clear 13.02.20 : TNP review 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 29.01.20 : kand A = submit 108°32'51.99"E - 6°47'11.30"S SST42
4 |  | JAW-JB-CBN-3842 | 30571040031 | 1260831003 | ARGASUNYA_BARAT | ACTIVE | TB | 108.5346 | -6.7682 | 30 | 60/130/330 | 2020 | JEDI 2020 [NEW] | Cibogo Kendung Mendeng, RT.04 RW.03, Kelurahan Argasunya, Kecamatan Harjamukti | HTI | JAW-JB-CBN-3842 | ARGASUNYA_BARAT | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KOTA CIREBON | 6614369 | 2020-01-13 |  | 220 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-07-03 | W27-2020 | Jul-2020 | 2020-08-19 | W34-2020 | Aug-2020 | MW | 2020-06-15 |  | 533113468388 | 6.6 |  | 2020-06-23 |  | 2020-07-15 | 2020-08-20 | W34-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.08.20 : RFIN sent (MULTIGUNA) plan PLN permanent 1 sept 17.08.20 : actual RFI dengan Multiguna, collecting doc RFIN plan submit 19 Aug 20 13.08.20 : plan RFI 21 Aug 10.08.20 : 03.08.20 : 27.07.20 : 23.07.20 : PLN connection terkendala isu stock KWH meter kosong 16.07.20 : 15.07.20 : email SRFI-N sent 13.07.20 : 09.07.20 : plan PLN connect 20 jul 20, masih terkendala isu stock kwh meter kosong 06.07.20 : proses PLN connection, isu stock KWH meter kosong 02.07.20 : 29.06.20 : 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 15.06.20 : Soft RFI 11.06.20 : ME & Grounding on going 08.06.20 : Erection OG, pagar halaman OG 04.06.20 : 01.06.20 : erection on going 28.05.20 : 25.05.20 : curingtime 21.05.20 : excavation on going 14.05.20 : 08.05.20 : excavation og 30.04.20 : proses perijinan 23.04.20 : 16.04.20 : Iw clear, proses eskalasi sitac 09.04.20 : wait TNP review 03.04.20 : RND OK 02.04.20 : IW on going new candidate 25.03.20 : reject dok legal lahan 19.03.20 : IW clear 11.03.20 : IW on going 20.02.20 : Hunting 13.02.20 : Kand A = Rehunting 06.02.20 : Kand A = Rehunting
36 |  | JAW-JI-MJK-4142 | 30571230031 | 1643001003 | DAWAR_RANDEGAN | ACTIVE | TB | 112.4777 | -7.3262 | 50 | 0/90/270 | 2020 | JEDI 2020 [NEW] | Dusun Sumberan Rt.002 Rw.002, Kel. Randegan, Kec. Dawar Blandong, Kab. Mojokerto | HTI | JAW-JI-MJK-4142 | DAWAR_RANDEGAN | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. MOJOKERTO | 6614369 | 2020-01-13 |  | 241 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-09-15 | W38-2020 | Sep-2020 | MW | 2020-06-12 |  | 511812242006 | 6.6 |  | 2020-06-19 |  | 2020-07-02 | 2020-09-10 | W37-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.09.20 : RFIN sent, RFI actual 9 sept dengan daya normal 6.6 kVA 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : 24.08.20 : PLN connection menunggu review add work PLN by Power eng XL (eskalasi isu besar daya PLN terkait isu BP vs Biaya Investasi PLN) 17.08.20 : 06.08.20 : eskalasi isu besar daya PLN terkait isu BP vs Biaya Investasi PLN 23.07.20 : 22.07.20 : PLN meminta daya menjadi 10,6kva 13.07.20 : 09.07.20 : proses PLN connection, terdapat perluasan jaringan penambahan 2 tiang, plan RFI 15 jul 02.07.20 : email SRFI-N sent, plan RFI 8 jul 29.06.20 : Proses PLN Connection 29.06.20 : 25.06.20 : SRFI, collecting doc RFIN 18.06.20 : PLN Connection need perluasan jaringan 3 gawang 17.06.20 : PSB PLN release 11.06.20 : 08.06.20 : tower erection on going 04.06.20 : 01.06.20 : tower erection on going 28.05.20 : prepare start erection 25.05.20 : 14.05.20 ; plan 14/4 cor borepile, besi ks MOS, pagar me plan mos 20/5 08.05.20 : bouwplank 30.04.20 : proses design/bouwplank dan apply perijinan 23.04.20 : 16.04.20 : collecting berkas legal untuk apply perijinan 09.04.20 : on going soiltest, collecting berkas legal untuk apply perijinan 02.04.20 : 25.03.20 : 19.03.20 : 11.03.20 : 28.02.20 : IW clear, proses review eskalasi sitac 26.02.20 : kand -7,3279167 112,47769, IW clear 21 kk, proses submit eskalasi sitac 20.02.20 : IW On going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
72 |  | JAW-JI-SIT-3803 | 30571560031 | 1643331003 | KAPONGAN_KESAMBIRAMPAK | ACTIVE | TB | 114.0638 | -7.69 | 40 | 0/100/240 | 2020 | JEDI 2020 [NEW] | KP.Sarse RT. 002 RW. 003 Desa Kesambirampak Kecamatan Kapongan Kabupaten Situbondo Provinsi Jawa Timur | HTI | JAW-JI-SIT-3803 | KAPONGAN_KESAMBIRAMPAK | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SITUBONDO | 6614369 | 2020-01-13 |  | 402 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-14 | W33-2020 | Aug-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-20 | W08-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 516500950850 | 10.6 |  | 2020-06-19 |  | 2020-07-10 | 2021-02-18 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.21 : PLN connection dengan daya 23 KVA, HO PLN diterima jika sudah downgrade 10.6 kVA, jaringan sudah ready 26.01.21 : BP paid, need perluasan jaringan 21.01.21 : PSB released, PLN connection OG 23.07.20 : 10.07.20 : email SRFI-N sent, PLN Connection menunggu konfirmasi dari XL 09.07.20 : PLN Connection menunggu konfirmasi dari XL 06.07.20 : SRFI actual, collecting doc RFIN 02.07.20 : 29.06.20 : erection og, pondari bts og, pondasi pagar og, 25.06.20 : erection on going 22.06.20 : curingtime & backfilling 18.06.20 : rebarring done, plan cor 18/6 11.06.20 : excavation on going 08.06.20 : 04.06.20 : 01.06.20 : 28.05.20 : bouwplank, proses perijinan 25.05.20 : 14.05.20 ; plan start cme 16/5, gdl blm terbit 08.05.20 : bouwplank, proses perijinan 30.04.20 : bouwplank, proses perijinan 23.04.20 : 16.04.20 : designpack dan bouwplank, proses perijinan 09.04.20 : on going soiltest, collecting berkas legal untuk apply perijinan 02.04.20 : 25.03.20 : renego BAN LL tetap di harga awal , review eskalasi sitac 19.03.20 : 11.03.20 : IW clear, proses renego dan validasi biaya sitac 28.02.20 : 20.02.20 : IW on going, Sign IW kurang 1 kk dari 33 KK , 20.02.20 : IW On going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
195 |  | JAW-JI-SMP-4112 | 30571600031 | 1643371003 | TOGULUK_SUMENEP | ACTIVE | TB | 113.8281 | -7.0083 | 40 | 90/180/250 | 2020 | JEDI 2020 [NEW] | Dsn Batuan Barat, RT 03 RW 04, Desa Batuan, Kec Batuan, Kab Sumenep | HTI | JAW-JI-SMP-4112 | Toguluk_Sumenep | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SUMENEP | 6614369 | 2020-01-13 |  | 392 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-27 | W22-2020 | May-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-13 | W07-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 517101263634 | 6.6 |  | 2020-06-19 |  | 2020-05-27 | 2021-02-08 | W07-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP Paid, waiting KWH stock 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SRFI, wait confirmation XL for PLN connection 27.05.20 : email SRFI-N sent 08.05.20 : SRFI 30.04.20 : on going erection, BTS foundation dan ME installation 23.04.20 : 09.04.20 : on going excavation (50% done), terkendala rocky soil 02.04.20 : on going excavation 25.03.20 : Proses perijinan 19.03.20 : 11.03.20 : proses soiltest, proses collect doc legal 28.02.20 : on going proses rekom l/c 27.02.20 : IW done, kand 07°00'31.96"S 113°49'37.37"E, 11 KK IW Done, Proses Collect Dokumen legal . 24.02.20 : IW done, Realisasi IW Done , collect legal sitac, soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : Kand B = Candidate B Submit
174 |  | JAW-JB-NPH-3691 | 30573570031 | 1260981003 | SUMUR BANDUNG | ACTIVE | TB | 107.4205 | -6.7804 | 40 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Kp. Cideupong Rt 02 Rw 06, Desa Sumur Bandung, Kecamatan Cipatat, Kabupaten Bandung Barat | HTI | JAW-JB-NPH-3691 | SUMUR BANDUNG | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614396 | 2020-01-15 |  | 149 | 121 - 150 days | 2020-06-13 | W24-2020 | Jun-2020 | 2020-04-27 | W18-2020 | Apr-2020 | 2020-06-04 | W23-2020 | Jun-2020 | 2020-06-08 | W24-2020 | Jun-2020 | MW | 2020-04-22 |  | 535852084042 | 6.6 |  | 2020-06-18 |  | 2020-05-14 | 2020-06-12 | W24-2020 |  | 2020-08-09 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.06.20 : RFIN sent 08.06.20 : revisi plan RFI Senin 8 Jun 20 04.06.20 : penempatan pole kwh nya menunggu design retaining wall, sedang di usahakan minggu ini, plan 6 juni 01.06.20 : plan PLN connect 6 june 30.05.20 : plan RFI 4 june 28.05.20 : 14.05.20 : SRFIN sent 12.05.20 : SRFIN actual 08.05.20 : ME og 30.04.20 : erection on going 23.04.20 : 22.04.20 : rebarring, plan cor 25 Apr 20, plan RFI 15 May 20 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 20.04.20 : bore pile done, excavation on going & rebarring 16.04.20 : cor borepile 4 titik 09.04.20 : borepile OG (16 titik @9 m) 02.04.20 : 01.04.20 : on going galian, plan besok galian done, plan cor 6 April 25.03.20 : start galian 19.03.20 : plan besok survey KBB (pemkot kota bandung barat) 11.03.20 : Rekom done, RFC, proses perijinan 20.02.20 : rekom L/C 13.02.20 : IW on going 06.02.20 : kand B = validasi done, Candidate B 27.01.20 : kand B = RND OK 50 70/150/220 27Jan20 : Ok candidate B, tower 52 27.01.20 : kand B = submit -6.77997 107.42200 22.01.20 : kand A = RND Not ok candidate A, rehunting to : 107.422267, -6.779806 20.01.20 : Kand A = submit kand A di -6.780630° 107.420450° 17.01.20 : hasil assessment PDI done (email arief), proses input STIP 1 B2S
184 |  | JAW-JI-SMP-4118 | 30571650031 | 1643421003 | TALANGO_POTERAN | ACTIVE | TB | 114.0538 | -7.0891 | 50 | 0/150/220 | 2020 | JEDI 2020 [NEW] | Jalan Raya Poteran Timur Dusun Andun RT.001 RW. 011 Desa Poteran Kecamatan Talango Kabupaten Sumenep | HTI | JAW-JI-SMP-4118 | TALANGO_POTERAN | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SUMENEP | 6614369 | 2020-01-13 |  | 143 | 121 - 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-09 | W19-2020 | May-2020 | 2020-06-04 | W23-2020 | Jun-2020 | 2020-06-04 | W23-2020 | Jun-2020 | MW | 2020-04-22 |  | 517101224147 | 6.6 |  | 2020-06-17 |  |  | 2020-06-04 | W23-2020 |  | 2020-07-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.06.20 : RFIN sent 01.06.20 : 29.05.20 : SRFI 28.05.20 : 25.05.20 : 14.05.20 : 13.05.20 ; erection done, pondasi bts og, me grounding done, pagar og 08.05.20 : erection og 30.04.20 : pouring concrete 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, rebarring OG, plan cor 24 apr 09.04.20 : on going excavation 02.04.20 : RFC, proses perijinan 25.03.20 : proses perijinan 19.03.20 : 11.03.20 : Proses perijinan, RFC, proses DP lahan 28.02.20 : on going proses rekom l/c 24.02.20 : IW done, Realisasi IW Done, collect legal sitac, soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
47 |  | JAW-JI-SMP-4114 | 30571610031 | 1643381003 | GAPURA_BANJAR_TIMUR | ACTIVE | TB | 113.9429 | -6.998 | 40 | 70/180/280 | 2020 | JEDI 2020 [NEW] | Dusun Ahadan RT 01 RW 02 Desa Banjar Timur Kec Gapura Kab Sumenep | HTI | JAW-JI-SMP-4114 | GAPURA_BANJAR_TIMUR | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SUMENEP | 6614369 | 2020-01-13 |  | 179 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-27 | W18-2020 | Apr-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-10 | W28-2020 | Jul-2020 | MW | 2020-06-12 |  | 517101229786 | 6.6 |  | 2020-06-17 |  | 2020-06-28 | 2020-07-10 | W28-2020 |  | 2020-09-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.07.20 : RFIN sent 09.07.20 : actual RFI, plan submit RFIN 10 jul 29.06.20 : Proses PLN Connection 28.06.20 : email SRFI-N sent 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 01.06.20 : SRFI actual, collecting doc SRFIN 28.05.20 : erection done, ME on going 25.05.20 : 14.05.20 : start erection, pondasi BTS OG, mat pagar me ground plan mos 18/5 08.05.20 : prepare cor 30.04.20 : rebarring 23.04.20 : 09.04.20 : on going rebarring 02.04.20 : on going excavation 25.03.20 : Proses perijinan 19.03.20 : 11.03.20 : Proses perijinan, RFC, proses DP lahan 28.02.20 : on going proses rekom l/c 27.2.020 : IW done, kand 06°59'55.20"S 113°56'30.69"E, 9 KK IW Done, Proses Collect Dokumen RFL . 24.02.20 :IW done, Realisasi IW Done , collect legal sitac, soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
165 |  | JAW-JI-SIT-3802 | 30571550031 | 1643321003 | SITUBONDO_KOTAKAN | ACTIVE | TB | 114.0065 | -7.7516 | 50 | 0/90/200 | 2020 | JEDI 2020 [NEW] | Kp. Krajan RT. 003 RW. 002, Desa Sliwung, Kecamatan Panji, Kabupaten Situbondo, Provinsi Jawa Timur | HTI | JAW-JI-SIT-3802 | SITUBONDO_KOTAKAN | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SITUBONDO | 6614369 | 2020-01-13 |  | 179 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-27 | W18-2020 | Apr-2020 | 2020-07-03 | W27-2020 | Jul-2020 | 2020-07-10 | W28-2020 | Jul-2020 | MW | 15-Jun-20 18-May-20 |  | 516500929104 | 10.6 |  | 2020-06-17 |  | 2020-04-16 | 2020-07-10 | W28-2020 |  | 2020-09-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.07.20 : RFIN sent 09.07.20 : actual RFI, plan submit RFIN 10 jul 29.06.20 : Proses PLN Connection 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 28.05.20 : 16.04.20 : email SRFI-N sent 09.04.20 : erection on going 02.04.20 : rebarring, prepare for pouring concrete 25.03.20 : PKS proses , proses perijinan, CME OG 19.03.20 : 11.03.20 : Proses perijinan, RFC, proses DP lahan 28.02.20 : on going proses rekom l/c 24.02.20 : IW done, Realisasi IW Done , collect legal sitac ,soiltest done 20.02.20 : IW clear, proses eskalasi sitac 13.02.20 : TNP review 06.02.20 : kand A = validasi done, Candidate A RF TX OK
140 |  | JAW-JI-SDA-4082 | 30571510031 | 1643281003 | RAYA_SIDOREJO_KRIAN | ACTIVE | TB | 112.6251 | -7.3797 | 40 | 70/250/330 | 2020 | JEDI 2020 [NEW] | Dusun Banjar Pertapan RT.05 RW. 05 Desa Pertapan Maduretno Kec. Taman Kab. Sidoarjo | HTI | JAW-JI-SDA-4082 | Raya_Sidorejo_Krian | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614369 | 2020-01-13 |  | 437 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-24 | W26-2020 | Jun-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-03-29 | W14-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 511610624782 | 6.6 |  | 2020-06-17 |  | 2020-06-24 | 2021-03-25 | W13-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23.03.21 : PLN Connected, collecting RFI documentation 18.03.21 : plan connect 18/03 08.03.21 : MoM 04/3, OG perluasan jaringan, revise RFI plan 29/3 18.02.21 : PLN connection daya 6.6 kVA, materail PLN NY ready 26.01.21 : OG perluasan jaringan 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : PLN Connection menunggu konfirmasi dari XL 29.06.20 : PLN Connection menunggu konfirmasi dari XL 24.06.20 : email SRFI-N sent 22.06.20 : SRFI, wait confirmation XL for PLN connection 01.06.20 : SRFI actual, collecting doc SRFIN 28.05.20 : erection done, ME OG 25.05.20 : 14.05.20 : Rebaring, mat angkur tower plan mos 14/5, plan cor 16/5, mat pagar me plan mos 20/5 08.05.20 : bouwplank 30.04.20 : proses apply perijinan, CME start wait perijinan release 23.04.20 : 16.04.20 : designpack dan bouwplank, proses perijinan 09.04.20 : on going soiltest, collecting berkas legal untuk apply perijinan 02.04.20 : 25.03.20 : IW clear, proses eskalasi SITAC 19.03.20 : IW on going, need approval kandidat 11.03.20 : IW on going 26.02.20 : (-07°22'28.6" 112°37'30.7"), IW on going 90% ( 25 kk) 20.02.20 : IW On going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 27.01.20 : kand A = 112.62483 -7.3773333 265.14 GF SST 42
83 |  | JAW-JI-PCT-4186 | 30571330031 | 1643101003 | KEBONAGUNG_MANTREN | ACTIVE | TB | 111.191 | -8.2264 | 50 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Dusun Krajan, RT.01 RW.04 Desa Mantren, Kecamatan Kebonagung, Kabupaten Pacitan, Propinsi Jawa Timur | HTI | JAW-JI-PCT-4186 | KEBONAGUNG_MANTREN | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. PACITAN | 6614369 | 2020-01-13 |  | 421 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-27 | W22-2020 | May-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-03-12 | W11-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 515421485879 | 13.2 |  | 2020-06-17 |  | 2020-05-27 | 2021-03-09 | W11-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.03.21 : PLN connected, NY RFIN -> plan 08/3 18.02.21 : PLN connection daya 13.2 kVA, material PLN NY ready, revise RFI plan W2 Mar 26.01.21 : proses register, waiting PLN survey, Revise RFI Plan W2 Mar 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SRFI, wait confirmation XL for PLN connection 27.05.20 : email SRFI-N sent 08.05.20 : SRFI 30.04.20 : on going erection, BTS foundation dan ME installation 23.04.20 : 09.04.20 : rebarring on going 02.04.20 : on going excavation 25.03.20 : Soiltest done, design done , Proses Perijinan 19.03.20 : 11.03.20 : proses soiltest, proses collect doc legal 28.02.20 : on going proses rekom l/c 24.02.20 : IW done, Soiltest done , design proses 17.02.20 : Capex Approved , realisasi IW , Penjadwalan soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : TNP review 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
116 |  | JAW-JI-PCT-4187 | 30571340031 | 1643111003 | NGADIROJO_HADILUWIH | ACTIVE | TB | 111.3088 | -8.2334 | 40 | 40/100/190 | 2020 | JEDI 2020 [NEW] | Jl. Pacitan Trenggalek Dusun Garenglor RT 001 RW 002 Desa Hadiluwih Kecamatan Ngadirojo Kabupaten Pacitan | HTI | JAW-JI-PCT-4187 | NGADIROJO_HADILUWIH | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. PACITAN | 6614369 | 2020-01-13 |  | 421 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-24 | W26-2020 | Jun-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-03-12 | W11-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 515421485887 | 13.2 |  | 2020-06-17 |  | 2020-06-24 | 2021-03-09 | W11-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.03.21 : PLN connected, NY RFIN -> plan 08/3 18.02.21 : PLN connection daya 13.2 kVA, material PLN NY ready, revise RFI plan W2 Mar 26.01.21 : Proses register, waiting PLN survey, Revise RFI Plan W2 Mar 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL 24.06.20 : email SRFI-N sent 22.06.20 : SRFI, wait confirmation XL for PLN connection 01.06.20 : 29.05.20 : SRFI 28.05.20 : 25.05.20 : 14.05.20 : 13.05.20 ; Curing time, pond BTS done, mat tower plan mos 14/5 08.05.20 : rebaring og 30.04.20 : bor pile on going, proses perijinan 23.04.20 : 16.04.20 : proses perijinan, CME stop 09.04.20 : on going excavation 02.04.20 : on going excavation 25.03.20 : proses review sitac 19.03.20 : 11.03.20 : IW clear, proses eskalasi sitac 28.02.20 : 24.02.20 : Kand A (S : 8°14'2.00" E : 111°18'29.50"), IW on going, IW 18KK , kurang 8 KK, proses submit biaya sitac 26 Feb 20.02.20 : 13.02.20 : IW on going, IW 7 KK 06.02.20 : kand A = validasi done, Candidate A RF TX OK
117 |  | JAW-JI-PCT-4184 | 30571310031 | 1643081003 | NGADIROJO_SIDOMULYO | ACTIVE | TB | 111.2774 | -8.2515 | 50 | 0/130/300 | 2020 | JEDI 2020 [NEW] | Dusun Tawang Kulon, RT.01 RW.10, Desa Sidomulyo, Kecamatan Ngadirojo, Kabupaten Pacitan, Propinsi Jawa Timur | HTI | JAW-JI-PCT-4184 | NGADIROJO_SIDOMULYO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. PACITAN | 6614369 | 2020-01-13 |  | 421 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-27 | W22-2020 | May-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-03-12 | W11-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 515421485853 | 13.2 |  | 2020-06-17 |  | 2020-05-27 | 2021-03-09 | W11-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.03.21 : PLN connected, NY RFIN -> plan 08/3 18.02.21 : PLN connection daya 13.2 kVA, material PLN NY ready, revise RFI plan W2 Mar 26.01.21 : Proses register, waiting PLN survey, Revise RFI Plan W2 Mar 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SRFI, wait confirmation XL for PLN connection 27.05.20 : email SRFI-N sent 08.05.20 : SRFI 30.04.20 : on going erection, BTS foundation dan ME installation 23.04.20 : 09.04.20 : on going excavation 02.04.20 : 25.03.20 : Soiltest done, design done , Proses Perijinan 19.03.20 : 11.03.20 : proses soiltest, proses collect doc legal 28.02.20 : on going proses rekom l/c 24.02.20 : IW done, Soiltest Done 17.02.20 : Capex Approved , realisasi IW , Penjadwalan soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : Kand B = Candidate B Submit
24 |  | JAW-JI-LMJ-4221 | 30571170031 | 1642941003 | CANDIPURO_SUMBERMUJUR | ACTIVE | TB | 113.0176 | -8.1319 | 50 | 50/130/250 | 2020 | JEDI 2020 [NEW] | Dusun Umbulrejo, RT.011 RW.004, Desa Sumbermujur, Kecamatan Candipuro, Kabupaten Lumajang | HTI | JAW-JI-LMJ-4221 | CANDIPURO_SUMBERMUJUR | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. LUMAJANG | 6614369 | 2020-01-13 |  | 388 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-22 | W21-2020 | May-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 516091068307 | 6.6 |  | 2020-06-17 |  | 2020-05-22 | 2021-02-04 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP Paid, Proses PK di UP3 Jember 21.01.21 : PSB released, PLN connection OG23.07.20 : 09.07.20 : PLN Connection menunggu konfirmasi dari XL 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SRFI, wait confirmation XL for PLN connection 22.05.20 : email SRFI-N sent 30.04.20 : SRFI actual 23.04.20 : 09.04.20 : curing time 02.04.20 : on going excavation 25.03.20 : PKS proses , proses perijinan, CME OG 19.03.20 : proses rekom on going 11.03.20 : proses design, proses collect doc legal 28.02.20 : on going proses rekom l/c 24.02.20 : IW done, Realisasi IW Done , collect legal doc sitac, soiltest done 20.02.20 : IW clear, proses eskalasi sitac 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
104 |  | JAW-JI-PBL-2914 | 20211100641 | 1643031003 | MAYANGAN_MANGUNHARJO | ACTIVE | TB | 113.2307 | -7.7463 | 30 | 100/180/270 | 2020 | JEDI 2020 [NEW] | Jl. Gajah Mada Rt. 005 Rw. 006 Kelurahan Mangunharjo Kecamatan Mayangan Kota Probolinggo | HTI | JAW-JI-PBL-2914 | MAYANGAN_MANGUNHARJO | B2S | TBG | EAST | JATIM | Jawa Timur | KOTA PROBOLINGGO | 6614369 | 2020-01-13 |  | 388 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-02 | W27-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 513562155038 | 6.6 |  | 2020-06-17 |  | 2020-07-02 | 2021-02-04 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP paid, need perluasan jaringan 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : PLN Connection menunggu konfirmasi dari XL 02.07.20 : email SRFI-N sent 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SRFI, wait confirmation XL for PLN connection 01.06.20 : 29.05.20 : SRFI 28.05.20 : 25.05.20 : 14.05.20 : 13.05.20 ; Plan 14/5 start erection, pagar done, me grounding MOS 08.05.20 : pouring concrete 30.04.20 : bor pile on going, proses perijinan 23.04.20 : 16.04.20 : CME start menunggu proses perijinan 09.04.20 : Bouwplank, plan start CME 9 April 02.04.20 : 25.03.20 : PKS proses , proses perijinan, CME OG 19.03.20 : 11.03.20 : IW clear, on going soiltest, collect legal doc 28.02.20 : kand A = IW clear, proses review eskalasi sitac 26.02.20 : kand A = IW Clear 15 kk, proses submit eskalasi sitac 20.02.20 : kand A = IW On going 13.02.20 : kand A = IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
136 |  | JAW-JI-MJK-4143 | 30571240031 | 1643011003 | PUNGGING_NGRAME | ACTIVE | TB | 112.5647 | -7.4915 | 50 | 20/190/310 | 2020 | JEDI 2020 [NEW] | Gading RT 05 RW 02 Desa Ngrame Kec. Pungging Kab. Mojokerto Prov. Jawa Timur | HTI | JAW-JI-MJK-4143 | PUNGGING_NGRAME | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. MOJOKERTO | 6614369 | 2020-01-13 |  | 382 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-02 | W27-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 514561044407 | 6.6 |  | 2020-06-17 |  | 2020-07-02 | 2021-01-29 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : survey done, proses pengajuan BPUJL 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : 02.07.20 : email SRFI-N sent, PLN Connection menunggu konfirmasi dari XL 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SRFI, wait confirmation XL for PLN connection 01.06.20 : SRFI actual, collecting doc SRFIN 28.05.20 : prepare erection 25.05.20 : 14.05.20 : Plan cor borepile 13/5, besi ks mos, pagar me sdh ada di sby, angkur + tower 13/5 sortir 08.05.20 : bouwplank 30.04.20 : proses design/bouwplank dan apply perijinan 23.04.20 : 16.04.20 : IW done, proses rekom dan soiltest 09.04.20 : IW clear, proses eskalasi sitac 02.04.20 : 25.03.20 : IW on going, IW 9 KK, done 6 KK, 3 KK masih menunggu terkait tali asih karena 1 KK mintanya 15 juta 19.03.20 : IW on going, need approval kandidat 11.03.20 : IW on going 26.02.20 : (07°29'38.67" 112°33'52.21"), IW on going 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
168 |  | JAW-JB-SOR-3832 | 30590120031 | 1262031003 | SUDI_IBUN | ACTIVE | TB | 107.7717 | -7.0884 | 40 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Kp. Cigumelor, RT.02/08, Desa Sudi, Kecamatan Ibun, Kabupaten Bandung - Jawa Barat. | HTI | JAW-JB-SOR-3832 | SUDI_IBUN | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614612 | 2020-04-03 |  | 113 | 91 - 120 days | 2020-08-31 | W36-2020 | Aug-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-24 | W30-2020 | Jul-2020 | MW | 2020-06-12 |  | 535312224820 | 6.6 |  | 2020-06-16 |  | 2020-07-15 | 2020-07-25 | W30-2020 |  | 2020-09-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.08.20 : RFIN sent dengan PLN {Permanent 25.07.20 : RFIN sent dengan MG 23.07.20 : actual RFI dengan connect PLN Multiguna, plan permanent 1 aug 16.07.20 : 13.07.20 : PLN connection masih terkendala isu stock kwh meter kosong 09.07.20 : 06.07.20 : 02.07.20 : 29.06.20 : SRFI actual, proses PLN Connection 22.06.20 : ME on going, plan SRFI 22 jun 20 18.06.20 : erection on going 17.06.20 : Go RFI, PSB PLN release 11.06.20 : curingtime, on going pondasi RBS 08.06.20 : curingtime 04.06.20 : rebaring on going, plan cor 6/6 01.06.20 : 28.05.20 : excavation on going 25.05.20 : Rekom, APD/BOQ approved 14.05.20 : Proses Rekom plan done tgl 15 Mei 08.05.20 : Proses pembayaran IW dan Rekom 30.04.20 : IW OG kurang 6 KK dari 20 KK 23.04.20 : 16.04.20 : IW on going 09.04.20 : 06.04.20 : Hunting
142 |  | JAW-JI-TBN-4056 | 30571680031 | 1643451003 | RENGEL_CAMPUREJO | ACTIVE | TB | 112.0443 | -7.0688 | 50 | 60/140/210 | 2020 | JEDI 2020 [NEW] | Dsn Ketapang RT 01 RW 01 Desa Campurejo Kec Rengel Kab Tuban | HTI | JAW-JI-TBN-4056 | RENGEL_CAMPUREJO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. TUBAN | 6614369 | 2020-01-13 |  | 430 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-03-29 | W14-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 518023274670 | 6.6 |  | 2020-06-16 |  | 2020-07-13 | 2021-03-18 | W12-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18.03.21 : 15.03.21 : PLN connected, prepare RFIN 08.03.21 : replan RFI 29 Mar 11.02.21 : Isu overblast trafo (Surat Jawaban per 10 Feb), Revise RFI Plan W2 Mar 26.01.21 : BP Paid, Proses PK di UP3 21.01.21 : PSB released, PLN connection OG 23.07.20 : 13.07.20 : email SRFI-N sent, PLN connection menunggu konfirmasi dari XL 09.07.20 : 29.06.20 : PLN connection menunggu konfirmasi dari XL 25.06.20 : SRFI, collecting doc RFIN 22.06.20 : ME on going 18.06.20 : erection done, tower painting paralel BTS foundation on going 11.06.20 : 08.06.20 : borepile on going 04.06.20 : 01.06.20 : excavation 28.05.20 : excavation 25.05.20 : 08.05.20 : bouwplank, proses perijinan 30.04.20 : bouwplank, proses perijinan 23.04.20 : 16.04.20 : 09.04.20 : proses perijinan, CME start after perijinan 06.04.20 : CME start after IMB 02.04.20 : RFC, proses perijinan 25.03.20 : proses perijinan 19.03.20 : 11.03.20 : Proses perijinan, RFC, proses DP lahan 28.02.20 : on going proses rekom l/c 27.02.20 : IW done, kand 07°03'59.3"S 112°02'38.5"E, 12 KK IW done, Proses Collect Dokumen RFL . 24.02.20 : IW done, Realisasi IW Done, collect legal sitac, soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : Kand E = RF OK, TX review 05.02.20 : kand E = submit E 112.04403 -7.066472 264.57 GF SST 52 In Cellplan Tuban. Pergeseran dari kandidat A yang sudah approved sebelumnya 28.01.20 : kand A = RND 50 110/195/270 28Jan20 : Ok candidate A, tower 52 27.01.20 : kand A = 112.04481 -7.066806 233.56 GF SST 52 Out Cellplan Tuban. Pengajuan Permohonan pertimbangan cellplan OG kand B = 112.04622 -7.070556 287.51 GF SST 52 Out Cellplan Tuban. Pengajuan Permohonan pertimbangan cellplan OG kand C = 112.04335 -7.066815 247.08 GF SST 52 In Cellplan Tuban kand D = 112.04252 -7.067451 247.21 GF SST 52 In Cellplan Tuban
127 |  | JAW-JI-LMJ-4223 | 30571190031 | 1642961003 | PASIRIAN_MADUREJO | ACTIVE | TB | 113.1421 | -8.21 | 50 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Dusun Krajan RT 17 RW 06 Desa Madurejo Kec. Pasirian Kab. Lumajang | HTI | JAW-JI-LMJ-4223 | PASIRIAN_MADUREJO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. LUMAJANG | 6614369 | 2020-01-13 |  | 400 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-20 | W08-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 516091070277 | 6.6 |  | 2020-06-12 |  | 2020-06-30 | 2021-02-16 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : OG perluasan jaringan, revise RFI plan W1 Mar 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : 30.06.20 : email SRFI-N sent, PLN Connection menunggu konfirmasi dari XL 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SRFI, wait confirmation XL for PLN connection 01.06.20 : SRFI actual, collecting doc SRFIN 28.05.20 : erection on going 25.05.20 : 14.05.20 : 13.05.20 : rebaring, mat angtem dan tower plan mos 14/5, plan cor 17/5, mat pagar me sdh ada di sby 08.05.20 : excavation og 30.04.20 : bouwplank, proses perijinan 23.04.20 : 16.04.20 : 09.04.20 : designpack dan bouwplank, proses perijinan 02.04.20 : 25.03.20 : proses soiltest, collect legal doc 19.03.20 : IW clear, proses realisasi pembayaran IW, cek regulasi lahan pertanian 11.03.20 : IW clear, proses realisasi pembayaran IW 28.02.20 : IW clear, proses review eskalasi sitac 26.02.20 : Kand 8,211028 113,143222, IW clear 11 kk, proses submit eskalasi sitac (RT + RW : 11 KK) 20.02.20 : IW clear, proses eskalasi sitac 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
112 |  | JAW-JI-TBN-4057 | 30571690031 | 1643461003 | MONTONG_GUWOTERUS | ACTIVE | TB | 111.8293 | -6.9548 | 50 | 10/90/280 | 2020 | JEDI 2020 [NEW] | Jl. Montong Singgahan RT 08 RW 01 Dusun Jaten Desa Guwo Terus Kec Montong Kab Tuban | HTI | JAW-JI-TBN-4057 | MONTONG_GUWOTERUS | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. TUBAN | 6614369 | 2020-01-13 |  | 396 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-03 | W27-2020 | Jul-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-13 | W07-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 518023274662 | 6.6 |  | 2020-06-12 |  | 2020-07-03 | 2021-02-12 | W07-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP Paid, Proses PK di UP3 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : PLN connection menunggu konfirmasi dari XL 03.07.20 : email SRFI-N sent 29.06.20 : PLN connection menunggu konfirmasi dari XL 25.06.20 : SRFI, collecting doc RFIN 22.06.20 : 18.06.20 : curingtime, on going backfilling, plan start erection 18/6 11.06.20 : 08.06.20 : excavation on going 04.06.20 : 01.06.20 : excavation start 28.05.20 : bouwplank, proses perijinan 25.05.20 : 14.05.20 : bouwplank, proses perijinan 30.04.20 : bouwplank, proses perijinan 23.04.20 : 16.04.20 : 09.04.20 : proses perijinan, CME start after perijinan 06.04.20 : CME start after IMB 02.04.20 : RFC, proses perijinan 25.03.20 : proses perijinan 19.03.20 : IW clear, doc legal complete, rekom on going 11.03.20 : proses soiltest, proses collect doc legal 28.02.20 : IW Clear, penyelesaian Case IW permintaan taliasih IW Sepadan yang masih tinggi/ effort pendekatan persuasif dibantu LL dan Tokoh. 20.02.20 : IW clear 15kk, proses realisasi IW dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 28.01.20 : kand A = RND 50 10/80/285 28Jan20 : Ok candidate A, tower 52 27.01.20 : kand A = 111.82969 -6.9545 55.42 GF SST 52 In Cellplan Tuban kand B = 111.83233 -6.954833 334.78 GF SST 52 In Cellplan Tuban
191 |  | JAW-JI-LMJ-4222 | 30571180031 | 1642951003 | TEMPEH_LEMPENI | ACTIVE | TB | 113.1591 | -8.2219 | 50 | 50/150/270 | 2020 | JEDI 2020 [NEW] | Dsn. Kebonan, RT 041 RW 010, Ds. Lempeni, Kec. Tempeh, Kab. Lumajang | HTI | JAW-JI-LMJ-4222 | TEMPEH_LEMPENI | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. LUMAJANG | 6614369 | 2020-01-13 |  | 388 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-22 | W21-2020 | May-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 516091068293 | 6.6 |  | 2020-06-12 |  | 2020-05-22 | 2021-02-04 | W06-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.01.21 : BP Paid 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : PLN Connection menunggu konfirmasi dari XL 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SRFI, wait confirmation XL for PLN connection 22.05.20 : email SRFI-N sent 30.04.20 : SRFI actual 23.04.20 : 16.04.20 : start galian 09.04.20 : Bouwplank, plan start CME 9 April 02.04.20 : 25.03.20 : PKS proses , proses perijinan, CME OG 19.03.20 : 11.03.20 : IW clear, on going soiltest, collect legal doc 26.02.20 : Kand C = target submit kandidat C done/ Submit tssr done/ pararel iw dan BAN 29-02 ( soswar bersama kades ) 19.02.20 : IW OG Cand C , Need approval cand , Target IW Clear 22.2.20 20.02.20 : IW On going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
6 |  | JAW-JI-SIT-3800 | 30571530031 | 1643301003 | ASEMBAGUS_TRIGONCO | ACTIVE | TB | 114.2072 | -7.7513 | 40 | 30/90/270 | 2020 | JEDI 2020 [NEW] | Jl.Raasan RT 002 RW 001, Desa Trigonco, Kecamatan Asembagus, Kabupaten Situbondo, Provinsi Jawa Timur | HTI | JAW-JI-SIT-3800 | ASEMBAGUS_TRIGONCO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SITUBONDO | 6614369 | 2020-01-13 |  | 396 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-22 | W21-2020 | May-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-20 | W08-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 516520538138 | 10.6 |  | 2020-06-05 |  | 2020-05-22 | 2021-02-12 | W07-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.21 : note daya PLN connection dengan daya 10.6 dan 13.2 kVA diterima HO PLN, jika lebih dari 13.2 kVA menunggu downgrade terlebih dahulu baru bisa di HO PLN. Jaringan sudah ready 26.01.21 : BP Paid 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : PLN Connection menunggu konfirmasi dari XL 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SRFI, wait confirmation XL for PLN connection 22.05.20 : email SRFI-N sent 30.04.20 : SRFI actual 23.04.20 : 09.04.20 : rebarring on going 02.04.20 : on going excavation 25.03.20 : PKS proses , proses perijinan, CME OG 19.03.20 : 11.03.20 : IW clear, proses realisasi IW, plan soiltest 28.02.20 : kand B = IW clear, proses eskalasi sitac (re nego), collecting legal doc 20.02.20 : kand B = IW clear, proses eskalasi sitac 13.02.20 : kand B = IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
13 |  | JAW-JI-SMP-4110 | 30571580031 | 1643351003 | BATUPUTIH_DAYA | ACTIVE | TB | 113.924 | -6.8907 | 50 | 20/100/200 | 2020 | JEDI 2020 [NEW] | Dusun Batu Bintang RT 03 RW 04 Desa Batuputih Daya Kec. Batuputih Kab Sumenep | HTI | JAW-JI-SMP-4110 | Batuputih_Daya | B2S | TBG | EAST | JATIM | Jawa Timur | Kab. Sumenep | 6614369 | 2020-01-13 |  | 179 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-27 | W18-2020 | Apr-2020 | 2020-06-18 | W25-2020 | Jun-2020 | 2020-07-10 | W28-2020 | Jul-2020 | MW | 20-May-20 18-May-20 |  | 517900555854 | 6.6 |  | 2020-06-04 |  | 2020-06-03 | 2020-07-10 | W28-2020 |  | 2020-08-25 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.07.20 : 10.07.20 : RFIN sent 09.07.20 : plan submit RFIN 10 jul 02.07.20 : actual RFI 1 jul, revisi plan submit RFIN 4 jul 29.06.20 : 25.06.20 : proses PLN connection, perluasan jaringan 3 tiang, plan connect Jumat 26 Jun 20 22.06.20 : proses PLN connection, perluasan jaringan 3 tiang, BP paid 03.06.20 : email SRFI-N sent 01.06.20 : 28.05.20 : 21.05.20 : ada perluasan jaringan PLN, plan RFI 18 jun 2020 08.05.20 : SRFI 30.04.20 : on going erection, BTS foundation dan ME installation 23.04.20 : 09.04.20 : on going excavation 02.04.20 : on going excavation 25.03.20 : Proses perijinan 19.03.20 : 11.03.20 : proses soiltest, proses collect doc legal 28.02.20 : on going proses rekom l/c 27.02.20 : kand 06°53'29.5"S 113°55'29.1"E, 8 kk IW Done, Proses Collect Dokumen legal 24.02.20 : IW done, Realisasi IW Done , collect legal sitac, soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
18 |  | JAW-JI-SIT-3804 | 30571570031 | 1643341003 | BESUKI_KALIMAS | ACTIVE | TB | 113.6922 | -7.7434 | 40 | 0120/240 | 2020 | JEDI 2020 [NEW] | Kp. Bringin RT 002 RW 001, Desa Langkap, Kec. Besuki, Kab. Situbond,o Jawa Timur | HTI | JAW-JI-SIT-3804 | BESUKI_KALIMAS | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SITUBONDO | 6614369 | 2020-01-13 |  | 402 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-15 | W25-2020 | Jun-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-20 | W08-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 516510648410 | 13.2 |  | 2020-06-04 |  | 2020-06-15 | 2021-02-18 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.21 : Daya PLN connection 13.2 kVA, jaringan sudah ready 26.01.21 : BP Paid, need perluasan jaringan 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SRFI, wait confirmation XL for PLN connection 15.06.20 : email SRFIN sent 01.06.20 : 29.05.20 : SRFI 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : ME og 30.04.20 : on going erection, BTS foundation dan ME installation 23.04.20 : 09.04.20 : rebarring borepile on going 02.04.20 : on going excavation 25.03.20 : PKS proses , proses perijinan, CME OG 19.03.20 : 11.03.20 : IW clear, proses realisasi IW, plan soiltest 28.02.20 : kand B = IW clear, proses eskalasi sitac (renego), collecting legal doc 20.02.20 : kand B = IW clear, proses collect legal doc 13.02.20 : kand A = IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
185 |  | JAW-JB-NPH-3700 | 30571060031 | 1260851003 | TAMANJAYA | ACTIVE | TB | 107.3269 | -6.9942 | 50 | 100/210/330 | 2020 | JEDI 2020 [NEW] | Kp.Nenggel Rt 02 Rw 18 Desa Tamanjaya Kecamatan Gununghalu Kabupaten Bandung Barat | HTI | JAW-JB-NPH-3700 | TAMANJAYA | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614369 | 2020-01-13 |  | 115 | 91 - 120 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-27 | W18-2020 | Apr-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-05-06 | W19-2020 | May-2020 | MW | 2020-04-22 |  | 535921323325 | 6.6 |  | 2020-05-08 |  |  | 2020-05-07 | W19-2020 |  | 2020-08-21 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.05.20 : RFIN sent 30.04.20 : SRFI actual 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 20.04.20 : tower painting 16.04.20 : erection on going 09.04.20 : curing time 02.04.20 : 01.04.20 : rebarring, angkur plan besok diambil, SST 52 01.04.20 : lantai kerja, paralel rebarring 25.03.20 : on going excavation 19.03.20 : plan besok survey KBB (pemkot kota bandung barat) 11.03.20 : Rekom done, RFC, proses perijinan 20.02.20 : rekom L/C 13.02.20 : IW on going 06.02.20 : Kand D = RF OK, TX review 05.02.20 : kand C-H = submit C-H, karena LL kand B membatalkan C JAW-JB-NPH-3700_C -6,99603 107,32570 D JAW-JB-NPH-3700_D -6,99264 107,32493 E JAW-JB-NPH-3700_E -6,99673 107,32353 F JAW-JB-NPH-3700_F -6,99858 107,32287 G JAW-JB-NPH-3700_G -6,99637 107,32525 H JAW-JB-NPH-3700_H -6,99271 107,32217 27.01.20 : kand B = RND OK 50 0/110/210 27Jan20 : Ok candidate B, tower 52 27.01.20 : kand B = submit -6,99603 107,32415 22.01.20 : kand A = RND not ok candidate A, rehunting to : 107.325005, -6.994985 20.01.20 : Kand A = submit kand A di -6,99398 107,3278
181 |  | JAW-JI-SMP-4117 | 30571640031 | 1643411003 | TALANGO_ESSANG | ACTIVE | TB | 114.015 | -7.1013 | 50 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Dusun Tokerpuy RT 004 / RW 006 Desa Essang Kecamatan Talango Kabupaten Sumenep | HTI | JAW-JI-SMP-4117 | TALANGO_ESSANG | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SUMENEP | 6614369 | 2020-01-13 |  | 143 | 121 - 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-09 | W19-2020 | May-2020 | 2020-06-04 | W23-2020 | Jun-2020 | 2020-06-04 | W23-2020 | Jun-2020 | MW | 2020-04-22 |  | 517101224154 | 6.6 |  | 2020-05-05 |  |  | 2020-06-04 | W23-2020 |  | 2020-09-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.06.20 : RFIN sent 01.06.20 : 29.05.20 : SRFI 28.05.20 : 25.05.20 : 14.05.20 : 13.05.20 ; erection done, pondasi bts og, pond bts og, mat me grounding mos 08.05.20 : erection og 30.04.20 : pouring concrete 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, rebarring OG, besok plan cor 09.04.20 : on going excavation 02.04.20 : RFC, proses perijinan 25.03.20 : proses perijinan 19.03.20 : 11.03.20 : Proses perijinan, RFC, proses DP lahan 28.02.20 : on going proses rekom l/c 24.02.20 : IW done, Realisasi IW Done, collect legal sitac, soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
310 |  | NUS-NB-SEL-4333 | 30591660031 | 180034109 | JURIT EX SEREMBAU | ACTIVE | TB | 116.4386 | -8.542 | 50 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Dusun Banok, Desa Jurit, Kec. Pringgasela | HTI | NUS-NB-SEL-4333 | PRINGGASELA_PENGADANGAN | COLO | TBG | EAST | BALINUSRA | Nusa Tenggara Barat | KAB. LOMBOK TIMUR | 6614644 | 2020-04-14 |  | 384 | > 150 days | 2020-05-14 | W20-2020 | May-2020 | 2020-05-27 | W22-2020 | May-2020 | 2021-04-30 | W18-2021 | Apr-2021 | 2021-05-03 | W19-2021 | May-2021 | FO (Change to MW as temp solution) | 2021-02-15 |  | 441204257552 | 6.6 Kva |  | 2020-05-04 |  | 2020-05-27 | 2021-05-03 | W19-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.05.21 : RFI 03.05.21 : Power Connection Process 26.04.21 : FO change to MW, OG PLN connection, RFI Plan 30 Apr 19.04.21 : SPK FO issue, PLN connection hold 06.08.20 : 29.06.20 : PLN connection menunggu konfirmasi XL (FO readiness XL) 28.05.20 : SRFI, email SRFIN sent 27 may 25.05.20 : 08.05.20 : Preparation team & material 30.04.20 : eskalasi ke TNP XL, karna plan menggunakan FO ada pergantian infonya jadi menggunakan MW tapi belum keluar link budgetnya sampai sekarang
377 |  | NUS-NB-SEL-4332 | 20210800041 | 180206110 | RAKAM | ACTIVE | TB | 116.5256 | -8.6539 | 30 | 60/180/300 | 2020 | JEDI 2020 [NEW] | Jl. Diponegoro Lingk. Kampung Baru RT.13 Kel.Majidi Kec. Selong Kab. Lombok Timur - NTB | HTI | NUS-NB-SEL-4332 | SELONG_MAJIDI | COLO | TBG | EAST | BALINUSRA | Nusa Tenggara Barat | KAB. LOMBOK TIMUR | 6614644 | 2020-04-14 |  | 384 | > 150 days | 2020-05-14 | W20-2020 | May-2020 | 2020-06-04 | W23-2020 | Jun-2020 | 2021-04-30 | W18-2021 | Apr-2021 | 2021-04-30 | W18-2021 | Apr-2021 | FO (Change to MW as temp solution) | 2021-02-15 |  | 441204257209 | 6.6 Kva |  | 2020-05-04 |  | 2020-06-04 | 2021-05-03 | W19-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.05.21 : RFI 03.05.21 : Power Connection Process 26.04.21 : FO change to MW, OG PLN connection, BPUJL paid 19.04.21 : SPK FO issue, PLN connection hold 06.08.20 - 29.06.20 : PLN connection menunggu konfirmasi XL (FO readiness XL) 04.06.20 : SRFIN sent 28.05.20 : delivery material baseframe dan ME, plan SRFI 30 May 25.05.20 : 08.05.20 : Preparation team & material 30.04.20 : eskalasi ke TNP XL, karna plan menggunakan FO ada pergantian infonya jadi menggunakan MW tapi belum keluar link budgetnya sampai sekarang
134 |  | JAW-JI-LMJ-4220 | 30571160031 | 1642931003 | PRONOJIWO_ORO_ORO_OMBO | ACTIVE | TB | 112.9852 | -8.2024 | 50 | 20/100/180 | 2020 | JEDI 2020 [NEW] | Jl. Sumber Bulus, RT 004 RW 009, Ds. Oro Oro Ombo, Kec. Pronojiwo, Kab. Lumajang | HTI | JAW-JI-LMJ-4220 | PRONOJIWO_ORO_ORO_OMBO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. LUMAJANG | 6614369 | 2020-01-13 |  | 125 | 121 - 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-05-12 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 516091052465 | 6.6 |  | 2020-05-04 |  | 2020-04-20 | 2020-05-17 | W21-2020 |  | 2020-07-09 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.05.20 : RFIN sent 15.05.20 : RFI actual, wait RFIN 12.05.20 : ada penambahan 3 tiang PLN 08.05.20 : ada penambahan 1tiang PLN, revisi RFI plan 12 may 20 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 20.04.20 : email SRFI-N sent 09.04.20 : curing time 02.04.20 : on going excavation 25.03.20 : PKS proses , proses perijinan, CME OG 19.03.20 : 11.03.20 : Proses perijinan, RFC, proses DP lahan 28.02.20 : on going proses rekom l/c 24.02.20 : IW done, Realisasi IW Done , collect legal doc sitac, soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : TNP review 06.02.20 : kand A = validasi done, Candidate A RF TX OK
180 |  | JAW-JI-SMP-4115 | 30571620031 | 1643391003 | TALANGO_CABBIYA | ACTIVE | TB | 113.9793 | -7.0954 | 50 | 10/110/240 | 2020 | JEDI 2020 [NEW] | Dusun Cabbiya RT 001 / RW 005 Desa Cabbiya Kecamatan Talango Kabupaten Sumenep | HTI | JAW-JI-SMP-4115 | TALANGO_CABBIYA | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SUMENEP | 6614369 | 2020-01-13 |  | 143 | 121 - 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-09 | W19-2020 | May-2020 | 2020-06-04 | W23-2020 | Jun-2020 | 2020-06-04 | W23-2020 | Jun-2020 | MW | 2020-04-22 |  | 517101221890 | 6.6 |  | 2020-05-04 |  |  | 2020-06-04 | W23-2020 |  | 2020-08-31 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.06.20 : RFIN sent 01.06.20 : RFI actual, collecting doc RFIN 28.05.20 : 25.05.20 : 14.05.20 : 13.05.20 ; Erection sect 8, pond bts og, ponds pagar og, semua mat me ground os 08.05.20 : poring concrete 30.04.20 : rebarring, plan cor 3 may 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, rebarring on going 09.04.20 : on going excavation 02.04.20 : RFC, proses perijinan 25.03.20 : proses perijinan 19.03.20 : 11.03.20 : Proses perijinan, RFC, proses DP lahan 28.02.20 : on going proses rekom l/c 24.02.20: IW done, Realisasi IW Done , collect legal sitac ,soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : Kand B = Candidate B Submit
182 |  | JAW-JI-SMP-4116 | 30571630031 | 1643401003 | TALANGO_GAPURANA | ACTIVE | TB | 114.0011 | -7.0882 | 50 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Dusun Jubluk Timur RT 001 / RW 022 Desa Gapurana Kecamatan Talango Kabupaten Sumenep | HTI | JAW-JI-SMP-4116 | TALANGO_GAPURANA | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SUMENEP | 6614369 | 2020-01-13 |  | 143 | 121 - 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-09 | W19-2020 | May-2020 | 2020-06-04 | W23-2020 | Jun-2020 | 2020-06-04 | W23-2020 | Jun-2020 | MW | 2020-04-22 |  | 517101224139 | 6.6 |  | 2020-05-04 |  |  | 2020-06-04 | W23-2020 |  | 2020-09-02 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.06.20 : RFIN sent 01.06.20 : 29.05.20 : SRFI 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : ME og 30.04.20 : on going erection, BTS foundation dan ME installation 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, curingtime, prepare backfilling dan prepare start erection 09.04.20 : on going rebarring 02.04.20 : RFC, proses perijinan 25.03.20 : proses perijinan 19.03.20 : 11.03.20 : proses soiltest, proses collect doc legal 28.02.20 : on going proses rekom l/c 24.02.20 : IW done, Realisasi IW Done, collect legal sitac, soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
183 |  | JAW-JI-SMP-4119 | 30571660031 | 1643431003 | TALANGO_KOMBANG | ACTIVE | TB | 114.0585 | -7.1084 | 50 | 30/240/300 | 2020 | JEDI 2020 [NEW] | Dusun Galisek Laok RT 004 / RW 004 Desa Kombang Kecamatan Talango Kabupaten Sumenep | HTI | JAW-JI-SMP-4119 | TALANGO_KOMBANG | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SUMENEP | 6614369 | 2020-01-13 |  | 143 | 121 - 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-09 | W19-2020 | May-2020 | 2020-06-04 | W23-2020 | Jun-2020 | 2020-06-04 | W23-2020 | Jun-2020 | MW | 2020-04-22 |  | 517101224121 | 6.6 |  | 2020-05-04 |  |  | 2020-06-04 | W23-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.06.20 : RFIN sent 01.06.20 : 29.05.20 : SRFI 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : ME og 30.04.20 : on going erection, BTS foundation dan ME installation 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, erection OG 09.04.20 : on going excavation 02.04.20 : RFC, proses perijinan 25.03.20 : proses perijinan 19.03.20 : 11.03.20 : Proses perijinan, RFC, proses DP lahan 28.02.20 : on going proses rekom l/c 24.02.20 : IW done, Realisasi IW Done, collect legal sitac, soiltest done 20.02.20 : IW clear, proses realisasi IW dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
43 |  | JAW-JI-SMP-4111 | 30571590031 | 1643361003 | DUNGKEK_SOKON_JADUNG | ACTIVE | TB | 114.0338 | -7.0062 | 50 | 0/110/270 | 2020 | JEDI 2020 [NEW] | Dusun Girsereng RT 02 RW 01 Desa Jadung Kec Dungkek Kab Sumenep | HTI | JAW-JI-SMP-4111 | Dungkek_Sokon_Jadung | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SUMENEP | 6614369 | 2020-01-13 |  | 142 | 121 - 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-27 | W18-2020 | Apr-2020 | 2020-06-04 | W23-2020 | Jun-2020 | 2020-06-04 | W23-2020 | Jun-2020 | MW | 2020-04-22 |  | 517101225617 | 6.6 |  | 2020-05-04 |  |  | 2020-06-03 | W23-2020 |  | 2020-08-12 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03.06.20 : email SRFI-N sent 01.06.20 : 29.05.20 : SRFI 28.05.20 : 25.05.20 : 14.05.20 : start erection, pondasi BTS OG, mat pagar me ground plan mos 18/5 08.05.20 : prepare erection 30.04.20 : plan pouring concrete besok 1 may 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, rebarring done, lantai kerja OG 09.04.20 : on going excavation 45% 02.04.20 : on going excavation 25.03.20 : Proses perijinan 19.03.20 : 11.03.20 : Proses perijinan, RFC, proses DP lahan 28.02.20 : on going proses rekom l/c 27.02.20 : IW done, kand 07°00'23.69"S 114°02'01.78"E, 10 KK IW Done, Proses Collect legal Dokumen 24.02.20 : IW done, Realisasi IW Done , collect legal sitac, soiltest done 20.02.20 : IW clear, proses eskalasi sitac 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
366 |  | SUM-SB-PYH-0816 | 30591270031 | 030646109 | PERUMAHAN MUTIARA HATI PAYAKUMBUH | ACTIVE | TB | 100.6155 | -0.22671 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl Kamboja RT 01 RW 01, Kel. Subarang Batuang, Kec. Payakumbuh Barat, Kota Payakumbuh | HTI | SUM-SB-PYH-0816 | SUBARANG BATUANG | COLO | TBG | WEST | SUMBAGTENG | Sumatera Barat | KOTA PAYAKUMBUH | 6614688 | 2020-04-23 |  | 74 | 61 - 90 days | 2020-05-23 | W21-2020 | May-2020 | 2020-05-20 | W21-2020 | May-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-04 | W27-2020 | Jul-2020 | MW | 2020-06-12 |  | 134520277780 | 6.6 |  | 2020-04-28 |  | 2020-06-09 | 2020-07-06 | W28-2020 |  | 2020-08-05 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.07.20 : RFIN sent 02.07.20 : 30.06.20 : RFI actual, collecting doc RFIN 29.06.20 : PLN connection, plan RFI besok 25.06.20 : 22.06.20 : BP paid 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 09.06.20 : email SRFI-N sent 28.05.20 : Soft RFI 25.05.20 : 18.05.20 : ME on going 14.05.20 : RBS foundation on going 08.05.20 : Preparation team & material
392 |  | SUM-SU-TBT-2213 | 30591290031 | 020615109 | SEI KELEMBAH | ACTIVE | TB | 99.1455 | 3.3229 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl. Sei Kelembah, lingkungan VII, kelurahan Durian, kec. Bajenis, Kota tebing tinggi | HTI | SUM-SU-TBT-2213 | DURIAN_BARAT | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KOTA TEBING TINGGI | 6614688 | 2020-04-23 |  | 64 | 61 - 90 days | 2020-05-23 | W21-2020 | May-2020 | 2020-05-21 | W21-2020 | May-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | MW | 2020-06-12 |  | 121101024010 | 6.6 |  | 2020-04-28 |  | 2020-05-19 | 2020-06-26 | W26-2020 |  | 2020-07-25 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.06.20 : RFIN sent 25.06.20 : plan percepatan PLN connect 26 jun, plan RFIN latest 30 jun 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 11.06.20 : plan RFI 30 juni, request SK PLN 25.05.20 : 19.05.20 : SRFIN sent 14.05.20 : mob demob, preparation start CME 08.05.20 : Preparation team & material
382 |  | SUM-SU-SDK-2081 | 30591300031 | 020325104 | RD_TIGA_LINGGA | ACTIVE | SMI | 98.2852 | 2.8058 | 50 | 50/140/310 | 2020 | JEDI 2020 [NEW] | JL TIGA LINGGA KM 75, DESA SUNGAI RAYA, KEC. SIEMPAT NEMPUHULU, KAB. DAIRI SUMATERA UTARA | HTI | SUM-SU-SDK-2081 | GUNUNG MERIAH | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. DAIRI | 6614687 | 2020-04-23 |  | 64 | 61 - 90 days | 2020-05-23 | W21-2020 | May-2020 | 2020-05-21 | W21-2020 | May-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | MW | 2020-06-12 |  | 129010068449 | 6.6 |  | 2020-04-28 |  | 2020-05-18 | 2020-06-26 | W26-2020 |  | 2020-07-31 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.06.20 : RFIN sent 25.06.20 : actual RFI, plan RFIN latest 30 jun 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 11.06.20 : plan RFI 30 juni, request SK PLN 18.05.20 : SRFIN sent 14.05.20 : mob demob, preparation start CME 08.05.20 : Preparation team & material
423 |  | SUM-SU-BNJ-2064 | 30591280031 | 021281109 | TANJUNG_MERAHE_2 | ACTIVE | TB | 98.4941 | 3.5713 | 30 | 0/180/270 | 2020 | JEDI 2020 [NEW] | Jln. Jamin Ginting Gg. Buntu , Kel. Pujidadi, Kec. Binjai Selatan, Kota Binjai Sumatera Utara | HTI | SUM-SU-BNJ-2064 | PUJI DADI | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KOTA BINJAI | 6614688 | 2020-04-23 |  | 64 | 61 - 90 days | 2020-05-23 | W21-2020 | May-2020 | 2020-05-21 | W21-2020 | May-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | MW | 2020-06-12 |  | 122010727409 | 6.6 |  | 2020-04-28 |  | 2020-05-19 | 2020-06-26 | W26-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.06.20 : RFIN sent 25.06.20 : actual RFI, plan RFIN latest 30 jun 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 11.06.20 : plan RFI 30 juni, request SK PLN 25.05.20 : 19.05.20 : SRFIN sent 14.05.20 : mob demob, preparation start CME 08.05.20 : Preparation team & material
299 |  | SUL-SN-SKG-1278 | 30591310031 | T002776 | HCPTSS-212357 | ACTIVE | SKP | 120.023 | -4.0788 | 40 | 0/180/280 | 2020 | JEDI 2020 [NEW] | Jl. Tani Dusun Ujunge Desa Ujunge Kec. Tanasitolo Kab. Wajo | HTI | SUL-SN-SKG-1278 | UJUNGE | COLO | TBG | EAST | SULAWESI | Sulawesi Selatan | KAB. WAJO | 6614686 | 2020-04-23 |  | 166 | > 150 days | 2020-05-23 | W21-2020 | May-2020 | 2020-06-01 | W23-2020 | Jun-2020 | 2020-10-05 | W41-2020 | Oct-2020 | 2020-10-05 | W41-2020 | Oct-2020 | FO | 2020-08-26 |  | 322400370261 | 6.6 |  | 2020-04-28 |  | 2020-06-01 | 2020-10-06 | W41-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.10.20 : RFIN sent 12.09.20 : request connect PLN oleh Bu Endang by WAG XL 06.08.20 - 29.06.20 : PLN connection menunggu konfirmasi XL (FO readiness XL) 25.06.20 : 22.06.20 : 11.06.20 : : Soft RFI actual, email SRFI-N sent, waiting confirmation request connect PLN from XL/tech partner 28.05.20 : ME on going 21.05.20 : Material ME, tray etc Just On Port makasar. ETA OS 22 May 2020, Plan SRFI 26 May 2020 18.05.20 : BTS Foundation DONE. Material ME, etc On Delivery (ETA OS on 22 May 2020). 14.05.20 : material fabrication 08.05.20 : preparation team & material 05.05.20 : KOM mitra, request SPK CME mitra
298 |  | SUL-SN-SKG-1303 | 30591320031 | T002767 | HCPTSS-212345 | ACTIVE | SKP | 120.0742 | -4.1812 | 50 | 0/120/230 | 2020 | JEDI 2020 [NEW] | Desa Patila, Kec. Pammana, Kab. Wajo, Prov. SulSel | HTI | SUL-SN-SKG-1303 | PATILA | COLO | TBG | EAST | SULAWESI | Sulawesi Selatan | KAB. WAJO | 6614686 | 2020-04-23 |  | 165 | > 150 days | 2020-05-23 | W21-2020 | May-2020 | 2020-06-01 | W23-2020 | Jun-2020 | 2020-10-05 | W41-2020 | Oct-2020 | 2020-10-05 | W41-2020 | Oct-2020 | FO | 2020-08-26 |  | 322400370253 | 6.6 |  | 2020-04-28 |  | 2020-06-01 | 2020-10-05 | W41-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.10.20 : RFIN sent 12.09.20 : request connect PLN oleh Bu Endang by WAG XL 06.08.20 - 29.06.20 : PLN connection menunggu konfirmasi XL (FO readiness XL) 25.06.20 : 22.06.20 : 11.06.20 : 01.06.20 : Soft RFI actual, email SRFI-N sent, waiting confirmation request connect PLN from XL/tech partner 28.05.20 : ME on going 21.05.20 : Material ME, tray etc Just On Port makasar. ETA OS 22 May 2020, Plan SRFI 26 May 2020 18.05.20 : BTS Foundation DONE. Material ME, etc On Delivery (ETA OS on 22 May 2020). 14.05.20 : material fabrication: 08.05.20 : preparation team & material 05.05.20 : KOM mitra, request SPK CME mitra
239 |  | SUL-SN-PLP-1328 | 30591150031 | 280031109 | BALOBALO EX SULI BARAT | ACTIVE | TRB | 120.3552 | -3.3828 | 30 | 40/110/260 | 2020 | JEDI 2020 [NEW] | Jl. Gunung Latimojong, rt 01 rw 01, desa Balo-Balo, Kec Belopa | HTI | SUL-SN-PLP-1328 | BALO-BALO | COLO | TBG | EAST | SULAWESI | Sulawesi Selatan | KAB. LUWU | 6614665 | 2020-04-17 |  | 76 | 61 - 90 days | 2020-05-17 | W21-2020 | May-2020 | 2020-06-25 | W26-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-02 | W27-2020 | Jul-2020 | MW | 2020-06-12 |  | 326401094884 | 6.6 |  | 2020-04-24 |  | 2020-05-28 | 2020-07-02 | W27-2020 |  | 2020-07-16 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02.07.20 : email RFIN sent 30.06.20 : actual RFI, collecting doc RFIN 29.06.20 : proses PLN connection, plan connect besok 30 jun 25.06.20 : 22.06.20 : BP paid 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 11.06.20 : 28.05.20 : email SRFI-N sent, waiting confirmation request connect PLN from XL/tech partner 21.05.20 : Material ME, tray etc Just On Port makasar. ETA OS 22 May 2020, Plan SRFI 26 May 2020 18.05.20 : BTS Foundation DONE. Material ME, etc On Delivery (ETA OS on 22 May 2020). 14.05.20 : on going RBS foundataion, material ME etc on delivery 08.05.20 : material pabrication 30.04.20 : CME preparation
428 |  | SUL-SN-PLP-1334 | 30591170031 | 280489109 | TBG MURANTE PALOPO | ACTIVE | TB | 120.177 | -3.0089 | 30 | 90/180/320 | 2020 | JEDI 2020 [NEW] | Jl. Pongsimpin, RT.02 RW.03, Kel. Mungkajang, Kec.Mungkajang, Kota Palop, Prov.Sulsel | HTI | SUL-SN-PLP-1334 | MUNGKAJANG | COLO | TBG | EAST | SULAWESI | Sulawesi Selatan | KOTA PALOPO | 6614661 | 2020-04-17 |  | 76 | 61 - 90 days | 2020-05-17 | W21-2020 | May-2020 | 2020-06-25 | W26-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-02 | W27-2020 | Jul-2020 | MW | 2020-06-12 |  | 326100991653 | 6.6 |  | 2020-04-24 |  | 2020-05-29 | 2020-07-02 | W27-2020 |  | 2020-07-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02.07.20 : email RFIN sent 30.06.20 : actual RFI, collecting doc RFIN 02.07.20 : 29.06.20 : proses PLN connection, plan connect besok 30 jun 25.06.20 : 22.06.20 : BP paid 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 11.06.20 : 29.05.20 : email SRFI-N sent, waiting confirmation request connect PLN from XL/tech partner 28.05.20 : Soft RFI 21.05.20 : Material ME, tray etc Just On Port makasar. ETA OS 22 May 2020, Plan SRFI 26 May 2020 18.05.20 : BTS Foundation DONE. Material ME, etc On Delivery (ETA OS on 22 May 2020). 14.05.20 : on going RBS foundataion, material ME etc on delivery 08.05.20 : material pabrication 30.04.20 : CME preparation
431 |  | KAL-KS-MTP-0930 | 30591160031 | 220733109 | TBG_DSLABATMUARA | ACTIVE | TB | 114.5218 | -3.5007 | 50 | 0/90/180 | 2020 | JEDI 2020 [NEW] | LABAT MUARA, DS. LABAT MUARA, RT 002/ KEC. ALUH-ALUH | HTI | KAL-KS-MTP-0930 | BAKAMBAT | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | Banjar | 6614661 | 2020-04-17 |  | 166 | > 150 days | 2020-05-17 | W21-2020 | May-2020 | 2020-09-20 | W39-2020 | Sep-2020 | 2020-08-08 | W32-2020 | Aug-2020 | 2020-09-29 | W40-2020 | Sep-2020 | MW | 2020-06-12 |  | 221600397613 | 6.6 |  | 2020-04-24 |  | 2020-09-30 | 2020-09-30 | W40-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.10.20 : 30.09.20 : RFIN sent 30.09.20 : plan connect dan RFI hari ini 28.09.20 : SRFI actual, plan RFI 29/09 24.09.20 : ME on going 21.09.20 : erection done, revisi plan RFI 28 sep 17.09.20 : erection on going 14.09.20 : 10.09.20 : curingtime, prepare erection 07.09.20 : Cor done 04/09 dan Curing Time 03.09.20 : rebarring, plan cor minggu ini 31.08.20 : rebarring on going 27.08.20 : excavation & cerucuk donedone, on going lantai kerja, bar bending & preparation rebarring, plan RFI 20 sep 24.08.20 : 17.08.20 : on going cerucuk, need percepatan progress CME untuk target RFI 20 Sept 13.08.20 : start excavation, XL meminta percepatan RFI 10 Sep 20 10.08.20 : plan start CME selasa 11 Aug 20, revisi plan RFI 15 Sep 20 06.08.20 : 03.08.20 : 23.07.20 : preparation start CME 16.07.20 : 13.07.20 : bouwplank (permanenisasi) 09.07.20 : 06.07.20 : 02.07.20 : posisi site di muara sungai, survey done untuk pekerjaan CME (permanenisasi) , jarak langsir 5 km pakai gerobak, plan RFI W1 Aug (8 Aug 20) 29.06.20 : 18.06.20 : akses berada di area pasang surut dan saat ini kondisi sedang pasang sehingga tidak dapat kerja, permanenisasi 17.06.20 : Go RFI, PSB PLN release 15.06.20 : 11.06.20 : 08.06.20 : akses berada di area pasang surut dan saat ini kondisi sedang pasang sehingga tidak dapat kerja, permanenisasi 04.06.20 : 01.06.20 : 28.05.20 : akses berada di area pasang surut dan saat ini kondisi sedang pasang sehingga tidak dapat kerja 25.05.20 : 14.05.20 : 08.05.20 : ME on going, permanenisasi 30.04.20 : preparation dan delivery material 28.04.20 : STO, preparation
10 |  | JAW-JI-SIT-3801 | 30571540031 | 1643311003 | BANYUPUTIH_SUMBEREJO | ACTIVE | TB | 114.2744 | -7.7494 | 40 | 20/110/200 | 2020 | JEDI 2020 [NEW] | KP.Sukorejo RT 02 RW 0, Desa Sumberejo, Kecamatan Banyuputih, Kabupaten Situbondo, Prov. Jawa Timur | HTI | JAW-JI-SIT-3801 | BANYUPUTIH_SUMBEREJO | B2S | TBG | EAST | JATIM | Jawa Timur | KAB. SITUBONDO | 6614369 | 2020-01-13 |  | 396 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-22 | W21-2020 | May-2020 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-02-20 | W08-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-01-18 |  | 516520538120 | 10.6 |  | 2020-04-23 |  | 2020-05-22 | 2021-02-12 | W07-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.21 : note daya PLN connection dengan daya 10.6 dan 13.2 kVA diterima HO PLN, jika lebih dari 13.2 kVA menunggu downgrade terlebih dahulu baru bisa di HO PLN. Jaringan sudah ready 26.01.21 : BP Paid 21.01.21 : PSB released, PLN connection OG 23.07.20 : 09.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SRFI, wait confirmation XL for PLN connection 28.05.20 : 22.05.20 : email SRFI-N sent 08.05.20 : SRFI 30.04.20 : erection done, on going tower painting 23.04.20 : 09.04.20 : erection on going 02.04.20 : on going excavation 25.03.20 : PKS proses , proses perijinan, CME OG 19.03.20 : 11.03.20 : Proses perijinan, RFC, proses DP lahan 28.02.20 : on going proses rekom l/c 24.02.20 : IW done, Realisasi IW Done , collect legal sitac, soiltest done 20.02.20 : IW clear, proses eskalasi sitac 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
303 |  | SUM-SB-BSK-0812 | 30590850031 | 030730109 | JALAN LINTAS PADANG PANJANG SOLOK | ACTIVE | TB | 100.4362 | -0.47201 | 40 | 90/200/270 | 2020 | JEDI 2020 [NEW] | Batang Arau Jorong Kubu Nan Limo, Nagari Batipuh Baruh, Kecamatan Batipuh, Kabupaten Tanah Datar, Provinsi Sumatera Barat | HTI | SUM-SB-BSK-0812 | BATIPUH BARUH | COLO | TBG | WEST | SUMBAGTENG | Sumatera Barat | KAB. TANAH DATAR | 6614657 | 2020-04-16 |  | 81 | 61 - 90 days | 2020-05-16 | W20-2020 | May-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-04 | W27-2020 | Jul-2020 | MW | 2020-06-12 |  | 132221314190 | 6.6 |  | 2020-04-22 |  | 2020-06-09 | 2020-07-06 | W28-2020 |  | 2020-07-21 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.07.20 : RFIN sent 02.07.20 : 30.06.20 : RFI actual, collecting doc RFIN 29.06.20 : PLN connection, plan RFI besok 25.06.20 : 22.06.20 : BP paid 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 09.06.20 : email SRFI-N sent 28.05.20 : Soft RFI 25.05.20 : 14.05.20 : ME on going 08.05.20 : RBS foundation 30.04.20 : preparation & material delivery 24.04.20 : STO, STIP release
379 |  | SUM-JA-MBN-0463 | 30590830031 | 060532109 | RAMBUTAN MASAM | ACTIVE | TB | 103.0818 | -1.7041 | 50 | 90/170/270 | 2020 | JEDI 2020 [NEW] | Desa Rambutan Masam, RT.09 Dusun Tengah, Desa Rambutan Masam, Kec. Muara Tembesi, Kab. Batang Hari | HTI | SUM-JA-MBN-0463 | RAMBUTAN MASAM | COLO | TBG | WEST | SUMBAGSEL | Jambi | KAB. BATANG HARI | 6614657 | 2020-04-16 |  | 69 | 61 - 90 days | 2020-05-16 | W20-2020 | May-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | MW | 2020-06-12 |  | 143509414873 | 6.6 |  | 2020-04-22 |  | 2020-06-16 | 2020-06-24 | W26-2020 |  | 2020-07-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.06.20 : RFIN sent 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 16.06.20 : email SRFI-N sent 08.06.20 : SRFI 04.06.20 : erection done, ME on going 28.05.20 : erection tower permanenisasi, plan finish erection 30 May 25.05.20 : borepile permanenisasi 14.05.20 : galian site permanenisasi 08.05.20 : prepare start CME 30.04.20 : preparation & material delivery 24.04.20 : STO, STIP release
342 |  | SUM-JA-SNT-0474 | 30590840031 | 060234109 | MUARO JAMBI1 | ACTIVE | TB | 103.5055 | -1.4709 | 40 | 30/100/180 | 2020 | JEDI 2020 [NEW] | Jl. Desa Lintas Timur, RT 08 RW 04, Kel.Sengeti, Kec. Sekernan, Kab. Muaro Jambi, Prov Jambi | HTI | SUM-JA-SNT-0474 | SENGETI_SEKERNAN | COLO | TBG | WEST | SUMBAGSEL | Jambi | KAB. MUARO JAMBI | 6614657 | 2020-04-16 |  | 69 | 61 - 90 days | 2020-05-16 | W20-2020 | May-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | MW | 2020-06-12 |  | 143205431662 | 6.6 |  | 2020-04-22 |  | 2020-05-18 | 2020-06-24 | W26-2020 |  | 2020-07-12 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.06.20 : RFIN sent 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 25.05.20 : 18.05.20 : SRFI actual, SRFIN sent 14.05.20 : on going RBS Foundation 08.05.20 : prepare start CME 30.04.20 : preparation & material delivery 24.04.20 : STO, STIP release
114 |  | SUM-JA-SNT-0470 | 30571730031 | 0605921003 | MUARO SEBAPO | ACTIVE | TB | 103.5707 | -1.7266 | 50 | 30/200/300 | 2020 | JEDI 2020 [NEW] | Dusun Melati RT. 014 RW. 000, Desa Muaro Sebapo, Kecamatan Mestong, Kabupaten Muaro Jambi, Provinsi Jambi | HTI | SUM-JA-SNT-0470 | MUARO SEBAPO | B2S | TBG | WEST | SUMBAGSEL | Kep. Bangka Belitung | KAB. MUARO JAMBI | 6614369 | 2020-01-13 |  | 170 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-30 | W18-2020 | Apr-2020 | 2020-07-03 | W27-2020 | Jul-2020 | 2020-07-03 | W27-2020 | Jul-2020 | MW | 2020-04-22 |  | 143105835415 | 6.6 |  | 2020-04-16 |  | 2020-05-29 | 2020-07-01 | W27-2020 |  | 2020-07-10 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02.07.20 : RFIN sent 1 jul 29.06.20 : 25.06.20 : plan percepatan PLN connect 30 jun 22.06.20 : Go RFI, proses PLN Connection 29.05.20 : email SRFI-N sent 28.05.20 : 27.05.20 : Soft RFI actual 25.05.20 : SRFI actual 14.05.20 : erection done, ME on going 08.05.20 : erection on going 30.04.20 : curingtime23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 16.04.20 : lantai kerja, start rebarring 09.04.20 : Proses perijinan, CME start wait perijinan 06.04.20 : plan angkur template on site dalam 3 hari, plan GDL angkur diusahakan hari ini, plan percepatan SRFI di April, isu tower 52m 02.04.20 : proses perijinan, RFC, preparation start CME, plan tower on site W2 Apr 25.03.20 : soiltest done, proses APD, proses perijinan 19.03.20 : on going soiltest, on going rekom camat plan minggu dpn W13 done 11.03.20 : 09.03.20 : eskalasi sitac approved, plan realisasi IW sabtu 14 feb, collecting & review legal doc, plan request soiltest 28.02.20 : collecting legal doc, proses eskalasi sitac 20.02.20 : IW clear, proses eskalasi sitac 13.02.20 : IW on going 06.02.20 : Kand C = RF OK, TX review 23.01.20 : kand A = TNP 48 0.6 16.13 22.01.20 : kand A = RND 50 30/210/310 22Jan20 : Ok candidate A, tower 52 21.01.20 : kand A, B = submit A 103.57014 -1.72631 B 103.56789 -1.72756
204 |  | SUM-JA-SNT-0467 | 30571720031 | 0605911003 | TALANG DUKU | ACTIVE | TB | 103.6664 | -1.5132 | 50 | 60/190/310 | 2020 | JEDI 2020 [NEW] | Dusun Mengkuang Belayar RT.011, Desa Talang Duku, Kecamatan Taman Rajo, Kabupaten Muaro Jambi, Provinsi Jambi. | HTI | SUM-JA-SNT-0467 | TALANG DUKU | B2S | TBG | WEST | SUMBAGSEL | Kep. Bangka Belitung | KAB. MUARO JAMBI | 6614369 | 2020-01-13 |  | 363 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-30 | W18-2020 | Apr-2020 | 2020-06-04 | W23-2020 | Jun-2020 | 2021-01-18 | W04-2021 | Jan-2021 | MW | 2020-04-22 |  | 143005584847 | 6.6 |  | 2020-04-13 |  | 2020-05-29 | 2021-01-10 | W03-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.01.21 : RFI sent 07.01.21 : perluasan jaringan done, menunggu stock KWH meter 28.12.20 : 17.12.20 : 14.12.20 : proses MoU sharing investasi dgn PLN 10.12.20 : waiting approval XL terkait sharing cost penyambungan dengan daya 6.6 kVA 03.12.20 : eskalasi daya 33 kVA rejected by Power Eng XL, propose sharing investasi 10.6 kVA tidak dilayani oleh PLN 30.11.20 : issue PLN tetap hanya melayani proses connect dengan daya 33kVA, menunggu approval XL terkait daya 33kVA 19.11.20 : issue pengadaan material tiang PLN (perluasan jaringan) 16.11.20 : plan connect PLN W3 Nov (17 Nov) 09.11.20 : 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 : 22.10.20 : issue daya 33kVA, proses pengajuan sharing investasi 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : 01.10.20 : 28.09.20 : 24.09.20 : 21.09.20 : PLN connection waiting approval XL (up daya), revisi plan RFI 5 oct, plan PLN connection 10 hari setelah approval XL 17.09.20 : 14.09.20 : 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : 24.08.20 : proses review eskalasi add work PLN, waiting approval XL Power Eng, re-plan RFI 10 sep 13.08.20 : proses koordinasi/nego ke PLN 06.08.20 : isu perluasan jaringan (BP<Biaya investasi PLN) sehingga masuk daftar tunggu atau permohonan sambungan daya 33 kVA, sedang proses eskalasi approval ke XL. 03.08.20 : proses PLN connection, eskalasi isu sambungan yang dilayani PLN adalah dengan daya 33 kVA 20.07.20 : revisi plan connect PLN rabu 22 jul 13.07.20 : plan connect PLN hari ini atau besok 14 jul 09.07.20 : revisi plan RFI 15 jul 20 06.07.20 : 02.07.20 : 29.06.20 : revisi plan RFI 8 jul 25.06.20 : plan PLN connect 27 jun 22.06.20 : 08.06.20 : 05.06.20 : isu stock KWH meter, info ready masih sekitar 1 bulan lagi, sedang di nego alternatif connect dg MG, REVISI PLAN RFI dri 4 juni menjadi akhir minggu ini 13 Jun 20 29.05.20 : email SRFI-N sent 28.05.20 : 27.05.20 : Soft RFI actual 25.05.20 : SRFI actual 14.05.20 : erection done, ME on going 08.05.20 : erection on going 30.04.20 : curingtime 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 16.04.20 : lantai kerja, start rebarring 09.04.20 : borepile done, on going galian pondasi 06.04.20 : plan angkur template on site dalam 3 hari, plan GDL angkur diusahakan hari ini, plan percepatan SRFI di April, isu tower 52m 02.04.20 : on going borepile, plan Soft RFI end of April 25.03.20 : proses perijinan, prepare CME, bouwplank 19.03.20 : proses perijinan, prepare CME, plan start CME minggu depan (W13) 11.03.20 : rekom done, soiltest done, on going proses APD, prepare apply imb, paralel 28.02.20 : Rekom L/C on going 20.02.20 : IW clear, proses eskalasi sitac 13.02.20 : IW on going 06.02.20 : kand A = validasi done 23.01.20 : kand A = TNP 48 0.6 193.90 22.01.20 : kand A = RND 50 25/170/320 22Jan20 : Ok candidate A, tower 52 21.01.20 : kand A, B, C = submit A 103.66822 -1.51306 B 103.66883 -1.51506 C 103.66578 -1.5095
294 |  | SUM-KR-BTM-0585 | 30590450031 | 050257110 | GALANG ISLAND | ACTIVE | TB | 104.2001 | 0.75018 | 60 | 100/180/300 | 2020 | JEDI 2020 [NEW] | jalan barelang, RT 001 RW 001, Desa/Kelurahan Sijantung, Kecamatan Galang - Batam | HTI | SUM-KR-BTM-0585 | CAMP VIETNAM GALANG | COLO | TBG | WEST | SUMBAGTENG | Kep. Riau | Kota Batam | 6614627 | 2020-04-08 |  | 58 | 31 - 60 days | 2020-05-08 | W19-2020 | May-2020 | 2020-04-30 | W18-2020 | Apr-2020 | 2020-04-30 | W18-2020 | Apr-2020 | 2020-06-29 | W27-2020 | Jun-2020 | MW | 2020-05-18 |  | 153000343653 | 6.6 |  | 2020-04-09 |  | 2020-04-24 | 2020-06-05 | W23-2020 |  | 2020-05-30 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.06.20 : RFIN sent 03.06.20 : actual RFI, PLN connection + trafo done 25.05.20 : BPRAB paid, proses pemasangan trafo 14.05.20 : 30.04.20 : Proses PLN connection dan pemasangan trafo 24.04.20 : email SRFIN sent 25.04.20 : SRFI
275 |  | SUM-SU-KBJ-2074 | 30590440031 | 021738109 | D A U L U | ACTIVE | TB | 98.5145 | 3.2266 | 30 | 10/90/290 | 2020 | JEDI 2020 [NEW] | Desa Semangat Gunung, Kec. Merdeka, Kab Karo, Prov Sumatra Utara | HTI | SUM-SU-KBJ-2074 | SEMANGAT GUNUNG | COLO | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KAB. KARO | 6614566 | 2020-03-19 |  | 78 | 61 - 90 days | 2020-04-18 | W16-2020 | Apr-2020 | 2020-04-30 | W18-2020 | Apr-2020 | 2020-06-13 | W24-2020 | Jun-2020 | 2020-06-13 | W24-2020 | Jun-2020 | MW | 20-May-20 18-May-20 |  | 129030028604 | 6.6 |  | 2020-04-08 |  | 2020-04-29 | 2020-06-05 | W23-2020 |  | 2020-08-28 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.06.20 : RFIN sent 30.04.20 : 29.04.20 : SRFIN sent 23.04.20 : 16.04.20 : 09.04.20 : 25.03.20 : under RNP review HTI
193 |  | SUM-AC-SGI-0716 | 30571710031 | 0109811003 | TEUNGKU DILAWEUENG | ACTIVE | TB | 95.8653 | 5.5119 | 50 | 120/200/280 | 2020 | JEDI 2020 [NEW] | Desa Tgk. Dilaweueng, Kec. Muara Tiga, Kab. Pidie, Prov. Aceh | HTI | SUM-AC-SGI-0716 | TEUNGKU DILAWEUENG | B2S | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KAB. PIDIE | 6614369 | 2020-01-13 |  | 246 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-06-04 | W23-2020 | Jun-2020 | 2020-09-15 | W38-2020 | Sep-2020 | MW | 2020-04-22 |  | 116600193382 | 6.6 |  | 2020-04-08 |  | 2020-05-19 | 2020-09-15 | W38-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.09.20 : RFIN sent 14.09.20 : RFI actual, RFIN menunggu penyelesaian isu comcase krn penanaman pole PLN, 13.09.20 : today masih perluasan jaringan pasang tiang 10.09.20 : proses pemasangan pole PLN (perluasan jaringan) 07.09.20 : 31.08.20 : 27.08.20 : plan RFI W2 Sept, plan hari ini bertemu dg manager PLN 24.08.20 : 18.08.20 : Hasil nego dg PLN OK, plan connect PLN 26 Aug 03.08.20 : 20.07.20 : proses PLN agar dapat di lakukan connect PLN, revisi plan connect 31 jul 06.07.20 : Surat balasan dari PLN SIGLI KOTA/ACEH 25 jun mengenai belum tersedianya material uprating trafo 29.06.20 : 25.06.20 : material KWH sudah ready, menunggu approval PLN manager, plan RFI 30 jun 22.06.20 : 11.06.20 : plan RFI juni 08.06.20 : 05.06.20 : PLN OVB need uprating trafo by PLN, masih kami nego alternatif connect Multiguna, REVISI PLAN RFI dri 4 juni menjadi akhir minggu ini 13 Jun 20 04.06.20 : stock KWH meter kosong, sedang di usahakan connect MG 25.05.20 : 19.05.20 : SRFIN sent 30.04.20 : erection start 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 22.04.20 : curing time 16.04.20 : rebarring 09.04.20 : 02.04.20 : on going excavation 25.03.20 : CME preparation/bouwplank 19.03.20 : preparation start cme, wait rekom for start CME, wait GDL tower 11.03.20 : RFC, proses apply imb, wait GDL T52m, CME start after IMB release 28.02.20 : Rekom Camat on going, Rekom Lurah done 20.02.20 : IW clear, proses eskalasi sitac 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 31.01.20 : Kand A = TNP OK 50 0.6 298.70 30.01.20 : Kand A = RND OK 50 120/205/285 30Jan20 : Ok candidate A, tower 52 28.01.20 : Kand A = Tower 52m, submit 95.86566 5.51197
345 |  | KAL-KB-SRY-0688 | 30590300031 | 200226109 | NEW_KUALADUA | ACTIVE | SKP | 109.444 | -0.18739 | 40 | 40/160/300 | 2020 | JEDI 2020 [NEW] | Jl. Kembang Wonosari, RT 07/04, Kel Sei Raya, Kec. Kuala Dua, Kab. Kubu Raya, Kalimantan Barat | HTI | KAL-KB-SRY-0688 | KUALADUA SUNGAI | COLO | TBG | JABO | KALIMANTAN | Kalimantan Barat | KAB. KUBU RAYA | 6614550 | 2020-03-13 |  | 83 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-30 | W18-2020 | Apr-2020 | 2020-06-13 | W24-2020 | Jun-2020 | 2020-06-13 | W24-2020 | Jun-2020 | MW | 20-May-20 18-May-20 |  | 211201761331 | 6.6 |  | 2020-04-03 |  | 2020-05-27 | 2020-06-04 | W23-2020 |  | 2020-07-05 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.06.20 : RFIN sent 28.05.20 : 27.05.20 : email SRFI-N sent 30.04.20 : SRFI actual 30.04.20 : RBS foundation on going 23.04.20 : 16.04.20 : CME preparation 09.04.20 : 02.04.20 : UNDER REVIEW TNP ALITA 25.03.20 : under RNP review
426 |  | KAL-KS-MRH-0888 | 30590290031 | 210540109 | TBG GM DESA SUNGAIKALI | ACTIVE | TB | 114.6642 | -3.0615 | 40 | 0/60/210 | 2020 | JEDI 2020 [NEW] | Desa Sungai Kali RT 007/003, Kec. Barambai, Kab. Barito Kuala | HTI | KAL-KS-MRH-0888 | SUNGAIKALI | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | KAB. BARITO KUALA | 6614551 | 2020-03-13 |  | 120 | 91 - 120 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-10 | W28-2020 | Jul-2020 | MW | 2020-06-12 |  | 221500499729 | 6.6 |  | 2020-04-03 |  |  | 2020-07-11 | W28-2020 |  | 2020-07-31 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.07.20 : RFIN sent 09.07.20 : plan PLN connect 10 jul 06.07.20 : 02.07.20 : plan PLN connection 6 jul, plan sent RFIN 7 jul 29.06.20 : Soft RFI, proses PLN Connection 18.06.20 : pemasangan cerucuk (permanenisasi) 17.06.20 : Go RFI, PSB PLN release 15.06.20 : 11.06.20 : 08.06.20 : pemasangan cerucuk (permanenisasi) 04.06.20 : 01.06.20 : 28.05.20 : lokasi berada di area pasang surut dan saat ini kondisi sedang pasang sehingga tidak dapat kerja (pemasangan cerucuk pondasi) 25.05.20 : 14.05.20 : 08.05.20 : ME on going, permanenisasi 30.04.20 : RBS foundation on going 23.04.20 : 16.04.20 : CME preparation 09.04.20 : 02.04.20 : UNDER REVIEW TNP ALITA 25.03.20 : under RNP review
245 |  | SUM-AC-SGI-0701 | 30590010031 | 010680109 | BARIEH | ACTIVE | TB | 95.9727 | 5.2292 | 50 | 20/90/240 | 2020 | JEDI 2020 [NEW] | Gampong Seuri Weuk, Kecamatan Pidie, Aceh | HTI | SUM-AC-SGI-0701 | BARIEH | COLO | TBG | WEST | SUMBAGUT | Aceh | KAB. PIDIE | 6614551 | 2020-03-13 |  | 84 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-28 | W18-2020 | Apr-2020 | 2020-05-14 | W20-2020 | May-2020 | 2020-05-16 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 116610137714 | 6.6 |  | 2020-04-02 |  | 2020-05-08 | 2020-06-05 | W23-2020 |  | 2020-07-07 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.06.20 : RFIN sent 04.06.20 : plan connect PLN hari ini 28.05.20 : collect doc RFIN, plan email RFIN besok, ada perluasan jaringan (nambah tiang dan perubahan jaringan 1 phase menjadi 3 phase) 25.05.20 : actual RFI 18.05.20 : area site banjir sehingga PLN tidak dapat access, plan PLN connect 21 May 20 14.05.20 : revisi plan RFI sabtu 16 may 08.05.20 : email SRFI-N sent 30.04.20 : RBS foundation done, ME on going 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 16.04.20 : BTS foundation done, delivery material ME grounding tray mounting 09.04.20 : 02.04.20 : UNDER REVIEW TNP ALITA 25.03.20 : under RNP review
280 |  | SUM-AC-SGI-0695 | 30590000031 | 010653109 | DESA KEUREUMBOK | ACTIVE | TB | 96.0177 | 5.3181 | 40 | 70/200/330 | 2020 | JEDI 2020 [NEW] | Jalan Teupin Raya-Ujong Rimba Gampong Reudeup Melayu, Kecamatan Glumpang Tiga, Kabupaten Pidie | HTI | SUM-AC-SGI-0695 | KEUREUMBOK | COLO | TBG | WEST | SUMBAGUT | Aceh | KAB. PIDIE | 6614551 | 2020-03-13 |  | 70 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-28 | W18-2020 | Apr-2020 | 2020-05-14 | W20-2020 | May-2020 | 2020-05-16 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 116600193906 | 6.6 |  | 2020-04-02 |  | 2020-05-08 | 2020-05-22 | W21-2020 |  | 2020-07-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22.05.20 : email RFIN sent 18.05.20 : area site banjir sehingga PLN tidak dapat access, plan PLN connect 21 May 20 14.05.20 : revisi plan RFI sabtu 16 may 08.05.20 : email SRFI-N sent 30.04.20 : RBS foundation done, ME on going 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 16.04.20 : BTS foundation done, delivery material ME grounding tray mounting 09.04.20 : 02.04.20 : UNDER REVIEW TNP ALITA 25.03.20 : under RNP review
401 |  | SUM-SU-BLG-2119 | 30590040031 | 022079126 | SIONGGANG UTARA | ACTIVE | TB | 99.0445 | 2.5872 | 50 | 140/210/290 | 2020 | JEDI 2020 [NEW] | Jl. Siborong borong-Prapat, Desa Sionggang Utara, Kec. Lumban Julu, Kab. Toba Samosir, Prov. Sumatera Utara | HTI | SUM-SU-BLG-2119 | PASAR LUMBAN JULU | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. TOBA SAMOSIR | 6614551 | 2020-03-13 |  | 64 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-28 | W18-2020 | Apr-2020 | 2020-05-14 | W20-2020 | May-2020 | 2020-05-16 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 123100295988 | 6.6 |  | 2020-04-02 |  | 2020-04-20 | 2020-05-16 | W20-2020 |  | 2020-07-30 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.05.20 : RFIN sent 14.05.20 : revisi plan RFI sabtu 16 may 20.04.20 : email SRFI-N sent 30.04.20 : pondasi done, wait ME 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 16.04.20 : CME preparation & material delivery 09.04.20 : 02.04.20 : UNDER REVIEW TNP ALITA 25.03.20 : under RNP review
417 |  | SUM-SU-LMP-2092 | 30590060031 | 021265109 | TALAWI | ACTIVE | TB | 99.5632 | 3.2232 | 40 | 100/210/300 | 2020 | JEDI 2020 [NEW] | Dusun 1, Desa Mesjid Lama, Kecamatan Talawi, Kabupaten Batubara | HTI | SUM-SU-LMP-2092 | MESJID LAMA | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. BATU BARA | 6614551 | 2020-03-13 |  | 62 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-28 | W18-2020 | Apr-2020 | 2020-05-14 | W20-2020 | May-2020 | 2020-05-16 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 121140725079 | 6.6 |  | 2020-04-02 |  | 2020-04-20 | 2020-05-14 | W20-2020 |  | 2020-07-12 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.05.20 : revisi plan RFI sabtu 16 mayRFIN sent 20.04.20 : email SRFI-N sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 16.04.20 : ME on going 09.04.20 : 02.04.20 : UNDER REVIEW TNP ALITA 25.03.20 : under RNP review
380 |  | SUM-SU-PSP-2147 | 30590070031 | 022000109 | RANJO BATO | ACTIVE | TB | 99.3226 | 1.3585 | 50 | 160/230/320 | 2020 | JEDI 2020 [NEW] | Jl. Labuhan Labo Lorong IV, Desa Labuhan Labo, Kec. Padangsidimpuan Tenggara | HTI | SUM-SU-PSP-2147 | LABUHAN LABO | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KOTA PADANGSIDIMPUAN | 6614551 | 2020-03-13 |  | 89 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-28 | W18-2020 | Apr-2020 | 2020-06-13 | W24-2020 | Jun-2020 | 2020-06-13 | W24-2020 | Jun-2020 | MW | 20-May-20 18-May-20 |  | 124011301805 | 6.6 |  | 2020-04-02 |  | 2020-05-06 | 2020-06-10 | W24-2020 |  | 2020-08-14 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.06.20 : RFIN sent 04.06.20 : on going proses PLN connection 25.05.20 : 06.05.20 : SRFIN sent 30.04.20 : pondasi done, wait ME 23.04.20 : 16.04.20 : CME preparation & material delivery 09.04.20 : 02.04.20 : UNDER REVIEW TNP ALITA 25.03.20 : under RNP review
358 |  | SUM-SU-SDK-2211 | 30590080031 | 022144126 | PEGAGAN JULU IX_SUMBUL | ACTIVE | TB | 98.3658 | 2.777 | 50 | 30/140/300 | 2020 | JEDI 2020 [NEW] | Jalan Besar Batang Ari, Harungguan, Dusun II, Desa Pagagan Julu IX, Kecamatan Sumbul, Kabupaten Dairi, Provinsi Sumatera Utara | HTI | SUM-SU-SDK-2211 | PEGAGAN JULU IX | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. DAIRI | 6614551 | 2020-03-13 |  | 133 | 121 - 150 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-07-05 | W28-2020 | Jul-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-24 | W30-2020 | Jul-2020 | MW | 2020-06-12 |  | 129010071051 | 6.6 |  | 2020-04-02 |  | 2020-06-30 | 2020-07-24 | W30-2020 |  | 2020-08-06 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.07.20 : wait perubahan type tower di system dan CAF permanent untuk proses PR 24.07.20 : RFIN sent 20.07.20 : 16.07.20 : revisi plan connect PLN 24 jul 20 13.07.20 : 06.07.20 : 02.07.20 : 30.06.20 : email SRFI-N sent 29.06.20 : erection on going plan sampai top hari ini 25.06.20 : 22.06.20 : 18.06.20 : plan pouring concrete/cor 18 jun 20 17.06.20 : Go RFI, PSB PLN release 15.06.20 : rebarring, plan cor kamis 18 jun 20 11.06.20 : excavation, plan RFI 10 JULI, request SK PLN 08.06.20 : 04.06.20 : 01.06.20 : on going borepile permanenisasi 28.05.20 : 25.05.20 : borepile permanenisasi 14.05.20 : 08.05.20 : on going mob demob CME permanenisasi, CME ny start 30.04.20 : 23.04.20 : 16.04.20 : start CME colo menunggu proses permanenisasi (wait material tower) 09.04.20 : 02.04.20 : UNDER REVIEW TNP ALITA 25.03.20 : under RNP review
331 |  | SUM-SU-KPI-2146 | 30590050031 | 022194109 | LINTAS BATU AJO | ACTIVE | TB | 100.1213 | 1.7781 | 50 | 0/150/240 | 2020 | JEDI 2020 [NEW] | Jl. Besar Batu Ajo, Dusun Sumber Sari, Desa Pasir Tuntung, Kecamatan Kota Pinang, Kabupaten Labuhanbatu Selatan, Prov. Sumatera Utara | HTI | SUM-SU-KPI-2146 | TELUK RAMPAH | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. LABUHAN BATU SE | 6614551 | 2020-03-13 |  | 130 | 121 - 150 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-07-05 | W28-2020 | Jul-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-20 | W30-2020 | Jul-2020 | MW | 2020-06-12 |  | 125100659094 | 6.6 |  | 2020-04-02 |  |  | 2020-07-21 | W30-2020 |  | 2020-09-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.07.20 : wait perubahan type tower di system dan CAF permanent untuk proses PR 21.07.20 : RFIN sent 13.07.20 : Permanenisasi site SRFI, on going RBS foundation XL 08.07.20 : curing time dan backfilling, sehunungan istri LL baru meninggal maka start erection baru dapat dilakukan setelah 7 harian (tahlilan) 06.07.20 : curingtime 02.07.20 : curingtime 30.06.20 : pouring concrete on going 29.06.20 : wait angkur template for pouring preparation, plan angkur template on site 29 jun, ada warga tetangga site terkena covid sehingga berdampak pada penyetopan pekerjaan. saat ini sedang proses negosiasi. 25.06.20 : plan angkur template on site 28 jun 22.06.20 : 18.06.20 : 17.06.20 : Go RFI, PSB PLN release, rebarring, wait angkur template 15.06.20 : rebarring, wait angkur template 11.06.20 : excavation, plan RFI 10 JULI, request SK PLN 08.06.20 : 04.06.20 : 01.06.20 : 28.05.20 : 25.05.20 : 08.05.20 : Lockdown karena Covid 19, warga menolak semua surat2 rekomendasi, dan tidak mau ada warga luar yang masuk ke daerahnya. Sudah ada Surat Penyetopan/penundaan pekerjaan dari Kepala Desa Pasir Tuntung. 30.04.20 : 23.04.20 : 16.04.20 : start CME colo menunggu proses permanenisasi (wait material tower) 09.04.20 : 02.04.20 : UNDER REVIEW TNP ALITA 25.03.20 : under RNP review
402 |  | SUM-SB-SRK-0837 | 30590030031 | 030802109 | SITANANG | ACTIVE | TB | 100.7451 | -0.28007 | 50 | 90/260/350 | 2020 | JEDI 2020 [NEW] | Jorong Tanjung Gadang Rumah, Nagari Tanjung Gadang, Kecamatan Lareh Sago Halaban, Kabupaten Lima Puluh Kota, Propinsi Riau. | HTI | SUM-SB-SRK-0837 | TANJUANG GADANG | COLO | TBG | WEST | SUMBAGTENG | Sumatera Barat | KAB. LIMA PULUH KOTA | 6614551 | 2020-03-13 |  | 174 | > 150 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-07-20 | W30-2020 | Jul-2020 | 2020-09-03 | W36-2020 | Sep-2020 | MW | 2020-04-22 |  | 134520283485 | 6.6 |  | 2020-04-02 |  | 2020-09-03 | 2020-09-03 | W36-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.09.20 : 03.09.20 : RFIN sent 31.08.20 : 27.08.20 : PLN connect, RFI actual, collecting doc RFIN 24.08.20 : revisi plan RFI 25 Aug 18.08.20 : waiting jadwal connect by PLN, revisi plan RFI 21 Aug 10.08.20 : revisi plan RFI 14 Aug 20 06.08.20 : 03.08.20 : ME on going, plan RFI sabtu 8 Aug 30.07.20 : 27.07.20 : on going pondasi RBS XL, plan RFI 30 jul 23.07.20 : on going pondasi RBS XL 20.07.20 : Permanenisasi SRFI, Colo preparing CME plan RFI 27 jul 16.07.20 : prepare erection. Pondasi bts done, need finishing 02.07.20 : on going rebarring borepile 29.06.20 : on going rebarring borepile 22.06.20 : on going rebarring borepile. baru dapat akses masuk lagi setelah PSBB pertengahan Juni lalu, plan RI 20 jul 20 18.06.20 : 15.06.20 : bore pile on going 11.06.20 : pembersihan longsoran lubang borepile yang sebelumnya di tinggalkan cukup lama karena stop isu covid 19 08.06.20 : 04.06.20 : 01.06.20 : 28.05.20 : pekerjaan di stop warga karena isu covid dan pekerja di minta meninggalkan lokasi, progress terakhir sedang on going borepile 25.05.20 : borepile permanenisasi 14.05.20 : 08.05.20 : galian pondasi di stop dan di demo warga karena khawatir isu Covid 19 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 16.04.20 : mobilisasi man power dan prepare start pondasi RBS, delivery material 09.04.20 : 02.04.20 : UNDER REVIEW TNP ALITA 25.03.20 : under RNP review
368 |  | SUM-BB-TDN-0518 | 30590020031 | 080352109 | PETALING SELAT NASIK | ACTIVE | TB | 107.4579 | -2.8896 | 50 | 30/240/320 | 2020 | JEDI 2020 [NEW] | Jl. Selat Nasik RT.03 RW.02, Desa Petaling, Kec. Selat Nasik, Kab. Belitung, Prov. Bangka Belitung | HTI | SUM-BB-TDN-0518 | PETALING_SELAT NASIK | COLO | TBG | WEST | SUMBAGSEL | Kep. Bangka Belitung | KAB. BELITUNG | 6614551 | 2020-03-13 |  | 156 | > 150 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2020-08-25 | W35-2020 | Aug-2020 | MW | 2020-06-12 |  | 163000617932 | 6.6 |  | 2020-04-02 |  |  | 2020-08-16 | W34-2020 |  | 2020-08-31 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.08.20 : RFIN sent 14.08.20 : RFI actual, collecting doc RFIN 13.08.20 : erection done, SRFI, on going F&Y 06.08.20 : erection on going, BPUJL waiting nomor register PLN release 03.08.20 : rebarring 27.07.20 : galian dan barbending on going 23.07.20 : Galian, Delivery material 16.07.20 : 13.07.20 : on going excavation 09.07.20 : start excavation 29.06.20 : prepare start CME, proses perijinan 25.06.20 : 22.06.20 : 18.06.20 : prepare start CME, proses perijinan 17.06.20 : Go RFI, PSB PLN release 15.06.20 : soiltest done, proses APD 11.06.20 : tim soiltest masih belum bisa memasuki/nyebarng ke P.Bangka 08.06.20 : 04.06.20 : preparation 28.05.20 : 25.05.20 : 14.05.20 : soiltest site permanenisasi (area bangka) 30.04.20 : 23.04.20 : 16.04.20 : start CME colo menunggu permanenisasi RFI (preparation), akses ke Babel ketat harus orang yang memiliki KTP Babel 09.04.20 : 02.04.20 : UNDER REVIEW TNP ALITA 25.03.20 : under RNP review
430 |  | SUL-SN-PLP-1336 | 30588670031 | 280486109 | TBG TOBULUNG BARA | ACTIVE | TB | 120.184 | -2.9433 | 30 | 0/170/270 | 2020 | JEDI 2020 [NEW] | Jl. DR. Ratulangi, RT 02, Rw 02, Kel. Tobulung, Kec. Bara, Kota Palopo | HTI | SUL-SN-PLP-1336 | TO'BULUNG | COLO | TBG | EAST | SULAWESI | Sulawesi Selatan | KOTA PALOPO | 6614563 | 2020-03-16 |  | 86 | 61 - 90 days | 2020-04-15 | W16-2020 | Apr-2020 | 2020-04-28 | W18-2020 | Apr-2020 | 2020-06-13 | W24-2020 | Jun-2020 | 2020-06-13 | W24-2020 | Jun-2020 | MW | 20-May-20 18-May-20 |  | 326100987539 | 6.6 |  | 2020-03-23 |  | 2020-05-20 | 2020-06-10 | W24-2020 |  | 2020-07-07 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.06.20 : RFIN sent 20.05.20 : email SRFI-N sent 30.04.20 : 27.04.20 : SRFI actual 23.04.20 : ME OG 16.04.20 : delivery material panel KWH/ACPDB, ME Grounding tray dan mounting msh on delivery dri JKt-Mksr. Pengiriman lebih lambat karena isu covid/pemeriksaan lebih ketat di pelabuhan. 13.04.20 : RBS pondasi done, wait Panel ME 09.04.20 : Actual Start Bowplank and foundation today . waiting delivery Material Panel KWH/ACPDB from Jkt 02.04.20 : delivery material, plan SRFI 15 Apr
393 |  | SUM-SU-STB-2167 | 30588300031 | 021447109 | SELAYANG_BARU_DCS | ACTIVE | TB | 98.3869 | 3.61 | 50 | 0/100/180 | 2020 | JEDI 2020 [NEW] | Dusun II, Desa Bekulap, Kec. Selesai, Kab, Langkat, Provinsi Sumatra Utara | HTI | SUM-SU-STB-2167 | BEKULAP | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. LANGKAT | 6614551 | 2020-03-13 |  | 58 | 31 - 60 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-15 | W16-2020 | Apr-2020 | 2020-05-10 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 129040027696 | 6.6 |  | 2020-03-20 |  | 2020-04-13 | 2020-05-10 | W20-2020 |  | 2020-06-26 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.05.20 : RFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 13.04.20 : email Soft RFI-N sent 09.04.20 : RBS foundation done, wait material ME 02.04.20 : material on site, prepare start CME, plan SRFI 7 Apr 30.04.20 : KOM mitra
383 |  | SUM-SB-SPE-0803 | 30588440031 | 030162104 | RD_TO_NATAL2_ | ACTIVE | SMI | 99.4597 | 0.26845 | 50 | 70/180/340 | 2020 | JEDI 2020 [NEW] | Jorong Air Balam Nagari Parit, Kec. Koto Balingka, Kab. Pasaman Barat, Sumatera Barat | HTI | SUM-SB-SPE-0803 | AIA BANGIH | COLO | TBG | WEST | SUMBAGTENG | Sumatera Barat | KAB. PASAMAN BARAT | 6614549 | 2020-03-13 |  | 79 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-13 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 132252266907 | 6.6 |  | 2020-03-20 |  | 2020-04-27 | 2020-05-31 | W23-2020 |  | 2020-07-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31.05.20 : RFIN sent 28.05.20 : RFI , collect doc RFIN 25.05.20 : 14.05.20 : 13.05.20 : besok konek, hr ini kwh dikirimkan dr area 08.05.20 : BP paid, revisi RFI plan 13 may 20 27.04.20 : email SRFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 16.04.20 : ME on going, plan besok Soft RFI 09.04.20 : on going pondasi 02.04.20 : delivery material, plan on site 5 Apr, plan SRFI 11 Apr
361 |  | SUM-SB-SPE-0797 | 30588240031 | 030734109 | PEMUKIMAN SUMBER AGUNG KINALI | ACTIVE | TB | 99.841 | -0.04067 | 50 | 50/140/240 | 2020 | JEDI 2020 [NEW] | Jorong Bancah Kariang Wonosari Nagari Kinali, Kecamatan Kinali, Kabupaten Pasaman Barat, Provinsi Sumatera Barat | HTI | SUM-SB-SPE-0797 | KINALI_BARAT | COLO | TBG | WEST | SUMBAGTENG | Sumatera Barat | KAB. PASAMAN BARAT | 6614551 | 2020-03-13 |  | 79 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-13 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 132252266915 | 6.6 |  | 2020-03-20 |  | 2020-04-21 | 2020-05-31 | W23-2020 |  | 2020-07-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31.05.20 : RFIN sent 28.05.20 : RFI, collect doc RFIN 14.05.20 : 13.05.20 : besok konek, hr ini kwh dikirimkan dr area 08.05.20 : BP paid, revisi RFI plan 13 may 20 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 21.04.20 : email SRFIN sent 16.04.20 : SRFI actual, collecting doc SRFIN 09.04.20 : ME on going 02.04.20 : delivery material, plan on site 5 Apr, plan SRFI 11 Apr
415 |  | SUM-RI-PKK-1133 | 30588280031 | 040872109 | SURYA INDAH | ACTIVE | TB | 102.0491 | 0.18935 | 50 | 70/130/315 | 2020 | JEDI 2020 [NEW] | Jln. Lintas Timur Dundangan. Kelurahan Dundangan, Kec. Pangkalan Kuras, Kota Pekanbaru- Riau | HTI | SUM-RI-PKK-1133 | DUNDANGAN | COLO | TBG | WEST | SUMBAGTENG | Riau | KAB. PELALAWAN | 6614551 | 2020-03-13 |  | 75 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-13 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 181800913611 | 6.6 |  | 2020-03-20 |  | 2020-04-24 | 2020-05-27 | W22-2020 |  | 2020-09-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.05.20 : RFIN sent 25.05.20 : 22.05.20 actual RFI/PLN Connect 14.05.20 : kwh kosong plan beli kwh 08.05.20 : BP paid, revisi RFI plan 13 may 20 24.04.20 : email SRFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 16.04.20 : SRFI actual, collecting doc SRFIN 09.04.20 : ME on going 02.04.20 : delivery material, plan on site 5 Apr, plan SRFI 11 Apr
387 |  | SUM-SB-BSK-0809 | 30588420031 | 030682109 | SABU BUNGO TANJUNG | ACTIVE | TB | 100.4834 | -0.50432 | 50 | 0/140/300 | 2020 | JEDI 2020 [NEW] | JORONG ARU, KENAGARIAN BUNGO TANJUNG, KEC.BATIPUH, KAB.TANAH DATAR - BATUSANGKAR | HTI | SUM-SB-BSK-0809 | BUNGO TANJUNG_BATIPUH | COLO | TBG | WEST | SUMBAGTENG | Sumatera Barat | KAB. TANAH DATAR | 6614551 | 2020-03-13 |  | 64 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-13 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 132221312792 | 6.6 |  | 2020-03-20 |  | 2020-04-16 | 2020-05-16 | W20-2020 |  | 2020-07-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.05.20 : RFIN sent 14.05.20 : 13.05.20 : need Add 1 tiang, hr ini hujan tiang blm dipasang, plan besok pasang tiang 08.05.20 : BP paid, revisi RFI plan 13 may 20 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 16.04.20 : SRFIN sent 09.04.20 : ME on going 02.04.20 : delivery material, plan on site 5 Apr, plan SRFI 11 Apr
420 |  | SUM-SB-BSK-0808 | 30588230031 | 030372109 | TANJUNG BONAI | ACTIVE | TB | 100.7274 | -0.38809 | 50 | 170/250/350 | 2020 | JEDI 2020 [NEW] | Jorong Sembayan, Nagari Tanjung Bonai, kec. Lintau Buo Utara, Kab. Tanah Datar - Sumatera Barat | HTI | SUM-SB-BSK-0808 | TANJUANG BONAI | COLO | TBG | WEST | SUMBAGTENG | Sumatera Barat | KAB. TANAH DATAR | 6614551 | 2020-03-13 |  | 64 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-13 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 134540058369 | 6.6 |  | 2020-03-20 |  | 2020-04-16 | 2020-05-16 | W20-2020 |  | 2020-07-02 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.05.20 : RFIN sent 14.05.20 : 13.05.20 : plan besok konek 08.05.20 : BP paid, revisi RFI plan 13 may 20 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 16.04.20 : SRFIN sent 09.04.20 : ME on going 02.04.20 : delivery material, plan on site 5 Apr, plan SRFI 11 Apr
388 |  | SUM-KR-TBK-0584 | 30588270031 | 050519109 | SAIPEM 2 | ACTIVE | TB | 103.3251 | 1.0406 | 50 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl.ambat III RT.01 RW.04, Desa pangke Barat, kec.meral barat, Kab Karimun, Prov. Kepulauan Riau | HTI | SUM-KR-TBK-0584 | PANGKE | COLO | TBG | WEST | SUMBAGTENG | Kep. Riau | KAB. KARIMUN | 6614551 | 2020-03-13 |  | 62 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-13 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 183051475462 | 6.6 |  | 2020-03-20 |  | 2020-04-29 | 2020-05-14 | W20-2020 |  | 2020-07-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.05.20 : RFIN sent 13.05.20 : RFI actual, collect doc RFIN, plan RFIN 14 may 08.05.20 : BP paid, revisi RFI plan 13 may 20 29.04.20 : email SRFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 16.04.20 : SRFI actual, 09.04.20 : ME on going 02.04.20 : delivery material, plan on site 5 Apr, plan SRFI 11 Apr
246 |  | SUM-SB-ARS-0832 | 30588290031 | 030089109 | BATU TUPANG-3 (SC_SL5184C) | ACTIVE | TB | 100.6202 | -0.84888 | 50 | 60/180/330 | 2020 | JEDI 2020 [NEW] | Jorong Kampung Baru, Nagari Gantuang Ciri, Kec. Kubung, Kab. Solok, Sumatra Barat | HTI | SUM-SB-ARS-0832 | SALAYO_BAWAH | COLO | TBG | WEST | SUMBAGTENG | Sumatera Barat | KAB. SOLOK | 6614551 | 2020-03-13 |  | 62 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-13 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 133312667099 | 6.6 |  | 2020-03-20 |  | 2020-04-20 | 2020-05-14 | W20-2020 |  | 2020-07-01 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.05.20 : RFIN sent 13.05.20 : RFI actual, collect doc RFIN, plan RFIN 14 may 08.05.20 : BP paid, revisi RFI plan 13 may 20 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 20.04.20 : email SRFIN sent 16.04.20 : SRFI actual, collecting doc SRFIN 09.04.20 : ME on going 02.04.20 : delivery material, plan on site 5 Apr, plan SRFI 11 Apr
391 |  | SUM-RI-BKN-1147 | 30588650031 | TBG03_RAU321 | SEI BELIMBING | ACTIVE | TB | 101.0051 | 0.2348 | 50 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl. Salo Sungai Abang, RT.01/05, Desa Siabu, Kec. Salo, Kabupaten Kampar | HTI | SUM-RI-BKN-1147 | SIABU_SALO | COLO | TBG | WEST | SUMBAGTENG | Riau | KAB. KAMPAR | 6614551 | 2020-03-13 |  | 61 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-22 | W17-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-13 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 181901115903 | 6.6 |  | 2020-03-20 |  | 2020-04-23 | 2020-05-13 | W20-2020 |  | 2020-07-01 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.05.20 : RFIN SENT 13 may 08.05.20 : BP paid, revisi RFI plan 13 may 20 23.04.20 : email SRFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 16.04.20 : RBS foundation on going 09.04.20 : 02.04.20 : delivery material, plan on site 5 Apr, plan SRFI 11 Apr
440 |  | SUM-KR-TBK-0579 | 30588360031 | 080154104 | UNGAR | ACTIVE | SMI | 103.4983 | 0.73715 | 50 | 0/180/270 | 2020 | JEDI 2020 [NEW] | KAB.KARIMUN, KEP.RIAU | HTI | SUM-KR-TBK-0579 | TANJUNG BERLIAN KOTA | COLO | TBG | WEST | SUMBAGTENG | Kep. Riau | KAB. KARIMUN | 6614549 | 2020-03-13 |  | 61 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-13 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 183063155708 | 6.6 |  | 2020-03-20 |  | 2020-04-16 | 2020-05-13 | W20-2020 |  | 2020-07-05 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.05.20 : RFIN SENT 13 may 08.05.20 : BP paid, revisi RFI plan 13 may 20 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 16.04.20 : email SRFIN sent 09.04.20 : ME on going 02.04.20 : delivery material, plan on site 5 Apr, plan SRFI 11 Apr
390 |  | SUM-SU-SRH-2087 | 30588660031 | 021427109 | SC-LP2231F | ACTIVE | TB | 98.9745 | 3.5527 | 40 | 0/90/270 | 2020 | JEDI 2020 [NEW] | Dusun Kedondong, Desa Melati II, Kecamatan Perbaungan, Kabupaten Serdang Bedagai | HTI | SUM-SU-SRH-2087 | MELATI KEBUN | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. SERDANG BEDAGAI | 6614551 | 2020-03-13 |  | 58 | 31 - 60 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-10 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 126140712559 | 6.6 |  | 2020-03-20 |  | 2020-04-20 | 2020-05-10 | W20-2020 |  | 2020-07-01 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.05.20 : RFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 20.04.20 : email SRFI-N sent 16.04.20 : Soft RFI 13.04.20 : plan SRFI 17 Apr 09.04.20 : RBS foundation done, wait material ME 02.04.20 : material on site, prepare start CME, plan SRFI 7 Apr 30.04.20 : KOM mitra
403 |  | SUM-SU-SDK-2217 | 30588430031 | 021323109 | SITINJO | ACTIVE | TB | 98.3527 | 2.7245 | 30 | 90/210/330 | 2020 | JEDI 2020 [NEW] | JL. PANJI BAKO, DESA SITINJO II, KEC SITINJO, DAIRI | HTI | SUM-SU-SDK-2217 | SITINJO II | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. DAIRI | 6614551 | 2020-03-13 |  | 58 | 31 - 60 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-10 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 129010059010 | 6.6 |  | 2020-03-20 |  | 2020-04-13 | 2020-05-10 | W20-2020 |  | 2020-07-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.05.20 : RFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 13.04.20 : email Soft RFI-N sent 09.04.20 : RBS foundation done, wait material ME 02.04.20 : material on site, prepare start CME, plan SRFI 7 Apr 30.04.20 : KOM mitra
360 |  | SUM-SU-PMS-2107 | 30588330031 | 020156104 | PEMATANG BANDAR | ACTIVE | SKP | 99.1415 | 3.0722 | 50 | 0/90/210 | 2020 | JEDI 2020 [NEW] | Jln. Penghubung Afdeling, VII, Dusun Sukarame, Desa Nagori Bahtobu, Kec. Dolok Batu Namggar Kab Simalungun, Sumatra Utara | HTI | SUM-SU-PMS-2107 | BAH TOBU | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. SIMALUNGUN | 6614550 | 2020-03-13 |  | 58 | 31 - 60 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-15 | W16-2020 | Apr-2020 | 2020-05-10 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 121120841956 | 6.6 |  | 2020-03-20 |  | 2020-04-16 | 2020-05-10 | W20-2020 |  | 2020-07-10 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.05.20 : RFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 16.04.20 : email SRFI-N sent 13.04.20 : Soft RFI 09.04.20 : RBS foundation done, wait material ME 02.04.20 : material on site, prepare start CME, plan SRFI 7 Apr 30.04.20 : KOM mitra
332 |  | SUM-SU-DLS-2206 | 30588370031 | 020217104 | LINTONG_HUTA | ACTIVE | SMI | 98.8654 | 2.2619 | 40 | 120/240/340 | 2020 | JEDI 2020 [NEW] | JL SIBORONG BORONG DOLOK SANGGUL, KEL PARGAULAN, KEC LINTONGNIHUTA, KAB HUMBANG HASUNDUTAN, SUMATERA UTARA | HTI | SUM-SU-DLS-2206 | PARGAULAN | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. HUMBANG HASUNDU | 6614549 | 2020-03-13 |  | 58 | 31 - 60 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-15 | W16-2020 | Apr-2020 | 2020-05-10 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 123120528828 | 6.6 |  | 2020-03-20 |  | 2020-04-13 | 2020-05-10 | W20-2020 |  | 2020-07-09 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.05.20 : RFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 13.04.20 : email Soft RFI-N sent 09.04.20 : RBS foundation done, wait material ME 02.04.20 : material on site, prepare start CME, plan SRFI 7 Apr 30.04.20 : KOM mitra
400 |  | SUM-SU-PYB-2153 | 30588390031 | 020297104 | SINUNUKAN_MDN | ACTIVE | SMI | 99.2311 | 0.57558 | 50 | 100/200/280 | 2020 | JEDI 2020 [NEW] | JL LINTAS PANTAI BARAT, KEL TAPUS, KEC LINGGA BAYU, KAB MANDAILING NATAL, SUMATERA UTARA | HTI | SUM-SU-PYB-2153 | TAPUS_LINGGA BAYU | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. MANDAILING NATA | 6614549 | 2020-03-13 |  | 58 | 31 - 60 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-22 | W17-2020 | Apr-2020 | 2020-04-15 | W16-2020 | Apr-2020 | 2020-05-10 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 124150418914 | 6.6 |  | 2020-03-20 |  | 2020-04-20 | 2020-05-10 | W20-2020 |  | 2020-07-10 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.05.20 : RFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 20.04.20 : email SRFI-N sent 16.04.20 : comcase 13.04.20 : plan tim arkom on site Kamis untuk pendekatan, plan SRFI 22 Apr 09.04.20 : CME stop, block akses by LL, proses penyelesaian 02.04.20 : material on site, prepare start CME, plan SRFI 7 Apr 30.04.20 : KOM mitra
334 |  | SUM-SU-KBJ-2219 | 30588380031 | 020222104 | MARDINDING | ACTIVE | SMI | 98.0068 | 3.2278 | 50 | 90/150/340 | 2020 | JEDI 2020 [NEW] | JL.Batu Rongkam, Kel.Mardinding, Kec.Mardingding, Kab.Karo, Prop Sumatera Utara | HTI | SUM-SU-KBJ-2219 | MARDINDING_MARDINGDING | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. KARO | 6614549 | 2020-03-13 |  | 84 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-22 | W17-2020 | Apr-2020 | 2020-05-14 | W20-2020 | May-2020 | 2020-05-31 | W23-2020 | May-2020 | MW | 2020-04-22 |  | 129020026511 | 6.6 |  | 2020-03-20 |  |  | 2020-06-05 | W23-2020 |  | 2020-07-31 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.06.20 : RFIN sent 04.06.20 : SRFI, plan connect PLN/RFI jari jumat besok 5 jun 20 01.06.20 : ME on going, plan RFI 5 jun 20 28.05.20 : 26.05.20 : open akses, preparation for start CME 25.05.20 : 14.05.20 : proses somasi/penyelesaian isu LL, revisi plan RFI sabtu 31 may 08.05.20 : 04.05.20 plan solve 11 may, plan RFI 14 may 30.04.20 : 23.04.20 : 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 20.04.20 : sudah dikirimkan somasi, updatenya rabu 22 April, risk SRFI end Apr 16.04.20 : stop by LL, permintaan kompensasi colo 20 jt, proses negosiasi 13.04.20 : plan nego besok siang, optimis bulan April 09.04.20 : CME stop, block akses by LL (permintaan kompensasi 70jt), proses penyelesaian 02.04.20 : material on site, prepare start CME, plan SRFI 7 Apr 30.04.20 : KOM mitra
374 |  | SUM-BB-TDN-0521 | 30588350031 | 080128104 | PULAU SELIU | ACTIVE | SMI | 107.5422 | -3.2026 | 50 | 90/180/270 | 2020 | JEDI 2020 [NEW] | Dsn. Tua RT 05, Ds. Pulau Seliu, Kec. Membalong, Kab. Belitung Barat | HTI | SUM-BB-TDN-0521 | PULAU SELIU | COLO | TBG | WEST | SUMBAGSEL | Kep. Bangka Belitung | KAB. BELITUNG | 6614549 | 2020-03-13 |  | 66 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-06-10 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 163000611762 | 6.6 |  | 2020-03-20 |  | 2020-04-13 | 2020-05-18 | W21-2020 |  | 2020-08-27 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18.05.20 : RFIN sent 08.05.20 : revisi RFI plan 15 may 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 13.04.20 : SRFIN sent 09.04.20 : pondasi done, wait material ME tray on site 02.04.20 : delivery material, hari ini masuk kapal laut, plan onsite Selasa 7 Apr 20, plan SRFI kamis 9 Apr 20
234 |  | SUM-SU-STB-2169 | 30588310031 | 022234109 | API_PURWOSARI SECANGGANG | ACTIVE | TB | 98.5133 | 3.8941 | 50 | 0/210/290 | 2020 | JEDI 2020 [NEW] | JL PURWOSARI-PASAR BARU, DUSUN IX PURWOSARI, DESA TANJUNG IBUS, KECAMATAN SECANGGANG | HTI | SUM-SU-STB-2169 | TANJUNG IBUS | COLO | TBG | WEST | SUMBAGUT | Sumatera Utara | KAB. LANGKAT | 6614551 | 2020-03-13 |  | 58 | 31 - 60 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-04-15 | W16-2020 | Apr-2020 | 2020-05-10 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 122140840740 | 6.6 |  | 2020-03-20 |  | 2020-04-13 | 2020-05-10 | W20-2020 |  | 2020-07-07 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.05.20 : RFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 13.04.20 : email Soft RFI-N sent 09.04.20 : RBS foundation done, wait material ME 02.04.20 : material on site, prepare start CME, plan SRFI 7 Apr 30.04.20 : KOM mitra
328 |  | JAW-JI-KRS-4249 | 30588340031 | 160908104 | KRUCIL | ACTIVE | SMI | 113.4879 | -7.9557 | 50 | 0/150/210 | 2020 | JEDI 2020 [NEW] | DSN. TIMUR RT19/3 DES. KRUCIL, KEC. KRUCIL, KAB. PROBOLINGGO | HTI | JAW-JI-KRS-4249 | KRUCIL_BERMI | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. PROBOLINGGO | 6614549 | 2020-03-13 |  | 61 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-03 | W14-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-12 | W20-2020 | May-2020 | MW | 2020-04-22 |  | 513572002717 | 6.6 |  | 2020-03-19 |  | 2020-04-09 | 2020-05-13 | W20-2020 |  | 2020-07-10 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.05.20 : RFIN SENT 13 may 12.05.20 : plan besok connect PLN 08.05.20 : revisi RFI plan 12 may 20 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 09.04.20 : SOFT RFIN sent 02.04.20 : ME on going, plan SRFI 3 apr
346 |  | JAW-JI-KPN-4364 | 30588320031 | 161418109 | NGADAS PONCO KUSUMA | ACTIVE | SKP | 112.8452 | -8.0162 | 50 | 70/220/290 | 2020 | JEDI 2020 [NEW] | Desa Gubugklakah, RT 07 RW 07, Kec. Poncokusumo, Kab Malang, Jawa Timur | HTI | JAW-JI-KPN-4364 | PONCOKUSUMO_GUBUGKLAKAH | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. MALANG | 6614550 | 2020-03-13 |  | 54 | 31 - 60 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-03 | W14-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-05-06 | W19-2020 | May-2020 | MW | 2020-04-22 |  | 513060881555 | 6.6 |  | 2020-03-19 |  | 2020-04-07 | 2020-05-06 | W19-2020 |  | 2020-07-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.05.20 : RFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 07.04.20 : SOFT RFIN sent 02.04.20 : aktual SOFT RFI, collecting doc SRFIN, plan announce SRFI besok
429 |  | SUL-SN-PIN-1310 | 30588260031 | 280141109 | TBG TALABANGI | ACTIVE | TB | 119.668 | -3.7323 | 50 | 0/180/270 | 2020 | JEDI 2020 [NEW] | Dsn.Talabangi, Kel.Tanyomang, Kec. Patampanua, Kab. Pinrang, Prop. Sulawesi selatan | HTI | SUL-SN-PIN-1310 | TONYAMANG | COLO | TBG | EAST | SULAWESI | Sulawesi Selatan | KAB. PINRANG | 6614551 | 2020-03-13 |  | 54 | 31 - 60 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-28 | W18-2020 | Apr-2020 | 2020-04-15 | W16-2020 | Apr-2020 | 2020-05-06 | W19-2020 | May-2020 | MW | 2020-04-22 |  | 324300203497 | 6.6 |  | 2020-03-19 |  |  | 2020-05-06 | W19-2020 |  | 2020-07-04 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.05.20 : RFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 16.04.20 : delivery material panel KWH/ACPDB, ME Grounding tray dan mounting msh on delivery dri JKt-Mksr. Pengiriman lebih lambat karena isu covid/pemeriksaan lebih ketat di pelabuhan. 13.04.20 : RBS pondasi done, wait Panel ME 09.04.20 : BTS Foundation OG, Material tray, Mounting, Grounding Just OS from PALU. waiting delivery Material Panel KWH/ACPDB from Jkt 02.04.20 : delivery material, plan SRFI 15 Apr
384 |  | NUS-NB-TJN-5263 | 30588250031 | 180422109 | REMPEK GANGGA | ACTIVE | TB | 116.2499 | -8.3351 | 50 | 70/210/340 | 2020 | JEDI 2020 [NEW] | Dusun Pancor Getah, Desa Rempek, Kec.Gangga, Kab.Lombok Utara, Prov.Nusa Tenggara Barat | HTI | NUS-NB-TJN-5263 | GANGGA_REMPEK | COLO | TBG | EAST | BALINUSRA | Nusa Tenggara Barat | KAB. LOMBOK UTARA | 6614551 | 2020-03-13 |  | 54 | 31 - 60 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-04-25 | W17-2020 | Apr-2020 | 2020-04-20 | W17-2020 | Apr-2020 | 2020-05-06 | W19-2020 | May-2020 | MW | 2020-04-22 |  | 441300967955 | 6.6 |  | 2020-03-19 |  | 2020-05-05 | 2020-05-06 | W19-2020 |  | 2020-07-04 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.05.20 : RFIN sent 05.05.20 : email SRFI-N sent, actual RFI 23.04.20 : SRFI actual 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 20.04.20 : ME on going 16.04.20 : start CME RBS foundation, delivery material, plan SRFI 25 April 09.04.20 : prepare team dan material, kendala isu covid 19 dan pembatasan akses
394 |  | KAL-KS-BLN-0907 | 30588400031 | 220161104 | SEPUNGGUR (RD TO PAGATAN) | ACTIVE | SMI | 115.9646 | -3.5228 | 50 | 40/200/280 | 2020 | JEDI 2020 [NEW] | RT 03 DS.SEPUNGGUR, KEC.KUSAN HILIR, KAB.TANAH BUMBU, KALIMANTAN SELATAN | HTI | KAL-KS-BLN-0907 | SEPUNGGUR_KUSAN HILIR | COLO | TBG | CENTRAL | KALIMANTAN | Kalimantan Selatan | KAB. TANAH BUMBU | 6614488 | 2020-03-13 |  | 360 | > 150 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-06-04 | W23-2020 | Jun-2020 | 2021-03-12 | W11-2021 | Mar-2021 | 2021-03-06 | W10-2021 | Mar-2021 | FO | 2021-02-15 |  | 223200540665 | 6.6 |  | 2020-03-19 |  | 2020-06-04 | 2021-03-08 | W11-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.03.21 : RFI, NY RFIN -> plan 8/03 04.03.21 : plan connect 6 Mar 01.03.21 : plan PLN connection W1 Mar 25.02.21 : plan survey PLN hari ini 16.07.20 : 09.07.20 : 02.07.20 : PLN connection menunggu konfirmasi XL, plan RFI adalah SK PLN release+14 hari 04.06.20 : email SRFI-N sent 28.05.20 : 22.04.20 : Soft RFI actual 20.04.20 : paln material hari ini on site, plan SRFI 2 hari lagi 22 Apr 20 16.04.20 : Pondasi done, plan material on site 18 Apr, plan SRFI 20 Apr 09.04.20 : BTS pondasi done, material paln onsite 14 Apr 02.04.20 : pabrikasi material, plan SRFI 20 Apr
607 |  | JAW-JI-MAD-3631 | 30596370031 | TBG03_EJ119 | MADIUN1 | ACTIVE - CME by XL | TB | 111.5275 | -7.6447 | 35 | 90/210/330 | 2019 | ORION [NEW] | Jl. Salak Kelurahan Taman Kecamatan Taman Kodya Madiun | HTI | JAW-JI-MAD-3631 | TAMAN PANDEAN | COLO | HTI | EAST | JATIM | Jawa Timur | KOTA MADIUN | 6614535 | 2020-03-09 |  | 252 | > 150 days | 2020-04-08 | W15-2020 | Apr-2020 | CME BY XL |  |  | 2020-04-08 | W15-2020 | Apr-2020 | 2020-04-08 | W15-2020 | Apr-2020 | MW | [5 empty] | 2020-03-10 |  |  | 2020-11-16 | W47-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.11.20 : SRFI 18.09.20 : CME BY XL, PO CME released, lacking PO PLN, plan RFI 10 oct 20
606 |  | JAW-JI-JBG-4141 | 30601940031 | 160227104 | JAPANAN | ACTIVE - CME by XL | SKP | 112.3231 | -7.6355 | 40 | 90/210/330 | 2019 | ORION [NEW] | Jl. Sumberboto, Desa Mojoduwur Dsn.Mojoduwur RT.01 RW.01 Kec.Mojowarno, Kab.Jombang Prov.Jawa Timur | HTI | JAW-JI-JBG-4141 | SUMBER BOTO | COLO | HTI | EAST | JATIM | Jawa Timur | Kab. Jombang | 6614496 | 2020-02-18 |  | 272 | > 150 days | 2020-03-19 | W12-2020 | Mar-2020 | CME BY XL |  |  | 2020-03-19 | W12-2020 | Mar-2020 | 2020-03-19 | W12-2020 | Mar-2020 | MW | [5 empty] | 2020-02-19 |  |  | 2020-11-16 | W47-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.01.21 : RFIN sent 05.11.20 : SRFI 18.09.20 : CME BY XL, PO CME released, lacking PO PLN, plan RFI 10 oct 20
225 |  | SUM-AC-BNA-0683 | 30581960031 | 010608109 | TINGKEM_2 | ACTIVE | TB | 95.3215 | 5.5098 | 30 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jalan Tgk Nek Tingkeum, Desa Tingkeum, Kecamatan Darul Imarah, Kabupaten Aceh Besar, Propinsi Aceh | HTI | SUM-AC-BNA-0683 | SUKARAMAI_BAITURRAHMAN | COLO | TBG | WEST | SUMBAGUT | Kep. Bangka Belitung | KOTA BANDA ACEH | 6614479 | 2020-02-13 |  | 17 | < 30 days | 2020-03-14 | W11-2020 | Mar-2020 | RFI |  |  | 2020-03-12 | W11-2020 | Mar-2020 | 2020-03-12 | W11-2020 | Mar-2020 | FO (Change to MW as temp solution) | 2020-02-23 |  | 111120218485 | 6.6 |  | 2020-02-18 |  |  | 2020-03-01 | W10-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.03.20: RFIN sent 20.02.20 : preparation 13.02.20 : SPK released
229 |  | SUM-LA-GDT-1045 | 30581970031 | 100092109 | AIR MINUM GRAND SUMBER AGUNG | ACTIVE | TB | 105.2006 | -5.4294 | 50 | 90/240/310 | 2020 | JEDI 2020 [NEW] | Jln Paredoan I, Kel Batu Putu, Kec Teluk Betung, Bandar Lampung | HTI | SUM-LA-GDT-1045 | TALANG MULYA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. PESAWARAN | 6614479 | 2020-02-13 |  | 43 | 31 - 60 days | 2020-03-14 | W11-2020 | Mar-2020 | RFI |  |  | 2020-03-16 | W12-2020 | Mar-2020 | 2020-03-27 | W13-2020 | Mar-2020 | MW | 2020-02-28 |  | 171802684683 | 6.6 |  | 2020-02-18 |  |  | 2020-03-27 | W13-2020 |  | 2020-06-30 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.03.20 : RFIN sent 25.03.20 : actual RFI 19.03.20 : 11.03.20 : Soft RFI, wait PLN connection 13.02.20 : SPK released
226 |  | JAW-JB-SOR-3679 | 30581990031 | 122241109 | 3-CIBALAKAN | ACTIVE | SKP | 107.5613 | -6.9725 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl. Raya Manglid No.2, RT.06 RW.11, Kec. Margahayu Selatan, Kab. Bandung, Prop. Jawa Barat 40266 | HTI | JAW-JB-SOR-3679 | MARGAHAYU SELATAN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614472 | 2020-02-13 |  | 174 | > 150 days | 2020-03-14 | W11-2020 | Mar-2020 | 2020-04-30 | W18-2020 | Apr-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-08 | W32-2020 | Aug-2020 | MW | 12-Jun-20 23-Feb-20 |  | 535756181649 | 6.6 |  | 2020-02-18 |  | 2020-06-28 | 2020-08-05 | W32-2020 |  | 2020-08-30 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.08.20 : RFIN sent 5 Aug 20 30.07.20 : on going pemasangan tiang PLN 28.07.20 : isu P2TL close, continue PLN connection 27.07.20 : 23.07.20 : 16.07.20 : Proses penyelesaian isu P2TL oleh XL 13.07.20 : PLN connection di tangguhkan dan terkendala isu ada P2TL site XL di rayon tersebut (eskalasi isu ke XL) 09.07.20 : 06.07.20 : 02.07.20 : 29.06.20 : Proses PLN Connection 28.06.20 : email SRFI-N sent 22.06.20 : 18.06.20 : SRFI actual, collecting doc SRFIN, proses PLN connection 17.06.20 : Go RFI, PSB PLN release 11.06.20 : open akses, prepare team & material 08.06.20 : proses penyelesaian case by tim arcom 04.06.20 : 01.06.20 : proses negosiasi dengan LL akan dilanjutkan besok 28.05.20 : 25.05.20 : 14.05.20 : proses negosiasi dengan keluarga LL 08.05.20 : proses penyelesaian isu 30.04.20 : 23.04.20 : 16.04.20 : 09.04.20 : on going proses negosiasi 02.04.20 : 25.03.20 : plan isu solve W1 Apr, plan RFI W3 Apr 19.03.20 : on going proses negosiasi 11.03.20 : Block access by LL 20.02.20 : preparation & mob demob 13.02.20 : SPK released
277 |  | JAW-JI-SDA-4077 | 30573490031 | 1643491003 | BUDURAN_SIDOMULYO | ACTIVE | TB | 112°44'6.00E | 7°25'33.56S | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | DUSUN SIDOMULYO RT 01 RW 01, DESA SIDOMULYO, KEC. BUDURAN, KAB. SIDOARJO, JAWA TIMUR | HTI | JAW-JI-SDA-4077 | BUDURAN_SIDOMULYO | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614451 | 2020-01-31 |  | 41 | 31 - 60 days | 2020-03-01 | W10-2020 | Mar-2020 | 2020-03-05 | W10-2020 | Mar-2020 | 2020-03-05 | W10-2020 | Mar-2020 | 2020-03-05 | W10-2020 | Mar-2020 | MW | 2020-02-13 |  | 511802209890 | 6.6 |  | 2020-02-14 |  |  | 2020-03-12 | W11-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.03.20 : RFIN sent 20.02.20 : RFI actual, collecting RFIN doc 20.02.20 : tower permanent sedang on going cor pondasi tower 13.02.20 : CME colo menunggu tower permanent RFI, progress sedang preparation galian pondasi, plan RFI 27 Mar. 10.02.20 : RND TNP OK, Go CME 06.02.20 : ERM, under review Power
338 |  | JAW-JI-SDA-4069 | 30571420031 | 164233123 | WARUSDA_PEPELEGI | ACTIVE | TB | 112°43'12.5E | 7°21'54.94S | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl. Kenongosari, RT.003 RW.002, Desa Pepelegi, Kecamatan Waru, Kabupaten Sidoarjo | HTI | JAW-JI-SDA-4069 | WARUSDA_PEPELEGI | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. SIDOARJO | 6614450 | 2020-01-31 |  | 180 | > 150 days | 2020-03-01 | W10-2020 | Mar-2020 | 2020-03-27 | W13-2020 | Mar-2020 | 2020-07-03 | W27-2020 | Jul-2020 | 2020-07-28 | W31-2020 | Jul-2020 | MW | 15-Jun-20 18-May-20 |  | 511464302426 | 6.6 |  | 2020-02-14 |  | 2020-03-28 | 2020-07-29 | W31-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29.07.20 : RFIN sent 23.07.20 : PLN connect/RFI actual, proses penyusunan RFIN 13.07.20 : 09.07.20 : Proses PLN Connection (antri jadwal pemasangan KWH), plan RFI 15 jul 29.06.20 : Proses PLN Connection 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 28.05.20 : 28.03.20 : email SRFIN sent 24.03.20 : Soft RFI, proses collecting SRFIN doc 19.03.20 : erection done, foundation dan ME colo on going 11.03.20 : erection tower, plan SRFI 20 Mar 20, TARGET SRFI 20.02.20 : menunggu permanenisasi tower, OG galian pondasi tower 13.02.20 : Preparation 10.02.20 : RND TNP OK, Go CME 06.02.20 : ERM, under review Power
258 |  | JAW-JB-CMS-3758 | 30578920031 | 125594109 | BO-WARINGINSARI-LANGENSARI | ACTIVE | TB | 108.664 | -7.3589 | 40 | 120/220/320 | 2020 | JEDI 2020 [NEW] | Dusun citamiang Rt 008 Rw 002, desa cintaratu, kec Lakbok, kab ciamis. | HTI | JAW-JB-CMS-3758 | CINTARATU_LAKBOK | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. CIAMIS | 6614396 | 2020-01-15 |  | 349 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-03-12 | W11-2020 | Mar-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | FO | 2020-12-10 |  | 532217733324 | 6.6 |  | 2020-01-29 |  | 2020-03-12 | 2020-12-29 | W53-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.12.20 : PLN connected, prepare RFIN 21.12.20 : 17.12.20 : proses konek PLN 10.12.20 : backbone already RFS, need PSB 27.07.20 : 23.07.20 : 20.07.20 : 16.07.20 : 09.07.20 : 06.07.20 : 02.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : 18.06.20 : 28.05.20 : 14.05.20 : 12.03.20 : Email SRFIN sent, wait plan MOS & konfirmasi permintaan PLN connection dari XL/tech part 11.03.20 : SRFI, collecting doc SRFI-N 20.02.20 : 19.02.20 : Pondasi done, material ME onsite 21/0, paralel finishing site permanent 17.02.20 : : Pondasi BTS OG, 06.02.20 : Progress tower permanen hari ini pouring concrete pondasi (target RFI end feb 2020) 30.01.19 : Progress tower permanent rebaring pondasi tower (target RFI end feb 2020) 17.01.20 : RND NOK -> ANTENNA TOO LOW, karena aktual GUYED MAST 42 M dan space available hanya 30m, propose XL di 50m
399 |  | JAW-JB-CMS-3757 | 30578910031 | 125487126 | SINDANGANGIN CIAMIS | ACTIVE | TB | 108.7158 | -7.4348 | 50 | 90/210/330 | 2020 | JEDI 2020 [NEW] | DUSUN SARIMURTI RT. 016 RW. 004 DESA SINDANGANGIN KECAMATAN LAKBOK KAB. CIAMIS JAWA BARAT | HTI | JAW-JB-CMS-3757 | SINDANGANGIN_LAKBOK | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. CIAMIS | 6614396 | 2020-01-15 |  | 349 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-03-12 | W11-2020 | Mar-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | FO | 2020-12-10 |  | 532217733294 | 6.6 |  | 2020-01-29 |  | 2020-03-12 | 2020-12-29 | W53-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.12.20 : PLN connected, prepare RFIN 21.12.20 : 17.12.20 : PLN connection process 10.12.20 : RFS 03.08.20 : 27.07.20 : 23.07.20 : 20.07.20 : 16.07.20 : 09.07.20 : 06.07.20 : 02.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : 28.05.20 : 14.05.20 : 12.03.20 : Email SRFIN sent, wait plan MOS & konfirmasi permintaan PLN connection dari XL/tech part 11.03.20 : SRFI, collecting doc SRFI-N 20.02.20 : Pondasi done, tray+mounting OG, material ME onsite 21/02; tower permanent sudah RFI 17.02.20 : Pondasi BTS OG, 06.02.20 : progress permanenisasi erection done 30.01.19 : Progress tower permanent plan RFI 31 jan 20 17.01.20 : RND NOK -> ANTENNA TOO LOW, karena aktual GUYED MAST 42 M dan space available hanya 30m, propose XL di 50m
445 |  | SUM-LA-GNS-1089 | 30574170031 | 101001126 | YUKUM JAYA_TERBANGGI BESAR | ACTIVE | TB | 105.1778 | -4.9415 | 50 | 30/100/250 | 2020 | JEDI 2020 [NEW] | Dusun YPP RT.016 RW.005, Desa Bumi Kencana, Kec. Seputih Agung, Kab. Lampung Tengah, Prov. Lampung | HTI | SUM-LA-GNS-1089 | BUMI KENCANA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. LAMPUNG TENGAH | 6614396 | 2020-01-15 |  | 29 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-12 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 172200956900 | 6.6 |  | 2020-01-24 |  |  | 2020-02-13 | W07-2020 |  | 2020-07-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.02.20 : RFIN sent 06.02.20 : 30.01.19 : OG RBS Foundation, delivery material
283 |  | SUM-LA-KOT-1039 | 30574330031 | 100914109 | DESA WAY HARONG | ACTIVE | TB | 104.7612 | -5.2947 | 50 | 10/200/300 | 2020 | JEDI 2020 [NEW] | JL. DESA WAY HARONG RT 01 RW 01, DESA WAY HARONG KEC. AIR NANINGAN, KAB. TANGGAMUS PROVINSI LAMPUNG | HTI | SUM-LA-KOT-1039 | WAY HARONG_AIR NANINGAN | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TANGGAMUS | 6614396 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-12 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 172300745106 | 6.6 |  | 2020-01-24 |  |  | 2020-02-11 | W07-2020 |  | 2020-05-11 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 06.02.20 : Foundation done, delivery material ME 30.01.19 : OG RBS Foundation, delivery material
356 |  | JAW-JI-LMJ-4225 | 30574850031 | 160814104 | PASRUJAMBI | ACTIVE | SMI | 113.0541 | -8.1179 | 72 | 30/180/270 | 2020 | JEDI 2020 [NEW] | DUSUN KRAJAN II RT 2 RW 3, DESA PASRUJAMBE,KEC PASRUJAMBE, KABUPATEN LUMAJANG | HTI | JAW-JI-LMJ-4225 | PASRUJAMBE_PASRUJAMBE | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. LUMAJANG | 6614408 | 2020-01-16 |  | 19 | < 30 days | 2020-02-15 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-12 | W07-2020 | Feb-2020 | FO | 2020-01-27 |  | 516021517066 | 6.6 |  | 2020-01-23 |  |  | 2020-02-04 | W06-2020 |  | 2020-05-04 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22.06.20 : SPK MMP 10 jun 20 (info by WA MMP XL) 21.04.20 : request MMP oleh XL (Pak Bayu by WAG) 04.02.20 : RFI actual, RFIN done 30.01.20 : OG RBS Foundation, delivery material
407 |  | SUM-SS-MPR-1182 | 30575060031 | 071301126 | SRIJAYA | ACTIVE | TB | 104.7796 | -3.9848 | 50 | 40/180/250 | 2020 | JEDI 2020 [NEW] | Desa Tegal Sari RT. 04 Dusun I Kecamatan Belitang II Kab OKU Timur | HTI | SUM-SS-MPR-1182 | SRIJAYA | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | KAB. OGAN KOMERING U | 6614396 | 2020-01-15 |  | 64 | 61 - 90 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-24 | W09-2020 | Feb-2020 | 2020-03-18 | W12-2020 | Mar-2020 | MW | 2020-01-27 |  | 149300064530 | 6.6 |  | 2020-01-23 |  |  | 2020-03-19 | W12-2020 |  | 2020-07-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.03.20 : actual RFI, RFIN sent 11.03.20 : plan connect jumat, plan RFIN 16 mar 20.02.20 : plan RFI 28 Mar 20 13.02.20 : prepare erection tower permanent 06.02.20 : 30.01.19 : Progress tower permanent Galian Done, Material On Site 1 Feb 2020, Target COR: 6 Feb 2020,target Start erection 10 Feb 2020, target RFI 17 Feb 2020 24.01.20 : DRM OK, progress permanent site sudah galian, Colo XL menunggu site permanent RFI 17.01.20 : RND NOK -> ANTENNA TOO LOW, karena aktual GUYED MAST 42 M dan space available hanya 30m, propose XL di 50m
259 |  | SUM-LA-KTB-1103 | 30575050031 | 101032109 | BUMI RESTU LAMPUNG UTARA | ACTIVE | TB | 105.0409 | -4.7357 | 50 | 80/180/350 | 2020 | JEDI 2020 [NEW] | Bumi Restu RT.001 Dusun Karya Maju, Desa Bumi Restu, Kec. Abung Surakarta, Kab. Lampung Utara, Prov. Lampung | HTI | SUM-LA-KTB-1103 | TATA KARYA_ABUNG | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. LAMPUNG UTARA | 6614396 | 2020-01-15 |  | 120 | 91 - 120 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-04-03 | W14-2020 | Apr-2020 | 2020-06-02 | W23-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | MW | 22 Apr 20 27 jan 20 |  | 173001400071 | 6.6 |  | 2020-01-23 |  | 2020-04-05 | 2020-05-14 | W20-2020 |  | 2020-06-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.05.20 : RFIN sent 08.05.20 : revisi RFI plan 15 may 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 05.04.20 : SRFIN sent 02.04.20 : wait konfirmasi ALITA mengenai material readiness, PLN process still wait confirmation 30.03.20 : Konfirmasi request PLN connection dari HTI dnegan MOS plan 17 April, email pak Ahenk 28.03.20 : SOFT RFI, PLN hold sesuai email XL 26 Mar 20 25.03.20 : on going erection 19.03.20 : on going erection tower permanent, plan RFI 30 maret 11.03.20 : target rfi permanent akhir maret, plan rfi colo 28 mar 20.02.20 : OG galian pondasi tower permanent 13.02.20 : 10.02.20 : alokasi tower done, wait GDL release 06.02.20 : 30.01.19 : Progress tower permanent Plan GDL Rel 7 Feb 2020, Target Mat On Site 12 Feb 2020, target COR: 17 Feb 2020, Erection 20 Feb, target RFI: 28 feb 2020 24.01.20 : DRM OK, site GM, Colo XL menunggu site permanent RFI 17.01.20 : RND NOK -> ANTENNA TOO LOW, karena aktual GUYED MAST 42 M dan space available hanya 30m, propose XL di 50m
404 |  | JAW-JB-BDG-3846 | 30575000031 | 122211109 | SMATKRIDA NUSANTARA | ACTIVE | SKP | 107.7254 | -6.9163 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | JL. Sukaluyu RT 06 RW 15 Kel. Cipadung Kec. Cibiru Kota Bandung | HTI | JAW-JB-BDG-3846 | CIPADUNG_CIBIRU | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANDUNG | 6614391 | 2020-01-15 |  | 112 | 91 - 120 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-03-12 | W11-2020 | Mar-2020 | 2020-02-10 | W07-2020 | Feb-2020 | 2020-05-06 | W19-2020 | May-2020 | MW | 22 Apr 20 27 jan 20 |  | 535716394165 | 6.6 |  | 2020-01-22 |  | 2020-03-25 | 2020-05-06 | W19-2020 |  | 2020-06-10 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.05.20 : RFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 25.03.20 : SRFIN done 19.03.20 : collecting doc SRFI-N, plan submit SRFIN 19 mar 11.03.20 : SRFI, collecting doc SRFI-N 20.02.20 : wait kekurangan material ME, plan RFI mundur 28 Mar 20 13.02.20 : ME OG (use existing CME ex XL) 06.02.20 : Pondasi done, Tray done, Mounting done, penggantian material hilang (ex existing CME XL yg pernah cancel) 30.01.19 : OG RBS Foundation, delivery material
250 |  | JAW-JB-SNG-3746 | 30573960031 | 125052109 | BLANAKAN-CLMYGRGTBG | ACTIVE | SKP | 107.6322 | -6.2565 | 40 | 120/180/330 | 2020 | JEDI 2020 [NEW] | Dusun Tegal Tangkil, RT.19 RW.04 Desa Jayamukti, Kecamatan Blanakan. Kabupaten Subang. | HTI | JAW-JB-SNG-3746 | JAYAMUKTI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUBANG | 6614391 | 2020-01-15 |  | 42 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 534112903248 | 6.6 |  | 2020-01-22 |  |  | 2020-02-26 | W09-2020 |  | 2020-07-05 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.02.20 : RFIN sent 20.02.20 : 19.02.20 : plan connect PLN besok 20 feb 18.02.20 : BTS Done, Tray+Mounting OG, ME+Panel plan onsite 19/02 13.02.20 : SRFI 06.02.20 : Pondasi OG, Tray OG, Mounting OG, ME OG , Panel OG 30.01.19 : OG RBS Foundation, delivery material
385 |  | JAW-JB-GRT-3736 | 20201103231 | 125056109 | Rnc_Krpawitan_P1_Site Planning 1_NewSite_432 | ACTIVE | SKP | 107.9867 | -7.0442 | 40 | 0/100/250 | 2020 | JEDI 2020 [NEW] | Kp. Sasakbeusi, RT 001/RW 011 Desa Sindangsuka, Kec. CIbatu. Kab GarutDESA SINDANGSUKA, KEC. CIBATU, | HTI | JAW-JB-GRT-3736 | SINDANGSUKA_CIBATU | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. GARUT | 6614391 | 2020-01-15 |  | 42 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | FO (Change to MW as temp solution) | 2020-01-27 |  | 532861202012 | 6.6 |  | 2020-01-22 |  |  | 2020-02-26 | W09-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.02.20 : RFIN sent 20.02.20 : 19.02.20 : RFI avtual, plan submit RFIN 20 feb 13.02.20 : SRFI 06.02.20 : Pondasi done, Tray OG , mounting OG, Panel plan besok 30.01.19 : OG RBS Foundation, delivery material
257 |  | JAW-JB-SNG-3743 | 30574400031 | 125586109 | BO-TEGALURUNG-LEGONKULON | ACTIVE | TB | 107.7629 | -6.2674 | 50 | 120/200/310 | 2020 | JEDI 2020 [NEW] | Dusun Anggaranu RT 12 / RW 04 Desa Anggasari Kecamatan Sukasari Kab Subang, Prov Jabar | HTI | JAW-JB-SNG-3743 | ANGGASARI_SUKASARI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUBANG | 6614396 | 2020-01-15 |  | 41 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 534112903230 | 6.6 |  | 2020-01-22 |  |  | 2020-02-25 | W09-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.02.20 : RFIN sent 20.02.20 : 19.02.20 : plan connect PLN besok 20 feb, plan RFIN 20 feb 13.02.20 : ME grounding 06.02.20 : Pondasi OG, Tray OG, Mounting OG, ME OG , Panel OG 30.01.19 : OG RBS Foundation, delivery material
386 |  | JAW-JB-NPH-3705 | 30574450031 | 125598109 | RONGGA-DSSIRNAJAYA | ACTIVE | TB | 107.276 | -7.0102 | 40 | 20/130/270 | 2020 | JEDI 2020 [NEW] | Kp Simpang Rt 1 Rw 3 desa Bunijaya kec Gununghalu Kab Bandung Barat. | HTI | JAW-JB-NPH-3705 | BUNIJAYA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614396 | 2020-01-15 |  | 33 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 535921313566 | 6.6 |  | 2020-01-22 |  |  | 2020-02-17 | W08-2020 |  | 2020-08-28 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.02.20 : RFIN sent 13.02.20 : actual RFI 06.02.20 : CME done/Soft RFI, proses PLN connection 30.01.19 : OG RBS Foundation, delivery material
254 |  | JAW-JB-SNG-3917 | 30574440031 | 125693109 | BO-CAPOLAGA | ACTIVE | TB | 107.6422 | -6.7054 | 40 | 80/210/350 | 2020 | JEDI 2020 [NEW] | Kp. Cicadas Rt. 11 Rw. 02 Desa Cicadas Kecamatan Sagalaherang Kab.Subang Prov. Jawa Barat | HTI | JAW-JB-SNG-3917 | CICADAS_SAGALAHERANG | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUBANG | 6614396 | 2020-01-15 |  | 42 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-17 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 534254025063 | 6.6 |  | 2020-01-22 |  |  | 2020-02-26 | W09-2020 |  | 2020-09-10 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.02.20 : RFIN sent 20.02.20 : 19.02.20 : RFI actual, plan RFIN 20 feb 13.02.20 : ME grounding 06.02.20 : Pondasi done, Tray OG, Mounting OG, ME done, Panel OG 30.01.19 : OG RBS Foundation, delivery material
326 |  | JAW-JB-IDM-3813 | 30574030031 | 125167109 | KPLANGUT2-CANTIGI | ACTIVE | SKP | 108.2412 | -6.3515 | 40 | 90/200/320 | 2020 | JEDI 2020 [NEW] | Jl. Desa Pranggong RT.011/RW.002, Desa Pranggong, Kecamatan Arahan, Kabupaten Indramayu, Jawa BaratKecamatan Arahan Kabupaten Indramayu | HTI | JAW-JB-IDM-3813 | CIDEMPET_ARAHAN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. INDRAMAYU | 6614391 | 2020-01-15 |  | 42 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-17 | W08-2020 | Feb-2020 | FO (Change to MW as temp solution) | 2020-01-27 |  | 534030053940 | 6.6 |  | 2020-01-22 |  |  | 2020-02-26 | W09-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.02.20 : RFIN sent 20.02.20 : 19.02.20 : RFI actual, plan RFIN 20 feb 13.02.20 : SRFI 06.02.20 : Pondasi done, Tray OG , mounting OG, Panel plan besok 30.01.19 : OG RBS Foundation, delivery material
235 |  | JAW-JB-CBN-3781 | 30573980031 | 125211109 | ARGASUNYA-DSPAMEKANG | ACTIVE | SKP | 108.5553 | -6.7682 | 30 | 70/210/330 | 2020 | JEDI 2020 [NEW] | Dusun IV Blok Wage RT02 RW06 Desa Pamekang Kec Mundu Kab CirebonKab.Cirebon. | HTI | JAW-JB-CBN-3781 | Pamengkang Harmoni | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KOTA CIREBON | 6614391 | 2020-01-15 |  | 42 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-17 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 533113421847 | 6.6 |  | 2020-01-22 |  |  | 2020-02-26 | W09-2020 |  | 2020-08-31 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.02.20 : RFIN sent 20.02.20 : 19.02.20 : RFI actual, collecting doc RFIN, plan RFIN 19 feb 13.02.20 : SRFI 06.02.20 : Pondasi done, Tray OG , mounting OG, Panel plan besok 30.01.19 : OG RBS Foundation, delivery material
268 |  | JAW-JB-SNG-3918 | 20210300021 | 121334104 | CIMEUHMEI | ACTIVE | SMI | 107.8343 | -6.7653 | 50 | 90/170/350 | 2020 | JEDI 2020 [NEW] | JL. CIKARAMAS / PETIR GG. MAKAM DS. CIKAWUNG Kec. TANJUNGSIANG Kab. SUBANG | HTI | JAW-JB-SNG-3918 | CIKAWUNG_TANJUNGSIANG | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUBANG | 6614394 | 2020-01-15 |  | 36 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-17 | W08-2020 | Feb-2020 | FO (Change to MW as temp solution) | 2020-01-27 |  | 534254023538 | 6.6 |  | 2020-01-22 |  |  | 2020-02-20 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.02.20 : RFIN sent 18.02.20 : RFI actual, collecting doc RFIN, plan RFIN 19 feb 13.02.20 : ME grounding 06.02.20 : Pondasi done, Tray OG, Mounting OG, ME done, Panel OG 30.01.19 : OG RBS Foundation, delivery material
323 |  | JAW-JB-SNG-3960 | 30573900031 | 120437109 | KORANJI | ACTIVE | MSI | 107.663 | -6.4625 | 40 | 100/190/350 | 2020 | JEDI 2020 [NEW] | Jl. Koranji,Kp. Krajan ,RT. 12/04, Desa Koranji Kec. Purwodadi Kab. Subang ,Prop. Jawa Barat | HTI | JAW-JB-SNG-3960 | KORANJI_PURWADADI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUBANG | 6614387 | 2020-01-15 |  | 36 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-17 | W08-2020 | Feb-2020 | FO (Change to MW as temp solution) | 2020-01-27 |  | 534254025071 | 6.6 |  | 2020-01-22 |  |  | 2020-02-20 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.02.20 : RFIN sent 17.02.20 : RFI actual, collecting doc RFIN, plan RFIN 19 feb 13.02.20 : SRFI 06.02.20 : Pondasi done, Tray OG, Mounting OG, ME OG , Panel OG 30.01.19 : OG RBS Foundation, delivery material
289 |  | JAW-JB-SNG-3961 | 30573990031 | 122215109 | DS. PANGSOR | ACTIVE | SKP | 107.7904 | -6.4796 | 50 | 40/200/300 | 2020 | JEDI 2020 [NEW] | Kp.bunut rt.17 rw.06 desa pangsor kec.pagaden barat,subang Jawa Barat | HTI | JAW-JB-SNG-3961 | PANGSOR | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUBANG | 6614391 | 2020-01-15 |  | 36 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-17 | W08-2020 | Feb-2020 | FO (Change to MW as temp solution) | 2020-01-27 |  | 534213343440 | 6.6 |  | 2020-01-22 |  |  | 2020-02-20 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.02.20 : RFIN sent 19.02.20 : RFI actual, collecting doc RFIN, plan RFIN 19 feb 13.02.20 : SRFI 06.02.20 : Pondasi OG, Tray OG, Mounting OG, ME OG , Panel OG 30.01.19 : OG RBS Foundation, delivery material
265 |  | JAW-JB-SNG-3915 | 30574430031 | 125475126 | CIJENGKOL-SAGALAHERANG | ACTIVE | TB | 107.6329 | -6.6634 | 40 | 110/250/340 | 2020 | JEDI 2020 [NEW] | Jl Raya Cijengkol RT13 RW07 Desa Cijengkol Kec Serang Panjang Kab Subang | HTI | JAW-JB-SNG-3915 | CIJENGKOL_SERANGPANJANG | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUBANG | 6614396 | 2020-01-15 |  | 42 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-16 | W08-2020 | Feb-2020 | FO (Change to MW as temp solution) | 2020-01-27 |  | 534254023520 | 6.6 |  | 2020-01-22 |  |  | 2020-02-26 | W09-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.02.20 : RFIN sent 20.02.20 : 18.02.20 : RFI actual, collecting doc RFIN, plan RFIN 19 feb 17.02.20 : Plan RFI/PLN Connect hari ini 13.02.20 : SRFI 06.02.20 : Pondasi done, Tray OG, Mounting OG, ME done, Panel OG 30.01.19 : OG RBS Foundation, delivery material
266 |  | JAW-JB-BDG-3844 | 30574100031 | 120845104 | CIJERAH2 | ACTIVE | SMI | 107.5571 | -6.9297 | 30 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl.Gempol Sari RT01 RW01 Kel. Gempolsari kec. Bandung kulon Kota bandung | HTI | JAW-JB-BDG-3844 | GEMPOLSARI_TIMUR | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANDUNG | 6614394 | 2020-01-15 |  | 36 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-16 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 535990628425 | 6.6 |  | 2020-01-22 |  |  | 2020-02-20 | W08-2020 |  | 2020-05-31 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.02.20 : RFIN sent 18.02.20 : RFI actual, collecting doc RFIN 17.02.20 : Plan RFI/PLN Connect besok 18 Feb 20 13.02.20 : SRFI 06.02.20 : CME done/Soft RFI, proses PLN connection 30.01.19 : OG RBS Foundation, delivery material
316 |  | JAW-JB-SNG-3955 | 30574410031 | 125578109 | KASOMALANG-PANEMBONG | ACTIVE | TB | 107.7617 | -6.6905 | 40 | 0/120/270 | 2020 | JEDI 2020 [NEW] | KP. Cisaat RT09 RW03 Desa Bojongloak Kec Kasomalang Kab Subang.Kec Kasomalang Kab.Subang | HTI | JAW-JB-SNG-3955 | BOJONGLOA_KASOMALANG | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUBANG | 6614396 | 2020-01-15 |  | 33 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-16 | W08-2020 | Feb-2020 | FO (Change to MW as temp solution) | 2020-01-27 |  | 534254025089 | 6.6 |  | 2020-01-22 |  |  | 2020-02-17 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.02.20 : RFIN sent 13.02.20 : SRFI 06.02.20 : Pondasi done, Tray OG, Mounting OG, ME done, Panel OG 30.01.19 : OG RBS Foundation, delivery material
290 |  | JAW-JB-KNG-3871 | 30573970031 | 125054109 | DSSAGUNG-SINDANGAGUNG | ACTIVE | SKP | 108.539 | -6.9764 | 30 | 30/170/270 | 2020 | JEDI 2020 [NEW] | Dusun Puhun RT06 RW02 Desa Mekarmukti Kec. SindangagungDesa MekarmuktiKec. Sindangagung | HTI | JAW-JB-KNG-3871 | KERTAYASA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. KUNINGAN | 6614391 | 2020-01-15 |  | 30 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-14 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 533212650816 | 6.6 |  | 2020-01-22 |  |  | 2020-02-14 | W07-2020 |  | 2020-09-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.02.20 : RFIN sent 13.02.20 : actual RFI 06.02.20 : Pondasi done, Tray done, Mounting done, ME done, Panel OG 30.01.19 : OG RBS Foundation, delivery material
256 |  | JAW-JB-MJL-3737 | 30574380031 | 125606109 | BO-MAJASARI-LIGUNG | ACTIVE | TB | 108.2987 | -6.6787 | 50 | 50/140/250 | 2020 | JEDI 2020 [NEW] | Blok Ekasari RT03 RW01 Desa Majasari Kecamatan Ligung Kabupaten Majalengka | HTI | JAW-JB-MJL-3737 | MAJASARI_LIGUNG | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. MAJALENGKA | 6614396 | 2020-01-15 |  | 30 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-14 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 535272101830 | 6.6 |  | 2020-01-22 |  |  | 2020-02-14 | W07-2020 |  | 2020-07-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.02.20 : RFIN sent 13.02.20 : actual RFI 06.02.20 : Pondasi done, Tray OG, Mounting OG, ME done, Panel OG 30.01.19 : OG RBS Foundation, delivery material
419 |  | JAW-JB-BDG-3390 | 30574540031 | T000250 | TAMAN HOLIS | ACTIVE | SKP | 107.5618 | -6.9484 | 25 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Taman Holis Rt.02 /03 Desa Sumur sari kel. Cigondewah Rahayu, Bandung Kulon, Kota Bandung | HTI | JAW-JB-BDG-3390 | CIGONDEWAH RAHAYU | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANDUNG | 6614391 | 2020-01-15 |  | 29 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-10 | W07-2020 | Feb-2020 | 2020-02-14 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 535756171417 | 6.6 |  | 2020-01-22 |  |  | 2020-02-13 | W07-2020 |  | 2020-05-30 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.02.20 : actual RFI 06.02.20 : CME done/Soft RFI, proses PLN connection 30.01.19 : OG RBS Foundation, delivery material
421 |  | SUM-LA-KOT-1037 | 30574310031 | 101027109 | TANJUNG KEMALA TANGGAMUS | ACTIVE | TB | 104.8771 | -5.3951 | 50 | 60/180/310 | 2020 | JEDI 2020 [NEW] | Tanjung Kemala RT.01 RW.01, Pekon Tanjung Kemala, Kec. Pugung Kab. Tanggamus, Prov. Lampung | HTI | SUM-LA-KOT-1037 | TANJUNG KEMALA_PUGUNG | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TANGGAMUS | 6614396 | 2020-01-15 |  | 40 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-20 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 172300745388 | 6.6 |  | 2020-01-22 |  |  | 2020-02-24 | W09-2020 |  | 2020-05-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.02.20 : RFIN sent 20.02.20 : plan submit RFIN 20 feb 13.02.20 : SRFI 06.02.20 : 30.01.19 : OG RBS Foundation, delivery material
353 |  | JAW-JI-KDR-8104 | 30574480031 | TBG03_EJ180 | PARE | ACTIVE | TB | 112.1991 | -7.7776 | 30 | 100/200/330 | 2020 | JEDI 2020 [NEW] | Jl. Argo wayang Kamp.Taruna RT 1 RW 1 masjid Solikhin | HTI | JAW-JI-KDR-8104 | Tarunsakti_Kediri | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. KEDIRI | 6614396 | 2020-01-15 |  | 38 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-20 | W08-2020 | Feb-2020 | FO | 2020-01-27 |  | 514061312694 | 6.6 |  | 2020-01-22 |  |  | 2020-02-22 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22.02.20 : RFIN sent 20.02.20 : SRFI, wait PLN connection, di area site sedang ada pemadaman info nya 2hr, jadi PLNmenungda pasang meter nya 06.02.20 : Foundation done, wait ME material 30.01.19 : OG RBS Foundation, delivery material
278 |  | SUM-LA-KOT-1034 | 30574300031 | 100912109 | DESA ASRAMA | ACTIVE | TB | 104.7552 | -5.3659 | 50 | 70/170/250 | 2020 | JEDI 2020 [NEW] | Jln. Sumberejo RT.02 RW.05, Dusun Padalarang, Desa Kalibening, Kecamatan Talang Padang, Kabupaten Tanggamus, Propinsi Lampung | HTI | SUM-LA-KOT-1034 | KALIBENING_TALANG | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TANGGAMUS | 6614396 | 2020-01-15 |  | 35 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-20 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 172300745370 | 6.6 |  | 2020-01-22 |  |  | 2020-02-19 | W08-2020 |  | 2020-07-12 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.02.20 : RFIN sent 13.02.20 : SRFI 06.02.20 : Foundation done, delivery material ME 30.01.19 : OG RBS Foundation, delivery material
376 |  | SUM-LA-BDL-1070 | 30574150031 | 100085109 | RAJA BASA | ACTIVE | TB | 105.2206 | -5.3831 | 30 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Pramuka Gg. Mekar RT.014 LK. I, Kel. Kemiling Raya, Kec. Kemiling, Kota Bandar Lampung.Kel. LangkapuraKec. Kemiling | HTI | SUM-LA-BDL-1070 | KEMILINGRAYATIMUR_TIMUR | COLO | TBG | WEST | LAMPUNG | Lampung | KOTA BANDAR LAMPUNG | 6614396 | 2020-01-15 |  | 33 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 171002388007 | 6.6 |  | 2020-01-22 |  |  | 2020-02-17 | W08-2020 |  | 2020-07-04 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.02.20 : RFI done, RFIN sent 13.02.20 : 06.02.20 : CME done/Soft RFI, OG proses PLN connection 30.01.19 : proses penyelesaian isu (LL meminta kompensasi Colo), mobilisasi team dan delivery material
228 |  | SUM-LA-TWG-0999 | 30574200031 | 100012109 | AGUNG_JAYA2 | ACTIVE | TB | 105.1544 | -4.2857 | 50 | 120/230/320 | 2020 | JEDI 2020 [NEW] | Desa Agung Jaya RT/RW 13/13 Kec. Way Kenang Tulang Bawang | HTI | SUM-LA-TWG-0999 | AGUNG JAYA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG BA | 6614396 | 2020-01-15 |  | 32 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 173400109141 | 6.6 |  | 2020-01-22 |  |  | 2020-02-16 | W08-2020 |  | 2020-05-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18.02.20 : Revisi STO 16.02.20 : RFIN sent 13.02.20 : SRFI 06.02.20 : Prepare material, Target Start pondasi 6 feb 2020, target mat ME On Site 6 feb 2020, BPUJL paid: done, target RFI: 10 Feb 2020 30.01.19 : OG RBS Foundation, delivery material
436 |  | SUM-LA-TWG-1001 | 30574210031 | 100983109 | TIRTA KENCANA | ACTIVE | TB | 105.1326 | -4.5468 | 50 | 0/150/250 | 2020 | JEDI 2020 [NEW] | Tirta Kencana, RT.029 RW.005, Desa Tirta Kencana, Kec. Tulang Bawang Tengah, Kab. Tulang Bawang Barat, Prop. Lampung | HTI | SUM-LA-TWG-1001 | TIRTA KENCANA_TIMUR | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG BA | 6614396 | 2020-01-15 |  | 32 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 173400109125 | 6.6 |  | 2020-01-22 |  |  | 2020-02-16 | W08-2020 |  | 2020-05-19 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.02.20 : RFIN sent 13.02.20 : SRFI 06.02.20 : pondasi OG, ME On Site, Traget SRFI: 6 Feb 2020, Target RFI 11 Feb 2020, BPUJL Paid 5 feb 30.01.19 : OG RBS Foundation, delivery material
231 |  | SUM-LA-PRW-1058 | 30574130031 | 100718109 | AMBARAWA BARAT | ACTIVE | TB | 104.8638 | -5.2956 | 50 | 80/210/340 | 2020 | JEDI 2020 [NEW] | Sinar Pugung RT 001 RW 001, Desa Fajar Mulia, Kec Pagelaran Utara, Kab Pring Sewu, Prov. Lampungkec. Pagelaran Utara | HTI | SUM-LA-PRW-1058 | MADARAYA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. PRINGSEWU | 6614396 | 2020-01-15 |  | 28 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-12 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 172500956048 | 6.6 |  | 2020-01-22 |  |  | 2020-02-12 | W07-2020 |  | 2020-05-21 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.02.20 : RFIN sent 06.02.20 : 30.01.19 : OG RBS Foundation, delivery material
285 |  | SUM-LA-KLA-1019 | 30574290031 | 100918109 | DESABUMI RESTU | ACTIVE | TB | 105.6384 | -5.5888 | 50 | 10/100/250 | 2020 | JEDI 2020 [NEW] | DUSUN BUMI AGUNG, RT/RW. 006/002, DESA BUMI RESTU, KEC. PALAS, KAB. LAMPUNG SELATAN, PROPINSI LAMPUNGDESA BUMI RESTU, KECAMATAN PALASKABUPATEN LAMPUNG SELATAN, PROPINSI LAMPUNG | HTI | SUM-LA-KLA-1019 | BUMI RESTU | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. LAMPUNG SELATAN | 6614396 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-12 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 171300611655 | 6.6 |  | 2020-01-22 |  |  | 2020-02-11 | W07-2020 |  | 2020-05-16 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 06.02.20 : Foundation done, delivery material ME 30.01.19 : OG RBS Foundation, delivery material
408 |  | SUM-LA-KOT-1038 | 30574320031 | 100024109 | SUKA_AGUNG3 | ACTIVE | TB | 104.8845 | -5.4562 | 50 | 0/90/220 | 2020 | JEDI 2020 [NEW] | Dusun Suka Agung Induk,Desa Suka Agung Kec.Bulok, Kab.Tanggamus | HTI | SUM-LA-KOT-1038 | SUKANEGARA_BULOK | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TANGGAMUS | 6614396 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-12 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 172400411699 | 6.6 |  | 2020-01-22 |  |  | 2020-02-11 | W07-2020 |  | 2020-05-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 06.02.20 : CME done/Soft RFI, OG proses PLN connection 30.01.19 : OG RBS Foundation, delivery material
227 |  | JAW-JI-KNR-4256 | 30574020031 | 160183104 | 3G_BENDO | ACTIVE | SKP | 112.1635 | -8.0719 | 40 | 60/180/270 | 2020 | JEDI 2020 [NEW] | Kp. Dukuh Kembangan RT. 04 RW. 09 Desa. Sumberedjo Kec. Sanan KulonKab. Blitar – Jawa Timur | HTI | JAW-JI-KNR-4256 | SANANKULON_SUMBERJO | COLO | TBG | EAST | JATIM | Jawa Timur | KAB. BLITAR | 6614391 | 2020-01-15 |  | 26 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-12 | W07-2020 | Feb-2020 | FO | 2020-01-27 |  | 514021858765 | 6.6 |  | 2020-01-22 |  |  | 2020-02-10 | W07-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.02.20 : aktual RFI, collecting document RFIN 30.01.19 : OG RBS Foundation, delivery material
373 |  | SUM-SS-PKB-1221 | 30574080031 | 070174104 | PTPN VII | ACTIVE | SMI | 104.151 | -2.8509 | 40 | 70/170/240 | 2020 | JEDI 2020 [NEW] | Kampung Simpang Gardu Kecamatan Lais Kabupaten Musi Banyuasin Sumatera Selatan | HTI | SUM-SS-PKB-1221 | TALANG JAYA INDAH | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | KAB. BANYU ASIN | 6614394 | 2020-01-15 |  | 66 | 61 - 90 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-03-16 | W12-2020 | Mar-2020 | MW | 2020-01-27 |  | 142300785683 | 6.6 |  | 2020-01-22 |  |  | 2020-03-21 | W12-2020 |  | 2020-07-31 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.03.20 : RFIN sent 19.03.20 : actual RFI, collecting RFIN doc, plan email RFIN today 11.03.20 : plan rfi Senin 16 mar 20 20.02.20 : pondasi done, wait material on site 13.02.20 : 06.02.20 : 30.01.19 : OG RBS Foundation, delivery material
365 |  | JAW-JB-SMD-3927 | 20201103201 | 122885109 | PERMATARANCAEKEK_CCLKBSC | ACTIVE | SKP | 107.8237 | -6.9663 | 30 | 60/230/310 | 2020 | JEDI 2020 [NEW] | JL Raya Cicalengka _ Garut RT 004 Rw 003 Kel/ Desa Sindang Pakuon Kec Cimanggung Prov. Jawa BaratKel/ Desa Sindang Pakuon Kec Cimanggung | HTI | JAW-JB-SMD-3927 | SINDANGPAKUON | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUMEDANG | 6614391 | 2020-01-15 |  | 42 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-28 | W09-2020 | Feb-2020 | FO (Change to MW as temp solution) | 2020-01-27 |  | 535171982260 | 6.6 |  | 2020-01-22 |  |  | 2020-02-26 | W09-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.02.20 : RFIN sent 25.02.20 : RFI actual 20.02.20 : 17.02.20 : PLan Konek PLN besok 18 feb 13.02.20 : ME on going 06.02.20 : Pondasi OG, Tray onsite 11/02, Mounting onsite 11/02, ME & Panel On proses 30.01.19 : pemintaan kompensasi colo oleh LL, delivery material
279 |  | SUM-LA-GDT-1051 | 30574360031 | 100114109 | DESA GEBANG | ACTIVE | TB | 105.2367 | -5.5555 | 50 | 90/240/310 | 2020 | JEDI 2020 [NEW] | Gebang Hilir, Desa Gebang, Kec. Padang Cermin, Kab. Pesawaran, Lampung. | HTI | SUM-LA-GDT-1051 | SIDODADI_TELUK PANDAN | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. PESAWARAN | 6614396 | 2020-01-15 |  | 32 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 171802680904 | 6.6 |  | 2020-01-22 |  |  | 2020-02-16 | W08-2020 |  | 2020-07-06 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.02.20 : RFIN sent 13.02.20 : 06.02.20 : CME done/Soft RFI, OG proses PLN connection 30.01.19 : Mobilisasi team, delivery material
307 |  | SUM-LA-GDT-1052 | 30574370031 | 100133109 | JEMBAT BATU-2 | ACTIVE | TB | 105.1702 | -5.6539 | 50 | 50/235/350 | 2020 | JEDI 2020 [NEW] | Desa Sanggi Tajur RT.06/00, Kec. Punduh Pidada, Kab. Pesawaran, Lampung. | HTI | SUM-LA-GDT-1052 | SUKAJAYA PUNDUH | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. PESAWARAN | 6614396 | 2020-01-15 |  | 32 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 171802681119 | 6.6 |  | 2020-01-22 |  |  | 2020-02-16 | W08-2020 |  | 2020-05-20 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.02.20 : RFIN sent 13.02.20 : 06.02.20 : CME done/Soft RFI, OG proses PLN connection 30.01.19 : Mobilisasi team, delivery material
443 |  | SUM-LA-GDT-1046 | 30574350031 | 100978126 | WAY URANG_LAMPUNG | ACTIVE | TB | 105.1122 | -5.6053 | 50 | 90/180/270 | 2020 | JEDI 2020 [NEW] | Way Urang, RT 001 RW 001, Desa Way Urang, Kec. Padang Cermin, Pesawaran, Lampung | HTI | SUM-LA-GDT-1046 | WAY URANG_PADANG CERMIN | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. PESAWARAN | 6614396 | 2020-01-15 |  | 32 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 171802680912 | 6.6 |  | 2020-01-22 |  |  | 2020-02-16 | W08-2020 |  | 2020-05-19 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.02.20 : RFIN sent 13.02.20 : SRFI 06.02.20 : 30.01.19 : OG RBS Foundation, delivery material
350 |  | SUM-SS-MRE-1188 | 30574140031 | 071304126 | PAGAR AGUNG | ACTIVE | TB | 104.1837 | -3.5522 | 50 | 10/100/260 | 2020 | JEDI 2020 [NEW] | Dusun I, Desa Pagar Agung, Kec. Rambang, Kab. Muara Enim, Sumatera Selatan | HTI | SUM-SS-MRE-1188 | PAGAR AGUNG_RAMBANG | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | KAB. MUARA ENIM | 6614396 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-13 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 149200060451 | 6.6 |  | 2020-01-22 |  |  | 2020-02-11 | W07-2020 |  | 2020-06-09 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 06.02.20 : 30.01.19 : OG RBS Foundation, delivery material
293 |  | SUM-LA-PRW-1054 | 30574490031 | 100985109 | FAJAR MULYA | ACTIVE | TB | 104.9379 | -5.4548 | 50 | 30/110/280 | 2020 | JEDI 2020 [NEW] | Wargo Mulyo, RT.001 RW.004, Desa Wargo Mulyo, Kec. Pardasuka, Kab. Pringsewu, Prop. Lampung. | HTI | SUM-LA-PRW-1054 | WARGA MULYO | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. PRINGSEWU | 6614396 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-13 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 172400411703 | 6.6 |  | 2020-01-22 |  |  | 2020-02-11 | W07-2020 |  | 2020-07-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 06.02.20 : OG ME installation 30.01.19 : Mobilisasi team, delivery material
267 |  | JAW-JB-PWK-3740 | 30574390031 | 125494126 | CIKOPO | ACTIVE | TB | 107.4886 | -6.428 | 40 | 90/210/330 | 2020 | JEDI 2020 [NEW] | KP. CIKOPO RT 10 RW04 DESA CIKOPO BUNGURSARI KEC.PURWAKARTA KAB. PURWAKARTA | HTI | JAW-JB-PWK-3740 | CIKOPO_BUNGURSARI | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. PURWAKARTA | 6614396 | 2020-01-15 |  | 26 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-13 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 534443744273 | 6.6 |  | 2020-01-22 |  |  | 2020-02-10 | W07-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.02.20 : RFIN sent 06.02.20 : RFI aktual, RFIN & Sistem NY, collecting RFI doc 30.01.19 : comcase permintaan biaya kordinasi dengan LSM yang tinggi, pekerjaan stop, OG proses negosiasi
318 |  | SUM-SS-LHT-1216 | 30573940031 | 070117109 | KEBAN LAHAT EX PASAR SELUMA-1 | ACTIVE | SKP | 103.574 | -3.7325 | 50 | 80/190/280 | 2020 | JEDI 2020 [NEW] | Jl.PTP Kebun Senabing Kampung Dua Desa Keban Kecamatan Lahat Kabupaten Lahat Sumsel | HTI | SUM-SS-LHT-1216 | KEBAN | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | KAB. LAHAT | 6614391 | 2020-01-15 |  | 26 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-13 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 147000687284 | 6.6 |  | 2020-01-22 |  |  | 2020-02-10 | W07-2020 |  | 2020-08-16 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.02.20 : RFIN done 06.02.20 : CME done/Soft RFI, OG proses PLN connection, target Connect PLN: 7 feb 2020 30.01.19 : OG RBS Foundation, delivery material 29.01.19 : Mobilisasi team, delivery material, plan start CME 31 Jan
425 |  | JAW-JB-SMD-3738 | 20201103211 | 122411109 | Tanjungsari-Marco | ACTIVE | SKP | 107.8046 | -6.9026 | 30 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Kp Babakan situ Rt03 Rw06 Kel Tanjung sari kec Tanjung sari kab sumedang | HTI | JAW-JB-SMD-3738 | TANJUNGSARI_Kenanga | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. SUMEDANG | 6614391 | 2020-01-15 |  | 40 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-14 | W07-2020 | Feb-2020 | 2020-02-28 | W09-2020 | Feb-2020 | FO (Change to MW as temp solution) | 2020-01-27 |  | 535171982789 | 6.6 |  | 2020-01-22 |  |  | 2020-02-24 | W09-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.02.20 : RFIN sent 20.02.20 : OG ME installation 17.02.20 : Material ME+tray+grounding+mounting onsite 18/02, BPUL plan bayar 18/02 13.02.20 : isu close,plan bowplank+pondasi BTS 14/02 07.02.20 - 06.02.20 : Comcase (LL minta kompensasi tinggi 5jt,) 30.01.19 : OG RBS Foundation, delivery material
287 |  | JAW-JB-BDG-3648 | 30574000031 | 124122109 | DIANPERMAI-MARGAHAYU | ACTIVE | SKP | 107.5682 | -6.9452 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jalan terusan Holis rt 1 rw 10 Kel Margahayu Utara Kec Babakan CiparayKec Babakan Ciparaykota bandung | HTI | JAW-JB-BDG-3648 | MARGAHAYU UTARA | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANDUNG | 6614391 | 2020-01-15 |  | 112 | 91 - 120 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-02-21 | W08-2020 | Feb-2020 | 2020-05-06 | W19-2020 | May-2020 | MW | 22 Apr 20 27 jan 20 |  | 535756178327 | 6.6 |  | 2020-01-22 |  | 2020-04-09 | 2020-05-06 | W19-2020 |  | 2020-06-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.05.20 : RFIN sent 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL, plan RFI 6 may 20 09.04.20 : SOFT RFIN sent 02.04.20 : stacking installation, plan SRFI 11 apr 25.03.20 : on going pondasi stacking, plan on site material stacking 27 Mar, plan RFI 7 Apr 19.03.20 : on going pabrikasi 10 hari start kemarin, plan on site 30 mar, plan RFI 7 apr 20.02.20 : need stacking baseframe, material ready w2 Maret, plan RFI mundur 20 Mar 20 07.02.20 - 06.02.20 : layout issue 05.02.20 : aktual lebar space hanya 0.8m, tidak mecukupi requirement pondasi XL lebar 1 m, pondasi hold 30.01.19 : OG RBS Foundation, delivery material
301 |  | JAW-JB-BDG-3645 | 30574460031 | 123517109 | HTLTLGSARI-KPCIKADO | ACTIVE | TB | 107.5976 | -6.8551 | 25 | 90/210/330 | 2020 | JEDI 2020 [NEW] | Cidadap Girang RT 01 RW05 Kelurahan Ledeng Kecamatan Cidadap Kota Bandung | HTI | JAW-JB-BDG-3645 | LEDENG_CIDADAP | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KOTA BANDUNG | 6614396 | 2020-01-15 |  | 42 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-21 | W08-2020 | Feb-2020 | 2020-02-25 | W09-2020 | Feb-2020 | MW | 2020-01-27 |  | 535596850412 | 6.6 |  | 2020-01-22 |  |  | 2020-02-26 | W09-2020 |  | 2020-06-30 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.02.20 : RFIN sent 25.02.20 : RFI actual 20.02.20 : need check RFI status 17.02.20 : plan connect PLN 18 Feb 14.02.20 : ME on going 13.02.20 : comcase clear, pondasi done 07.02.20 - 06.02.20 : Comcase, LL tidak memberikan izin ada colo baru, isu design klem 30.01.19 : OG RBS Foundation, delivery material
363 |  | JAW-JB-KNG-3866 | 30574420031 | 125582109 | PERMANENISASIDSTIMBANG | ACTIVE | TB | 108.5129 | -6.8786 | 40 | 0/100/210 | 2020 | JEDI 2020 [NEW] | Dusun I RT2 RW1 Desa Timbangan Kec Cigandamekar Kab Kuningan. | HTI | JAW-JB-KNG-3866 | TIMBANG | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. KUNINGAN | 6614396 | 2020-01-15 |  | 42 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-21 | W08-2020 | Feb-2020 | 2020-02-21 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 533711125273 | 6.6 |  | 2020-01-22 |  |  | 2020-02-26 | W09-2020 |  | 2020-09-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.02.20 : RFIN sent 20.02.20 : 19.02.20 : RFI actual, plan RFIN 20 Feb 13.02.20 : comcase close, plan start CME 15 feb 07.02.20 : Comcase 30.01.19 : OG RBS Foundation, delivery material
354 |  | JAW-JB-SOR-3657 | 30575040031 | 120592109 | PASAR WANGISAGARA | ACTIVE | TB | 107.7392 | -7.0802 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Kp. Bojong Koneng RT/RW 02/06, Kel. Wangisagara, Kec. Majalaya, Kab. Bandung | HTI | JAW-JB-SOR-3657 | WANGISAGARA_SELATAN | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614396 | 2020-01-15 |  | 173 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-03-12 | W11-2020 | Mar-2020 | 2020-06-13 | W24-2020 | Jun-2020 | 2020-07-15 | W29-2020 | Jul-2020 | MW | 20-May-20 18-May-20 |  | 535312221665 | 6.6 |  | 2020-01-22 |  | 2020-03-12 | 2020-07-06 | W28-2020 |  | 2020-09-14 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.07.20 : 09.07.20 : 06.07.20 : RFIN sent 03.07.20 : actual RFI connect Multiguna, collecting doc RFIN 02.07.20 : revisi plan connect PLN 15 juli, karena isu KWH meter masih kosong 29.06.20 : 22.06.20 : 16.06.20 : isu stock KWH meter, sedang di usahakan connect dengan revisi plan RFI akhir minggu ini 19-20 Jun ini 28.05.20 : 14.05.20 : 12.03.20 : Email SRFIN sent 11.03.20 : SRFI, collecting doc SRFI-N 20.02.20 : wait kekurangan material ME dan og pln connection 13.02.20 : SRFI (use existing CME ex XL) 06.02.20 : CME done/Soft RFI, proses PLN connection 30.01.19 : OG RBS Foundation, delivery material
264 |  | JAW-JB-SOR-3654 | 30574990031 | 120487109 | CIGANITRI-STO CIJAURA | ACTIVE | MSI | 107.6565 | -6.9682 | 30 | 100/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Ciganitri mukti, Kel. Cipagalo, Kec.Bojongsoang, Kab.Bandung, Jawa barat | HTI | JAW-JB-SOR-3654 | CIPAGALO | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614387 | 2020-01-15 |  | 145 | 121 - 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-03-12 | W11-2020 | Mar-2020 | 2020-06-13 | W24-2020 | Jun-2020 | 2020-06-13 | W24-2020 | Jun-2020 | MW | 20-May-20 18-May-20 |  | 535679748049 | 6.6 |  | 2020-01-22 |  | 2020-03-12 | 2020-06-08 | W24-2020 |  | 2020-07-21 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.06.20 : RFIN sent 28.05.20 : 14.05.20 : 12.03.20 : Email SRFIN sent 11.03.20 : plan SRFIN senin 16 Mar 20.02.20 : wait kekurangan material ME, plan RFI mundur 28 Mar 20 13.02.20 : ME OG (use existing CME ex XL) 06.02.20 : 30.01.19 : OG RBS Foundation, delivery material
271 |  | JAW-JB-SOR-3687 | 30574530031 | 122398109 | COBLONG - JL. IMAM BONJOL ( BTS HOTEL ) / CIPAKUMJLY-PADAMUKTI | ACTIVE | SKP | 107.7689 | -7.0242 | 30 | 10/120/190 | 2020 | JEDI 2020 [NEW] | Jln. Raya Panyadap RT.02 RW.03, Ds.Panyadap, Kec. Solokan Jeruk, Kab . Bandung | HTI | JAW-JB-SOR-3687 | PANYADAP | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG | 6614391 | 2020-01-15 |  | 145 | 121 - 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-04-03 | W14-2020 | Apr-2020 | 2020-06-13 | W24-2020 | Jun-2020 | 2020-06-13 | W24-2020 | Jun-2020 | MW | 20-May-20 18-May-20 |  | 535312218152 | 6.6 |  | 2020-01-22 |  | 2020-04-29 | 2020-06-08 | W24-2020 |  | 2020-07-19 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.06.20 : email RFIN sent 03.06.20 : actual RFI, PLN connect 3 jun 20 28.05.20 : 14.05.20 : 29.04.20 : email SRFI-N sent 11.03.20 : comcase 20.02.20 : plan solved end of Feb, potensi RFI mundur W1 mar (7 mar 20) 13.02.20 : OG penyelesaian isu, 07.02.20 - 06.02.20 : Comcase, warga dan PJS demo minta sosialisasi colo dan ormas minta unang koordinasi 30.01.19 : OG RBS Foundation, delivery material
372 |  | JAW-JB-CMH-3652 | 30574470031 | 123764109 | PROTEL BAROS | ACTIVE | TB | 107.5446 | -6.893 | 30 | 50/210/340 | 2020 | JEDI 2020 [NEW] | Komplek Pusdikom Kota Cimahi | HTI | JAW-JB-CMH-3652 | CIGUGUR TENGAH | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KOTA CIMAHI | 6614396 | 2020-01-15 |  | 211 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-04-30 | W18-2020 | Apr-2020 | 2020-07-03 | W27-2020 | Jul-2020 | 2020-08-20 | W34-2020 | Aug-2020 | MW | 15-Jun-20 27-Jan-20 |  | 535812171555 | 6.6 |  | 2020-01-22 |  | 2020-07-16 | 2020-08-13 | W33-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.08.20 : RFIN sent 10.08.20 : 03.08.20 : masih belum mendapat ijin akses dari PUSDIKOM 27.07.20 : 23.07.20 : 16.07.20 : proses instalasi PLN terkendala akses ke area PUSDIKOM, karena di sekitar tower digunakan sebagai tempat karantina siswa SECAPA terkait isu covid yang sedang terjadi di SECAPA AD Bandung, KWH meter ready, email SRFI-N sent 13.07.20 : PLN connection masih terkendala isu stock kwh meter kosong 09.07.20 : plan PLN connect 20 jul 20, isu stock kwh meter kosong 06.07.20 : 02.07.20 : 29.06.20 : 22.06.20 : 18.06.20 : proses PLN connection 17.06.20 : Go RFI, PSB PLN release 11.06.20 : actual SRFI, collecting doc SRFIN 08.06.20 : pondasi bts done, waiting tray+mounting ME, plan onsite 9/6 04.06.20 : pondasi bts done, waiting tray+mounting ME 01.06.20 : plan besok release surat tugas unk tim dari pusdikpom dan start CME 28.05.20 : 25.05.20 : 21.05.20 : 19.05.20 : open akses (info pak beni), plan start CME after lebaran 15.05.20 : Kasi TNI yg mengurus isu ini sdg dinas diluar kota, shg Untuk open akses blm bisa krn perlu sirkuler memo di internal Pusdikpom utk akses dan perlu menunggu beliau kembali di hari Rabu 20 Mei 2020 14.05.20 : proses penjadwalan pertemuan dengan 08.05.20 : proses penyelesaian isu 30.04.20 : 23.04.20 : 16.04.20 : 09.04.20 : proses negosiasi dg Pusdikom 02.04.20 : 25.03.20 : plan isu solve W1 Apr, plan RFI W3 Apr 19.03.20 : 11.03.20 : minta ada perubahan di pks, CME ny start 20.02.20 : 15.02.20 : proses negossiasi dengan PUSDIKOM, plan isu solve end of Feb, plan RFI W2 Mar 07.02.20 - 06.02.20 : Comcase dengan PUSDIKPOM karena ada MOU yang belum disepakati dengan TBG 30.01.19 : OG RBS Foundation, delivery material
325 |  | JAW-JB-NPH-3669 | 20200602551 | 124091109 | KPCIKAWATIMW_TANIMULYA | ACTIVE | SKP | 107.5242 | -6.85 | 30 | 70/150/250 | 2020 | JEDI 2020 [NEW] | Kp. Cibuntu RT.03 RW.09 Desa Cilame, Kec. Ngamprah, Kab. Bandung Barat, Kec. Ngamprah, Kab. Bandung Barat | HTI | JAW-JB-NPH-3669 | CILAME_NGAMPRAH | COLO | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614391 | 2020-01-15 |  | 237 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-04-29 | W18-2020 | Apr-2020 | 2020-09-08 | W37-2020 | Sep-2020 | 2020-09-08 | W37-2020 | Sep-2020 | FO | 29-Jun-20 18-May-20 |  | 535812177567 | 6.6 |  | 2020-01-22 |  | 2020-04-29 | 2020-09-08 | W37-2020 |  | 2020-09-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.09.20 : RFIN sent 03.08.20 : 27.07.20 : 23.07.20 : 16.07.20 : PLN connection, wait SK PLN release dan wait progress FO XL, paralel on going progress MMP TBG 09.07.20 : 06.07.20 : 02.07.20 : wait SK PLN release, plan RFI = SPK release + 14 hari 29.06.20 : PLN Connection menunggu konfirmasi dari XL 22.06.20 : SPK FO/MMP release 15 jun 20, plan RFS W27 (4 Jul 20), need request SK PLN, plan RFI 10 jul 20 22.06.20 : 28.05.20 : 14.05.20 : 29.04.20 : email SRFI-N sent, wait plan MOS & konfirmasi permintaan PLN connection dari XL/tech part 23.04.20 : 16.04.20 : isu solve, RBS foundation done, wait material ME grounding 09.04.20 : plan isu solve W2 Apr, plan SRFI W4 Apr 02.04.20 : 25.03.20 : plan isu solve W1 Apr, plan RFI W3 Apr 19.03.20 : on going proses negosiasi 11.03.20 : plan solved minggu ini, plan SRFI 25 mar 20.02.20 : plan solved end of Feb, potensi RFI mundur W1 mar (7 mar 20) 13.02.20 : OG penyelesaian isu 07.02.20 - 06.02.20 : Comcase (LL minta pertemuan dengan pic TBG ttg akses) 30.01.19 : OG RBS Foundation, delivery material
244 |  | SUM-LA-PRW-1057 | 30574120031 | 101035109 | BANYU URIP | ACTIVE | TB | 104.9271 | -5.3192 | 50 | 150/210/330 | 2020 | JEDI 2020 [NEW] | Jl. Banjarejo RT.003 RW.002, Pekon Banjarejo, Kec. Banyumas, Kab. Pringsewu, Prov. Lampung | HTI | SUM-LA-PRW-1057 | SINAR BARU TIMUR | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. PRINGSEWU | 6614396 | 2020-01-15 |  | 35 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-20 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 172500956055 | 6.6 |  | 2020-01-21 |  |  | 2020-02-19 | W08-2020 |  | 2020-05-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.02.20 : RFIN sent 13.02.20 : 06.02.20 : CME done/Soft RFI, OG proses PLN connection 30.01.19 : OG RBS Foundation, delivery material
236 |  | SUM-LA-TWG-0996 | 30574190031 | 100130109 | BALAM JAYA | ACTIVE | TB | 105.1724 | -4.251 | 50 | 90/200/330 | 2020 | JEDI 2020 [NEW] | Kampung Balam Jaya RT.01/05, Desa Balam Jaya, Kec. Way Kenanga, Kab. Tulang Bawang Barat, Lampung. | HTI | SUM-LA-TWG-0996 | BALAM JAYA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG BA | 6614396 | 2020-01-15 |  | 40 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 173301740355 | 6.6 |  | 2020-01-21 |  |  | 2020-02-24 | W09-2020 |  | 2020-06-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.02.20 : RFIN sent 20.02.20 : plan submit RFIN 20 feb 13.02.20 : SRFI 06.02.20 : 05.02.20 : Prepare material, Target Start pondasi 6 feb 2020, target mat ME On Site 6 feb 2020, BPUJL paid: done, target RFI: 10 Feb 2020 30.01.19 : OG RBS Foundation, delivery material
281 |  | SUM-LA-TWG-0994 | 30574180031 | 100916109 | DESA LAMBU KIBANG | ACTIVE | TB | 105.1507 | -4.3661 | 50 | 0/90/270 | 2020 | JEDI 2020 [NEW] | RT 005/RW 001, Desa Pagar Jaya, kecamatan lambu kibang, kabupaten Tulang bawang barat, Propinsi Lampung | HTI | SUM-LA-TWG-0994 | PAGAR JAYA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG BA | 6614396 | 2020-01-15 |  | 32 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 173400109182 | 6.6 |  | 2020-01-21 |  |  | 2020-02-16 | W08-2020 |  | 2020-05-26 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.02.20 : RFIN sent 13.02.20 : 06.02.20 : CME done/Soft RFI, OG proses PLN connection, BPUJL Paid, target Connect: 10 Feb 2020 30.01.19 : OG RBS Foundation, delivery material
286 |  | SUM-LA-KLA-1016 | 30574270031 | 100921109 | DESAKELATEN | ACTIVE | TB | 105.697 | -5.7378 | 50 | 150/230/310 | 2020 | JEDI 2020 [NEW] | Klaten RT.001 RW 004 Desa Klaten Kec.Penengahan Kab.Lampung Selatan Pro.Lampung | HTI | SUM-LA-KLA-1016 | KELATEN | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. LAMPUNG SELATAN | 6614396 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-12 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 171300611614 | 6.6 |  | 2020-01-21 |  |  | 2020-02-11 | W07-2020 |  | 2020-07-07 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 06.02.20 : CME done/Soft RFI, OG proses PLN connection 30.01.19 : OG RBS Foundation, delivery material
276 |  | SUM-LA-TWG-1003 | 30574220031 | 060370109 | DAYA MURNI 2 | ACTIVE | TB | 105.1085 | -4.6228 | 50 | 0/120/250 | 2020 | JEDI 2020 [NEW] | Jl. Murni Jaya RT. 03 RW.03 Kelurahan Murni Jaya Kecamatan Tumi Jajar Kab. Tulang Bawang Barat Prop. Lampung | HTI | SUM-LA-TWG-1003 | MURNI JAYA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG BA | 6614396 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-12 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 173400109203 | 6.6 |  | 2020-01-21 |  |  | 2020-02-11 | W07-2020 |  | 2020-05-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 06.02.20 : CME done/Soft RFI, OG proses PLN connection, BPUJL Paid, target Connect: 10 Feb 2020 30.01.19 : OG RBS Foundation, delivery material
233 |  | SUM-LA-KLA-1017 | 30574280031 | 101055109 | API_PALAS V | ACTIVE | TB | 105.6924 | -5.6221 | 50 | 50/200/300 | 2020 | JEDI 2020 [NEW] | PALAS PASEMAH RT 002 RW 002 DESA PALAS PASEMAH KEC PALAS | HTI | SUM-LA-KLA-1017 | PALAS JAYA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. LAMPUNG SELATAN | 6614396 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-12 | W07-2020 | Feb-2020 | 2020-02-12 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 171300611622 | 6.6 |  | 2020-01-21 |  |  | 2020-02-11 | W07-2020 |  | 2020-06-11 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 06.02.20 : Foundation done, delivery material ME 30.01.19 : OG RBS Foundation, delivery material
398 |  | SUM-LA-TWG-0997 | 30574070031 | 100291104 | SIMPANG_SIMARASAHAN | ACTIVE | SMI | 105.2114 | -4.176 | 50 | 20/130/250 | 2020 | JEDI 2020 [NEW] | JL. LINTAS TIMUR DESA SIMPANG SINAS ASAHAN DUSUN II RT 01 KEL. INDRALOKA, KEC. LAMBU KIBANG KAB. TULANG BAWANG | HTI | SUM-LA-TWG-0997 | INDRALOKA II | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG BA | 6614394 | 2020-01-15 |  | 40 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 173301740795 | 6.6 |  | 2020-01-21 |  |  | 2020-02-24 | W09-2020 |  | 2020-05-22 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.02.20 : RFIN sent 20.02.20 : plan submit RFIN 20 feb 13.02.20 : SRFI 06.02.20 : pondasi OG, ME On Site, Traget SRFI: 6 Feb 2020, Target RFI 11 Feb 2020, BPUJL Paid 5 feb 30.01.19 : Mobilisasi team, delivery material
243 |  | SUM-LA-TWG-1000 | 30573930031 | 100051104 | BANJAR AGUNG SELATAN | ACTIVE | SKP | 105.2069 | -4.4043 | 50 | 90/220/310 | 2020 | JEDI 2020 [NEW] | Gilang Tunggal Makarta RT 03 RW 01 Desa Gilang Tunggal Makarta,Kec. Lambu Kibang Kabupaten Tulang Ba | HTI | SUM-LA-TWG-1000 | GILANG TUNGGAL MAKARTA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG BA | 6614391 | 2020-01-15 |  | 32 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 173400109211 | 6.6 |  | 2020-01-21 |  |  | 2020-02-16 | W08-2020 |  | 2020-05-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.02.20 : RFIN sent 13.02.20 : 06.02.20 : CME done/Soft RFI, OG proses PLN connection, BPUJL Paid, target Connect: 10 Feb 2020 30.01.19 : Mobilisasi team, delivery material
339 |  | SUM-LA-MGL-0983 | 30573920031 | 100083104 | MEKARSARI | ACTIVE | SKP | 105.4557 | -4.2765 | 50 | 30/180/270 | 2020 | JEDI 2020 [NEW] | JL. Poros Bina Bumi RT 09/ RW04 Ds Bina Bumi LAmpung Kec Mraksa Aji Kab Tulang BawangDesa Bina Bumi, Kec Meraksa Aji, Kab Tulang Bawang | HTI | SUM-LA-MGL-0983 | BINA BUMI | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG | 6614391 | 2020-01-15 |  | 40 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 173301740363 | 6.6 |  | 2020-01-21 |  |  | 2020-02-24 | W09-2020 |  | 2020-05-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.02.20 : RFIN sent 20.02.20 : plan submit RFIN 20 feb 17.02.20 : Plan RFI/PLN Connect 19 Feb 20 13.02.20 : SRFI 06.02.20 : Prepare material, Target Start pondasi 6 feb 2020, target mat ME On Site 6 feb 2020, BPUJL paid: done, target RFI: 10 Feb 2020 30.01.19 : Mobilisasi team, delivery material
446 |  | SUM-LA-BDL-1120 | 30574260031 | 100628109 | ZAENAL ABIDIN BDL | ACTIVE | TB | 105.2331 | -5.3668 | 30 | 0/120/240 | 2020 | JEDI 2020 [NEW] | Jl. Z A Pagar Alam No. 73 - 49 RT. 01 Link. II Kel Rajabasa Kec. Rajabasa Kota Bandar Lampung | HTI | SUM-LA-BDL-1120 | RAJABASA_RAJABASA | COLO | TBG | WEST | LAMPUNG | Lampung | KOTA BANDAR LAMPUNG | 6614396 | 2020-01-15 |  | 33 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 171202752183 | 6.6 |  | 2020-01-21 |  |  | 2020-02-17 | W08-2020 |  | 2020-07-04 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.02.20 : RFI done, RFIN sent 13.02.20 : 06.02.20 : CME done/Soft RFI, OG proses PLN connection 30.01.19 : OG RBS Foundation, delivery material
340 |  | SUM-LA-SDN-1028 | 30574090031 | 100251104 | MELINTING | ACTIVE | SMI | 105.7508 | -5.3645 | 50 | 100/210/320 | 2020 | JEDI 2020 [NEW] | JL RADEN PAKSI DUSUN II RT 03 KEL WANA KEC MELINTING KAB LAMPUNG TIMUR | HTI | SUM-LA-SDN-1028 | WANA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. LAMPUNG TIMUR | 6614394 | 2020-01-15 |  | 33 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 172100922428 | 6.6 |  | 2020-01-21 |  |  | 2020-02-17 | W08-2020 |  | 2020-05-20 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.02.20 : RFI done, RFIN sent 13.02.20 : SRFI 06.02.20 : mobilisasi tim, material onsite: 5 feb 2020, Target SRFI: 7 feb 2020, bpujl paid 5 feb 2020, target Connect PLN 7 Feb 2020 30.01.19 : Mobilisasi team, delivery material, plan start CME 3 Feb
343 |  | SUM-LA-TWG-1011 | 30574250031 | 100127109 | MURNI JAYA | ACTIVE | TB | 105.1273 | -4.694 | 50 | 80/180/330 | 2020 | JEDI 2020 [NEW] | Dusun Gunung Menanti RT.002/ RW.001 Desa Gunung Menanti Kecamatan Tumijajar Kabupaten Tulang Bawang Barat | HTI | SUM-LA-TWG-1011 | GUNUNG MENANTI | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG BA | 6614396 | 2020-01-15 |  | 32 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 173400109229 | 6.6 |  | 2020-01-21 |  |  | 2020-02-16 | W08-2020 |  | 2020-06-04 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.02.20 : RFIN sent 13.02.20 : SRFI 06.02.20 : Prepare material, Target Start pondasi 6 feb 2020, target mat ME On Site 6 feb 2020, BPUJL paid: done, target RFI: 10 Feb 2020 30.01.19 : OG RBS Foundation, delivery material
357 |  | SUM-LA-PRW-1055 | 30574500031 | 101044126 | PATOMAN II | ACTIVE | TB | 104.9115 | -5.3823 | 40 | 70/160/330 | 2020 | JEDI 2020 [NEW] | Karang Sari II Gg. SDN 1 Karang Sari, RT.001 RW.002, Desa Karang Sari, Kec. Pagelaran, Kab. Pringsewu, Prov. LampungKel.Karang SariKec.Pagelaran | HTI | SUM-LA-PRW-1055 | KARANG SARI_PAGELARAN | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. PRINGSEWU | 6614396 | 2020-01-15 |  | 32 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 172500956119 | 6.6 |  | 2020-01-21 |  |  | 2020-02-16 | W08-2020 |  | 2020-05-16 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.02.20 : RFIN sent 13.02.20 : SRFI 06.02.20 : OG RBS Foundation, delivery material 30.01.19 : Mobilisasi team, delivery material
284 |  | SUM-LA-TWG-1009 | 30574240031 | 100935109 | DESA WAY SIDO | ACTIVE | TB | 105.0136 | -4.6411 | 50 | 40/200/300 | 2020 | JEDI 2020 [NEW] | Jalan Dua, RT.012 RW.004, Desa Way Sido, Kecamatan Tulang Bawang Udik, Kabupaten Tulang Bawang Barat, Propinsi Lampung | HTI | SUM-LA-TWG-1009 | WAY SIDO | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG BA | 6614396 | 2020-01-15 |  | 32 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 173400109190 | 6.6 |  | 2020-01-21 |  |  | 2020-02-16 | W08-2020 |  | 2020-05-21 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.02.20 : RFIN sent 13.02.20 : SRFI 06.02.20 : pondasi OG, ME On Site, Traget SRFI: 6 Feb 2020, Target RFI 11 Feb 2020, BPUJL Paid 5 feb 30.01.19 : OG RBS Foundation, delivery material
230 |  | SUM-LA-KOT-1075 | 30573910031 | 100037104 | AIRMANINGAN | ACTIVE | SKP | 104.7304 | -5.2734 | 50 | 130/240/320 | 2020 | JEDI 2020 [NEW] | Jl.Airmaningan Rt 01 Rw 01 Dusun Cita Laksana Desa Air KubangKecamatan Airmaningan Kabupaten Tanggamus Propinsi Lampung | HTI | SUM-LA-KOT-1075 | AIR KUBANG_AIR NANINGAN | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TANGGAMUS | 6614391 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-13 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 172300745092 | 6.6 |  | 2020-01-21 |  |  | 2020-02-11 | W07-2020 |  | 2020-05-22 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 06.02.20 : Foundation done, delivery material ME 30.01.19 : Mobilisasi team, delivery material
369 |  | SUM-LA-KTB-1116 | 30574060031 | 100254104 | PLEMBANGAN | ACTIVE | SMI | 104.7439 | -4.8742 | 50 | 80/200/270 | 2020 | JEDI 2020 [NEW] | Dusun Plembangan Desa.Bumi Mandiri Kec.Abung Barat | HTI | SUM-LA-KTB-1116 | BUMI MANDIRI | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. LAMPUNG UTARA | 6614394 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-13 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 173001383908 | 6.6 |  | 2020-01-21 |  |  | 2020-02-11 | W07-2020 |  | 2020-05-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 06.02.20 : Prepare material, Target Start pondasi 6 feb 2020, target mat ME On Site 6 feb 2020, BPUJL paid: done, target RFI: 10 Feb 2020 30.01.19 : Mobilisasi team, delivery material
232 |  | SUM-LA-TWG-1004 | 30574230031 | 101052109 | API_MAKARTI TUMIJAJAR | ACTIVE | TB | 105.0695 | -4.6718 | 50 | 100/200/300 | 2020 | JEDI 2020 [NEW] | MAKARTI RT 010 RW 003 DESA MAKARTI KECAMATAN TUMIJAJAR | HTI | SUM-LA-TWG-1004 | MAKARTI_TUMIJAJAR | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TULANGBAWANG BA | 6614396 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-13 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 173400109133 | 6.6 |  | 2020-01-21 |  |  | 2020-02-11 | W07-2020 |  | 2020-05-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 11.02.20 : RFIN sent 06.02.20 : CME done/Soft RFI, OG proses PLN connection, BPUJL Paid, target Connect: 10 Feb 2020 30.01.19 : OG RBS Foundation, delivery material
422 |  | SUM-SS-PBM-1202 | 30574160031 | 071238109 | TANJUNG TELANG | ACTIVE | TB | 104.1759 | -3.3856 | 50 | 150/220/290 | 2020 | JEDI 2020 [NEW] | Jalan Raya Sungai Medang - Tanjung Telang Dusun IV Desa Tanjung Telang Kec. Prabumulih Barat Sumatera Selatan | HTI | SUM-SS-PBM-1202 | TANJUNG TELANG | COLO | TBG | WEST | SUMBAGSEL | Sumatera Selatan | KOTA PRABUMULIH | 6614396 | 2020-01-15 |  | 27 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-13 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 149200060469 | 6.6 |  | 2020-01-21 |  |  | 2020-02-11 | W07-2020 |  | 2020-05-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.20 : RFIN sent 06.02.20 : 30.01.19 : OG RBS Foundation, delivery material
247 |  | SUM-LA-LIW-1080 | 30574050031 | 100242104 | BATU_KEBAYAN | ACTIVE | SMI | 104.2731 | -5.0275 | 50 | 90/160/290 | 2020 | JEDI 2020 [NEW] | DESA BATU KEBAYAN KEC BELALAU KAB LAMPUNG BARAT PROP LAMPUNG | HTI | SUM-LA-LIW-1080 | KUBU LIKU JAYA | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. LAMPUNG BARAT | 6614394 | 2020-01-15 |  | 37 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 173800645998 | 6.6 |  | 2020-01-21 |  |  | 2020-02-21 | W08-2020 |  | 2020-05-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.02.20 : RFIN sent 20.02.20 : plan submit RFIN 20 feb 13.02.20 : SRFI 06.02.20 : 30.01.19 : Mobilisasi team, delivery material
313 |  | SUM-LA-KOT-1040 | 30574340031 | 100986109 | KALISARI II | ACTIVE | TB | 104.5365 | -5.5072 | 50 | 10/200/300 | 2020 | JEDI 2020 [NEW] | Pekon Karang Anyar, RT.001 RW.001, Kec. Wonosobo, Kab. Tanggamus, Prop. Lampung. | HTI | SUM-LA-KOT-1040 | KARANG ANYAR_TANGGAMUS | COLO | TBG | WEST | LAMPUNG | Lampung | KAB. TANGGAMUS | 6614396 | 2020-01-15 |  | 28 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 172400411760 | 6.6 |  | 2020-01-21 |  |  | 2020-02-12 | W07-2020 |  | 2020-05-26 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.02.20 : RFIN sent 06.02.20 : 30.01.19 : Mobilisasi team, delivery material
395 |  | JAW-JT-BNR-0256 | 30574760031 | 140044109 | SIJERUK | ACTIVE | TB | 109.7012 | -7.3373 | 50 | 70/150/280 |  |  | Jl. Raya karangkobar km.10 Dusun Cantrikan RT.06 RW.02 Desa kendaga Kec.Banjarmangu Kab. Banjarnegara | EID | JAW-JT-BNR-0256 | SIJERUK BANJARNEGARA | COLO |  | CENTRAL | JATENG | Jawa Tengah | BANJARNEGARA | 6614397 | 2020-01-15 |  | 35 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | FO | 2020-01-27 |  | 522042745273 | 7,7 |  |  |  |  | 2020-02-19 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.02.20 : RFI sent 13.02.20 : actual RFI, collecting doc RFIN 06.02.20 : RBS Foundation done 30.01.19 : OG RBS Foundation, material ME Grounding tray dan mounting on site
NEW SPK |  | SUM-SS-MBL-1201 | 30734220031 | 070077104 | JAJARAN BARU MEGANG | BP2022 | SKP | 103°0.18.0'E | 2°57.8.6'S | 60 | 150/250/330 | 2022 | New site 2022 - P2 | Dusun 3 Desa Jajaran Baru 2 Kec Magang Sakti, Kab.Musi Rawas | HTI | SUM-SS-MBL-1201 | JAJARAN_BARU_II | COLO | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Musi Rawas | 6617983 | 2022-01-28 | 2022-01-28 | 71 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-01 | 2022-02-02 | 147800877433 | 6.6 |  | 2022-03-22 |  |  | 2022-04-09 | W15-2022 |  |  | STIP RELEASED, GO CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:04:22: RFIN 06:04:22-29:03:22: SRFI 27:03:22-20:03:22: ME OG KWH KOSONG 16:03:22-09:03:22: BTS PONDASI OG 06:03:22-09:02:22: STO RECALL 06:02:22: NEED REVIEW POWER HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | buffer apr
NEW SPK |  | SUM-LA-KLA-1148 | 0030740710031 | 101101123 | TANJUNG SENANG LAMPUNG | BP2022 | TB | 105°16.49.08'E | 5°20.52.73'S | 50 | 25/205/275 | 2022-2024 | New site 2022 - P1 | Jl. AMD RT.012 LK. I, Kel. Way Kandis, Kec. Tanjung Senang, Kota Bandar Lampung, Prov. Lampung | HTI | SUM-LA-KLA-1148 | TANJUNG_SENANG_WAY_KANDIS | COLO | TBG | West | SUMBAGSEL | Lampung | Kab. Lampung Selatan | 6617991 | 2022-01-28 | 2022-01-28 | 63 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-06-05 | W24-2022 | Jun-2022 | 2022-06-05 | W24-2022 | Jun-2022 | MW | 2022-02-02 | 2022-02-03 | 171202978132 | 6.6 |  | 2022-03-22 |  |  | 2022-04-01 | W14-2022 |  |  | NY STIP, ERM PROCESS | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01:04:22: RFIN 30:03:22-27:03:22: ME OG 23:03:22-20:03:22: PONDASI OG 16:03:22-13:03:22: NEED REVIEW RNP HUAWEI, RF OK 38 09:03:22-08:02:22: RND NOK NEED 50 METER 06:02:22-02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | buffer apr
947 |  | SUL-ST-LWK-1105 | 30714610031 | 2604941003 | LUWUK_UTARA_BUNGA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 122°54.17.52'E | 0°55.14.25'S | 60 | 20/70/230 | 2021 | BLITZKRIEG 2021 [NEW] | RT003/RW003 DESA BUNGA, KEC LUWUK UTARA, KAB BANGGAI | HTI | SUL-ST-LWK-1105 | LUWUK_UTARA_BUNGA | B2S | TBG | EAST | SULAWESI | Sulawesi Tengah | Kab. Banggai | 6617749 | 2021-10-25 |  | 182 | > 150 days | 2022-03-24 | W13-2022 | Mar-2022 | TBD | TBD | TBD | 2022-04-25 | W18-2022 | Apr-2022 | 2022-04-25 | W18-2022 | Apr-2022 | MW | 2022-02-21 | 2022-02-23 | 319500346250 |  |  | 2022-03-01 |  |  | 2022-04-25 |  |  |  | CME | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 25:04:22: RFIN 24:04:22: RFI, WAIT RFIN 20:04:22-13:04:22: ERECTION 10:04:22-06:04:22: CURRING 03:04:22-16:03:22: REBARRING 13:03:22-28:02:22: EXCAVATION 25:02:22: ANNOUNCEMENT GO UNTIL RFI 23:02:22: EXCAVATION 20:02:22-02:02:22: DELIVERY MATERIAL & PARALEL ON CHECK PERIZINAN 30:01:22-26:01:22: APD & REKOM DONE, RFC 19:01:22-16:01:22: WAITING APD & PARALEL REKOM 12:01:22-09:01:22: REKOM OG, REQ SOIL TEST DONE 05:01:22: IW CLEAR, REKOM OG 02:01:22-26:12:21: IW OG (10 KK,6 KK OG) 22:12:21-19:12:21: SITAC PREPARATION 16:12:21: PMO XL CONFIRMED GO SITAC 15:12:21-05:12:21: REVIEW TNP OK, NEED CONFIRMATION FROM XL TO CONTINUE SITAC PROCESS 01:12:21-10:11:21-08:11:21: RNP REVIEW OK, OG REVIEW TNP PROCESS 07:11:21: CANDIDAT VERIFICATION OG 03:11:21-31:10:21: SURVEY OG, PLAN SUBMIT KANDIDAT W1 NOV | apr
NEW SPK B2S |  | SUM-SS-LHT-1236 | 30730660031 | 0719221003 | SIRAH_PULAU | BP2022 | TB | 103°40.58.59'E | 3°43.39.37'S | 60 | 10/90/200 | 2022 | New site 2022 - P2 | Desa Sirah Pulau Kecamatan Merapi Timur Kabupaten Lahat Provinsi Sumatera Selatan | HTI | SUM-SS-LHT-1236 | SIRAH_PULAU | B2S | TBG | West | SUMBAGSEL | Sumatera Selatan | Kab. Lahat | 6617950 | 2022-01-25 | 2022-01-28 | 91 | 91 - 120 days | 2022-06-24 | W26-2022 | Jun-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-02-25 | 2022-03-02 | 147000760955 | [5 empty] | 2022-04-26 |  |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26:04:22: RFIN 24:04:22-20:04:22: ERECTION 17:04:22-10:06:22: BACKFIL 06:04:22-27:03:22: REBARRING 23:03:22-06:03:22: REKOM 28:02:22-23:02:22: IW CLEAR 20:02:22-16:02:22: IW OG 13:02:22: IW OG 09:02:22-30:01:22: SURVEY OG 28:01:22: SPK RECEIVED FROM EMAIL LMS
NEW SPK |  | JAW-JT-CLP-0567 | 30736060031 | 1433281023 | CILACAP CIPARI | BP2022 | TB | 108°44.26.23'E | 7°25.52.36'S | 49 | 90/220/320 | 2022-2024 | New site 2022 - P1 | Jl. Wijaya Kusuma No.45, Desa Mulyadadi RT.006 RW.002 Kec. Cipari, Kab. Cilacap Prov. Jawa Tengah | NOKIA | JAW-JT-CLP-0567 | PURWASARI_WANAREJA | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Cilacap | 6617993 | 2022-01-28 | 2022-01-28 | 87 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-07 | W15-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 525061585123 | 11 |  | 2022-03-08 |  |  | 2022-04-25 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-23:03:22: PLN CONNECTION 20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-20:02:22: NEED REVIEW CIVIL 16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
|  | JAW-BT-TNG-1529 | 30743240031 | 1320402001 |  | NEW COLO | TB | 106°37.49.66'E | 6°10.22.87'S | 21 | 120/240/350 |  | New COLO |  | EID | JAW-BT-TNG-1529 | PENGAIRAN SUKARASA BARU | COLO | TBG | Jabodetabek | JABODETABEK | Banten | Kota Tangerang | 6618126 | 2022-03-16 | 2022-03-16 | 36 | 31 - 60 days | 2022-04-15 | W16-2022 | Apr-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | [5 empty] | 2022-04-20 |  |  | 2022-04-21 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21:04:22: RFIN 20:04:22: STO DECLARE 20:04:22-20:03:22: ERM PROCESS 16:03:22: SPK RECEIVED | apr
NEW SPK |  | JAW-JT-KBM-0636 | 30735990031 | 140204104 | TUGU | BP2022 | SKP | 109°27.29.2'E | 7°37.57.65'S | 69 | 0/110/200 | 2022 | New site 2022 - P2 | Jl. Desa Tugu Prigi I,RT.03/05, Kec. Buayan, Kab. Kebumen Prov. Jawa Tengah | NOKIA | JAW-JT-KBM-0636 | TUGU_KEBUMEN | COLO | TBG | Central | JATENG | Jawa Tengah | Kab. Kebumen | 6617984 | 2022-01-28 | 2022-01-28 | 87 | 61 - 90 days | 2022-02-27 | W10-2022 | Feb-2022 | TBD | TBD | TBD | 2022-04-08 | W15-2022 | Apr-2022 | 2022-04-30 | W18-2022 | Apr-2022 | MW | 2022-02-02 | 2022-03-14 | 525031643459 | 11 |  | 2022-03-09 |  |  | 2022-04-25 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25:04:22: RFIN 24:04:22-17:04:22: SRFI LMS CHANGE TO NOKIA 13:04:22-27:03:22: SRFI, PLN CONENCTION 23:03:22-20:03:22: ME OG 16:03:22-13:03:22: WAIT PSB 09:03:22: PONDASI OG 06:03:22: READY TO STO 23:02:22-16:02:22: NEED REVIEW POWER 13:02:22-08:02:22: NEED REVIEW TNP HUAWEI 06:02:22: NEED REVIEW TNP ALITA 02:02:22: NEED REVIEW RNP HUAWEI 30:01:22: ESR REVIEW, NEED REVIEW RNP HUAWEI 28:01:22: SPK RELEASED | apr
|  | JAW-JI-KDR-4348 | 30740170031 | 1655171003 | PADANGAN_KAYEN_KIDUL | BP2022 | TB | 112°7.38.46'E | 7°43.38.24'S | 50 | 40/150/295 | 2022 | Newsite 2022 - P2 | Dusun Prambatan RT.003 RW.001 Desa Padangan Kecamatan Kayen Kidul Kabupaten Kediri Prop. Jawa Timur | HTI | JAW-JI-KDR-4348 | PADANGAN_KAYEN_KIDUL | B2S | TBG | East | JATIM | Jawa Timur | Kab. Kediri | 6618108 | 2022-03-07 | 2022-03-07 | 49 | 31 - 60 days | 2022-08-04 | W32-2022 | Aug-2022 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | MW | 2022-04-11 | 2022-04-13 | MG | [5 empty] | 2022-04-25 |  |  |  | SITAC | 38.RFI | 21.RFI | CURRENTLY NO ISSUE | 25:04:22: RFIN 24:04:22: ME OG 20:04:22-17:04:22: ERECTION 13:04:22: EXCAVATION 10:04:22-30:03:22: REKOM 27:03:22-23:03:22: IW CLEAR 20:03:22-16:03:22: IW OG 15:03:22-15:03:22: UNDER TNP 13:03:22-09:03:22: SURVEY OG & MITRA ASSIGNMENT 07:03:22: SPK RECEIVED
956 |  | JAW-JT-SKT-2147 | 30714510031 | 1448921003 | KOLONEL SUTARTO JEBRES | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110.8515 | -7.5563 | 30 | 90/210/330 | 2021 | BLITZKRIEG 2021 [NEW] | Kentingan Kulon RT 03 RW 10 Kelurahan Jebres Kecamatan Jebres Kota Surakarta Provinsi Jawa Tengah | EID | JAW-JT-SKT-2147 | KOLONEL SUTARTO JEBRES | B2S | TBG | CENTRAL | JATENG | Jawa Tengah | Kota Surakarta | 6617739 | 2021-10-22 |  | 138 | 121 - 150 days | 2022-03-21 | W13-2022 | Mar-2022 | TBD | TBD | TBD | 2022-03-21 | W13-2022 | Mar-2022 | 2022-03-21 | W13-2022 | Mar-2022 | MW | 2021-12-28 |  | 520521518427 | 7.7 |  |  |  |  | 2022-03-09 | W11-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:06:22: RFIN 06:03:22: ERECTION OG 28:02:22-20:02:22: CURRING TIME 16:02:22-13:02:22: REBARRING KETINGGIAN 14M 09:02:22-06:02:22: REBARRING KOLOM & BALOK 10.5M OF 14M 02:02:22-26:01:22: POURING, STACKING 7m 23:01:22: PREPARE POURING 19:01:22: CURRING TIME OG 16:01:22: REBARING OG 12:01:22: PONDASI OG, REBARRING 09:01:22: EXCAVATION OG 05:01:22-02:01:22: APD RELEASED, CME PREPARATION, CME START 9 JAN 29:12:21-12:12:21: SOIL TEST DONE, WAIT APD RELEASED 08:12:21: REALISASI IW OG 05:12:21-28:11:21: IW OG, PLAN SOIL TEST 6 DEC 24:11:21: NEED APPROVAL XL RF 25 M (26m (stacking 14m + pole 12m), OG PROCESS APPROVAL KARENA REJECT WARGA RF 30M 21:11:21-17:11:21: IW OG (16 KK) 14:11:21-10:11:21: TNP REVIEW OG 08:11:21: RNP REVIEW OG 07:11:21: SURVEY OG, HARD SITAC, PLAN SUBMIT KANDIDAT W1 NOV
941.8 |  | SUM-BB-PGP-0531 | 30714550031 | 0804341003 | TUATUNU_INDAH | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 106°4.46.34'E | 2°5.37.33'S | 50 | 105/190/350 | 2021 | BLITZKRIEG 2021 [NEW] | Jl. Kulan RT. 007 RW. 002 Kelurahan Jerambah Gantung, Kecamatan Gabek Kota Pangkal Pinang, Provinsi Kepulauan Bangka Belitung. | HTI | SUM-BB-PGP-0531 | TUATUNU_INDAH | B2S | TBG | WEST | SUMBAGSEL | Kepulauan Bangka Belitung | Kota Pangkal Pinang | 6617734 | 2021-10-21 |  | 130 | 121 - 150 days | 2022-03-20 | W13-2022 | Mar-2022 | TBD | TBD | TBD | 2022-02-21 | W09-2022 | Feb-2022 | 2022-02-28 | W10-2022 | Feb-2022 | MW | 2021-11-24 |  | 161001841798 | 6.6 |  |  |  |  | 2022-02-28 | W10-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28:02:22: RFIN 23:02:22-20:02:22: ERECTION 16:02:22: START ERECTION 13:02:22: BACKFILL OG 09:02:22-06:02:22: REBARING OG 02:02:22-30:01:22: CERUCUK OG 26:01:22-16:01:22: BOREPILE OG 12:01:22: OG PREPARE MATERIAL CERUCUK & BOREPILE 09:01:22: EXCAVATION OG 05:01:22: PERMIT OG 02:01:22-29:12:21: PARALEL REKOM & REVISED DESIGN OG 26:12:21: REVISED DESIGN OG 22:12:21-19:12:21: DESIGN PROCESS OG 15:12:21-28:11:21: DONE REQ SOIL TEST, WAIT FOR SOIL TEST KEPULAUAN 24:11:21-17:11:21: IW CLEAR, OG PROCESS LL MENGURUS SURAT TANAH 14:11:21: IW OG, KURANG 1 KK, PLAN IW DONE 17 NOV 10:11:21: BAN/BAK PROCESS OG & PARALEL IW OG 07:11:21: KANDIDAT APPROVED TNP RNP 03:10:21-24:10:21: NEW SPK NEW BUILT, HUNTING PROSES, PLAN SUBMIT KANDIDAT 4 NOV 2021
654 |  | NUS-NB-MTR-5391 | 30705460031 | 1806861003 | MONJOK BARAT RELOCATION | RELOCATION | TB | 116°6.28.18'E | 8°34.29.53'S | 30 | 80/190/300 | 2021 | RELOCATION | JL. Hos Cokroaminoto Gang Mawar No.14 RT.01 Lingkungan Cemara, Kel. Monjok Barat, Kec. Selaparang, Kota Mataram, Prop. Nusa Tenggara Barat | CAA | NUS-NB-MTR-5391 | MONJOK BARAT RELOCATION | B2S | TBG | East | BALINUSRA | Nusa Tenggara Barat | Kota Mataram | 6617595 | 2021-09-07 |  | 105 | 91 - 120 days | 2022-02-04 | W06-2022 | Feb-2022 | 2021-12-20 | W52-2021 | Dec-2021 | 2021-12-08 | W50-2021 | Dec-2021 | 2021-12-21 | W52-2021 | Dec-2021 | MW | 2021-11-12 |  | 441503329783 | 6.6 |  |  |  |  | 2021-12-21 | W52-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21:12:21: RFIN 19:12:21: RFI, WAIT FOR RFIN 15:12:21: ERECTION OG -2 SECTION, TERSTOP KARENA NGABEN & HUJAN 12:12:21: ERECTION OG 08:12:21: CURING TIME, START ERECTION 10 DEC 21 05:12:21: POURING OG 01:12:21: REBARING OG, MATERIAL ONSITE DONE 28:11:21-24:11:21: REBARING OG, PLAN MOS 30 NOV (DELAY MATERIAL, TRUK RUSAK) 21:11:21: LANTAI KERJA OG, PLAN MOS 23 NOV 17:11:21: EXCAVATION OG 14:11:21: BOUWPLANK OG, PLAN EXCAVATION & DELIVERY MATERIAL ON 15 NOV 10:11:21: SOIL TEST DONE, OG PROCESS DESIGN APD 07:11:21: REKOM CLEAR, SOILTEST OG, CME OG REQUEST GDL 03:11:21: REKOM OG, PLAN REKOM CLEAR 4 NOV 23:10:21: IW CLEAR, PREPARE ESKALASI SITAC, REKOM OG, PLAN REKOM CLEAR 5 NOV 20:10:21: IW CLEAR, PROSES REALISASI IW PLAN REKOM DAN SOILTEST W1 NOV 17:10:21-06:10:21: KANDIDAT APPROVE, IW OG, PLAN SOSWAR 14 OCT 2021 29:09:21: HUNTING SESUAI ARAHAN DONE, SUBMIT KANDIDAT DONE, PROSES REVIEW RNP 26:09:2021 - 22:09:21: REHUNTING SESUAI ARAHAN, PLAN SUBMIT KANDIDAT 27 SEP 2021 19:09:21: 15:09:21: 13:09:21: SPK RELEASED HUNTING OG
528 |  | JAW-JT-SKT-2146 | 30700500031 | 1447851003 | DR RAJIMAN PAJANG | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°47.24.52'E | 7°34.4.38'S | 35 | 45/120/185/330 | 2021 | BLITZKRIEG 2021 [NEW] |  | EID | JAW-JT-SKT-2146 | DR RAJIMAN PAJANG | B2S | TBG | CENTRAL | JATENG | Jawa Tengah | Kota Surakarta | 6617569 | 2021-08-27 |  | 168 | > 150 days | 2022-01-24 | W05-2022 | Jan-2022 | 2021-12-15 | W51-2021 | Dec-2021 | 2022-01-24 | W05-2022 | Jan-2022 | 2022-02-10 | W07-2022 | Feb-2022 | MW | 2021-12-28 |  | 520512091107 | 7.7 |  |  |  |  | 2022-02-11 | W07-2022 |  |  | CME | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11:02:22: RFIN 09:02:22-26:01:22: SRFI, PLN CONNECTION 23:01:22: CURRING TIME, PREPARE ERECTION 19:01:22: POURING OG 16:01:22: REBARING OG 12:01:22: PONDASI OG, REBARRING 09:01:22: EXCAVATION OG 05:01:22-02:01:22: APD RELEASED, CME PREPARATION 29:12:21-26:12:21: SOIL TEST & REKOM DONE, WAIT APD RELEASED 22:12:21: WAIT SOIL TEST DONE & APD RELEASED & PARALEL REKOM LURAH CAMAT 15:12:21: REALISASI IW, PARALEL REQ SOIL TEST 12:12:21: IW OG (5KK) 10:12:21: RNP TNP VALIDATION KANDIDAT N 08:12:21-05:12:21: KANDIDAT J GAGAL, KONFLIK KELUARGA, OG REHUNTING, PLAN SUBMIT KANDIDAT 9 DEC 01:12:21-30:11:21: KANDIDAT K&L REEJCT WARGA, OG IW KANDIDAT J 28:11:21-24:11:21: KANDIDAT K&L APPROVED, IW OG ON KANDIDAT K (TOTAL KK 20) 21:11:21: KANDIDAT H&I REJECT WARGA, OG PROCESS REVIEW RNP TNP KANDIDAT J,K,&L 17:11:21: IW OG PADA KANDIDAT H & I, ANTENA HEIGHT 25 M MONOPOLE + 1 M 17:11:21-16:11:21: KANDIDAT G REJECT BY WARGA, OG PARALEL REVIEW RNP TNP KANDIDAT H & I 14:11:21: UNDER TNP REVIEW KANDIDAT G 10:11:21-07:11:21: REHUNTING OG 03:11:21: KANDIDAT F TNP NOK BY TNP XL, PROSES REHUNTING 31:10:21: KANDIDAT NOK BY TNP XL, PROSES REHUNTING 27:10:21 - 23:10:21: IW OG HARD SITAC, SOSWAR ON SCHEDULE 25 OCT, PLAN IW CLEAR 30 OKT 21 20:10:21: IW OG, PLAN SOSWAR 25 OCT PLAN IW CLEAR W1 NOV 17:10:21-13:10:21: KANDIDAT C GAGAL IW, VALIDASI KANDIDAT D DONE, IW OG 10:10:21-06:10:21: IW OG, MASIH LURANG 2 KK LAGI, PLAN SONDIR 14 OCT 29:09:21: IW OG, MASIH KURANG 17 KK dari 25 KK, PLAN SONDIR 1 OCT 26:09:21-19:09:21: VALIDASI DONE, IW OG 15:09:21: 13:09:21: 08:09:21: VALIDASI DONE, IW OG PROSES PENDEKATAN 3 KK DARI 18 KK, PLAN CLEAR 20 SEP 2021 06:09:21: PLAN SUBMIT KANDIDAT 6 SEP 2021 01:09:21: HUNTING OG, PLAN SUBMIT KANDIDAT 7 SEP 08:20:2021: SPK RELEASED 27 AUG, HUNTING OG
522 |  | SUL-SR-MJN-0175 | 30695750031 | 2901171003 | MALUNDA_MALIAYA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 118°52.38.44'E | 2°55.26.9'S | 60 | 30/120/190 | 2021 | BLITZKRIEG 2021 [NEW] | MALIAYA UTARA RT 000 RW 000, DESA MALIAYA, KEC. MALUNDA, KAB. MAJENE, PROV. SULAWESI BARAT | HTI | SUL-SR-MJN-0175 | MALUNDA_MALIAYA | B2S | TBG | East | SULAWESI | Sulawesi Barat | Kab. Majene | 6617465 | 2021-08-10 |  | 121 | 121 - 150 days | 2022-01-07 | W02-2022 | Jan-2022 | 2021-12-17 | W51-2021 | Dec-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-12-10 | W50-2021 | Dec-2021 | MW | 2021-10-03 | [7 empty] | 2021-12-09 | W50-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09:12:21: RFIN 08:12:21-05:12:21: RFI, WAITING FOR RFIN 01:12:21-28:11:21: SRFI, OG PLN CONNECTION, PLAN RFI 14 DEC 21 24:11:21-23:11:21: OVERBLAST, OG PROCESS PENGADAAN MATERIAL 21:11:21-17:11:21: SRFI, WAIT PLN CONNECTION, PENARIKAN JARINGAN (200-250 M), WAIT SURAT PLN SHARING INVEST (BANGUN TIANG & NARIK JARINGAN KARENA JARINGAN TIDAK TERSEDIA), OG FU PLN, PLAN MENDAPAT JAWABAN PLN 22 NOV 14:11:21: OG PEKERJAAN PENARIKAN JARINGAN PLN, PLAN RFI 17 NOV 10:11:21-03:11:21: ERECTION OG, PLAN RFI 13 NOV, KENDALA CUACA BURUK 31:10:21: POURING DONE, START ERECTION 1 NOV 21 27:10:21: POURING DONE, PLAN START CME 30 OCT 23:10:21: REBARING OG, PLAN POURING 27/28 OCT 21 17:10:21: 13:10:21: MENUNGGU SURVEY PIHAK PU, PARALEL PERSIAPAN MATERIAL BESI, TEAM ON SITE 10:10:21: EXCAVATION TERTUNDA KARENA HARUS MENUNGGU SURVEY DARI KEMINFO, PLAN SURVEY 13 OCT 06:10:21: BOWPLANK OG, PLAN START GALIAN MENUNGGU TIM EXCAV ON SITE PLAN 10 OCT 2021 04:10:21: PREPARE TIM CME, MENUNGGU MATERIAL GALIAN, PLAN START GALIAN 13 OCT 29:09:21: APD&DESIGPACK, MENUNGGU GDL RELEASED, PLAN GALIAN 7 OCT 26:09:21-22:09:21: REKOM LURAH DONE, REKOM CAMAT OG 15:09:21: IW CLEARE, PRSOES PENGAJUAN SOLTEST 16 SEP 2021 13:09:21: IW OG, SOSWAR 15 KK 08:09:21: BA KETENTUAN TINGGI TOWER DONE SUBMIT, VALIDASI DONE, IW OG 15 kk 06:09:21: NEED BA TERKAIT TINGGI TOWER YANG DIIZINKAN DI AREA TERSEBUT, PLAN SUBMIT BA 7 SEPT 01:09:21: 30:08:21: NEED PERUBAHAN KETINGGIAN KANDIDAT, PERATURAN PERDA SETEMPAT HANYA BOLEH MEMBANGUN MAX TINGGI TOWER 52M 25:08:21: VALIDASI UNDER RNP REVIEW 22:08:21: PLAN SUBMIT KANDIDAT 26 AUG 18:08:21: 08:12:2021 : SPK NEW BUILD RELEASED, HUNTING PROSES
527 |  | JAW-JT-KRG-2137 | 30696720031 |  |  | ACTIVE - BLITZKRIEG 2021 [NEW] |  | 111°3.51.48'E | 7°39.34.92'S | 50 | 90/210/330 | 2021 |  | Mendalan RT 002 RW 005 Desa Koripan Kecamatan Matesih Kabupaten Karanganyar Provinsi Jawa Tengah | EID | JAW-JT-KRG-2137 | TAWANGMANGU MATESI KORIPAN | B2S | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Karanganyar | 6617448 | 2021-08-09 |  | 91 | 91 - 120 days | 2022-01-06 | W02-2022 | Jan-2022 | 2021-12-07 | W50-2021 | Dec-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-11-16 | W47-2021 | Nov-2021 | MW | 2021-10-21 |  | 526550148393 | 7.7 |  |  |  |  | 2021-11-08 | W46-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:11:21: RFIN DONE 07:11:21-03:11:21: RFI, WAIT FOR RFIN, PLAN RFIN 8 NOV 31:10:21-27:10:21: SRFI 23:10:21: ERECTION OG, PLAN RFI ..., PSB RECIVED ON CHECK 20:10:21: CURRING TIME OG, PLAN ERECTION 25 OCT, NEED SK PLN 17:10:21-13:10:21: EXCAVATION OG, PLAN PENGECORAN 20 OCT 2021 10:10:21: TIM ON SITE, PLAN GALIAN 13 OCT 06:10:21-04:10:21: BOWPLANK OG, PLAN START GALIAN 8 OCT 2021 29:09:21-22:09:21: PROSES APD, PLAN START CME END OF SEPT 19:09:21: SOILTEST OG, PARALEL REALISASI REKOM LURAH CAMAT 15:09:21: 13:09:21: IW CLEAR, PROSES KORDINASI DENGAN PEMDA TERKAIT ISSUE OPSIC 08:09:21: REKOM OG, PARALEL SOILTEST 06:09:21: KANDIDAT APPROVE TNP & RNP PROSES IW OG 10:08:21 : SPK RETURN BY XL PERUBAHAN DESIGN 09:08:21 : SPK NEW BUILD RELEASED
525 |  | JAW-JT-MKD-1143 | 30692140031 | 1446911003 | MUNTILAN RELOCATION | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 110°18.21.04'E | 7°36.47.83'S | 60 | 50/160/310 | 2021 |  | Dusun Jumoyo Kidul RT 003 RW 002 Desa Jumoyo Kecamatan Salam Kabupaten Magelang Provinsi Jawa Tengah | EID | JAW-JT-MKD-1143 | MUNTILAN RELOCATION | B2S | TBG | CENTRAL | JATENG | JAWA TENGAH | Kab. Magelang | 6617428 | 2021-08-05 |  | 107 | 91 - 120 days | 2022-01-02 | W02-2022 | Jan-2022 | 2022-01-01 | W01-2022 | Jan-2022 | 2022-01-02 | W02-2022 | Jan-2022 | 2021-11-30 | W49-2021 | Nov-2021 | MW | 2021-11-24 |  | 521541397291 | 7.7 |  |  |  |  | 2021-11-20 | W47-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20:11:21: RFIN 17:11:21: ERECTION OG, PLAN SRFI 19 NOV, PLN 22, RFI 25 NOV 14:11:21: CURRING TIME OG, PLAN RFI 25 NOV 10:11:21: REBARING OG 07:11:21: BOREPILE OG 03:11:21: EXCAVATION OG 31:10:21-23:10:21: REKOM LURAH CAMAT OG, PARALEL SOIL TEST 20:10:21-13:10:21: IW CLEAR, CAPEX APPROVE, PERSIAPAN REKOM LURAH CAMAT PLAN REKOM OG W2 OCT 26:09:21: IW CLEAR, PLAN REKOM 25 SEP 2021 19:09:21: 15:09:21: PROSES IW MASIH KURANG 2 KK, RENEGO KOMPENSASI DIBANTU DENGAN PEJABAT SETEMPAT PLAN CLEAR 22 SEP 2021 13:09:21: 08:09:21: IW OG, RENEGOSIASI KOMPENSASI WARGA 06:09:21: IW OG KURANG 2 KK DARI TOTAL KK 25 KK 06:09:21: 01:09:21: KANDIDAT B SUBMIT DONE, IW OG 25 KK, PROSES SOSIALISAI WARGA 30:08:21: REHUNTING, GAGAL IW, PLAN SUBMIT CANDIDAT 1 SEPT 22:08:21: 18:08:21: 16:08:21: IW OG, PROSES PERIZINAN WARGA MASIH KURANG 4 KK lagi dari total 32 KK 10:08:21: VALIDASI RNP & TNP DONE, KANDIDAT A GO, PROSES NEGOSIASI IW OG 09:08:21 : SPK NEW BUILD RELEASED, HUNTING PROSES
531 |  | JAW-JT-TGL-2607 | 30695970031 | 140459104 | PEGADINGAN | ACTIVE - BLITZKRIEG 2021 [NEW] | SKP | 109°10.33.17'E | 6°55.19.27'S | 60 | 75/185/235/325 | 2021 |  | Jl. Desa Tarup RT 03/ RW.02 Kel. Tarup / Kec. Tarup Tegal | EID | JAW-JT-TGL-2607 | JOKO TINGKIR TARUB | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Tegal | 6617414 | 2021-08-04 |  | 27 | < 30 days | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-04 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | MW | 2021-08-10 |  | 522521757456 | 7.7 |  |  |  |  | 2021-08-31 | W36-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:30:2021: RBS/BTS PONDASI OG 08:25:2021: MAPPING MITRA CME 08:22:2021: 08:18:2021: CME PREPARATION 08:16:2021: STO DECLARE 13 AUG 08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES
530 |  | JAW-JB-DPK-0484 | 30695790031 | 1261081023 | TAPOS DEPOK | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 106°53.2.08'E | 6°24.40.1'S | 30.00.00 | 40/130/220/310 | 2021 |  | Kel. Cilangkap Kp. Setu RT.004 RW.008, Kec. Tapos, Kota Depok Prov. Jawa Barat | EID | JAW-JB-DPK-0484 | DEPOK TAPOS CILANGKAP | COLO | TBG | JABO | JABODETABEK (INNER) | Jawa Barat | Kota Depok | 6617408 | 2021-08-03 |  | 20 | < 30 days | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-03 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | 2021-09-02 | W36-2021 | Sep-2021 | MW | 2021-08-10 |  | 538722715028 | 6.6 |  |  |  |  | 2021-08-23 | W35-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:22:2021 RFI 08:22:2021: SRFI, POWER CONNECTION PROSES 08:18:2021: ME OG 08:16:2021: STO DECLARE, RBS/BTS FOUNDATION 08:09:2021: 08:04:2021 : SPK COLO RELEASED, ERM PROSES
529 |  | JAW-JI-BTU-4114 | 30692030031 | 1652511003 | BUMIAJI_PANDANREJO | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 112°32.55.47'E | 7°51.50.77'S | 40 | 30/140/245 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun Sumbersari RT077 RW012 Desa Giripurno Kecamatan Bumiaji Kota Batu Provinsi Jawa Timur | HTI | JAW-JI-BTU-4114 | BUMIAJI_PANDANREJO | B2S | TBG | East | JATIM | Jawa Timur | Kota Batu | 6617420 | 2021-08-03 |  | 119 | 91 - 120 days | 2021-12-31 | W53-2021 | Dec-2021 | 2021-12-30 | W53-2021 | Dec-2021 | 2021-11-20 | W47-2021 | Nov-2021 | 2021-11-30 | W49-2021 | Nov-2021 | MW | 2021-10-26 | 2021-10-27 | 513031073530 | 6.6 |  |  |  |  | 2021-11-30 | W49-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30:11:21: RFIN 28:11:21: ERECTION DONE, ME OG & PLN PROCESS 24:11:21: ERECTION OG, PLAN RFI 30 NOV 21:11:21-17:11:21: CURRING TIME OG 14:11:21: REBARING OG 10:11:21-07:11:21: EXCAVATION OG 03:11:21: BOUWPLANK OG, STAR CME 4 NOV 31:10:21: RFC, OG CME PREPARATION 27:10:21: REALISASI IW, SOILTEST OG 23:10:21: IW CLEAR, CANDIDAT APPROVED, OG CIRCULAR SITAC 17:10:21: TNP REVIEW, PARALEL IW OG 13:10:21: UNDER REVIEW RNP, PENGAJUAN KANDIDAT SESUAI ARAHAN DONE NEED HASIL VALIDASI RNP TNP 10:10:21-29:09:21: REHUNTING OG 3 KANDIDAT ARAHAN RNP, HARD KANDIDAT KARENA KAWASAN PADAT PENDUDUK, PLAN SUBMIT KANDIDAT 15 OCT 2021 26:09:21: KANDIDAT E NOK KARENA FAR FROM NOM REHUNTING SESUAI ARAHAN PAK RAHMAT 22:09:21: KANDIDAT E DONE SUBMIT UNDER REVIEW RNP 15:09:21: REHUNTING OG, PLAN SUBMIT KANDIDAT 20 SEP 2021 14:09:21: KANDIDAT GAGAL IW DARI 18 KK MENOLAK 4 KK 13:09:21: 08:09:21: VALIDASI KANDIDAT RNP & TNP OK, LANJUT IW OG 06:09:21: KANDIDAT B GAGAL IW, PROSES REVALIDASI UNDER REVIEW RNP 01:09:21: SUBMIT KANDIDAT DONE, REVIEW TNP RNP DONE, KANDIDAT B GO SITAC IW OG 30:08:21: REVIEW TSSR, PLAN SUBMIT CANDIDAT 30 AUG 25:08:21: 22:08:21: REHUNTING SESUAI ARAHAN PAK RAHMAT, PLAN SUBMIT KANDIDAT 30 AUG 18:08:21: HASIL VALIDASI RNP KANDIDAT NOT OK, 16:08:21: 10:08:21 : 09:08:21 : SPK NEW BUILD RELEASED, HUNTING PROSES
521 |  | JAW-JI-BTU-4117 | 30692040031 | 1652521003 | BUMIAJI_TULUNGREJO | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 112°31.45.51'E | 7°48.41.93'S | 40 | 105/175/245 | 2021 | BLITZKRIEG 2021 [NEW] | Dusun Gerdu RT 003 RW 017 Desa Tulungrejo Kec. Bumiaji Kota Batu Prov. Jawa Timur | HTI | JAW-JI-BTU-4117 | BUMIAJI_TULUNGREJO | B2S | TBG | East | JATIM | Jawa Timur | Kota Batu | 6617420 | 2021-08-03 |  | 120 | 91 - 120 days | 2021-12-31 | W53-2021 | Dec-2021 | 2021-12-30 | W53-2021 | Dec-2021 | 2021-10-30 | W44-2021 | Oct-2021 | 2021-12-10 | W50-2021 | Dec-2021 | MW |  |  | 513031070006 | 6.6 |  |  |  |  | 2021-12-01 | W49-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01:12:21: RFIN 28:11:21: CURRING TIME, PLAN START ERECTION 29 NOV 24:11:21: PREPARE POURING, PLAN POURING START 25 NOV 21 21:11:21-17:11:21: REBARRING OG 14:11:21: EXCAVATION DONE, FORMWORK (LANTAI KERJA) OG, 10:11:21: IW & REKOM DONE, PREPARE RFC, PLAN RFC 11 NOV 07:11:21: REALISASI IW DONE, SIGN LURAH DONE, SIGN CAMAT TARGET LUSA DONE 03:11:21: PROSES LEGAL DONE, OG FOLLOW UP BPN 4 NOV 31:10:21: REVIEW DONE, PROSES IW DAN REVIEW TERKAIT LEGALITAS (Legal LL, NIK KTP LL beda yg di IJB dan sekarang) 27:10:21: CANDIDAT APPROVED RNP, OG REVIEW, PLAN SUBMIT EKSKALASI SITAC 29 OCT 23:10:21: IW CLEAR, PERGESERAN KANDIDAT 19M DARI SBLMNYA&NEED APPROVAL&PLAN RESUBMIT 25 OCT, PARALEL KOORD LEGAL DOC LAHAN&AJB, PLAN SUBMIT EKSKALASI SITAC 26 OCT 20:10:21-17:10:21: SENGKETA PEMILIH AHLI WARIS, COMMCASE PEROSES REHUNTING KANDIDAT BARU PLAN SUBMIT 21 OCT 13:10:21: CLEARING DOKUMEN DARI NOTARIS ANTARA PIHAK AHLI WARIS, PLAN SURAT RELEASED 19 OCT 2021 10:10:21-04:10:21: RFC DONE, CME START MASIH MENUNGGU OPSIC RELEASED 26:09:21-19:09:21: APD PROSES & DESIGN, PLAN RFC 2 OCT 2021 15:09:21: REALISASI REKOM LURAH CAMAT, APD PROSES ON REQUEST 13:09:21: 08:09:21: 06:09:21: PROSES REKOM LURAH CAMAT, PARALEL PENGAJUAN SOILTEST 01:09:21: SUBMIT KANDIDAT UNDER REVIEW TNP, KANDIDAT A GAGAL IW 30:08:21: 25:08:21: IW OG, 22:08:21: VALIDASI TNP OK 18:08:21: HASIL VALIDASI RNP KANDIDAT OK, WAITING VALIDASI TNP BY ALITA 16:08:21: 10:08:21 : 09:08:21 : SPK NEW BUILD RELEASED, HUNTING PROSES
524 |  | JAW-JB-TSM-4130 | 30692020031 | 1272511003 | MANGKUBUMI_CIPAWITRA | ACTIVE - BLITZKRIEG 2021 [NEW] | TB | 108°9.16.7'E | 7°19.37.99'S | 40 | 15/100/180 | 2021 | BLITZKRIEG 2021 [NEW] | Gn.Bango RT002 RW006 Kel.Cipawitra Kec.Mangkubumi Kota Tasikmalaya Prov Jabar | HTI | JAW-JB-TSM-4130 | MANGKUBUMI_CIPAWITRA | B2S | TBG | CENTRAL | JABAR | Jawa Barat | Kota Tasikmalaya | 6617420 | 2021-08-03 |  | 153 | > 150 days | 2021-12-31 | W53-2021 | Dec-2021 | 2021-12-30 | W53-2021 | Dec-2021 | 2022-01-01 | W01-2022 | Jan-2022 | 2022-01-03 | W02-2022 | Jan-2022 | MW | 2021-12-08 |  | 532413348556 | [5 empty] | 2022-01-03 | W02-2022 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03:01:22: RFIN 02:01:22-31:12:21: RFI, WAIT RFIN 29:12:21-26:12:21: ERECTION OG 22:12:21: CURRING TIME OG 19:12:21: REBARING OG, PLAN POURING 21 DES 15:12:21: LANTAI KERJA OG 12:12:21-08:12:21: EXCAVATION OG 05:12:21-01:12:21: TEAM PREPARATION CME, START CME 6 DEC 28:11:21: SOIL TEST DONE, OG DRAW DESIGN, PLAN RFI 31 DEC 24:11:21-17:11:21: NEED APPROVAL GM, RFC ACTUAL, OPSIC OG, PROSES LAGI UBAH OUTCELL JADI INCELL, PLAN GM 3 BULAN MENUNGGU IMB TERBIT 14:11:21: FINALISASI DENGAN PEMKOT 15 NOV, DIBANTU OLEH LSM TASIK, PLAN PENGGUNAAN GM, PENURUNAN KETINGGIAN DARI 52 TO 42 NY APPROVED TIM XL 10:11:21: PLAN PENGGUNAAN GUYEDMASK, WAIT APPROVAL PEMKOT PLAN FINAL APPROVAL 10 NOV 21 07:11:21-17:10:21: UNDER REVIEW RNP TERKAIT PENGAJUAN PENGGUNAAN GUYEDMASK, PENURUNAN KETINGGAN DARI 52 KE 42 NEED APPROVAL TEAM XL PRALEL MENUNGGU APPROVAL PEMKOT UNTUK IMPLEMENTASI 13:10:21: UNDER RNP REVIEW, NEED APPROVAL PENGAJUAN GUYED MASK 10:10:21: 26:09:21: IW OG, MASIH KURANG 2 KK DARI 14 KK, PLAN SOSWAR 10 OCT 2021 22:09:21-15:09:21: IW OG, SOSIALISASI WARGA DI UNDUR DIHARI SABTU 18 SEP 2021 13:09:21: 08:09:21: IW OG PLAN SELASA MALAM NGUMPUL SOSWAR 06:09:21: KANDIDAT APPROVE RNP AND TNP, IW OG 01:09:21: NOM OUTCELL, PROSES REHUNTING KANDIDAT 25:08:21: REKOM 22:08:21: PLAN SUBMIT KANDIDAT REVIEW RNP & TNP 18:08:21: 16:08:21: 10:08:21 : 09:08:21 : SPK NEW BUILD RELEASED, HUNTING PROSES
504 |  | JAW-JT-BYL-0238 | 30689770031 | 1442442001 | IBS BLUE KALIMATI JUWANGI | ACTIVE - BLITZKRIEG | TB | E°41.43.22'E | S°14.26.2'S | 50 | 20/90/170/270 | 2021 |  | Desa Krobokan RT.019 RW.001 Kec.Juwangi, Kab.Boyolali Prov. Jawa Tengah | EID | JAW-JT-BYL-0238 | ALHUDA KROBOKAN | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Boyolali | 6616739 | 2021-07-12 |  | 46 | 31 - 60 days | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-12 | W33-2021 | Aug-2021 | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-11 | W33-2021 | Aug-2021 | MW |  |  | 525520287756 | 7.7 |  |  |  |  | 2021-08-27 | W35-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:25:2021: PLN CONNECTED, COLLECT DOKUMENTASI RFI 08:22:2021 : 08:18:2021: 08:16:2021: 08:10:2021: SRFI, PROSES REGISTER PLN, SURVEY DONE RE PLAN 23 AUG 2021 08:09:2021: 08:04:2021: 08:02:2021 : SRFI, SK PLN RELEASED, PLN PROSES REGISTER 07:29:21: PONDASI DONE, ME PG, SK PLN NY RELEASED 07.26.21 : 07.22.21 : 07:19:21 SPK REACTIVE, CME PREPARATION 03.05.21 : SPK return by XL
503 |  | JAW-JT-TGL-2613 | 30689780031 | 1441822004 | IBS SIGEDONG | ACTIVE - BLITZKRIEG | TB | E°7.34.28'E | S°12.45.94'S | 50 | 145/240/320 | 2021 |  | Jl. Dukuh Ratna, Desa Sigedong RT.003 RW.002 Kec.Bumijawa, Kab. Tegal Prov. Jawa Tengah | EID | JAW-JT-TGL-2613 | SIGEDONG BUMIJAWA | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Tegal | 6616739 | 2021-07-12 |  | 35 | 31 - 60 days | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-12 | W33-2021 | Aug-2021 | 2021-08-11 | W33-2021 | Aug-2021 | 2021-08-11 | W33-2021 | Aug-2021 | MW |  |  | 522591209411 | 6.6 |  |  |  |  | 2021-08-16 | W34-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:16:2021: 08:10:2021: SRFI, BPUJL PAID, CONNECTION PROSESS 08:09:2021: SRFI, PLN PROSES REGISTER 08:04:2021: 08:02:2021 : ME OG, SK PLN RELEASED 07:29:2021 : PONDASI DONE, ME OG, SK PLN NY RELEASED 07.26.21 : 07.22.21 : 07:19:21 SPK REACTIVE, CME PREPARATION 03.05.21 : SPK return by XL
650 |  | SUM-LA-MET-0656 | 30688690031 | 100630109 | BUDUT METRO | ACTIVE - RELOCATION | TB | E°18.7.52'E | S°7.5.2'S | 39 | 110/180/350 |  | RELOCATION | Jl. Anggrek RT. 009 RW. 002 Kel. Metro Kec. Metro Pusat Kota Metro Lampung | HTI | SUM-LA-MET-0656 | METRO RELOCATION | COLO | TBG | WEST | LAMPUNG | Lampung | kota metro | 6617226 | 2021-06-22 |  | 53 | 31 - 60 days | 2021-07-22 | W30-2021 | Jul-2021 | 2021-08-14 | W33-2021 | Aug-2021 | 2021-07-22 | W30-2021 | Jul-2021 | 2021-07-22 | W30-2021 | Jul-2021 | MW |  |  | 172000856747 | 6.6 |  |  |  |  | 2021-08-14 | W33-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:10:21: 08:09:21: Power Connection Proses 08:04:21: 08:02:21: 07:29:21: SRFI, PLN CONNECT HOLD BY XL 07:19:2021 : Mechanical & Electrical Proses 07:19:2021: RBS dan BTS Foundation, SK PLN NY RELEASED 07:15:2021 : CME PREPARATION
648 |  | JAW-JB-BDG-4215 | 30682840031 | 120481109 | LEUWI GAJAH | ACTIVE - RELOCATION | MSI | E°33.56.88'E | S°54.0.04'S | 30 | 45/120/300 |  | RELOCATION | Jl.Cibeureum Komplek Saptamarga RT.4 RW.4 Kel.Campaka Kec.Andir, Kota Bandung | HTI | JAW-JB-BDG-4215 | BANDARA HUSEIN SASTRANEGARA RELOCATION | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kota Bandung | 6617180 | 2021-04-29 |  | 32 | 31 - 60 days | 2021-05-29 | W22-2021 | May-2021 | 2021-05-27 | W22-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-27 | W22-2021 | May-2021 |  |  |  | 535556193516 | 6.6 |  |  |  |  | 2021-05-31 | W23-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.31.2021 : Power Connection Process, Plan Connect PLN W1 Jun 05.26.2021 : 05.23.2021 : ME OG, PSB Released, OG Register 05.17.2021 : 05.10.2021 CME Preparation
647 |  | JAW-JB-BDG-4214 | 30682850031 | T000313 | IPTN | ACTIVE - RELOCATION | SKP | 107°34.22.8'E | 6°53.42.14'S | 30 | 90/210/330 |  | RELOCATION | Jl. Agusta RT/RW 04/08, Komplek Sukaraja II, Lanud Husein Sastranegara, kota Bandung | HTI | JAW-JB-BDG-4214 | PASIRKALIKI SUKARAJA RELOCATION | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Kota Bandung | 6617179 | 2021-04-28 |  | 30 | < 30 days | 2021-05-28 | W22-2021 | May-2021 | 2021-05-27 | W22-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-27 | W22-2021 | May-2021 |  |  |  | 535812217807 | 6.6 |  |  |  |  | 2021-05-28 | W22-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.26.2021 : Power Connection Prosess, Plan RFI W1 Jun 05.23.2021 : ME OG, PSB Released, OG Register 05.17.2021 : 05.10.2021 CME Preparation
500 |  | JAW-JT-JPA-0701 | 30681490031 | 1443752004 | IBS SURODADI KEDUNG | ACTIVE - BLITZKRIEG | TB | E°39.1.47'E | S°41.18.6'S | 50 | 60/200/300 | 2021 |  | Surodadi RT 012 RW 04 Desa Surodadi Kecamatan Kedung kabupaten Jepara, Jawa Tengah | EID | JAW-JT-JPA-0701 | GANG JAMBU SURODADI | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Jepara | 6616739 | 2021-03-18 |  | 137 | 121 - 150 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW | 2021-11-16 |  | 520022060900 | 7.7 |  |  |  |  | 2021-08-02 | W32-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:02:2021: 07.29.2021: PLN Proses Multiguna Plan W1 Aug 07.26.2021 : BPUJL Paid, Proses Connect PLN Plan Connect 29 Jul 07.22.2021: 07:19:2021: Power Connection Prosess, waiting connect PLN 07:15:2021 : 07:12:2021: ME & Grounding System 07.08.2021 : RBS/BTS Foundation 07.05.2021 : 07.01.2021 : comcase, plan solve 5 Jul, plan cme start 7 Jul, revisi plan RFI 20 Jul 06.28.2021 : 06.24.2021 : CME Hold Comecase issue, proses approval pengajuan kompensasi, plan close end JUN revisi Plan RFI W3 JUL 06.21.2021 : 06.07.2021 : 06.07.2021 : 06.02.2021 : 05.26.2021 : 05.23.2021 : 05.17.2021 : 05.10.21 : 05.06.2021 : CME Hold karena Issue Access Block by LO 05.03.2021 CME PREPARATION
499 |  | JAW-JT-KDS-0858 | 30681430031 | 1439982007 | IBS TENGGALES | ACTIVE - BLITZKRIEG | TB | E°53.32.82'E | S°48.19.48'S | 40 | 0/90/180/270 | 2021 |  | Dukuh Rau RT.003 RW. 004, Desa Tenggeles, Kecamatan Mejabo, Kabupaten Kudus, Provinsi Jawa Tengah | EID | JAW-JT-KDS-0858 | KALANGAN TENGGELES | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Kudus | 6616739 | 2021-03-18 |  | 104 | 91 - 120 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW | 2021-11-16 |  | 520013335752 | [5 empty] | 2021-06-30 | W27-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.28.2021 : Power Connection Process, plan connect multiguna 29 Jun 06.24.2021 : 06.21.2021 :06.17.2021 : Power Connection Process, Registrasi PLN NY Released revisi plan RFI 25 Jun 06.14.2021 : 06.10.2021 : ME Grounding System Process 06.07.2021 : 06.02.2021 : Comecase Open, CME Start, BTS RBS Foundation 05.26.2021 : 05.23.2021 : 05.23.2021 : 05.19.2021 : 05.17.2021 : 05.10.21 : 05.06.2021 : CME Hold karena Issue Access Block by LO 05.03.2021 CME PREPARATION
490 |  | JAW-JT-BLA-0139 | 30681540031 | 1441172004 | IBS NGUMBUL TODANAN | ACTIVE - BLITZKRIEG | TB | E°8.19.36'E | S°57.4.64'S | 50 | 100/140/255 | 2021 |  | Dukuh Manggir RT.003 RW.01, Desa Ngumbul, Kecamatan Todanan, Kabupaten Blora, Provinsi Jawa Tengah | EID | JAW-JT-BLA-0139 | BADAR NGUMBUL | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Blora | 6616739 | 2021-03-18 |  | 82 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 520071594307 | 7.7 |  |  |  |  | 2021-06-08 | W24-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.02.2021 : 05.31.2021 : 05.26.2021 : 05.23.2021 : 05.19.2021 : Power Connection Prosess, Proses Register PLN 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG 05.03.2021 CME PREPARATION
495 |  | JAW-JT-BNR-0263 | 30681510031 | 1442642010 | IBS PUCUNG BEDUG | ACTIVE - BLITZKRIEG | TB | E°35.15.36'E | S°28.19.6'S | 50 | 65/170/265/330 | 2021 |  | Desa Pucungbedug RT. 002 / RW. 004, Desa Pucungbedug, Kecamatan Purwanegara, Kabupaten Banjarnegara, Propinsi Jawa Tengah | EID | JAW-JT-BNR-0263 | MANDIRAJA SADANG PUCUNGBEDUG | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Banjarnegara | 6616739 | 2021-03-18 |  | 82 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 522042889330 | 7.7 |  |  |  |  | 2021-06-08 | W24-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.02.2021 : 05.31.2021 : 05.26.2021 :05.23.2021 : 05.19.2021 : 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG WAITING MATERIAL ON SITE PLAN MOS 22 MAY 05.03.2021 CME PREPARATION
496 |  | JAW-JT-BNR-0269 | 30681420031 | 1443352004 | IBS MERTASARI | ACTIVE - BLITZKRIEG | TB | E°33.19.51'E | S°27.10.94'S | 50 | 30/210/300 | 2021 |  | Mertasari RT.002 RW.002, Desa Mertasari, Kec. Purwanegara, Kab. Banjarnegara, Prop. Jawa Tengah | EID | JAW-JT-BNR-0269 | MERTASARI PURWANEGARA | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Banjarnegara | 6616739 | 2021-03-18 |  | 82 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 522042889720 | 7.7 |  |  |  |  | 2021-06-08 | W24-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.02.2021 : Power Connection Process 05.31.2021 : 05.26.2021 : 05.23.2021 : 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG WAITING MATERIAL ON SITE PLAN MOS 22 MAY 05.03.2021 CME PREPARATION
493 |  | JAW-JT-JPA-0702 | 30681440031 | 1442752010 | IBS ZSMG_1524 | ACTIVE - BLITZKRIEG | TB | E°45.28.73'E | S°33.50.87'S | 42 | 45/130/230/300 | 2021 |  | Guyangan rt 2 rw 5 Desa Guyangan kec Bangsri | EID | JAW-JT-JPA-0702 | NURUL HIKMAH GUYANGAN | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Jepara | 6616739 | 2021-03-18 |  | 82 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | MULTIGUNA | [5 empty] | 2021-06-08 | W24-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.02.2021 : 05.31.2021 : 05.26.2021 : Power Connection Prosess, Proses Register PLN 05.23.2021 : 05.23.2021 : 05.19.2021 : POWER CONNECTION PROSESS 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG 05.03.2021 CME PREPARATION
494 |  | JAW-JT-BNR-0266 | 30681400031 | 1442652010 | IBS KERAJAN KARANGSARI | ACTIVE - BLITZKRIEG | TB | E°34.24.42'E | S°21.15.37'S | 50 | 80/140/260 | 2021 |  | Kerajan RT 06 RW 01 Desa Karangsari Kecamatan Punggelan Kabupaten Banjarnegara PropinsiJawa Barat | EID | JAW-JT-BNR-0266 | PUNGGELAN KARANGSARI | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Banjarnegara | 6616739 | 2021-03-18 |  | 82 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 522042889609 | 7.7 |  |  |  |  | 2021-06-08 | W24-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.02.2021 : 05.31.2021 : 05.26.2021 : Power Connection Prosess, Proses Register PLN 05.26.2021 : ME and Grounding system process 05.23.2021 : 05.19.2021 : 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG WAITING MATERIAL ON SITE PLAN MOS 22 MAY 05.03.2021 CME PREPARATION
497 |  | JAW-JT-PWD-0031 | 30681460031 | 1442972010 | IBS TARUMAN | ACTIVE - BLITZKRIEG | TB | E°50.46.42'E | S°0.55.56'S | 50 | 70/190/300 | 2021 |  | Dsn. Taruman RT 003 RW 002 Desa Taruman Kecamatan Klambu Kabuaten Grobogan Propinsi Jawa Tengah | EID | JAW-JT-PWD-0031 | RAYA TARUMAN KUDUS | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Grobogan | 6616739 | 2021-03-18 |  | 82 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 525530241829 | 7.7 |  |  |  |  | 2021-06-08 | W24-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.02.2021 :05.31.2021 : 05.26.2021 : Power Connection Prosess, Proses Register PLN 05.23.2021 : 05.23.2021 : 05.19.2021 : 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG PLAN MOS 22 MAY 2021 05.03.2021 CME PREPARATION
492 |  | JAW-JT-PWD-0021 | 30681500031 | 1443622004 | IBS SEM0347 | ACTIVE - BLITZKRIEG | TB | E°7.12.0'E | S°8.54.24'S | 50 | 10/90/240 | 2021 |  | Dusun Banyu Urip, Rt.02 Rw.06, Desa BanjarSari, Kecamatan Kradenan Kab Grobogan | EID | JAW-JT-PWD-0021 | TUKO JALUR REL | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Grobogan | 6616739 | 2021-03-18 |  | 82 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 525540179638 | 7.7 |  |  |  |  | 2021-06-08 | W24-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.02.2021 : 05.31.2021 : 05.26.2021 : 05.23.2021 : Power Connection Prosess, Proses Register PLN 05.19.2021 : 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG PLAN MOS 22 MAY 05.03.2021 CME PREPARATION
491 |  | JAW-JT-PWR-1671 | 30681520031 | 1443032010 | IBS JENAR KIDUL | ACTIVE - BLITZKRIEG | TB | E°59.43.03'E | S°48.30.88'S | 50 | 90/170/280/345 | 2021 |  | Dusun Kauman, RT 002/001 Desa Jenar Kidul, Kec.Purwodadi, Kabupaten Purworejo, Provinsi Jawa Tengah. | EID | JAW-JT-PWR-1671 | SANGUBANYU JENAR KIDUL | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purworejo | 6616739 | 2021-03-18 |  | 79 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | MULTIGUNA | [5 empty] | 2021-06-05 | W23-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.02.2021 : 05.31.2021 : 05.26.2021 : 05.23.2021 : 05.19.2021 : Power Connection Prosess, Proses Register PLN 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG 05.03.2021 CME PREPARATION
486 |  | JAW-JT-KBM-0632 | 30681410031 | 1441482004 | IBS BODEH WETAN | ACTIVE - BLITZKRIEG | TB | E°33.30.82'E | S°36.40.72'S | 50 | 110/200/290 | 2021 |  | Bodeh Wetan RT. 03 RW. 01, Kelurahan Wonorejo, Kecamatan Karanganyar, Kabupaten Kebumen, Provinsi Jawa Tengah | EID | JAW-JT-KBM-0632 | WONOREJO KARANGANYAR | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Kebumen | 6616739 | 2021-03-18 |  | 70 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 525031599037 | 7.7 |  |  |  |  | 2021-05-27 | W22-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.26.2021 : Power Connection Prosess 05.23.2021 : 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG WAITING MATERIAL ON SITE PLAN MOS 22 MAY 05.03.2021 CME PREPARATION
488 |  | JAW-JT-WSB-2944 | 30681480031 | 1443202010 | IBS SEMAYU - KERTEK | ACTIVE - BLITZKRIEG | TB | E°56.2.4'E | S°24.30.17'S | 50 | 0/60/160/225 | 2021 |  | Jalan Semayu-Kertek , RT 02/RW 02 . Kel Semayu , Kec Selomerto , Kab Wonosobo Jawa Tengah | EID | JAW-JT-WSB-2944 | PANDAN KELAYANG SEMAYU | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Wonosobo | 6616739 | 2021-03-18 |  | 69 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 522052411547 | 7.7 |  |  |  |  | 2021-05-26 | W22-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.26.2021 : RFI 05.23.2021 : 05.19.2021 : 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG WAITING MATERIAL ON SITE PLAN MOS 22 MAY 2021 05.03.2021 CME PREPARATION
489 |  | JAW-JT-PWR-1672 | 30681530031 | 1443022010 | IBS TEGALISER KLIWONAN | ACTIVE - BLITZKRIEG | TB | E°57.12.96'E | S°45.23.94'S | 50 | 15/95/185/260 | 2021 |  | Dusun Tegaliser, RT 001/003 Desa Kliwonan, Kec Banyuurip, Kabupaten Purworejo, Provinsi Jawa Tengah. | EID | JAW-JT-PWR-1672 | TAQWA KLIWONAN | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purworejo | 6616739 | 2021-03-18 |  | 67 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 521521358172 | 7.7 |  |  |  |  | 2021-05-24 | W22-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.26.2021 : RFI 05.23.2021 : 05.19.2021 : POWER CONNECTION PROSESS 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG 05.03.2021 CME PREPARATION
481 |  | JAW-JT-PWR-1668 | 30681450031 | 1441682004 | IBS WONOSUKO KEMIRI | ACTIVE - BLITZKRIEG | TB | E°55.16.41'E | S°39.10.22'S | 50 | 20/160/260 | 2021 |  | Dusun Panunggalan RT.03 RW.02, Desa Wonosuko, Kecamatan Kemiri, Kabupaten Purworejo, Provinsi Jawa Tengah | EID | JAW-JT-PWR-1668 | WONOSUKO KEMIRI | COLO | TBG | CENTRAL | JATENG | Jawa Tengah | Kab. Purworejo | 6616739 | 2021-03-18 |  | 63 | 61 - 90 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 521531192282 | 7.7 |  |  |  |  | 2021-05-20 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.19.2021 : POWER CONNECTION PROSES 05.17.2021 : 05.10.2021 : 05.06.2021 RBS/BTS FOUNDATION OG 05.03.2021 CME PREPARATION
480 |  | JAW-JB-SKB-2382 | 30681650031 | 1269852004 | IBS BOJONGLOA - LEMBUR SITU | ACTIVE - BLITZKRIEG | TB | E°53.17.22'E | S°57.57.63'S | 40 | 0/90/280 | 2021 |  | Jl. Nanggerang, RT. 01 RW. 12, Kelurahan Lembursitu, Kecamatan Lembursitu, Kota Sukabumi, Provinsi Jawa Barat | EID | JAW-JB-SKB-2382 | NANGARENG LEMBURSITU | COLO | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kota Sukabumi | 6616739 | 2021-03-18 |  | 55 | 31 - 60 days | 2021-04-17 | W16-2021 | Apr-2021 | 2021-05-07 | W19-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 536112268555 | 6.6 Kva |  |  |  |  | 2021-05-12 | W20-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.17.2021 RFI 05.10.2021 Power Connection Process, menunggu PLN 05.06.2021 RBS/BTS FOUNDATION OG 05.03.2021 CME PREPARATION
626 |  | SUM-JA-JMB-0495 | 30627070031 | T000186 | SRIWIJAYA | ACTIVE - RELOCATION | SKP | 103°34.4.58'E | 1°37.40.4'S | 33 | 90/210/330 |  | RELOCATION | Jl. TP. Sriwijaya LR Kejayaan RT 19/05 Desa Rawasari Kota Baru Jambi 36125 | HTI | SUM-JA-JMB-0495 | PAGARDRUM RELOCATION | COLO | TBG | WEST | SUMBAGSEL | Jambi | Kota Jambi | 6617090 | 2021-03-09 |  | 143 | 121 - 150 days | 2021-04-08 | W15-2021 | Apr-2021 | 2021-04-18 | W17-2021 | Apr-2021 | 2021-04-08 | W15-2021 | Apr-2021 | 2021-04-08 | W15-2021 | Apr-2021 | MW |  |  | 143105944428 | 6.6 |  |  |  |  | 2021-07-30 | W31-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02:08:21: RFI MULTIGUNA, RFIN SEND 30 JUL 07:29:21: PROSES CONNECT PLN AKAN DI MULTIGUNAKAN 07:26:21: Connect PLN Proses menunggu ketersediaan distribusi KWH dari PLN 07:22:21 : Power Connection Prosess, SK PLN Released 07:19:21 : Confirm Connect PLN By XL, Need SK PLN, SK NY Released 07:15:21 : 07.08.21 : 07.05.21 : 06.28.21 : 06.21.21 : 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 19.04.21 : SRFIN sent 15.04.21 : ME OG, plan SRFI 16 Apr 08.04.21 : CME preparation 01.04.21 : STO announced 09.03.21 : SPK release
646 |  | JAW-JK-KYB-0280 | 30621460031 | 110433104 | SIMATUPANG REP | ACTIVE - RELOCATION | SKP | 106°46.50.16'E | 6°17.47.18'S | 25 | 90/210/330 |  |  | Jl. Adhiyaksa VII, Kel. Lebak Bulus RT.03 RW.05 Kec. Cilandak, Kota Jakarta Selatan Prov. DKI Jakarta | EID | JAW-JK-KYB-0280 | TAMAN LEBAK BULUS RELOCATION | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6616762 | 2021-01-22 |  | 94 | 91 - 120 days | 2021-02-21 | W09-2021 | Feb-2021 | 2021-03-12 | W11-2021 | Mar-2021 | 2021-04-30 | W18-2021 | Apr-2021 | 2021-04-30 | W18-2021 | Apr-2021 | MW |  |  | 543602649171 | 6.6 |  |  |  |  | 2021-04-26 | W18-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.04.21 : RFIN sent 26.04.21 : PLN Connected 22.04.21 : PLN process, RFI Plan 30 Apr 19.04.21 : PSB released, proses register PLN 15.04.21 : email konfirmasi konek PLN 14/04, waiting SK PLN release 08.03.21 : erection stacking OG 01.03.21 : curring time pondasi stacking, waiting fabrikasi stacking 22.02.21 : 18.02.21 : 15.02.21 : fabrikasi material stacking OG 08.02.21 : RNP TNP OK 28.01.21 : ESR submitted, under RNP review 22.01.21 : SPK COLO release
619 |  | SUL-GO-GTO-0171 |  |  |  | ACTIVE - RELOCATION |  | 123°4.5.3'E | 0°33.56.77'N | 50 | 90/210/330 |  | RELOCATION |  | HTI | SUL-GO-GTO-0171 | KOTA UTARA GORONTALO RELOCATION | B2S | TBG | EAST | SULAWESI | Gorontalo | Kota Gorontalo | 6616689 | 2021-01-15 |  | 35 | 31 - 60 days | 2021-06-14 | W25-2021 | Jun-2021 | 2021-06-13 | W25-2021 | Jun-2021 | 2021-02-20 | W08-2021 | Feb-2021 | 2021-02-20 | W08-2021 | Feb-2021 | MW | 2021-02-04 | [7 empty] | 2021-02-19 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.21 : PLN connection OG 08.02.21 : erection OG, PSB released 15.01.21 : SPK B2S release
645 |  | JAW-JB-BGR-0233 | 30619480031 | 120086109 | BARANANG SIANG II | ACTIVE - RELOCATION | TB | 106°49.37.24'E | 6°36.16.85'S | 38 | 90/210/300 |  |  | Kel. Cimahpar Kp. Pasir RT. 01 RW.012, Kec. Bogor Utara, Kota Bogor Prov. Jawa Barat | EID | JAW-JB-BGR-0233 | KATULAMPANG TOL RELOCATION | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kota Bogor | 6616657 | 2021-01-08 |  | 20 | < 30 days | 2021-02-07 | W07-2021 | Feb-2021 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-03-18 | W12-2021 | Mar-2021 | 2021-03-18 | W12-2021 | Mar-2021 | MW |  |  | 538216372240 | 6.6 |  |  |  |  | 2021-01-28 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.03.21 : PSB released, PLN connection OG 28.01.21 : ESR done 14.01.21 : waiting RNP approval 08.01.21 : SPK release
643 |  | JAW-JB-CBI-0094 | 30618660031 | T000787 | PAGELARAN | ACTIVE - RELOCATION | SKP | 106°47.1.93'E | 6°37.25.07'S | 40 | 90/210/330 |  |  | Jl. Sakura, Kel. Kotabatu RT.02/09 Kec. Ciomas, Kab. Bogor Prov. Jawa Barat | EID | JAW-JB-CBI-0094 | YUSUP_CIAPUS_RELOCATION | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6616573 | 2020-12-14 |  | 154 | > 150 days | 2021-01-13 | W03-2021 | Jan-2021 | 2021-02-06 | W06-2021 | Feb-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 538315745780 | 6.6 |  |  |  |  | 2021-05-17 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.21.21 : RFI 05.17.21 : 05.10.21 : 05.06.21 : Power Connection Process 03.05.21 : 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 11.01.21 : CME preparation 14.12.20 : SPK COLO release
222 |  | JAW-BT-TNG-1458 | 30572080031 | 1317441003 | TAMAN GOLF BOULEVARD | ACTIVE | TB | 106.6492 | -6.1935 | 35 | 0/90/180/270 |  |  | Jl. Raya Bukit golf RT. 04 Rw.014 Kel. Poris pelawad Indah kec. cipondoh Kota Tangerang | EID | JAW-BT-TNG-1458 | Taman Golf Boulevard | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6616544 | 2020-12-03 |  | 89 | 61 - 90 days | 2021-05-02 | W19-2021 | May-2021 | 2021-02-26 | W09-2021 | Feb-2021 | 2021-02-26 | W09-2021 | Feb-2021 | 2021-02-26 | W09-2021 | Feb-2021 | MW | 2021-02-02 |  | 566100979353 | 6.6 |  |  |  |  | 2021-03-02 | W10-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.03.21 : PLN connected, prepare RFIN 22.02.21 : 18.02.21 : PLN connection OG 15.02.21 : ME installation, waiting PSB release 11.02.21 : pouring OG 08.02.21 : galian done, plan pouring 8 Jan 04.02.21 : galian OG 01.02.21 : CME preparation, plan start 02 Feb 28.01.21 : rekom done, plan CME start W1 Feb 14.01.21 : target penyelesaian rekom PUPR W4 Jan 11.01.21 : 21.12.20 : rekom L/C ongoing, need rekom PUPR 03.12.20 : SPK release
618 |  | JAW-JK-TJP-0653 | 30615460031 | 1129561003 | POLE_KAWASAN_INDUSTRI_RELOCATION | ACTIVE - RELOCATION | TB | 106°42.54.56'E | 6°6.2.65'S | 21 | 90/210/330 |  |  | Jl. Kapuk Kamal Raya, Kel. Kamal Muara RT.12 RW.01, Kec. Penjaringan, Kota Jakarta Utara Prov. DKI Jakarta | EID | JAW-JK-TJP-0653 | POLE_KAWASAN_INDUSTRI_RELOCATION | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | Kota Adm. Jakarta Utara | 6616516 | 2020-11-25 |  | 167 | > 150 days | 2021-04-24 | W17-2021 | Apr-2021 | 2021-04-23 | W17-2021 | Apr-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 542103852978 | 6.6Kva |  |  |  |  | 2021-05-11 | W20-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.11.21 : RFI 05.10.21 : 05.06.21 : Power Connection Process 03.05.21 : 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 25.01.21 : SRFIN sent, PLN waiting confirmation from XL 18.01.21 : pouring OG 14.01.21 : CME preparation 11.01.21 : rekom ongoing 04.01.21 : kand D RF TX OK, IW ongoing 21.12.20 : 17.12.20 : submit kand A,B,C, under RNP review
468 |  | JAW-JB-BKS-0710 | 30615480031 | 123417121 | BULAK 22 MC-T-GF | ACTIVE | TB | 107°1.35.87'null | 6°15.18.94'S | 18 | 30/240/320 |  |  | Jalan Bulak Kapal Permai No.22-36, Tambun Selatan, Bekasi, Jawa Barat 17510 | EID | JAW-JB-BKS-0710 | Joyomartono Bekasi Timur | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kota Bekasi | 6616509 | 2020-11-24 |  | 133 | 121 - 150 days | 2020-12-24 | W52-2020 | Dec-2020 | 2021-01-23 | W04-2021 | Jan-2021 | TBD | TBD | TBD | 2021-04-02 | W14-2021 | Apr-2021 | FO |  |  | 537116695042 | 6.6 |  |  |  |  | 2021-04-06 | W15-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.04.21 : aktual RFI, plan submit RFIN 8 Apr 07.01.21 : SRFI sent 28.12.20 : 21.12.20 : 14.12.20 : fabrikasi material bracket dudukan BTS, mounting 07.12.20 : ESR done, proses input stip 03.12.20 : under power-civil review 30.11.20 : ESR submitted, under RNP review 24.11.20 : SPK colo release
466 |  | JAW-YO-WNO-0008 | 30615050031 | 150035109 | GIRIASIH | ACTIVE | TB | 110°20.55.72'E | 7°59.50.32'S | 65 | 80/220/290 |  |  | Jl. Parangtritis KM.6 RT.22/RW.06, Girijati, Kec. Purwosari, Kab. Gunung Kidul | EID | JAW-YO-WNO-0008 | Giriasih Purwosari | COLO |  | CENTRAL | JATENG | DI Yogyakarta | Kab. Gunungkidul | 6616476 | 2020-11-19 |  | 57 | 31 - 60 days | 2020-12-19 | W51-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2021-01-18 | W04-2021 | Jan-2021 | MW | 2020-12-08 |  | 521052269553 | 7.7 |  |  |  |  | 2021-01-15 | W03-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.01.21 : plan PLN connect 16 Jan 28.12.20 : 21.12.20 : 14.12.20 : SRFI, proses pln connection 10.12.20 : 07.12.20 : survey site, prepare start CME 03.12.20 : ESR done, proses input STIP 30.11.20 : RNP TNP OK, reject by power-civil dengan remark reheight 57m -> 50m 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
636 |  | JAW-JK-GGP-0500 | 30617590031 | 110452109 | JALAN DESA PEGADUNGAN | ACTIVE - RELOCATION | SKP | 106°42.46.73'E | 6°8.45.96'S | 27 | 90/210/330 |  |  | Jl. Utan Jati No.27, Kel. Pegadungan RT.009 RW.11 Kec. KaliDeres, Kota Jakarta Barat Prov. DKI Jakarta | EID | JAW-JK-GGP-0500 | TAMPAK_SIRING_PEGADUNGAN_RELOCATION | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | Kota Adm. Jakarta Barat | 6616399 | 2020-11-19 |  | 188 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | 2021-01-15 | W03-2021 | Jan-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 546303217777 | 6.6 |  |  |  |  | 2021-05-26 | W22-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.26.2021 : RFI 05.23.21 : 05.19.21 : Power Connection Prosess, Plan connect PLN 20 May 05.17.21 : 05.10.21 : 05.06.21 : PSB Done Released, Power Connection Process 03.05.21 : 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 07.01.21 : SRFI 28.12.20 : pondasi done, ME installation 21.12.20 : pondasi BTS ongoing 17.12.20 : cme preparation 30.11.20 : 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
634 |  | JAW-JK-GGP-0496 | 30615750031 | 110955109 | BUMI CENGKARENG INDAH | ACTIVE - RELOCATION | SKP | 106°44.11.33'E | 6°8.20.04'S | 27 | 90/210/330 |  |  | Kel. Cengkareng, Kampung Rawa Kedaung Rt.06 RW.04 Kec. Cengkareng, Kota Jakarta Barat Prov. DKI Jakarta | EID | JAW-JK-GGP-0496 | PERUM_CENGKARENG_INDAH_RELOCATION | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | Kota Adm. Jakarta Barat | 6616399 | 2020-11-19 |  | 183 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | 2021-01-22 | W04-2021 | Jan-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 546303217769 | 6.6 |  |  |  |  | 2021-05-21 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.24.21 : RFI 05.19.21 : PLN Connect FU mitra terkait RFIN plan RFIN 20 May 05.17.21 : 05.10.21 : 05.06.21 : PSB Done Released, Power Connection Process 03.05.21 : 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 21.01.21 : SRFIN sent 18.01.21 : 11.01.21 : 07.01.21 : pondasi stacking ongoing 28.12.20 : 21.12.20 : fabrikasi material stacking baseframe 17.12.20 : cme preparation 30.11.20 : 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
639 |  | JAW-JB-DPK-0464 | 30617360031 | 123542109 | PURI GANDUL ASRI | ACTIVE - RELOCATION | TB | 106°47.34.87'E | 6°20.36.46'S | 35 | 90/210/330 |  |  | Jl. Jamhur No.4, Kel. Gandul RT.004 RW.01, Kec. Cinere, Kota Depok Prov. Jawa Barat | EID | JAW-JB-DPK-0464 | DAMAI_GANDUL_RELOCATION | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kota Depok | 6616402 | 2020-11-19 |  | 182 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | 2021-01-22 | W04-2021 | Jan-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 543602655218 | 6.6 |  |  |  |  | 2021-05-20 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.19.21 : PLN Connect FU mitra terkait RFIN plan RFIN 20 May 05.17.21 : 05.10.21 : 05.06.21 : PSB Done Released, Power Connection Process 03.05.21 : 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 25.01.21 : SRFIN sent 11.01.21 : pondasi stacking ongoing 28.12.20 : fabrikasi material stacking single row 21.12.20 : 17.12.20 : cme preparation 30.11.20 : 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
640 |  | JAW-JK-TJP-0670 | 30618370031 | TBG05_NJKT195 | SEMPER BARAT | ACTIVE - RELOCATION | BK | 106°55.33.24'E | 6°7.39.94'S | 35 | 90/210/330 |  |  | Jl. Semper Barat I, Kel. Semper Barat RT.008 RW.006 Kec. Cilincing, Kota Jakarta Utara Prov. DKI Jakarta | EID | JAW-JK-TJP-0670 | BRANTAS_SEMPER_BARAT_RELOCATION | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | Kota Adm. Jakarta Utara | 6616406 | 2020-11-19 |  | 181 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | 2021-01-23 | W04-2021 | Jan-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 545302846613 | 6.6 |  |  |  |  | 2021-05-19 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.19.21 : RFI 05.17.21 : 05.10.21 : 05.06.21 : PSB Done Released, Power Connection Process 03.05.21 : 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 11.01.21 : SRFI sent 28.12.20 : CME preparation 19.11.20 : SPK colo release
635 |  | JAW-JK-GGP-0497 | 30617560031 | 110502109 | JOGLO BARU | ACTIVE - RELOCATION | SKP | 106°43.18.62'E | 6°12.58.1'S | 23 | 90/210/330 |  |  | Jl. Masjid Darul hikmah , Joglo Baru RT.05 RW.06 Kel. Joglo, Kec. Kembangan, Kota Jakarta Barat Prov. DKI Jakarta | EID | JAW-JK-GGP-0497 | KOMP._WALIKOTA_JOGLO_RELOCATION | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | Kota Adm. Jakarta Barat | 6616399 | 2020-11-19 |  | 180 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | 2021-01-22 | W04-2021 | Jan-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 543301815499 | 6.6 |  |  |  |  | 2021-05-18 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.19.21 : RFI 05.17.21 : 05.10.21 : 05.06.21 : PSB Done Released, Power Connection Process 03.05.21 : 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 28.01.21 : SRFIN sent 18.01.21 : 11.01.21 : pondasi stacking ongoing, plan material stacking ready 13 Jan 28.12.20 : 21.12.20 : 17.12.20 : fabrikasi material stacking baseframe 30.11.20 : 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
637 |  | JAW-JB-BKS-0695 | 30617670031 | 123322109 | HPINDAHBEKASIMW | ACTIVE - RELOCATION | SKP | 106°59.24.25'E | 6°11.32.64'S | 32 | 90/210/330 |  |  | Kel. Pejuang Kp. Kaliabang Bahagia RT.001 RW.004, Kec. Medan Satria, Kota Bekasi Prov. Jawa Barat | EID | JAW-JB-BKS-0695 | MESJID_PEJUANG_RELOCATION | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kota Bekasi | 6616399 | 2020-11-19 |  | 173 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | 2021-01-22 | W04-2021 | Jan-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 545302845296 | 6.6Kva |  |  |  |  | 2021-05-11 | W20-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.10.21 : 05.06.21 : PSB Done Released, Power Connection Process 03.05.21 : 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 14.01.21 : SRFIN sent 07.01.21 : SRFI 28.12.20 : 21.12.20 : CME preparation 30.11.20 : 26.11.20 : ESR submitted, under RNP review 19.11.20 : SPK colo release
644 |  | JAW-JB-CKR-0065 | 30617750031 | 120454109 | SUKAMANTRI | ACTIVE - RELOCATION | MSI | 107° 9' 59.98" E | 6° 8' 36.31" S | 47 | 90/210/330 |  |  | Jl. Desa Sukakarya RT.13 RW.01, Kec. Sukakarya, Kab. Bekasi Prov. Jawa Barat | EID | JAW-JB-CKR-0065 | SUKAMANTRI_BEKASI_RELOCATION | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bekasi | 6616403 | 2020-11-19 |  | 173 | > 150 days | 2020-12-19 | W51-2020 | Dec-2020 | 2021-01-21 | W04-2021 | Jan-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-20 | W21-2021 | May-2021 | MW |  |  | 5370411044558 | 6.6Kva |  |  |  |  | 2021-05-11 | W20-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.11.21 : RFI 05.10.21 : 05.10.2021 : 05.06.21 : Power Connection Process 03.05.21 : 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 07.01.21 : SRFIN sent 28.12.20 : CME preparation 16.12.20 : STO announced 19.11.20 : SPK colo release
620 |  | JAW-JK-GGP-0493 | 30617530031 | TBG02_BTN017 | CENGKARENG | ACTIVE - RELOCATION | TI | 106°44.38.47'E | 6°8.53.52'S | 38 | 90/210/330 |  |  | Jl. Mawar, Kel. Kapuk RT.07 RW.09 Kec. Cengkareng, Kota Jakarta Barat Prov. DKI Jakarta | EID | JAW-JK-GGP-0493 | WARU_RAYA_KAPUK_RELOCATION | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA BARAT | 6616407 | 2020-11-16 |  | 273 | > 150 days | 2020-12-16 | W51-2020 | Dec-2020 | 2021-01-12 | W03-2021 | Jan-2021 | 2020-12-16 | W51-2020 | Dec-2020 | 2020-12-16 | W51-2020 | Dec-2020 | MW |  |  | MULTIGUNA | 5.5 |  |  |  |  | 2021-08-16 | W34-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:16:21: RFI MULTIGUNA 08:10:21: 08:04:21: 08:02:21 : Proses Connect PLN, SK PLN RELEASED, BPUJL PAID, WAITING SPK PENYAMBUNGAN RELEASED 07.29.21 : Confirm Connect PLN By Pak Hakim Plan 15 Aug 07.22.21: 07:19:21: 07:15:21: 07.08.21 : 07.05.21 : 06.24.21 : 06.21.21 : 06.16.21 : XL Req Hold PLN Connection ( Pak Hakim ) 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 07.01.21 : SRFI sent 28.12.20 : pondasi BTS done, instalasi tray 21.12.20 : 17.12.20 : pondasi ongoing 07.12.20 : RNP TNP OK, rejected by civil, proses upload APD 30.11.20 : 23.11.20 : ESR submitted, under RNP review 16.11.20 : SPK colo release
649 |  | JAW-JT-SGN-1836 | 30617740031 | 142647109 | BENER NGRAMPAL | ACTIVE - RELOCATION | TB | 111°4.4.12'E | °24.53.17'S | 45 | 90/210/330 |  |  | Desa Bener Dukuh Mentir RT.07 RW.03 Kec. Ngrampal, Kab. Sragen Prov. Jawa Tengah | EID | JAW-JT-SGN-1836 | WONOTOLO_GONDANG_RELOCATION | COLO |  | CENTRAL | JATENG | Jawa Tengah | Kab. Sragen | 6616433 | 2020-11-16 |  | 288 | > 150 days | 2020-12-16 | W51-2020 | Dec-2020 | 2021-01-21 | W04-2021 | Jan-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-08-30 | W36-2021 | Aug-2021 | MW |  |  | 520582110815 | 11 |  |  |  |  | 2021-08-31 | W36-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08:30:2021:08:25:2021:08:18:2021: BPUJL PAID, PROSES CONNECTION PLN, PENAMBAHAN JARINGAN 11 KVa, CONFIRM BY PAK IMAM XL, PLAN CONNECT 30 AUG 08:16:2021: 08:10:2021: 08:09:2021: 08:04:2021: PLN ON PROGRESS, PLAN 9 AUG REGISTER RELEASED, NEED APPROVAL EMS DAN KELENGKAPAN DOK PLN 07:29:2021: 07.26.2021 : distri busi travo Ny ready, terkendala oleh PPKM, PLN belum bisa melayani pengajuan PLN dengan Jaringan 07.22.2021: 07:19:2021: 07:15:2021: 07:12:2021: 07.08.2021 : 07.05.2021 : 07.01.2021 : 06.28.2021 : 06.24.2021 : OB Travo, proses eskalasi distribusi travo, travo Ny Ready masih menunggu antrian pemasangan dari PLN Seragen, revisi plan RFI 23 Jul, proses terkendala karena lockdown di seragen 06.21.2021 : 06.17.2021 : Waiting Material Travo, masih dalam antrian PLN Revisi Plan 25 Jun 06.14.2021 : 06.10.2021 : Survey PLN Done, Proses Perhitungan Register 06.07.2021 : 06.02.2021 : Overblast Travo menunggu approval UP3 Penggantian Travo 05.31.21 : 05.26.21 : 05.23.21 : 05.19.21 : 05.17.21 : Power Connection Process, Proses Register 05.10.21 : 03.06.21 : 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 07.01.21 : aktual SRFI 28.12.20 : CME preparation 03.12.20 : 23.11.20 : ESR submitted, under RNP review 16.11.20 : SPK colo release
621 |  | JAW-JT-CLP-0552 | 30615180031 | 140606104 | PLTUCILACAP | ACTIVE - RELOCATION | SMI | 109°4.54.95'E | 7°40.37.98'S | 47 | 90/210/330 |  |  | Jl. Nanas RT.02/01, Ds. Karang Kandri Kec. Kesugihan, Kab. Cilacap Prov. Jawa Tengah | EID | JAW-JT-CLP-0552 | MERTASINGA_RELOCATION | COLO |  | CENTRAL | JATENG | Jawa Tengah | Cilacap | 6616432 | 2020-11-16 |  | 204 | > 150 days | 2020-12-16 | W51-2020 | Dec-2020 | 2021-01-11 | W03-2021 | Jan-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-06-07 | W24-2021 | Jun-2021 | MW | 2020-12-08 |  | 525011382041 | 7.7 |  |  |  |  | 2021-06-08 | W24-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.07.2021 : 06.02.2021 : 05.31.21 : 05.26.21 : 05.23.21 : 05.19.21 : 05.17.21 : Power Connection Process, Proses Register 05.10.21 : 03.06.21 : 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 11.01.21 : PLN connection need confirmation from XL, actual SRFI 28.12.20 : aktual SRFI, proses PLN connection 21.12.20 : 17.12.20 : pondasi BTS ongoing 14.12.20 : start CME 10.12.20 : prepare start CME 07.12.20 : ESR done 03.12.20 : under power-civil review 30.11.20 : 23.11.20 : ESR submitted, under RNP review 16.11.20 : SPK colo release
465 |  | JAW-JB-BGR-0203 | 30615160031 | 123250109 | SUKARESMIBOGORMW | ACTIVE | SKP | 106°48.19.8'E | 6°32.43.55'S | 40 | 10/150/220 |  |  | KAMPUNG TUNGGILIS RT,01 RW,013 KEL,KEDUNG HALANG ,KEC,KOTA BOGOR UTARA,KATAMADYA BOGOR JAWA BARATKel. Kedung Halang Kec. Kota Bogor UtamaKotamadya Bogor Jawa Barat | EID | JAW-JB-BGR-0203 | Sukaresmi Bogor Utara | COLO |  | JABO | JABODETABEK (INNER) | Jawa Barat | Kota Bogor | 6616452 | 2020-11-12 |  | 70 | 61 - 90 days | 2020-12-12 | W50-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-30 | W53-2020 | Dec-2020 | 2021-01-22 | W04-2021 | Jan-2021 | MW | 2020-12-08 |  | 538216361734 | 6.6 |  |  |  |  | 2021-01-21 | W04-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : RFIN sent 18.01.21 : PLN connection process 14.01.21 : plan RFI 25 Jan 11.01.21 : 07.01.21 : curring time pondasi stacking, plan material stacking ready 13 Jan 28.12.20 : 21.12.20 : 17.12.20 : proses fabrikasi material stacking baseframe 10.12.20 : cme preparation 07.12.20 : ESR done, proses input stip 03.12.20 : under power-civil review 30.11.20 : 23.11.20 : ESR submitted 16.11.20 : ESR preparation 12.11.20 : SPK colo release
464 |  | JAW-JB-BKS-0680 | 30622230031 | 120939104 | GEMPOL_RAGAS | ACTIVE | SMI | 107°3.56.34'E | 6°9.54.5'S | 50 | 180/270/350 |  |  | Jl. Raya Gabus Gedong, Desa Srimukti RT.01 RW.06, Kec. Tambun Utara, Kab. Bekasi Prov. Jawa Barat | EID | JAW-JB-BKS-0680 | SRIAMUR BEKASI | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bekasi | 6616417 | 2020-11-04 |  | 147 | 121 - 150 days | 2020-12-04 | W49-2020 | Dec-2020 | CME BY XL |  |  | TBD | TBD | TBD | 2021-03-30 | W14-2021 | Mar-2021 | MW |  |  | 537321689024 | 6.6 |  |  |  |  | 2021-03-31 | W14-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.04.21 : RFIN sent 29.03.21 : 18.03.21 : SRFIN sent, OG PLN connection 15.03.21 : stacking baseframe OG, issue CME distop oleh pengurus DKM masjid (commcase) 08.03.21 : Perubahan komitmen menjadi CME by TBG, CME preparation 28.01.21 : STO announced CME by XL 19.01.21 : ESR submitted 04.11.20 : SPK COLO release
462 |  | JAW-JT-KBM-0625 | 30614980031 | TBG03_CJ077 | GN. TUGU | ACTIVE | TB | 109°27.47.45'E | 7°38.58.16'S | 56 | 0/90/270 |  |  | Dkh Tugu Rt4/Rw5 Banyumudal Buayan Kebumenayan Kebumen | EID | JAW-JT-KBM-0625 | Gn. TUGU BUAYAN II | COLO |  | CENTRAL | JATENG | Jawa Tengah | Kab. Kebumen | 6616366 | 2020-10-28 |  | 52 | 31 - 60 days | 2020-11-27 | W48-2020 | Nov-2020 | 2020-11-26 | W48-2020 | Nov-2020 | 2020-11-26 | W48-2020 | Nov-2020 | 2020-12-30 | W53-2020 | Dec-2020 | [9 empty] | 2020-12-19 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 07.12.20 : prepare start CME 03.12.20 : ESR done, proses input stip 26.11.20 : under power-civil review, data azimuth berbeda dengan data XL 09.11.20 : 05.11.20 : proses upload ulang ESR karena revisi koordinat, under RNP review 02.11.20 : review RNP, prepare upload ESR 28.10.20 : SPK COLO release
461 |  | JAW-JB-BKS-0665 | 30614810031 | TBG03_WJ235 | BEKASI | ACTIVE | TB | 107°0.21.71'E | 6°14.34.01'S | 32 | 90/210/330 |  |  | Jl. Ir. H. Juanda, Kel. Bekasi Jaya RT.001 RW.004, Kec. Bekasi Timur, Kota Bekasi Prov. Jawa Barat | EID | JAW-JB-BKS-0665 | Ir. JUANDA BEKASI II | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kota Bekasi | 6616366 | 2020-10-28 |  | 47 | 31 - 60 days | 2020-11-27 | W48-2020 | Nov-2020 | 2020-11-26 | W48-2020 | Nov-2020 | 2020-11-26 | W48-2020 | Nov-2020 | 2020-12-12 | W50-2020 | Dec-2020 | MW | [8 empty] | 2020-12-14 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.12.20 : RFIN sent 07.12.20 : CME preparation 03.12.20 : proses input STIP, cme preparation 30.11.20 : ESR done 23.11.20 : ESR approved, APD ongoing 12.11.20 : 09.11.20 : 05.11.20 : ESR uploaded, proses review oleh RNP 02.11.20 : review RNP, prepare upload ESR 28.10.20 : SPK COLO release
220 |  | JAW-JK-TJP-0625 | 30572380031 | 1127881003 | JALAN PANTAI INDAH SELATAN 2 | ACTIVE | TB | 106°45.38.24'E | 6°7.41.17'S | 20 | 60/180/270 |  |  | Jalan Mandara Indah VII RT.10 RW.06 Kel. Kapuk Muara Kec.Penjaringan Jakarta Utara. | EID | JAW-JK-TJP-0625 | Jalan Pantai Indah Selatan 2 | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6616353 | 2020-10-23 |  | 95 | 91 - 120 days | 2021-03-22 | W13-2021 | Mar-2021 | 2020-11-30 | W49-2020 | Nov-2020 | 2020-11-30 | W49-2020 | Nov-2020 | 2021-01-25 | W05-2021 | Jan-2021 | MW | 2020-12-01 |  | 542103806359 | 6.6 |  |  |  |  | 2021-01-26 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : 18.01.21 : galian kabel OG 14.01.21 : 28.12.20 : menunggu konfirmasi pihak PIK terkait kabel bawah tanah 21.12.20 : 03.12.20 : proses connect PLN 30.11.20 : aktual SRFI, need PSB release untuk proses connect PLN 26.11.20 : erection ongoing, plan SRFI 28 Nov 23.11.20 : galian pondasi 19.11.20 : 16.11.20 : 12.11.20 : proses rekom ongoing, plan W3 Nov RFC 09.11.20 : realisasi IW ongoing 23.10.20 : SPK reaktivasi release
221 |  | JAW-BT-CPT-0476 | 30572180031 | 1317501003 | PONDOK CABE RAYA | ACTIVE | TB | 106°45.58.48'E | 6°19.52.62'S | 35 | 45/130/200/330 |  |  | Jl. Cabe III/6, Kel. Pondok Cabe Ilir RT.001 RW.005 Kec. Pamulang, Kota Tangerang Selatan Prov. Banten | EID | JAW-BT-CPT-0476 | Pondok Cabe Raya | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | Kota Tangerang Selatan | 6616353 | 2020-10-23 |  | 91 | 91 - 120 days | 2021-03-22 | W13-2021 | Mar-2021 | 2020-12-10 | W50-2020 | Dec-2020 | 2021-01-31 | W06-2021 | Jan-2021 | 2021-01-31 | W06-2021 | Jan-2021 | FO | 2021-01-15 |  | 543602613018 | 6.6 |  |  |  |  | 2021-01-22 | W04-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.01.21 : RFIN sent 03.12.20 : SRFIN sent 30.11.20 : pouring done 23.11.20 : CME start, galian ongoing 19.11.20 : rekom lurah done, rekom camat ongoing 16.11.20 : 12.11.20 : proses rekom, plan W3 Nov RFC 09.11.20 : proses approval sitac 23.10.20 : SPK reaktivasi release
463 |  | JAW-JB-BKS-0673 | 30607350031 | 110467109 | MASJID PULO GEBANG | ACTIVE | SKP | 106°58.1.45'E | 6°12.32.9'S | 30 | 90/210/330 |  |  | Jl.Apel Raya No.01,Perum.Harapan Baru,kel.Kota baru Kec.Bekasi Barat Prop.Jawa Barat | EID | JAW-JB-BKS-0673 | DELIMA HARAPAN BARU | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kota Bekasi | 6616313 | 2020-10-09 |  | 132 | 121 - 150 days | 2020-11-08 | W46-2020 | Nov-2020 | 2020-12-18 | W51-2020 | Dec-2020 | 2021-02-28 | W10-2021 | Feb-2021 | 2021-02-28 | W10-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-02-11 |  | 544204794340 | 6.6 |  |  |  |  | 2021-02-18 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.02.21 : perubahan transport FO to MW per 22 Jan 10.12.20 : SRFIN sent 03.12.20 : aktual SRFI 30.11.20 : fabrikasi material 26.11.20 : material on delivery, plan MOS 26 Nov 23.11.20 : site preparetion 19.11.20 : proses survey dan CME preparation 16.11.20 : plan CME start 21 Nov 12.11.20 : STO announced, prepare CME 05.11.20 : re-upload ESR karena terdapat reject civil (space kurang), proses review RNP 09.10.20 : SPK COLO release
218 |  | JAW-JK-CKG-0669 | 30572370031 | 1127871003 | JALAN R. A. FADILLAH | ACTIVE | TB | 106°51.29.84'E | 6°19.1.53'S | 30 | 0/90/180/270 |  |  | Jl. RA. Fadillah, Kel. Cijantung Kec. Pasar Rebo, Kota Jakarta Timur Prov. DKI Jakarta | EID | JAW-JK-CKG-0669 | Jalan R. A. Fadillah | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | Kota Adm. Jakarta Timur | 6616272 | 2020-09-25 |  | 122 | 121 - 150 days | 2021-02-22 | W09-2021 | Feb-2021 | 2021-01-22 | W04-2021 | Jan-2021 | 2020-11-30 | W49-2020 | Nov-2020 | 2021-01-31 | W06-2021 | Jan-2021 | MW |  |  | 547202236017 | 6.6 |  |  |  |  | 2021-01-25 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.01.21 : SRFI 18.01.21 : erection OG 11.01.21 : curring time 07.01.21 : galian OG 28.12.20 : 21.12.20 : PKS Kopassus done, CME preparation -> plan CME start 28 Dec 17.12.20 : 13.12.20 : 07.12.20 : 03.12.20 : PKS under kopassur review (birokrasi panjang), plan issue PKS clear W3 Dec 26.11.20 : target RFC W5 Nov 19.11.20 : menunggu release surat jawaban resmi dari Kopassus 12.11.20 : 09.11.20 : 05.11.20 : 02.11.20 : review PKS dengan Kopassus 26.10.20 : 22.10.20 : 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : 01.10.20 : Proses PKS dengan pihak Kopassus, Join Survey done, Approval dari bagian Aslog 28.09.20 : IW clear (PKS process) 28.09.20 : SPK reaktivasi release, kandidat melanjutkan SPK lama dengan menggunakan STIP lama
457 |  | JAW-JB-BGR-0198 | 30605680031 | 123251109 | JALAN CIPINANG GADING | ACTIVE | SKP | 106°48.8.75'E | 6°37.26.58'S | 40 | 60/150/240/340 |  |  | JI. Cipinang Gading, Kel. Rangga Mekar RT.01 RW.03, Kec. Kota Bogor Selatan, Kota Bogor Prov. Jawa Barat | EID | JAW-JB-BGR-0198 | Ranggamekar Bogor Selatan | COLO |  | JABO | JABODETABEK (INNER) | Jawa Barat | Kota Bogor | 6616262 | 2020-09-23 |  | 63 | 61 - 90 days | 2020-10-23 | W43-2020 | Oct-2020 | 2020-10-22 | W43-2020 | Oct-2020 | 2020-10-22 | W43-2020 | Oct-2020 | 2020-11-24 | W48-2020 | Nov-2020 | MW | 2020-11-06 |  | 538315692100 | 6.6 |  |  |  |  | 2020-11-25 | W48-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.11.20 : RFIN sent 23.11.20 : plan connect PLN 24 Nov 19.11.20 : 12.11.20 : proses connect PLN 09.11.20 : SRFIN sent 05.11.20 : 02.11.20 : 29.10.20 : 26.10.20 :22.10.20 : STO done, preparation CME, shelter installation 19.10.20 : 15.10.20 : TNP review 12.10.20 : 08.10.20 : 05.10.20 : waiting review RND EID 01.10.20 : ERM process
455 |  | JAW-JK-TJP-0622 | 20210805631 | 1127831003 | Tol Pelabuhan Ancol | ACTIVE | TB | 106°50.4.01'null | 6°7.50.05'S | 20 | 0/90/160 |  |  | R.E MARTADINATA RT.01 RW.013 Kel. PADEMANGAN BARTA KEC.PADEMANGAN KOTA.JAKARTA UTARA | EID | JAW-JK-TJP-0622 | Tol Pelabuhan Ancol | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta |  | 6616240 | 2020-09-17 |  | 35 | 31 - 60 days | 2020-10-17 | W42-2020 | Oct-2020 | 2019-10-10 | W41-2019 | Oct-2019 | 2020-10-10 | W41-2020 | Oct-2020 | 2020-10-16 | W42-2020 | Oct-2020 | MW | 2020-10-01 |  | 542103760990 | 6.6 |  |  |  |  | 2020-10-22 | W43-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.10.20 : RFIN sent tgl 22 Oct 22.10.20 : aktual RFI, hari ini submit doc RFIN 15.10.20 : 12.10.20 : revisi PLN connection 16 oct 20 05.10.20 : 01.10.20 : proses PLN connection 28.09.20 : SRFI actual 24.09.20 : ME on going 21.09.20 : 17.09.20 : SPK COLO reaktivasi release 17 sep 20 sebagai pengganti SPK B2S Terurn pada site yg sama 09.07.20 : 06.07.20 : 18.06.20 : Propose reaktivasi SPK, progress start excavation 11.06.20 : excavation, actual status di Tower rental sudah return 08.06.20 : 04.06.20 : 01.06.20 : sudah galian, plan balik ke galian awal (ada pipa PDAM 4) geser ada pipa GAS --> prosesredesign dg borepile, sudah diajukan 28.05.20 : 25.05.20 : 21.05.20 : 18.05.20 : kand D RND NOK krn near existing, paralel penyelesaian comcase site sebelumnya 16.05.20 : submit kand D, pindah lokasi karena comcase 14.05.20 : excavation geser titik, galian pondasi ketemu pipa gas 08.05.20 : excavation on going 30.04.20 : preparation start CME 23.04.20 : 16.04.20 : Plan Start CME 17/04 09.04.20 : IW clear, RT RW, Lurah Clear, Plan start CME 15/04 02.04.20 : under review RND 25.03.20 : Candidat NOK, Rehunting 19.03.20 : validasi RND 20.02.20 : rehunting 06.02.20 : Hunting kandidat
215 |  | JAW-BT-TNG-1456 | 20210901341 | 1317701003 | SMPN 14 Tangerang | ACTIVE | TB | 106°38.32.93'null | 6°13.3.72'S | 20 | 90/240/350 |  |  | Kp. Sawah Dalam RT 003 RW 004, Kelurahan Panunggangan Utara, Kecamatan Pinang, Kota Tangerang | EID | JAW-BT-TNG-1456 | SMPN 14 Tangerang | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6616232 | 2020-09-14 |  | 35 | 31 - 60 days | 2021-02-11 | W07-2021 | Feb-2021 | 2020-11-10 | W46-2020 | Nov-2020 | 2020-11-30 | W49-2020 | Nov-2020 | 2020-11-10 | W46-2020 | Nov-2020 | MW | 2020-10-01 |  | 566100924444 | 6.6 |  |  |  |  | 2020-10-19 | W43-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22.10.20 : RFIN sent 19 Oct 19.10.20 : erection ongoing 15.10.20 : 12.10.20 : OG Curing Time, Plan Start Erection 17/10, Finish 20/10, S RFI 23/10 08.10.20 : Galian finish, plan pouring 09/10 05.10.20 : 01.10.20 : Plan Bowplank 01/10 28.09.20 : 24.09.20 : REKOM LURCAM OG NEW SPK B2S released menggunakan STIP yang lama
453 |  | JAW-JB-SBM-2104 | 30601990031 | 125429126 | CIDAHUPARAKANSALAKTBG | ACTIVE | TB | 106°44.40.7'E | 6°45.34.2'S | 40 | 60/140/260 |  |  | Kp.Tenjolaya RT 004 RW 002 Desa Girijaya Kec.Cidahu Kab.Sukabumi | EID | JAW-JB-SBM-2104 | Girijaya Cidahu Sukabumi | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Sukabumi | 6616193 | 2020-09-07 |  | 94 | 91 - 120 days | 2020-10-07 | W41-2020 | Oct-2020 | 2020-10-15 | W42-2020 | Oct-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 536590552783 | 6.6 |  |  |  |  | 2020-12-10 | W50-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.12.20 : RFIN sent 07.12.20 : PLN connection process 09.11.20 : SRFIN sent 05.11.20 : aktual SFRI 02.11.20 : 26.10.20 : 22.10.20 : 19.10.20 : erection ongoing, proses permanenisasi 15.10.20 : 12.10.20 : 08.10.20 : Permanenisasi tower, on going galian pondasi tower 05.10.20 : 01.10.20 : preparation CME 28.09.20 : 25.09.20 : ERM done, request input STIP by Marketing 24.09.20 : prepare STO dan preparation CME start 21.09.20 : 18.09.20 : 17.09.20 : TNP OK, wait review RND EID 14.09.20 : ERM
452 |  | JAW-JK-CKG-0668 | 30572350031 | 1127861003 | GANG INDUK PASAR REBO | ACTIVE | TB | 106°51.47.64'null | 6°17.36.84'S | 20 | 50/120/210/340 |  |  | JL. H. Ali Gang Mundu II, RT.04 RW.04, Kel. Tengah, Kec. Keramat Jati, Kota Jakarta Timur | EID | JAW-JK-CKG-0668 | Gang Induk Pasar Rebo | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | Kota Adm. Jakarta Timur | 6616188 | 2020-09-04 |  | 19 | < 30 days | 2020-10-04 | W41-2020 | Oct-2020 | 2020-09-20 | W39-2020 | Sep-2020 | 2020-09-20 | W39-2020 | Sep-2020 | 2020-09-20 | W39-2020 | Sep-2020 | MW | 2020-09-10 |  | 547104785433 | 6.6 |  |  |  | 2020-08-19 | 2020-09-23 | W39-2020 |  | 2020-09-25 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23.09.20 : RFIN sent 21.09.20 : SRFI, proses PLN connection 14.09.20 : 10.09.20 : SRFI, reaktivasi SPK B2S menjadi SPK Colo
656 |  | JAW-JB-PWK-4062 |  |  |  | ACTIVE - RELOCATION TBG to TBG |  | 107°26.44.64'E | 6°29.33.48'S | 40 | 90/210/330 |  | RELOCATION |  | HTI | JAW-JB-PWK-4062 | CIBENING PURWAKARTA RELOCATION | B2S | TBG | CENTRAL | JABAR | Jawa Barat | Kab. Purwakarta | 6616184 | 2020-09-03 |  | 312 | > 150 days | 2021-01-31 | W06-2021 | Jan-2021 | 2021-02-22 | W09-2021 | Feb-2021 | 2020-10-03 | W40-2020 | Oct-2020 | 2020-10-03 | W40-2020 | Oct-2020 | MW |  |  | 534443844470 | 6.6 |  |  |  |  | 2021-07-12 | W29-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07:15:2021: Proses Reloc Perangkat 07.12.21 : 07.08.21 : Plan Reloc Perangkat 12 Jul 07.05.21 : 07.01.21 : 06.24.21 : 06.21.21 : 06.17.21 : 06.14.21 : Power Connection Prosess 06.10.21 : Instalasi Mounting 06.07.21 : 06.02.21 : 05.31.21 : 05.26.21 : 05.23.21: Proses Connected PLN, Connect PLN OG, Waiting Mounting Plan Mounting & Connect Pln W1 Jun 05:19:21 : 05.10.21 : PSB PLN Released, Power Connection Proses 11.02.21 : CME done, SRFI, PLN connection waiting confirmation from XL 21.12.20 : rebaring, plan pengecoran start 23 Dec 30.11.20 : 19.11.20 : pondasi ongoing 15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : 01.10.20 : 28.09.20 : start CME menunggu proses perijinan, existing site akan di didmantle setelah site reloc RFI 24.09.20 : 21.09.20 : 17.09.20 : 14.09.20 : prepare start CME by Waskita Karya, existing site terkena gusur proyek jalan tol
615 |  | SUM-SU-KBJ-2226 |  |  |  | ACTIVE - RELOCATION |  | 98°25.47.92'E | 3°6.58.24'N | 60 | 70/170/325 |  | RELOCATION | Desa Beganding, Kec. Simpang Empat, Kab. Karo, Prov. Sumatera Utara | HTI | SUM-SU-KBJ-2226 | SURBAKTI RELOCATION | B2S | TBG | WEST | SUMBAGUT | Sumatera Utara | Kab. Karo | 6616153 | 2020-08-31 |  | 81 | 61 - 90 days | 2021-01-28 | W05-2021 | Jan-2021 | 2020-11-30 | W49-2020 | Nov-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-30 | W49-2020 | Nov-2020 | MW | 2020-10-07 |  | 129030036001 | 10.6 |  |  |  |  | 2020-11-20 | W47-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.12.20 : RFIN sent 30.11.20 : site on air, proses announce RFIN 19.11.20 : RFI done, proses reloc perangkat 22.10.20 : 19.10.20 : 15.10.20 : SK PLN release, proses PLN connection 12.10.20 : SRFI, wait SK PLN release dari XL 07.10.20 : request SK PLN 05.10.20 : waiting review TNP 21.09.20 : 17.09.20 : 14.09.20 : under review RND Huawei
617 |  | JAW-JB-BKS-0670 |  |  |  | ACTIVE - RELOCATION |  | 107°0.20.23'E | 6°20.4.81'S | 40 | 30/160/300 |  |  | Jalan Lingkungan, RT.01, RW.02, Kel. Sumur Batu, Kec. Bantar Gebang, Kota. Bekasi, Prov. Jawa Barat | EID | JAW-JB-BKS-0670 | SUMUR BATU BANTARGEBANG RELOCATION | B2S | TBG | JABO | JABODETABEK | Jawa Barat | Kota Bekasi | 6616154 | 2020-08-31 |  | 91 | 91 - 120 days | 2021-01-28 | W05-2021 | Jan-2021 | 2020-10-30 | W44-2020 | Oct-2020 | 2020-10-30 | W44-2020 | Oct-2020 | 2020-11-30 | W49-2020 | Nov-2020 | MW | 2020-10-01 |  | 537421849056 | 10.6 |  |  |  |  | 2020-11-30 | W49-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30.11.20 : site on air, proses announce RFIN 19.11.20 : aktual RFI, proses reloc perangkat 22.10.20 : 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 :05.10.20 : 01.10.20 : 28.09.20 : preparation & mob demob 24.09.20 : prepare STO dan preparation CME start 21.09.20 : 18.09.20 : 17.09.20 : TNP OK, wait review RND EID 14.09.20 : ERM
207 |  | JAW-JB-BDG-4060 | 30598380031 | 1262331003 | ERMAWAR RELOCATION | ACTIVE | TB | 107°37.14.35'E | 6°54.41.4'S | 30 | 90/210/330 |  | RELOCATION | Jl. lombok No. 10 Kelurahan Merdeka kecamatan sumur Bandung Kota Bandung | HTI | JAW-JB-BDG-4060 | ERMAWAR RELOCATION | B2S | TBG | CENTRAL | JABAR | Jawa Barat | Kota Bandung | 6615569 | 2020-08-18 |  | 291 | > 150 days | 2021-01-15 | W03-2021 | Jan-2021 | 2021-03-22 | W13-2021 | Mar-2021 | 2020-10-20 | W43-2020 | Oct-2020 | 2021-06-15 | W25-2021 | Jun-2021 | MW |  |  | 535635861701 | 6.6 |  |  |  |  | 2021-06-05 | W23-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.02.21 : ERECTION OG, BPUJL Paid 05.31.2021 : 05.26.21 : 05.23.21 : CURRING TIME, PLAN ERECTION 1 JUN 05.19.21 : 05.17.21 : Rebaring Plan Cor 21 May 2021 05.10.21 : Proses Galian 05.06.21 : Rekom Proses, Paralel Bowplank 05.04.21 : PKS done review by KODAM, proses sirkules ttd aslogkodam estimasi sampai dengan end of April 23.03.21 : proses negosiasi PKS dengan JASDAM dan KODAM karena masing2 instansi meminta PKS dengan poin ketentuan yang berbeda 08.03.21 : re-plan target PKS done W2 Mar 11.02.21 : estimasi PKS fully signed W4 Feb 01.02.21 : kandidat MCP approved, BAK process 28.01.21 : 21.01.21 : submit TSSR (panoramic view) kandidat MCP, under RND review 14.01.21 : note -> target RFC Feb, target RFI akhir Mar 2021 11.01.21 : rehunting, isu ketinggian menara max 20m 28.12.20 : 21.12.20 : pole milik JASDAM kondisi aktual tidak memungkinkan untuk relokasi perangkat (keropos) dan dilakukan perkuatan. kandidat MCP 20 yang diajukan rejected by RNP 26.11.20 : kandidat E propose MCP 20 proses review oleh planning XL karena kandidat dekat dengan kawasan militer, menunggu konfirmasi dari instansi terkait 12.11.20 : proses nego dengan JASDAM, paralel submit kandidat baru propose tower MCP 20 (perda kota Bandung) 09.11.20 : 05.11.20 : 02.11.20 : kembali ke kand A, proses negosiasi ulang dengan JASDAM terkait instalasi pole 26.10.20 : 22.10.20 : 19.10.20 : kand A failed, proses rehunting 15.10.20 : menunggu approval kodam untuk start CME dan paralel proses approval eskalasi sitac 12.10.20 : 08.10.20 : menunggu approval kodam untuk start CME 05.10.20 : RFC, menunggu review TNP CAA 05.10.20 : 01.10.20 : realisasi IW done, rekom done, waiting review TNP 28.09.20 : plan hari ini atau besok finalisasi harga sewa, wait info status TNP review 24.09.20 : 21.09.20 : 18.09.20 : proses review TNP CAA (Pak Said), angka sudah ada dari KODAM, proses eskalasi 17.09.20 : proses finalisasi dengan KODAM, hari ini plan menghadap jasdam utk biayanya 14.09.20 : kembali ke kandidat A, proses review TNP, paralel finalisasi dengan KODAM 10.09.20 : kandidat A failed, proses rehunting 07.09.20 : 03.09.20 : propose pasang di pole milik TNI, proses review RND 28.08.20 : submit kand A, B, C, D ditiang stadion, kand E max 25m sesual Perwal
459 |  | JAW-BT-TNG-2111 | 30605960031 | 131148126 | MCP TNG TANAH TINGGI 1 | ACTIVE | TB | 106°38.38.08' | 6°10.16.68'S | 18 | 0/90/180/270 |  |  | Jl. Jend. Sudirman (samping jembatan penyebrangan depan komp kehakiman), Kota Tangerang Prov. Banten | EID | JAW-BT-TNG-2111 | SHOAIB ABDUL AZIZ Relocation | COLO |  | JABO | JABODETABEK (INNER) | Banten | Kota Tangerang | 6615567 | 2020-08-18 |  | 101 | 91 - 120 days | 2020-09-17 | W38-2020 | Sep-2020 | 2020-11-30 | W49-2020 | Nov-2020 | 2020-11-30 | W49-2020 | Nov-2020 | 2020-11-30 | W49-2020 | Nov-2020 | MW |  |  | 566100942289 | 6.6 |  |  |  |  | 2020-11-27 | W48-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30.11.20 : RFIN sent 23.11.20 : plan connect PLN 27 Nov 09.11.20 : SRFIN sent 05.11.20 : 02.11.20 : 29.10.20 : proses fabrikasi material (colo mcp) 16.10.20 : STIP release
460 |  | JAW-JI-KPN-4378 | 30606050031 | TBG06_EJ071 | TAWANG ARGO | ACTIVE | PMS | 112.5712 | -7.8721 | 48 | 90/210/330 |  | RELOCATION | Jl. Dusun Leban RT.17 RW. 05 Kel.Tawang argo Kec.Karang ploso Kab. Malangel.Tawang argo Kec.Karang ploso Kab. Malang | HTI | JAW-JI-KPN-4378 | TAWANG ARGO RELOCATION | COLO | TBG | EAST | JATIM | Jawa Timur | MALANG | 6614896 | 2020-07-14 |  | 156 | > 150 days | 2020-08-13 | W33-2020 | Aug-2020 | 2020-11-28 | W48-2020 | Nov-2020 | 2020-11-28 | W48-2020 | Nov-2020 | 2020-12-14 | W51-2020 | Dec-2020 | MW | 2020-11-09 |  | 513031025522 | 6.6 |  |  |  |  | 2020-12-17 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 17.12.20 : 14.12.20 : 10.12.20 : isu stock kwh meter kosong (area distribusi PLN Malang) 26.11.20 : proses PLN connection (no register) 12.09.20 : aktual SRFI, need PSB PLN 09.11.20 : 05.11.20 : pondasi done, ME installation 02.11.20 : prepare start CME 29.10.20 : 19.10.20 : STIP release
22 |  | JAW-JT-PWT-0553 | 30597160031 | 1434151003 | BOJONGSARI KEMBARAN | ACTIVE | TB | 109.2828 | -7.4225 | 50 | 35/130/210/320 |  |  | JL. Raya Bojongsari RT 01 RW 08 Desa Bojongsari, Kecamatan Kembaran, Kabupaten Banyumas | EID | JAW-JT-PWT-0553 | Bojongsari Kembaran | B2S | TBG | CENTRAL | JATENG | DI Yogyakarta | BANYUMAS | 6614888 | 2020-07-14 |  | 136 | 121 - 150 days | 2020-12-11 | W50-2020 | Dec-2020 | 2020-11-25 | W48-2020 | Nov-2020 | 2020-12-10 | W50-2020 | Dec-2020 | 2020-11-30 | W49-2020 | Nov-2020 | MW | 2020-11-03 |  | 522012429848 | 7,7 |  |  |  |  | 2020-11-27 | W48-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.11.20 : RFIN sent 26.11.20 : PLN connected, proses finishing site dan collect doc RFIN 23.11.20 : ongoing PLN survey 19.11.20 : erection done, pondasi BTS done, ME installation ongoing 16.11.20 : 12.09.20 : erection ongoing 09.11.20 : pondasi ongoing 05.11.20 : rebaring, plan pengecoran start 6 Nov 02.11.20 : 29.10.20 : 26.10.20 : proses analisa ulang terkait design pondasi karena berada di lahan timbunan sampah 22.10.20 : 19.10.20 : proses galian 15.10.20 : bouwplank, plan start CME hari ini 12.10.20 : plan start CME kamis 15 oct 20 08.10.20 : 05.10.20 : 01.10.20 : rekom lurah & camat done, proses perijinan 28.09.20 : realisasi IW done, on going proses rekom 24.09.20 : eskalasi approved, plan realisasi IW 25 Sep 21.09.20 : TNP OK 50m/0.3, IW CLEAR, proses eskalasi sitac 17.09.20 : kand C RNP OK, RF 50 50/120/200/280, proses review TNP paralel IW 14.09.20 : kand B gagal IW, kandidat baru under review RNP (cand C 109.278069, -7.423286) 10.09.20 : 09.09.20 : plan IW clear 14 Sep 07.09.20 : IW ongoing, minus 3KK 03.09.20 : 01.09.20 : TNP OK, IW on going 31.08.20 : 28.08.20 : kand B RND OK, review TNP 27.08.20 : kandidat B (koordinat 109.28651, -7.42448) under RNP review 24.08.20 : IW failed, rehunting kand B, plan submit kand B selasa 25 Aug 17.08.20 : TNP OK, MW height 50m/0.3, IW on going, plan IW clear 20 Aug 20 13.08.20 : paralel IW on going, dari 64KK kurang 7 kk, plan IW clear 20 Aug 20 10.08.20 : 06.08.20 : proses review TNP, IW ongoing di kandidat A 03.08.20 : 30.07.20 : kandidat A sedang dijalankan proses IW sesuai request RND tower 52 (TBG propose tower 42 untuk menghindari penolakan warga sekitar NOM) 27.07.20 : 23.07.20 : kandidat A koordinat 109.284361, -7.424769 approved by RND dengan RF 50m, waiting TNP review 20.07.20 : hunting
45 |  | JAW-JT-PWD-0014 | 30597150031 | 1434141003 | GAJAH MADA PURWODADI | ACTIVE | TB | 110.9038 | -7.0908 | 50 | 75/140/310 |  |  | Jl. Gajah Mada RT 06 RW 01 Kelurahan Kuripan Kecamatan Purwodadi Kabupaten Grobogan Jawa Tengah | EID | JAW-JT-PWD-0014 | Gajah Mada Purwodadi | B2S | TBG | CENTRAL | JATENG | DI Yogyakarta | GROBOGAN | 6614888 | 2020-07-14 |  | 255 | > 150 days | 2020-12-11 | W50-2020 | Dec-2020 | 2020-10-25 | W44-2020 | Oct-2020 | 2021-02-28 | W10-2021 | Feb-2021 | 2021-03-13 | W11-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-02-11 |  | 525530230524 | 7.7 |  |  |  |  | 2021-03-26 | W13-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.03.21 : PLN connected, plan submit RFIN hari ini 25.02.21 : OG PLN connection 11.02.21 : perubahan transport FO -> MW, waiting PSB release 19.10.20 : doc SRFI sent 15.10.20 : SRFI actual, preparing doc SRFIN, plan submit latest 16 oct 20 12.10.20 : ME on going, finishing F & Y 08.10.20 : erection done, ME dan F&Y on going 05.10.20 : erection on going, plan besok top section 01.10.20 : pouring done, curing time, plan start erection minggu 4 oct 20 28.09.20 : rebarring, plan cor 28 sep 20 24.09.20 : on going pondasi sumuran, progress terkendala galian longsor, plan cor 28 sep 20 21.09.20 : revisi design done 19 sep, pekerjaan pondasi start dengan new design (pondasi sumuran) 17.09.20 : proses revisi design pondasi karena borepile longsor terus 14.09.20 : 10.09.20 : start excavation 07.09.20 : plan sudah bisa start CME minggu depan, paralel dengan proses perijinan 03.09.20 : status RFC, proses perijinan 31.08.20 : 27.08.20 : rekom camat done, soiltest done, proses design pack 24.08.20 : realisasi IW done, proses rekom 17.08.20 : 13.08.20 : IW clear, proses eskalasi biaya sitac 06.08.20 : kandidat B approved by TNP, MW height 50m/0.6, proses IW ongoing 03.08.20 : kandidat B OK RF 50m, proses review TNP 30.07.20 : kandidat A terkendala issue penolakan warga, submit kandidat baru bergeser 30m (cand B koordinat 110.903722, -7.091994) under RNP review 27.07.20 : 23.07.20 : kandidat A koordinat 110.903722, -7.09175 approved by RND dengan RF 50m, waiting TNP review 20.07.20 : hunting
224 |  | JAW-JB-KWG-1073 | 30597320031 | 121180104 | CIPARAGE | ACTIVE | SMI | 107.489 | -6.1733 | 40 | 10/145/240 |  |  | Dusun Banjar RT 16 RW 05. Desa Ciparage Jaya. Kec. Tempuran. Kab.Karawang | EID | JAW-JB-KWG-1073 | Sumurgede Karawang | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Karawang | 6614852 | 2020-07-06 |  | 50 | 31 - 60 days | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-28 | W35-2020 | Aug-2020 | MW | 2020-08-10 |  | 534685915150 | 6.6 |  |  |  |  | 2020-08-25 | W35-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.08.20 : RFIN sent 24.08.20 : SK PLN release 18 Aug 20, revisi plan RFI 28 Aug 20 18.08.20 : SRFI, PLN connection menunggu SK PLN release dari XL 10.08.20 : 06.08.20 : SRFI 30.07.20 : mobilisasi
261 |  | JAW-JT-SLW-2320 | 30596380031 | 141655109 | CANGKRING | ACTIVE | SKP | 109.1569 | -6.9074 | 50 | 25/165/265 |  |  | CANGKRING RT 013 RW 03 DESA CANGKRING KEC.TALANG, KAB.TEGAL, JAWA TENGAH | EID | JAW-JT-SLW-2320 | DAWUHAN TALANG | COLO |  | CENTRAL | JATENG | DI Yogyakarta | TEGAL | 6614810 | 2020-07-01 |  | 239 | > 150 days | 2020-07-31 | W31-2020 | Jul-2020 | 2020-07-30 | W31-2020 | Jul-2020 | 2021-02-28 | W10-2021 | Feb-2021 | 2021-02-28 | W10-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2021-02-11 |  | 522521737122 | 7.7 |  |  |  | 2020-07-28 | 2021-02-25 | W09-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.02.21 : PLN connected, RFIN ongoing collect document 11.02.21 : perubahan transport FO -> MW, waiting PSB release 28.07.20 : email SRFI-N sent 27.07.20 : actual SRFI, collecting doc SRFIN 20.07.20 : 19.07.20 : start RBS foundation 13.07.20 : STIP done & CME preparation 10.07.20 : RND & TNP OK, GO CME 09.07.20 : under review RND EID 01.07.20 : SPK release
447 |  | JAW-JB-CBI-0108 | 30597310031 | 125966123 | SUKARAJA CILEBUT | ACTIVE | TB | 106.7989 | -6.522 | 30 | 90/190/330 |  |  | Kp. Bojong Sempu RT 03/06, Desa Cilebut Barat, Kecamatan Sukaraja, Kab. Bogor | EID | JAW-JB-CBI-0108 | BOJONG_GEDE_RAYA | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614797 | 2020-06-26 |  | 56 | 31 - 60 days | 2020-07-26 | W31-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-12 | W33-2020 | Aug-2020 | MW | 2020-08-10 |  | 538414576873 | 6.6 |  |  |  | 2020-07-30 | 2020-08-21 | W34-2020 |  | 2020-09-05 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.08.20 : 21.08.20 : RFIN sent 18.08.20 : SRFI, PLN connection menunggu SK PLN release dari XL 30.07.20 : SRFIN sent 20.07.20 : 16.07.20 : 13.07.20 : 09.07.20 : 02.07.20 : under review RND EID 26.06.20 : SPK Release 26 jun 20
409 |  | JAW-JB-BGR-0226 | 30595650031 | 120873104 | SUKADAMAI | ACTIVE | SMI | 107.0565 | -6.5575 | 50 | 135/240/340 |  |  | Kp.Waru RT.02 RW.03, Ds.Sukadamai, Kec.Sukamakmur, Kab.Bogor | EID | JAW-JB-BGR-0226 | Sukadamai Sukamakmur Bogor | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614795 | 2020-06-26 |  | 66 | 61 - 90 days | 2020-07-26 | W31-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-09-05 | W36-2020 | Sep-2020 | MW | 2020-07-16 |  | 538671118910 | 6.6 |  |  |  | 2020-08-05 | 2020-08-31 | W36-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 31.08.20 : RFIN sent 27.08.20 : proses PLN connection, SK PLN release 24 Aug 24.08.20 : PLN connection masih menunggu SK PLN yang belum release dari XL/EID, rev plan RFI 5 Sep 18.08.20 : SRFI, PLN connection menunggu SK PLN release dari XL 10.08.20 : revisi plan RFI 25 Aug 06.08.20 : 05.08.20 : email SRFI-N sent 20.07.20 : start RBS foundation 16.07.20 : 13.07.20 : 09.07.20 : STO, CME preparation 02.07.20 : Go CME 26.06.20 : SPK Release 26 jun 20
413 |  | JAW-JB-KWG-1065 | 30595640031 | 121175104 | SUNGAITERONG | ACTIVE | SMI | 107.1976 | -6.0455 | 50 | 90/200/270 |  |  | Dsn. Kobak Gabus RT. 02 RW. 05 Ds. Karya Bhakti Kec. Batu Jaya Kab. Karawang | EID | JAW-JB-KWG-1065 | Karyabakti Batujaya Karawang | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Karawang | 6614793 | 2020-06-26 |  | 167 | > 150 days | 2020-07-26 | W31-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 534826726240 | 6.6 |  |  |  | 2020-07-24 | 2020-12-10 | W50-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.12.20 : RFIN sent 07.12.20 : PLN connection process 27.07.20 : 24.07.20 : email SRFI-N sent 20.07.20 : SRFI actual 16.07.20 : mobilisasi team & material 13.07.20 : preparation 09.07.20 : 02.07.20 : Go CME 26.06.20 : SPK Release 26 jun 20
322 |  | NUS-NT-KPG-0286 | 30595580031 | 190053110 | KLAMIK KUPANG BARAT | ACTIVE | MSI | 123.497 | -10.3205 | 50 | 45/125/285 |  |  | Jl. Kupang-Tablolong, Nufeleu Kelamik, Kec. Kupang Tengah, Kab. Kupang | ALT | NUS-NT-KPG-0286 | KLAMIK RATBA | COLO |  | EAST | BALINUSRA | Nusa Tenggara Timur | Kab. Kupang | 6614783 | 2020-06-24 |  | 43 | 31 - 60 days | 2020-07-24 | W30-2020 | Jul-2020 | 2020-07-23 | W30-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-11 | [7 empty] | 2020-08-06 | W32-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.08.20 : RFIN sent 06.08.20 : plan declare RFIN 7 Aug 03.08.20 : RFI actual dengan Multiguna, plan declare RFIN 5 Aug 23.07.20 : 22.07.20 : SRFI actual, proses PLN connection 09.07.20 : delivery material dan preparation team 02.07.20 : Go CME 02.07.20 : Preparation team dan material 29.06.20 : proses STIP dan preparation 27.06.20 : STO done 24.06.20 : SPK Release 24 jun 20
418 |  | NUS-NT-KPG-0282 | 30597300031 | 190837109 | TALOETAN | ACTIVE | TB | 123.605 | -10.3163 | 50 | 110/180/310 |  |  | Dusun 3 RT. 09 RW. 05 Desa Taloetan Kecamatan Nekamese Kabupaten Kupang Propinsi Nusa Tenggara Timur | ALT | NUS-NT-KPG-0282 | BONE TALOETAN | COLO |  | EAST | BALINUSRA | Nusa Tenggara Timur | Kab. Kupang | 6614781 | 2020-06-24 |  | 131 | 121 - 150 days | 2020-07-24 | W30-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-09-10 | W37-2020 | Sep-2020 | 2020-10-15 | W42-2020 | Oct-2020 | MW | 2020-07-11 | [7 empty] | 2020-11-02 | W45-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02.11.20 : RFIN sent 29.10.20 : 26.10.20 : PLN sudah connect, proses penyusunan doc RFIN 22.10.20 :19.10.20 : 15.10.20 : ME on going & proses PLN connection 12.10.20 : Permanenisasi : F & Y on going, CME colo XL : ME on going 08.10.20 : Permanenisasi ME on going, CME colo XL : Pondasi RBS on going, material ME, tray & mounting on site, No reg PLN release & proses bayar BP 05.10.20 : erection on going, plan top erection besok 01.10.20 : pouring done, curingtime, plan start erection sabtu 3 oct 20 28.09.20 : rebarring 24.09.20 : lantai kerja dan barbending 21.09.20 : 17.09.20 : on going galian pondasi tower, material sudah sampai kupang 14.09.20 : 10.09.20 : galian pondasi tower permanent SST 42m, delivery material, plan RFI 15 oct 20 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : 17.08.20 : 13.08.20 : Start CME terkendala isu pengiriman material 10.08.20 : 06.08.20 : 03.08.20 : preparation CME permanenisasi tower 23.07.20 : 20.07.20 : permanenisasi : proses soiltest dan APD, plan percepatan permanenisasi end og Aug 10.07.20 : TNP OK, prepare STO 09.07.20 : RND, Power & Civil OK, under review TNP ALITA 02.07.20 : under review TNP ALITA 29.06.20 : ERM on going, RND review, site GM 24.06.20 : SPK Release 24 jun 20
8 |  | JAW-JB-BGR-0222 | 30595410031 | 1262171003 | BABAKAN MADANG BOGOR | ACTIVE | TB | 106.902 | -6.6184 | 40 | 155/250/330 |  |  | Desa Bojong Koneng Kp. Curug RT.001 RW.009, Kec. Babakan Madang, Kab. Bogor Prov. Jawa Barat | EID | JAW-JB-BGR-0222 | Babakan Madang Bogor | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614778 | 2020-06-24 |  | 155 | > 150 days | 2020-11-21 | W47-2020 | Nov-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-25 | W48-2020 | Nov-2020 | MW | 2020-11-06 |  | 538614702053 | 6.6 |  |  |  |  | 2020-11-26 | W48-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.11.20 : aktual RFI, proses collect doc RFIN 23.11.20 : erection done, ME installation ongoing 19.11.20 : 16.11.20 : erection ongoing 12.11.20 : curring time 09.11.20 : rebaring pondasi 05.11.20 : start galian 02.11.20 : 26.10.20 : bouwplank, start CME 22.10.20 : prepare start CME W5 Oct 19.10.20 : rekom done, RFC 15.10.20 : 12.10.20 : rekom ongoing, Soil Test OG, Plan Design dan APD done 15/10 08.10.20 : IW clear kand E, realisasi IW done, proses soiltest paralel rekom 05.10.20 : 01.10.20 : submit kandidat baru, kand E RF OK 50m, MW 49m/0.6, proses negosiasi BAN/BAK, plan IW clear 6 oct 28.09.20 : 24.09.20 : IW on going 21.09.20 : TNP OK MW 39m/0.6, proses BAN/BAK & IW on going 17.09.20 : proses negosiasi BAN/BAK, paralel review TNP ALITA 14.09.20 : kandidat D RND propose RF 50m, koordinat OK, proses review TNP 10.09.20 : Approval kandidat 07.09.20 : IW on going 03.09.20 : 31.08.20 : 27.08.20 : submit kand baru (cand C 106.90206, -6.61829) under RNP review 27.08.20 : submit kand baru (cand C 106.90206, -6.61829) under RNP review 24.08.20 : 18.08.20 : IW failed, rehunting B 13.08.20 : IW on going kand A, paralel submit kandidat baru, kand B RF OK 40m 10.08.20 : IW on going 06.08.20 : kandidat A TX OK , MW height 39m/0.6 03.08.20 : 30.07.20 : 27.07.20 : kandidat A approved by RNP dgn RF 40m, proses validasi TNP 27.07.20 : kandidat A approved by RNP dgn RF 40m, proses validasi TNP 23.07.20 : 20.07.20 : 16.07.20 : kandidat A koordinat 106.9017, -6.61767 under RNP review 16.07.20 : 13.07.20 : 02.07.20 : 29.06.20 : hunting 24.06.20 : SPK Release 24 jun 20
17 |  | JAW-JB-BGR-0210 | 30595360031 | 1262121003 | BERINGIN BATULAYANG | ACTIVE | TB | 106.9432 | -6.6747 | 50 | 15/90/190/295 |  |  | Kp. Batukasur Rt 002 RW 003 Desa Batulayang Kecamatan Cisarua Kabupaten Bogor. | EID | JAW-JB-BGR-0210 | Beringin Batulayang | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614778 | 2020-06-24 |  | 117 | 91 - 120 days | 2020-11-21 | W47-2020 | Nov-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-10-30 | W44-2020 | Oct-2020 | MW | 2020-10-01 |  | 538114210549 | 6.6 |  |  |  |  | 2020-10-19 | W43-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22.10.20 : RFIN sent 19.10.20 : SRFI 15.10.20 : 12.10.20 : Erection Tower OG, Plan Finish 15/10, Plan S RFI 19/10 08.10.20 : curingtime 05.10.20 : 01.10.20 : Galian OG, Plan Pouring 05/10, Erection start 12/10 finish 17/10, S RFI 20/10 28.09.20 : 24.09.20 : excavation 21.09.20 : 18.09.20 : bouwplank 17.09.20 : soiltest on going 14.09.20 : rekom on going 10.09.20 : Soiltest 07.09.20 : Proses realisasi, collect dokumen IW dan Lahan 03.09.20 : Proses collect dokumen IW dan Lahan 31.08.20 :27.08.20 : kembali ke kandidat A, proses eskalasi SITAC 24.08.20 : 18.08.20 : menunggu konfirmasi dari RND, tbg provide SST 52 sesuai permintaan (pergeseran 15m), IW clear 10.08.20 : 06.08.20 : menunggu konfirmasi dari RND, tbg provide SST 52 sesuai permintaan (pergeseran 15m) 03.08.20 : 30.07.20 : submit kandidat baru (cand C koordinat 106.94575, -6.67345) propose tower SST 42, under RNP review 27.07.20 : 23.07.20 : 20.07.20 : kandidat A under TNP review 16.07.20 : kembali ke kandidat A koordinat 106.94588, -6.6734 dengan RF 50m RND OK 13.07.20 : 09.07.20 : RND not OK kand A dan B, rehunting C 08.07.20 : submit kand A dan B 02.07.20 : 29.06.20 : hunting 24.06.20 : SPK Release 24 jun 20
61 |  | JAW-JB-BGR-0223 | 30595420031 | 1262181003 | JALAN RAYA CARIU JONGGOL | ACTIVE | TB | 107.1101 | -6.4873 | 40 | 100/175/350 |  |  | Kampung Seredang RT. 010 RW. 003, Desa Tegal Panjang, Kecamatan Cariu, Kabupaten Bogor, Provinsi Jawa Barat | EID | JAW-JB-BGR-0223 | Jalan Raya Cariu Jonggol | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614778 | 2020-06-24 |  | 98 | 91 - 120 days | 2020-11-21 | W47-2020 | Nov-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-09-30 | W40-2020 | Sep-2020 | MW | 2020-09-10 |  | 538671124640 | 6.6 |  |  |  | 2020-09-30 | 2020-09-30 | W40-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30.09.20 : RFIN sent 28.09.20 : plan submit RFIN paling lambat 30 sep 20 24.09.20 : RFI actual, collecting doc RFIN 21.09.20 : on going ME installation 17.09.20 : Rebaring OG, Plan Pouring 14/09 14.09.20 : 10.09.20 : Rebaring OG, Plan Pouring 14/09 07.09.20 : Galian Pondasi OG 03.09.20 : 31.08.20 : RFC, proses perijinan 27.08.20 : Plan REKOM done 28/08 24.08.20 : 18.08.20 : proses realisasi IW 10.08.20 : 06.08.20 : 30.07.20 : proses eskalasi sitac, plan RFC 7 Agustus 2020 23.07.20 : 22.07.20 : TNP OK kand A 40 0.6 127.9 20.07.20 : 16.07.20 : wait TNP review kandidat A (1 minggu) 13.07.20 : wait TNP review A 09.07.20 : RND OK A 02.07.20 : 29.06.20 : hunting 24.06.20 : SPK Release 24 jun 20
109 |  | JAW-JB-BGR-0214 | 30595380031 | 1262141003 | MEKARWANGI BOGOR | ACTIVE | TB | 107.1188 | -6.5216 | 40 | 30/165/240 |  |  | Kampung Jangkar RT. 001 RW. 001, Desa Mekarwangi, Kecamatan Cariu Kabupaten Bogor, Provinsi Jawa Barat | EID | JAW-JB-BGR-0214 | Mekarwangi Bogor | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614778 | 2020-06-24 |  | 98 | 91 - 120 days | 2020-11-21 | W47-2020 | Nov-2020 | 2020-09-30 | W40-2020 | Sep-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-09-30 | W40-2020 | Sep-2020 | MW | 2020-09-10 |  | 538671124632 | 6.6 |  |  |  | 2020-09-30 | 2020-09-30 | W40-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30.09.20 : RFIN sent 28.09.20 : plan submit RFIN paling lambat 30 sep 20 24.09.20 : RFI actual, collecting doc RFIN 21.09.20 : SRFI, proses PLN connection 17.09.20 : Plan finish 21/09, Plan S RFI 24/09 14.09.20 : 10.09.20 : Curing Time, Plan start Erection 14/09 finish 21/09, Plan S RFI 24/09 07.09.20 : Galian Pondasi 03.09.20 : Galian pondasi, plan finish 31/08, plan pouring 07/09 31.08.20 : 27.08.20 : Galian pondasi, plan finish 31/08, plan pouring 07/09 24.08.20 : 18.08.20 : rekom on going 10.08.20 : IW clear, proses eskalasi sitac 06.08.20 : 30.07.20 : proses eskalasi sitac, IW on going 23.07.20 : 22.07.20 : TNP OK kand A 40 0.6 33.87 20.07.20 : 16.07.20 : 13.07.20 : wait TNP review A 09.07.20 : Kandidat A & B propose 42 m, namun RND meminta ketinggian min. 50m, paralel dilakukan IW radius 52m untuk kandidat A koordinat 107.11858, -6.521 02.07.20 : 29.06.20 : hunting 24.06.20 : SPK Release 24 jun 20
34 |  | JAW-JB-BGR-0224 | 30595430031 | 1262191003 | CIPINANG RUMPIN BOGOR | ACTIVE | TB | 106.6196 | -6.4411 | 40 | 35/170/315 |  |  | Kp. GN. Cabe, RT 001 RW 004, Desa Cipinang, Kec Rumpin, Kab.Bogor | EID | JAW-JB-BGR-0224 | Cipinang Rumpin Bogor | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614778 | 2020-06-24 |  | 96 | 91 - 120 days | 2020-11-21 | W47-2020 | Nov-2020 | 2020-10-15 | W42-2020 | Oct-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-09-30 | W40-2020 | Sep-2020 | MW | 2020-09-10 |  | 538531101128 | 6.6 |  |  |  |  | 2020-09-28 | W40-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.09.20 : RFIN sent 24.09.20 : RFI actual, collecting doc RFIN 21.09.20 : on going ME installation 17.09.20 : Plan Erection Finish 22/09, ME Finish 24/09, Plan RFI 28/09 14.09.20 : borepole done, sor pondasi done 10.09.20 : Borepile, plan Finish 11/09, Plan Pouring pondasi 15/09 07.09.20 : Pengecoran Bore pile 03.09.20 : 31.08.20 : RFC, proses perijinan 27.08.20 : Plan REKOM done 28/08 24.08.20 : 18.08.20 : proses realisasi IW 17.08.20 : kandidat C TNP OK MW 49m/0.6, IW on going 13.08.20 : 10.08.20 : 06.08.20 : 03.08.20 : 30.07.20 : 27.07.20 : kandidat C apprved by RNP dengan ketinggian tower 52m (RF 50m), menunggu review TNP 23.07.20 : submit kandidat baru dengan tinggi tower 42m (cand C koordinat -6.440028 106.617667), proses review RND 20.07.20 : kandidat A koordinat OK, RNP request 50m 16.07.20 : 14 jul submit kandidat B koordinat 106.61789, -6.4397 propose SST 42, waiting RNP review 13.07.20 : 09.07.20 : RND NOT OK kand A, arahan geser ke -6.440318, 106.617316 Propose SST 52, rehunting B 08.07.20 : submit kand A 02.07.20 : 29.06.20 : hunting 24.06.20 : SPK Release 24 jun 20
124 |  | JAW-JB-BGR-0220 | 30595400031 | 1262161003 | PARUNG PANJANG BOGOR | ACTIVE | TB | 106.588 | -6.4162 | 40 | 20/155/320 |  |  | Jl. Raya Dago-Parung Panjang, RT. 003 RW. 003, Desa Dago, Kecamatan Parung Panjang, Kabupaten Bogor | EID | JAW-JB-BGR-0220 | Parung Panjang Bogor | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614778 | 2020-06-24 |  | 79 | 61 - 90 days | 2020-11-21 | W47-2020 | Nov-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-09-25 | W39-2020 | Sep-2020 | MW | 2020-08-16 |  | 538531094526 | 6.6 |  |  |  |  | 2020-09-11 | W37-2020 |  | 2020-09-26 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 11.09.20 : RFIN sent 10.09.20 : Finishing ME dan Pagar 07.09.20 : ME on going 03.09.20 : 31.08.20 : erection on going 27.08.20 : Plan Start Erection 28/08, Finish 04/09, Plan S RFI 09/09 24.08.20 : rebarring on going 18.08.20 : TNP review, paralel iW 10.08.20 : 06.08.20 : menunggu konfirmasi RND request tower 52 03.08.20 : 30.07.20 : under TNP review untuk kandidat C (koordinat 106.58765, -6.4141), target RFC 7 Agustus 20.07.20 : kandidat B & C koordinat OK, RNP request 50m 16.07.20 : RND propose RF 50m untuk kandidat A, paralel submit kandidat baru (B dan C) 13.07.20 : wait TNP review A 09.07.20 : RND OK A 29.06.20 : hunting 24.06.20 : SPK Release 24 jun 20
26 |  | JAW-JB-BGR-0213 | 30595370031 | 1262131003 | CIBEBER BARENGKOK | ACTIVE | TB | 106.64 | -6.6055 | 40 | 10/170/300 |  |  | Kp. Citeureup I RT.005 RW 004, Desa Barengkok, Kecamatan, Leuwiliang, Kabupaten Bogor | EID | JAW-JB-BGR-0213 | Cibeber Barengkok | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | Kab. Bogor | 6614778 | 2020-06-24 |  | 65 | 61 - 90 days | 2020-11-21 | W47-2020 | Nov-2020 | 2020-09-10 | W37-2020 | Sep-2020 | 2020-11-20 | W47-2020 | Nov-2020 | 2020-08-31 | W36-2020 | Aug-2020 | MW | 2020-08-10 |  | 538515841787 | 6.6 |  |  |  |  | 2020-08-28 | W35-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.08.20 : RFIN sent 27.08.20 : RFI actual, cpllecting doc RFIN 24.08.20 : 18.08.20 : erection on going 10.08.20 : start rebarring, plan cor kamis 13 Aug 06.08.20 : galian 30.07.20 : proses eskalasi sitac, IW on going 23.07.20 : 22.07.20 : TNP OK kand A 40 0.6 115.12 20.07.20 : 16.07.20 : wait TNP review A ( 1 minggu) 13.07.20 : wait TNP review A 09.07.20 : RND OK kand A 29.06.20 : hunting 24.06.20 : SPK Release 24 jun 20
19 |  | JAW-JB-BKS-0708 | 30595820031 | 1262221003 | BINTARA KENCANA TIMUR | ACTIVE | TB | 106.9584 | -6.2245 | 30 | 30/150/280 |  |  | Jl. Bintara 8 RT 04 RW 03 Kel. Bintara Kec. Bekasi Barat Kota Bekasi | EID | JAW-JB-BKS-0708 | BINTARA KENCANA TIMUR | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | KOTA BEKASI | 6614768 | 2020-06-23 |  | 262 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2021-02-22 | W09-2021 | Feb-2021 | 2020-11-19 | W47-2020 | Nov-2020 | 2021-03-10 | W11-2021 | Mar-2021 | MW | 2021-02-02 |  | 544204798116 | 6.6 |  |  |  |  | 2021-03-12 | W11-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.03.21 : erection OG 04.03.21 : 01.03.21 : Curring time, erection tower start tgl 04/02 finish 07/02, RFI 10/02 15.02.21 : pouring raft foundation OG 08.02.21 : borepile done 01.02.21 : 28.01.21 : borepile stacking OG, plan pengecoran 30 Jan 21.01.21 : 14.01.21 : galian OG 07.01.21 : bouwplank 28.12.20 : soiltest done, waiting APD 21.12.20 : 10.12.20 : soiltest dan APD ongoing 07.12.20 : 03.12.20 : 26.11.20 : rekom PUPR done, minus rekom camat, target clear minggu ini 23.11.20 : 19.11.20 : plan RFC W5 Nov, proses rekom PUPR ongoing 16.11.20 : proses rekom PUPR terkait zonasi tower, hammer test done 12.11.20 : 09.11.20 : confirm dijalankan kand D, IW clear, proses approval sitac 05.11.20 : 02.11.20 : 26.10.20 : 22.10.20 : re-validasi kandidat D dengan ketinggian tower 25m, under RNP review 19.10.20 : proses review design pole+stacking , TNP approved dengan MCP21 15.10.20 : 12.10.20 : RND NOK dengan penurunan tinggi tower menjadi 24m, jika ketinggian tetap 25m IW not secure 08.10.20 : 05.10.20 : proses nego RND untuk penurunan tinggi tower menjadi SST 24 karena isu penolakan warga di radius 26m 03.10.20 : RND EID propose di top 25m 02.10.20 : request revalidasi propose penurunan ketinggian tower menjadi 24m krn comcase/penolakan warga di radius 26m 01.10.20 : IW Clear, Proses Collect Dokumen IW. Plan REKOM LURCAM done 07/10 28.09.20 : 24.09.20 : IW on going 21.09.20 : 17.09.20 : Plan IW Clear 27/09, Terkendala 1 warga (+) Covid 14.09.20 : 10.09.20 : IW on going, Plan IW Clear 15/09 07.09.20 : IW on going 03.09.20 : submit kandidat baru inSAR (cand D 106.95764, -6.22488) under RNP review 31.08.20 : 27.08.20 : 24.08.20 : kand C (106.961380, -6.224510) NOK dekat dgn existing, proses rehunting arahan -6.225014, 106.958019 18.08.20 : IW failed, rehunting C 10.08.20 : 06.08.20 : Propose change SoW SPK B2S to SPK Colo 06.08.20 : submit kandidat B (106.959620 -6.226520) under RNP review 03.08.20 : 30.07.20 : 27.07.20 : 20.07.20 : 16.07.20 : kandidat A NOK near existing, proses rehunting 13.07.20 : 02.07.20 : 29.06.20 : hunting 25.06.20 : RND XL (Pak Siro) NOT OK CHANGE TO COLO karena dekat ke existing XL (300m).arahan propose B2S di titik (-6.224461, 106.957705) 24.06.20 : propose colo dg jarak 258m ke site 120820109 JATIKRAMAT INDAH 2 / MASJID ASYIFA, Tower kamuflase GF 31m 23.06.20 : SPK Release 23 jun 20
177 |  | JAW-JK-TJP-0677 | 30594970031 | 1128741003 | SWASEMBADA TANJUNG PRIOK | ACTIVE | TB | 106.888 | -6.1218 | 30 | 20/190/295 |  |  | Jl. Swasembada Barat XII No.60B RT.011 RW.013 Kel. Kebon Bawang Kec. Tanjung Priok Kota Jakarta Utara | EID | JAW-JK-TJP-0677 | SWASEMBADA TANJUNG PRIOK | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | Jakarta Utara | 6614768 | 2020-06-23 |  | 196 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2021-01-15 | W03-2021 | Jan-2021 | MW | 2020-12-16 |  | 545103565214 | 6.6 |  |  |  |  | 2021-01-05 | W02-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.01.21 : RFIN sent 28.12.20 : pouring ongoing 21.12.20 : 17.12.20 : galian ongoing 14.12.20 : 10.12.20 : CME belum bisa start, issue LL meminta DP lahan, plan pembayaran minggu ini -> 15 Dec CME start 07.12.20 : 30.11.20 : RFC, prepare start CME W1 Dec 26.11.20 : rekom ongoing, target minggu ini clear 23.11.20 : 19.11.20 : IW clear , proses realisasi IW 16.11.20 : IW clear, plan 21 Nov 12.11.20 : 09.11.20 : 02.11.20 : 19.10.20 : 15.10.20 : 12.10.20 : IW on going, plan IW clear 18 oct 20 08.10.20 : 05.10.20 : 01.10.20 : Ijin warga masih terkendala adanya warga yang + COVID 28.09.20 : 24.09.20 : IW on going 24.09.20 : 21.09.20 : IW on going 17.09.20 : Rehunting site, plan submit kandidat 18/09 14.09.20 : rehunting 10.09.20 : Rehunting site, plan submit kandidat 12/09 07.09.20 : rehunting 03.09.20 : 31.08.20 : SITAC HOLD, Change Planning dari RND XL 27.08.20 : 24.08.20 : IW on going 18.08.20 : 13.08.20 : proses cek existing kooordinat kand C 10.08.20 : 06.08.20 : submit kandidat baru (cand C 106.888540 -6.120390) under RNP review 03.08.20 : 30.07.20 : 27.07.20 : kandidat B approved by RND XL untuk ketinggian 20m (RF 20m), under TNP review 20.07.20 : kandidat B koordinat OK, menunggu konfirmasi Pak Siro untuk ketinggian 20m 16.07.20 : submit kandidat B koordinat 106.88721, -6.12183 propose MCP 20 , menunggu review RND 13.07.20 : 09.07.20 : RND not OK kand A krn near existing 08.07.20 : submit kand A 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20, confirm by RND XL (Pak Siro) untuk lanjut di ketinggian 20m sesuai regulasi pemerintah
613 |  | SUM-SB-PAD-0857 | 30595810031 | 0309091003 | KAMPUNG JAMBAK KOTA PADANG RELOCATION | ACTIVE - RELOCATION | TB | 100.3895 | -0.88469 | 40 | 100/210/330 |  | RELOCATION | Jl. Diklat Sungai Sapih RT 005 RW 003 ,kelurahan Sungai Sapih, Kecamatan Kuranji, Kota Padang | HTI | SUM-SB-PAD-0857 | KAMPUNG JAMBAK KOTA PADANG RELOCATION | B2S | TBG | WEST | SUMBAGTENG | Sumatera Barat | Kota Padang | 6614774 | 2020-06-23 |  | 203 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2021-01-09 | W02-2021 | Jan-2021 | MW | 2020-11-12 |  | 131123877781 | 6.6 |  |  |  |  | 2021-01-12 | W03-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.01.21 : RFIN sent 11.01.21 : plan hari ini announce RFI 07.01.21 : erection done, PLN connection on process 04.01.21 : 28.12.20 : 21.12.20 : erection ongoing 17.12.20 : pondasi done, curring time, plan erection tower start 17 Dec 14.12.20 : rebaring, plan pouring start 14 Dec 03.12.20 : perbaikan galian karena genangan air 30.11.20 : lean concrete ongoing, pengecoran start 30 Nov 26.11.20 : 23.11.20 : plan pouring start 25 Nov 19.11.20 : pembesian ongoing 16.11.20 : start galian 12.09.20 : preparation, start CME 14 Nov 09.11.20 : 05.11.20 : proses SIOP untuk start CME 02.11.20 : 29.10.20 : 26.10.20 : aktual site RFC, plan start CME W5 Oct 22.10.20 : proses rekom LH, plan RFC minggu ini 19.10.20 : plan start CME W3 Oct 15.10.20 : 12.10.20 : proses perijinan 08.10.20 : 05.10.20 : plan submit berkas perijinan 01.10.20 : Rekom Camat Done Prepare Dokumen submit ke Perijinan, plan RFC 7 Okt Rekom Camat Done Prepare Dokumen submit ke Perijinan 28.09.20 : 21.09.20 : IW Done, proses rekom ongoing 17.09.20 : TNP ok, IW on going 14.09.20 : 10.09.20 : 07.09.20 : 03.09.20 : 31.08.20 : kand C under review CAA (site relocation) 27.08.20 : kand C under review CAA (site relocation) 24.08.20 : kandidat C RF 40m OK, proses review TNP, paralel IW clear dan proses eskalasi sitac 17.08.20 : prepare submit kandidat baru 13.08.20 : kandidat B IW failed, proses rehunting 10.08.20 : IW failed, dilakukan pergeseran dg status IW clear, wait koordinat untuk di validasikan 06.08.20 : IW ongoing kandidat B 30.07.20 : kandidat B (koordinat 100.39053, -0.88336) reviewed by RNP OK -> RF 40m, TNP OK -> MW Height 40m/0.6, IW Ongoing 27.07.20 : IW failed, rehunting 23.07.20 : kandidat A TNP reviewed dengan MW height 40m, diameter 0.6m 20.07.20 : kandidat A RNP OK dengan RF 40m, waiting TNP review 16.07.20 : Ok candidate A, tower 42 16.07.20 : 13 jul submit kandidat A koordinat 100.38828, -0.88424 propose SST 42, masih menunggu review RNP 09.07.20 : on going hunting, plan submit kand minggu ini atau senin depan 02.07.20 : 29.06.20 : hunting 25.06.20 : RND XL (Pak Doddy) NOT OK CHANGE TO COLO karena need tinggi tower 30m 24.06.20 : propose colo dg jarak 352m ke site 30460109 TERMINAL BINGKUANG ROOF TOP 8m + pole 12 = 20m 23.06.20 : SPK Release 23 jun 20
58 |  | JAW-BT-CPT-0447 | 30594960031 | 1318231003 | JALAN MENTAWAI TOL | ACTIVE | TB | 106.6953 | -6.3003 | 30 | 60/150/220/310 |  |  | Kel. Jombang Kp. Rawa Lele RT.006 RW.010 Kec. Ciputat, Kota Tangerang Selatan Prov. Banten | EID | JAW-BT-CPT-0447 | Jalan Mentawai Tol | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614768 | 2020-06-23 |  | 160 | > 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-30 | W49-2020 | Nov-2020 | MW | 2020-11-16 |  | 543802940322 | 6.6 |  |  |  |  | 2020-11-30 | W49-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03.12.20 : RFIN sent 30.11.20 : PLN connected, finishing site 26.11.20 : prepare start erection 23.11.20 : curring time, plan SRFI 29 Nov 19.11.20 : pembesian ongoing 16.11.20 : start galian 12.11.20 : prepare start CME 14 Nov 09.11.20 : 05.11.20 : 02.11.20 : 26.10.20 : 22.10.20 : 19.10.20 : rekom done, site RFC 15.10.20 : 12.10.20 : proses rekom lurah camat menunggu rekom zonasi release 08.10.20 : 05.10.20 : 01.10.20 : IW Clear, proses collecting dokumen IW dan REKOM 28.09.20 : 24.09.20 : IW clear OG, Pengajuan cost SITAC, NOM berada di kompleks perumahan pemukiman padat, kandidat site berada di lahan fasum milik PEMKOT 21.09.20 : 17.09.20 : IW Clear, proses collecting dokumen IW dan REKOM 14.09.20 : 10.09.20 : IW Clear, proses collecting dokumen IW dan REKOM 07.09.20 : IW on going 03.09.20 : 31.08.20 : 27.08.20 : Proses pengajuan pemanfaatan lahan fasum PEMKOT 24.08.20 : 18.08.20 : Proses Pemanfaatan lahan fasum PEMKOT 10.08.20 : 06.08.20 : kandidat A TX OK, MW height 20m/0.3, IW on going 03.08.20 : 30.07.20 : 27.07.20 : kandidat A RF OK ketinggian 20m, proses validasi TNP 20.07.20 : kandidat A submit tgl 15 Jul (koordinat 106.69608,-6.30106 propose MCP 20) waiting RNP review 16.07.20 : 13.07.20 : 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20
100 |  | JAW-JK-TJP-0679 | 30594980031 | 1128751003 | LONTAR DALAM KOJA | ACTIVE | TB | 106.9133 | -6.119 | 30 | 10/80/290 |  |  | Jl. Mahoni Blok F No. 1A Kel. Tugu Utara, Kec. Koja, Jakarta Utara | EID | JAW-JK-TJP-0679 | LONTAR DALAM KOJA | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | Jakarta Utara | 6614768 | 2020-06-23 |  | 121 | 121 - 150 days | 2020-11-20 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | 2020-11-19 | W47-2020 | Nov-2020 | MW | 2020-10-06 |  | 545302759851 | 6.6 |  |  |  |  | 2020-10-22 | W43-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.10.20 : RFIN sent tgl 22 Oct 22.10.20 : aktual RFI, prepare doc RFIN plan submit hari ini 19.10.20 : ME installed 15.10.20 : prepare erection tower, plan start 17 oct 12.10.20 : 08.10.20 : curingtime, cor done 05.10.20 : 01.10.20 : Galian Pondasi OG 28.09.20 : 24.09.20 : eskalasi sitac approved, , need rekom PTSP, plan RFC 7 Okt, realisasi IW on going 21.09.20 : IW on going, need rekom PTSP 17.09.20 : Need REKOM PTSP 14.09.20 : rehunting 10.09.20 : 07.09.20 : perizinan PTSP 03.09.20 : Ijin warga OG, Plan IW Clear 05/09 31.08.20 : 27.08.20 : Ijin warga OG, Plan IW Clear 31/08 24.08.20 : 18.08.20 : IW on going 10.08.20 : 06.08.20 : 03.08.20 : 30.07.20 : 27.07.20 : proses nego (re-validasi) kandidat A dgn pertimbangan inSAR dan IW secure, menunggu konfirmasi RND 20.07.20 : 16.07.20 : 13.07.20 : 09.07.20 : RND not OK kand A, arahan -6.118543 106.913458 08.07.20 : submit kand A 02.07.20 : 29.06.20 : hunting 23.06.20 : SPK Release 23 jun 20, confirm by RND XL (Pak Siro) untuk lanjut di ketinggian 20m sesuai regulasi pemerintah
929 |  | JAW-BT-TGR-1180 |  |  |  | X RENEWAL | [8 empty] | EID | JAW-BT-TGR-1180 | Jengkol | COLO |  | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614757 | 2020-06-19 |  | 678 | > 150 days | 2020-07-19 | W30-2020 | Jul-2020 |  |  |  | TBD | TBD | TBD | [17 empty] | 38.RFI | 21.RFI | CLOSED - RFI DONE
931 |  | JAW-JK-TJP-2504 |  |  |  | X RENEWAL | [8 empty] | EID | JAW-JK-TJP-2504 | KBN (Kawasan Berikat Nusantara) Cakung | COLO | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6614758 | 2020-06-19 |  | 678 | > 150 days | 2020-07-19 | W30-2020 | Jul-2020 |  |  |  | TBD | TBD | TBD | [17 empty] | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.06.20 : SPK XL release
930 |  | JAW-JB-CKR-1085 |  |  |  | X RENEWAL | [8 empty] | HTI | JAW-JB-CKR-1085 | Setu Taman Rahayu | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BEKASI | 6614757 | 2020-06-19 |  | 678 | > 150 days | 2020-11-16 | W47-2020 | Nov-2020 |  |  |  | TBD | TBD | TBD | [17 empty] | 38.RFI | 21.RFI | CLOSED - RFI DONE
928 |  | JAW-JT-SKH-1990 |  |  |  | X RENEWAL | [8 empty] | EID | JAW-JT-SKH-1990 | Sukoharjo Timur | COLO |  | CENTRAL | JATENG | Jawa Tengah | SUKOHARJO | 6614759 | 2020-06-19 |  | 678 | > 150 days | 2020-07-19 | W30-2020 | Jul-2020 |  |  |  | TBD | TBD | TBD | [17 empty] | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.06.20 : SPK XL release
616 |  | JAW-JI-SDA-4296 | 30595350031 | 1644451003 | TAMBAK PINGGIR RELOCATION | ACTIVE - RELOCATION | TB | 112.7607 | -7.3536 | 30 | 90/210/330 |  | RELOCATION | Ngeni Rt 03 Rw 02 Desa Kepuhkiriman Kec Waru Kab Sidoarjo | HTI | JAW-JI-SDA-4296 | TAMBAK PINGGIR RELOCATION | B2S | TBG | EAST | JATIM | Jawa Timur | Kab. Sidoarjo | 6614727 | 2020-06-13 |  | 338 | > 150 days | 2020-11-10 | W46-2020 | Nov-2020 | 2021-01-15 | W03-2021 | Jan-2021 | 2021-05-20 | W21-2021 | May-2021 | 2021-05-24 | W22-2021 | May-2021 | MW |  |  | 511464354400 | 6.6 |  |  |  |  | 2021-05-17 | W21-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.19.21 : RFI 05.10.21 : 05.06.21 : 03.05.21 : Power Connection Process 29.04.21 : Konfirmasi Lanjut PLN Connection, Waiting PSB Released 19.04.21 : SRFIN sent, PLN connection hold (menunggu plan relokasi perangkat XL) 07.01.21 : SRFI sent 04.01.21 : prepare erection 28.12.20 : curring time 21.12.20 : 14.12.20 : galian ongoing 10.12.20 : 7.12.20 : 03.12.20 : 30.11.20 : 26.11.20 : plan start CME 1 Dec, menunggu IMB release , estimasi CME start 14 Dec 12.11.20 : rekom done, paralel proses review design tower kamuflase 09.11.20 : 05.11.20 : proses review design tower kamuflase 02.11.20 : 29.10.20 : kand D CAA approved dengan tinggi tower 25m, IW Clear, proses realisasi IW 26.10.20 : menunggu approval CAA terkait reduce ketinggian tower menjadi 25m 22.10.20 : 19.10.20 : IW clear di ketinggian 25m, propose penurunan ketinggian ke CAA dari tower 32 ke 25m 15.10.20 : proses IW ongoing pada kand E dalam radius untuk tower 25m, CAA OK tinggi tower 25m 13.10.20 : IW radius 25m done, plan sore ini pengajuan validasi tinggi 25m ke RND XL Pak Fikky dan Bu Dina (CAA) 12.10.20 : 08.10.20 : CAA NOK kand D dgn ketinggian 20m (dekat existing), proses IW di kand D dengan ketinggian tower 25m, paralel hunting alternatif kandidat 05.10.20 : proses nego ketinggian + submit JR, under review CAA 01.10.20 : hasil review CAA koordinat OK, namun request ketinggian tower mendekati existing min. 30m 28.09.20 : 24.09.20 : 21.09.20 : 18.09.20 : proses review RND CAA (Pak Kustriono/Bu Dhina), paralel IW clear, XL meminta 32m tetapi hanya bisa 20m (RT) 17.09.20 : MOM ; Soswar done tadi malam, IW clear 17.09.20 : kand C gagal IW, proses review RNP kandidat baru (kand D) propose RT total 20m karena kandidat di dalam cellplan sehingga tidak diijinkan mendirikan tower macro (Perwali Kab Sidoarjo) , sekitar NOM terkendala isu provokasi warga di tower dismantle milik XL 14.09.20 : 10.09.20 : 07.09.20 : IW ongoing (kurang 2kk), mediasi dengan warga yang menolak, plan IW Clear 9 Sep 31.08.20 : 27.08.20 : reschedule resoswar forum malam ini. 24.08.20 : 23.08.20 : malam ini akan di lakukan resoswar lagi 17.08.20 : proses resoswar minggu ini 13.08.20 : IW ongoing, plan sabtu 15 Jul 20 clear soswar forum 10.08.20 : IW on going 06.08.20 : kandidat C TX OK, MW height 28m, diameter 0.6m, IW on going 03.08.20 : 30.07.20 : kandidat C proses review TNP oleh CAA XL , paralel on going IW 23.07.20 :20.07.20 : 16.07.20 : kandidat C menunggu review TNP (sudah 1 minggu) 13.07.20 : 09.07.20 : kandidat C approved by RNP koordinat 112.76121, -7.35448 propose MP 30 m (RF 28.5m OK) 29.06.20 : Hunting 23.06.20 : RND XL (Pak Fikky) not OK, kedua kandidat tsb mendekati existing XL lainnya. arahan rehunting ke selatan radius 100m dr NOM Existing XL. 23.06.20 : hasil analisa sitac : NOM berada pada existing XL Issue Penolakan & provokasi dari batas lahan existing yang menjadi Penyebab dismantle existing tersebut. Tower Dismantle 22/6/20 dikarenakan Perbup Kab Sidoarjo No. 34 Tahun 2018, bahwasanya titik nominal dan kandidat berada di zona penataan menara Mengacu Perda tersebut jarak antar menara 300m >> Potensi dari hasil penjajakan di area NOM yang possible ada candidate yang bisa kita propose dengan Camuflase dan reduce ke 20 / 18 m MCP dan Rooftop 9/12m >> InSAR 300m dari NOM terdapat 2 Eksisting dengan tenant XL dan Indosat. Submit kand A --> Need REDUCE >> Regulasi Jarak Antar Menara, Areal Pemukiman Padat, (Komplek Kepuh Permai , Potensial IW 50% ± 40KK , Cand GF (Bongkar Rumah) Submit kand B --> Areal Pemukiman Padat, (Komplek Kepuh Permai , Potensial IW 50% ± 40KK , Cand RT tinggi bangunan 6m + Stacking 4m Propose Pole 9/12m . 22.06.20 : STIP 8 survey release 16.06.20 : ketinggian 17.5m Not OK by RND XL (pak Fikky) 15.06.20 : berdasarkan hasil assessment/desktop analisis, NOM berada di pemukiman padat, SAR 100m tidak ada space utk proposes GF MCP atau 30m, max tinggi bangunan 2 lantai (RT 7.5m + stacking 4m + pole 6M = 17.5m) 13.06.20 : SPK release
925 |  | JAW-BT-SRG-0037 |  |  |  | X RELOC TBG |  | 106.0689 | -6.0529 | 40 | 0/90/200 |  |  | Kp. Jalumprit RT 06 RW 01 desa waringinkurung kecamatan waringinkurung kabupaten serang-banten | EID | JAW-BT-SRG-0037 | JELUMPIT KIDUL RELOCATION | COLO |  | JABO | JABODETABEK (OUTER) | Banten | Serang | 6614689 | 2020-04-24 |  | 734 | > 150 days | 2020-05-24 | W22-2020 | May-2020 | RFI |  |  | TBD | TBD | TBD | RFI |  |  | MW | [13 empty] | 38.RFI | 21.RFI | CLOSED - RFI DONE | 04.06.20 : 01.06.20 : 29.05.20 : RFI
923 |  | SUM-BB-SGL-0534 |  |  |  | X RELOC TBG |  | 105.7784 | -1.6283 | 50 | 100/200/310 |  | RELOCATION | jalan Lurus RT 01 Lingkungan I | HTI | SUM-BB-SGL-0534 | BUKIT KETOK BELINYU RELOCATION | COLO | TBG | WEST | SUMBAGSEL | Kep. Bangka Belitung | Kab. Bangka Induk | 6614692 | 2020-04-24 |  | 734 | > 150 days | 2020-05-24 | W22-2020 | May-2020 |  |  |  | TBD | TBD | TBD |  |  |  | MW | [13 empty] | 38.RFI | 21.RFI | CLOSED - RFI DONE
629 |  | JAW-JT-PML-0955 | 30591130031 | 140096109 | SURAJAYA | ACTIVE - RELOCATION | TI | 109.3785 | -6.9922 | 50 | 90/210/330 |  |  | Desa Lenggrong RT.04 RW.01 Kec.Bantarbolang, Kab.Pemalang Prov. Jawa Tengah | EID | JAW-JT-PML-0955 | Surajaya Relocation | COLO |  | CENTRAL | JATENG | Jawa Tengah | Kab. Pemalang | 6614590 | 2020-03-27 |  | 123 | 121 - 150 days | 2020-04-26 | W18-2020 | Apr-2020 | 2020-05-28 | W22-2020 | May-2020 | 2020-07-23 | W30-2020 | Jul-2020 | 2020-07-29 | W31-2020 | Jul-2020 | MW | 2020-07-08 |  | 522531764667 | 7,7 |  |  |  | 2020-05-28 | 2020-07-28 | W31-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.07.20 : RFIN sent 23.07.20 : nomor register PLN release, plan bayar BP besok 24 jul, plan connect PLM/RFI 29 jul 20 20.07.20 : 16.07.20 : 13.07.20 : SK PLN release 09.07.20 : 08.07.20 : email konfirmasi request PLN connection from XL, SK PLN request done, plan connect 23 juli 02.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL, plan RFI adalah SK PLN release+14 hari 28.05.20 : SRFIN sent, wait XL confirmation untuk connect PLN nya
627 |  | JAW-JB-GRT-3975 | 30590580031 | 122876109 | JL TELADAN GARUT | ACTIVE - RELOCATION | SKP | 107.9053 | -7.214 | 33 | 100/235/310 |  | RELOCATION | Jl. Kenanga, Kel. Pakuwon RT.002 RW.007, Kec. Garut Kota, Kab. Garut Prov. Jawa Barat | HTI | JAW-JB-GRT-3975 | GARUT RELOCATION | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Garut | 6614537 | 2020-03-13 |  | 87 | 61 - 90 days | 2020-04-12 | W16-2020 | Apr-2020 | 2020-05-28 | W22-2020 | May-2020 | 2020-07-27 | W31-2020 | Jul-2020 | 2020-07-27 | W31-2020 | Jul-2020 | MW | 2020-04-16 |  | 532711684787 | 6.6 |  |  |  | 2020-05-10 | 2020-06-08 | W24-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.06.20 : RFIN sent 07.06.20 : actual RFI, PLN connect 7 jun 20, plan submit RFIN 8 jun 14.05.20 : 10.05.20 : SRFIN sent, wait plan MOS & konfirmasi permintaan PLN connection dari XL/tech part 06.05.20 : email konfirmasi permintaan PLN connection dari XL (Pak Ari F) 06.05.20 : ME on going 30.04.20 : pabrikasi material baseframe 23.04.20 : 16.04.20 : STIP input, CME preparation 09.04.20 : 02.04.20 : 25.03.20 : under TNP review HTI
926 |  | JAW-JB-BDG-3982 |  |  |  | X RELOC TBG |  | 107.6096 | -6.9635 | 50 | 90/120/330 |  | RELOCATION | Komp. Perumahan Cibiuk Indah Kel.Pesawahan Bandungel.Pesawahan Bandung | HTI | JAW-JB-BDG-3982 | NARADIREJABANDUN RELOCATION | COLO | TBG | CENTRAL | JABAR | Jawa Barat | Bandung | 6614512 | 2020-02-26 |  | 792 | > 150 days | 2020-03-27 | W13-2020 | Mar-2020 | 2020-04-22 | W17-2020 | Apr-2020 | 2020-04-11 | W15-2020 | Apr-2020 | 2020-06-21 | W26-2020 | Jun-2020 | MW | [13 empty] | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30.04.20 : RFI done dan OA 23.04.20 : mob demob
614 |  | SUM-KR-TBK-0587 | 30579870031 | 0505871003 | TAMBANG BATU GRANIT RELOCATION | ACTIVE - RELOCATION | TB | 103.3405 | 1.1139 | 50 | 90/120/330 |  | RELOCATION | Kawasan Perumahan PT. Karimun Granite Desa Pasir Panjang Kecamatan Meral Barat Kabupaten Karimun Provinsi Kepuluan Riau | HTI | SUM-KR-TBK-0587 | TAMBANG BATU GRANIT RELOCATION | B2S | TBG | WEST | SUMBAGTENG | Kep. Riau | Kab. Karimun | 6614468 | 2020-02-10 |  | 272 | > 150 days | 2020-07-09 | W28-2020 | Jul-2020 | 2020-10-30 | W44-2020 | Oct-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-11-09 | W46-2020 | Nov-2020 | MW | 2020-10-26 |  | 183051486670 | 6.6 |  |  |  |  | 2020-11-08 | W46-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 09.11.20 : RFIN sent 05.11.20 : proses collect dokumen RFIN 02.11.20 : ME done, PSB released, proses konek PLN 29.10.20 : 26.10.20 : 22.10.20 : Erection 6 section, Pondasi bts done, Pagar OG. 19.10.20 : erection 5 section, pondasi BTS done, need PSB PLN 15.10.20 : prepare erection, PLN connection menunggu konfirmasi XL karena site relocation 12.10.20 : 08.10.20 : curingtime, material tower ready, plan start erection 12 oct 07.10.20 : pouring concrete foundation done 05.10.20 : rebarring 01.10.20 : plan start CME 3 oct 20 28.09.20 : 21.09.20 : 14.09.20 : rekom done, proses perijinan 07.09.20 : 03.09.20 : rekom on going 31.08.20 : 27.08.20 : 24.08.20 : rekom L/C, Dependency doc Legal PT Karimun Granite 17.08.20 :13.08.20 : proses review pengajuan biaya Sitac 10.08.20 : plan RFC minggu ini 06.08.20 : 03.08.20 : 30.07.20 : proses perijinan dari managemen pusat PT Karimun Granite 23.07.20 : kandidat A approved dengan RF 50m, MW height 45m/1.2m, proses pengiriman surat ke PT Karimun Granite konfirmasi persetujuan dari pihak XL 09.07.20 : proses disposisi dari OSO pusat ke Regional terkait plan survey 02.07.20 : 29.06.20 : sdh ada jawaban verbal bahwa bisa survey, hari ini dikejar jawaban tertulisnya untuk selanjutnya dilakukan join visit dilapangan untuk penentuan titik yg diizinkan 22.06.20 : 18.06.20 : 15.06.20 : TBG mengirim ulang surat kepada OSO Group untuk follow up/meminta konfirmasi 11.06.20 : 08.06.20 : 04.06.20 : 01.06.20 : 28.05.20 : masih menunggu jawaban dari OSO Group 25.05.20 : BAN on going 15.05.20 : 30.04.20 : rehunting 23.04.20 : 16.04.20 : paralel rehunting, Proses Persetujuan dr PT Karimun Granite jakarta 09.04.20 : 02.04.20 : Proses Persetujuan dr PT Karimun Granite jakarta 25.03.20 : rehunting 19.03.20 : 26.02.20 : hasil survey dan hunting, NOM berada di kawasan hutan lindung dan daerah sengketa lahan antara warga dan PT. Karimun Granite 20.02.20 : hunting, on going survey 10.02.20 : SPK released
611 |  | JAW-JB-BGR-0400 | 30597810031 | 123061109 | JALAN RAYA PEMUDA | ACTIVE - CME by XL (RELOCATION) | SKP | 106.8121 | -6.5442 | 50 | 90/210/330 |  |  | Jl. Pembangunan Kaum RT 04 RW 11 Kel. Ciparigi Kec. Bogor Utara, Kota Bogor Prov. Jawa Barat | EID | JAW-JB-BGR-0400 | VILLA BOGOR RELOCATION | COLO | XL | JABO | JABODETABEK (OUTER) | Jawa Barat | Bogor | 6614459 | 2020-02-04 |  | 275 | > 150 days | 2020-03-05 | W10-2020 | Mar-2020 | CME BY XL |  |  | TBD | TBD | TBD | CME BY XL |  |  | MW | [8 empty] | 2020-11-05 | W45-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.11.20 : aktual RFI 31.08.20 : 27.08.20 : CME BY XL, Soft RFI 11.03.20 : CME BY XL 06.02.20 : ERM, under review RND EID
371 |  | JAW-JK-CKG-0247 | 30574860031 | 110468109 | PPA DEPSOS | ACTIVE | SKP | 106.8984 | -6.319 | 36 | 30/100/210/290 |  |  | Jl. Swadaya II Rt.003/01, Kel. Bambu Apus, Kec. Cipayung | EID | JAW-JK-CKG-0247 | Jalan Beringin Raya | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614409 | 2020-01-16 |  | 27 | < 30 days | 2020-02-15 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-17 | W08-2020 | Feb-2020 | 2020-02-17 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 547202154524 | 6.6 |  |  |  |  | 2020-02-12 | W07-2020 |  | 2020-09-05 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.02.20 : 12.02.20 : RFIN sent 06.02.20 : CME done/Soft RFI, wait PLN connection plan 12 feb 30.01.20 : OG RBS Foundation
433 |  | JAW-JB-CBI-0083 | 30575110031 | 122284109 | TELAGA KAHURIPAN2 | ACTIVE | SKP | 106.7187 | -6.4802 | 42 | 70/150/250/330 |  |  | Jl. Kampung Kandang, Rt.05/ Rw.02, Kel. Tegal / Kec. Kemang, Bogor-Jawa Barat | EID | JAW-JB-CBI-0083 | Kahuripan Kemang | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614409 | 2020-01-16 |  | 29 | < 30 days | 2020-02-15 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 538414539858 | 6.6 |  |  |  |  | 2020-02-14 | W07-2020 |  | 2020-06-26 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.02.20 : RFIN sent 13.02.20 : CME done/Soft RFI, wait PLN connection 06.02.20 : OG ME installation 30.01.20 : OG RBS Foundation
367 |  | JAW-JK-GGP-0526 | 30578600031 | 110453109 | PETA SEMANGAN TANEGRANG | ACTIVE | SKP | 106.6977 | -6.1721 | 25 | 90/180/270 |  |  | Jl. Gaga Utama (Samping SMP N 187) kp. Gaga Rt. 01/03, Kel. Semanan, Kec. Kalideres Jakarta Barat | EID | JAW-JK-GGP-0526 | Jalan Haji Aseni | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA BARAT | 6614409 | 2020-01-16 |  | 33 | 31 - 60 days | 2020-02-15 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-24 | W09-2020 | Feb-2020 | 2020-02-24 | W09-2020 | Feb-2020 | MW | 2020-01-28 |  | 546303032728 | 6.6 |  |  |  |  | 2020-02-18 | W08-2020 |  | 2020-07-04 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18.02.20 : RFIN sent 13.02.20 : OG Baseframe installation, material on site 06.02.20 : OG pabrikasi baseframe (RT), plan material baseframe on site 11 Feb 30.01.20 : OG pabrikasi baseframe (RT)
439 |  | NUS-NT-KPG-0265 | 30574510031 | 190621109 | TUAPUKAN KUPANG TIMUR | ACTIVE | TB | 123.773 | -10.109 | 40 | 70/150/260 |  |  | Jl Timor Raya Desa Tuapukan , RT 003 / RW 002 , Dusun 1 | ALT | NUS-NT-KPG-0265 | Tuapukan | COLO |  | EAST | BALINUSRA | Nusa Tenggara Timur | Kab. Kupang | 6614398 | 2020-01-15 |  | 42 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-25 | W09-2020 | Feb-2020 | MW | 2020-01-27 | [7 empty] | 2020-02-26 | W09-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.02.20 : RFIN sent 25.02.20 : RFIcatual. collec doc RFIN 20.02.20 : 17.02.20 : XL approved KWH pra bayar dengan pengisian token awal 1 juta by TBG, plan RFI 25 feb 20 13.02.20 : eskalasi terkait surat jawaban PLN yang melayani sambungan PRA BAYAR (Token), need approval XL 06.02.20 : CME done (Soft RFI), PLN connection terkendala isu stock kwh meter pasca bayar, jika pra bayar kwh ready (menunggu surat jawab PLN terkait istu stock KWH meter pasca bayar) 30.01.19 : OG RBS Foundation, delivery material, isu stock kwh meter pasca bayar, jika pra bayar kwh ready (need approval XL)
349 |  | NUS-NT-KPG-0257 | 30574040031 | 190372109 | NOELBAKI 2 | ACTIVE | SKP | 123.7 | -10.1319 | 40 | 60/130/245 |  |  | JL. TIMOR RAYA KM 15 RT 003/01, DESA NOELBAKI KEC. KUPANG TENGAH, NUSA TENGGARA TIMUR | ALT | NUS-NT-KPG-0257 | Timor Noelbaki | COLO |  | EAST | BALINUSRA | Nusa Tenggara Timur | Kab. Kupang | 6614393 | 2020-01-15 |  | 33 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-13 | W07-2020 | Feb-2020 | 2020-02-25 | W09-2020 | Feb-2020 | MW | 2020-01-27 | [7 empty] | 2020-02-17 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.02.20 : RFIN sent 13.02.20 : actual RFI, collecting doc RFIN 06.02.20 : CME done (Soft RFI), PLN connection terkendala isu stock kwh meter pasca bayar, jika pra bayar kwh ready (menunggu surat jawab PLN terkait istu stock KWH meter pasca bayar) 30.01.19 : OG RBS Foundation, delivery material, isu stock kwh meter pasca bayar, jika pra bayar kwh ready (need approval XL)
295 |  | JAW-JT-KDS-0872 | 30574770031 | 140360109 | GAMONG | ACTIVE | TB | 110.7729 | -6.7908 | 50 | 15/150/295 |  |  | Jl Raya Jetak Blimbing Kidul RT 01 RW 02 Kel.Banget Kec.Kaliwungu Kab.Kudus, Jawa Tengah | EID | JAW-JT-KDS-0872 | BANGET KALIWUNGU | COLO |  | CENTRAL | JATENG | Jawa Tengah | KUDUS | 6614397 | 2020-01-15 |  | 71 | 61 - 90 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-14 | W07-2020 | Feb-2020 | 2020-03-27 | W13-2020 | Mar-2020 | FO | 2020-01-27 |  | 520013233917 | 7.7 |  |  |  |  | 2020-03-26 | W13-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.03.20 : RFIN sent 25.03.20 : ACTUAL RFI, collecting doc RFIN 11.03.20 : 03.04.20 : plan RFIN 03.05.20 26.02.20 : SRFI, plan RFI+ MG 28 Feb 20.02.20 : 13.02.20 : RBS Foundation done 06.02.20 : OG RBS Foundation 30.01.19 : Mobilisasi team, delivery material, plan start CME 1 Feb
309 |  | JAW-JT-BYL-0233 | 30575560031 | 141151109 | JRAKAH BOYOLALI | ACTIVE | TB | 110.4171 | -7.4981 | 50 | 25/85/285 |  |  | Dsn. Bangunrejo RT.03/02 Ds. Jrakah, Kec. Selo, Kab. Boyolali | EID | JAW-JT-BYL-0233 | JRAKAH BOYOLALI | COLO |  | CENTRAL | JATENG | Jawa Tengah | BOYOLALI | 6614397 | 2020-01-15 |  | 71 | 61 - 90 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-14 | W07-2020 | Feb-2020 | 2020-03-27 | W13-2020 | Mar-2020 | MW | 2020-01-28 |  | 521541317303 | 7,7 |  |  |  |  | 2020-03-26 | W13-2020 |  | 2020-07-17 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.03.20 : RFIN sent 25.03.20 : ACTUAL RFI, collecting doc RFIN 11.03.20 : 03.04.20 : plan RFIN 03.05.20 26.02.20 : SRFI, plan RFI+ MG 28 Feb 20.02.20 : 13.02.20 : ME & Grounding installataion 06.02.20 : 30.01.19 : Mobilisasi team, delivery material, plan start CME 1 Feb
341 |  | JAW-JT-BLA-0146 | 30574790031 | 142717126 | MENDEN RANDUBLATUNG | ACTIVE | TB | 111.4224 | -7.2308 | 40 | 30/100/300 |  |  | Ds Ngampon RT.01 RW.04 Desa Mendenrejo Kecamatan Kradenan Kabupaten Blora | EID | JAW-JT-BLA-0146 | Temulus Randublatung | COLO |  | CENTRAL | JATENG | Jawa Tengah | BLORA | 6614397 | 2020-01-15 |  | 47 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-14 | W07-2020 | Feb-2020 | 2020-02-25 | W09-2020 | Feb-2020 | FO | 2020-01-27 |  | 520081224655 | 7,7 |  |  |  |  | 2020-03-02 | W10-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02.03.20 : RFIN sent 20.02.20 : 13.02.20 : RBS Foundation done 06.02.20 : OG RBS Foundation, delivery material 30.01.19 : Mobilisasi team, delivery material, plan start CME 1 Feb
435 |  | JAW-YO-BTL-0124 | 30575010031 | 150051104 | TIMBULHARJO | ACTIVE | SMI | 110.371 | -7.863 | 40 | 95/190/270/350 |  |  | KLEGEN RT.01/RW.36, KEL. BANGUNHARJO, KEC. SEWON, KAB. BANTUL. | EID | JAW-YO-BTL-0124 | Semar Bangunharjo | COLO |  | CENTRAL | JATENG | DI Yogyakarta | BANTUL | 6614395 | 2020-01-15 |  | 41 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-14 | W07-2020 | Feb-2020 | 2020-02-21 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 521032412856 | 7,7 |  |  |  |  | 2020-02-25 | W09-2020 |  | 2020-07-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.02.20 : RFIN sent 20.02.20 : plan RFI 21 feb 13.02.20 : CME done/Soft RFI, 06.02.20 : 30.01.19 : OG RBS Foundation, delivery material
237 |  | JAW-JT-MKD-1150 | 30574680031 | 141231109 | BALEREJO | ACTIVE | SKP | 110.1282 | -7.4367 | 50 | 80/170/350 |  |  | Dsn Tempel RT001 RW001, Ds Balerejo, Kec Kaliangkrik, Kab Magelang, JAWA TENGAH | EID | JAW-JT-MKD-1150 | Balerejo Kaliangkrik | COLO |  | CENTRAL | JATENG | Jawa Tengah | MAGELANG | 6614392 | 2020-01-15 |  | 41 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-14 | W07-2020 | Feb-2020 | 2020-02-20 | W08-2020 | Feb-2020 | FO | 2020-01-27 |  | 521512290165 | 7,7 |  |  |  |  | 2020-02-25 | W09-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.02.20 : RFIN sent 20.02.20 : CME done/Soft RFI, plan RFI 21 feb 13.02.20 : ME & Grounding installataion 06.02.20 : OG RBS Foundation, delivery material 30.01.19 : Mobilisasi team, delivery material
337 |  | JAW-JT-MKD-1158 | 30574660031 | 140268104 | MARUNGAN | ACTIVE | SKP | 110.074 | -7.4538 | 50 | 125/180/280 |  |  | Jl.Raya Marungan-Kaliangkrik, Ds. Tenggalar, Kel. Sutopati, Kec. Kajoran, Kab. Magelang, Jawa Tengah | EID | JAW-JT-MKD-1158 | Marungan Kajoran Magelang | COLO |  | CENTRAL | JATENG | Jawa Tengah | MAGELANG | 6614392 | 2020-01-15 |  | 41 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-14 | W07-2020 | Feb-2020 | 2020-02-20 | W08-2020 | Feb-2020 | FO | 2020-01-27 |  | 5215111091097 | 7.7 |  |  |  |  | 2020-02-25 | W09-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.02.20 : RFIN sent (MG) 20.02.20 : CME done/Soft RFI, plan RFI 21 feb 13.02.20 : RBS Foundation done 06.02.20 : OG RBS Foundation, delivery material 30.01.19 : Mobilisasi team, delivery material
414 |  | JAW-JT-SMG-0552 | 30574780031 | 140523109 | SURATMO TBG | ACTIVE | TB | 110.3793 | -6.9964 | 30 | 110/240/325 |  |  | Jl. Muradi No.78, RT.07 RW.07, Kel. Kembang Arum, Kec.Semarang Barat, Kota Semarang | EID | JAW-JT-SMG-0552 | WOLOGITO TENGAH | COLO |  | CENTRAL | JATENG | Jawa Tengah | KOTA SEMARANG | 6614397 | 2020-01-15 |  | 41 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-14 | W07-2020 | Feb-2020 | 2020-02-20 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 523024822053 | 7,7 |  |  |  |  | 2020-02-25 | W09-2020 |  | 2020-08-28 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.02.20 : RFIN sent 20.02.20 : CME done/Soft RFI, plan RFI 24 feb 13.02.20 : 06.02.20 : OG RBS Foundation, delivery material 30.01.19 : Mobilisasi team, delivery material
317 |  | JAW-JT-MKD-1159 | 30574670031 | 140448104 | KDSARI TIMUR (WONOKERTO) | ACTIVE | SKP | 110.2401 | -7.4529 | 50 | 50/160/235/335 |  |  | JL. Geger I Kel. Girirejo, Kec Tegalrejo, Kab Magelang | EID | JAW-JT-MKD-1159 | Girirejo Magelang | COLO |  | CENTRAL | JATENG | Jawa Tengah | MAGELANG | 6614392 | 2020-01-15 |  | 33 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-14 | W07-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 521570915045 | 7,7 |  |  |  |  | 2020-02-17 | W08-2020 |  | 2020-09-09 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.02.20 : RFI done, RFIN sent 13.02.20 : ME & Grounding installataion 06.02.20 : OG RBS Foundation, delivery material 30.01.19 : Mobilisasi team, delivery material
296 |  | JAW-JT-PWR-1657 | 30574710031 | 140754104 | GEBANG | ACTIVE | SMI | 110.0132 | -7.6152 | 50 | 10/150/230 |  |  | Ds. Redin RT.01/01 Kec. Gebang Kab.Purworejo | EID | JAW-JT-PWR-1657 | Redin Raya Purworejo | COLO |  | CENTRAL | JATENG | Jawa Tengah | PURWOREJO | 6614395 | 2020-01-15 |  | 30 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-14 | W07-2020 | Feb-2020 | 2020-02-14 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 521521300613 | 7,7 |  |  |  |  | 2020-02-14 | W07-2020 |  | 2020-07-24 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.02.20 : RFIN sent 13.02.20 : actual RFI, collecting doc RFIN 06.02.20 : 30.01.19 : OG RBS Foundation, delivery material
252 |  | JAW-JT-BYL-0232 | 30574820031 | 142879109 | BLUE NGLAJI KEMUSU | ACTIVE | TB | 110.7596 | -7.2786 | 40 | 60/115/200 |  |  | Rejosari RT.01 RW.03 Kel. Kedungmulyo Kec. Kemusu Kab. Boyolali | EID | JAW-JT-BYL-0232 | NGLAJI KEMUSU | COLO |  | CENTRAL | JATENG | Jawa Tengah | BOYOLALI | 6614397 | 2020-01-15 |  | 32 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-15 | W07-2020 | Feb-2020 | 2020-02-15 | W07-2020 | Feb-2020 | MW | 2020-01-27 |  | 520592156890 | 7,7 |  |  |  |  | 2020-02-16 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 16.02.20 : RFIN sent 13.02.20 : CME done/Soft RFI 06.02.20 : RBS Foundation done 30.01.19 : OG RBS Foundation, material ME Grounding tray dan mounting on site
273 |  | JAW-BT-SRG-0020 | 30574600031 | 130962109 | DALUNGRAYACIPETIR | ACTIVE | SKP | 106.1749 | -6.1437 | 40 | 0/90/210 |  |  | Jl. Raya Petir KM 4 RT 02/RW 04 Kel. Cipocok Kec. Cipocok Jaya, Kota Serang | EID | JAW-BT-SRG-0020 | DALUNG RAYA CIPETIR | COLO |  | JABO | JABODETABEK (OUTER) | Banten | KOTA SERANG | 6614392 | 2020-01-15 |  | 30 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-17 | W08-2020 | Feb-2020 | 2020-02-17 | W08-2020 | Feb-2020 | FO | 2020-12-08 |  | 561100613208 | 6.6 |  |  |  |  | 2020-02-14 | W07-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.02.20 : RFIN sent 13.02.20 : 06.02.20 : CME done/Soft RFI, wait PLN connection 30.01.20 : OG RBS foundation
270 |  | JAW-JK-GGP-0523 | 30574590031 | 111118109 | CITRA2 UTAMAI4THW_HBTS | ACTIVE | SKP | 106.7022 | -6.1352 | 36 | 15/140/230/295 |  |  | JL Peta Utara Kampung Maja RT.004 RW.002 Kel. Pegadungan Kec.Kalideres Jakarta Barat | EID | JAW-JK-GGP-0523 | Pegadungan Kali Deres | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA BARAT | 6614392 | 2020-01-15 |  | 30 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-17 | W08-2020 | Feb-2020 | 2020-02-17 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 546303033292 | 6.6 |  |  |  |  | 2020-02-14 | W07-2020 |  | 2020-09-07 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.02.20 : RFIN sent 13.02.20 : 06.02.20 : CME done/Soft RFI, wait PLN connection 30.01.20 : OG RBS foundation
375 |  | JAW-BT-SRG-0023 | 30574810031 | 131525126 | PURIANGGREKSERANG | ACTIVE | TB | 106.2093 | -6.1102 | 50 | 120/190/300 |  |  | Kp.Kewunen RW02 Kel.Teritih Kec. Walantaka | EID | JAW-BT-SRG-0023 | PURI ANGGREK SERANG | COLO |  | JABO | JABODETABEK (OUTER) | Banten | KOTA SERANG | 6614397 | 2020-01-15 |  | 30 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-17 | W08-2020 | Feb-2020 | 2020-02-17 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 561100613224 | 6.6 |  |  |  |  | 2020-02-14 | W07-2020 |  | 2020-05-26 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.02.20 : RFIN sent 13.02.20 : 06.02.20 : CME done/Soft RFI, wait PLN connection 30.01.20 : OG RBS foundation
410 |  | JAW-YO-SMN-0032 | 30575020031 | 150068104 | SUMBERHARJO | ACTIVE | SMI | 110.4833 | -7.811 | 40 | 130/245/350 |  |  | Dsn. Jlatren, Ds. Jogoroto, Kec.Berbah, Kab. Sleman, Daerah Istimewa Yogyakarta | EID | JAW-YO-SMN-0032 | JLATREN JOGOTIRTO | COLO |  | CENTRAL | JATENG | DI Yogyakarta | SLEMAN | 6614395 | 2020-01-15 |  | 71 | 61 - 90 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-03-27 | W13-2020 | Mar-2020 | MW | 2020-01-27 |  | 521012878127 | 5,5 |  |  |  |  | 2020-03-26 | W13-2020 |  | 2020-09-07 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.03.20 : RFIN sent 25.03.20 : ACTUAL RFI, daya PLN 5.5 kVA sesuai approval XL 11.03.20 : OVB 20.02.20 : plan RFI 21 Feb 13.02.20 : CME done/Soft RFI 06.02.20 : OG RBS Foundation 30.01.19 : Mobilisasi team, delivery material, plan start CME 1 Feb
251 |  | JAW-JT-BLA-0145 | 30578700031 | 142885109 | BLUE KARANG BOGOREJO | ACTIVE | TB | 111.4966 | -6.9479 | 50 | 70/250/345 |  |  | Prantaan, RT.005 RW.001 Desa Prantaan, Kecamatan Bogorejo, Kabupaten Blora | EID | JAW-JT-BLA-0145 | Prantaan Bogorejo | COLO |  | CENTRAL | JATENG | Jawa Tengah | BLORA | 6614397 | 2020-01-15 |  | 64 | 61 - 90 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-03-15 | W12-2020 | Mar-2020 | FO | 2020-01-29 |  | 520071553061 | 7,7 |  |  |  |  | 2020-03-19 | W12-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.06.20 : SPK FO/MMP release 19.03.20 : RFIN sent 11.03.20 : 03.04.20 : plan RFIN 03.05.20 26.02.20 : SRFI, plan RFI+ MG 28 Feb 20.02.20 : : RBS Foundation done 13.02.20 : OG RBS Foundation 06.02.20 : 30.01.19 : Mobilisasi team, delivery material
240 |  | JAW-YO-WNO-0010 | 30574830031 | 150033109 | BALONG | ACTIVE | TB | 110.4418 | -8.0334 | 50 | 40/125/230 |  |  | Jl.Wonosari - Panggang Km.3 RT 02/ RW 05 Girimulyo, Kec.Panggang - Kab.Gunung Kidul Prop.Daerah Istimewa Yogyakarta | EID | JAW-YO-WNO-0010 | Balong Panggang | COLO |  | CENTRAL | JATENG | DI Yogyakarta | GUNUNGKIDUL | 6614397 | 2020-01-15 |  | 41 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-21 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 521052206026 | 7,7 |  |  |  |  | 2020-02-25 | W09-2020 |  | 2020-07-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.02.20 : RFIN sent 20.02.20 : CME done/Soft RFI, plan RFI 21 Feb 13.02.20 : RBS Foundation done 06.02.20 : OG RBS Foundation 30.01.19 : Mobilisasi team, delivery material, plan start CME 1 Feb
314 |  | JAW-YO-WNO-0011 | 30574840031 | 150037109 | KANIGORO | ACTIVE | TB | 110.5228 | -8.0908 | 50 | 85/225/320 |  |  | Dusun Mendak RT 6/RW 3 Desa Kanigoro Kec.Saptosari Kab.Gunung Kidul Prop Daerah Ostimewa | EID | JAW-YO-WNO-0011 | Kanigoro Saptosari | COLO |  | CENTRAL | JATENG | DI Yogyakarta | GUNUNGKIDUL | 6614397 | 2020-01-15 |  | 41 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-21 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 521052206018 | 7,7 |  |  |  |  | 2020-02-25 | W09-2020 |  | 2020-08-27 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.02.20 : RFIN sent 20.02.20 : CME done/Soft RFI, plan RFI 21 Feb 13.02.20 : RBS Foundation done 06.02.20 : OG RBS Foundation 30.01.19 : Mobilisasi team, delivery material, plan start CME 1 Feb
297 |  | JAW-JT-CLP-0538 | 30574620031 | 140210104 | GRUGU | ACTIVE | SKP | 108.9117 | -7.6552 | 50 | 40/170/330 |  |  | Desa Grugu Karangsalam RT/RW 03/03, Kec.Kawunganten, Kabupaten Cilacap, Jawa Tengah | EID | JAW-JT-CLP-0538 | Bayaragas Grugu | COLO |  | CENTRAL | JATENG | Jawa Tengah | CILACAP | 6614392 | 2020-01-15 |  | 40 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-21 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 525061472821 | 7,7 |  |  |  |  | 2020-02-24 | W09-2020 |  | 2020-07-24 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.02.20 : RFIN sent 20.02.20 : actual RFI, collecting doc RFIN 13.02.20 : CME done/Soft RFI 06.02.20 : RBS Foundation done 30.01.19 : OG RBS Foundation, material ME Grounding tray dan mounting on site
312 |  | JAW-JT-PBG-1250 | 30574650031 | 141619109 | KALIKAJAR BANYUMAS | ACTIVE | SKP | 109.4214 | -7.3601 | 50 | 85/185/270 |  |  | Jl. Ds. Sidanegara RT 01 RW 03, Ds. Sidanegara, Kec. Kaligondang, Kab. Purbalingga | EID | JAW-JT-PBG-1250 | KALIKAJAR BANYUMAS | COLO |  | CENTRAL | JATENG | Jawa Tengah | PURBALINGGA | 6614392 | 2020-01-15 |  | 40 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-21 | W08-2020 | Feb-2020 | FO | 2020-01-27 |  | 522032553260 | 7,7 |  |  |  |  | 2020-02-24 | W09-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.02.20 : RFIN sent 20.02.20 : 13.02.20 : actual RFI, collecting doc RFIN 06.02.20 : RBS Foundation done 30.01.19 : OG RBS Foundation, material ME Grounding tray dan mounting on site
359 |  | JAW-JT-PWT-0543 | 30574720031 | 140771104 | PEKUNCEN | ACTIVE | SMI | 109.0636 | -7.3481 | 50 | 45/125/260 |  |  | KAMPUNG SINDANG, DS KARANGKEMIRI, KEC. PEKUNCEN, KAB. BANYUMAS | EID | JAW-JT-PWT-0543 | Karangkemiri Pekuncen | COLO |  | CENTRAL | JATENG | Jawa Tengah | BANYUMAS | 6614395 | 2020-01-15 |  | 40 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-21 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 522060957324 | 7,7 |  |  |  |  | 2020-02-24 | W09-2020 |  | 2020-06-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.02.20 : RFIN sent 20.02.20 : 13.02.20 : actual RFI, collecting doc RFIN 06.02.20 : RBS Foundation done 30.01.19 : OG RBS Foundation, material ME Grounding tray dan mounting on site
441 |  | JAW-JT-BNR-0257 | 30574630031 | 140218104 | WANADRI | ACTIVE | SKP | 109.6055 | -7.4574 | 50 | 70/180/270/320 |  |  | Desa Wiramastra RT 04 RW 06, kec. Bawang, Kabupaten Banjarnegara, Jawa Tengah | EID | JAW-JT-BNR-0257 | Wiramastra Bawang | COLO |  | CENTRAL | JATENG | Jawa Tengah | BANJARNEGARA | 6614392 | 2020-01-15 |  | 40 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-21 | W08-2020 | Feb-2020 | FO | 2020-01-27 |  | 522042745265 | 7,7 |  |  |  |  | 2020-02-24 | W09-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.02.20 : RFIN sent 20.02.20 : 13.02.20 : actual RFI, collecting doc RFIN 06.02.20 : RBS Foundation done 30.01.19 : OG RBS Foundation, material ME Grounding tray dan mounting on site
253 |  | JAW-JB-KWG-1046 | 30574800031 | 123506109 | BNTNG_ALAM_KRWNG | ACTIVE | TB | 107.3215 | -6.3341 | 30 | 0/90/160/250 |  |  | Dsn. Bintang Alam RT 06 / 012 Desa Teluk Jambe Kec. Teluk Jambe Timur Kab. Karawang | EID | JAW-JB-KWG-1046 | Telukjambe Telukjambe Timur | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | KARAWANG | 6614397 | 2020-01-15 |  | 37 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-21 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 534757708232 | 6.6 |  |  |  |  | 2020-02-21 | W08-2020 |  | 2020-07-04 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.02.20 : RFI hanya minus mounting, plan 21 Feb pasang mounting, plan RFI 21 Feb 13.02.20 : actual RFI, collecting doc RFIN 11.02.20 : SRFI 06.02.20 : RBS Foundation done, plan material ME on site 8 Feb 30.01.20 : OG RBS Foundation
364 |  | JAW-BT-CPT-0477 | 30574980031 | 130008102 | PERMATA PAMULANG | ACTIVE | BK | 106.7008 | -6.343 | 42 | 90/215/320 |  |  | Jl. H. Jamat Kp. Jati RT. 14/05 Ds. Buaran Serpong | EID | JAW-BT-CPT-0477 | Bumi Serpong Residence | COLO |  | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614376 | 2020-01-15 |  | 35 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | FO | 2020-12-08 |  | 543602474960 | 6.6 |  |  |  |  | 2020-02-19 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.02.20 : RFI actual, RFIN sent 13.02.20 : CME done/Soft RFI, wait PLN connection 06.02.20 : 30.01.20 : OG RBS Foundation
302 |  | JAW-JT-BBS-0157 | 30575030031 | 140588104 | INDRAJAYA | ACTIVE | SMI | 108.7749 | -7.1751 | 50 | 65/220/260 |  |  | DESA INDRA JAYA, KEC.SALEM, KAB.BREBES | EID | JAW-JT-BBS-0157 | Indrajaya Salem Brebes | COLO |  | CENTRAL | JATENG | Jawa Tengah | BREBES | 6614395 | 2020-01-15 |  | 35 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | FO | 2020-01-27 |  | 522561313226 | 7,7 |  |  |  |  | 2020-02-19 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.02.20 : RFI sent 13.02.20 : actual RFI, collecting doc RFIN 06.02.20 : RBS Foundation done 30.01.19 : OG RBS Foundation, material ME Grounding tray dan mounting on site
351 |  | JAW-JT-BNR-0258 | 30574640031 | 141617109 | PAGEDONGAN2 | ACTIVE | SKP | 109.6626 | -7.4219 | 50 | 70/205/290 |  |  | Dusun Semayun RT.01 RW. 03, Desa Gentansari, Kec. Pagedongan, Kab. Banjarnegara | EID | JAW-JT-BNR-0258 | Pucang Gentansari | COLO |  | CENTRAL | JATENG | Jawa Tengah | BANJARNEGARA | 6614392 | 2020-01-15 |  | 35 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | FO | 2020-01-27 |  | 522042745257 | 7,7 |  |  |  |  | 2020-02-19 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.02.20 : RFI sent 13.02.20 : actual RFI, collecting doc RFIN 06.02.20 : RBS Foundation done 30.01.19 : OG RBS Foundation, material ME Grounding tray dan mounting on site
389 |  | JAW-JB-SBM-2102 | 30574700031 | 121387104 | SAMPORA | ACTIVE | SMI | 106.582 | -7.331 | 50 | 15/100/260 |  |  | Kp. Cimahi Rt.02/Rw.02 , Ds. Citanglar, Kec. Surade, Kab. Sukabumi. | EID | JAW-JB-SBM-2102 | CITANGLAR SURADE | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | SUKABUMI | 6614395 | 2020-01-15 |  | 30 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 536311975714 | 6.6 |  |  |  |  | 2020-02-14 | W07-2020 |  | 2020-06-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.02.20 : RFIN sent 13.02.20 : actual RFI, collecting doc RFIN 06.02.20 : CME done/Soft RFI, wait PLN connection 30.01.20 : OG RBS Foundation
305 |  | JAW-JB-CBI-0074 | 30581650031 | 122188109 | JAMPANG JABON MEKAR | ACTIVE | SKP | 106.7212 | -6.4573 | 50 | 30/160/350 |  |  | Jln. Lengkong Barang Rt.003 Rw.002, Kel. Iwul / Kec. Parung, Bogor-Jawa Barat | EID | JAW-JB-CBI-0074 | Iwul Parung | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614392 | 2020-01-15 |  | 30 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | FO | 2020-12-08 |  | 538414539841 | 6.6 |  |  |  |  | 2020-02-14 | W07-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.02.20 : RFIN sent 13.02.20 : CME done/Soft RFI, wait PLN connection 06.02.20 : OG ME installation 30.01.20 : OG RBS Foundation
262 |  | JAW-JB-CKR-0043 | 30574750031 | 120585109 | CI RANGGON | ACTIVE | TB | 107.0809 | -6.3607 | 50 | 0/90/180/270 |  |  | Kp. Jati RT04/02, Ds. Sukasejati, Kec. Cikarang Selatan, Bekasi | EID | JAW-JB-CKR-0043 | Cibening Cikarang Selatan | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | BEKASI | 6614397 | 2020-01-15 |  | 29 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 537030212576 | 6.6 |  |  |  |  | 2020-02-13 | W07-2020 |  | 2020-06-22 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.02.20 : actual RFI, RFIN done 06.02.20 : RBS Foundation done, plan material ME on site 8 Feb 30.01.20 : OG RBS Foundation
333 |  | JAW-JB-SBM-2103 | 30574730031 | 121395104 | MANGGAH_DUA | ACTIVE | SMI | 106.7441 | -6.9825 | 50 | 0/80/170 |  |  | Jl Bojong Kerta, Kp Sindang Resmi, Ds Bojongkerta, RT02/10, Kec Warung Kiara, Kab Sukabumi | EID | JAW-JB-SBM-2103 | BOJONGKERTA | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | SUKABUMI | 6614395 | 2020-01-15 |  | 28 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 536411512282 | 6.6 |  |  |  |  | 2020-02-12 | W07-2020 |  | 2020-07-01 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.02.20 : 12.02.20 : RFIN sent 06.02.20 : CME done/Soft RFI, wait PLN connection 30.01.20 : OG RBS Foundation
263 |  | JAW-JB-SBM-2107 | 30574690031 | 122178104 | CIBUNTU | ACTIVE | SKP | 106.733 | -6.8042 | 40 | 60/130/330 |  |  | Kp.Pasir Muncang, Rt 16/05, Desa Cipanengah, Kec.Bojonggenteng, SUKABUMI, Jawa Barat | EID | JAW-JB-SBM-2107 | CIPANENGAH BOJONGGENTENG | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | SUKABUMI | 6614392 | 2020-01-15 |  | 28 | < 30 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-18 | W08-2020 | Feb-2020 | 2020-02-18 | W08-2020 | Feb-2020 | MW | 2020-01-27 |  | 536211817024 | 6.6 |  |  |  |  | 2020-02-12 | W07-2020 |  | 2020-05-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.02.20 : 12.02.20 : RFIN sent 06.02.20 : CME done/Soft RFI, wait PLN connection 30.01.20 : OG RBS Foundation
269 |  | JAW-BT-TGR-0034 | 30578970031 | 131238109 | CISAUKBANTEN | ACTIVE | SKP | 106.6321 | -6.3286 | 36 | 0/70/190/270 |  |  | Jl. Cisauk Girang, Cisauk, Tangerang, Banten 15341 | EID | JAW-BT-TGR-0034 | Padat Karya Cisauk | COLO |  | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614392 | 2020-01-15 |  | 44 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-22 | W08-2020 | Feb-2020 | 2020-02-22 | W08-2020 | Feb-2020 | MW | 2020-02-17 |  | 566201353287 | 6.6 |  |  |  |  | 2020-02-28 | W09-2020 |  | 2020-07-28 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.02.20 : RFIN sent 26.02.20 : plan connect PLN & RFI 29 Feb 20 13.02.20 : Pondasi done, OG ME Grounding 06.02.20 : preparation 04.02.20 : ERM done
344 |  | JAW-JT-BBS-0151 | 30575540031 | 141876109 | NDEBLAG KOBER | ACTIVE | TB | 109.0102 | -7.2413 | 50 | 85/240/355 |  |  | Talok RT003 RW005, Kel Dukuh Turi, Kec Bumi Ayu, Kab Brebes | EID | JAW-JT-BBS-0151 | Diponegoro Dukuhturi | COLO |  | CENTRAL | JATENG | Jawa Tengah | BREBES | 6614397 | 2020-01-15 |  | 35 | 31 - 60 days | 2020-02-14 | W07-2020 | Feb-2020 | RFI |  |  | 2020-02-23 | W09-2020 | Feb-2020 | 2020-02-23 | W09-2020 | Feb-2020 | FO | 2020-01-27 |  | 522561313234 | 7.7 |  |  |  |  | 2020-02-19 | W08-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.02.20 : RFI sent 13.02.20 : CME done/Soft RFI 06.02.20 : 30.01.19 : Mobilisasi team, delivery material
306 |  | JAW-BT-SRG-0017 | 30575070031 | 131566109 | JAWILANCIKANDE | ACTIVE | TB | 106.3386 | -6.2396 | 42 | 75/185/320 |  |  | Kp. Mandung, Rt.004 Rw.002, Desa Junti, Kec.Jawilan, Kab.Serang, PROP. BANTEN | EID | JAW-BT-SRG-0017 | Penamping Jawilan | COLO |  | JABO | JABODETABEK (OUTER) | Banten | SERANG | 6614397 | 2020-01-15 |  | 125 | 121 - 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-03-10 | W11-2020 | Mar-2020 | 2020-03-10 | W11-2020 | Mar-2020 | 2020-05-20 | W21-2020 | May-2020 | MW | 2020-05-06 |  | 561400702269 | 6.6 |  |  |  | 2020-03-27 | 2020-05-19 | W21-2020 |  | 2020-05-26 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.05.20 : email konfirmasi XL request connect PLN PLN (Pak Wawan), plan connect 20 may if besok SK PLN nya release 27.03.20 : email SRFIN sent 25.03.20 : collecting SRFIN doc 19.03.20 : SRFI, plan RFI dengan FO 2 bulan dari tgl SRFI 11.03.20 : Soft RFI, Plan FO target hanya sampai SRFI, collecting doc SRFI Notification 13.02.20 : progress tower permanent rebarring pondasi, plan cor sabtu 15 Feb 06.02.20 : progress tower permanent galian pondasi 30.01.20 : start CME Colo XL menunggu site permanent RFI akhir Feb, start CME tower permanen 7 feb, plan RFI Colo XL 10 Mar 24.01.20 : DRM OK, site GM, Colo XL menunggu site permanent RFI
241 |  | JAW-BT-SRG-0018 | 30575080031 | 131488126 | BANDUNGBANDUNG | ACTIVE | TB | 106.3022 | -6.2322 | 42 | 40/195/310 |  |  | Kamp Pasir Ampo RT.011 RW.03, Desa Bandung, Kecamatan Bandung, Kab/Kotamadya, Serang Prov. Banten | EID | JAW-BT-SRG-0018 | Babakan Bandung | COLO |  | JABO | JABODETABEK (OUTER) | Banten | SERANG | 6614397 | 2020-01-15 |  | 125 | 121 - 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-05-06 | W19-2020 | May-2020 | 2020-05-06 | W19-2020 | May-2020 | 2020-05-20 | W21-2020 | May-2020 | MW | 2020-05-06 |  | 561400702277 | 6.6 |  |  |  | 2020-03-27 | 2020-05-19 | W21-2020 |  | 2020-05-26 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.05.20 : email RFIN sent 06.05.20 : email konfirmasi XL request connect PLN PLN (Pak Wawan), plan connect 20 may if besok SK PLN nya release 22.04.20 : email permintaan connect PLN oleh Bu Anggie, email request PSB PLN, plan RFI = SK PLN + 14 days (6 may 20) tp SK PLN belum di rilis EID krn material NY ready 02.04.20 : 27.03.20 : SRFIN sent 25.03.20 : ME Installation, plan SOFT RFI 27 Mar 20 19.03.20 : 11.03.20 : curingtime pondasi tower permanen, No FO plan, plan RFI 30 Mar 13.02.20 : 06.02.20 : progress tower permanen preparation start galian pondasi 30.01.20 : start CME Colo XL menunggu site permanent RFI akhir Feb, start CME tower permanen 7 feb, plan RFI Colo XL 10 Mar 24.01.20 : DRM OK, site GM, Colo XL menunggu site permanent RFI
80 |  | JAW-JK-GGP-0515 | 30573650031 | 1127971003 | KAYUMANIS KELAPA DUA | ACTIVE | TB | 106.7654 | -6.2064 | 30 | 0/90/160/270 |  |  | Jalan Inpeksi Kali Pesanggrahan Barat RT 01 RW 06 Kel Srengseng Kec Kembangan Jakarta Barat 11510 | EID | JAW-JK-GGP-0515 | Kayumanis Kelapa Dua | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA BARAT | 6614397 | 2020-01-15 |  | 182 | > 150 days | 2020-06-13 | W24-2020 | Jun-2020 | 2020-05-20 | W21-2020 | May-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 543301728527 | 6.6 |  |  |  | 2020-05-08 | 2020-07-15 | W29-2020 |  | 2020-07-28 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.07.20 : RFIN sent 13.07.20 : 29.06.20 : Proses PLN connection 19.06.20 : SK PLN release, plan RFI 6 Jul 20 08.05.20 : SRFIN sent 30.04.20 : SRFI actual 23.04.20 : 16.04.20 : on going excavation 09.04.20 : preparation CME 02.04.20 : IW Clear 25.03.20 : Candidat NOK, Rehunting 19.03.20 : validasi RND 20.02.20 : 13.02.20 : 06.02.20 : Hunting kandidat, hard sitac 17.01.20 : hasil assessment PDI done (email arief), propose change to colo (email sherly), proses input STIP 1 B2S
291 |  | JAW-JK-CKG-0671 | 30574610031 | 110898109 | DUKUH5MD | ACTIVE | SKP | 106.8767 | -6.293 | 30 | 0/120/190/300 |  |  | Jl. Dukuh 5, Gang Mesjid Al Madinah, RT 002 RW 05, Kel. Dukuh, Kec. Kramat Jati, Jakarta Timur | EID | JAW-JK-CKG-0671 | Dukuh Kramatjati | COLO |  | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614392 | 2020-01-15 |  | 163 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-04-17 | W16-2020 | Apr-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 547104770304 | 6.6 |  |  |  | 2020-05-22 | 2020-06-26 | W26-2020 |  | 2020-07-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.06.20 : RFIN sent 19.06.20 : SK PLN release, plan RFI 6 Jul 20 22.05.20 : email SRFI-N sent 14.05.20 : SRFI actual 08.05.20 : tray OG 30.04.20 : start CME 23.04.20 : 16.04.20 : ME NY start, Proses ijin lingkungan terkait COVID 09.04.20 : CME NY start, team mitra belum mendapatkan ijin kerja karena kawasan RED ZONE 02.04.20 : 25.03.20 : 19.03.20 : 11.03.20 : limited space, pabrikasi stacking baseframe (revisi design), plan RFI 17 Apr 29.02.20 : revisi RFI plan 29 Feb 20 13.02.20 : pabrikasi material stacking 06.02.20 : 30.01.20 : limited space sehingga menggunakan stacking baseframe, OG pabrikasi stacking baseframe 2 minggu
161 |  | JAW-JK-KYB-0101 | 30573610031 | 1127931003 | SITU BABAKAN SRENGSENG SAWAH | ACTIVE | TB | 106.8273 | -6.3401 | 25 | 0/100/190/270 |  |  | Jl. Desa Putra RT 01 RW 06, Kel. Srengseng Sawah Kec. Jagakarsa, Kota Jakarta Selatan, DKI JAKARTA | EID | JAW-JK-KYB-0101 | Situ Babakan Srengseng Sawah | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614397 | 2020-01-15 |  | 169 | > 150 days | 2020-06-13 | W24-2020 | Jun-2020 | 2020-06-02 | W23-2020 | Jun-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-10 | W28-2020 | Jul-2020 | MW | 2020-06-12 |  | 547401708346 | 6.6 |  |  |  | 2020-06-17 | 2020-07-02 | W27-2020 |  | 2020-08-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02.07.20 : RFIN sent 29.06.20 : Proses PLN Connection 18.06.20 : 17.06.20 : email SRFI-N sent 15.06.20 : ME on going 11.06.20 : prepare erection 08.06.20 : excavation on going 04.06.20 : excavation on going 01.06.20 : 29.05.20 : plan start galian besok 28.05.20 : 26.05.20 : plan start gali besok 27 May 20 14.05.20 : 08.05.20 : rekom, RFC 30.04.20 : IW OG, Terbatasnya komunikasi dengan perangkat kelurahan karena WFH 23.04.20 : 16.04.20 : IW OG, Terbatasnya komunikasi dengan perangkat kelurahan karena WFH 09.04.20 : Proses perijinan lingkungan dan Kelurahan, info pelayanan kelurahan sementara masih tutup terkait wabah corona. 02.04.20 : 25.03.20 : IW on going 19.03.20 : validasi TNP 20.02.20 : kand A = kandidat A, waiting approval menjadi MCP 20m 13.02.20 : 06.02.20 : Kand A = Candidate A Submit 17.01.20 : hasil assessment PDI done (email arief), propose change to colo (email sherly), proses input STIP 1 B2S
311 |  | JAW-JT-BYL-0208 | 30574740031 | 141869109 | KADIPIRO 3 | ACTIVE | TB | 110.8098 | -7.5301 | 30 | 90/220/315 |  |  | Dusun Padokan, RT.001 Rw.005, Desa Sawahan, Kec Ngemplak, Kab Boyolali | EID | JAW-JT-BYL-0208 | KARANGMOJO NGEMPLAK | COLO |  | CENTRAL | JATENG | Jawa Tengah | BOYOLALI | 6614397 | 2020-01-15 |  | 161 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-04-12 | W16-2020 | Apr-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-07-10 | W28-2020 | Jul-2020 | MW | 12-Jun-20 18-May-20 |  | 520551237236 | 7,7 |  |  |  | 2020-04-17 | 2020-06-24 | W26-2020 |  | 2020-09-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.06.20 : RFIN sent 28.05.20 : 21.05.20 : waiting plan MOS & konfirmasi request PLN connection dari XL/Tech part 17.04.20 : email SRFI-N sent 16.04.20 : plan Soft RFI 09.04.20 : comcase clear, lanjut on going pondasi 02.04.20 : 25.03.20 : progress pondasi 50%, stop karena comcase, proses penyelesain comcase plan solve W4 Mar, plan RFI W2 Apr 12.03.20 : penyelesaian comcase, plan RFI 18 Mar 25.02.20 : Comecase LL minta kompensasi 10Jt/operator, saat ini sedang proses pengajuan dana di Arcom, area Banjir, pondasi type 3 (tinggi 2 m) 20.02.20 : RBS Foundation done, plan RFI W11 13.02.20 : RBS Foundation done 06.02.20 : 30.01.19 : OG RBS Foundation, material ME Grounding tray dan mounting on site
324 |  | JAW-BT-CLG-0142 | 20210903121 | 131570109 | KOTABUMICILEGON | ACTIVE | TB | 106.0422 | -5.9876 | 42 | 10/190/270 |  |  | LINK SERDAG BARU, RT 004 RW 008, KELURAHAN KOTABUMI, KECAMATAN PURWAKARTA, KOTA CILEGON | EID | JAW-BT-CLG-0142 | SERDAG BARU SUKABUMI | COLO |  | JABO | JABODETABEK (OUTER) | Banten | KOTA CILEGON | 6614397 | 2020-01-15 |  | 188 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-06-29 | W27-2020 | Jun-2020 | 2020-07-15 | W29-2020 | Jul-2020 | 2020-07-15 | W29-2020 | Jul-2020 | MW | 24-Jun-20 27-Jan-20 |  | 561200383422 | 6.6 |  |  |  | 2020-06-29 | 2020-07-21 | W30-2020 |  | 2020-08-21 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.07.20 : RFIN sent 20.07.20 : proses PLN connection 13.07.20 : 29.06.20 : email SRFI-N sent 22.06.20 : 18.06.20 : on going cor stacking baseframe (untuk RBS foundation) 15.06.20 : on going RBS foundation 11.06.20 : 08.06.20 : 04.06.20 : open akses, start CME 29.05.20 : open, proses negosiasi 28.05.20 : 25.05.20 : 14.05.20 : commcase, warga dan ormas, meminta kompensasi 08.05.20 : 30.04.20 : CME Colo waiting perkuatan tower dan memerlukan stacking baseframe 23.04.20 : 16.04.20 : 09.04.20 : CME Colo waiting perkuatan tower dan memerlukan stacking baseframe 02.04.20 : 25.03.20 : 19.03.20 : 11.03.20 : on going perkuatan tower 13.02.20 : preparation perkuatan, on going pabrikasi material perkuatan 06.02.20 : 03.02.20 : Tower permanent 3legs sudah RFI tetapi menunggu proses perkuatan karena sudah overcapacity 30.01.20 : start CME Colo XL menunggu site permanent RFI akhir Mar, start CME tower permanen 20 Mar, plan RFI Colo XL 10 Apr 24.01.20 : DRM OK, site GM, Colo XL menunggu site permanent RFI
355 |  | JAW-JT-PWT-0544 | 30575530031 | 141851109 | PASIR WETAN | ACTIVE | TB | 109.2012 | -7.4083 | 40 | 0/125/265 |  |  | RT.01 RW.05 Pasir Kulon, Kec. Karanglewas, Kab. Banyumas | EID | JAW-JT-PWT-0544 | Pasir Kulon Karanglewas | COLO |  | CENTRAL | JATENG | Jawa Tengah | BANYUMAS | 6614397 | 2020-01-15 |  | 217 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-04-30 | W18-2020 | Apr-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-19 | W34-2020 | Aug-2020 | MW | 24-Jun-20 18-May-20 |  | 522012406238 | 7.7 |  |  |  | 2020-04-16 | 2020-08-19 | W34-2020 |  | 2020-09-17 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.08.20 : 19.08.20 : RFIN sent 18.08.20 : actual RFI, plan submit RFIN 19 Aug 13.08.20 : isu ketersediaan stock KWH meter sehingga PLN belum mengeluarkan nomor register, plan PLN connect Selasa 18 Aug 20 10.08.20 : isu KWH meter, masih belum ready minggu lalu, fu kembali ke PLN hari ini 06.08.20 : plan KWH meter ready minggu ini 03.08.20 : 27.07.20 : isu stock KWH meter kosong, estimasi KWH meter ready minggu ini 20.07.20 : 16.07.20 : SK PLN release 15 jul 13.07.20 : 09.07.20 : SK PLN masih belum release from XL 02.07.20 : 29.06.20 : Menunggu SK PLN release dari XL, plan RFI menyesuaikan kembali dg SK release (SK date+14 hari) 29.06.20 : PLN Connection menunggu konfirmasi dari XL 28.05.20 : 21.05.20 : waiting plan MOS & konfirmasi request PLN connection dari XL/Tech part 16.04.20 : email SRFI-N sent 09.04.20 : on going install tray dan ME, erection done, permanenisasi 02.04.20 : on going bore pile site permanent 25.03.20 : survey dan prepare start CME permanent tower 12.03.20 : comcase 11.03.20 : 13.02.20 : proses permanenisasi on going 06.02.20 : 30.01.19 : Mobilisasi team, delivery material
89 |  | JAW-JK-GGP-0524 | 30573620031 | 1127941003 | KENCANA TIMUR CENGKARENG | ACTIVE | TB | 106.7296 | -6.1267 | 22 | 70/130/280 |  |  | Jalan Outer luar RT 11 RW 11, Kel. Cengkareng Timur, Kec . Cengkareng, Kota Jakarta Barat | EID | JAW-JK-GGP-0524 | Kencana Timur Cengkareng | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA BARAT | 6614397 | 2020-01-15 |  | 195 | > 150 days | 2020-06-13 | W24-2020 | Jun-2020 | 2020-06-19 | W25-2020 | Jun-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-10 |  | 546303095396 | 6.6 |  |  |  | 2020-06-19 | 2020-07-28 | W31-2020 |  | 2020-08-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.07.20 : RFIN sent 23.07.20 : 20.07.20 : proses PLN connection 13.07.20 : 09.07.20 : 06.07.20 : 29.06.20 : 19.06.20 : email SRFI-N sent, PLN connection menunggu konfirmasi XL/Tech partner 18.06.20 : SRFI, collecting doc SRFIN 15.06.20 : ME on going 11.06.20 : 08.06.20 : 04.06.20 : 04.06.20 : erection on going 01.06.20 : 29.05.20 : erection 28.05.20 : 25.05.20 : curingtime 14.05.20 : 08.05.20 : 30.04.20 : IW on going 23.04.20 : TNP review 16.04.20 : under review RND 09.04.20 : 02.04.20 : iw on going 25.03.2020 : 23.03.2020 : Kandidat OG, OG pengajuan surat ke AGUNG SEDAYU GROUP, IW on going 19.03.20 : validasi TNP 20.02.20 : kand A = kandidat A, waiting approval menjadi MCP 20m 13.02.20 : 06.02.20 : Kand A = Candidate A Submit 17.01.20 : hasil assessment PDI done (email arief), propose change to colo (email sherly), proses input STIP 1 B2S
242 |  | JAW-JB-SBM-2105 | 30581940031 | 131614109 | BANGBAYANTANGKIL | ACTIVE | TB | 106.7662 | -6.7799 | 40 | 10/90/160/280 |  |  | Kp. Cibarigbeg RT005 RW001, Desa Caringin, Kec. Cicurug, Kab. Sukabumi | EID | JAW-JB-SBM-2105 | CARINGIN CICURUG | COLO |  | JABO | JABODETABEK (OUTER) | Jawa Barat | SUKABUMI | 6614397 | 2020-01-15 |  | 335 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-07-15 | W29-2020 | Jul-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 536590552917 | 6.6 |  |  |  | 2020-07-16 | 2020-12-15 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.12.20 : RFIN sent 07.12.20 : PLN connection process 06.08.20 : 27.07.20 : 16.07.20 : email SRFI-N sent 13.07.20 : 02.07.20 : erection 29.06.20 : 22.06.20 : Borepile done, OG lantai kerja, Plan pouring 25/06, Erection start 30/06 Finish 07/07, S RFI 10/07 18.06.20 : pondasi tower permanen (borepile done) 15.06.20 : on going RBS foundation 11.06.20 : 08.06.20 : 04.06.20 : BTS foundation on going 29.05.20 : plan survey untuk start CME Selasa 2 jun, isu close 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : CME NY Start commcase, Waiting tower permanen RFI 23.04.20 : 16.04.20 : 09.04.20 : CME NY Start commcase, Permintaan biaya pembinaan karang taruna dan kepala desa 02.04.20 : 25.03.20 : 19.03.20 : 11.03.20 : COMCASE tower permanen, CME colo ny start, Kepala desa meminta kompensasi tambahan 13.02.20 : progress tower permanent plan start minggu depan 06.02.20 : 04.02.20 : under review Power 21.01.20 : belum permanenisasi, IMB release, plan RFI permanent W4 maret
272 |  | JAW-BT-SRG-0019 | 30575090031 | 131564109 | CURUG SERANG | ACTIVE | TB | 106.1991 | -6.1678 | 42 | 65/170/310 |  |  | Jl. Cigemuk, Kampung Lingsangku, RT.11/RW.03, Kel.Curug Manis Kec. CurugKel.Curug Manis Kec. Curug | EID | JAW-BT-SRG-0019 | Banjarsari Curug | COLO |  | JABO | JABODETABEK (OUTER) | Banten | KOTA SERANG | 6614397 | 2020-01-15 |  | 334 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-03-27 | W13-2020 | Mar-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 561400778225 | 6.6 |  |  |  | 2020-03-27 | 2020-12-14 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.12.20 : RFIN sent 07.12.20 : PLN connection process 29.06.20 : PLN Connection menunggu konfirmasi XL 27.03.20 : email SRFIN sent 19.03.20 : SOFT RFI, plan RFI dengan FO 2 bulan dari tgl SRFI 11.03.20 : Tower permanen RFI, colo XL ME on going, FO plan, plan SOFT RFI 13 Mar 13.02.20 : progress tower permanent rebarring pondasi, plan cor minggu depan 06.02.20 : progress tower permanent galian pondasi 30.01.20 : start CME Colo XL menunggu site permanent RFI akhir Feb, start CME tower permanen 6 feb, plan RFI Colo XL 10 Mar 24.01.20 : DRM OK, site GM, Colo XL menunggu site permanent RFI
223 |  | JAW-JT-PWD-0016 | 30575550031 | 142902109 | GENUKSURAN PURWODADI | ACTIVE | TB | 110.8823 | -7.1081 | 50 | 20/95/185/270 |  |  | Dusun Doplang, RT.001 RW.004, Kelurahan Genuksuran, Kecamatan Purwodadi, Kabupaten Grobogan | EID | JAW-JT-PWD-0016 | GENUKSURAN PURWODADI | COLO |  | CENTRAL | JATENG | Jawa Tengah | GROBOGAN | 6614397 | 2020-01-15 |  | 534 | > 150 days | 2020-02-14 | W07-2020 | Feb-2020 | 2020-04-03 | W14-2020 | Apr-2020 | 2021-02-28 | W10-2021 | Feb-2021 | 2021-07-05 | W28-2021 | Jul-2021 | FO (Change to MW as temp solution) | 2021-02-11 |  | 525530246280 | 7.7 |  |  |  | 2020-04-02 | 2021-07-02 | W27-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.01.21 : 06.28.21 : 06.24.21 : Power Connection Prosess, BPUJL Paid, revisi Plan RFI 5 Jul 06.21.21 : 06.17.21 : 06.14.21 : Register Released, Plan Connect 21 Jun 06.10.21 : Register Paid, Proses Persiapan instalasi Travo 06.07.21 : 06.02.21 :05.31.21 : 05.26.21 : 05.26.21 : 05.23.21 : 05.19.21 : FU PLN Terkair ketersedian Travo, revise RFI Plan W2 Jun 05.17.21 : 05.10.21 : 05.06.21 : 26.04.21 : 22.04.21 : OG pengadaan material trafo by PLN, estimasi s.d End of May 15.04.21 : waiting approval pembagian beban trafo PLN 12.04.21 : 05.04.21 : koordinasi dengan UP lain untuk peminjaman stock Trafo, plan RFI 25 Apr 01.04.21 : 29.03.21 : OG register PLN 25.03.21 : overblast tarfo, propose connect Multiguna (waiting info PLN) 25.02.21 : OG PLN connection 11.02.21 : perubahan transport FO -> MW, waiting PSB release 03.08.20 : 20.07.20 : 16.07.20 : 09.07.20 : 02.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL, plan RFI adalah SK PLN release+14 hari 28.05.20 : 21.05.20 : waiting plan MOS & konfirmasi request PLN connection dari XL/Tech part 02.04.20 : email SRFIN sent 25.03.20 : SRFI 11.03.20 : 03.04.20 : plan RFIN 03.05.20 26.02.20 : SRFI, plan RFI+ MG 28 Feb 20.02.20 : RBS Foundation done 13.02.20 : OG RBS Foundation 06.02.20 : 30.01.19 : Mobilisasi team, delivery material, plan start CME 1 Feb
35 |  | JAW-BT-TGR-0026 | 30572250031 | 1317551003 | CIRUMPAK TANGERANG | ACTIVE | TB | 106.4396 | -6.1057 | 50 | 50/245/310 |  |  | Kp. Pasir, RT.06/03, Desa Pasir Kec. Kronjo Kabupaten Tangerang | EID | JAW-BT-TGR-0026 | Cirumpak Tangerang | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 114 | 91 - 120 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-15 | W16-2020 | Apr-2020 | 2020-05-06 | W19-2020 | May-2020 | 2020-05-06 | W19-2020 | May-2020 | MW |  |  | 566401480561 | 6.6 |  |  |  | 2020-03-31 | 2020-05-06 | W19-2020 |  | 2020-05-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.05.20 : RFIN sent 22.04.20 : email permintaan connect PLN oleh Bu Anggie, email request PSB PLN, plan RFI = SK PLN + 14 days (6 may 20) 31.03.20 : email SRFI-N sent 09.04.20 : SRFI, wait SRFIN 02.04.20 : 25.03.20 : Erection Tower OG 23.03.20 : Erection Tower OG 19.03.20 : galian pondasi 11.03.20 : galian pondasi OG, Plan Done 14/03 06.03.20 : Bowplank done, Galian plan start 07/03 20.02.20 : OG rekom lurah camat 13.02.20 : IW on going/realisasi IW 06.02.20 : kand A, B, C = validasi done, Candidate A, B & C RF TX OK 24.01.20 : kand A = RND A OK (50m) 50 Prio 1 B OK (50m) 50 Prio 2 C OK (50m) 50 Prio 3
107 |  | JAW-BT-TGR-0021 | 30572000031 | 1317391003 | MEKAR WANGI TANGERANG | ACTIVE | TB | 106.5907 | -6.3461 | 40 | 80/170/250/320 |  |  | Kp.Panyirapan 008/004, Desa Mekarwangi, Kec. Cisauk, Tangerang, Banten | EID | JAW-BT-TGR-0021 | Mekar Wangi Tangerang | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 140 | 121 - 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-15 | W16-2020 | Apr-2020 | 2020-05-12 | W20-2020 | May-2020 | 2020-05-20 | W21-2020 | May-2020 | MW | 2020-05-06 |  | 566201406819 | 6.6 |  |  |  | 2020-05-12 | 2020-06-01 | W23-2020 |  | 2020-05-22 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.06.290 : RFIN sent 12.05.20 : email Soft RFIN sent 06.05.20 : email konfirmasi XL request connect PLN PLN (Pak Wawan), plan connect 20 may if besok SK PLN nya release 23.04.20 : SRFI actual 16.04.20 : ME on going 09.04.20 : Erection Towet OG, Issue Missing material plat kopel 02.04.20 : erection on going 25.03.20 : Plan start Erection 26/03 23.03.20 : Waiting team erector onsite 19.03.20 : Curing time 11.03.20 : galian pondasi OG, Plan galian Done 14/03 06.03.20 : Bowplank done, Galian plan start 07/03 20.02.20 : OG rekom lurah camat 13.02.20 : IW on going/realisasi IW 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = RND OK 40
28 |  | JAW-JB-NPH-3704 | 30571070031 | 1260861003 | CIBITUNG_RONGGA | ACTIVE | TB | 107.305 | -6.9284 | 50 | 0/100/200 | 2020 | JEDI 2020 [NEW] | KP PASIR GOMBONG, RT 01 RW 07, DESA CIBITUNG, KECAMATAN RONGGA, KABUPATEN BANDUNG BARAT | HTI | JAW-JB-NPH-3704 | CIBITUNG_RONGGA | B2S | TBG | CENTRAL | JABAR | Jawa Barat | KAB. BANDUNG BARAT | 6614369 | 2020-01-13 |  | 114 | 91 - 120 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-27 | W18-2020 | Apr-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-05-06 | W19-2020 | May-2020 | MW | 2020-04-22 |  | 535950876137 | 6.6 |  |  |  |  | 2020-05-06 | W19-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.05.20 : RFIN sent 23.04.20 : SRFI actual 22.04.20 : erection done, start ME grounding 22.04.20 : email konfirmasi RFI/request PLN Connection dari XL (Pak Bayu), request SK PLN ke XL 20.04.20 : tower painting 16.04.20 : erection on going 09.04.20 : curingtime 02.04.20 : 01.04.20 : rebarring done, plan cor 4 apr, SST 52m 19.03.20 : galian on going, bsk stop krn ada survey KBB (pemkot bandung barat), wait GDL tower 11.03.20 : Rekom done, RFC, proses perijinan 20.02.20 : rekom L/C 13.02.20 : IW on going 06.02.20 : Kand A = RF OK, TX review 22.01.20 : kand A = RND 50 80/140/215 22Jan20 : RND ok candidate A, tower 52 20.01.20 : Kand A = submit kand A di -6,92756 107,30578
106 |  | JAW-JK-CKG-0354 | 30572210031 | 1127791003 | MEJING BAMBU APUS | ACTIVE | TB | 106.8978 | -6.3104 | 30 | 0/90/180/270 |  |  | Bambu kuning selatan RT 13 , RW 02, Kel. Baambu apus, kec. Cipayung, kota jakarta Timur | EID | JAW-JK-CKG-0354 | Mejing Bambu Apus | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614368 | 2020-01-13 |  | 128 | 121 - 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-20 | W21-2020 | May-2020 | 2020-06-06 | W23-2020 | Jun-2020 | 2020-05-20 | W21-2020 | May-2020 | MW | 2020-05-06 |  | 547202173233 | 6.6 |  |  |  | 2020-04-16 | 2020-05-20 | W21-2020 |  | 2020-07-03 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.05.20 : RFIN sent 06.05.20 : email konfirmasi XL request connect PLN PLN (Pak Wawan), plan connect 20 may if besok SK PLN nya release 16.04.20 : PLN Connection, SRFIN sent 09.04.20 : ME on going 02.04.20 : 25.03.20 : Curing Time OG 23.30.20 : Curing Time, Pondasi Done 19.03.20 : IW clear 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
65 |  | JAW-BT-TGR-0027 | 30572310031 | 1317571003 | JATAKE RANGKASBITUNG | ACTIVE | TB | 106.5996 | -6.3373 | 40 | 70/190/260/340 |  |  | Kampung Kandang RT.05 RW.01 Kelurahan Jatake Kecamatan Pagedangan | EID | JAW-BT-TGR-0027 | Jatake Rangkasbitung | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 177 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-12 | W20-2020 | May-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 566201432938 | 6.6 |  |  |  | 2020-05-14 | 2020-07-08 | W28-2020 |  | 2020-07-11 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.07.20 : RFIN sent 29.06.20 : Proses PLN connection 19.06.20 : SK PLN release, plan RFI 6 Jul 20 14.05.20 : SRFIN sent 08.05.20 : ME og 30.04.20 : CURING TIME 23.04.20 : 16.04.20 : on going excavation 09.04.20 : REKOM LURCAM done, Soil test done, Plan Start CME 11/04 02.04.20 : rekom on going 25.03.20 : 20.03.20 : IW Clear, Proses approval Eskalasi SITAC 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = RND OK 40
29 |  | JAW-BT-TGR-0040 | 30572300031 | 1317561003 | CIBUGEL CISOKA | ACTIVE | TB | 106.4229 | -6.2509 | 35 | 75/160/275 |  |  | Kp. Cibugel RT.009 RW.004, Desa. Cibugel, Kec. Cisoka, Kab. Tangerang | EID | JAW-BT-TGR-0040 | Cibugel Cisoka | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 172 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-12 | W20-2020 | May-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 566401509439 | 6.6 |  |  |  | 2020-05-06 | 2020-07-03 | W27-2020 |  | 2020-06-30 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 03.07.20 : RFIN sent 29.06.20 : Proses PLN connection 19.06.20 : SK PLN release, plan RFI 6 Jul 20 06.05.20 : SRFIN sent 22.04.20 : email permintaan connect PLN oleh Bu Anggie, email request PSB PLN 16.04.20 : Soft RFI actual 16.04.20 : ME on going, plan SRFI 09.04.20 : Erection Tower OG 02.04.20 : rebarring 25.03.20 : Galian Pondasi OG 20.03.20 : Galian pondasi OG 19.03.20 : rekom lc on going 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : Kand A, B = validasi done RF TX OK 24.01.20 : kand A = RND A OK 35 Prio 2 B OK 35 Prio 1
139 |  | JAW-BT-TGR-0024 | 30572220031 | 1317531003 | RAYA CISAUK BSD | ACTIVE | TB | 106.6561 | -6.3104 | 30 | 90/180/290 |  |  | Kp.Sampora RT.02 RW.02 Desa Sampora Kecamatan Cisauk Kabupaten Tangerang | EID | JAW-BT-TGR-0024 | Raya Cisauk BSD | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 170 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-12 | W20-2020 | May-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 566201431275 | 6.6 |  |  |  | 2020-05-16 | 2020-07-01 | W27-2020 |  | 2020-07-11 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.07.20 : RFIN sent 29.06.20 : Proses PLN connection 19.06.20 : SK PLN release, plan RFI 6 Jul 20 16.05.20 : SRFIN sent 14.05.20 : ME & Grounding system process 08.05.20 : curingtime 30.04.20 : Galian pondasi OG 23.04.20 : 16.04.20 : on going excavation 09.04.20 : Proses REKOM LURCAM Done, proses perijinan 02.04.20 : rekom on going 25.03.20 : 20.03.20 : IW Clear, Proses approval Eskalasi SITAC 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : Kand A, B = validasi done RF TX OK 24.01.20 : kand A, B = A OK 30 Prio 2 dan B OK 30 Prio 1
46 |  | JAW-JK-TJP-0615 | 30571920031 | 1127721003 | GANG MERPATI KEBANTENAN | ACTIVE | TB | 106.9268 | -6.1108 | 25 | 0/90/210/330 |  |  | Jl. Kebantenan RT.001, RW 02, Kel. Semper timur, Kec. Cilincing, Jakarta Utara | EID | JAW-JK-TJP-0615 | Gang Merpati Kebantenan | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6614368 | 2020-01-13 |  | 169 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-15 | W16-2020 | Apr-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 545302712469 | 6.6 |  |  |  | 2020-04-16 | 2020-06-30 | W27-2020 |  | 2020-07-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29.06.20 : RFIN sent 19.06.20 : SK PLN release, plan RFI 6 Jul 20 16.04.20 : SRFIN sent 09.04.20 : ME on going 02.04.20 : 25.03.20 : rebarring 19.03.20 : galian pondasi 11.03.20 : Galian pondasi OG, plan pouring 13/03 06.03.20 : Plan Bowplank 07/03 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°55'32.16"E 6°06'40.43"S/106.9256 -6.111231 OK, Center Antenna 20m
57 |  | JAW-JK-GGP-0527 | 30571900031 | 1127711003 | JALAN MANGGA UBI | ACTIVE | TB | 106.7556 | -6.1457 | 35 | 0/70/200/310 |  |  | Jalan Mangga Ubi RT. 6 RW. 7, Kel. Kapuk, Kec. Cengkareng, Jakarta Barat, DKI Jakarta | EID | JAW-JK-GGP-0527 | Jalan Mangga Ubi | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA BARAT | 6614368 | 2020-01-13 |  | 169 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-12 | W20-2020 | May-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 542103703114 | 6.6 |  |  |  | 2020-04-17 | 2020-06-30 | W27-2020 |  | 2020-07-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29.06.20 : RFIN sent 19.06.20 : SK PLN release, plan RFI 6 Jul 20 17.04.20 : SRFIN sent 16.04.20 : PLN Connection 09.04.20 : ME on going 02.04.20 : RFC, proses perijinan 25.03.20 : 23.03.20 : IW Clear, Cand B 19.03.20 : 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°45'22.08"E 6°08'44.56"S/106.756133 -6.145711 OK, Center Antenna 20m
60 |  | JAW-JK-KYB-0110 | 30573440031 | 1127911003 | JALAN PURNAWARMAN | ACTIVE | TB | 106.8052 | -6.2344 | 30 | 0/90/180/270 |  |  | Jl. Daksa II RT.06 RW. 02, Kel. Selong, Kec. Kebayoran Baru, Jakarta pusat | EID | JAW-JK-KYB-0110 | Jalan Purnawarman | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614368 | 2020-01-13 |  | 169 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-04-15 | W16-2020 | Apr-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 543105613735 | 6.6 |  |  |  | 2020-04-16 | 2020-06-30 | W27-2020 |  | 2020-07-22 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29.06.20 : RFIN sent 19.06.20 : SK PLN release, plan RFI 6 Jul 20 16.04.20 : SRFIN sent 16.04.20 : erection on going 09.04.20 : Curing time, Erection proses ijin lingkungan 02.04.20 : 25.03.20 : Curing Time, Plan erection 26/03 19.03.20 : Curing TIme 19.03.20 : galian pondasi 11.03.20 : Galian pondasi OG, plan pouring 13/03 06.03.20 : Plan Bowplank 07/03 20.02.20 : 13.02.20 : IW on going/realisasi IW 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°48'19.48"E 6°14'32.7"S/106.80541 -6.234241 OK, Center Antenna 20m 16.01.20 : Proses input STIP 1 B2S 15.01.20 : propose change to colo (email Rudi), konfirmasi NOK dari XL (Pak Siro)
81 |  | JAW-JK-TJP-0626 | 20210805621 | 1127771003 | Kebon Bawang Tanjung Priok | ACTIVE | TB | 106.8888 | -6.1143 | 30 | 20/170/280 |  |  | Jl. Bugis RT. 01 RW. 01, Kel. Kebon Bawang, Kec. Tanjung Priok, Jakarta Utara | EID | JAW-JK-TJP-0626 | Kebon Bawang Tanjung Priok | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6614368 | 2020-01-13 |  | 169 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-06 | W23-2020 | Jun-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 545103527637 | 6.6 |  |  |  | 2020-05-16 | 2020-06-30 | W27-2020 |  | 2020-07-15 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29.06.20 : RFIN sent 19.06.20 : SK PLN release, plan RFI 6 Jul 20 16.05.20 : SRFIN sent 14.05.20 : erection 08.05.20 : excavation on going 30.04.20 : Lingkungan clear, proses perijinan kelurahan, staf dan lurah WFH 23.04.20 : 16.04.20 : Lingkungan clear, proses perijinan kelurahan sementara tutup terkait isu corona 09.04.20 : 02.04.20 : 25.03.20 : 23.03.20 : Lingkungan clear, proses perijinan kelurahan sementara tutup terkait isu corona 19.03.20 : IW on going 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
88 |  | JAW-JK-KYB-0107 | 30572330031 | 1127841003 | KENANGA TERUSAN PASMING | ACTIVE | TB | 106.8157 | -6.287 | 25 | 0/90/180/270 |  |  | Kenanga RT.012 RW 02, Kel. Cilandak timur, Kec. Pasar Minggu | EID | JAW-JK-KYB-0107 | Kenanga Terusan Pasming | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614368 | 2020-01-13 |  | 169 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-03-31 | W14-2020 | Mar-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 543105613743 | 6.6 |  |  |  | 2020-03-31 | 2020-06-30 | W27-2020 |  | 2020-07-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 29.06.20 : RFIN sent 19.06.20 : SK PLN release, plan RFI 6 Jul 20 31.03.20 : email SRFI-N sent 02.04.20 : SRFI, collecting doc RFIN 25.03.20 : ME installation 19.03.20 : galian pondasi 11.03.20 : Galian pondasi OG, plan pouring 13/03 06.03.20 : Plan Bowplank 07/03 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°49'00.85"E 6°17'13.35"S/106.816903 -6.287042 OK, Center Antenna 20m
63 |  | JAW-BT-TGR-0030 | 30572040031 | 1317431003 | JALAN RAYA KUKUN DAUN | ACTIVE | TB | 106.4449 | -6.146 | 50 | 50/125/190/270 |  |  | Kp.Tegal Murni, RT 001 RW 002, Desa Benda, Kecamatan Sukamulya, Kabupaten Tangerang - Banten | EID | JAW-BT-TGR-0030 | Jalan Raya Kukun Daun | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 165 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-03-31 | W14-2020 | Mar-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 566401509462 | 6.6 |  |  |  | 2020-03-31 | 2020-06-26 | W26-2020 |  | 2020-08-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.06.20 : RFIN sent 19.06.20 : SK PLN release, plan RFI 6 Jul 20 ]31.03.20 : email SRFI-N sent 25.03.20 : Soft RFI 19.03.20 : ME installation 11.03.20 : Erection OG 06.03.20 : Erecton OG 19.02.20 : Plan start bowplank 22/02 20.02.20 : rekom lurah done, land clearing 13.02.20 : IW on going 06.02.20 : kand A, B, C = validasi done, Candidate A, B & C RF TX OK 24.01.20 : kand A, B, C = RND A OK (50m) 50 Prio 2 B OK (50m) 50 Prio 3 C OK (50m) 50 Prio 1
129 |  | JAW-BT-TGR-0025 | 30572240031 | 1317541003 | PATRASANA KRESEK | ACTIVE | TB | 106.4042 | -6.1555 | 40 | 0/90/275 |  |  | Jl. Raya Kresek RT 001 RW 001 Desa Patrasana Kecamatan Kresek Kabupaten Tangerang - Banten. | EID | JAW-BT-TGR-0025 | Patrasana Kresek | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 165 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-12 | W20-2020 | May-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 566401509454 | 6.6 |  |  |  | 2020-05-06 | 2020-06-26 | W26-2020 |  | 2020-07-11 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.06.20 : RFIN sent 19.06.20 : SK PLN release, plan RFI 6 Jul 20 06.05.20 : SRFIN sent 30.04.20 : ERECTION OG 23.04.20 : curingtime 16.04.20 : on going excavation 09.04.20 : Team CME Onsite, BOwplank OG 02.04.20 : 25.03.20 : 19.03.20 : 20.02.20 : OG rekom lurah camat 13.02.20 : IW on going/realisasi IW 06.02.20 : kand A, B, C = validasi done, Candidate A, B & C RF TX OK 24.01.20 : kand A = RND A OK 40 Prio 1 B OK 40 Prio 2 C NOK
156 |  | JAW-BT-TGR-0032 | 30572170031 | 1317491003 | SERANG CIKANDE | ACTIVE | TB | 106.3826 | -6.187 | 50 | 95/175/320 |  |  | Kp.Babakan, RT 012 RW 002, Desa Pasir Gintung, Kecamatan Jayanti, Kabupaten Tangerang-Banten | EID | JAW-BT-TGR-0032 | Serang Cikande | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 165 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-03-31 | W14-2020 | Mar-2020 | 2020-07-06 | W28-2020 | Jul-2020 | 2020-07-06 | W28-2020 | Jul-2020 | MW | 19-Jun-20 18-May-20 |  | 566401509916 | 6.6 |  |  |  | 2020-04-01 | 2020-06-26 | W26-2020 |  | 2020-08-13 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 26.06.20 : RFIN sent 19.06.20 : SK PLN release, plan RFI 6 Jul 20 01.04.20 : email SRFI-N sent 25.03.20 : Soft RFI 19.03.20 : Curing time 11.03.20 : Curing Time, Pouring done 11/03 06.03.20 : Galian Pondasi OG, Plan galian done 10/03 20.02.20 : galian pondasi 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = RND OK 40
33 |  | JAW-JT-BBS-0153 | 30571890031 | 1432321003 | CIPEMALI BREBES | ACTIVE | TB | 109.0364 | -6.8063 | 50 | 100/290/340 |  |  | KALIWLINGI RT 003/ RW 005, DESA KALIWLINGI, KEC. BREBES, KAB. BREBES | EID | JAW-JT-BBS-0153 | Cipemali Brebes | B2S | TBG | CENTRAL | JATENG | DI Yogyakarta | BREBES | 6614368 | 2020-01-13 |  | 245 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-07-10 | W28-2020 | Jul-2020 | 2020-09-14 | W38-2020 | Sep-2020 | MW | 2020-06-12 |  | 522551431936 | 11 |  |  |  | 2020-06-15 | 2020-09-14 | W38-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.09.20 : RFIN sent (MULTIGUNA) 14.09.20 : plan submit RFIN hari ini 12.09.20 : RFI actual dengan PLN Multiguna, collecting doc RFIN 10.09.20 : proses koneksi PLN Multiguna, plan RFI minggu ini 12 sep 20 07.09.20 : plan register Multiguna terbit hari ini dan plan connect PLN MG besok 8 Sept 03.09.20 : plan connect PLN diusahakan minggu ini 5 sep 20, proses prepare material pole PLN oleh AKLI 31.08.20 : 27.08.20 : proses perluasan jaringan PLN terkendala material, plan connect 3 sept 24.08.20 : 17.08.20 : plan PLN connect jumat 24 Aug 20 13.08.20 : plan PLN connect jumat 14 Aug 20 10.08.20 : 06.08.20 : BP paid, plan PLN connect Rabu 12 Aug 20 03.08.20 : 20.07.20 : 16.07.20 : 13.07.20 : ada perluasan jaringan penambahan 5 tiang PLN,saat ini sedang menunggu approval PLN untuk penambhan jaringannya, terkendala aturan baru yg sekarang jaringan/investasinya dibebankan ke Pelanggan dlm bentuk BPUJL, dari PLN rayon setempat masih menghitung nilai investasinya, besok akan di update kembali, plan connect PLN 25 jul 09.07.20 : 02.07.20 : 29.06.20 : Proses PLN Connection 15.06.20 : email SRFIN sent 04.06.20 : SRFI actual, collecting doc SRFIN 01.06.20 : 28.05.20 : 21.05.20 : ME on going 14.05.20 : erection on going 30.04.20 : curingtime 23.04.20 : 16.04.20 : borepile done, rebarring 09.04.20 : on going borepile 02.04.20 : 25.03.20 : start excavation 19.03.20 : prepare start CME, plan minggu ini 28.02.20 : proses perijinan, proses design pack (APD), plan design done minggu depan, material tower ready 20.02.20 : rekom done, submit berkas proses perijinan 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 20.01.20 : Kand A = submit kand A di 109.03506 -6.80666 (147m) proposes Tower 52m
55 |  | JAW-JK-KYB-0096 | 30571750031 | 1127601003 | JALAN GARUDA MAS | ACTIVE | TB | 106.8445 | -6.311 | 30 | 40/150/300 |  |  | Jl. Nangka, GG. H. Nawi No. 7 RT.002 RW.006, Kel. Tanjung Barat, Kec. Jagakarsa, Jakarta Selatan | EID | JAW-JK-KYB-0096 | Jalan Garuda Mas | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614368 | 2020-01-13 |  | 207 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-15 | W29-2020 | Jul-2020 | 2020-08-10 | W33-2020 | Aug-2020 | MW | 2020-06-29 |  | 547401723708 | 6.6 |  |  |  | 2020-06-29 | 2020-08-07 | W32-2020 |  | 2020-08-28 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.08.20 : RFIN sent 06.08.20 : 23.07.20 : 20.07.20 : proses PLN connection 13.07.20 : 09.07.20 : 06.07.20 : 02.07.20 : email SRFI-N sent, wait SK PLN release from XL 29.06.20 : email SRFI-N sent 25.06.20 : curingtime 22.06.20 : cor done, paralel rekom on going 22.06.20 : Pouring 20/06, Erection start 27/06, Finish 29/06, S RFI 30/06 18.06.20 : on going excavation, Plan SRFI/RFI end of June 15.06.20 : 11.06.20 : proses validasi, paralel IW clear 08.06.20 : RND review 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review, paralel IW on going 28.05.20 : 25.05.20 : 22.05.20 : RND review 21.05.20 : 18.05.20 : RND propose ketinggian 25 m 16.05.20 : submit kand D 15.05.20 : RND review 14.05.20 : RF review 08.05.20 : 30.04.20 : rehunting 23.04.20 : 16.04.20 : Rehunting site, NOM berada di dalam kawasan developer PT. TCP INTERNUSA, 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : validasi RND 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°50'38.77"E 6°18'38.09"S/106.844103 -6.310581 OK, Center Antenna 20m
94 |  | JAW-JB-CBI-0068 | 30573430031 | 1260971003 | KLAPANUNGGAL CILEUNGSI | ACTIVE | TB | 106.9579 | -6.444 | 50 | 30/140/290 |  |  | Kampung Sindanglengo, RT. 006 RW. 004, Desa Klapanunggal, Kecamatan Klapanunggal, Kabupaten Bogor, Provinsi Jawa Barat | EID | JAW-JB-CBI-0068 | Klapanunggal Cileungsi | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614368 | 2020-01-13 |  | 193 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-21 | W21-2020 | May-2020 | 2020-07-15 | W29-2020 | Jul-2020 | 2020-07-28 | W31-2020 | Jul-2020 | MW | 2020-06-24 |  | 538657233015 | 6.6 |  |  |  | 2020-05-21 | 2020-07-24 | W30-2020 |  | 2020-08-13 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.07.20 : RFIN sent 20.07.20 : proses PLN connection 13.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi XL 21.05.20 : email SRFI-N sent 14.05.20 : Erection 08.05.20 : rebarring 30.04.20 : preparation start CME 23.04.20 : 16.04.20 : Realisasi done, Proses REKOM 09.04.20 : realisasi IW, rekom 02.04.20 : IW Clear 25.03.20 : TNP review 19.03.20 : validasi RND 13.02.20 : IW on going 06.02.20 : Kand A, B = validasi done RF TX OK 24.01.20 : kand A = RND OK 40 A OK 40 Prio 2 B OK 40 Prio 1 16.01.20 : Proses input STIP 1 B2S 15.01.20 : propose change to colo (email Rudi), konfirmasi NOK dari XL (Pak Siro)
119 |  | JAW-JB-CBI-0071 | 30572150031 | 1260931003 | PABUARAN KEMANG | ACTIVE | TB | 106.7513 | -6.5032 | 50 | 90/190/290 |  |  | KP. KEMANG, RT.001 RW.003, DS. KEMANG, KEC. KEMANG, KAB. BOGOR, JAWA BARAT | EID | JAW-JB-CBI-0071 | Pabuaran Kemang | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614368 | 2020-01-13 |  | 189 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-15 | W29-2020 | Jul-2020 | 2020-07-15 | W29-2020 | Jul-2020 | MW | 2020-06-24 |  | 538414568448 | 6.6 |  |  |  | 2020-06-11 | 2020-07-20 | W30-2020 |  | 2020-07-24 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.07.20 : RFIN sent 20.07.20 : proses PLN connection 13.07.20 : 09.07.20 : 06.07.20 : 02.07.20 : email SRFI-N sent, wait SK PLN release from XL 29.06.20 : 18.06.20 : 11.06.20 : email SRFI-N sent 08.06.20 : ME on going 04.06.20 : erection on going 01.06.20 : 29.05.20 : erection 28.05.20 : 25.05.20 : curingtime 14.05.20 : Rebaring 08.05.20 : excavation on going 30.04.20 : preparation start CME 23.04.20 : 16.04.20 : Plan Start CME 18/04 09.04.20 : RFC done, Plan Start CME 12/04 02.04.20 : rekom on going 25.03.20 : 19.03.20 : rekom l/c on going 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = RND OK 40
56 |  | JAW-JK-KYB-0105 | 30571840031 | 1127661003 | JALAN KUBUR ISLAM | ACTIVE | TB | 106.7817 | -6.2316 | 25 | 0/60/250 |  |  | Jl. Kubur Islam Kel. Grogol Selatan Kec. Kebayoran Lama Jakarta Selatan | EID | JAW-JK-KYB-0105 | Jalan Kubur Islam | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614368 | 2020-01-13 |  | 358 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-15 | W29-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2021-01-11 | W03-2021 | Jan-2021 | MW | 2020-12-16 |  | 543105663905 | 6.6 |  |  |  |  | 2021-01-05 | W02-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 05.01.21 : RFIN sent 28.12.20 : erection ongoing 21.12.20 : 17.12.20 : galian ongoing 14.12.20 : 10.12.20 : issue commcase clear, IW clear, target CME start W3 Dec 07.12.20 : 03.12.20 : proses sosialisasi warga dilaksanakan 4 Nov, target RFC W2 Dec 26.11.20 : 23.11.20 : 19.11.20 : penyelesaian issue commcase warga dalam radius, target issue closed dan RFC W5 Nov 16.11.20 : IW clear, proses negosiasi LL untuk realisasi IW 12.11.20 : minus 1 IW bangunan gudang kosong, proses follow up ke pemilik gudang 09.11.20 : IW ongoing 05.11.20 : target solved minggu depan, target RFI diupayakan end of Nov 02.11.20 : commcase sehingga kandidat bergeser 20m, prose IW ulang 22.10.20 : 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : 01.10.20 : 28.09.20 : 24.09.20 : Commcase warga radius, mengadu ke PTSP JAKARTA SELATAN meminta lokasi pole di geser, plan RFI revisi dari 25 sep menjadi 10 oct 21.09.20 : 17.09.20 : CME Stop, Commcase warga provokasi ORMAS. Menarik persetujuan IW, Plan mediasi dengan Dinas perijinan 14.09.20 : ME on going, paralel penyelesaian comcase warga luar radius 10.09.20 : 07.09.20 : ME on going 03.09.20 : Commcase, warga radius masih di follow up ke PTSP terkait pengaduan warga, Plan Solved 04/09, geser 20m, plan start gali minggu depan 31.08.20 : 27.08.20 : Commcase, warga radius masih di follow up ke PTSP terkait pengaduan warga, Plan Solved 04/09 24.08.20 : 17.08.20 : proses penyelesaian isu, plan clear dan lanjut CME minggu ini, plan perijinan clear minggu ini 13.08.20 : 10.08.20 : CME Stop, Commcase warga provokasi ORMAS. Menarik persetujuan IW, Plan mediasi dengan Dinas perijinan, tokoh masyarakat, plan clear 12/08 06.08.20 : proses negosiasi dilakukan secara personal, plan clear 12 Aug 03.08.20 : 30.07.20 : CME Stop (ME installation), Commcase warga provokasi ORMAS. Meminta posisi pole digeser 27.07.20 : 23.07.20 : CME Stop, Commcase warga provokasi ORMAS. Mediasi dengan PTSP masih belum menemui kata sepakat, sedang dilakukan pendekatan personal terhadap warga yang vokal dengan penolakan 20.07.20 : 16.07.20 : 13.07.20 : 09.07.20 : ME on going 06.07.20 : cor done, curing time 02.07.20 : rebarring 29.06.20 : on going excavation 25.06.20 : Risk RFC Juni,on going excavation 22.06.20 : 18.06.20 : on going excavation, plan percepatan RFI mid July 15.06.20 : 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : IW on going 04.06.20 : 01.06.20 : IW on going 28.05.20 : 25.05.20 : rehunting 21.05.20 : 20.05.20 : RND NOK krn near existing, rehunting sesuai arahan RND 15.05.20 : RND review 13.05.20 : submit kand C 08.05.20 : 30.04.20 : IW on going 23.04.20 : 16.04.20 : IW OG, Terbatasnya komunikasi dengan perangkat kelurahan karena WFH 09.04.20 : Proses perijinan lingkungan dan Kelurahan, info pelayanan kelurahan sementara masih tutup terkait wabah corona. 02.04.20 : 25.03.20 : 23.03.20 : Proses IW OG 19.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°46'55.69"E 6°13'52.70"S/106.782136 -6.231306 OK, Center Antenna 20m
7 |  | JAW-BT-TGR-0042 | 30572520031 | 1317711003 | BABAKAN ASEM TELUK NAGA | ACTIVE | TB | 106.6632 | -6.0863 | 50 | 90/210/330 |  |  | Kp. Rawa Rotan, RT 02 RW 04, Desa Babakan Asem, Kec. Teluk Naga, Kab Tangerang | EID | JAW-BT-TGR-0042 | BABAKAN ASEM TELUK NAGA | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 232 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-04 | W27-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-28 | W35-2020 | Aug-2020 | MW | 2020-07-10 |  | 566601622819 | 6.6 |  |  |  | 2020-07-30 | 2020-09-01 | W36-2020 |  | 2020-08-28 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.09.20 : RFIN sent 31.08.20 : 27.08.20 : RFI actual, collecting doc RFIN 24.08.20 : rev plan RFI 28 Aug 17.08.20 : plan RFI 25 Aug 20 13.08.20 : 06.08.20 : 03.08.20 : 30.07.20 : SRFIN sent, proses PLN connection 23.07.20 : 20.07.20 : proses PLN connection 16.07.20 : 13.07.20 : SRFI actual 09.07.20 : 06.07.20 : 02.07.20 : ME on going, Tower Done, Plan Announce SRFI on 4 Juli 2020 29.06.20 : 25.06.20 : curingtime, prepare erection 22.06.20 : cor done, curingtime & backfilling 18.06.20 : 15.06.20 : rebarring 11.06.20 : 08.06.20 : excavation on going 04.06.20 : preparation start CME 01.06.20 : plan start cme 2 jun 28.05.20 : 25.05.20 : 14.05.20 : soiltest 08.05.20 : rekom on going 30.04.20 : Proses verifikasi eskalasi COST SITAC, High price cost SITAC 23.04.20 : TNP review 16.04.20 : under review RND, IW clear 09.04.20 : review RND, iw clear 08.04.20 : submit kand 02.04.20 : 25.03.20 : 20.03.20 : IW Clear, Proses approval Eskalasi SITAC 19.03.20 : IW clear 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = RND OK 40
53 |  | JAW-JK-TJP-0617 | 30571960031 | 1127741003 | INSPEKSI SUKAPURA | ACTIVE | TB | 106.9344 | -6.1492 | 25 | 20/90/210/330 |  |  | Jl. Pal 2, RT.004 RW.003, Kel. Sukapura, KEC. Cilincing, JAKARTA UTARA, DKI JAKARTA | EID | JAW-JK-TJP-0617 | Inspeksi Sukapura | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA UTARA | 6614368 | 2020-01-13 |  | 218 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-25 | W35-2020 | Aug-2020 | MW | 2020-08-30 |  | 545302733444 | 6.6 |  |  |  | 2020-07-14 | 2020-08-18 | W34-2020 |  | 2020-08-29 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 24.08.20 : 18.08.20 : RFIN sent 17.08.20 : RFI actual 16 aug 20 13.08.20 : 10.08.20 : revisi plan RFI 19 Aug 06.08.20 : 27.07.20 : 23.07.20 : 20.07.20 : proses PLN connection 14.07.20 : email SRFI-N sent 13.07.20 : ME on going 09.07.20 : Propose reaktivasi, erection on going 06.07.20 : Propose reaktivasi, progress CME cor pondasi done dan sedang curingtime 18.06.20 : Propose reaktivasi SPK, progress start excavation 11.06.20 : IW clear, actual status di Tower rental sudah return 08.06.20 : 04.06.20 : 01.06.20 : lahan KOMATSU, plan submit kand 4 jun. 29.05.20 : email return dari XL, site tetap continue dan need reaktivasi jika tower sudah berdiri/erection done 28.05.20 : 25.05.20 : 15.05.20 : IW on going 14.05.20 : 08.05.20 : 30.04.20 : rehunting 23.04.20 : 16.04.20 : Rehunting site, NOM berada di kawasan industri Komatsu 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : validasi RND 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°56'04.40"E 6°08'57.20"S/106.934556 -6.149222 OK, Center Antenna 20m
93 |  | JAW-JK-CKG-0667 | 30572270031 | 1127811003 | KESATRIAN KEBON MANGGIS | ACTIVE | TB | 106.8551 | -6.2084 | 25 | 0/90/180/300 |  |  | JL. Manggarai Utara 2, RT.01, RW 04, Kel. Manggarai, Kec. Tebet Jakarta Selatan | EID | JAW-JK-CKG-0667 | Kesatrian Kebon Manggis | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614368 | 2020-01-13 |  | 213 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-29 | W27-2020 | Jun-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-19 | W34-2020 | Aug-2020 | MW | 2020-08-30 |  | 544104322022 | 6.6 |  |  |  | 2020-06-29 | 2020-08-13 | W33-2020 |  | 2020-08-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 13.08.20 : RFIN sent 10.08.20 : revisi plan RFI 19 Aug 06.08.20 : 23.07.20 : 20.07.20 : proses PLN connection 13.07.20 : 09.07.20 : 06.07.20 : 02.07.20 : 29.06.20 : email SRFI-N sent, PLN connection menunggu konfirmasi XL/Tech partner 29.06.20 : SRFI, collecting doc SRFIN 25.06.20 : ME on going 22.06.20 : 18.06.20 : curingtime 15.06.20 : start CME 11.06.20 : proses validasi, paralel IW clear 08.06.20 : RND review 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review 28.05.20 : 25.05.20 : 22.05.20 : RND review 15.05.20 : RND review 08.05.20 : 30.04.20 : IW on going 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : validasi RND 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°51'18.24"E 6°12'27.32"S/106.855067 -6.207589 OK, Center Antenna 20m
167 |  | JAW-BT-TGR-0051 | 30572200031 | 1317521003 | STASIUN CIKOYA | ACTIVE | TB | 106.4124 | -6.3357 | 30 | 25/110/180/265 |  |  | Kp. Pos Cikoya Rt.002 Rw.001, Desa Cikasungka, Kec. Solear, Kab. Tangerang | EID | JAW-BT-TGR-0051 | Stasiun Cikoya | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 206 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-02 | W27-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-10 |  | 566401536248 | 6.6 |  |  |  | 2020-07-02 | 2020-08-06 | W32-2020 |  | 2020-08-29 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.08.20 : RFIN sent 03.08.20 : 30.07.20 : RFI actual, collecting doc 27.07.20 : 23.07.20 : 20.07.20 : proses PLN connection 16.07.20 : 13.07.20 : 09.07.20 : 06.07.20 : 02.07.20 : email SRFI-N sent, PLN connection menunggu konfirmasi XL/Tech partner 29.06.20 : 25.06.20 : curingtime, prepare erection 22.06.20 : curingtime 19.06.20 : pouring 18.06.20 : on going excavation 15.06.20 : 11.06.20 : excavation start 08.06.20 : 04.06.20 : preparation start CME 01.06.20 : RFC, plan start CME minggu depan 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : Plan Start CME 10/05 30.04.20 : Rekom Lurah done, Issue REKOM CAMAT, karena camat tidak mau mengeluarkan rekomendasi 23.04.20 : 16.04.20 : IW clear, proses pengajuan ulang eskalasi SITAC 09.04.20 : IW clear, proses pengajuan ulang eskalasi SITAC 02.04.20 : rekom on going 25.03.20 : 19.03.20 : 20.02.20 : Rekom lurah on going. Terkendala lurah akibat commcase tower existing 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = Ok 30
54 |  | JAW-JK-KYB-0097 | 30571760031 | 1127611003 | JALAN ASEM CIPEDAK | ACTIVE | TB | 106.8036 | -6.353 | 30 | 0/90/180/270 |  |  | Jl.Timbul III B RT.08, RW 04, Kel. Cipedak, Kec. Jagakarsa, Jakarta Selatan | EID | JAW-JK-KYB-0097 | Jalan Asem Cipedak | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614368 | 2020-01-13 |  | 192 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-10 |  | 547401717015 | 6.6 |  |  |  | 2020-06-30 | 2020-07-23 | W30-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.07.20 : 23.07.20 : RFIN sent 20.07.20 : proses PLN connection 13.07.20 : 09.07.20 : 06.07.20 : 30.06.20 : email SRFI-N sent, PLN connection menunggu konfirmasi XL/Tech partner 29.06.20 : 25.06.20 : curingtime 22.06.20 : 18.06.20 : on going excavation 15.06.20 : start CME 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : IW on going 04.06.20 : 01.06.20 : IW clear kand B 28.05.20 : 25.05.20 : 21.05.20 : IW on going 14.05.20 : TNP ok C, tower 25 08.05.20 : 30.04.20 : IW on going, terkendala RT sebelah warga radius yang belum setuju 23.04.20 : RND review 16.04.20 : proses eskalasi sitac 09.04.20 : 02.04.20 : IW Clear 25.03.20 : Candidat NOK, Rehunting 19.03.20 : 20.02.20 : IW on going 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
144 |  | JAW-JK-KYB-0027 | 30571980031 | 1127761003 | SABAR RAYA KEMAJUAN | ACTIVE | TB | 106.7527 | -6.2406 | 25 | 0/90/180/270 |  |  | Jl.Sabar II No.43 RT.07, RW.04, Kel.Petukangan Selatan, Kec.Pesanggrahan, Jakarta Selatan | EID | JAW-JK-KYB-0027 | Sabar Raya Kemajuan | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614368 | 2020-01-13 |  | 191 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-24 | W26-2020 | Jun-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-10 |  | 543802871087 | 6.6 |  |  |  | 2020-06-24 | 2020-07-22 | W30-2020 |  | 2020-08-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22.07.20 : RFIN sent 20.07.20 : proses PLN connection 13.07.20 : 09.07.20 : 06.07.20 : 29.06.20 : 24.06.20 : email SRFI-N sent, PLN connection menunggu konfirmasi XL/Tech partner 22.06.20 : ME on going 18.06.20 : curingtime, prepare erection 15.06.20 : 11.06.20 : 08.06.20 : 04.06.20 : curingtime 28.05.20 : 25.05.20 : curingtime 14.05.20 : 08.05.20 : rekom on going 30.04.20 : Proses IW OG, terkendala pembatasan lingkungan 23.04.20 : 16.04.20 : IW OG, Terbatasnya komunikasi dengan perangkat kelurahan karena WFH 09.04.20 : validasi done, IW on going 02.04.20 : under review RND 25.03.20 : IW on going 19.03.20 : validasi RND 20.02.20 :06.02.20 : Hunting kandidat
77 |  | JAW-BT-TGR-0029 | 30572020031 | 1317411003 | KARET SEPATAN TANGERANG | ACTIVE | TB | 106.5804 | -6.1467 | 50 | 40/140/320 |  |  | Kp. Karet RT 02 Rw 03, Desa Karet, Kecamatan Sepatan, Kabupaten Tangerang - Banten. | EID | JAW-BT-TGR-0029 | Karet Sepatan Tangerang | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 185 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-02 | W27-2020 | Jul-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-07-10 |  | 566601592387 | 6.6 |  |  |  | 2020-07-02 | 2020-07-16 | W29-2020 |  | 2020-08-07 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 20.07.20 : 16.07.20 : RFIN sent 13.07.20 : 09.07.20 : 06.07.20 : 02.07.20 : email SRFI-N sent, PLN connection menunggu konfirmasi XL/Tech partner 29.06.20 : 25.06.20 : SRFI, collecting doc SRFIN 22.06.20 : 18.06.20 : curingtime, prepare erection 15.06.20 : 11.06.20 : rebarring 08.06.20 : 04.06.20 : excavation on going 01.06.20 : excavation start 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : rekom on going 30.04.20 : Proses negosiasi ke lingkungan untuk realisasi IW 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : rekom on going 25.03.20 : 19.03.20 : rekon l/c on going 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A, B, C = validasi done, Candidate A, B & C RF TX OK 24.01.20 : kand A, B, C = RND A OK 40 Prio 2 B OK 40 Prio 3 C OK 40 Prio 1
130 |  | JAW-JK-GGP-0529 | 30571970031 | 1127751003 | PEGADUNGAN TEGAL ALUR | ACTIVE | TB | 106.7029 | -6.1179 | 30 | 50/140/190 |  |  | Jalan Prepedan Dalam RT. 006 / RW. 009, Kel. Kamal, Kec. Kali Deres - Jakarta Barat | EID | JAW-JK-GGP-0529 | Pegadungan Tegal Alur | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA BARAT | 6614368 | 2020-01-13 |  | 196 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-29 | W27-2020 | Jun-2020 | 2020-07-25 | W30-2020 | Jul-2020 | 2020-07-28 | W31-2020 | Jul-2020 | MW | 2020-07-10 |  | 546303095490 | 6.6 |  |  |  | 2020-06-29 | 2020-07-27 | W31-2020 |  | 2020-08-06 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 27.07.20 : RFIN sent 23.07.20 : 20.07.20 : proses PLN connection 13.07.20 : 09.07.20 : 06.07.20 : 29.06.20 : email SRFI-N sent, PLN connection menunggu konfirmasi XL/Tech partner 25.06.20 : curingtime 22.06.20 : P[MIM] optimis RFI Jun 22.06.20 : Pouring done 20/06, Erection start 26/06 finish 28/06, S RFI 29/06 18.06.20 : on going excavation 15.06.20 : proses perijinan, APD & bouwplank 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : RND review 04.06.20 : IW clear 01.06.20 : 29.05.20 : waiting RND review, paralel IW on going 28.05.20 : 25.05.20 : 22.05.20 : RND review 21.05.20 : 20.05.20 : Apakah bisa tinggi RF 25m? Menjauh dari yg mau dicover 15.05.20 : RND review 13.05.20 : submit kand C 14.05.20 : 08.05.20 : 30.04.20 : rehunting 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : validasi RND 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
87 |  | JAW-JK-CKG-0666 | 30572260031 | 1127801003 | KEMUNING MATRAMAN | ACTIVE | TB | 106.8633 | -6.1976 | 25 | 0/90/180/270 |  |  | Jl. Kemuning II RT 004 RW 004 kel. Utan Kayu Utara kec. Matraman Jakarta Timur. | EID | JAW-JK-CKG-0666 | Kemuning Matraman | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614368 | 2020-01-13 |  | 254 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-09-22 | W39-2020 | Sep-2020 | MW | 2020-06-12 |  | 541301474411 | 6.6 |  |  |  |  | 2020-09-23 | W39-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23.09.20 : RFIN sent 21.09.20 : 17.09.20 : 14.09.20 : 07.09.20 : 03.09.20 : 02.09.20 : XL approved dg Prabayar (Token) dan pengisisn token 1 jt by TBG, proses PLN Connection 31.08.20 : 25.08.20 : SRFIN sent, waiting approval daya 16.5 kVA rayon cempaka putih 27.08.20 : 24.08.20 : revisi plan RFI 28 Aug 17.08.20 : plan RFI 21 Aug 20 13.08.20 : 10.08.20 : SRFI, proses PLN connection 06.08.20 : Plan Finish Erection 08/08, Plan S RFI 10/08 03.08.20 : on going erection, plan erection done 8 aug 30.07.20 : Erection start 30/07 27.07.20 : curingtimec 23.07.20 : Galian pondasi OG, Re design pondasi terkait perubahan type Pole MCP, plan Pouring 25/07 20.07.20 : Galian pondasi OG, Re design pondasi terkait perubahan type Pole MCP 16.07.20 : 13.07.20 : excavation 09.07.20 : 06.07.20 : On Going Excavation 02.07.20 : On Going Excavation, Due to need Process Permit Issue (Done Solve) 29.06.20 : on going rekom 25.06.20 : Plan IW Done Jun 2020 22.06.20 : Risk RFC Juni, tiba2 muncul penolakan warga, plan geser dan proses nego ke XL, paralel pengajuan kand baru ke XL 22.06.20 : 18.06.20 : 15.06.20 : 11.06.20 : excavation start 08.06.20 : proses rekom 04.06.20 : IW on going 01.06.20 : 29.05.20 : IW on going, paralel validasi kand alternatif, waiting TNP review, kand geser 15m, plan start minggu depan, plan RFI 15 juni (KLS) 28.05.20 : 25.05.20 : 21.05.20 : IW on going 14.05.20 : TNP ok B, tower 20 08.05.20 : 30.04.20 : 30.04.20 : IW on going 23.04.20 : 16.04.20 : IW OG, Terbatasnya komunikasi dengan perangkat kelurahan karena WFH 09.04.20 : Proses perijinan lingkungan dan Kelurahan, info pelayanan kelurahan sementara masih tutup terkait wabah corona. - sampai dengan saat ini pihak kelurahan masih belum bisa membantu proses ijin lingkungan di karenakan dengan adanya issue corona. 02.04.20 : 25.03.20 : 23.03.20 : Proses IW, kelurahan pelayanan tutup sementara terkait isu corona 19.03.20 : IW on going 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
111 |  | JAW-JK-KYB-0102 | 30571790031 | 1127641003 | MENTENG LENTENG AGUNG | ACTIVE | TB | 106.8307 | -6.3285 | 25 | 0/180/290 |  |  | Jl.Menteng, RT.07 RW.06 Kel. Lenteng Agung, Kec. Jagakarsa, Jakarta Selatan | EID | JAW-JK-KYB-0102 | Menteng Lenteng Agung | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614368 | 2020-01-13 |  | 246 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-09-15 | W38-2020 | Sep-2020 | MW | 2020-06-12 |  | 547401737021 | 6.6 |  |  |  | 2020-07-23 | 2020-09-15 | W38-2020 |  | 2020-09-25 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.09.20 : RFIN sent 14.09.20 : 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : 24.08.20 : Proses Ijin ke Dinas Pertamanan, karena menggunakan kabel bawah tanah, rev plan RFI 5 sep (W1 sep) 17.08.20 : Need kabel bawah tanah, plan Connect 19/08 13.08.20 : 10.08.20 : revisi plan RFI 19 Aug 06.08.20 : 27.07.20 : 23.07.20 : email SRFI-N sent 23.07.20 : Finishing ME Istallation 20.07.20 : Erection OG 16.07.20 : 13.07.20 : 09.07.20 : erection on going 06.07.20 : cor done, curing time 02.07.20 : excavation start, On Going Excavation Due to late in Process Permit Dinas Pertanaman Jaksel (Issue Solve) 29.06.20 : bouwplank, paralel proses perijinan 25.06.20 : bouwplank, Plan RFI Jul 2020 22.06.20 : Risk RFC Juni, 22.06.20 : 18.06.20 : 15.06.20 : proses perijinan, APD & bouwplank 11.06.20 : design pack & bouwplank, proses perijinan, menunggu perijinan dinas pertamanan 08.06.20 : 04.06.20 : proses perijinan, preparation start CME 01.06.20 : rekom 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : Negosiasi BAN 23.04.20 : 16.04.20 : IW OG, Terbatasnya komunikasi dengan perangkat kelurahan karena WFH 09.04.20 : 02.04.20 : 25.03.20 : 19.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°49'50.74"E 6°19'41.56"S/106.830761 -6.328211 OK, Center Antenna 20m
92 |  | JAW-JK-CKG-0664 | 30571800031 | 1127651003 | KESADARAN CIPINANG | ACTIVE | TB | 106.8863 | -6.2367 | 25 | 0/70/180/275 |  |  | Bambu kuning selatan, RT 13, RW 02 , Kel. BAMBU Apus, Kec. Cipayung, Kota jakarta timur | EID | JAW-JK-CKG-0664 | Kesadaran Cipinang | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614368 | 2020-01-13 |  | 197 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-30 | W27-2020 | Jun-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-06-24 |  | 544104319788 | 6.6 |  |  |  | 2020-06-26 | 2020-07-28 | W31-2020 |  | 2020-08-18 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.07.20 : RFIN sent 23.07.20 : actual RFI20.07.20 : proses PLN connection 13.07.20 : 09.07.20 : 06.07.20 : 02.07.20 : email SRFI-N sent, wait SK PLN release from XL 29.06.20 : 25.06.20 : email SRFI-N sent 25.06.20 : ME on going 22.06.20 : [MIM] optimis RFI Jun 22.06.20 : Erection Plan start 23/06, Plan S RFI 26/06 18.06.20 : curingtime, plan RFI end June 15.06.20 : proses perijinan, APD & bouwplank 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : IW on going 04.06.20 : 01.06.20 : kand approved, IW on going 28.05.20 : 25.05.20 : 15.05.20 : TNP review 14.05.20 : approval kandidat, kabdidat sebelumnya commcase 08.05.20 : 30.04.20 : Galian Pondasi Block akses warga 30.04.20 : need cek status RND validationnya 23.04.20 : 16.04.20 : on going excavation 09.04.20 : Galian pondasi OG 02.04.20 : RFC, proses perijinan 25.03.20 : 23.03.20 : IW Clear 19.03.20 : IW on going 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
79 |  | JAW-BT-TGR-0031 | 30572160031 | 1317481003 | KAYU AGUNG SEPATAN | ACTIVE | TB | 106.5919 | -6.0966 | 40 | 15/90/280 |  |  | Jalan Mangga 2 RT 05 RW 05 Desa Kayu Agung Kecamatan Sepatan Kabupaten Tangerang-Banten | EID | JAW-BT-TGR-0031 | Kayu Agung Sepatan | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 170 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-12 | W20-2020 | May-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-07 | W32-2020 | Aug-2020 | MW | 2020-06-12 |  | 566601578127 | 6.6 |  |  |  |  | 2020-07-01 | W27-2020 |  | 2020-07-23 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.07.20 : RFIN sent 29.06.20 : Proses PLN Connection 22.06.20 : 18.06.20 : curingtime, prepare erection 15.06.20 : prepare cor 11.06.20 : rebarring 08.06.20 : excavation on going 04.06.20 : proses perijinan, preparation start CME 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : Proses REKOM, terkendala permintaan biaya LURCAM yang tinggi 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : rekom on going 25.03.20 : 19.03.20 : rekom l/c on going 11.03.20 : 09.03.20 : IW CLear, Realisasi OG 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A, B, C = validasi done, Candidate A, B & C RF TX OK 24.01.20 : kand A = RND A OK 40 Prio 2 B OK 40 Prio 3 C OK 40 Prio 1
135 |  | JAW-JK-CKG-0155 | 30571880031 | 1127701003 | PULO BUARAN JATINEGARA | ACTIVE | TB | 106.9178 | -6.2063 | 30 | 0/65/140/240 |  |  | JL. Pulobuaran I (komplek Pergudangan) PT. JIEP RT.004 RW.006, Kelurahan Jatinegara, Kecamatan Cakung, Kota Jakarta Timur, Provinsi DKI Jakarta | EID | JAW-JK-CKG-0155 | Pulo Buaran Jatinegara | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614368 | 2020-01-13 |  | 291 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-08-04 | W32-2020 | Aug-2020 | 2020-10-16 | W42-2020 | Oct-2020 | MW | 2020-10-01 |  | 541301488450 | 6.6 |  |  |  | 2020-09-30 | 2020-10-30 | W44-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 02.11.20 : RFIN sent 26.10.20 : proses penyambungan PLN 22.10.20 : 19.10.20 : 15.10.20 : 12.10.20 : revisi PLN connection 16 oct 20, waiting approval Power Eng XL terkait isu Rayon PLN Cempaka Putih (Daya 13.5 kVA kebawah dilayani dg Pra bayar, Daya 16.5 kVA keatas dengan Pasca Bayar) 05.10.20 : 01.10.20 : proses PLN connection, plan 10 oct 30.09.20 : email SRFI-N sent 28.09.20 : Finishing ME, on going Pagar & halaman 24.09.20 : ME Installation OG 21.09.20 : 17.09.20 : Curing Time OG, Plan Erection 24/09 finish 26/09, Plan S RFI 28/09 14.09.20 : rebarring, plan cor besok menunggu usrat ijin dari PT. JIEP 10.09.20 : Plan galian Finish 10/09, Plan Pouring 12/09, Plan S RFI 20/09 07.09.20 : galian on going, PKS signed dan rekom lurcam, proses perijinan 03.09.20 : MOM : start galian 31.08.20 : 27.08.20 : 24.08.20 : menunggu rilis Surat ijin kerja dr PT JIP untuk start CME 17.08.20 : proses BA jaminan dari JIP (Jakarta Idustrial Estate PuloGadung) untuk syarat start CME, plan start CME paling lmabat 20 AUG 13.08.20 : Survey done, PT. JIEP meminta digeser sitenya 200m untuk mendekati utilitas kabel power dan FO 10.08.20 : OG Join Survey dengan PT JIEP, untuk penempatan posisi Pole MCP (kand A) 06.08.20 : kembali kand A, plan bouwplank minggu depan 30.07.20 : 23.07.20 : 20.07.20 : Mediasi pertama belum menemui titik temu, plan mediasi kedua melibatkan Lurah, MUSPIKA, dan tokoh masyarkat 18/07 16.07.20 : 13.07.20 : 09.07.20 : MOM : ada comcase, sudah IW clear tetapi ada provokasi warga luar radius, besok malam diadakan mediasi dengan tokoh masyarakat, jika isu clear maka proses realisasi dilanjutkan minggu depan. 06.07.20 : 02.07.20 : IW clear, plan rekom release 6 juli, plan start CME 10 jul, Plan RFI 4 aug 29.06.20 : IW clear 25.06.20 : IW kurang 3 kk dari 20 kk, pole MCP 20m 22.06.20 : 18.06.20 : XL ok 20 m, kembali ke kand awal, proses rekom 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20 08.06.20 : RND review 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review, paralel IW on going 28.05.20 : 25.05.20 : 22.05.20 : RND review 21.05.20 : 20.05.20 : remark RND Apakah bisa tinggi RF 25m? Menjauh dari yg mau dicover 15.05.20 : RND review 13.05.20 : submit kand C 14.05.20 : 08.05.20 : 30.04.20 : rehunting 23.04.20 : 16.04.20 : Rehunting site, NOM berada dikawasan Industri JIP, high price sewa lahan PT.JIEP, rehunting hard space 300 meter. Mohon arahan 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : validasi RND 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°55'03.87"E 6°12'22.44"S/106.917742 -6.206233 OK, Center Antenna 20m
96 |  | JAW-JK-CKG-0665 | 30571850031 | 1127671003 | KRAMA YUDHA CAKUNG | ACTIVE | TB | 106.9226 | -6.1792 | 30 | 0/90/180/270 |  |  | Jl. Krama Yudha, RT.006 RW.005, Kel. Rawa Terate, Kec.Cakung, Jakarta Timur. | EID | JAW-JK-CKG-0665 | Krama Yudha Cakung | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA TIMUR | 6614368 | 2020-01-13 |  | 256 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-08 | W32-2020 | Aug-2020 | 2020-08-08 | W32-2020 | Aug-2020 | 2020-09-22 | W39-2020 | Sep-2020 | MW | 2020-09-10 |  | 545302748868 | 6.6 |  |  |  | 2020-09-08 | 2020-09-25 | W39-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.09.20 : RFIN sent 24.09.20 : RFI actual, collecting doc RFIN 21.09.20 : 17.09.20 : 08.09.20 : SRFI N sent, proses PLN Connection 10.09.20 : Erection Done, ME Installation OG 07.09.20 : erection OG 03.09.20 : erection on going 31.08.20 : curingtime 27.08.20 : GALIAN Pondasi OG, Plan Finish 27/08, Plan pouring 30/08 24.08.20 : 17.08.20 : bouwplang, Plan Start CME 22/08 13.08.20 : Plan Start CME 15/08 10.08.20 : rekom l/c on going, revisi plan RFI 19 Aug 06.08.20 : IW kandidat C Clear, REKOM plan done 12/08, plan realisasi IW minggu ini 03.08.20 : 30.07.20 : 23.07.20 : 20.07.20 : Proses PKS dengan PT. Mitsubishi Motors, Direksi PT. Mitsubishi motors masih belum bisa ditemui, paralel sedang di follow re IW kandidat A 16.07.20 : 13.07.20 : 09.07.20 : MOM : menunggu feedback pengajukan kerjasama/PKS dg PT. Mitsubishi, wait persetujuan PKS dari dirut operational, lokasi di kawasan industri (area mitsubishi), plan minggu depan ketemu management Mitsubishi 06.07.20 : 02.07.20 : IW clear, proses pembahasan PKS dengan PT.Mitsubishi Motor dengan plan clear PKS minggu depan, plan start CME 15 jul, plan RFI 8 aug 29.06.20 : 25.06.20 : IW clear, pole MCP 25m, pengambilan foto panoramic by drone 22.06.20 : 18.06.20 : akan diukur ketinggian existing (25m) untuk referensi approval 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20 08.06.20 : RND review 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review 28.05.20 : 25.05.20 : 22.05.20 : RND review 15.05.20 : RND review 08.05.20 : 30.04.20 : 30.04.20 : IW on going 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : IW on going 25.03.20 : IW on going 19.03.20 : validasi RND 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 30.01.20 : kand A = submit A 106°55'20.39"E 6°10'41.38"S/106.922331 -6.178161 OK, Center Antenna 20m
50 |  | JAW-JT-BBS-0156 | 30571950031 | 1432341003 | GLONGGONG | ACTIVE | TB | 109.0322 | -6.9241 | 50 | 20/110/190/290 |  |  | GLONGGONG, RT 004/ RW 004, DESA GLONGGONG, KEC. WANASARI, KAB. BREBES | EID | JAW-JT-BBS-0156 | GLONGGONG | B2S | TBG | CENTRAL | JATENG | DI Yogyakarta | BREBES | 6614368 | 2020-01-13 |  | 219 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | 2020-08-14 | W33-2020 | Aug-2020 | 2020-08-19 | W34-2020 | Aug-2020 | MW | 2020-06-24 |  | 522582398996 | 7,7 |  |  |  | 2020-06-15 | 2020-08-19 | W34-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 19.08.20 : RFIN sent 18.08.20 : actual RFI, plan submit RFIN 19 Aug 13.08.20 : plan PLN connect jumat 14 Aug 20 10.08.20 : 06.08.20 : BP paid, plan PLN connect Rabu 12 Aug 20 03.08.20 : 27.07.20 : SLO released 20.07.20 : 16.07.20 : SK PLN release 15 jul 13.07.20 : 09.07.20 : SK PLN masih belum release from XLz02.07.20 : 29.06.20 : Menunggu SK PLN release dari XL, plan RFI menyesuaikan kembali dg SK release (SK date+14 hari) 15.06.20 : email SRFI-N sent 04.06.20 : SRFI actual, collecting doc SRFIN 01.06.20 : 28.05.20 : erection done, ME on going 21.05.20 : ME on going 14.05.20 : erection on going 30.04.20 : curingtime 23.04.20 : 16.04.20 : rebarring, plan cor besok 17 Apr 09.04.20 : on going rebarring dan bekisting, prepare for pouring concrete 02.04.20 : 25.03.20 : start excavation 19.03.20 : prepare start CME, plan minggu ini 28.02.20 : proses perijinan, proses design pack (APD), plan design done minggu depan, material tower ready 20.02.20 : rekom done, submit berkas proses perijinan 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 20.01.20 : Kand A, B = submit kand A di 109.03193 -6.9246 (58m) propose Tower 52m, submit kand B di 109.03233 -6.92281 (148m) propose Tower 52m
69 |  | JAW-BT-TGR-0045 | 30572550031 | 1317741003 | KAMPUNG BESAR TELUK NAGA | ACTIVE | TB | 106.6546 | -6.0613 | 50 | 90/210/330 |  |  | Kp Kampung Besar, RT. 12 RW. 06, Kel. Kampung Besar, Kec. Teluk Naga, Kab. Tangerang | EID | JAW-BT-TGR-0045 | KAMPUNG BESAR TELUK NAGA | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 215 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-15 | W33-2020 | Aug-2020 | MW | 2020-08-30 |  | 566601624992 | 6.6 |  |  |  | 2020-08-10 | 2020-08-15 | W33-2020 |  | 2020-08-31 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.08.20 : RFIN sent 14.08.20 : actual RFI, collecting doc RFIN 13.08.20 : 10.08.20 : SRFIN sent 06.08.20 : ME Installation OG, Plan S RFI 09/08 03.08.20 : 30.07.20 : Tower Erection, Plan Finish 02/08, Plan S RFI 08/08 27.07.20 : 23.07.20 : rebarring 20.07.20 : Borpile done, OG perapihan lantai kerja 16.07.20 : rebarring 13.07.20 : 09.07.20 : excavation 06.07.20 : 02.07.20 : RFC, plan start CME 6 juli, plan SRFI 31 jul 29.06.20 : soiltest done, plan APD senin/selasa 30 jun 25.06.20 : plan sabtu soiltest, rekom done, plan APD senin/selasa 30 jun 22.06.20 : 18.06.20 : on going rekom process,realisasi IW dan soiltest, Plan start CME Jun 2020 15.06.20 : IW done, proses rekom 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : 04.06.20 : 01.06.20 : IW clear, proses eskalasi sitac 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : Rehunting OG 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : IW on going 25.03.20 : TNP review 19.03.20 : 19.03.20 : Rehunting 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = RND OK 50
122 |  | JAW-BT-TGR-0044 | 30572540031 | 1317731003 | PANTAI DADAP | ACTIVE | TB | 106.7138 | -6.0894 | 50 | 90/210/330 |  |  | Kp. Dadap Gili, RT. 003 RW.001, Desa Dadap, Kecamatan Kosambi, Kabupaten Tangerang | EID | JAW-BT-TGR-0044 | PANTAI DADAP | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 259 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-09-30 | W40-2020 | Sep-2020 | 2020-08-20 | W34-2020 | Aug-2020 | 2020-09-30 | W40-2020 | Sep-2020 | MW | 2020-08-30 |  | 566601649407 | 6.6 |  |  |  |  | 2020-09-28 | W40-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.09.20 : RFIN sent 28.09.20 : Finishing ME, on going Pagar & halaman 24.09.20 : Finishing ME, Plan S RFI 26/09 21.09.20 : 18.09.20 : erection on going 17.09.20 : plan finish 21/09, Plan S RFI 24/09, Plan RFI 25/09 14.09.20 : erection on going 10.09.20 : Erection start 10/09 finish 17/09, Plan S RFI 21/09 07.09.20 : Curing time 03.09.20 : re design penambahan sumuran menjadi 9 titik, Cor Sumuran done 1/9 31.08.20 : OG Rebaring pondasi sumuran, Plan Pouring sumuran done 03/09 27.08.20 : OG Galian sumuran, re design penambahan sumuran menjadi 9 titik 24.08.20 : 17.08.20 : OG Galian pondasi sumuran, terkendala debit air yang tinggi 13.08.20 : OG Galian pondasi sumuran, Plan pengecoran pondasi sumuran 19/08 10.08.20 : 06.08.20 : Galian pondasi OG, Plan Pengecoran sumuran 15/08, Plan pengecoran pondasi tower 21/08 03.08.20 : 30.07.20 : Galian pondasi, terkendala galian berbatu dan beton, Re design Done, Plan Re start CME 02/08 27.07.20 : 23.07.20 : 20.07.20 : Galian pondasi, terkendala galian berbatu dan beton 16.07.20 :13.07.20 : 09.07.20 : excavation 02.07.20 : rekom process, plan rekom done 7 juli, on going soiltest, plan design done 10 Aug, plan start CME 13 juli, plan RFI 7 aug 20 29.06.20 : IW clear 25.06.20 : Plan IW clear, SST 52m, plan start CME minggu depan 2 jul 22.06.20 : 18.06.20 : IW clear dg tinggi twr 35 m (RT + MT 25), propose RND 50m (tidak ada design tower>25m utk RT). Plan rehunting di seberang possibility SST GF 50m, plan update minggu ini 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20, sudah ada kandidat (plan re-IW), propose tinggi tower 35m 08.06.20 : RND review 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review 28.05.20 : 25.05.20 : 14.05.20 : BAK 08.05.20 : 30.04.20 : Rehunting OG 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : under review RND 25.03.20 : rehunting 19.03.20 : 19.03.20 : Rehunting 11.03.20 : 20.02.20 : Hunting, area NOM berada di kawasan pegudangan Mutiara Kosambi 13.02.20 : 06.02.20 : Hunting kandidat
147 |  | JAW-BT-TGR-0043 | 30572530031 | 1317721003 | SALEMBARAN JAYA KOSAMBI | ACTIVE | TB | 106.666 | -6.0789 | 50 | 90/210/330 |  |  | Pemukiman GG Putri V, RT 02 RW 15, Kel. Salembaran Jaya, Kec. Kosambi, Kab Tangerang | EID | JAW-BT-TGR-0043 | SALEMBARAN JAYA KOSAMBI | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 232 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-08-20 | W34-2020 | Aug-2020 | 2020-09-04 | W36-2020 | Sep-2020 | MW | 2020-07-10 |  | 566601627916 | 6.6 |  |  |  |  | 2020-09-01 | W36-2020 |  | 2020-09-19 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.09.20 : RFIN sent 31.08.20 : ME on going 27.08.20 : Plan Finish erection 30/08, Plan RFI 04/09 24.08.20 : 17.08.20 : Erection tower OG, Plan Finish 20/08, Plan S RFI 24/08 13.08.20 : Erection tower OG, Plan Finish 20/08, Plan S RFI 24/08 10.08.20 : erection on going 06.08.20 : curingtime, plan start erection 7 Aug 20 03.08.20 : curingtime 30.07.20 : Pengecoran Pondasi Tower 23.07.20 : 20.07.20 : Lean concrete, pembesian di ulang kembali karena longsor galian 16.07.20 : 13.07.20 : rebarring 09.07.20 : galian done, lantai kerja, prepare rebarring 06.07.20 : 02.07.20 : On Going Lean Concrete due to Problem Hard Community Issue (Already Solve on 30 June 2020) 29.06.20 : 25.06.20 : 22.06.20 : curingtime 18.06.20 : rebarring, Plan Pouring 19/06 15.06.20 : 11.06.20 : excavation 08.06.20 : 04.06.20 : preparation start CME 01.06.20 : RFC, plan start CME minggu depan 28.05.20 : 25.05.20 : soiltest 14.05.20 : 08.05.20 : iw clear 30.04.20 : OG negosiaisi eskalasi SITAC 23.04.20 : 16.04.20 : OG negosiaisi eskalasi SITAC, high price 09.04.20 : 02.04.20 : 25.03.20 : 20.03.20 : IW Clear, Proses approval Eskalasi SITAC 19.03.20 : IW clear 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = RND OK 40
202 |  | JAW-BT-CPT-0472 | 30572500031 | 1317691003 | WIJAYAKUSUMA CEGER | ACTIVE | TB | 106.7286 | -6.2614 | 35 | 90/210/330 |  |  | KP.Blok kelapa Rt.06,Rw.05,Kelurahan.jurang Mangu Barat,Kecamatan.pondok Aren,kota tangerang selatan,Provinsi Banten | EID | JAW-BT-CPT-0472 | WIJAYAKUSUMA CEGER | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 444 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2021-02-25 | W09-2021 | Feb-2021 | 2020-08-25 | W35-2020 | Aug-2020 | 2021-03-31 | W14-2021 | Mar-2021 | MW | 2020-08-30 | [7 empty] | 2021-04-01 | W14-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 01.04.21 : RFIN sent 29.03.21 : CME done, OG PLN connection 23.03.21 : galian OG 15.03.21 : rekom camat done, CME preparation 04.03.21 : rekom OG, plan CME start W2 Mar 22.02.21 : IW CLEAR, realisasi IW OG, plan CME start W2 Mar 18.02.21 : target IW clear 20 Feb 11.02.21 : target penyelesaian mediasi warga 15 Feb, paralel IW OG di kandidat alternatif 28.02.21 : proses mediasi warga yg menolak dengan bantuan BABINSA dilaksanakan 29 Jan, plan IW clear 30 Jan 18.01.21 : 14.01.21 : CME belum bisa start karena ada 1 warga yg menyatakan belum clear (IW terlewat) -> note : start CME latest W4 Jan 28.12.20 : CME preparation 21.12.20 : realisasi IW done, plan CME start 23 Dec 17.14.20 : isu commcase clear, proses realisasi IW 10.12.20 : penyelesaian mediasi lanjutan 11 Dec 07.12.20 : 03.12.20 : plan issue clear W2 Dec 26.11.20 : 23.11.20 : 19.11.20 : penyelesaian issue commcase warga luar radius, plan issue closed dan RFC W5 Nov 16.11.20 : proses IW ongoing karena ada pergeseran kandidat 05.11.20 : plan solved minggu depan, target RFI diupayakan end of Nov 02.11.20 : 22.10.20 : 19.10.20 : 15.10.20 : 12.10.20 : 08.10.20 : 05.10.20 : erection masih stop, proses renegosiasi dan pendekatan dengan warga yang luar radius 01.10.20 : Pekerjaan erection di STOP kembali oleh warga, Plan dilakukan mediasi kembali tgl 03/10, rev RFI plan 15 oct 28.09.20 : 24.09.20 : Erection OG, Plan Finish 27/09, ME Done 28/09, Plan RFI 30/09 21.09.20 : Erection Stop Commcase warga radius 17.09.20 : penyelesaian COMCASE warga radius, pencabutan BAP ke kepolisian, plan Start Erection 21/09, Finish 23/09, Plan S RFI 25/09 14.09.20 : plan isu clear dan lanjut ME 18 sep 20 10.09.20 : 07.09.20 : 03.09.20 : erection STOP, minus 1 section & mounting, proses penyelesaian isu commcase, plan solve minggu depan 31.08.20 : 27.08.20 : comcase, erection on going 24.08.20 : 17.08.20 : 13.08.20 : COMCASE warga radius, Plan Mediasi dengan perangkat lingkungan Done, OG FU permintaan warga 10.08.20 : comcase, revisi plan RFI 28 Aug 06.08.20 : erection on going, COMCASE warga radius, Plan Mediasi dengan perangkat lingkungan 08/08 03.08.20 : 30.07.20 : Plan erection Tower Done 31/07 23.07.20 : Erection Tower Start 23/07, Finish 25/07, S RFI 29/07 20.07.20 : Curing Time 16.07.20 : rebarring 13.07.20 : 09.07.20 : excavation 02.07.20 : rekom process, plan rekom done 7 jul, plan start CME 9 jul, plan SRFI 5 aug 20 29.06.20 : IW clear 25.06.20 : IW on going, kurang 2kk, MCP 25m, , plan IW clear paling lambat Senin 29 Juni or drop by XL 25.06.20 : submit kandidat C , RNP approved RF 24m, Plan IW Done Jun 2020 22.06.20 : 18.06.20 : IW on going, Plan IW Done Jun 2020 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20 , sudah ada kandidat (plan re-IW) 08.06.20 : 04.06.20 : 01.06.20 : IW on going 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : IW on going 23.04.20 : TNP review 16.04.20 : under review RND 09.04.20 : review RND 08.04.20 : submit kand 02.04.20 : 25.03.20 : rehunting 19.03.20 : 19.03.20 : Rehunting 11.03.20 : 20.02.20 : rehunting, makesure regulasi tangsel 13.02.20 : 06.02.20 : Hunting kandidat
15 |  | JAW-JK-KYB-0103 | 30573400031 | 1127901003 | BENDA CIGANJUR | ACTIVE | TB | 106.8046 | -6.3272 | 30 | 20/180/280 |  |  | Jl. Manggis Dalam No 1, RT 01, RW 01, Kel. Ciganjur, Kec. Jagakarsa, Jakarta Selatan | EID | JAW-JK-KYB-0103 | Benda Ciganjur | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614368 | 2020-01-13 |  | 212 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-05 | W32-2020 | Aug-2020 | 2020-08-25 | W35-2020 | Aug-2020 | 2020-08-19 | W34-2020 | Aug-2020 | MW | 2020-08-30 |  | 547401725305 | 6.6 |  |  |  |  | 2020-08-12 | W33-2020 |  | 2020-09-08 |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 12.08.20 : RFIN sent 10.08.20 : revisi plan RFI 19 Aug 06.08.20 : 03.08.20 : SRFI actual 27.07.20 : ME on going 23.07.20 : ERECTion Tower Start 22/07, Finish 23/07 20.07.20 : Curing Time 16.07.20 : curingtime 13.07.20 : start excavation 09.07.20 : MOM : on going realisasi, sebelumnya terkendala peribahan permintaan warga 06.07.20 : 02.07.20 : plan rekom done selasa 7 jul, plan start CME 10 juli, plan SRFI 5 Aug 29.06.20 : on going rekom 25.06.20 : IW kurang 1 kk, pole MCP 20m 22.06.20 : 18.06.20 : IW on going, plan RFC end of June 15.06.20 : 11.06.20 : IW on going 08.06.20 : RND review 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review, paralel IW on going 28.05.20 : 25.05.20 : 22.05.20 : RND review 21.05.20 : 20.05.20 : RND note minta ketinggian 27m (atau minimal 25m) 15.05.20 : RND review 13.05.20 : submit kand B 08.05.20 : 30.04.20 : Terbatasnya komunikasi dengan LL karena belum mau ditemui 23.04.20 : 16.04.20 : terbatasnya komunikasi dengan LL karena belum mau ditemui 09.04.20 : Lahan private, proses BAN, saat ini LL menunda pertemuan negosiasi harga sampai issu corona selesai.alternatif rehunting , info tim sar 200 meter hard space 02.04.20 : 25.03.20 : rehunting 19.03.20 : 20.02.20 : 06.02.20 : Hunting kandidat 16.01.20 : Proses input STIP 1 B2S 15.01.20 : propose change to colo (email Rudi), konfirmasi NOK dari XL (Pak Siro)
30 |  | JAW-JB-CBI-0085 | 30572090031 | 1260901003 | CILLIWUNG PONDOK RAJEG | ACTIVE | TB | 106.819 | -6.463 | 50 | 80/170/250/310 |  |  | Jl. Penjara Pondok Rajeg RT 001 RW 005, Kelurahan Pondok Rajeg, Kecamatan Cibinong, Kabupaten Bogor | EID | JAW-JB-CBI-0085 | Cilliwung Pondok Rajeg | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614368 | 2020-01-13 |  | 239 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-12 | W33-2020 | Aug-2020 | 2020-08-31 | W36-2020 | Aug-2020 | 2020-08-31 | W36-2020 | Aug-2020 | MW | 2020-08-10 |  | 538722643487 | 6.6 |  |  |  |  | 2020-09-08 | W37-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.09.20 : RFIN sent 07.09.20 : 03.09.20 : SRFI actual 31.08.20 : 27.08.20 : ME on going 24.08.20 : curingtime 18.08.20 : Plan Pouring Today 13.08.20 : perapihan/pembersihan galian krn tanah longsor 10.08.20 : 06.08.20 : Rebaring OG, Plan Pouring 13/08 03.08.20 : Rebaring OG, Plan Pouring 10/08 23.07.20 : Design OG, Plan design released 24/07 20.07.20 : on going APD/design pack 16.07.20 : proses design pack/APD 13.07.20 : 09.07.20 : MOM : soiltest. plan APD selasa 14 jul, plan start CME 15 jul 06.07.20 : 02.07.20 : plan rekom selesai 10 jul, plan start CME 15 jul, plan RFI 12 aug 29.06.20 : on going rekom 25.06.20 : IW clear, plan realisasi besok sabtu 27 jun, tower SST 42m 22.06.20 : 18.06.20 : IW on going, IW OG kurang 1 kk, plan start CME end of June 15.06.20 : 11.06.20 : IW clear 08.06.20 : 04.06.20 : 01.06.20 : 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : IW on going 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : IW on going 25.03.20 : 19.03.20 : 12.03.20 : IW on going 20.02.20 : rehunting 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = RND OK 40
51 |  | JAW-BT-CPT-0468 | 30572480031 | 1317671003 | GN RAYA CIREUNDEU | ACTIVE | TB | 106.7654 | -6.3062 | 35 | 90/210/330 |  |  | Jl. Gunung Raya Indah IV, Rt.04/Rw.11, Kel. Cirendeu, Kec. Ciputat timur, Kota Tangerang Selatan | EID | JAW-BT-CPT-0468 | GN RAYA CIREUNDEU | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 253 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-30 | W36-2020 | Aug-2020 | 2020-09-15 | W38-2020 | Sep-2020 | 2020-09-15 | W38-2020 | Sep-2020 | MW | 2020-08-16 |  | 543602552495 | 6.6 |  |  |  |  | 2020-09-22 | W39-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 22.09.20 : RFIN sent 21.09.20 : 17.09.20 : RFI actual, collecting doc RFIN 14.09.20 : 07.09.20 : 03.09.20 : SRFI actual 31.08.20 : ME on going 27.08.20 : Plan Start Erection 27/08, Plan S RFI 30/08 24.08.20 : cor done 22 Aug, curingtime 18.08.20 : Galian pondasi OG, Plan pouring 20/08 13.08.20 : Galian pondasi OG, Plan pouring 15/08 10.08.20 : Plan Realisasi 12/08 06.08.20 : Realisasi OG, REKOM plan done 11/08 03.08.20 : 30.07.20 : IW Clear, OG Collecting doc. SITAC 23.07.20 : OG IW 12kk, sudah tanda tangan 09kk, plan clear 26/07 20.07.20 : Og Re IW Kandidat A, sudah bisa diajak komunikasi 16.07.20 : 13.07.20 : 09.07.20 : MOM : target IW clear minggu ini 06.07.20 : 02.07.20 : 02.07.20 : IW minus 1 kk, plan IW clear 4 jul, plan start CME paling lambat weekly meeting minggu depan 9 juli, plan SRFI 5 Aug 20. 29.06.20 : 25.06.20 : IW on going, kurang 3kk dari 7 kk, MCP 25m, , plan IW clear paling lambat Senin 29 Juni or drop by XL 22.06.20 : 18.06.20 : IW on going, Plan start CME Jun 2020 15.06.20 : 11.06.20 : Proses kerjasama corporate 08.06.20 : rehunting 04.06.20 : 01.06.20 : IW on going, paralel rehunting kand alternatif dengan plan submit kandidat 4 jun 28.05.20 : 25.05.20 : 15.05.20 : IW on going 14.05.20 : 08.05.20 : rehunting 30.04.20 : rehunting 23.04.20 : 16.04.20 : rehunting 09.04.20 : 02.04.20 : 25.03.20 : rehunting 19.03.20 : 19.03.20 : Rehunting 11.03.20 : 20.02.20 : rehunting, makesure regulasi tangsel 06.02.20 : Hunting kandidat
59 |  | JAW-JK-KYB-0098 | 30571770031 | 1127621003 | JALAN PEMUDA CIPEDAK | ACTIVE | TB | 106.8122 | -6.3595 | 30 | 0/90/200/270 |  |  | Kp. Cipedak No.8, RT.08 RW.09, Kel. Srengseng Sawah, Kec. Jagakarsa, Jakarta Selatan | EID | JAW-JK-KYB-0098 | Jalan Pemuda Cipedak | B2S | TBG | JABO | JABODETABEK (INNER) | DKI Jakarta | JAKARTA SELATAN | 6614368 | 2020-01-13 |  | 247 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-09-15 | W38-2020 | Sep-2020 | 2020-09-15 | W38-2020 | Sep-2020 | MW | 2020-08-30 |  | 547401761272 | 6.6 |  |  |  | 2020-07-22 | 2020-09-16 | W38-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 17.09.20 : 16.09.20 : RFIN sent 14.09.20 : 11.09.20 : RFI actual 07.09.20 : 03.09.20 : 31.08.20 : 27.08.20 : 24.08.20 : Proses PLN connection terkendala Comcase, plan solve akhir bulan Aug, rev plan RFI W1 Sep (5 sept) 17.08.20 : 13.08.20 : 10.08.20 : revisi plan RFI 19 Aug 06.08.20 : 23.07.20 : 22.07.20 : email SRFI-N sent 20.07.20 : ME on going 16.07.20 : 13.07.20 : 09.07.20 : erection on going 06.07.20 : On Going Excavation 02.07.20 : rekom process, plan start CME 8 juli, plan SRFI 31 jul 20 29.06.20 : IW clear 25.06.20 : IW kurang 2 kk, pole MCP 20m 22.06.20 : 18.06.20 : IW on going, plan RFC end of June 15.06.20 : 11.06.20 : IW clear 08.06.20 : IW on going 04.06.20 : 01.06.20 : kand approved, IW on going 28.05.20 : 25.05.20 : 21.05.20 : 20.05.20 : RND OK, TNP review 15.05.20 : RND review 13.05.20 : submit kand C 08.05.20 : 30.04.20 : Negosiasi BAN 23.04.20 : 16.04.20 : IW OG, Terbatasnya komunikasi dengan perangkat kelurahan karena WFH 09.04.20 : Lahan private, waiting approval BAN, IW og 02.04.20 : 25.03.20 : validasi done kand B, IW OG 19.03.20 : rehunting kand B 20.02.20 : IW on going 20.02.20 : IW on going 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
14 |  | JAW-BT-TGR-0041 | 30573470031 | 1317851003 | BELIMBING KOSAMBI | ACTIVE | TB | 106.6776 | -6.0827 | 50 | 90/210/330 |  |  | Kp. Belimbing RT 023 RW 012, Desa Belimbing, Kec. Kosambi, Kab. Tangerang, Prov. Banten | EID | JAW-BT-TGR-0041 | BELIMBING KOSAMBI | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 254 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-09-24 | W39-2020 | Sep-2020 | 2020-09-24 | W39-2020 | Sep-2020 | 2020-09-24 | W39-2020 | Sep-2020 | MW | 2020-08-10 |  | 566601655232 | 6.6 |  |  |  |  | 2020-09-23 | W39-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 23.09.20 : RFIN sent 21.09.20 : on going ME installation 17.09.20 : Curing Time Starcking BTS, Plan S RFI 24/09/09 14.09.20 : 10.09.20 : ME on going 07.09.20 : 07.09.20 : erection og 03.09.20 : curingtime, cor done 31 aug 31.08.20 : Pengecoran pondasi sumuran done 27.08.20 : OG pembesian sumuran, Plan Pouring sumuran 28/08 24.08.20 : 18.08.20 : Galian pondasi sumuran, plan pouring pndasi sumuran 28/08 13.08.20 : Revisi design Done, Plan Mobilisasi team 14/08 10.08.20 : start excavation 06.08.20 : redesign pondasi, Plan start CME 09/08 03.08.20 : Plan start galian 05/08 23.07.20 : Design OG, Plan design released 24/07 20.07.20 : on going APD/design pack 16.07.20 : Proses APD 13.07.20 : 09.07.20 : MOM : IW clear plan soiltest 15 jul, realisasi IW akhir minggu ini 06.07.20 : 02.07.20 : plan iW done minggu ini, plan soiltest 7 juli, plan design done 10 juli, plan start CME 13 juli, plan SRFI 8 Aug 29.06.20 : 25.06.20 : kandidat approved, IW on going, plan IW clear minggu ini (kurang 4 kk dari 28kk) 22.06.20 : 18.06.20 : 15.06.20 : 11.06.20 : IW on going 08.06.20 : 04.06.20 : 01.06.20 : IW on going, proses negosiasi harga 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : Proses BAN terkendala LL tidak mau ditemui karena COVID 23.04.20 : 16.04.20 : IW OG, Terbatasnya komunikasi untuk melakukan Soswar 09.04.20 : 02.04.20 : 25.03.20 : 19.03.20 : 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = RND OK 40 16.01.20 : Proses input STIP 1 B2S 15.01.20 : propose change to colo (email Rudi), konfirmasi NOK dari XL (Pak Siro)
84 |  | JAW-BT-TNG-1450 | 30571990031 | 1317381003 | KEDAUNG BARU TANGERANG | ACTIVE | TB | 106.615 | -6.1324 | 40 | 60/130/200/320 |  |  | Kp. Pulo Indah, RT 06, RW 01, Desa Kedaung Barat, Kecamatan Sepatan Timur, Kabupaten Tangerang, Provinsi Banten | EID | JAW-BT-TNG-1450 | Kedaung Baru Tangerang | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 261 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-09-18 | W38-2020 | Sep-2020 | 2020-09-29 | W40-2020 | Sep-2020 | 2020-09-29 | W40-2020 | Sep-2020 | MW | 2020-08-16 |  | 566601657125 | 6.6 |  |  |  | 2020-09-30 | 2020-09-30 | W40-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 30.09.20 : RFIN sent 28.09.20 : 24.09.20 : ME Installation OG 21.09.20 : erection on going 18.09.20 : start erection 17.09.20 : Rebaring OG, Plan Pouring 14/09 14.09.20 : cor done hari ini, curingtime 10.09.20 : Rebaring OG, Plan Pouring 14/09 07.09.20 : 03.09.20 : Galian Pondasi OG, Plan Finish 04/08, Plan Pouring 06/09, Erection start 12/09 finish 18/09, Plan S RFI 21/09 31.08.20 : 27.08.20 : Galian Pondasi OG, Plan Finish 30/08, Plan Pouring 03/09, Erection start 08/09 finish 15/09, Plan S RFI 18/09 24.08.20 : 17.08.20 : bouwplang, Plan Start CME 22/08 13.08.20 : bouwplang, Plan Start CME 15/08 10.08.20 : 06.08.20 : OG REKOM KKOP, Plan REKOM KKOP released 12/08 03.08.20 : 30.07.20 : OG REKOM KKOP 23.07.20 : OG Realisasi IW, Plan REKOM LURCAM done 29/07 20.07.20 : OG Collect dokumen SITAC 16.07.20 : 13.07.20 : IW OG, terkendala provokasi ORMAS luar radius 09.07.20 : MOM : IW on going, kurang 4 kk yang terprovokasi ormas 06.07.20 : 02.07.20 : plan IW done 7 juli, plan rekom 10 juli, plan start CME 15 jul, plan SRFI 10 Aug 29.06.20 : 25.06.20 : IW kurang 4 kk, plan IW clear minggu ini, tidak ada isu ketinggian 25.06.20 : kandidat D approved by RND, RF height 40m OK , Plan IW Done Jun 2020 22.06.20 : 18.06.20 : area tangkot, outcell dan depan landasan bandara, max tower heigh 20m (sesuai Perda, max diusahakan 25m), req XL 35 m. Akan di xcheck kembali hari ini. Revisi email Propose tinggi tower (not MCP 20), continue site dengan tinggi tower sesuai propose XL 35/40m 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20, sudah ada kandidat (plan re-IW) 08.06.20 : 04.06.20 : 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : Rehunting OG 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : IW on going 25.03.20 : 19.03.20 : IW on going 12.03.20 : waiting RND validation 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
62 |  | JAW-BT-TGR-0028 | 30572320031 | 1317581003 | JALAN RAYA KORELET | ACTIVE | TB | 106.5408 | -6.2888 | 40 | 70/140/240/340 |  |  | Kp. Serdang Rt.008 Rw.004 Ds. Serdang Kulon Kec. Panongan Kab. Tangerang | EID | JAW-BT-TGR-0028 | Jalan Raya Korelet | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 380 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2021-01-27 | W05-2021 | Jan-2021 | FO | 2020-12-01 |  | 566401713414 | 6.6 |  |  |  | 2020-09-03 | 2021-01-27 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.01.21 : PLN connected, prepare RFIN 21.01.21 : 18.01.21 : perluasan jaringan og penarikan kabel dan penambahan tiang 28.12.20 : 21.12.20 : 07.12.20 : PLN connection process 14.09.20 : 07.09.20 : 03.09.20 : SRFI actual, SRFIN sent 31.08.20 : 27.08.20 :24.08.20 : 17.08.20 : SRFI actual, collecting doc SRFIN 13.08.20 : ME Installation OG, Plan S RFI 16/08 10.08.20 : Erection tower OG, Plan Finish 15/08, Plan S RFI 20/08 06.08.20 : curingtime, plan start erection 7 Aug 20 03.08.20 : curingtime 30.07.20 : Pengecoran Pondasi Tower 27.07.20 : 23.07.20 : Rebaring OG, Plan Pouring 27/07 20.07.20 : 16.07.20 : rebarring 13.07.20 : 09.07.20 : excavation 06.07.20 : 02.07.20 : on going rekom, paralel soiltest, plan APD done 7 juli, plan start CME 9 juli, plan SRFI 8 Aug 20 29.06.20 : on going rekom 25.06.20 : IW clear, realisasi IW done hari ini, plan rekom l/c besok jumat, plan start CME minggu depan 22.06.20 : 18.06.20 : IW on going, Plan IW Done Jun 2020 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20, sudah ada kandidat (plan re-IW) 08.06.20 : 04.06.20 : 01.06.20 : IW clear, negosiasi harga 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : Rehunting OG 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : 25.03.20 : 19.03.20 : 11.03.20 : 20.02.20 : 13.02.20 : IW on going 06.02.20 : Kand A, B = validasi done RF TX OK 24.01.20 : kand A = RND A OK 40 Prio 1 B OK 40 Prio 2
64 |  | JAW-JB-CBI-0063 | 30572230031 | 1260941003 | JALAN RAYA PUSPITEK | ACTIVE | TB | 106.6817 | -6.3703 | 50 | 40/130/210/275 |  |  | Kp. Jeletreng RT. 05 RW 04 Desa Pengasinan Kecamatan Gunung Sindur Kab. Bogor - Jawa Barat | EID | JAW-JB-CBI-0063 | Jalan Raya Puspitek | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614368 | 2020-01-13 |  | 379 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-06-23 | W26-2020 | Jun-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2021-01-25 | W05-2021 | Jan-2021 | FO | 2020-12-01 |  | 538733551408 | 6.6 |  |  |  | 2020-06-23 | 2021-01-26 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.01.21 : PLN connected, prepare RFIN 18.01.21 : perluasan jaringan og penarikan kabel dan penambahan tiang 28.12.20 : 21.12.20 : 07.12.20 : PLN connection process 06.08.20 : 23.07.20 : 20.07.20 : 09.07.20 : 06.07.20 : 02.07.20 : 29.06.20 : 23.06.20 : email SRFI-N sent, PLN connection menunggu konfirmasi XL/Tech partner 18.06.20 : 11.06.20 : SRFI, collecting doc SRFIN 08.06.20 : ME on going 04.06.20 : erection on going 01.06.20 : 29.05.20 : erection 28.05.20 : 25.05.20 : curingtime 14.05.20 : 08.05.20 : borepile OG, Plan Borepile done 10/05, Pouring 15/05, Erection Start 18/05 Finish 23/05 30.04.20 : preparation start CME 23.04.20 : 16.04.20 : OG proses ijin lingkungan untuk start CME 09.04.20 : RFC DONE, CME START terkendala issue COVID 02.04.20 : APD design 25.03.20 : rekom process 19.03.20 : IW clear 20.02.20 : IW on going 13.02.20 : Kand C = Rehunting 06.02.20 : Kand B = Candidate B Submit 24.01.20 : kand A = RND OK 40
200 |  | JAW-BT-CPT-0460 | 30572410031 | 1317601003 | VILLA MELATI MAS RAYA | ACTIVE | TB | 106.6651 | -6.2582 | 35 | 70/140/240/340 |  |  | Jl Jati, RT 12 RW 08 Kel. Pondok Jagung, Kec. Serpong Utara, Kota Tangerang Selatan | EID | JAW-BT-CPT-0460 | VILLA MELATI MAS RAYA | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 379 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-08 | W32-2020 | Aug-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2021-01-18 | W04-2021 | Jan-2021 | FO | 2020-12-01 |  | 566201562878 | 6.6 |  |  |  | 2020-09-03 | 2021-01-26 | W05-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 18.01.21 : PLN connected, minus RFIN 28.12.20 : 21.12.20 : 07.12.20 : PLN connection process 03.09.20 : SRFIN sent 06.08.20 : 03.08.20 : SRFI actual 30.07.20 : ME on going 27.07.20 : on going erection 23.07.20 : Erection Start 24/07, Finish 26/07 20.07.20 : 16.07.20 : rebarring 13.07.20 : 09.07.20 : excavation 02.07.20 : rekom done, plan SRFI W1 Aug (8 Aug 20) 29.06.20 : 25.06.20 : rekom done, MCP 25m, plan start CME minggu depan menunggu green light dari perijinan (PUPR), sudah register dan submit berkas ke KOMINFO, plan rekom KOMINFO release senin 29/selasa 30 jun 22.06.20 : 18.06.20 : on going rekom process, plan start CME minggu depan 15.06.20 : IW done, proses rekom 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : IW on going 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : 30.04.20 : IW on going 23.04.20 : TNP review 16.04.20 : under review RND 09.04.20 : review RND 08.04.20 : submit kand 02.04.20 : 25.03.20 : rehunting 19.03.20 : rehunting 11.03.20 : 20.02.20 : rehunting, makesure regulasi tangsel 06.02.20 : Hunting kandidat
44 |  | JAW-BT-CPT-0474 | 30572140031 | 1317471003 | ELANG SAWAH | ACTIVE | TB | 106.7371 | -6.3009 | 35 | 30/150/220/340 |  |  | Jalan Ki Hajar dewantara,Rt.04/Rw.11,Komplek DEPKES,Keluarahan Sawah,Kecamatan Ciputat | EID | JAW-BT-CPT-0474 | Elang Sawah | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 350 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-15 | W33-2020 | Aug-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 543602595959 | 6.6 |  |  |  | 2020-09-03 | 2020-12-28 | W53-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.12.20 : 21.12.20 : 07.12.20 : PLN connection process 03.09.20 : SRFIN sent 31.08.20 : 27.08.20 : SRFI actual, PLN connection waing confirmation XL 24.08.20 : 18.08.20 : ME Installation OG 13.08.20 : Erection Tower OG, Plan Finish 15/08 10.08.20 : Erection Tower OG 06.08.20 : curingtime, plan start erection 8 Aug 20 03.08.20 : curingtime 30.07.20 : Rebaring Pondasi, Plan Pouring 01/08 23.07.20 : 20.07.20 : 16.07.20 : rebarring 13.07.20 : 09.07.20 : excavation 02.07.20 : plan rekom done, 6 juli, plan start CME 9 juli, plan SRFI 5 Aug 29.06.20 : on going rekom 25.06.20 : realisasi IW, submit berkas IW dan proses rekom, paralel register perijinan, plan start CME minggu depan 3 juli 20 22.06.20 : 18.06.20 : IW on going, plan IW clear minggu ini, propose RND 25m, Perda 20m dan diusahakan 25m 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20, sudah ada kandidat (plan re-IW) 08.06.20 : rehunting 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review 28.05.20 : 25.05.20 : 15.05.20 : IW on going 14.05.20 : 08.05.20 : rehunting 30.04.20 : Rehunting OG 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : validasi RND 12.03.20 : rehunting 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK 20.01.20 : Kand A = Titik OK, Ketinggian NOK, sesuai arahan RND XL minimal Ketinggian RF 25m 16.01.20 : Kand A = submit kand A (136m, Propose MCP 20m) di 106°44'10.43"E // 106.736230° 6°17'59.50"S // -6.299860°
73 |  | JAW-BT-TNG-1492 | 20201103281 | 1317351003 | Karang Timur Tangerang | ACTIVE | TB | 106.7172 | -6.2213 | 40 | 0/90/180/270 |  |  | Jl. H. Mean V, RT.004, RW.010, Kelurahan Karang Timur, Kecamatan Karang Tengah, Kota Tangerang, Provinsi Banten | EID | JAW-BT-TNG-1492 | Karang Timur Tangerang | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 345 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-09-28 | W40-2020 | Sep-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 543802945748 | 6.6 |  |  |  | 2020-09-30 | 2020-12-23 | W52-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 28.12.20 : RFIN sent 21.12.20 : 07.12.20 : PLN connection process 30.09.20 : email SRFI-N sent 28.09.20 : 24.09.20 : Finishing ME, on going Pagar & halaman 21.09.20 : on going ME installation 17.09.20 : Plan finish 21/09, Plan S RFI 24/09 14.09.20 : start erection 10.09.20 : Curing Time, Erection start 15/09 finish 21/09, Plan S RFI 24/09 07.09.20 : rebaring pondasi, cor sumuran done 03.09.20 : Galian Pondasi Done, Rebaring Sumuran OG, Plan Pouring 05/09, Erection start 10/09 finish 17/09, Plan S RFI 20/09 31.08.20 : 27.08.20 : Galian Pondasi sumuran OG, Plan Finish 30/08, Plan Pouring 03/09, Erection start 08/09 finish 15/09, Plan S RFI 18/09 24.08.20 : 24.08.20 : 17.08.20 : 13.08.20 : bongkar existing 10.08.20 : 06.08.20 : Proses pengajuan perijinan PUPR, CME Stop perijinan, Perijinan released 13/08 03.08.20 : Proses pengajuan perijinan PUPR, CME Stop 30.07.20 : 23.07.20 : CME (rebarring) Stop, Proses pengajuan perijinan PUPR 20.07.20 : 16.07.20 : rebarring 13.07.20 : 09.07.20 : excavation 06.07.20 : rekom process 02.07.20 : proses review legal dan ada ahli waris yang diluar kota, plan minggu ini clear dan start rekom, plan CME start 12juli, plan SRFI 7 Aug 29.06.20 : IW clear 25.06.20 : IW kurang 3 kk dari 11 kk, SST 42m (Incell) 22.06.20 : 18.06.20 : kand tower 20m not OK, konfirmasi bisa/tidak plan 25m max akhir Juni (Confirm by RND OK), jika gagal 25m maka risk return 15.06.20 : 11.06.20 : IW clear 08.06.20 : 04.06.20 : 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : IW on going 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : 25.03.20 : Proses IW 2kk, Tanah Kosong 19.03.20 : IW on going 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
16 |  | JAW-BT-CPT-0465 | 20201103441 | 1317651003 | BERANDA SERPONG | ACTIVE | TB | 106.7072 | -6.317 | 35 | 90/210/330 |  |  | jl.raya serua,RT.04/Rw.04,kelurahan serua,kecamatan ciputat,kota tangerang selatan,provinsi banten | EID | JAW-BT-CPT-0465 | BERANDA SERPONG | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 340 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-31 | W36-2020 | Aug-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 543602592363 | 6.6 |  |  |  | 2020-09-03 | 2020-12-18 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 07.12.20 : PLN connection process 14.09.20 : 07.09.20 : 03.09.20 : SRFI actual, SRFIN sent 31.08.20 : erection done, on going install mounting dan bracket 27.08.20 : Plan Start Erection 29/08, Plan S RFI 31/08 24.08.20 : rebarring on going 18.08.20 : Galian pondasi OG, Plan pouring 20/08 13.08.20 : 10.08.20 : on going excavation 06.08.20 : Plan Bowplank 06/08 30.07.20 : 27.07.20 : 23.07.20 : REKOM Lurah done, OG REKOM Camat, plan release 24/07 20.07.20 : Iw clear, plan realisasi IW 18/07, REKOM LURCAM released 21/07 16.07.20 : IW clear, proses eskalasi sitac 13.07.20 : Proses pendekatan terhadap warga yang belum memberikan approval 09.07.20 : MOM : IW kurang 1 kk, warga sulit ditemui, plan selesai minggu ini, plan IW clear minggu ini 06.07.20 : 02.07.20 : IW on going kurang 1 kk, plan IW clear minggu ini, plan rekom minggu depan, plan start CME akhir minggu depan 12 jul 20, plan SRFI 7 aug 20 29.06.20 : 25.06.20 : validasi RNP kandidat B OK , ketinggian 25m, Plan IW Done Jun 2020, plan IW clear paling lambat senin 29 jun, ada tambahan IW 6 kk karena penambahan tinggi pole dari 20m menjadi 25 m, XL meminta sketsa layout penambahan IW tersebut 22.06.20 : 18.06.20 : propose RND 25m, perda 20, sedang di updayakan nego ketinggian 15.06.20 : 11.06.20 : IW clear 08.06.20 : 04.06.20 : IW on going 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : IW on going 23.04.20 : TNP review 16.04.20 : under review RND, terbatasnya komunikasi dengan PIC developer dikarenakan WFH 09.04.20 : 02.04.20 : under review RND 31.03.20 : submit kand 25.03.20 : rehunting 19.03.20 : 19.03.20 : Rehunting 11.03.20 : 20.02.20 : rehunrting, makesure regulasi tangsel 06.02.20 : Hunting kandidat
25 |  | JAW-BT-CPT-0451 | 30573420031 | 1317831003 | CIATER SERPONG | ACTIVE | TB | 106.6963 | -6.3214 | 35 | 0/90/180/270 |  |  | Jl. Ciateer Tengah RT 009/007 Kel Ciater Kec Serpong Kota Tangerang Selatan BANTEN | EID | JAW-BT-CPT-0451 | Ciater Serpong | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 340 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 543602593324 | 6.6 |  |  |  | 2020-08-25 | 2020-12-18 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 07.12.20 : PLN connection process 25.08.20 : SRFIN sent 06.08.20 : 03.08.20 : SRFI actual 30.07.20 : Erection tower, Plan Finish 30/07 27.07.20 : 23.07.20 : 20.07.20 : 16.07.20 : excavation 13.07.20 : 09.07.20 : MOM : isu kompensasi warga luar radius, tangsel 25m OK, plan solve sabtu ini pertemuan dengan warga luar radius yang menolak. wait isu clear untuk start CME. 06.07.20 : 02.07.20 : IW clear, wait approval PEMDA untuk Tinggi 25m (area Tangsel), target solve dengan Pemda minggu depan, plan CME start paling lambat 9 jul 20/weekly minggu depan, plan SRFI W1 Aug (8 Aug 20) 29.06.20 : 25.06.20 : existing pole TBG 18m, maximal diusahakan 21m plan submit foto panoramic by drone, need segera email JR ke XL mengenai isu ketinggian kandidat ini, jika pproved need revisi SPK menjadi SPK colo. 22.06.20 : Kand OK propose RND di 25 m (req 27-30m), need Negosiasi ke PEMDA Tinggi 25m, TBG ok di 21m IW clear 18.06.20 : Kand OK propose RND di 25 m (req 27-30m), need Negosiasi ke PEMDA Tinggi 25m, TBG ok di 21m IW clear 15.06.20 : 11.06.20 : IW clear 08.06.20 : 04.06.20 : IW clear, proses eskalasi, paralel rekom 01.06.20 : IW clear, proses eskalasi 28.05.20 : 25.05.20 : 22.05.20 : TNP review 21.05.20 : 20.05.20 : need cek koordinat, beda DMS dg desimal 13.05.20 : submit kand D 08.05.20 : 30.04.20 : IW clear 23.04.20 : TNP review 16.04.20 : Negosiasi BAN, IW CLear 09.04.20 : 02.04.20 : under review RND 31.03.20 : submit kand 25.03.20 : rehunting 19.03.20 : rehunting 11.03.20 : 20.02.20 : rehunting, makesure regulasi tangsel 06.02.20 : Hunting kandidat 16.01.20 : Proses input STIP 1 B2S 15.01.20 : propose change to colo (email Rudi), konfirmasi NOK dari XL (Pak Siro)
38 |  | JAW-BT-CPT-0469 | 30572490031 | 1317681003 | DISCOVERY CONSERVA | ACTIVE | TB | 106.6973 | -6.2617 | 35 | 90/210/330 |  |  | KP PONDOK KACANG,RT02/RW07,KEL,PONDOK KACANG TIMUR,KEC.PONDOK AREN,TANGERANG SELATAN,PROVINSI BANTEN | EID | JAW-BT-CPT-0469 | DISCOVERY CONSERVA | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 340 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-28 | W35-2020 | Aug-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 543802946645 | 6.6 |  |  |  | 2020-09-03 | 2020-12-18 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 07.12.20 : PLN connection process 14.09.20 : 07.09.20 : 03.09.20 : SRFI actual, SRFIN sent 31.08.20 : 27.08.20 : Plan ME Finsih 27/08, Plan S RFI 28/08 18.08.20 : Plan Erection start 22/08 13.08.20 : excavation on going 10.08.20 : bouwplank 06.08.20 : Plan Bowplank 06/08 30.07.20 : rekom process 23.07.20 : 20.07.20 : OG Collect dokumen SITAC 16.07.20 : IW clear, proses eskalasi sitac 13.07.20 : Masih terkendala 2kk yang belum setuju 09.07.20 : MoM : plan IW clear minggu ini 06.07.20 : 02.07.20 : plan IW done 5 jul, plan start CME 13 jul, plan SRFI 7 aug 29.06.20 : 25.06.20 : IW on going, kurang 2kk, MCP 25m, , plan IW clear paling lambat Senin 29 Juni or drop by XL 25.06.20 : Plan IW Done Jun 2020 22.06.20 : 18.06.20 : IW on going, Plan IW Done Jun 2020 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20,, sudah ada kandidat (plan re-IW) 08.06.20 : 04.06.20 : 01.06.20 : IW on going, paralel validasi new kand alternatif 28.05.20 : 25.05.20 : 08.05.20 : 30.04.20 : IW on going 23.04.20 : TNP review 16.04.20 : under review RND 09.04.20 : review RND 08.04.20 : submit kand 02.04.20 : 25.03.20 : rehunting 19.03.20 : 19.03.20 : Rehunting 11.03.20 : 20.02.20 : rehunting, makesure regulasi tangsel 06.02.20 : Hunting kandidat
39 |  | JAW-BT-CPT-0473 | 30572130031 | 1317461003 | DJUNA RAYA PAKUJAYA | ACTIVE | TB | 106.6911 | -6.2298 | 35 | 90/180/270 |  |  | Kp. Kayu Gede Rt 008 RW 04 Kelurahan Pakujaya Kecamatan Serpong Utara Kota Tangerang Selatan | EID | JAW-BT-CPT-0473 | Djuna Raya Pakujaya | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 340 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-05 | W32-2020 | Aug-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 566201558459 | 6.6 |  |  |  |  | 2020-12-18 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 07.12.20 : PLN connection process 25.08.20 : SRFIN sent 06.08.20 : 03.08.20 : SRFI actual 30.07.20 : Erection tower, Plan Finish 30/07 23.07.20 : 20.07.20 : 16.07.20 : rebarring 13.07.20 : 09.07.20 : excavation 02.07.20 : rekom process, plan rekom done 7 jul, plan start CME 9 jul, plan SRFI 5 aug 20 29.06.20 : IW clear 25.06.20 : IW on going, kurang 3kk dari 15kk, MCP 25m, , plan IW clear paling lambat Senin 29 Juni or drop by XL 25.06.20 : Plan IW Done Jun 2020 22.06.20 : 18.06.20 : kand approved, IW on going, Plan IW Done Jun 2020 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20, sudah ada kandidat (plan re-IW) 08.06.20 : 04.06.20 : 01.06.20 : IW on going 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : IW on going 23.04.20 : TNP review 16.04.20 : under review RND 09.04.20 : review RND 08.04.20 : submit kand 02.04.20 : 25.03.20 : rehunting 19.03.20 : 19.03.20 : Rehunting 11.03.20 : 20.02.20 : rehunting, makesure regulasi tangsel 06.02.20 : Hunting kandidat
95 |  | JAW-BT-CPT-0461 | 20201103421 | 1317611003 | KOMPLEKS SASMITA LOKA PAMULANG BARAT | ACTIVE | TB | 106.7326 | -6.3527 | 35 | 90/210/330 |  |  | Jl. Ketapang II Rt 007/005 Kel. Pamulang Barat Kec. Pamulang Kota Tangerang Selatan | EID | JAW-BT-CPT-0461 | KOMPLEKS SASMITA LOKA PAMULANG BARAT | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 340 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-02 | W27-2020 | Jul-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 543602591889 | 6.6 |  |  |  | 2020-07-02 | 2020-12-18 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 07.12.20 : PLN connection process 06.08.20 - 02.07.20 : email SRFI-N sent, PLN connection menunggu konfirmasi XL/Tech partner 29.06.20 : SRFI, collecting doc SRFIN 25.06.20 : 22.06.20 : ME on going 18.06.20 : 15.06.20 : prepare erection 11.06.20 : 08.06.20 : curing time 04.06.20 : start excavation 01.06.20 : 29.05.20 : RFC, plan start minggu 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : rekom on going 30.04.20 : IW clear 23.04.20 : 16.04.20 : IW on going, Proses negosiasi BAN 09.04.20 : 02.04.20 : under review RND 31.03.20 : submit kand 25.03.20 : rehunting 19.03.20 : Rehunting 11.03.20 : 20.02.20 : rehunting, makesure regulasi tangsel 06.02.20 : Hunting kandidat
128 |  | JAW-JB-CBI-0066 | 30572070031 | 1260891003 | PASIRMUKTI CITEUREUP | ACTIVE | TB | 106.8993 | -6.5056 | 31 | 30/180/270 |  |  | KP. RAWABOGO, RT. 004 RW. 006, DESA, PASIRMUKTI, KECAMATAN. CITEUREUP, KAB. BOGOR, JAWA BARAT | EID | JAW-JB-CBI-0066 | Pasirmukti Citeureup | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614368 | 2020-01-13 |  | 340 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-12 | W20-2020 | May-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 538614708734 | 6.6 |  |  |  | 2020-05-06 | 2020-12-18 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 07.12.20 : PLN connection process 29.06.20 : PLN Connection menunggu konfirmasi XL 06.05.20 : SRFIN sent 30.04.20 : Lean concrete, Plan Pouring 23.04.20 : 16.04.20 : on going excavation 09.04.20 : Galian pondasi OG 02.04.20 : 25.03.20 : 19.03.20 : rekom l/c on going 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : Kand B = RF OK, TX review 28.01.20 : Kand B = RND OK 40 80/180/270 tower 42m, wait TNP review 28.01.20 : Kand B = submit 106°53'59.34"E 6°30'20.20"S 20.01.20 : Kand A = RND OK 40m 80/180/270 --> CEK krn proposes hanya tower 32m 16.01.20 : Kand A = submit kand A (84m) di 106°53'58.95"E // 106.899708° 6°30'21.52"S // -6.505978°, Propose 32m
163 |  | JAW-BT-CPT-0467 | 20201103451 | 1317661003 | SITU GINTUNG CIREUNDEU | ACTIVE | TB | 106.763 | -6.3003 | 35 | 90/210/330 |  |  | Jl.IrH.juanda,Rt.01/Rw.08,kelurahan.Cirendeu,kecamatan.Ciputat Timur,kota tangerang selatan,Provinsi Banten | EID | JAW-BT-CPT-0467 | SITU GINTUNG CIREUNDEU | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 340 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-28 | W35-2020 | Aug-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 543602592355 | 6.6 |  |  |  | 2020-09-03 | 2020-12-18 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 07.12.20 : PLN connection process 14.09.20 : 07.09.20 : 03.09.20 : SRFI actual, SRFIN sent 31.08.20 : 27.08.20 : Plan erection done 27/08, Plan S RFI 28/08 24.08.20 : rebarring on going 17.08.20 : Galian pondasi OG, Plan pouring 20/08 13.08.20 : Galian pondasi OG, Plan pouring 14/08 10.08.20 : Plan Realisasi 12/08 06.08.20 : Realisasi OG, REKOM plan done 11/08 03.08.20 : 30.07.20 : IW Clear, OG Collecting doc. SITAC 23.07.20 : Proses IW, masih dikejar 1 kk Kepsek SMK Muhammadiyah, plan released surat kuasa penandatangan IW ke bagian Tata usaha 24/07 20.07.20 : Proses IW, masih dikejar 1 kk Kepsek SMK Muhammadiyah 16.07.20 : 13.07.20 : Proses IW, masih dikejar 1 kk Kepsek SMK Muhammadiyah 09.07.20 : MOM : 06.07.20 : 02.07.20 : IW minus 1 kk, plan IW clear 4 jul, plan start CME paling lambat weekly meeting minggu depan 9 juli, plan SRFI 5 Aug 20. 29.06.20 : 25.06.20 : IW minus 1 kk (area sekolah, IW dengan kepsek Muhammadiyah, proses negosiasi), plan IW clear paling lambat Senin 29 Juni or drop by XL 25.06.20 : submit kandidat D propose RT (building 12m + pole 12m) , validasi RNP approved RF 24m, 22.06.20 : 18.06.20 : 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20, sudah ada kandidat (plan re-IW) 08.06.20 : 04.06.20 : 01.06.20 : IW on going, paralel approval kand B 28.05.20 : 25.05.20 : 14.05.20 : IW on going 08.05.20 : TNP review 30.04.20 : RND review 23.04.20 : RND review 16.04.20 : under review RND, Proses negosiasi BAN 09.04.20 : 02.04.20 : under review RND 31.03.20 : submit kand 25.03.20 : Candidat NOK, Rehunting 19.03.20 : validasi RND 20.02.20 : rehunrting, makesure regulasi tangsel 06.02.20 : Hunting kandidat
199 |  | JAW-BT-CPT-0463 | 30572440031 | 1317631003 | UNIVERSITAS TERBUKA PAMULANG | ACTIVE | TB | 106.7594 | -6.3415 | 35 | 90/210/330 |  |  | JL.TALAS III NO.37,RT.03/RW.02,KEL.PONDOK CABE ILIR,KEC.PAMULANG,TANGERANG SELATAN,PROVINSI BANTEN | EID | JAW-BT-CPT-0463 | UNIVERSITAS TERBUKA PAMULANG | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | KOTA TANGERANG SELAT | 6614368 | 2020-01-13 |  | 340 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-09-15 | W38-2020 | Sep-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 543602591897 | 6.6 |  |  |  | 2020-09-03 | 2020-12-18 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 07.12.20 : PLN connection process 14.09.20 : 07.09.20 : 03.09.20 : SRFI actual, SRFIN sent 31.08.20 : start erection 27.08.20 : Plan Start Erection 29/08, Plan S RFI 31/08 24.08.20 : cor hari ini 17.08.20 : Galian Pondasi Pole, Plan Pouring 20/08 13.08.20 : Og pembongkaran bangunan existing 10.08.20 : 06.08.20 : Plan Start pembongkaran bangunan existing 08/08 03.08.20 : 30.07.20 : Plan Start CME 07/08 27.07.20 : preparation CME 23.07.20 : Plan Start CME 26/07 20.07.20 : 16.07.20 : RFC, proses perijinan 13.07.20 : rekom 09.07.20 : MOM : IW clear, collecting doc legal dan doc IW, plan sabtu realisasi, plan rekom minggu depan, plan CME start rabu minggu depan, plan SRFI juli 06.07.20 : 02.07.20 : IW clear, review PKS (isu 2 poin PKS) plan clear PKS minggu ini, plan rekom minggu depan, plan SRFI W2 Aug/15 Aug 20 29.06.20 : IW clear 25.06.20 : kandidat B approved by RND, IW Done Jun 2020, tetapi ada isu anak LL yang mempermasalahkan, TBG akan segera mengirimkan email pengajuan kandidat yang sudah di approved by meeting minggu lalu 22.06.20 : 18.06.20 : IW clear, proses PKS dengan kampus (butuh waktu), submit 2 kand MCP alternatif yang lebih cepat secara perijinan, propose RND 25-30m, akan diupayakan tinggi 25m (kand Ok) 15.06.20 : 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : 04.06.20 : Proses BAN terkendala karena pihak Universitas WFH dan ada staff yg positif COVID 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : 30.04.20 : 23.04.20 : 16.04.20 : Proses BAN terkendala karena pihak Universitas WFH dan ada staff yg positif COVID 09.04.20 : 02.04.20 : under review RND 31.03.20 : submit kand 25.03.20 : rehunting 19.03.20 : Rehunting 11.03.20 : 20.02.20 : rehunting, makesure regulasi tangsel 06.02.20 : Hunting kandidat
42 |  | JAW-BT-TGR-0023 | 30571910031 | 1317371003 | DUKUH CUKANGGALIH | ACTIVE | TB | 106.5416 | -6.2439 | 40 | 20/150/290 |  |  | Kp. Ranca Balok RT 08 RW 013 Desa Cukanggalih Kecamatan Curug Kabupaten Tangerang | EID | JAW-BT-TGR-0023 | Dukuh Cukanggalih | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 339 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-02 | W27-2020 | Jul-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 566201554597 | 6.6 |  |  |  | 2020-07-02 | 2020-12-17 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 21.12.20 : RFIN sent 07.12.20 : PLN connection process 06.08.20 : 23.07.20 : 20.07.20 : 16.07.20 : 09.07.20 : 06.07.20 : 02.07.20 : email SRFI-N sent, PLN connection menunggu konfirmasi XL/Tech partner 29.06.20 : ME on going 25.06.20 : curingtime, prepare erection 22.06.20 : cor done, curingtime & backfilling 18.06.20 : rebarring 11.06.20 : excavation 08.06.20 : site preparation, proses perijinan 04.06.20 : on going rekom 01.06.20 : plan rekom dane minggu depan 28.05.20 : 25.05.20 : rekom on going 14.05.20 : 08.05.20 : iw clear 30.04.20 : IW OG, Terbatasnya komunikasi untuk melakukan Soswar 23.04.20 : 16.04.20 : IW OG, Terbatasnya komunikasi untuk melakukan Soswar 09.04.20 : IW OG, Soswar masih terkendala COVID 02.04.20 : 25.03.20 : IW on going 19.03.20 : validasi RND 11.03.20 : 20.02.20 : 13.02.20 : IW on going 06.02.20 : Kand A, B = validasi done RF TX OK 24.01.20 : kand A = RND A OK 40 Prio 1 B OK 40 Prio 2
132 |  | JAW-JB-CBI-0082 | 30572360031 | 1260951003 | PENGASINAN GUNUNG SINDUR | ACTIVE | TB | 106.6928 | -6.3768 | 50 | 60/140/230/320 |  |  | Kp Kebon Kopi RT. 05 RW. 06 Desa Pengasinan Kec. Gunung Sindur, Kab. Bogor Jawa Barat | EID | JAW-JB-CBI-0082 | Pengasinan Gunung Sindur | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614368 | 2020-01-13 |  | 336 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-02 | W27-2020 | Jul-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 538733551416 | 6.6 |  |  |  | 2020-07-16 | 2020-12-14 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.12.20 : RFIN sent 07.12.20 : PLN connection process 06.08.20 : 23.07.20 : 20.07.20 : 16.07.20 : email SRFI-N sent 09.07.20 : 06.07.20 : 02.07.20 : SRFI, Optimis Sent SRFI Announce today, PLN connection menunggu konfirmasi XL/Tech partner 29.06.20 : ME on going 25.06.20 : curingtime, prepare erection 22.06.20 : 18.06.20 : curingtime, prepare start erection 15.06.20 : excavation on going 11.06.20 : excavation 08.06.20 : bouwplank 04.06.20 : preparation start CME 01.06.20 : RFC, plan start CME 5 jun 28.05.20 : 25.05.20 : 14.05.20 : soiltest 08.05.20 : rekom on going 30.04.20 : IW OG, Revisi pengajuan cost SITAC 23.04.20 : 16.04.20 : under review RND, IW clear 09.04.20 : review RND, iw clear 08.04.20 : submit kand 02.04.20 : 25.03.20 : 19.03.20 : IW on going 11.03.20 : 09.03.20 : IW CLear, Realisasi OG 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : Kand B = Candidate B Submit 24.01.20 : kand A = RND OK 40
145 |  | JAW-JB-CBI-0084 | 30572400031 | 1260961003 | SABILILAH CITEUREUP | ACTIVE | TB | 106.8916 | -6.4876 | 50 | 10/150/220 |  |  | Kp. Lemper Rt 002 Rw 006 Desa Citeureup Kecamtan Citeureup Kabupaten Bogor | EID | JAW-JB-CBI-0084 | Sabililah Citeureup | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614368 | 2020-01-13 |  | 336 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-28 | W35-2020 | Aug-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 538614708742 | 6.6 |  |  |  | 2020-09-03 | 2020-12-14 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.12.20 : RFIN sent 07.12.20 : PLN connection process 14.09.20 : 07.09.20 : 03.09.20 : SRFI actual, SRFIN sent 31.08.20 : SRFI actual 27.08.20 : ME on going, Plan S RFI 28/08 24.08.20 : 17.08.20 : ME Installation OG 13.08.20 : Erection Tower OG, Plan Finish 16/08, Plan S RFI 22/08 10.08.20 : pouring concrete done, Curing Time, Plan start Erection 13/08 06.08.20 : Rebaring OG, Plan Pouring 10/08 03.08.20 : Rebaring OG, Plan Pouring 10/08 30.07.20 : Galian pondasi done, Plan Pouring 10/08 23.07.20 : Plan Start CME 26/07 20.07.20 : on going APD/design pack 16.07.20 : proses design pack/APD 13.07.20 : 09.07.20 : MOM : soiltest, on going realisasi hari ini, plan start CME 16 jul 06.07.20 : 02.07.20 : plan rekom selesai 10 jul, plan start CME 15 jul, plan RFI 12 aug 29.06.20 : on going rekom 25.06.20 : IW clear, plan realisasi besok sabtu 27 jun, tower SST 42m 22.06.20 : 18.06.20 : Submit kand OK tinggi 40m, IW clear, proses eskalasi, plan realisasi IW minggu depan 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20 08.06.20 : 04.06.20 : 01.06.20 : 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : IW on going 23.04.20 : 16.04.20 : rehunting karena penolakan warga radius 09.04.20 : validasi done, IW on going 02.04.20 : under review RND 25.03.20 : plan soswar terkendala wabah corona 18.03.20 : Plan Soswar 18/03 19.03.20 : IW on going 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : Kand A, B = validasi done RF TX OK 20.01.20 : Kand A, B, Propose tower 42m = kand A OK 40 0/150/220 Prio 1, kand B OK 40 10/150/220 Prio 2 16.01.20 : Kand A, B, Propose tower 42m = submit kand A (136m) di 106°53'33.45"E // 106.892625° 6°29' 17.44"S // -6.488178° dan submit kand B (127m) 106°53'26.36"E // 106.890656° 6°29' 12.77"S // -6.486881°
162 |  | JAW-JB-CBI-0086 | 30572110031 | 1260921003 | SITU COGARONGSONG PENGASINAN | ACTIVE | TB | 106.6892 | -6.3598 | 50 | 0/140/220 |  |  | Kp Cibarengkok RT 05 RW 02 Desa Pengasinan Kecamatan GUnung Sindur Kabupaten Bogor | EID | JAW-JB-CBI-0086 | Situ Cogarongsong Pengasinan | B2S | TBG | JABO | JABODETABEK (OUTER) | Jawa Barat | BOGOR | 6614368 | 2020-01-13 |  | 336 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-02 | W27-2020 | Jul-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 538733551424 | 6.6 |  |  |  | 2020-07-15 | 2020-12-14 | W51-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 14.12.20 : RFIN sent 07.12.20 : PLN connection process 15.07.20 : SRFIN sent 02.07.20 : SRFI, Optimis Sent SRFI Announce today, PLN connection menunggu konfirmasi XL/Tech partner 29.06.20 : ME on going 25.06.20 : curingtime, prepare erection 22.06.20 : 18.06.20 : curingtime, prepare erection 15.06.20 : 11.06.20 : 08.06.20 : borepile on going 04.06.20 : excavation on going 01.06.20 : 29.05.20 : plan start galian besok 28.05.20 : 25.05.20 : 14.05.20 : 08.05.20 : rekom, RFC 30.04.20 : Soil test OG 23.04.20 : 16.04.20 : realisasi IW, start rekom process 09.04.20 : validasi done, IW clear 02.04.20 : under review RND 25.03.20 : 20.03.20 : IW OG, Minus 1 kk 19.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : Kand B = Candidate B Submit 24.01.20 : kand A = RND OK 40
2 |  | JAW-BT-TNG-1464 | 30572570031 | 1317761003 | ALAM JAYA JATIUWUNG | ACTIVE | TB | 106.578 | -6.1933 | 35 | 90/210/330 |  |  | KP.LEDUG,RT.03/RW.01,KELURAHAN.ALAM JAYA,KECAMATAN.JATIUWUNG,KOTA TANGGERANG,PROVINSI BANTEN | EID | JAW-BT-TNG-1464 | ALAM JAYA JATIUWUNG | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 332 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-10-01 | W40-2020 | Oct-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 566100948050 | 6.6 |  |  |  | 2020-10-05 | 2020-12-10 | W50-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.12.20 : RFIN sent 07.12.20 : PLN connection process 05.10.20 : SRFIN sent 01.10.20 : 30.09.20 : SRFI actual, plan email SRFIN 2 oct 28.09.20 : site continue, progress curingtime, plan SRFI 30 sep 14.09.20 : 03.09.20 : MOM : XL PROPOSE RETURN SPK 03.09.20 : 31.08.20 : 27.08.20 : bouwplank, start CME menunggu rekom PUPR release 24.08.20 : start CME menunggu rekom PUPR release 17.08.20 : 13.08.20 : MoM : Bouwplank 13.08.20 : Proses REKOM PUPR untuk Start CME 10.08.20 : 06.08.20 : MoM : plan start CME paling lamabat weekly minggu depan 13 Aug 20, Rekom Camat memerlukan rekomendasi dari REKOM PUPR 30.07.20 : 23.07.20 : 20.07.20 : OG Collect dokumen SITAC 16.07.20 : 13.07.20 : 09.07.20 : MOM : masih koordinasi dengan pemda utk 25m, tangkot, outcell, plan minggu depan diundang presentasi oleh pemda/PUPR, IW clear 06.07.20 : 02.07.20 : IW clear, proses pengajuan ke PEMDA Tinggi 25m (area Tangkot), target solve dengan Pemda minggu depan, plan CME start paling lambat 9 jul 20/weekly minggu depan, plan SRFI W1 Aug (8 Aug 20) 29.06.20 : 25.06.20 : Cand Approved, proses negosiasi ke PEMDA Tinggi 25m, paralel pengambilan foto panoramic by drone, paralel proses rekom. plan Start CME paling lambat senin 29 Jun 2020 22.06.20 : 18.06.20 : 15.06.20 : 11.06.20 : proses validasi, paralel IW clear 08.06.20 : RND review, site Alam Jawa Jatiuwung, berada di outcell. Maksimum yang dijinkan maksimal 20m. 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review 28.05.20 : 25.05.20 : 30.04.20 : Rehunting OG, propose return by XL krn durasi 108 hari (MoM 30 Apr 20) 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 25.03.20 : Candidat NOK, Rehunting 19.03.20 : IW on going 12.03.20 : rehunting 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
121 |  | JAW-BT-TNG-1452 | 30571830031 | 1317361003 | PANDAWA CIBODAS | ACTIVE | TB | 106.6041 | -6.1984 | 30 | 60/140/200/270 |  |  | JL.RAHWANA II UJUNG,RT.05/RW.02,KEL.CIBODAS BARU,KEC.CIBODAS,KOTA TANGGERANG | EID | JAW-BT-TNG-1452 | Pandawa Cibodas | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 332 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-10-01 | W40-2020 | Oct-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 566100948068 | 6.6 |  |  |  | 2020-10-05 | 2020-12-10 | W50-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.12.20 : RFIN sent 07.12.20 : PLN connection process 05.10.20 : SRFIN sent 01.10.20 : 30.09.20 : SRFI actual, plan email SRFIN 2 oct 28.09.20 : erection done, on going ME 24.09.20 : Curing Time, Plan Start Erection 25/09 21.09.20 : curingtime 20.09.20 : prouring concrete on going 17.09.20 : galian on going, Plan Pouring 19/09, Erection Pole 25/09, ME Finish 27/09, Plan S RFI 27/09 14.09.20 : CME Preparation, menunggu PUPR release 10.09.20 : 07.09.20 : 03.09.20 : MOM : start CME minggu depan, jika tidak akan di return 31.08.20 : 27.08.20 : bouwplank, start CME menunggu rekom PUPR release 24.08.20 : 17.08.20 : Proses REKOM Camat, REKOM Lurah done 12/08, Plan rekom Camat released 21/08 13.08.20 : MOM : SPK SUDAH RETURN 4 AUG 20, NEED AKTIVASI SPK, progress hari ini bouwplank 13.08.20 : 10.08.20 : 04.08.20 : email SPK return, Category Return ommunity Issue, Return By XL, Remark Mediasi pertama belum bisa dilaksanakan, karena warga 03.08.20 : OG Collection dokumen SITAC, Plan realisasi IW 12/08, REKOM LURCAM done 14/08 06.08.20 : mediasi done, collecting doc SITAC, plan realisasi 9 Aug 03.08.20 : 30.07.20 : Mediasi pertama belum bisa dilaksanakan, karena warga yang terkena provokasi tidak hadir semua, jadwal ulang pertemuan tgl 01/08 27.07.20 : 23.07.20 : 20.07.20 : Mediasi pertama belum bisa dilaksanakan, karena warga yang terkena provokasi tidak hadir semua, jadwal ulang pertemuan tgl 18/07 16.07.20 : 13.07.20 : 09.07.20 : MOM : proses realisasi terkendala provokasi warga luar radius, perlu extratime untuk penyelesainnya, plan start CME minggu depan 06.07.20 : 02.07.20 : IW clear, proses realisasi IW, plan SRFI W1 Aug (8 Aug 20) 29.06.20 : IW clear 25.06.20 : need konfirmasi request ketinggian min. 27 m, Plan IW Done Jun 2020 22.06.20 : 18.06.20 : IW on going, plan RFC end of June 15.06.20 : 11.06.20 : rehunting, plan IW done jun 20 08.06.20 : rehunting 04.06.20 : 01.06.20 : plan submit kand 2 jun 29.05.20 : plan submit kand 30 May 28.05.20 : 25.05.20 : 30.04.20 : Rehunting OG, propose return by XL krn durasi 108 hari (MoM 30 Apr 20) 23.04.20 : 16.04.20 : 09.04.20 : kand NOK 02.04.20 : 25.03.20 : rehunting 19.03.20 : Rehunting 12.03.20 : rehunting 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
52 |  | JAW-BT-TGR-0049 | 30572190031 | 1317511003 | GRIYA SUKATANI MEKARSARI | ACTIVE | TB | 106.5325 | -6.1272 | 50 | 60/150/290 |  |  | Kp.Pondok Cikurus RT.07/02, Desa Mekarsari, Kec. Rajeg Kabupaten Tangerang - Banten | EID | JAW-BT-TGR-0049 | Griya Sukatani Mekarsari | B2S | TBG | JABO | JABODETABEK (OUTER) | Banten | TANGERANG | 6614368 | 2020-01-13 |  | 329 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-07-31 | W31-2020 | Jul-2020 | 2020-12-23 | W52-2020 | Dec-2020 | 2020-12-23 | W52-2020 | Dec-2020 | FO | 2020-12-01 |  | 566601731346 | 6.6 |  |  |  | 2020-07-22 | 2020-12-07 | W50-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 10.12.20 : RFIN sent 06.08.20 : 27.07.20 : 23.07.20 : 22.07.20 : email SRFI-N sent 20.07.20 : SRFI actual, collecting doc 16.07.20 : ME on going 13.07.20 : 09.07.20 : erection on going 06.07.20 : on going rebarring 02.07.20 : galian done, prepare rebarring 29.06.20 : excavation on going 25.06.20 : RFC done, rekom done, plan start CME sabtu 27 jul, plan RFI jul 22.06.20 : on going rekom process 22.06.20 : 18.06.20 : on going rekom process, isu rekom terkendala surat cerai LL, plan start CME Juni (minggu depan) 15.06.20 : IW done, proses rekom 11.06.20 : IW clear, proses pengajuan eskalasi sitac, proses rekom 08.06.20 : IW clear, proses rekom 04.06.20 : 01.06.20 : comcase (1 warga narik IW) 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : Proses negosiasi ke lingkungan untuk realisasi IW 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : 25.03.20 : 19.03.20 : rekom l/c on going 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 24.01.20 : kand A = RND OK 40
103 |  | JAW-BT-TNG-1470 | 30572120031 | 1317451003 | MAWI KUNCIRAN INDAH | ACTIVE | TB | 106.6813 | -6.2279 | 35 | 20/90/180/280 |  |  | Jl.K.H.Mas Mansyur,Gang H Mawi,RT.05/RW.15,Kelurahan.kunciran indah,Kecamatan Pinang,Kota Tangerang,Provinsi Banten | EID | JAW-BT-TNG-1470 | Mawi Kunciran Indah | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 399 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-08-28 | W35-2020 | Aug-2020 | 2021-02-18 | W08-2021 | Feb-2021 | 2021-02-18 | W08-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2020-12-08 |  | 566201597566 | 6.6 |  |  |  | 2020-09-03 | 2021-02-15 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.02.21 : PLN connected, prepare RFIN 04.02.21 : PLN connection process 03.09.20 : SRFIN sent 31.08.20 : SRFI actual 27.08.20 : ME on going, Plan S RFI 28/08 24.08.20 : curingtime 17.08.20 : cor done, curing time, Plan start Erection 22/08 Finish 25/08, S RFI 28/08 13.08.20 : Rebaring pondasi, Plan Pouring 13/08 10.08.20 : start excavation 06.08.20 : Plan start CME 09/08 03.08.20 : 30.07.20 : Plan Start CME 03/08 23.07.20 : Plan Start CME 26/07 20.07.20 : 16.07.20 : RFC, proses perijinan 13.07.20 : rekom on going, Follow up dokumen pendukung legal tanah, Kuasa waris 09.07.20 : MOM : IW clear, isu PKS dg LL ada 2 pasal PKS yg blm clear, plan isu clear besok 06.07.20 : 02.07.20 : on going rekom, plan CME start 9 juli, plan SRFI 4 Aug 29.06.20 : on going rekom 25.06.20 : IW clear, besok realisasi, MCP 20m, plan rekom selesai senin/selasa 30 jun, plan start CME minggu depan 22.06.20 : 18.06.20 : IW clear 20m, RND OK 20m, plan start CME end of June 15.06.20 : 11.06.20 : IW clear, proses pengajuan eskalasi sitac 08.06.20 : 04.06.20 : 01.06.20 : IW on going 28.05.20 : 25.05.20 : 21.05.20 : IW on going 14.05.20 : TNP ok B, tower 20 08.05.20 : IW on going 30.04.20 : 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : 25.03.20 : 19.03.20 : IW on going 11.03.20 : 20.02.20 : IW on going 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
125 |  | JAW-BT-TNG-1465 | 30572580031 | 1317771003 | PASIR JAYA JATIUWUNG | ACTIVE | TB | 106.5661 | -6.1922 | 35 | 90/210/330 |  |  | Kel. Pasir Jaya Kp. Pasir Rt.001 Rw.002 Kec. Jatiuwung, Kota Tangerang Prov. Banten | EID | JAW-BT-TNG-1465 | PASIR JAYA JATIUWUNG | B2S | TBG | JABO | JABODETABEK (INNER) | Banten | KOTA TANGERANG | 6614368 | 2020-01-13 |  | 399 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-11-30 | W49-2020 | Nov-2020 | 2021-02-18 | W08-2021 | Feb-2021 | 2021-02-18 | W08-2021 | Feb-2021 | FO (Change to MW as temp solution) | 2020-12-08 |  | 566100973014 | 6.6 |  |  |  |  | 2021-02-15 | W08-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 15.02.21 : PLN connected, prepare RFIN 11.02.21 : perubahan transport FO to MW per 22 Jan 04.02.21 : PLN connection process 03.12.20 : SRIN sent 26.11.20 : ME ongoing, plan SRFI 29 Nov 23.11.20 : ME installation ongoing 16.11.20 : 12.11.20 : erection done 09.11.20 : erection ongoing 05.11.20 : 02.11.20 : 26.10.20 : plan hari ini start pengecoran 22.10.20 : rebaring 19.10.20 : 15.10.20 : OG Borepile 9 Titik, kedalaman 6m 12.10.20 : plan start borepile 14 oct 08.10.20 : bouwplank, Plan MOS team Borepile 10/10 05.10.20 : 01.10.20 : CME Start memerlukan REKOM PUPR, Plan start CME 08/10 28.09.20 : SPK confirm lanjut, proses perijinan, bouwplank, plan start CME minggu ini, target SRFI 30 oct 20 14.09.20 : 03.09.20 : MOM : XL PROPOSE RETURN SPK 03.09.20 : 31.08.20 : 27.08.20 : 24.08.20 : start CME menunggu rekom PUPR release 17.08.20 : plan start CME 20 AUG 13.08.20 : MOM : fu rekom PUPR, paln start CME minggu depan 13.08.20 : 10.08.20 : 06.08.20 : MoM : plan start CME paling lamabat weekly minggu depan 13 Aug 20 06.08.20 : Need rekomendasi PUPR untuk start CME, Plan start CME 18/08 03.08.20 : 30.07.20 : 23.07.20 : 20.07.20 : Need rekomendasi PUPR untuk start CME, Plan start CME 24/07 16.07.20 : IW clear, proses perijinan 13.07.20 : 09.07.20 : MOM : IW clear, plan realisasi IW akhir minggu ini 06.07.20 : 02.07.20 : plan IW done 7 juli, plan start CME 15 jul, plan SRFI 12 Aug 29.06.20 : 25.06.20 : IW kurang 2 kk, SST 42m 25.06.20 : paralel submit kandidat E, RNP approved RF 40m, Plan IW Done Jun 2020 22.06.20 : 18.06.20 : IW on going, plan RFC end of June 15.06.20 : 11.06.20 : IW clear 08.06.20 : rehunting 04.06.20 : 01.06.20 : 29.05.20 : waiting RND review 28.05.20 : 25.05.20 : 08.05.20 : IW on going 30.04.20 : IW on going 23.04.20 : 16.04.20 : 09.04.20 : 02.04.20 : IW on going 25.03.20 : 19.03.20 : IW on going 12.03.20 : waiting RND validation 20.02.20 : 13.02.20 : 06.02.20 : Kand A = Rehunting, Candidate A RF NOK
1 |  | JAW-JT-TMG-2656 | 30571810031 | 1432311003 | TEMANGGUNG BULU | ACTIVE | TB | 110.152 | -7.306 | 50 | 15/145/275 |  |  | JOHO SELATAN RT 001/ RW 001 DESA JOHO, KEC. TEMANGGUNG, KAB. TEMANGGUNG | EID | JAW-JT-TMG-2656 | TEMANGGUNG BULU | B2S | TBG | CENTRAL | JATENG | Jawa Tengah | TEMANGGUNG | 6614368 | 2020-01-13 |  | 536 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | 2021-02-28 | W10-2021 | Feb-2021 | 2021-07-06 | W28-2021 | Jul-2021 | FO (Change to MW as temp solution) | 2021-02-11 |  | 521552117528 | 7.7 |  |  |  | 2020-06-25 | 2021-07-02 | W27-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 07.01.21 : BPUJL Paid, plan connect 6 Jul, revisi RFI 6 Jul 06.24.21 : Registrasi PLN NY Released, plan Released 1 Jul, replan RFI 3 Jul 06.24.21: proses rekom PLN Released, Revisi Plan RFI 28 JUN 06.21.21 : 06.17.21 : 06.14.21 : 06.10.21 : Percepatan Pengurusan OPSIC (Ganti mitra OPSIC) estimasi 25 Jun 06.07.21 : 06.02.21 : 05.31.21 : 05.23.21 : 05.26.21 : 05.23.21 : 05.19.21 : Percepatan Pengurusan OPSIC estimasi solve W2 Jun Revise RFI W2 Jun 05.17.21 : 05.10.21 : 05.05.21 : 22.04.21 : 12.04.21 : hasil Surat Jawaban PLN connection akan dilayani jika IMB sudah release, OG percepatan ijin permit, revise RFI Plan W2 Jun 05.04.21 : 01.04.21 : plan PLN connect W2 Apr, waiting register released 29.03.21 : OG register PLN 25.03.21 : propose percepatan connect Multiguna, revise RFI plan end of Mar 25.02.21 : OG PLN connection 25.02.21 : OG PLN connection 11.02.21 : perubahan transport FO -> MW, waiting PSB release 03.08.20 : 20.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL, plan RFI adalah SK PLN release+14 hari 25.06.20 : email SRFI-N sent 25.06.20 : erection on going (top), plan SRFI today 22.06.20 : erection on going 3 section 18.06.20 : curingtime 15.06.20 : pouring concrete 11.06.20 : 08.06.20 : 04.06.20 : rebarring on going, tim baru start lg 2 jun 01.06.20 : rebarring on going 28.05.20 : excavation done 21.05.20 : excavation on going 14.05.20 : excavation on going 08.05.20 : stop isu perijinan 30.04.20 : excavation 23.04.20 : 16.04.20 : 09.04.20 : proses perijinan 02.04.20 : 25.03.20 : start CME masih menunggu konfirmasi perijinan area Temanggung 19.03.20 : prepare start CME, plan minggu ini 28.02.20 : proses perijinan, proses design pack (APD), plan design done minggu depan, material tower ready 20.02.20 : proses rekom L/C dan penjadwalan soiltest 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK
32 |  | JAW-JT-BBS-0155 | 30571940031 | 1432331003 | CIPAJANG BANJARHARJO | ACTIVE | TB | 108.81 | -7.0627 | 50 | 70/140/280 |  |  | PENANGGAPAN RT 001 RW 007 DESA PENANGGAPAN KEC. BANJARHARJO KAB. BREBES PROVINSI JAWA TENGAH | EID | JAW-JT-BBS-0155 | Cipajang Banjarharjo | B2S | TBG | CENTRAL | JATENG | DI Yogyakarta | BREBES | 6614368 | 2020-01-13 |  | 420 | > 150 days | 2020-06-11 | W24-2020 | Jun-2020 | 2020-05-15 | W20-2020 | May-2020 | 2021-02-28 | W10-2021 | Feb-2021 | 2021-03-06 | W10-2021 | Mar-2021 | FO (Change to MW as temp solution) | 2021-02-11 |  | 522582439529 | 7.7 |  |  |  | 2020-06-25 | 2021-03-08 | W11-2021 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 08.03.21 : PLN connected, NY RFIN -> plan 08/3 25.02.21 : OG PLN connection 11.02.21 : perubahan transport FO -> MW, waiting PSB release 03.08.20 : 20.07.20 : 16.07.20 : 09.07.20 : 02.07.20 : 29.06.20 : PLN Connection menunggu konfirmasi dari XL, plan RFI adalah SK PLN release+14 hari 25.06.20 : email SRFI-N sent 25.06.20 : SRFI, collecting doc SRFIN 22.06.20 : erection done, finishing,ME grounding OG 18.06.20 : erection on going 15.06.20 : STOP isu perijinan, proses negosiasi 11.06.20 : tower painting 04.06.20 : erection top 01.06.20 : 28.05.20 : 21.05.20 : 14.05.20 : erection on going 30.04.20 : curingtime 23.04.20 : 16.04.20 : galian done, lantai kerja, prepare rebarring 09.04.20 : on going galian 02.04.20 : 25.03.20 : start excavation 19.03.20 : prepare start CME, plan minggu ini 28.02.20 : proses perijinan, proses design pack (APD), plan design done minggu depan, material tower ready 20.02.20 : rekom done, submit berkas proses perijinan 13.02.20 : IW on going 06.02.20 : kand A = validasi done, Candidate A RF TX OK 20.01.20 : Kand A, B = submit kand A di 108.80813 -7.06279 (209m) propose Tower 52m, submit kand B di 108.80984 -7.06365 (112m) propose Tower 52m
628 |  | SUM-AC-JTH-0720 | 30573870031 | T000739 | SIBREH | ACTIVE - RELOCATION | SKP | 95.3613 | 5.5115 | 50 | 90/210/330 |  | RELOCATION | Jl. Sultan Iskandar Muda | HTI | SUM-AC-JTH-0720 | SUKA MAKMUR RELOCATION | COLO | TBG | WEST | SUMBAGUT |  |  | 6614363 | 2020-01-10 |  | 320 | > 150 days | 2020-02-09 | W07-2020 | Feb-2020 | 2020-02-06 | W06-2020 | Feb-2020 | 2020-04-06 | W15-2020 | Apr-2020 | 2020-11-25 | W48-2020 | Nov-2020 | MW | 2020-10-26 |  | 111120242916 | 6.6 |  |  |  | 2020-02-06 | 2020-11-25 | W48-2020 |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 25.11.20 : RFIN sent 03.08.20 : 07.07.20 : email konfirmasi untuk TIDAK CONNECT PLN nya dulu dari XL (Pak Roy) 20.07.20 : 29.06.20 : 25.06.20 : 22.06.20 : wait confirmation from XL for PLN connection
920 |  | SUL-SR-PLW-0166 | 30573390031 | 290011109 | PAPPANG | X ACTIVE - SPK 2019 | TRB | [5 empty] | RELOCATION | Jl. Cepa Kel. Pappang Kec. Campalagian,Kab.Polewali Mandar Sulawesi Barat | HTI | SUL-SR-PLW-0166 | CAMPALAGIAN RELOCATION | COLO | TBG | EAST | SULAWESI | Sulawesi Barat | Kab. Polewali Mandar | 6614296 | 2019-12-06 |  | 62 | 61 - 90 days | 2020-01-05 | W02-2020 | Jan-2020 | 2020-01-04 | W01-2020 | Jan-2020 | 2020-01-04 | W01-2020 | Jan-2020 | 2020-01-04 | W01-2020 | Jan-2020 | MW | [8 empty] | 2020-02-06 |  |  |  |  | 38.RFI | 21.RFI | CLOSED - RFI DONE | 06.02.20 : RFIN email done 21.01.20 : RBS foundation done, plan minggu ini material ME on site, wait konfirmasi permintaan PLN connection dari XL. Request PR CME done.
X
Formulas:
SPK DURATION (DAY) = IF(AND([SPK DATE]=""),"",IF(AND([SPK DATE]<>"",[RFI]<>""),[RFI]-[SPK DATE],IF(AND([SPK DATE]<>"",[RFI]=""),TODAY()-[SPK DATE])))
RFI TARGET BASED ON SLA (SLA) = IF(AND([SOW]=""),"TBD",IF(AND([SOW]="COLO"),[SPK DATE]+30,[SPK DATE]+150))
RFI TARGET BASED ON SLA (SLA) = [SPK DATE]+30
RFI PLAN (TP COMMITMENT) = [RFI TARGET BASED ON SLA (SLA)]
CME START = [ACTUAL DATE OF IMPLEMENTATION]+45
RFI REVISE PLAN = [RFI PLAN (TP COMMITMENT)]
Note on X638: Nur Indah Setyawati:

## Request PMIS
No | Site ID XL | Site Name XL | Tech. Partner | Region | SPK Type | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA)
1 | SUM-JA-JMB-0495 | PAGARDRUM RELOCATION | CAA | WEST | Jambi | 2021-08-16 |  |  | 143105944428 | 6.6
2 | BAL-BA-DPR-1508 | KECUBUNG_DENPASAR_RELOCATION | HTI | East | COLO | 2021-07-19 |  |  | 551004981534 | 6.6
0.74138
No | Site ID XL | Site Name XL | Tech. Partner | Region | SPK Type | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA) |  |  | 0.6069
1 | JAW-JT-BYL-0238 | ALHUDA KROBOKAN | EID | Central | Jawa Tengah | 2021-08-27 |  |  | 525520287756 | 7.7
2 | JAW-JT-BNR-0263 | MANDIRAJA SADANG PUCUNGBEDUG | EID | Central | Jawa Tengah | 2021-08-18 |  |  | 522042889330 | 7.7
| Site ID XL | Site Name XL | ID PELANGGAN PLN | DAYA (KVA)
| JAW-JT-MKD-1158 | Marungan Kajoran Magelang | 535812217807 | 6.6
| JAW-JB-BDG-4215 | BANDARA HUSEIN SASTRANEGARA RELOCATION | 535556193516 | 6.6
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUM-SS-MRE-1229 | KEPUR | HTI | 2021-10-14 |  |  | 147100685541 | 6.6 | 2021-10-13
| SUM-SS-PKB-1256 | SUKOMORO_PALEMBANG_BETUNG | HTI | 2021-10-14 |  |  | 141203537020 | 6.6 | 2021-10-13
| SUM-SS-PLG-1271 | ALANGLEBAR_TALANG_KELAPA | HTI | 2021-10-14 |  |  | 141203537053 | 6.6 | 2021-10-13
| SUM-SS-PKB-1258 | SUKOMORO_ALHIDAYAH | HTI | 2021-10-14 |  |  | 141203537046 | 6.6 | 2021-10-13
| SUM-SS-PLG-1273 | TALANG_KELAPA_JALAN_BYPASS | HTI | 2021-10-14 |  |  | 141203537038 | 6.6 | 2021-10-13
| SUM-LA-KLA-1121 | KALIANDA_KALIANDA | HTI | 2021-10-14 |  |  | 171300676079 | 6.6 | 2021-10-13
| JAW-JB-CJR-4244 | KADUPANDAK_SUKARAHARJA | HTI | 2021-10-14 |  |  | 536911857056 | 6.6 | 2021-10-14
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA)
| JAW-JB-SBR-4246 | SUMBER_KENANGA | HTI | 2021-10-14 |  |  | 533313478129 | 6.6
| JAW-JB-SBR-4245 | DEPOK_KEJUDEN | HTI | 2021-10-14 |  |  | 533313478137 | 6.6
| JAW-JI-MJK-4168 | MOJOSARI MOJOKERTO RELOCATION | HTI | 2021-10-28 |  |  | 514561067549 | 6.6
| JAW-JI-PSN-4127 | PURWOREJO WIROGUNAN | HTI | 2021-10-14 |  |  | 513500998222 | 6.6
| JAW-JI-SDA-4315 | JABON KEDUNGREJO | HTI | 2021-10-14 |  |  | 513500998222 | 6.6
| SUM-SU-LBP-2290 | LUBUK_PAKAM_TANJUNG_GARBUS_I | HTI | 2021-10-14 |  |  | 122021125525 | 6.6
| SUM-SS-MPR-1254 | CUTNYAKDIEN_SUMBER_MULYO | HTI | 2021-09-06 |  |  | 147600643560 | 6.6
| SUM-RI-DUM-1145 | RATU_SIMA | HTI | 2021-09-06 |  |  | 182501156609 | 6.6
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA)
| SUM-SU-LBP-2257 | KUTALIMBARU_SAWIT_REJO | HTI | 2021-10-14 |  |  | 122021125694 | 6.6
| SUL-ST-PAL-1124 | MANTIKULORE_TALISE | HTI | 2021-10-14 |  |  | 312101265485 | 6.6
| SUM-SU-STB-2219 | PEKAN_SELESAI | HTI | 2021-10-14 |  |  | 122030622843 | 6.6
| SUM-SU-STB-2218 | PERK_TANJUNG__BERINGIN | HTI | 2021-10-14 |  |  | 122150553680 | 6.6
| SUM-LA-MET-1131 | METRO_TIMUR_YOSODADI | HTI | 2021-10-15 |  |  | 172000864111 | 6.6
| SUL-ST-PAL-1123 | PALU_UTARA_TAIPA | HTI | 2021-10-15 |  |  | 312300275192 | 6.6
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUM-AC-JTH-0741 | LAM_KAWE | HTI | 2021-10-16 |  |  | 111120269512 | 6.6 | 2021-10-15
| SUM-JA-JMB-0504 | TENGAH_ULU_GEDONG | HTI | 2021-10-16 |  |  | 143205451254 | 6.6 | 2021-10-15
| SUM-JA-JMB-0507 | LEGOK | HTI | 2021-10-16 |  |  | 143005622696 | 6.6 | 2021-10-15
| JAW-JB-GRT-4251 | BANJARWANGI_KADONGDONG | HTI | 2021-10-16 |  |  | 532762045566 | 6.6 | 2021-10-15
| JAW-JI-KPN-4398 | TIRTOYUDO GADUNGSARI | HTI | 2021-10-16 |  |  | 513080337178 | 6.6 | 2021-10-15
| JAW-JI-KPN-4411 | KALIPARE ARJOWILANGUN | HTI | 2021-10-16 |  |  | 513100329904 | 6.6 | 2021-10-15
| SUM-LA-BDL-1128 | CAMPANG_RAYA_SOETTA | HTI | 2021-10-16 |  |  | 171202936753 | 6.6 | 2021-10-15
| SUM-LA-BDL-1130 | TIMUR_SUKAMAJU_REMARTADINATA | HTI | 2021-10-16 |  |  | 171802765325 | 6.6 | 2021-10-15
| SUM-SS-KAG-1243 | KUTARAYA | HTI | 2021-10-16 |  |  | 149100127229 | 6.6 | 2021-10-15
| SUM-SS-PLG-1274 | SAKO_SAKO | HTI | 2021-10-16 |  |  | 141103467801 | 6.6 | 2021-10-15
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA)
| JAW-JI-JMR-5123 | BALUNG KARANG SEMANDING | HTI | 2021-10-27 |  |  | 516041138833 | 6.6 | jatim
| JAW-JI-MJY-4141 | MEJAYAN BANGUNSARI | HTI | 2021-10-22 |  |  | 515071136343 | 6.6
| JAW-JI-NJK-4250 | PACE BABADAN | HTI | 2021-10-22 |  |  | 514601929137 | 6.6
| JAW-JI-PNG-4293 | JENANGAN SETONO | HTI | 2021-10-22 |  |  | 515402536977 | 6.6
| SUM-KR-BTM-0606 | TIBAN_BARU | HTI | 2021-10-22 |  |  | 152002074451 | 6.6
| JAW-JI-KPN-4407 | NGEMBAL WAJAK | HTI | 2021-10-21 |  |  | 513020736952 | 6.6
| JAW-JI-LMG-4294 | LOPANG KEMBANGBAHU | HTI | 2021-10-21 |  |  | 518031807284 | 6.6
| JAW-JI-NGW-3676 | JURUREJO NGAWI | HTI | 2021-10-21 |  |  | 515042230448 | 6.6
| SUM-JA-JMB-0503 | SIJENJANG | HTI | 2021-10-21 |  |  | 143005622990 | 6.6
| JAW-JI-SDA-4316 | TANGGULANGIN KALITENGAH | HTI | 2021-10-27 |  |  | Non Pelanggan | 6.6 | jatim
| JAW-JI-JBG-4167 | TEMBELANG KEDUNGLOSARI | HTI | 2021-10-27 |  |  | Non Pelanggan | 6.6 | jatim
| JAW-JI-PMK-4237 | BATUMARMAR PANGERREMAN | HTI | 2021-10-27 |  |  | Non Pelanggan | 6.6 | jatim
| JAW-JI-SPG-4232 | KETAPANG PAOPALELAOK | HTI | 2021-10-27 |  |  | Non Pelanggan | 6.6 | jatim
| JAW-JI-SPG-4230 | KETAPANG PANCOR | HTI | 2021-10-27 |  |  | Non Pelanggan | 6.6 | jatim
| JAW-JI-TRK-4264 | POGALAN GEMBLEB | HTI | 2021-10-27 |  |  | Non Pelanggan | 6.6 | jatim
| JAW-JB-GRT-4250 | SINGAJAYA_GIRIMUKTI | HTI | 2021-10-27 |  |  | 532762048277 | 6.6 | jabar
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA)
| JAW-BT-TNG-1524 | KARANGSARI PEMBANGUNAN RELIOCATION | EID | 2021-10-28 |  |  | 566101065949 | 6.6 | JABO
| JAW-JT-SMG-0624 | PUCUNG RAYA INDUSTRI RELOCATION | EID | 2021-10-28 |  |  | 523024864892 | 7.7 | JATENG
PAGI | Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA)
| JAW-JB-CMS-4142 | CIPAKU_CIAKAR | HTI | 2021-10-31 |  |  | 566101065949 | 6.6 | jabar | central
| JAW-JB-NPH-4176 | PARONGPONG_SARIWANGI | HTI | 2021-10-31 |  |  | 535812240425 | 6.6 | JABAR | CENTRAL
| JAW-JI-GSK-4326 | MANYAR_GRESIK | HTI | 2021-10-31 |  |  | 511201194981 | 6.6 | JATIM | EAST
| SUM-LA-GNS-1137 | BUMI_NABUNG_UTARA | HTI | 2021-10-31 |  |  | 172801510119 | 6.6 | sumbagsel | west
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA)
| JAW-JB-MJL-4124 | MALAUSMA_BANYUSARI |  |  |  |  | non pelanggan | 5.5 | jabar | central
malam | Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA)
| SUM-SS-PLG-1275 | TALANG_KELAPA_SUKOSARI | HTI | 2021-10-31 |  |  | 141203544150 | 6.6 | sumbagsel
| SUM-SB-BSK-0856 | SIMAWANG | HTI | 2021-10-31 |  |  | 134510175465 | 6.6 | sumbagteng | west
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA)
| JAW-JT-KLN-0919 | TELOYO | EID | 2021-11-01 |  |  | 524020698374 | 7.7 | JATENG
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA)
| KAL-KS-MRH-1116 | ANTAR_JAYA | HTI | 2021-11-02 |  |  | 221500569291 | 6.6 | KALIMANTAN
| BAL-BA-DPR-1511 | SOUTH_GLOGOR_CARIK_RELOCATION | HTI | 2021-11-02 |  |  | 551400481716 | 6.6 | BALNUS
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA)
| JAW-JT-KRG-2132 | MOJOGEDANG SEWUREJO | EID | 2021-11-04 |  |  | 526550131833 | 7.7 | JATENG
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA)
| JAW-JT-PBG-1232 | PAGERANDONG MREBET | EID | 2021-11-05 |  |  | 522032686844 | 7.7 | JATENG
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA)
| BAL-BA-DPR-1519 | DENPASARTIMUR_SUMERTAKAJA | HTI | 2021-11-06 |  |  | 551004998418 | 6.6 | BALNUS
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA)
| KAL-KS-KGN-0944 | PADANG_BATUNG | HTI | 2021-11-08 |  |  | 222200235589 | 6.6 | KALIMANTAN
| KAL-KS-PLI-0982 | BATUAMPAR_DAMAR_LIMA | HTI | 2021-11-08 |  |  | 221400592277 | 6.6 | KALIMANTAN
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA)
| JAW-JT-KRG-2147 | PEMERINTAH REJOSARI | EID | 2021-11-10 |  |  | 520521495640 | 7.7 | JATENG
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA)
| SUM-SB-BSK-0856 | SIMAWANG | HTI | 2021-11-10 |  |  | 134510175465 | 6.6 | SUMBAGTENG
No | Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
1 | SUM-RI-RGT-0976 | PANGKALANKASAI_LINTAS_SUMATERA | HTI | 2021-11-12 |  |  | 184103616399 | 6.6 | 2021-11-11 |  | BLM SUBMIT | sumbagteng
2 | SUM-RI-RGT-0973 | KAMPUNG_BESAR_SEBERANG | HTI | 2021-11-12 |  |  | 184103616402 | 6.6 | 2021-11-11 |  |  | sumbagteng
3 | JAW-JI-LMJ-4235 | YOSOWILANGUN_WOTGALIH | HTI | 2021-11-12 |  |  | 516021598269 | 6.6 | 2021-09-30 |  |  | jatim
4 | JAW-JI-TRK-4263 | TRENGGALEK DAWUHAN | HTI | 2021-11-12 |  |  | 515432223415 | 6.6 | 2021-10-15 |  |  | jatim
5 | JAW-JI-JMR-5127 | UMBULSARI SUKORENO | HTI | 2021-11-12 |  |  | 516070871672 | 6.6 | 2021-10-15 |  |  | jatim
6 | JAW-JI-KDR-4324 | KEPUNG DAMARWULAN | HTI | 2021-11-12 |  |  | 514541403592 | 6.6 | 2021-10-21 |  |  | jatim
7 | JAW-JI-BDW-3622 | TAMANAN WONOSUKO | HTI | 2021-11-12 |  |  | 516532680668 | 6.6 | 2021-10-19 |  |  | jatim
8 | JAW-JI-KNR-4191 | BINANGUN_BIROWO | HTI | 2021-11-12 |  |  | 514091929021 | 6.6 | 2021-09-13 |  |  | jatim
9 | JAW-JI-PMK-4237 | BATUMARMAR PANGERREMAN | HTI | 2021-11-12 |  |  | 517800670601 | 6.6 | 2021-10-25 |  |  | jatim
10 | JAW-JI-TRK-4264 | POGALAN GEMBLEB | HTI | 2021-11-12 |  |  | 515432223360 | 6.6 | 2021-10-25 |  |  | jatim
11 | JAW-JI-PNG-4298 | SAMBIT BANCANGAN | HTI | 2021-11-12 |  |  | 515413782084 | 6.6 | 2021-10-19 |  |  | jatim
12 | JAW-JI-BYW-4148 | SONGGON SUMBERBULU KOESNO REJO | HTI | 2021-11-12 |  |  | 516711495042 | 6.6 | 2021-10-19 |  |  | jatim
13 | JAW-JI-BDW-3619 | JAMBESARI DARUS SHOLAH JAMBESARI | HTI | 2021-11-12 |  |  | 516532680650 | 6.6 | 2021-10-19 |  |  | jatim
14 | JAW-JI-TBN-4070 | BANCAR BANCAR | HTI | 2021-11-12 |  |  | 518070794721 | 6.6 | 2021-10-18 |  |  | jatim
15 | JAW-JI-NJK-4250 | PACE BABADAN | HTI | 2021-11-12 |  |  | 514601929137 | 6.6 | 2021-10-21 |  |  | jatim
16 | JAW-JI-PNG-4293 | JENANGAN SETONO | HTI | 2021-11-12 |  |  | 515402536977 | 6.6 | 2021-10-21 |  |  | jatim
17 | JAW-JI-GSK-4332 | KEDAMEAN TULUNG | HTI | 2021-11-12 |  |  | 511812349935 | 6.6 | 2021-10-18 |  |  | jatim
18 | JAW-JI-JBG-4175 | TEMBELANG PULO GEDANG | HTI | 2021-11-12 |  |  | 514550993876 | 6.6 | 2021-10-18 |  |  | jatim
19 | JAW-JI-JMR-5123 | BALUNG KARANG SEMANDING | HTI | 2021-11-12 |  |  | 516041138833 | 6.6 | 2021-10-25 |  |  | jatim
20 | JAW-JI-BDW-3623 | MAESAN TANAH WULAN | HTI | 2021-11-12 |  |  | 516532681368 | 6.6 | 2021-10-25 |  |  | jatim
21 | JAW-JI-LMG-4294 | LOPANG KEMBANGBAHU | HTI | 2021-11-12 |  |  | 518031807284 | 6.6 | 2021-10-19 |  |  | jatim
22 | JAW-JI-KPN-4414 | TAJINAN PURWOSEKAR | HTI | 2021-11-12 |  |  | 513020736911 | 6.6 | 2021-10-19 |  |  | jatim
23 | JAW-JI-KDR-4322 | PLEMAHAN TEGOWANGI | HTI | 2021-11-12 |  |  | 514061372217 | 6.6 | 2021-10-19 |  |  | jatim
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA)
| KAL-KT-KLK-0426 | KAPUAS_BARAT | HTI | 2021-11-13 |  |  | 225100184795 | 6.6 | BLM SUBMIT | kalimantan
| SUM-SS-MRE-1233 | TANJUNG_ENIM_LINTAS_TENGAH | HTI | 2021-11-13 |  |  | 147100688003 | 6.6 |  | sumbagsel
| SUM-SU-LBP-2256 | PERCUT_SEI_TUAN_SAMBIREJO_TIMUR | HTI | 2021-11-13 |  |  | 128050016992 | 6.6 |  | sumbagut
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-BLA-0138 | SAMBONG_KAWENGAN | EID | 2021-11-13 |  |  | 520071607803 | 7.7 | 2021-11-13
| JAW-JT-PWR-1670 | PANDANREJO KALIGESING | EID | 2021-11-13 |  |  | 521521373838 | 7.7 | 2021-09-20
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-SGN-1825 | KEBAYANAN BANARAN KALIJAMBE | EID | 2021-11-17 |  |  | 520592269559 | 7.7 | 2021-11-17
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-JPA-0705 | BENTENG PORTUGIS BANDUNGHARJO | EID | 2021-11-18 |  |  | 520031344866 | 7.7 | 2021-09-09
| JAW-JT-KDS-0853 | LAU DAWE KUDUS | EID | 2021-11-18 |  |  | 520013357867 | 7.7 | 2021-11-18
| JAW-JT-PWD-0034 | BANGSRI GEYER GROBOGAN | EID | 2021-11-18 |  |  | 525540196895 | 7.7 | 2021-11-18
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JB-CBI-0134 | MOH_TOHA_PARUNG_PANJANG | EID | 2021-11-19 |  |  | 538531213966 | 6.6 | 2021-11-19
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-TRK-4258 | WATULIMO_WATUAGUNG | HTI | 2021-11-19 |  |  | 515432223593 | 6.6 | 2021-11-19
| JAW-JI-NGW-3667 | WIDODAREN KEDUNGGUDEL | HTI | 2021-11-19 |  |  | 515090793511 | 6.6 | #REF!
| JAW-JI-NGW-3677 | NGAWI GRUDO | HTI | 2021-11-19 |  |  | 515042230393 | 6.6 | #REF!
| JAW-JI-NGW-3672 | KENDAL PATALAN | HTI | 2021-11-19 |  |  | 515031650545 | 6.6 | #REF!
| JAW-JI-MJY-4142 | DOLOPO KRADINAN | HTI | 2021-11-19 |  |  | 515081001675 | 6.6 | #REF!
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| KAL-KB-PTK-0809 | ABDULLAH_SAIGON | HTI | 2021-11-23 |  |  | 211002617744 | 6.6 | 2021-11-18
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-WNG-2771 | MENTO WONOHARJO | EID | 2021-11-24 |  |  | 526530134532 | 7.7 | 2021-11-23
| JAW-JT-PBG-1234 | KARANGKLESEM KUTASARI | EID | 2021-11-24 |  |  | 522032706779 | 7.7 | 2021-11-20
| JAW-JT-MKD-1143 | MUNTILAN RELOCATION | EID | 2021-12-11 |  |  | 521541397291 | 7.7 | 2021-11-20
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by HTI) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUM-SB-SRK-0940 | LABUAH_GUNUANG | HTI | 2021-11-23 |  |  | 134520326445 | 6.6 | 2021-11-09
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUM-KR-BTM-0617 | PEMPING | HTI | 2021-12-04 |  |  | 183041635485 | 6.6 | 2021-12-03
| KAL-KU-TAR-0109 | KAMPUNG4(RRITARAKAN) RELOCATION | CAA | 2021-12-04 |  |  | 235200030349 | 6.6 | 2021-11-25
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-KNR-4282 | SELOPURO SELOPURO | HTI | 2021-12-09 |  |  | 514080992478 | 6.6 | 2021-10-21
| KAL-KT-KSN-0435 | MENDAWAI_MENDAWAI | HTI | 2021-12-11 |  |  | 224400773973 | 6.6 | 2021-10-05
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-PNG-4295 | SUKOREJO BANGUNREJO | HTI | 2021-12-14 |  |  | 515402549206 | 6.6 | 2021-10-18
| JAW-JI-PNG-4300 | SAMPUNG_TULUNG | HTI | 2021-12-14 |  |  | 515402547522 | 6.6 | 2021-10-17
| JAW-JI-PNG-4293 | JENANGAN SETONO | HTI | 2021-12-14 |  |  | 515402549214 | 6.6 | 2021-10-21
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by EID) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JB-BGR-0235 | JAGORAWI CIMAHPAR RELOCATION | EID | 2021-12-17 |  |  | 538216433530 | 6.6 | 2021-12-16
| JAW-JT-PBG-1233 | CANDIWULAN KUTASARI | EID | 2021-12-17 |  |  | 522032711320 | 7.7 | 2021-12-03
| JAW-JB-SBM-2134 | RAYA CIDAHU MEKARSARI | EID | 2021-12-17 |  |  | 536590596124 | 6.6 | 2021-12-14
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| NUS-NB-MTR-5391 | MONJOK BARAT RELOCATION | CAA | 2021-12-23 |  |  | 441503329783 | 6.6 | 2021-12-21
| JAW-JB-MJL-4124 | MALAUSMA_BANYUSARI | HTI | 2021-12-23 |  |  | 535212664637 | 5.5 | 2021-10-29
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-KNR-4196 | SRENGAT_MARON | HTI | 2022-01-05 |  |  | 514051659104 | 10.6 | 2021-12-24
| SUM-KR-BTM-0617 | PEMPING | HTI | 2022-01-05 |  |  | 183041635485 | 6.6 | 2021-12-06
| JAW-JI-KPN-4417 | PONCOKUSUMO KARANGNONGKO | HTI | 2022-01-05 |  |  | 513060942376 | 6.6 | 2021-11-01
| SUL-ST-LWK-1082 | LUWUK_KILONGAN_PERMAI | HTI | 2022-01-05 |  |  | 319500337732 | 6.6 | 2022-01-04
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| KAL-KS-BLN-0964 | MANTEWE | HTI | 2022-01-06 |  |  | 223200582873 | 6.6 | 2021-12-27
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-PWD-0026 | HIKMAH REJOSARI | EID | 2022-01-11 |  |  | 525540201381 | 7.7 | 2021-11-27
| JAW-YO-SMN-0064 | SIDOREJO GODEAN | EID | 2022-01-11 |  |  | 521041710933 | 7.7 | 2022-01-10
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| BAL-BA-GIN-1489 | GIANYAR_SUMITA | HTI | 2022-01-11 |  |  | 552001743730 | 6.6 | 2022-01-10
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| KAL-KS-KBR-0981 | KELUMPANG_HULU | HTI | 2022-01-13 |  |  | 223200578803 | 6.6 | 2021-11-04
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUL-SG-RAH-0472 | REPEATER KASIMPA JAYA | HTI | 2022-01-14 |  |  | 328200582331 | 6.6 | 2022-01-13
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| KAL-KS-TJG-0954 | MUARA_UYA_UWIE | HTI | 2022-01-18 |  |  | 222400317590 | 6.6 | 2022-01-11
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUM-KR-RAN-0601 | TANJUNG_KUMBIK_UTARA | HTI | 2022-01-24 |  |  | 183082846970 | 6.6 | 2022-01-23
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-BLT-1917 | KEPANJEN_KIDUL_SENTUL | HTI | 2022-01-31 |  |  | 183082846970 | 6.6 | 2021-03-16
| JAW-JI-BLT-1915 | SANAN_BENDO | HTI | 2022-01-31 |  |  | 514021937038 | 6.6 | 2021-03-16
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-KRG-2137 | TAWANGMANGU MATESI KORIPAN | EID | 2022-01-04 |  |  | 526550148393 | 7.7 | 2021-11-08
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUM-SU-LBP-2269 | TEMBUNG_PEMBANGUNAN | HTI | 2022-02-09 |  |  | 128050014438 | 6.6 | 2022-10-31
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-BTU-4117 | BUMIAJI_TULUNGREJO | HTI | 2022-02-10 |  |  | 513031070006 | 6.6 | 2022-12-01
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-SKT-2146 | DR RAJIMAN PAJANG | EID | 2022-02-14 |  |  | 520512091107 | 7.7 | 2022-02-11
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUM-KR-BTM-0595 | TEMBESI | HTI | 2022-02-14 |  |  | 153000398174 | 6.6 | 2022-02-04
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| KAL-KS-MRH-0948 | ALALAK | HTI | 2022-02-21 |  |  | 221500582244 | 6.6 | 2022-02-02
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-BTU-4114 | BUMIAJI_PANDANREJO | HTI | 2022-02-22 |  |  | 513031073530 | 6.6 | 2021-11-30
| JAW-JI-SPG-4230 | KETAPANG PANCOR | HTI | 2022-02-22 |  |  | 517800690857 | 6.6 | 2021-10-25
| JAW-JI-SDA-4316 | TANGGULANGIN KALITENGAH | HTI | 2022-02-22 |  |  | 511821724552 | 6.6 | 2021-10-25
| JAW-JI-SPG-4233 | SOKOBANAH BIRA TIMUR | HTI | 2022-02-22 |  |  | 517800690857 | 6.6 | 2021-10-20
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUM-RI-BLS-1133 | PINGGIR_TENGGANAU | HTI | 2022-02-25 |  |  | 182103613019 | 6.6 | 2022-02-24
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-SKH-1900 | CEMANI SUKOHARJO | EID | 2022-02-25 |  |  | 520512082411 | 6.6 | 2022-02-24
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JB-BDG-4313 | TALAGA BODAS RELOCATION | CAA | 2022-02-25 |  |  | 535515962915 | 6.6 | 2022-02-23
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-PNG-4290 | BABADAN LEMBAH | HTI | 2022-02-25 |  |  | 515402558166 | 6.6 | 2022-10-22
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-SPG-4231 | BANYUATES TEROSAN | HTI | 2022-03-01 |  |  | 517500847210 | 6.6 | 2021-10-25
| SUM-BB-PGP-0531 | TUATUNU_INDAH | HTI | 2022-03-01 |  |  | 161001841798 | 6.6 | 2022-02-28
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-JBG-4178 | BARENG NGRIMBI | HTI | 2022-03-11 |  |  | 514541411739 | 6.6 | 2022-11-18
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-SKT-2142 | KALINGGA KADIPIRO | EID | 2022-03-11 |  |  | 520521518979 | 7.7 | 2022-03-02
| JAW-JT-SKT-2147 | KOLONEL SUTARTO JEBRES | EID | 2022-03-11 |  |  | 520521518427 | 7.7 | 2022-03-09
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JB-DPK-0496 | KELAPA DUA RELOCATION | EID | 2022-03-23 |  |  | 547401893080 | 7.7 | 2022-03-15
| JAW-BT-SRG-0051 | BATUKUDA_SERANG | EID | 2022-03-23 |  |  | 561200506958 | 7.7 | 2022-03-22
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JB-CJR-4341 | SUKABAKTI | HTI | 2022-03-23 |  |  | 536911877238 | 6.6 | 2022-03-14
| JAW-JB-CMS-4298 | CILEUNGSIR | HTI | 2022-03-23 |  |  | 532217825759 | 6.6 | 2022-03-14
| JAW-JB-GRT-4268 | SITUGEDE | HTI | 2022-03-23 |  |  | 532861294529 | 6.6 | 2022-03-17
| JAW-JB-SOR-4416 | CIWIDEY_RAWABOGO | HTI | 2022-03-23 |  |  | 535322209600 | 6.6 | 2022-03-22
| JAW-JB-CMH-4322 | VELODROME_CIMAHI_PADASUKA | HTI | 2022-03-23 |  |  | 535812260942 | 6.6 | 2022-03-22
| JAW-JB-NPH-4385 | CIPONGKOR_KARANGSARI | HTI | 2022-03-23 |  |  | 535950926520 | 6.6 | 2022-03-22
| SUM-LA-KTB-1143 | KOTABUMI_UTARA_MARGO_REJO | HTI | 2022-03-23 |  |  | 173001522318 | 6.6 | 2022-03-22
| JAW-JB-SOR-4415 | PADAULUN | HTI | 2022-03-23 |  |  | 535312338572 | 6.6 | 2022-03-22
| SUM-LA-KLA-1128 | SINAR_PASEMAH | HTI | 2022-03-23 |  |  | 171310603829 | 6.6 | 2022-03-22
| SUL-SN-SDR-1280 | KELURAHAN_RAPPANG_PANCA_RIJANG | HTI | 2022-03-23 |  |  | 325300489255 | 6.6 | 2022-03-22
| JAW-JB-NPH-4377 | CIPATAT_RAJAMANDALAKULON | HTI | 2022-03-23 |  |  | 535950926587 | 6.6 | 2022-03-23
| JAW-JB-SMD-4366 | TRUNAMANGGALA | HTI | 2022-03-23 |  |  | 535113438378 | 6.6 | 2022-03-23
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| BAL-BA-DPR-8075 | UBUNG TIMUR RELOCATION | CAA | 2022-03-23 |  |  | 551005019757 | 6.6 | 2022-03-16
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-SPG-4232 | KETAPANG PAOPALELAOK | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2021-10-25
| JAW-JI-TLG-4243 | KALIDAWIR DOMASAN | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2021-12-06
| JAW-JI-BJN-4303 | SUGIHWARAS_PANUNGGALAN | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-TBN-4072 | MERAKURAK_PONGPONGAN | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-BJN-4298 | NGASEM_NGANTRU | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-BJN-4301 | BOJONEGORO_SUKOREJO | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-BJN-4304 | BALEN_PRAMBATAN | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-JBG-5133 | PLOSO_PAGERTANJUNG | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-BJN-4307 | KASIMAN_TAMBAKMERAK | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-BJN-4302 | PADANGAN_BANJARJO | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-GSK-4340 | DUDUKSAMPEYAN_SUMENGKO | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-PNG-4309 | BADEGAN_BANDARALIM | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-BJN-4296 | GAYAM_MOJODELIK | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-LMG-4297 | DEKET_SIDOBINANGUN | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-GSK-4339 | BALONGPANGGANG_WOTANSARI | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-LMG-4305 | DEKET_DINOYO | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-LMG-4301 | KARANGBINANGUN_SAMBOPINGGIR | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-MJY-4144 | WUNGU_KARANGREJO | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-PNG-4304 | SAMPUNG_KAUMAN | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-KDR-4333 | MOJO_PAMONGAN | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-NJK-4255 | BAGOR_BUDURAN | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-KDR-4350 | PESANTREN_TOSAREN | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-KDR-4332 | PAGU_KAMBINGAN | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-KDR-4330 | GURAH_BESUK | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-KNR-4289 | KADEMANGAN_MARON | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| JAW-JI-BKL-4321 | MODUNG_KWANYAR | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| SUM-RI-PBR-1201 | KELURAHAN_TIRTASIAK | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-23
| SUM-RI-BKN-1169 | BUKIT_KEMUNING | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| SUM-RI-BLS-1141 | PANGKALAN_BATANG | HTI | 2022-03-25 |  |  | #REF! | 6.6 | 2022-03-24
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUL-SN-WNS-0973 | KELURAHAN_LEMBA_LALABATA | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUL-SN-SDR-1285 | BAPANGI_PANCA_LAUTAN | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUL-SN-WNS-0977 | TELLULIMPOE_MARIORIAWA | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-AC-STB-2239 | STABAT_KARANG_REJO | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-AC-STB-2230 | BARU_PASAR_VIII | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-RI-PRP-1110 | RAMBAH_SUKA_MAJU | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUL-SN-WNS-0988 | LARINGGI_MARIORIAWA | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-LA-KLA-1135 | NATAR_CANDI_MAS | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-LA-KLA-1139 | GEDUNG_HARTA | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-LA-KLA-1145 | TANJUNG_BINTANG_SABAH_BALAU | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-LA-KLA-1147 | WAY_HUI | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUL-SN-PLP-1343 | LAMASI_PANTAI_WALENRANG_TIMUR | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-LA-GNS-1139 | MOJOPAHIT | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-SS-MRE-1236 | GELUMBANG_SUKA_MENANG | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-LA-SDN-1151 | MEKAR_SARI | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-LA-KLA-1133 | PURWODADI_DALAM | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUM-SB-PNN-0804 | PULAU_KARAM_AMPANG_PULAI | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| SUM-KR-TPG-0598 | PINANG_KENCANA_GANET | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| JAW-JB-CJR-4330 | CIBEBER_CIBADAK | HTI | 2022-03-31 |  |  | #REF! | 6.6 | #REF!
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-SKT-2142 | KALINGGA KADIPIRO | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| JAW-JT-SKT-2147 | KOLONEL SUTARTO JEBRES | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| JAW-JB-DPK-0496 | KELAPA DUA RELOCATION | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| JAW-BT-SRG-0058 | CURUG_AGUNG | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| JAW-BT-SRG-0051 | BATUKUDA_SERANG | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| JAW-JT-KRG-2152 | PABLENGAN_KARANGANYAR | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| JAW-JB-CKR-0125 | JARAKOSTA_DANAUINDAH | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| JAW-JB-SBM-2450 | GUNUNG_PADANG | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| JAW-BT-RKB-0591 | SUKAJAYA_SOBANG | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| JAW-BT-PDG-0617 | BULAGOR_PAGELARAN | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| JAW-BT-RKB-0587 | CILAYANG_LEBAK | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| JAW-JB-SBM-2452 | JALAN_KERAMAT_SUKALARANG | EID | 2022-04-01 |  |  | #REF! | #REF! | #REF!
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUM-RI-TBH-1089 | TEMBILAHAN_HULU | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JI-PNG-4307 | SUKOREJO_SIDOREJO | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-SU-SRH-2249 | KERAPUH | HTI | 2022-04-08 |  |  | 126180006928 | 6.6 | #REF!
| SUM-SU-SRH-2239 | SEI_BELUTU | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUL-SN-SDR-1279 | KELURAHAN_LAWAWOI_WATANG_PULU | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-SU-MDN-2237 | MEDAN_AMPLAS_HARJOSARI_II | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-CJR-4337 | CUGENANGTALAGA | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-SOR-4422 | PANGGUH | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-SPA-4242 | MANDALAHAYU | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-CJR-4320 | LELES_SUKAMULYA | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-SPA-4233 | PAGERAGEUNG_PUTERAN_GURANTENG | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-CMS-4292 | SUKAMANTRI_MEKARWANGI | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-SPA-4224 | BURUJULJAYA | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-CMS-4286 | SADANANYA_TANJUNGSARI | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-MJL-4127 | BANTARUJEG_CIKIDANG | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-LA-KOT-1087 | KOTA_AGUNG_KEDAMAIAN | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| NUS-NB-TJN-5384 | GENGGELANG | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-SS-MBL-1202 | SUKOWARNO | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-SS-MBL-1206 | JAYA_BHAKTI | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-CJR-4331 | CAMPAKA_CIDADAP | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-SS-MRD-1012 | ANUGERAH_KEMU | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JI-TLG-4251 | REJOTANGAN_BLIMBING | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-LA-PRW-1126 | MARGOSARI | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-SS-MPR-1274 | SEMENDAWAI_SUKU_III_KARANG_ENDAH | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-SPA-4230 | CIKUPA | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUL-ST-LWK-1068 | TOILI | HTI | 2022-04-08 |  |  | 532652455637 | 6.6 | #REF!
| SUL-ST-LWK-1090 | TOILIBARAT_MEKAR_JAYA | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-GRT-4258 | CILAMPUYANG | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-JA-KLT-0473 | SRI_AGUNG | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-LA-KTB-1146 | GEDUNG_KETAPANG | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-SS-MRD-1007 | PULAU_KEMILING | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUL-SA-BIT-0393 | TENDEKI_MATUARI | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| SUM-LA-KTB-1147 | KOTA_NAPAL | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| NUS-NB-TJN-5377 | SENGGIGI_PEMENANG_BARAT | HTI | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-GRT-4257 | CINTARASA | HTI | 2022-04-08 |  |  | #REF! | 6.6 | #REF!
| SUM-LA-KLA-1148 | TANJUNG_SENANG_WAY_KANDIS | HTI | 2022-04-08 |  |  | #REF! | 6.6 | #REF!
| JAW-JB-GRT-4254 | CISOMPET_NEGLASARI | HTI | 2022-04-08 |  |  | #REF! | 6.6 | #REF!
| JAW-JB-CMS-4293 | CIOMAS | HTI | 2022-04-08 |  |  | #REF! | 6.6 | #REF!
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-BT-TGR-0099 | KRAGILAN_TANGERANG | EID | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JT-JPA-0714 | MINDAHAN_KIDUL_JEPARA | EID | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-KWG-1101 | ANGGADITA_KLARI | EID | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JT-SMG-0626 | GONDANG_TEMBALANG | EID | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| JAW-JB-CKR-0104 | BABELAN_KOTA | EID | 2022-04-08 |  |  | #REF! | #REF! | #REF!
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JB-CJR-4322 | NAGASARI | HTI | 2022-04-12 |  |  | 536911879805 | 6.6 | 2022-04-08
| JAW-JB-SMD-4367 | CIPAMEUNGPEUK | HTI | 2022-04-12 |  |  | 535113442730 | 6.6 | 2022-04-08
| JAW-JB-SMD-4365 | MARGAMEKAR | HTI | 2022-04-12 |  |  | 535113442381 | 6.6 | 2022-04-08
| JAW-JB-CJR-4318 | CINERANG | HTI | 2022-04-12 |  |  | 536911879870 | 6.6 | 2022-04-08
| JAW-JB-CJR-4327 | SINDANGBARANG_GIRIMUKTI | HTI | 2022-04-12 |  |  | 536911879792 | 6.6 | 2022-04-08
| JAW-JB-CJR-4319 | MEKARLAKSANA | HTI | 2022-04-12 |  |  | 536911880015 | 6.6 | 2022-04-08
| SUL-ST-LWK-1091 | TOILIBARAT_KAMI_WANGI | HTI | 2022-04-12 |  |  | 319100338641 | 6.6 | 2022-04-09
| SUM-LA-GDT-1132 | JL_UMBUL_KUNCI_KETEGUHAN | HTI | 2022-04-12 |  |  | 171802788465 | 6.6 | 2022-04-08
| SUM-SS-MBL-1201 | JAJARAN_BARU_II | HTI | 2022-04-12 |  |  | 147800877433 | 6.6 | 2022-04-09
| SUM-SS-MPR-1262 | JL_KALANG_TAWANGREJO | HTI | 2022-04-12 |  |  | 149300218199 | 6.6 | 2022-04-08
| SUM-SB-LBB-0836 | AMPEK_ANGKEK_PASIA | HTI | 2022-04-12 |  |  | 132260127223 | 6.6 | 2022-04-11
| SUM-SU-AKK-2239 | PERKEBUNAN_PANGKATAN | HTI | 2022-04-12 |  |  | 125150244399 | 6.6 | 2022-04-08
| SUM-SU-TBT-2220 | TAMBANGAN_HULU | HTI | 2022-04-12 |  |  | 121101069934 | 6.6 | 2022-04-08
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUL-ST-LWK-1091 | TOILIBARAT_KAMI_WANGI | HTI | 2022-04-19 |  |  | 319100338641 | 6.6 | 2022-04-09
| JAW-JB-GRT-4265 | PASAR_DESA_CARINGIN | HTI | 2022-04-19 |  |  | 532770754426 | 6.6 | 2022-04-15
| JAW-JB-NPH-4379 | JATIMEKAR | HTI | 2022-04-19 |  |  | 535852226270 | 6.6 | 2022-04-14
| SUL-ST-LWK-1085 | TOILI_TOLISU | HTI | 2022-04-19 |  |  | 319100338625 | 6.6 | 2022-04-15
| JAW-JB-NPH-4380 | NYENANG | HTI | 2022-04-19 |  |  | 535852226558 | 6.6 | 2022-04-12
| SUM-SU-AKK-2254 | PERKEBUNAN_KANOPAN_ULU_SELATAN | HTI | 2022-04-19 |  |  | 125120754062 | 6.6 | 2022-04-14
| SUL-SN-WNS-0980 | PANINCONG_MARIORIAWA | HTI | 2022-04-19 |  |  | 325600253534 | 6.6 | 2022-04-14
| SUM-SU-PYB-2172 | KELURAHAN_MUARA_SOMA | HTI | 2022-04-19 |  |  | 124150469123 | 6.6 | 2022-04-14
| SUM-KR-BSB-0576 | BINTAN_TIMUR_GUNUNG_LENGKUAS | HTI | 2022-04-19 |  |  | 183021818286 | 6.6 | 2022-04-13
| SUL-ST-LWK-1102 | KINTOM_MANYULA | HTI | 2022-04-19 |  |  | 319500346268 | 6.6 | 2022-04-14
| SUM-SS-MPR-1279 | SEMENDAWAI_BARAT_SUKA_NEGERI | HTI | 2022-04-19 |  |  | 149100152593 | 6.6 | 2022-04-12
| SUM-SS-MBL-1210 | MI_ALMUHAJIRIN_SIDOMULYO | HTI | 2022-04-19 |  |  | 147800877441 | 6.6 | 2022-04-18
| SUM-BE-CRP-0189 | CURUP_SELATAN_TELADAN | HTI | 2022-04-19 |  |  | 146102458010 | 6.6 | 2022-04-18
| SUM-SU-AKK-2248 | KUALUH_SELATAN_TANJUNG_PASIR | HTI | 2022-04-19 |  |  | 125120754054 | 6.6 | 2022-04-14
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-BT-RKB-0775 | CIGOONG_UTARA_CIKULUR | EID | 2022-04-19 |  |  | 562101019303 | 6.6 | 2022-04-18
| JAW-BT-RKB-0774 | BANJARSARI_WARUNGGUNUNG | EID | 2022-04-19 |  |  | 562101020031 | 6.6 | 2022-04-18
| JAW-BT-SRG-0057 | CIKANDE_CEMPLANG | EID | 2022-04-19 |  |  | 561400951596 | 6.6 | 2022-04-18
| JAW-BT-TGR-0108 | ABAS_KEMIRI | EID | 2022-04-19 |  |  | 566602157918 | 6.6 | 2022-04-13
| JAW-JK-GGP-0459 | KEBON_JAHE_KAPUK | EID | 2022-04-19 |  |  | 542103991826 | 10.6 | 2022-04-18
| JAW-JB-CKR-0118 | BABAKAN_BEKASI | EID | 2022-04-19 |  |  | 537422013604 | 10.6 | 2022-04-18
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUM-KR-BTM-0605 | KARAS | HTI | 2022-04-20 |  |  | 183090454902 | 6.6 | 2022-01-03
| SUM-LA-TWG-1029 | PAGAR_DEWA_SUKA_MULYA | HTI | 2022-04-20 |  |  | 173400203925 | 6.6 | 2022-04-19
| SUM-LA-KLA-1134 | SINAR_PALEMBANG | HTI | 2022-04-20 |  |  | 171310604209 | 6.6 | 2022-04-19
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JB-SPA-4229 | SINGKIR | HTI | 2022-04-21 |  |  | 532652455645 | 6.6 | 2022-04-06
| JAW-JB-NPH-4386 | PARONGPONG - RELOC | HTI | 2022-04-21 |  |  | 535891356089 | 6.6 | 2022-04-11
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-BKL-4329 | BLEGA_BATES | HTI | 2022-04-25 |  |  | 517600665934 | 6.6 | 2022-04-05
| JAW-JI-BKL-4324 | BLEGA_KAMPAO | HTI | 2022-04-25 |  |  | 517600665900 | 6.6 | 2022-04-11
| JAW-JI-BKL-4323 | KARANG_GAYAM_BLEGA | HTI | 2022-04-25 |  |  | 517600665854 | 6.6 | 2022-04-05
| JAW-JI-BKL-4322 | BLEGA_KARANG_GAYAM | HTI | 2022-04-25 |  |  | 517600665862 | 6.6 | 2022-04-05
| JAW-JI-BKL-4331 | MODUNG_ALAS_KOKON | HTI | 2022-04-25 |  |  | 517401350389 | 6.6 | 2022-04-05
| KAL-KT-PPS-0703 | GOHONG_KAHAYAN_HILIR | HTI | 2022-04-25 |  |  | 225100195277 | 6.6 | 2022-04-14
| SUM-SS-KAG-1250 | MUKTISARI | HTI | 2022-04-25 |  |  | 149300221239 | 6.6 | 2022-04-21
| SUM-LA-TWG-1029 | PAGAR_DEWA_SUKA_MULYA | HTI | 2022-04-25 |  |  | 173400203925 | 6.6 | 2022-04-19
| SUM-LA-BBU-0878 | BLAMBANGAN_UMPU_GISTANG | HTI | 2022-04-25 |  |  | 173700729262 | 6.6 | 2022-04-22
| SUM-SS-SKY-1242 | NGULAK_I | HTI | 2022-04-25 |  |  | 142200517499 | 6.6 | 2022-04-20
| SUM-SU-PMS-2248 | DOLOK_PARRIASAN | HTI | 2022-04-25 |  |  | 121130193690 | 6.6 | 2022-04-20
| SUM-LA-KLA-1134 | SINAR_PALEMBANG | HTI | 2022-04-25 |  |  | 171310604209 | 6.6 | 2022-04-19
| SUM-LA-KTB-1148 | MUARA_SUNGKAI_SUMBER_AGUNG | HTI | 2022-04-25 |  |  | 173001529010 | 6.6 | 2022-04-20
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JI-TLG-4245 | KAUMAN KALANGBRET | HTI | 2022-04-25 |  |  | 514032193553 | 6.6 | 2021-10-20
| SUM-SU-LBP-2249 | SAMBIREJO_TIMUR_MEDAN_BATANGKUIS | HTI | 2022-04-25 |  |  | 128050013157 | 6.6 | 2021-10-31
| SUM-SU-LBP-2291 | BATANG_KUIS_BAKARAN_BATU | HTI | 2022-04-25 |  |  | 128010141005 | 6.6 | 2021-11-04
| SUM-SU-LBP-2252 | PERDAMEAN_PURWO | HTI | 2022-04-25 |  |  | 126120950900 | 6.6 | 2021-11-13
| SUM-SU-STB-2215 | SELESAI_PEKAN_SELESAI | HTI | 2022-04-25 |  |  | 122030625513 | 6.6 | 2021-11-29
| SUM-SS-KAG-1256 | BENAWA | HTI | 2022-04-25 |  |  | 149100150095 | 6.6 | 2022-03-27
| SUM-SU-STB-2225 | HINAI_KANAN | HTI | 2022-04-25 |  |  | 122150561374 | 6.6 | 2022-03-31
| SUM-SU-STB-2229 | HINAI_KIRI | HTI | 2022-04-25 |  |  | 122140915926 | 6.6 | 2022-03-31
| SUM-SU-SDK-2227 | SITINJO_I | HTI | 2022-04-25 |  |  | 129010129372 | 6.6 | 2022-03-31
| SUM-SU-SDK-2228 | PAGAGAN_JULU_II | HTI | 2022-04-25 |  |  | 129010129364 | 6.6 | 2022-03-31
| SUM-SU-MDN-2231 | MEDAN_LABUHAN_BESAR | HTI | 2022-04-25 |  |  | 128040132677 | 6.6 | 2022-03-31
| SUM-SS-MPR-1271 | BELITANG_MULYA_SRI_MULYO | HTI | 2022-04-25 |  |  | 149300217425 | 6.6 | 2022-04-02
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-WNG-2766 | JARANMATI_BULUSARI | HTI | 2022-04-25 |  |  | MG |  | 2022-04-06
| JAW-JT-PTI-1430 | KEBEN_TAMBAKROMO | HTI | 2022-04-25 |  |  | MG |  | 2022-04-06
| JAW-JT-JPA-0714 | MINDAHAN_KIDUL_JEPARA | HTI | 2022-04-25 |  |  | 520022109564 | 11 | 2022-04-06
| JAW-YO-SMN-0076 | PRAMBANAN_SLEMAN | HTI | 2022-04-25 |  |  | 521013005670 | 11 | 2022-04-14
| JAW-JT-BYL-0261 | MANGGUNG_BOYOLALI | HTI | 2022-04-25 |  |  | 520551342430 | 11 | 2022-04-11
| JAW-JT-SMG-0626 | GONDANG_TEMBALANG | HTI | 2022-04-25 |  |  | 523041113381 | 11 | 2022-04-05
| JAW-JT-CLP-0563 | JALAN_JATI_CILACAP | HTI | 2022-04-25 |  |  | 525011421993 | 11 | 2022-04-08
| JAW-YO-BTL-0140 | TRIMULYO_BANTUL | HTI | 2022-04-25 |  |  | 521032604426 | 11 | 2022-04-08
| JAW-JT-KRG-2152 | PABLENGAN_KARANGANYAR | HTI | 2022-04-25 |  |  | 526550154448 | 11 | 2022-03-23
| JAW-JT-KBM-0636 | TUGU_KEBUMEN | HTI | 2022-04-25 |  |  | 525031643459 | 11 | 2022-04-25
| JAW-JT-SKT-2142 | KALINGGA KADIPIRO | HTI | 2022-04-25 |  |  | 520521518979 | 7.7 | 2022-03-02
| JAW-JT-SKH-1900 | CEMANI SUKOHARJO | HTI | 2022-04-25 |  |  | 520512082411 | 7.7 | 2022-02-24
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-BT-PDG-0622 | MAKUI_BANYUMEKAR | EID | 2022-04-25 |  |  | 562400512324 | 6.6 | 2022-04-22
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| SUL-SN-PKJ-1595 | BULU_TELLUE_TONDONG_TALLASA | HTI | 2022-04-26 |  |  | 320400193178 | 6.6 | 2022-04-25
| SUL-ST-LWK-1073 | MOILONG | HTI | 2022-04-26 |  |  | 319100339182 | 6.6 | 2022-04-25
| SUL-SN-SDR-1282 | KELURAHAN_RIJANG_PITU_MARITENGNGAE | HTI | 2022-04-26 |  |  | 325500312145 | 6.6 | 2022-04-25
| JAW-JB-SOR-4420 | NEGLAS_SARI_PINGGIRSARI | HTI | 2022-04-26 |  |  | 535342252845 | 6.6 | 2022-04-26
| SUL-SN-SDR-1284 | KELURAHAN_BILOKKA_PANCA_LAUTAN | HTI | 2022-04-26 |  |  | 325500312812 | 6.6 | 2022-04-25
| SUL-SN-SDR-1283 | WANIO_TIMORENG_PANCA_LAUTAN | HTI | 2022-04-26 |  |  | 325500312463 | 6.6 | 2022-04-25
| SUM-LA-BBU-0869 | SAPTO_RENGGO | HTI | 2022-04-26 |  |  | 173700729213 | 6.6 | 2022-04-26
| SUM-SS-BTA-1081 | SINAR_PENINJAUAN_SRI_MULYA | HTI | 2022-04-26 |  |  | 147500959272 | 6.6 | 2022-04-25
| SUM-LA-GDT-1131 | GEDONG_TATAAN_WIYONO | HTI | 2022-04-26 |  |  | 172501123469 | 6.6 | 2022-04-25
| SUM-LA-BBU-0876 | TALANG_MANGGA | HTI | 2022-04-26 |  |  | 173700729205 | 6.6 | 2022-04-26
| SUL-ST-LWK-1105 | LUWUK_UTARA_BUNGA | HTI | 2022-04-26 |  |  | 319500346250 | 6.6 | 2022-04-25
| SUM-SS-LHT-1236 | SIRAH_PULAU | HTI | 2022-04-26 |  |  | 147000760955 | 6.6 | 2022-04-26
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-BT-PDG-0614 | TANJUNG_LESUNG_PANDEGLANG | EID | 2022-04-26 |  |  | 562400513574 | 10.6 | 2022-04-25
| JAW-BT-TGR-0110 | PETE_TEGAL_SARI | EID | 2022-04-26 |  |  | 566402075773 | 6.6 | 2022-04-25
| JAW-BT-TGR-0109 | JEUNGJING_CISOKA | EID | 2022-04-26 |  |  | 566402074692 | 6.6 | 2022-04-25
| Site ID XL | Site Name XL | Tech. Partner | PMIS Request Date | HO PLN Date | PMIS Update Date (filled by FTK) | ID PELANGGAN PLN | DAYA (KVA) | RFI DATE
| JAW-JT-JPA-0714 | MINDAHAN_KIDUL_JEPARA | NOKIA | 2022-04-26 |  |  | 520022109564 | 11 | 2022-04-06
| JAW-YO-SMN-0076 | PRAMBANAN_SLEMAN | NOKIA | 2022-04-26 |  |  | 521013005670 | 11 | 2022-04-14
| JAW-JT-BYL-0261 | MANGGUNG_BOYOLALI | NOKIA | 2022-04-26 |  |  | 520551342430 | 11 | 2022-04-11
| JAW-JT-SMG-0626 | GONDANG_TEMBALANG | NOKIA | 2022-04-26 |  |  | 523041113381 | 11 | 2022-04-05
| JAW-JT-CLP-0563 | JALAN_JATI_CILACAP | NOKIA | 2022-04-26 |  |  | 525011421993 | 11 | 2022-04-08
| JAW-YO-BTL-0140 | TRIMULYO_BANTUL | NOKIA | 2022-04-26 |  |  | 521032604426 | 11 | 2022-04-08
| JAW-JT-KRG-2152 | PABLENGAN_KARANGANYAR | NOKIA | 2022-04-26 |  |  | 526550154448 | 11 | 2022-03-23
| JAW-JT-SKT-2142 | KALINGGA KADIPIRO | NOKIA | 2022-04-26 |  |  | 520521518979 | 7.7 | 2022-03-02
| JAW-JT-SKH-1900 | CEMANI SUKOHARJO | NOKIA | 2022-04-26 |  |  | 520512082411 | 7.7 | 2022-02-24
| JAW-JT-CLP-0567 | PURWASARI_WANAREJA | NOKIA | 2022-04-26 |  |  | 525061585123 | 11 | 2022-04-25
| JAW-JT-KBM-0636 | TUGU_KEBUMEN | NOKIA | 2022-04-26 |  |  | 525031643459 | 11 | 2022-04-25

## Pivot New SPK B2S 7 Mar 2022
SPK DATE | 2022-03-07
Row Labels | Count of SITE ID XL
BALINUSRA | 7
JABAR | 16
JABODETABEK | 24
JATENG | 7
JATIM | 11
KALIMANTAN | 5
SUMBAGSEL | 3
SUMBAGTENG | 8
SUMBAGUT | 9
Grand Total | 90

## Sheet14
No | SONumber | Site ID | ID Opr | Site Name | Tenant Type | Customer ID | Status | RFI Date | STO DATE | RFI COMMITMENT
1 | 30734680031 | 130219104 | JAW-BT-RKB-0591 | CILEBANG | COLO | XL | SRFI | 2022-03-02 | #REF! | 2022-04-08
2 | 30734640031 | 130214104 | JAW-BT-RKB-0587 | CILAYANG | COLO | XL | SRFI | 2022-03-01 | #REF! | 2022-04-07
3 | 30735530031 | 1267522007 | JAW-JB-CKR-0118 | IBS KP BABAKAN BEKASI | COLO | XL | SRFI | 2022-02-28 | NY STO | 2022-04-30 | tanggal STO dibuka = tanggal SPK
4 | 30735510031 | 120651104 | JAW-JB-SBM-2450 | GUNUNG PADANG | COLO | XL | SRFI | 2022-02-27 | #REF! | 2022-04-08
5 | 30735490031 | 122282109 | JAW-JB-SBM-2452 | JALAN KERAMAT SUKALARANG | COLO | XL | SRFI | 2022-02-27 | #REF! | 2022-04-08
6 | 30734620031 | 1321462010 | JAW-BT-TGR-0099 | IBS KRAGILAN | COLO | XL | SRFI | 2022-02-27 | #REF! | 2022-04-07
7 | 30735150031 | 131497126 | JAW-BT-PDG-0617 | JALANPATIADMT | COLO | XL | SRFI | 2022-02-23 | #REF! | 2022-04-08
8 | 30734000031 | 131404109 | JAW-BT-TGR-0119 | CIKUYASOLEAR | COLO | XL | SRFI | 2022-02-23 | #REF! | 2022-04-07
9 | 30735430031 | 125279126 | JAW-JB-KWG-1101 | ANGGADITA KLARI | COLO | XL | SRFI | 2022-02-21 | #REF! | 2022-04-08
10 | 30735500031 | 123234109 | JAW-JB-CKR-0104 | BABELAN KOTA 2 | COLO | XL | SRFI | 2022-02-21 | #REF! | 2022-04-08
11 | 30730850031 | T000916 | JAW-JB-DPK-0496 | HJ SYUKUR LENTENG AGUNG | COLO | XL | SRFI | 2022-02-21 | #REF!
12 | 30735370031 | 130238104 | JAW-BT-SRG-0051 | BATUKUDA | COLO | XL | SRFI | 2022-02-21 | #REF! | 2022-04-08
13 | 30734690031 | 120836104 | JAW-BT-SRG-0058 | CURUG AGUNG | COLO | XL | SRFI | 2022-02-16 | #REF! | 2022-04-08
Formulas:
RFI COMMITMENT = VLOOKUP([ID Opr],DATA!Q4:AJ1674,20,0)

## Pico & P2M (hidden)
2
PROJECT | X | STATUS | Site ID XL | Site Name XL | Cand | Tech. Partner | Region | Propinsi | Kabupaten | SPK Type | SPK No. | SPK date. | SPK AGING | SPK AGING GROUP | Tower Type | Tower Height | SSR Longitude | SSR Latitude | Proposed RF Height | RF Azimuth | Commitment | CME | RFI Plan (sesuai MLA) (D) | RFI Plan (sesuai MLA) (W) | SOFT RFI Plan XL (D) | SOFT RFI Plan XL (W) | RFI Plan XL (D) | RFI Plan (W) | REVISI RFI Plan XL (D) | REVISI RFI Plan (W) | CURRENT PROGRESS | PROGRESS SUMMARY | PROGRESS GROUP | PROBLEM CLASS | PROGRESS DETAIL | Unlock (OA) Date | SOFT RFI date (D) | RFI date (D) | SOFT RFI Notification Email | RFI Notification Email | Update TRANSMISSION TRANSPORT | SPK FO No. | Status SPK FO | Progress FO (12-01-2021) | Sonumb | Site ID TBG | Site Name TBG | SITE TYPE | STIP CATEGORY | OPERATOR | Company | STIP date | REGIONAL TBG | Scheme | Site Address | Residence | Province | PSB req date | Propose Plan RFI | MOS Plan | SK PSB STATUS | SK PSB PLN Number | PSB received date | Remarks
| x | ACTIVE | NUS-NT-KPG-0270 | Transmart Kupang |  | HTI | EAST | Nusa Tenggara Timur | Kupang | Pico & P2M | 6616748 | 2021-01-26 | 457 | 1 - 30 days | Existing |  | 0°0.0.0'null | 0°0.0.0'N | 0 | 90/180/290 | No Commitment | By Tower Provider | 2021-06-24 | W26-2021 | 2021-06-24 | W26-2021 | 2021-03-06 | W10-2021 | 2021-03-06 | W10-2021 | 38.RFI | 21.RFI | 07.RFI | Currently no issue | 08.03.21 : RFIN sent 04.03.21 : RFI, RFI notification email waiting status STO LMS 18.02.21 : plan MOS 21 Feb 11.02.21 : CME preparation 26.01.21 : SPK Pico P2M release |  |  |  |  | 2021-03-04 | FO | Need Confirmation | Need Confirmation |  | 30619620031 | 1909641003 | TRANSMART_KUPANG | IBS/DAS | STIP 1 | XL | SKP | 2021-01-28 | BALINUSRA
| x | ACTIVE | SUM-SS-PLG-1227 | Transmart Palembang | existing | HTI | WEST | Sumatera Selatan | Kota Palembang | Pico & P2M | 6616747 | 2021-01-26 | 457 | 1 - 30 days | Existing |  | 0°0.0.0'null | 0°0.0.0'N | 0 | 90/180/290 | No Commitment | By Tower Provider | 2021-06-24 | W26-2021 | 2021-06-24 | W26-2021 | 2021-02-28 | W10-2021 | 2021-02-28 | W10-2021 | 38.RFI | 21.RFI | 07.RFI | Currently no issue | 04.03.21 : RFIN sent 25.02.21 : material onsite, CME start 18.02.21 : plan MOS hari ini 08.02.21 : CME preparation 26.01.21 : SPK Pico P2M release |  |  |  |  | 2021-02-26 | FO | Need Confirmation | Need Confirmation |  | 30619660031 | 071327126 | TRANSMART PALEMBANG | COLO IBS | STIP 1 | XL | SKP | 2021-01-28 | SUMBAGSEL
03.SITAC
Formulas:
SPK AGING = TODAY()-[SPK date.]
RFI Plan (sesuai MLA) (D) = [SPK date.]+149
RFI Plan (sesuai MLA) (W) = "W"&WEEKNUM([RFI Plan (sesuai MLA) (D)]) &"-"&YEAR([RFI Plan (sesuai MLA) (D)])
SOFT RFI Plan XL (W) = "W"&WEEKNUM([SOFT RFI Plan XL (D)]) &"-"&YEAR([SOFT RFI Plan XL (D)])
RFI Plan (W) = "W"&WEEKNUM([RFI Plan XL (D)]) &"-"&YEAR([RFI Plan XL (D)])
REVISI RFI Plan (W) = "W"&WEEKNUM([REVISI RFI Plan XL (D)]) &"-"&YEAR([REVISI RFI Plan XL (D)])

## Sheet9 (hidden)
PROJECT NAME | XL REGION | HUAWEI REGION | CURRENT SITE ID NE | CURRENT SITE NAME NE | SOW | CME BY | ACTUAL RFI (D) | ID PELANGGAN PLN | PERMANENT/MULTIGUNA
JEDI 2020 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-BLT-1917 | KEPANJEN_KIDUL_SENTUL | B2S | TBG | 2021-03-10 | MULTIGUNA | MULTIGUNA
BLITZKRIEG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-PNG-4300 | SAMPUNG_TULUNG | COLO | TBG | 2021-10-16 | MULTIGUNA | MULTIGUNA
BLITZKRIEG 2021 [NEW] | CENTRAL | WEST JAVA | JAW-JB-MJL-4124 | MALAUSMA_BANYUSARI | B2S | TBG | 2021-10-29 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | WEST | SOUTH SUMATERA | JAW-JI-KNR-4282 | SELOPURO SELOPURO | COLO | TBG | 2021-10-21 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-BDW-3619 | JAMBESARI DARUS SHOLAH JAMBESARI | COLO | TBG | 2021-10-19 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-BDW-3622 | TAMANAN WONOSUKO | COLO | TBG | 2021-10-19 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-BDW-3623 | MAESAN TANAH WULAN | COLO | TBG | 2021-10-25 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-JMR-5127 | UMBULSARI SUKORENO | COLO | TBG | 2021-10-15 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-JBG-4167 | TEMBELANG KEDUNGLOSARI | COLO | TBG | 2021-10-25 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-JBG-4175 | TEMBELANG PULO GEDANG | COLO | TBG | 2021-10-18 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-JBG-4177 | JOMBANG SUMBERJO | COLO | TBG | 2021-10-16 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-KDR-4322 | PLEMAHAN TEGOWANGI | COLO | TBG | 2021-10-19 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-KPN-4414 | TAJINAN PURWOSEKAR | COLO | TBG | 2021-10-19 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-NGW-3667 | WIDODAREN KEDUNGGUDEL | COLO | TBG | 2021-10-19 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-PMK-4237 | BATUMARMAR PANGERREMAN | COLO | TBG | 2021-10-25 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-PNG-4290 | BABADAN LEMBAH | COLO | TBG | 2021-10-22 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-PNG-4295 | SUKOREJO BANGUNREJO | COLO | TBG | 2021-10-19 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-PNG-4298 | SAMBIT BANCANGAN | COLO | TBG | 2021-10-19 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | CENTRAL | WEST JAVA | JAW-JI-SPG-4230 | KETAPANG PANCOR | COLO | TBG | 2021-10-25 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-SPG-4231 | BANYUATES TEROSAN | COLO | TBG | 2021-10-25 | MULTGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-SPG-4232 | KETAPANG PAOPALELAOK | COLO | TBG | 2021-10-25 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-SPG-4233 | SOKOBANAH BIRA TIMUR | COLO | TBG | 2021-10-19 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-SDA-4316 | TANGGULANGIN KALITENGAH | COLO | TBG | 2021-10-25 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-TRK-4263 | TRENGGALEK DAWUHAN | COLO | TBG | 2021-10-15 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-TRK-4264 | POGALAN GEMBLEB | COLO | TBG | 2021-10-25 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-TBN-4070 | BANCAR BANCAR | COLO | TBG | 2021-10-18 | MULTIGUNA | MULTIGUNA
RORO JONGRANG 2021 [NEW] | EAST | EAST & BALI LOMBOK | JAW-JI-TLG-4245 | KAUMAN KALANGBRET | COLO | TBG | 2021-10-19 | MULTIGUNA | MULTIGUNA

## Sheet10 (hidden)
DU ID | SITE NAME (PMIS) | REGION | PROJECT GROUP | REMARK | Nama Site TBG | STIP | Status | RFI Date
JAW-JI-SPG-4159_WN0 | KEDUNGDUNG_KOMIS | EJBN | 2020 COVERAGE | PLN ISSUE | #N/A | #N/A | #N/A | #N/A
BAL-BA-DPR-1490_WN0 | DENPASAR_SELATAN_PEMOGAN | EJBN | 2020 COVERAGE | SPK DROP NE SITE, FE RFS BY FIBERSTAR | #N/A | #N/A | #N/A | #N/A
JAW-JI-KNR-4256_WN0 | SANANKULON_SUMBEREJO | EJBN | 2020 COVERAGE | SPK TBG ISSUE | 3G_BENDO | STIP 1 | RFI | 2020-02-10
JAW-JI-BYW-4121_WN0 | GENTENG_GENTENG_KULON | EJBN | 2020 COVERAGE | SPK TBG ISSUE | TEGALARUM | STIP 1 | RFI | 2021-01-27
JAW-JI-SIT-3801_WN0 | BANYUPUTIH_SUMBEREJO | EJBN | 2020 COVERAGE | SPK TBG ISSUE | BANYUPUTIH_SUMBEREJO | STIP 1 | RFI | 2020-04-27
JAW-JI-SIT-3803_WN0 | KAPONGAN_KESAMBIPARAK | EJBN | 2020 COVERAGE | SPK TBG ISSUE | KAPONGAN_KESAMBIRAMPAK | STIP 1 | RFI | 2020-06-29
JAW-JI-PCT-4186_WN0 | KEBONAGUNG_MANTREN | EJBN | 2020 COVERAGE | SPK TBG ISSUE | KEBONAGUNG_MANTREN | STIP 1 | RFI | 2020-04-30
JAW-JI-NJK-3913_WN0 | REJOSO_MUNGKUNG | EJBN | 2020 COVERAGE | SPK TBG ISSUE | #N/A | #N/A | #N/A | #N/A
BAL-BA-DPR-1510_WN0 | SANUR_UTARA_ROAD_RELOCATION | EJBN | 2020 DISMANTLE-RELOC JEDI | WAITING PERMIT SIMARU | #N/A | #N/A | #N/A | #N/A
JAW-JI-JBG-4135_WN0 | MOJOWARNO_MOJOWARNO | EJBN | 2020 COVERAGE | WAITING PLN ISSUE | #N/A | #N/A | #N/A | #N/A
_WN0

## Sheet8 (hidden)
21 | <30
13 | <40<32
11 | <30<392
1 | >21
12 | #N/A